## KC-AF
KC-AF Funded SPs
Phase_Cycle | REGION |  | PROVINCE |  | MUNICIPALITY |  | BARANGAY |  | SUB-PROJECT NAME | NoOfBgys | Major SP Category | SP Sub-Category | Physical_Target | Phy_Target_Unit | Kalahi_Amount | LCC_Amount | Total_Amount | Date_Started | Date_of_Completion | KC_Fund_Released | Remarks | Tranche | SchoolType | Status | PlannedDate_Completion | PamanaGrant
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Alunogan | 144405001 | Improvement of Alunogan Water System | 1 | Basic Social Services | Water System | 1 | system | 609843.19 | 268435 | 878278.19 | 2011-03-28 | 2011-04-30 | 594130.25 | Level 3 Water System | 2nd |  | Completed | 2011-03-24
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Balangao | 144405002 | Improvement of Balangao-Poblacion Footpath | 1 | Basic Access Infrastructure | Access Trail | 0.966 | kms | 561671.5 | 240825 | 802496.5 | 2011-02-18 | 2011-03-31 | 560713.2 |  | 2nd |  | Completed | 2011-03-30
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Banao | 144405003 | Improvement of Banao Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 524000 | 246000 | 770000 | 2011-02-26 | 2011-07-31 | 501492.5 | Level 3 Water System | 2nd |  | Completed | 2011-04-04
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Butac | 144405005 | Improvement of Opet-Feeg Irrigation Canal (630.00 ln.m) | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | 80 | has. | 639045 | 273967 | 913012 | 2011-02-21 | 2011-04-30 | 638207.53 | 630 ln.m irrigation and 8.5m grouted riprap | 2nd |  | Completed | 2011-04-05
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Maducayan | 144405006 | Concreting of Senarang - Maccotor Footpath | 1 | Basic Access Infrastructure | Access Trail | 1.2 | kms | 483245.75 | 207500.75 | 690746.5 | 2011-02-22 | 2011-05-31 | 467014.58 |  | 2nd |  | Completed | 2011-04-09
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Poblacion | 144405007 | Improvement of Poblacion Water System | 1 | Basic Social Services | Water System | 1 | system | 376444 | 161215 | 537659 | 2011-02-28 | 2011-04-30 | 360767 | Level 3 Water System | 2nd |  | Completed | 2011-03-21
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Pudo | 144405011 | Improvement of Pap-arong Yebyeb Palipar & Mapaganah Water System | 1 | Basic Social Services | Water System | 1 | system | 461827.53 | 189674.24 | 651501.77 | 2011-02-28 | 2011-04-30 | 424102.45 | Level 3 Water System | 2nd |  | Completed | 2011-03-30
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Saliok | 144405008 | Construction of Water System in Sitios Mangnao and Macottor | 1 | Basic Social Services | Water System | 1 | system | 488943.84 | 217484.32 | 706428.16 | 2011-02-26 | 2011-04-30 | 462102.69 | Level 3 Water System | 2nd |  | Completed | 2011-04-07
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Sta. Isabel | 144405009 | Improvement of Nafongfongwah, Balacbac, Galanagan Water Works | 1 | Basic Social Services | Water System | 1 | system | 523185 | 224260 | 747445 | 2011-02-23 | 2011-04-30 | 504741.55 | Level 3 Water System | 2nd |  | Completed | 2011-03-20
M1 | CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Tonglayan | 144405010 | Construction and Concreting of Tonglayan-Daulan Footpath | 1 | Basic Access Infrastructure | Access Trail | 1.3 | kms | 658000 | 337000 | 995000 | 2011-02-28 | 2011-05-31 | 637894.11 |  | 2nd |  | Completed | 2011-04-29
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Anonat | 144406001 | Improvement of Dannal FMR | 1 | Basic Access Infrastructure | Road | 0.17 | kms | 377770.38 | 46395.16 | 424165.54 | 2011-02-20 | 2011-06-30 | 376054.46 |  | 2nd |  | Completed | 2011-04-13
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bacarri | 144406002 | Improvement of Bue-Wala FMR | 1 | Basic Access Infrastructure | Road | 0.24 | kms | 868712.97 | 99027.25 | 967740.22 | 2011-04-04 | 2011-06-30 | 794377.4 |  | 2nd |  | Completed | 2011-06-15
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bananao | 144406003 | Construction of Multi-Purpose Pavement at Sitio Asiga | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 480 | sq.m | 437773.39 | 54054.92 | 491828.31 | 2011-03-07 | 2011-05-31 | 436612.57 |  | 2nd |  | Completed | 2011-04-07
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bantay | 144406004 | Improvement of Masablang-Banwang Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.485 | kms | 578379.72 | 61620.28 | 640000 | 2011-03-01 | 2011-04-30 | 462703.78 |  | 1st |  | Completed | 2011-03-17
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bunot | 144406006 | Construction of Tabbad Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 60 | sq.m | 312231.54 | 108174.05 | 420405.59 | 2011-02-25 | 2011-06-30 | 302568.82 |  | 2nd |  | Completed | 2011-03-15
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Buringal | 144406007 | Construction of Catao Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 60 | sq.m | 375617.39 | 47131.35 | 422748.74 | 2011-03-15 | 2011-07-31 | 349392 |  | 2nd |  | Completed | 2011-04-05
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Butigue | 144406005 | Improvement of Pontian FMR | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 471331.77 | 68734.29 | 540066.06 | 2011-03-18 | 2011-07-31 | 377128.69 |  | 1st |  | Completed | 2011-04-25
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Palitod | 144406008 | Construction of Panapa Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 448 | sq.m | 342597.31 | 43827.66 | 386424.97 | 2011-02-24 | 2011-06-30 | 293318.81 | 16X28M=448 sq.m | 2nd |  | Completed | 2011-03-14
M1 | CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Poblacion | 144406009 | Improvement of Banilag-Pakawang Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.7 | kms | 735585.53 | 86814.47 | 822400 | 2011-03-01 | 2011-04-30 | 687694.06 |  | 2nd |  | Completed | 2011-04-16
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Anabel | 144408001 | Improvement of Machummay CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 718000 | 145608 | 863608 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Anabel | 144408001 | Improvement of Machummay CIS (1,430 ln.m Concrete Canal Lining) | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | 6 | has. | 718000 | 145608 | 863608 | 2011-02-21 | 2011-07-31 | 707357.52 |  | 2nd |  | Completed | 2011-05-30
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Bekigan | 144408004 | Improvement of Bekigan Foothpath | 1 | Basic Access Infrastructure | Access Trail |  | kms | 342356.88 | 75753.12 | 418110 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Bekigan | 144408004 | Improvement of Bekigan Footpath | 1 | Basic Access Infrastructure | Access Trail | 0.22 | kms | 342356.88 | 75753.12 | 418110 | 2011-03-28 | 2011-06-30 | 339092.46 |  | 2nd |  | Completed | 2011-05-30
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Belwang | 144408002 | Construction of Belwang Water System | 1 | Basic Social Services | Water System | 1 | system | 468000 | 244000 | 712000 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Belwang | 144408002 | Construction of Belwang Water System | 1 | Basic Social Services | Water System | 1 | system | 468000 | 244000 | 712000 | 2011-04-02 | 2011-06-30 | 374400 | Level 3 Water System | 1st |  | Completed | 2011-05-30
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Demang | 144408008 | Improvement of Demang Footpath | 1 | Basic Access Infrastructure | Access Trail |  | kms | 458892.4 | 98657.6 | 557550 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Demang | 144408008 | Improvement of Demang Footpath | 1 | Basic Access Infrastructure | Access Trail | 0.76 | kms | 458892.4 | 98657.6 | 557550 | 2011-02-21 | 2011-06-30 | 442259.81 |  | 2nd |  | Completed | 2011-04-30
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Poblacion | 144408005 | Improvement of Lidem Road | 1 | Basic Access Infrastructure | Road |  | kms | 817098.67 | 295201.33 | 1112300 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Poblacion | 144408005 | Improvement of Lidem Road | 1 | Basic Access Infrastructure | Road | 0.19 | kms | 817098.67 | 295201.33 | 1112300 | 2011-03-23 | 2011-05-31 | 782394.64 |  | 2nd |  | Completed | 2011-05-30
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Sacasacan | 144408006 | Improvement of Makamkamamar Road | 1 | Basic Access Infrastructure | Road |  | kms | 565038.76 | 113461.24 | 678500 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Sacasacan | 144408006 | Improvement of Makamkamamar Road | 1 | Basic Access Infrastructure | Road | 0.165 | kms | 565038.76 | 113461.24 | 678500 | 2011-03-13 | 2011-06-30 | 564706.23 |  | 2nd |  | Completed | 2011-04-30
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Saclit | 144408007 | Construction of Kaliptingan Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges |  | ln.m | 603391.32 | 136308.68 | 739700 |  |  | 0 |  |  |  | Not yet started
M1 | CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Saclit | 144408007 | Construction of Kaliptingan Foot Bridge with Railings and Access Pathway | 1 | Basic Access Infrastructure | Foot/Small Bridges | 21 | ln.m | 603391.32 | 136308.68 | 739700 | 2011-03-14 | 2011-07-31 | 565782.1 |  | 2nd |  | Completed | 2011-05-20
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Gosoon | 160204002 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 634779 | 103477 | 738256 | 2012-01-28 | 2012-06-15 | 634779 |  | 3rd |  | Completed | 2012-04-06
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Manoligao | 160204004 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 129.2 | sq. m | 1240923 | 164093 | 1405016 | 2012-02-13 | 2012-06-15 | 1240923 |  | 3rd | HS | Completed | 2012-05-12
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Rojales | 160204010 | Constrcution of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 634779 | 103477 | 738256 | 2012-01-25 | 2012-06-15 | 634779 | No movement as of May 31, 2012 reports | 3rd |  | Completed | 2012-04-03
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | San Agustin | 160204011 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq. m | 1240923 | 164093 | 1405016 | 2012-01-30 | 2012-06-15 | 1240922.99 |  | 3rd | Elem | Completed | 2012-04-28
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Tagcatong | 160204012 | Construction of 1 Unit 1 Classroom Kindergarten Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 248596 | 480358 | 728954 |  |  | 0 |  |  | PS | Not yet started
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | A. Beltran | 160205003 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 529088 | 241257 | 770345 | 2011-04-04 | 2011-06-25 | 515562.73 |  | 2nd |  | Completed | 2011-06-14
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | A. Beltran | 160205003 | Construction of Fish Landing & Mini Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 48 | sq.m | 1016849.17 | 308897.83 | 1325747 | 2012-04-09 |  | 1016849.17 |  | 2nd |  | On-going | 2012-06-27
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Bangonay | 160205002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 501652 | 221552 | 723204 | 2011-03-30 | 2011-06-25 | 475836.31 |  | 2nd |  | Completed | 2011-06-20
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Bunga | 160205004 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq.m | 1220612 | 429483 | 1650095 | 2011-04-20 | 2011-07-25 | 905944 |  | 1st | Elem | Completed | 2011-07-05
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Colorado | 160205005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 501652 | 221552 | 723204 | 2011-04-25 | 2011-06-25 | 501652 |  | 2nd |  | Completed | 2011-06-05
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Cuyago | 160205006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 277709.14 | 501198.11 | 778907.25 | 2012-02-20 | 2012-05-15 | 277709.14 |  | 2nd |  | Completed | 2012-04-29
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magdagooc | 160205008 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 129.2 | sq.m | 1220612 | 412483 | 1633095 | 2011-04-28 | 2011-07-25 | 926505.9 | Not yet started | 2nd | HS | Completed | 2011-07-18
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magdagooc | 160205008 | Construction of 0.3 Km. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1547813.34 | 436930.67 | 1984744.01 | 2012-03-05 | 2012-07-15 | 1547813.34 |  | 2nd |  | Completed | 2012-05-23
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magsaysay | 160205009 | Construction of Evacuation Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 432 | sq.m | 1562001.67 | 469230.33 | 2031232 | 2012-03-12 | 2012-05-15 | 1562001.67 |  | 2nd |  | Completed | 2012-05-30
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Jose | 160205012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 501652 | 221552 | 723204 | 2011-04-11 | 2011-06-25 | 501651.4 |  | 2nd |  | Completed | 2011-06-20
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Pablo | 160205013 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq.m | 1220612 | 427483 | 1648095 | 2011-04-26 | 2011-07-25 | 920064.8 |  | 1st | Elem | Completed | 2011-07-16
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Vicente | 160205014 | Construction of Multi Purpose Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 441 | sq.m | 1208788 | 520053 | 1728841 | 2011-05-09 | 2011-07-25 | 1206994 | Not yet started | 2nd |  | Completed | 2011-07-20
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Vicente | 160205014 | Construction of 0.3 Km. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1547813.34 | 446930.67 | 1994744.01 | 2012-03-05 | 2012-05-15 | 1547813.34 |  | 2nd |  | Completed | 2012-05-23
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Sto. Niño | 160205015 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 595332 | 164436 | 759768 | 2011-04-12 | 2011-06-25 | 476265.6 |  | 1st |  | Completed | 2011-06-23
M1 | Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Sto. Niño | 160205015 | Construction of 0.3 Km. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1547813.34 | 446930.67 | 1994744.01 | 2012-03-05 | 2012-05-15 | 1547813.34 |  | 2nd |  | Completed | 2012-05-23
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Agsabu | 160303031 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 625176 | 172662 | 797838 | 2012-03-04 | 2012-05-17 | 625176 |  | 2nd |  | Completed | 2012-05-17
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Aguinaldo | 160303032 | Construction and Installation of Rice Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 122.29 | sq.m | 981003 | 212748 | 1193751 | 2012-02-28 | 2012-07-15 | 981003 |  | 2nd |  | Completed | 2012-06-01
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Bakingking | 160303002 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 666836 | 157952 | 824788 | 2012-02-11 | 2012-05-05 | 666836 |  | 2nd |  | Completed | 2012-05-05
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Balubo | 160303033 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 635707 | 155384 | 791091 | 2012-02-15 | 2012-05-15 | 635707 |  | 2nd |  | Completed | 2012-04-29
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Bunaguit | 160303004 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 656909 | 156479 | 813388 | 2012-02-21 | 2012-05-15 | 656909 |  | 2nd |  | Completed | 2012-04-02
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Catmonon | 160303006 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1234528 | 274075 | 1508603 | 2012-02-02 | 2012-05-08 | 1234528 |  | 2nd | Elem | Completed | 2012-05-08
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Concordia | 160303007 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 634678 | 155413 | 790091 | 2012-02-17 | 2012-04-15 | 634678 |  | 2nd |  | Completed | 2012-05-02
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Cubo | 160303036 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 629628 | 146522 | 776150 | 2012-02-09 | 2012-04-23 | 629628 |  | 2nd |  | Completed | 2012-04-24
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Duangan | 160303009 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 637175 | 147675 | 784850 | 2012-02-06 | 2012-03-15 | 637175 |  | 2nd |  | Completed | 2012-04-22
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Guibonon | 160303037 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 635459 | 154349 | 789808 | 2012-04-18 | 2012-05-15 | 635459 |  | 2nd |  | Completed | 2012-06-16
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Kalabuan | 160303038 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1137055 | 239699 | 1376754 | 2012-04-25 |  | 909644 |  | 1st | Elem | On-going | 2012-07-28
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Kinamaybay | 160303039 | Construction and Installation of Corn Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 77 | sq.m | 1253827 | 242530 | 1496357 | 2012-04-23 | 2012-07-15 | 1003061.6 |  | 1st |  | Completed | 2012-07-26
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Labao | 160303013 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 629751 | 146579 | 776330 | 2012-02-09 | 2012-04-23 | 629751 |  | 2nd |  | Completed | 2012-04-24
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Maasin | 160303014 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 639150 | 150591 | 789741 | 2012-02-10 | 2012-05-15 | 639150 |  | 2nd |  | Completed | 2012-04-26
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Mac Arthur | 160303010 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 629597 | 149602 | 779199 | 2012-04-24 | 2012-07-15 | 503677.6 |  | 1st |  | Completed | 2012-07-07
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Mahagcot | 160303015 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 629628 | 146522 | 776150 | 2012-02-10 | 2012-04-24 | 629628 |  | 2nd |  | Completed | 2012-04-25
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Maliwanag | 160303041 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1138352 | 239892 | 1378244 | 2012-04-18 |  | 910681.6 |  | 1st | Elem | On-going | 2012-07-21
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Odiong | 160303043 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 622697 | 147954 | 770651 | 2012-04-20 | 2012-06-15 | 590875 |  | 2nd |  | Completed | 2012-07-03
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Piglawigan | 160303044 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 271389 | 516228 | 787617 | 2012-02-09 | 2012-05-15 | 271389 |  | 2nd |  | Completed | 2012-04-24
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Poblacion | 160303019 | Construction of 586 Ln.m Concrete Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 586 | ln.m | 930695 | 221080 | 1151775 | 2012-02-17 | 2012-04-15 | 744556 |  | 1st |  | Completed | 2012-05-23
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Remedios | 160303020 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1244640 | 279848 | 1524488 | 2012-03-07 | 2012-05-15 | 995712 |  | 1st | Elem | Completed | 2012-06-09
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Salug | 160303021 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 668138 | 158163 | 826301 | 2012-03-03 | 2012-05-16 | 668138 |  | 2nd |  | Completed | 2012-05-16
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | San Isidro | 160303045 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 641057 | 148929 | 789986 | 2012-02-04 | 2012-04-18 | 641057 |  | 2nd |  | Completed | 2012-04-19
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | San Jose | 160303046 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 627148 | 148603 | 775751 | 2012-02-11 | 2012-06-15 | 501718.4 |  | 1st |  | Completed | 2012-04-11
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | San Toribio | 160303022 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 640566 | 148850 | 789416 | 2012-02-16 | 2012-06-15 | 640566 |  | 2nd |  | Completed | 2012-05-01
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Sinakungan | 160303048 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 641987 | 147521 | 789508 | 2012-03-24 | 2012-05-15 | 513589.6 |  | 1st |  | Completed | 2012-06-06
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Taganahaw | 160303027 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.22 | sq. m | 1234667 | 274056 | 1508723 | 2012-02-10 | 2012-05-16 | 1234667 |  | 2nd | Elem | Completed | 2012-05-16
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Tagbalili | 160303028 | Construction of 1,500 Ln.m Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.5 | kms | 1314296 | 319525 | 1633821 | 2012-02-20 | 2012-04-15 | 1314295.99 |  | 2nd |  | Completed | 2012-05-20
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Tahina | 160303029 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 637964 | 155907 | 793871 | 2012-02-11 | 2012-04-25 | 637964 |  | 2nd |  | Completed | 2012-04-26
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Tandang Sora | 160303030 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 630297 | 149114 | 779411 | 2012-02-10 | 2012-04-24 | 630297 |  | 2nd |  | Completed | 2012-04-25
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Comota | 160304002 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 645100 | 150236 | 795336 | 2012-02-29 | 2012-05-05 | 645100 |  | 3rd | PS | Completed | 2012-05-04
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Halapitan | 160304003 | Construction of 300 Ln.m Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 443700 | 116501 | 560201 | 2012-02-08 | 2012-03-15 | 443700 |  | 2nd |  | Completed | 2012-04-06
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Kasapa II | 160304010 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 649200 | 147497 | 796697 | 2012-02-14 | 2012-07-15 | 649200 |  | 3rd | PS | Completed | 2012-05-11
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Langasian | 160304004 | Construction of 300 Ln.m Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 443700 | 116501 | 560201 | 2012-02-08 | 2012-03-15 | 443700 |  | 2nd |  | Completed | 2012-04-06
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Lydia | 160304011 | Construction of 200 Ln.m Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 320300 | 91279 | 411579 | 2012-02-07 | 2012-03-15 | 320300 |  | 2nd |  | Completed | 2012-03-30
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Poblacion | 160304006 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1079600 | 229638 | 1309238 | 2012-02-29 | 2012-05-15 | 1079600 |  | 3rd | Elem | Completed | 2012-06-05
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Sagunto | 160304007 | Acquisition of Farm Tractor Equipment w/ Complete Accessories | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 1693000 | 287839 | 1980839 |  |  | 1354400 |  | 1st |  | Not yet started
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | San Patricio | 160304014 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1079600 | 229638 | 1309238 | 2012-02-20 | 2012-05-15 | 1079600 |  | 3rd | Elem | Completed | 2012-06-04
M1 | Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Villa Paz | 160304008 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1079600 | 229638 | 1309238 | 2012-02-29 | 2012-05-15 | 1079600 |  | 3rd | Elem | Completed | 2012-06-04
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Ferdinand | 168505003 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq.m | 1402028 | 134906 | 1536934 | 2011-04-05 | 2011-07-25 | 1352750.5 |  | 2nd | Elem | Completed | 2011-07-08
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Kasapa | 160305013 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 779016 | 103586 | 882602 | 2011-06-01 | 2011-08-15 | 699885.95 | Not yet started | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Kauswagan | 160305015 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 557739 | 325223 | 882962 | 2011-07-04 | 2011-08-15 | 501965.1 | Additional SP with Special MIBF (not yet started) | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Mabuhay | 160301007 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 779376 | 103586 | 882962 | 2011-04-12 | 2011-07-25 | 779376 |  | 2nd |  | Completed | 2011-07-09
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Magaud | 160305003 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 129.2 | sq.m | 1402099 | 134906 | 1537005 | 2011-04-05 | 2011-07-25 | 1353266.45 |  | 2nd | HS | Completed | 2011-07-08
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Maitom |  | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 779376 | 103586 | 882962 | 2011-04-08 | 2011-07-25 | 779376 |  | 2nd |  | Completed | 2011-07-06
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Nueva Gracia | 160305004 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 129.2 | sq.m | 1405961 | 134906 | 1540867 | 2011-04-08 | 2011-07-25 | 1353266.45 |  | 2nd | HS | Completed | 2011-07-12
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Loreto | 160305 | Sto. Tomas | 160305010 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq.m | 1394405 | 134906 | 1529311 | 2011-04-04 | 2011-07-25 | 1353266.45 |  | 2nd | Elem | Completed | 2011-07-07
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Cecilia | 160309010 | Installation of 12 Units Rain Water Harvesting | 1 | Basic Social Services | Water System | 1 | system | 221640 | 553822 | 775462 | 2012-04-08 | 2012-06-15 | 220390 |  | 2nd |  | Completed | 2012-06-03
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Coalicion | 160309003 | Rehabilitation of 1 Km. Manampaling Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 1855000 | 266582 | 2121582 | 2012-06-05 |  | 1484000 |  | 1st |  | On-going | 2012-08-14
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Culi | 160309004 | Installation of 10 Units Jetmatic Pump | 1 | Basic Social Services | Water System | 1 | system | 367900 | 87919 | 455819 | 2012-02-13 | 2012-06-15 | 354711.58 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-04-12
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Don Alejandro | 160309012 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 163.35 | sq. m | 1267000 | 219167 | 1486167 | 2012-02-21 | 2012-06-15 | 1209899.55 |  | 3rd | Elem | Completed | 2012-05-20
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Don Pedro | 160309013 | Construction of Gravity Driven Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 850000 | 162040 | 1012040 | 2012-03-05 | 2012-05-03 | 808554.02 | 1,820 ln.m | 3rd |  | Completed | 2012-05-03
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Doña Flavia | 160309014 | Improvement of 0.300 Km. Purok 2 to Purok 4 Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 815000 | 140470 | 955470 | 2012-02-28 | 2012-07-15 | 804336.6 | No movement as of May 31, 2012 reports | 3rd |  | Completed | 2012-04-09
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Mahapag | 160309016 | Construction of 550 Ln.m Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.55 | kms | 707500 | 104377 | 811877 | 2012-03-17 | 2012-06-15 | 680578.1 |  | 3rd |  | Completed | 2012-04-19
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Mahayahay | 160309017 | Construction of Pump Driven Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 1113000 | 203498 | 1316498 | 2012-03-13 | 2012-06-15 | 1075408.16 | 1,190 ln.m | 2nd |  | Completed | 2012-05-01
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Muritula | 160309018 | Construction of 400 Ln.m Concrete Pathways | 1 | Basic Access Infrastructure | Access Trail | 0.4 | kms | 549500 | 84959 | 634459 | 2012-02-29 | 2012-05-15 | 524797.1 |  | 3rd |  | Completed | 2012-03-29
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | San Pedro | 160309021 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1287200 | 211297 | 1498497 | 2012-02-23 | 2012-06-15 | 1228982.99 | No movement as of May 31, 2012 reports | 3rd | Elem | Completed | 2012-05-22
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Santiago | 160309023 | Construction of 300 Ln.m Concrete Pavement Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 967800 | 151740 | 1119540 | 2012-03-18 | 2012-06-15 | 967800 |  | 3rd |  | Completed | 2012-05-16
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Sta. Ines | 160309007 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1258460 | 228398.4 | 1486858.4 | 2012-02-27 | 2012-06-15 | 1203196 |  | 3rd | Elem | Completed | 2012-05-26
M1 | Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Sta. Rita | 160309022 | Construction of 75 Ln.m Concrete Stairway | 1 | Basic Access Infrastructure | Access Trail | 0.075 | kms | 1240000 | 203380 | 1443380 | 2012-04-02 | 2012-06-15 | 1211452.11 |  | 3rd |  | Completed | 2012-06-15
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Anitap | 160313013 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 602589 | 178805 | 781394 | 2012-02-01 | 2012-05-03 | 602589 |  | 3rd |  | Completed | 2012-05-03
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Binongan | 160313001 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 591491 | 185092 | 776583 | 2012-02-13 | 2012-05-21 | 558598 |  | 3rd |  | Completed | 2012-05-21
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Candiis | 160313016 | Construction of 109 Units Individual Rain Water Harvesting | 1 | Basic Social Services | Water System | 1 | system | 1428293 | 368241 | 1796534 | 2012-02-18 | 2012-05-15 | 1347536 |  | 2nd |  | Completed | 2012-05-26
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Katipunan | 160313017 | Construction of 175 Units Individual Rain Water Harvesting | 1 | Basic Social Services | Water System | 1 | system | 2237579 | 563546 | 2801125 | 2012-02-18 | 2012-07-15 | 1790063 | No movement as of May 31, 2012 reports | 1st |  | Completed | 2012-05-26
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Sawagan | 160313019 | Rehabilitation of 1.64 Km. Sitio-Payle-Sawagan FMR | 1 | Basic Access Infrastructure | Road | 1.64 | kms | 2021829 | 476610 | 2498439 | 2012-04-17 |  | 1617463 |  | 1st |  | On-going | 2012-08-15
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Sisimon | 160313020 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 598865 | 178246 | 777111 | 2012-01-13 | 2012-05-03 | 566146 |  | 3rd |  | Completed | 2012-05-03
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Sta. Cruz | 160313018 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 602071 | 186799 | 788870 | 2012-02-16 | 2012-05-04 | 602071 |  | 3rd |  | Completed | 2012-05-04
M1 | Caraga | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Sta. Emelia | 160313011 | Construction of 1 Box Culvert 2 Channel | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6.9 | ln.m | 917283 | 933119 | 1850402 | 2012-04-25 |  | 825554.7 |  | 2nd |  | On-going | 2012-06-14
M1 | Caraga | 16 | Dinagat Islands | 1685 | Cagdianao | 168502 | Boa | 168502001 | Construction of 60 Ln.m Cable Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 60 | ln.m | 2764950 | 830856 | 3595806 | 2011-05-23 | 2011-08-15 | 2488455 |  | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Albor | 168504001 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-02-14 | 2011-06-25 | 541240.31 |  | 2nd |  | Completed | 2011-05-30
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Arellano | 168504002 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 723003 | 92377 | 815380 | 2011-05-20 | 2011-07-25 | 650700.5 | not yet started | 2nd |  | Completed | 2011-07-20
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Doña Helen | 168504004 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-04-04 | 2011-07-25 | 518899.6 |  | 2nd |  | Completed | 2011-07-06
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Garcia | 168504005 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-05-20 | 2011-07-25 | 518900.4 | Not yet started | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Kanihaan | 168504007 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq.m | 1187851 | 189806 | 1377657 | 2011-04-07 | 2011-07-25 | 1069065.9 |  | 2nd | Elem | Completed | 2011-06-30
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Magsaysay | 168504008 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq.m | 1187851 | 189806 | 1377657 | 2011-03-30 | 2011-07-25 | 1069065.9 |  | 2nd | Elem | Completed | 2011-06-24
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Osmeña | 168504009 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-03-28 | 2011-07-25 | 518900.4 |  | 2nd |  | Completed | 2011-06-25
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Plaridel | 168504010 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-03-28 | 2011-06-25 | 576556 |  | 2nd |  | Completed | 2011-06-25
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Quezon | 168504011 | Construction of 187 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 187 | ln.m | 565470 | 180906 | 746376 | 2011-03-31 | 2011-06-25 | 565465 |  | 2nd |  | Completed | 2011-06-09
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | San Antonio | 168504012 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-03-21 | 2011-07-25 | 576556 |  | 3rd |  | Completed | 2011-06-20
M1 | Caraga | 16 | Dinagat Islands | 1685 | Libjo | 168504 | Sto. Niño | 168504014 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 576556 | 171182 | 747738 | 2011-05-20 | 2011-07-25 | 576556 | Not yet started | 3rd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Cabunga-an | 168502002 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 655033 | 146370 | 801403 | 2012-07-16 |  | 524026 |  | 1st |  | On-going | 2012-08-31 | 0
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Del Pilar | 168502003 | Construction & Intallation of 100 Units Rain Water Harvesting | 1 | Basic Social Services | Water System | 1 | system | 1944323 | 354408 | 2298731 | 2012-07-19 |  | 1555458.4 |  | 1st |  | On-going | 2012-09-15 | 0
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Mabini (Borja) | 168502013 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1287545 | 262355 | 1549900 | 2012-07-16 |  | 1030036 |  | 1st | Elem | On-going | 2012-09-15 | 0
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Ma- taas | 168502006 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 485779 | 332687 | 818466 | 2012-07-10 |  | 388623.32 |  | 1st | PS | On-going | 2012-08-31 | 0
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Poblacion | 168502008 | Construction of 620 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 620 | ln.m | 1160364 | 346497 | 1506861 | 2011-05-23 | 2011-08-15 | 1160364 |  | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | R. Ecleo Sr. | 168502014 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 129.2 | sq. m | 1186156 | 366063 | 1552219 | 2011-05-20 | 2011-08-15 | 1067540.4 |  | 2nd | HS | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Santa Rita | 168502010 | Construction of 100 Ln.m Concrete Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 100 | ln.m | 1927320 | 429489 | 2356809 |  |  | 0 |  |  |  | Not yet started |  | 0
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Cagdianao | 168502 | Tigbao | 168502011 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq. m | 1186156 | 366063 | 1552219 | 2011-05-20 | 2011-08-15 | 1067540.4 |  | 2nd | Elem | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Alambique | 166711001 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq. m | 1043854 | 561246 | 1605100 | 2011-05-25 | 2011-08-15 | 1011993.84 |  | 3rd | Elem | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Anibongan | 166711002 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 532342 | 284158 | 816500 | 2011-06-20 | 2011-08-15 | 479107.2 |  | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Camam-onan | 166711003 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 588922 | 217278 | 806200 | 2011-06-01 | 2011-08-15 | 541884.1 |  | 3rd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Ipil | 166711005 | Construction of Brgy. Trading Post | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 54 | sq.m | 391203 | 288197 | 679400 | 2011-05-25 | 2011-08-15 | 391203 |  | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Lahi | 166711006 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 588922 | 217278 | 806200 | 2011-06-01 | 2011-09-15 | 588921.4 |  | 3rd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Poniente | 166711008 | Construction of 90 Ln.m River Bank Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 90 | ln.m | 969902 | 270598 | 1240500 | 2011-06-01 | 2011-08-15 | 872911.2 |  | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Sico-Sico | 166711011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 606768 | 176932 | 783700 | 2011-06-01 | 2011-09-15 | 606768 |  | 3rd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Villaflor | 166711012 | Acquisition of Farm Tractor Equipment | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 603945 | 1201951 | 1805896 | 2011-05-25 | 2011-08-15 | 603945 | Land Ownership - N/A | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Gigaquit | 166711 | Villafranca | 166711013 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 524142 | 265158 | 789300 | 2011-05-25 | 2011-08-15 | 471727.8 |  | 2nd |  | Completed | 2011-07-30
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Consolacion | 166716012 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 129.2 | sq. m | 1353693.6 | 226306.4 | 1580000 | 2012-02-07 | 2012-05-15 | 1291667.6 |  | 3rd | Elem | Completed | 2012-04-21
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Katipunan | 166716002 | Construction & Installation of Individual 110 Units Rain Water Collector | 1 | Basic Social Services | Water System | 1 | system | 1946061 | 293939 | 2240000 | 2012-02-18 | 2012-05-15 | 1946061 | 110 Units Rain Water Collector | 3rd |  | Completed | 2012-03-18
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Mabini | 166716004 | Construction of Solar Dryer Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 334 | sq.m | 316809 | 130191 | 447000 | 2012-02-06 | 2012-03-15 | 316809 |  | 2nd |  | Completed | 2012-03-04
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Mabuhay | 166716005 | Construction of 134 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 134 | ln.m | 827600.25 | 252399.75 | 1080000 | 2012-02-15 | 2012-04-15 | 827600.25 |  | 3rd |  | Completed | 2012-06-13
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Punta & Pilaring | 166716011 | Construction of 291 Ln.m Sea Wall | 2 | Environmental Protection and Conservation | Sea Wall | 291 | ln.m | 2121008.71 | 328991.29 | 2450000 | 2012-02-20 | 2012-04-15 | 2121008.7 |  | 3rd |  | Completed | 2012-06-18
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Salvacion | 166716006 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 557013.79 | 192986.21 | 750000 | 2012-02-10 | 2012-04-19 | 557013.79 |  | 3rd |  | Completed | 2012-04-19
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Del Pilar | 166723001 | Construction of 0.4 Km Navarro to Del Pilar FMR | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 2413038.53 | 423001.47 | 2836040 | 2012-01-13 | 2012-07-15 | 2171734.67 |  | 2nd |  | Completed | 2012-04-14
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Navarro | 166723004 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 697775.22 | 144542.78 | 842318 | 2012-01-09 | 2012-03-15 | 697775.22 |  | 2nd |  | Completed | 2012-03-19
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Pamosaingan | 166723006 | Construction of Gravity Driven Level II WS | 1 | Basic Social Services | Water System | 1 | system | 1184806.38 | 260712.62 | 1445519 | 2012-01-12 | 2012-06-15 | 1134806.38 | 4,200 ln.m (No movement as of May 31, 2012 reports | 3rd |  | Completed | 2012-04-28
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Rizal | 166723007 | Construction of 0.25 Km. Concrete Drainage Canal w/ Cover | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 250 | ln.m | 736722.17 | 211922.83 | 948645 | 2012-01-10 | 2012-03-15 | 736722.17 |  | 2nd |  | Completed | 2012-02-25
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Albino Taruc | 166723014 | Construction of 100 Ln.m Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 1966835.8 | 444772.2 | 2411608 | 2012-01-10 | 2012-06-15 | 1966835.8 |  | 3rd |  | Completed | 2012-04-24
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Bayabas | 166802 | Amag | 166802001 | Construction of 1,320 Ln.m Gravity Driven Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 858924 | 162667 | 1021591 | 2012-04-02 | 2012-06-15 | 773032 | 1,320 Ln.m | 2nd |  | Completed | 2012-06-21
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Bayabas | 166802 | Balete | 166802002 | Construction of 1,950 Ln.m Gravity Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 748306 | 140279 | 888585 | 2012-04-11 | 2012-06-15 | 673475 | 1,950 Ln.m | 2nd |  | Completed | 2012-06-30
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Bayabas | 166802 | Cabugo | 166802003 | Construction of 2 Units Box Culvert Single Channel | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 129.2 | sq.m | 906788 | 213770 | 1120558 | 2012-02-21 | 2012-04-15 | 906788 |  | 2nd |  | Completed | 2012-05-21
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Bayabas | 166802 | Magobawok | 166802006 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 133.2 | sq. m | 676803 | 112471 | 789274 | 2012-03-26 | 2012-06-14 | 643924 |  | 2nd | Elem | Completed | 2012-06-14
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Aras-asan | 166804001 | Construction of 242 Ln.m Drainage Canal w/ One Unit Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 242 | ln.m | 850005.6 | 305293.4 | 1155299 | 2012-02-02 | 2012-04-11 | 850005.6 |  | 2nd |  | Completed | 2012-04-11
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Lactudan | 166804006 | Construction of Gravity Driven Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 767613.5 | 259841.5 | 1027455 | 2012-02-21 | 2012-06-15 | 723963.6 |  | 3rd |  | Completed | 2012-05-05
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Poblacion | 166804009 | Construction of 610 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 610 | ln.m | 987063.2 | 332949.8 | 1320013 | 2012-02-20 | 2012-06-15 | 948563.2 |  | 3rd |  | Completed | 2012-05-05
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Tubo-Tubo | 166804012 | Construction of 385 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 385 | ln.m | 843578.4 | 292906.6 | 1136485 | 2012-02-02 | 2012-04-15 | 843578.4 |  | 3rd |  | Completed | 2012-03-28
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Unidad | 166804011 | Construction of 50 Ln.m Shore Protection | 1 | Environmental Protection and Conservation | Sea Wall | 50 | ln.m | 1194776.8 | 395426.2 | 1590203 | 2012-02-27 | 2012-05-19 | 1194776.8 |  | 2nd |  | Completed | 2012-05-19
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Baculin | 166809002 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 122.29 | sq. m | 1284232 | 218969 | 1503201 | 2012-03-14 | 2012-05-15 | 1284214.55 |  | 3rd | HS | Completed | 2012-06-11
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Campa | 166809006 | Construction of 100 ln.m Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 1074480.3 | 298584.7 | 1373065 | 2012-04-16 | 2012-05-15 | 1017307.7 | Portlamon (Road) was replaced by Campa (Seawall) | 2nd |  | Completed | 2012-07-14
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Loyola | 166809014 | Construction of 100 Ln.m Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 1150798 | 222267 | 1373065 | 2012-04-04 | 2012-05-15 | 1090592 |  | 3rd |  | Completed | 2012-06-30
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Maligaya | 166809017 | Construction of Corn & Coffee Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 116.9 | sq.m | 987771 | 144816 | 1132587 | 2012-05-01 |  | 790213.76 |  | 1st |  | On-going
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Pocto | 166809022 | Construction of 93 Ln.m Cable Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 93 | ln.m | 1124844 | 178355 | 1303199 | 2012-04-18 |  | 899875 |  | 1st |  | On-going | 2012-07-16
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Roxas | 166809025 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1284232 | 218969 | 1503201 | 2012-03-15 | 2012-05-15 | 1260821.51 |  | 3rd | HS | Completed | 2012-06-12
M1 | Caraga | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Punta & Pilaring | 166716010 | Construction of 291 Ln.m Sea Wall | 2 | Environmental Protection and Conservation | Sea Wall | 291 | ln.m | 2121008.71 | 328991.29 | 2450000 | 2012-02-20 | 2012-04-15 | 2121008.7 |  | 3rd |  | Completed | 2012-06-18
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | San Ramon |  | Construction of 24.4 Ln.m Bailey Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 24.4 | ln.m | 779210 | 1490337 | 2269547 | 2012-04-22 | 2012-06-15 | 741606.9 |  | 2nd |  | Completed | 2012-06-20
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Sasa | 166809031 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1284232 | 218969 | 1503201 | 2012-03-12 | 2012-05-15 | 1217931.25 |  | 3rd | Elem | Completed | 2012-06-09
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Talisay | 166809037 | Road Rehabilitation of 5.2 Km. FMR | 1 | Basic Access Infrastructure | Road | 5.2 | kms | 1879402.7 | 264869.3 | 2144272 | 2012-07-01 |  | 1503521 |  | 1st |  | On-going
M1 | Caraga | 16 | Surigao del Sur | 1668 | Hinatuan | 166809 | Tidman | 166809039 | Construction of 100 Ln.m Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 1150798 | 222267 | 1373065 | 2012-03-13 | 2012-05-15 | 1090591 |  | 3rd |  | Completed | 2012-06-10
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Marihatag | 166814 | Alegria | 166814001 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.92 | sq. m | 1292509 | 287117 | 1579626 | 2011-12-26 | 2012-04-15 | 1292509 |  | 3rd | Elem | Completed | 2012-03-27
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Marihatag | 166814 | Antipolo | 166814003 | Construction of 40 Ln.m River Dike | 1 | Environmental Protection and Conservation | River Control/Flood Control | 40 | ln.m | 810739 | 192261 | 1003000 | 2011-12-26 | 2012-02-15 | 810739 |  | 2nd |  | Completed | 2012-03-03
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Marihatag | 166814 | Mahaba | 166814006 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.92 | sq. m | 1292509 | 287117 | 1579626 | 2011-12-26 | 2012-04-15 | 1292509 |  | 3rd | Elem | Completed | 2012-03-27
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Marihatag | 166814 | Mararag | 166814007 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.92 | sq. m | 1292509 | 287117 | 1579626 | 2011-12-26 | 2012-04-15 | 1292509 |  | 2nd | Elem | Completed | 2012-03-27
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Marihatag | 166814 | Poblacion | 166814008 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.92 | sq. m | 1292509 | 287117 | 1579626 | 2011-12-26 | 2012-03-15 | 1292509 |  | 2nd | Elem | Completed | 2012-03-27
M1 | Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 1668160 | Baras | 166816002 | Construction of 4,218 Ln.m Pump Driven Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2368249 | 520835 | 2889084 | 2012-02-16 | 2012-05-15 | 2232350 | 4,218 ln.m | 3rd |  | Completed | 2012-06-14
M1 | Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 1668160 | Libas Sud | 166816009 | Construction of 1.7 Km. Mauswagon-Kalamboayon FMR | 1 | Basic Access Infrastructure | Road | 1.7 | kms | 1658559 | 367274 | 2025833 | 2012-05-14 |  | 1160991.3 |  | 1st |  | On-going | 2012-06-20
M1 | Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 1668160 | Mahayag | 166816011 | Construction of 5,597 Ln.m Pump Driven Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2524248 | 554955 | 3079203 | 2012-02-13 | 2012-06-15 | 2271823.2 | 5,597 Ln.m | 2nd |  | Completed | 2012-05-13
M1 | Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 1668160 | Patong | 166816012 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 616360 | 141936 | 758296 | 2012-01-10 | 2012-04-29 | 616360 |  | 2nd |  | Completed | 2012-03-24
M1 | Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 1668160 | Sagbayan | 166816014 | Construction of 2,610 Ln.m Pump Driven Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1800624 | 399082 | 2199706 | 2012-02-16 | 2012-05-15 | 1620561.6 | 2,610 Ln.m | 2nd |  | Completed | 2012-05-16
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Banagbanag | 160314003 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1114048 | 148603 | 1262651 | 2012-02-23 | 2012-07-15 | 1114048 |  | 3rd | Elem | Completed | 2012-05-22
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Ilihan | 160314006 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 52 | sq.m | 667778 | 121782 | 789560 | 2012-01-09 | 2012-05-15 | 667778 |  | 2nd |  | Completed | 2012-04-08
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Kioya | 160314008 | Gravelling of 0.6 Km. Kioya FMR w/ 200 Concreting | 1 | Basic Access Infrastructure | Road | 0.6 | kms | 2144171 | 213046 | 2357217 | 2012-06-04 |  | 1715336.8 |  | 1st |  | On-going | 2012-08-17
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Mahayahay | 160314011 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 52 | sq.m | 667778 | 121782 | 789560 | 2012-01-23 | 2012-06-15 | 667778 |  | 3rd |  | Completed | 2012-04-21
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Perez | 160314014 | Construction of 125 Ln.m Cable Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 125 | ln.m | 3565655 | 365412 | 3931067 | 2012-01-12 |  | 3565655 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-04-11
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | San Isidro | 160314016 | Construction of Gravity Driven Level II WS | 1 | Basic Social Services | Water System | 1 | system | 1172842 | 144252 | 1317094 | 2012-02-20 | 2012-06-15 | 1119302.5 |  | 3rd |  | Completed | 2012-05-04
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Sta. Cruz | 160314018 | Construction of Gravity Driven Level II WS | 1 | Basic Social Services | Water System | 1 | system | 788814 | 138076 | 926890 | 2012-03-15 | 2012-07-15 | 788814 | 1,464 ln.m | 3rd |  | Completed | 2012-05-28
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Sta. Maria | 160314019 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1061118 | 170704 | 1231822 | 2012-02-01 | 2012-06-15 | 1061118 |  | 3rd | Elem | Completed | 2012-04-30
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Sibagat | 160314 | Villangit | 160314023 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 776088 | 997141 | 1773229 | 2012-02-10 | 2012-06-15 | 776088 | 99.59% physical as of June 30, 2012 | 3rd | Elem | Completed | 2012-05-09
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Carpenito | 166817002 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 585713 | 123401 | 709114 | 2012-01-20 | 2012-04-26 | 583182.84 |  | 2nd |  | Completed | 2012-04-03
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Hinagdanan | 166817026 | Construction of Level II Pump Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 1403087 | 691977.46 | 2395046 | 2012-01-30 |  | 1392350.98 | With PAMANA - 299,981.54 TPC 2,395,046.00 | 3rd |  | On-going | 2012-05-28 | 299981.54
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Kahayagan | 166817003 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 595850 | 124922 | 720772 | 2012-01-31 | 2012-05-15 | 596649 |  | 3rd |  | Completed | 2012-04-14
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Lago | 166817004 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.62 | sq.m | 655615 | 134508 | 790123 | 2012-01-31 | 2012-04-28 | 645129.5 |  | 3rd |  | Completed | 2012-04-14
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Maglambing | 166817006 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 652331 | 134016 | 786347 | 2012-01-20 | 2012-04-15 | 654058.25 |  | 2nd |  | Completed | 2012-04-03
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Malixi | 166817009 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.62 | sq.m | 652804 | 134087 | 786891 | 2012-02-03 | 2012-05-15 | 654521.57 |  | 3rd |  | Completed | 2012-04-17
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Quezon | 166817013 | Construction of 470 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 470 | ln.m | 1383348 | 327409 | 1710757 | 2012-01-20 | 2012-05-15 | 1354817.78 |  | 2nd |  | Completed | 2012-05-18
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | San Vicente II | 166817014 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.62 | sq.m | 656568 | 134651 | 791219 | 2012-01-24 | 2012-05-15 | 658291 |  | 3rd |  | Completed | 2012-04-07
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Sayon | 166817019 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 587697 | 123699 | 711396 | 2012-02-02 | 2012-04-20 | 588495.2 |  | 2nd |  | Completed | 2012-04-16
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Sta. Cruz | 166817015 | Construction of 1 Unit 6.10 Ln.m Slab Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 6.1 | ln.m | 721469 | 153900 | 875369 | 2012-01-27 | 2012-04-15 | 721469 |  | 2nd |  | Completed | 2012-04-10
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Sta. Fe | 166817016 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 590297 | 124089 | 714386 | 2012-01-20 | 2012-04-15 | 591092.33 |  | 2nd |  | Completed | 2012-04-03
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Sta. Juana | 166817017 | Construction of 1 Unit 6.10 Ln.m Slab Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 6.1 | ln.m | 494277 | 113590 | 607867 | 2012-01-30 | 2012-05-02 | 494083.42 |  | 2nd |  | Completed | 2012-05-02
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Sta. Maria | 166817018 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 589243 | 123931 | 713174 | 2012-01-25 | 2012-05-15 | 590041.39 |  | 3rd |  | Completed | 2012-04-08
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Trinidad | 166817022 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.62 | sq.m | 648450 | 133433 | 781883 | 2012-01-27 | 2012-05-15 | 650173 |  | 3rd |  | Completed | 2012-06-30
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Ugoban | 166817023 | Construction of 1 Unit CL Pre-School Building (PS) | 1 | Basic Social Services | School | 79.86 | sq. m | 718866 | 150045 | 868911 | 2012-01-30 | 2012-05-15 | 718866 |  | 3rd | PS | Completed | 2012-04-13
M1 | Caraga | 16 | Surigao Del Sur | 1668 | Tagbina | 166817 | Villaverde | 166817024 | Construction of Level II Pump Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 1526128 | 851705.18 | 2677827 | 2012-02-04 |  | 1524187.55 | With PAMANA - 299,993.82 TPC 2,677,827.00 (7,553 ln.m) | 3rd |  | On-going | 2012-06-01 | 299993.82
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Batabat Norte | 045605004 | Construction of Water System Level II (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 944347.83 | 302652.17 | 1247000 | 2012-06-01 |  | 755478.26 | 2,866.80 l.m. & 15-units Tapstand | 1st |  | On-going | 2012-08-30
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Batabat Sur | 045605005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 572172.28 | 155827.72 | 728000 | 2012-01-27 | 2012-05-15 | 572172.28 |  | 3rd |  | Completed | 2012-04-11
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Buenavista | 045605006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 545009.39 | 190990.61 | 736000 | 2012-02-08 | 2012-05-15 | 545009.39 |  | 3rd |  | Completed | 2012-04-23
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cadlit | 045605010 | Construction of 217 Ln.m Covered Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 217 | ln.m | 451304.35 | 267695.65 | 719000 | 2012-04-12 |  | 406173.91 |  | 2nd |  | On-going | 2012-05-30
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Catulin | 045605011 | Improvement of 628.75m FMR w/ 1,200sq.m PCCP on Critical Slope & Masonry Line Canal | 1 | Basic Access Infrastructure | Road | 0.627 | kms | 1438569.22 | 413430.78 | 1852000 | 2012-06-16 |  | 1150855.38 |  | 1st |  | On-going | 2012-09-14
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cawa | 045605012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 531304.35 | 205695.65 | 737000 | 2012-01-23 | 2012-04-15 | 531304.35 |  | 3rd |  | Completed | 2012-04-07
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | De La Paz | 045605013 | Construction of Multi-Purpose Building | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 63 | sq.m | 565217.39 | 240782.61 | 806000 | 2012-05-02 |  | 508695.65 |  | 2nd |  | On-going | 2012-07-16
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Lilukin | 045605019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 492173.91 | 235826.09 | 728000 | 2012-01-30 | 2012-04-15 | 492173.91 |  | 3rd |  | Completed | 2012-04-14
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Mabini | 045605020 | Improvement of 1.8 Km. FMR w/ 1,200 sq.m PCCP on Critical Slope & Line Canal | 1 | Basic Access Infrastructure | Road | 1.8 | kms | 2299426.78 | 526573.22 | 2826000 | 2012-04-12 |  | 2069484.09 |  | 2nd |  | On-going | 2012-07-11
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Mabutag | 045605021 | Improvement of 1.556 Km. FMR w/ 0.60 Ln.m RCPC & Masonry Line Canal | 1 | Basic Access Infrastructure | Road | 1.556 | kms | 1057968.7 | 307031.45 | 1365000.15 | 2012-04-24 |  | 846374.96 |  | 1st |  | On-going | 2012-07-23
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Magallanes | 045605022 | Construction of 1.847 Km. FMR | 1 | Basic Access Infrastructure | Road | 1.847 | kms | 1606838.48 | 292161.68 | 1899000.16 |  |  | 1285470.78 |  | 1st |  | Not yet started
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Masaya | 045605025 | Concreting of 386 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.386 | kms | 1222643.48 | 483356.52 | 1706000 | 2012-04-10 |  | 1100379.13 |  | 2nd |  | On-going | 2012-07-19
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Poblacion | 045605026 | Construction of 206 Linear Meters Covered Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 206 | ln.m | 421739.13 | 183260.87 | 605000 | 2012-02-15 | 2012-06-15 | 421739.13 |  | 3rd |  | Completed | 2012-04-30
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Rizal | 045605027 | Construction of 2.190 Km. FMR | 1 | Basic Access Infrastructure | Road | 2.19 | kms | 3161217.39 | 706782.61 | 3868000 |  |  | 2528973.91 |  | 1st |  | Not yet started
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | San Vicente | 045605035 | Construction of 1.08 Km. FMR w/ Spillway | 1 | Basic Access Infrastructure | Road | 1.08 | kms | 1050000 | 363000.15 | 1413000.15 | 2012-04-24 | 2012-07-23 | 945000 |  | 2nd |  | Completed | 2012-07-23
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Siain | 045605036 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 180317.75 | 564682.25 | 745000 | 2012-03-14 | 2012-07-15 | 142399.38 |  | 1st |  | Completed | 2012-05-28
M1 | IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Villa Batabat | 045605039 | Improvement of 1.9 Km. w/ 1,200sq.m PCCP on Critical Slope & Masonry Line Canal | 1 | Basic Access Infrastructure | Road | 1.9 | kms | 1959749.57 | 540250.64 | 2500000.21 | 2012-04-28 |  | 1763774.61 |  | 2nd |  | On-going | 2012-07-27
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Amot | 045606002 | Improvement of 600 Ln.m Pathway w/ 1,200 PCCP | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 825322.06 | 129658.1 | 954980.16 | 2012-04-13 | 2012-07-15 | 742789.27 |  | 2nd |  | Completed | 2012-06-06
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Cabugao | 045606005 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1163426.99 | 182774.38 | 1346201.37 | 2012-06-04 |  | 930741.66 |  | 1st | HS | On-going | 2012-08-18
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Cabungalunan | 045606006 | Construction of 100 Ln.m Cable Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 100 | ln.m | 1126839.77 | 177026.4 | 1303866.17 | 2012-05-03 |  | 901471.15 |  | 1st |  | On-going | 2012-07-12
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Calutcot | 045606007 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1298074.39 | 274272.8 | 1572347.19 | 2012-05-07 |  | 1038460.84 | Brgy. Palasan was changed by brgy Calutcot | 1st | Elem | On-going | 2012-08-05
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Caniwan | 045606008 | Construction of 500m Pathway w/ 500 Ln.m. PCCP & 10 Ln.m RCBC | 1 | Basic Access Infrastructure | Access Trail | 0.5 | kms | 1007748.64 | 158317.31 | 1166065.95 | 2012-03-08 | 2012-07-15 | 906973.77 |  | 2nd |  | Completed | 2012-05-07
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Mabini | 045606010 | Improvement of Pathway w/ 1,200 sq.m PCCP | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 910247.33 | 142999.85 | 1053247.18 | 2012-04-10 | 2012-06-15 | 819222.24 |  | 2nd |  | Completed | 2012-06-09
M1 | IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Rizal | 045606013 | Construction of Pathway w/ 1,200sq.m PCCP | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 668340.82 | 104996.49 | 773337.31 | 2012-04-11 |  | 601506.85 |  | 2nd |  | On-going | 2012-06-04
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Anusan | 045610002 | Construction of Brgy. Health Station Building | 1 | Basic Social Services | Health Station | 51.4 | sq.m | 528610.47 | 317389.53 | 846000 | 2012-02-13 | 2012-05-15 | 528610.47 |  | 3rd |  | Completed | 2012-04-23
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Bolo | 045610012 | Construction of Level II Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 2481721.29 | 848278.71 | 3330000 | 2012-05-28 |  | 1985377.03 | 4,500 l.m. & 32-Units Tapstand | 1st |  | On-going | 2012-08-26
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Cutcutan | 045610019 | Construction of Level II Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 2490596.08 | 899403.92 | 3390000 | 2012-06-12 |  | 1743417.26 |  | 1st |  | On-going | 2012-10-10
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Doongan Ilaya | 045610022 | Construction of 2 Units 2 CL School Building (HS) | 1 | Basic Social Services | School | 252 | sq. m | 2262499.27 | 887500.73 | 3150000 | 2012-05-09 |  | 2036242.34 |  | 2nd | HS | On-going | 2012-09-06
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Gatasan | 045610023 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.4 | sq.m | 547148.97 | 294851.03 | 842000 | 2012-02-01 | 2012-05-15 | 547148.97 |  | 3rd |  | Completed | 2012-03-10
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Macpac | 045610024 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.4 | sq.m | 580522.46 | 261477.54 | 842000 | 2012-02-01 | 2012-05-15 | 580522.46 |  | 3rd |  | Completed | 2012-03-10
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | San Isidro | 045610033 | Construction of 1.6 Km. Stone Masonry Line Canal w/ Intermittent Re-Gravelling | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 1600 | ln.m | 1366081.93 | 768918.07 | 2135000 | 2012-04-13 |  | 956257.35 |  | 1st |  | On-going | 2012-06-12
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | San Jose Anyao | 045610034 | Construction of 2.96 Km. FMR | 1 | Basic Access Infrastructure | Road | 2.96 | kms | 3691735.07 | 1158264.93 | 4850000 | 2012-04-23 |  | 2399627.79 |  | 1st |  | On-going | 2012-08-21
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | San Vicente Kanluran | 045610037 | Improvement of 3.5 Km. FMR | 1 | Basic Access Infrastructure | Road | 3.5 | kms | 2698346.18 | 871653.82 | 3570000 | 2012-03-05 | 2012-07-15 | 2698346.18 |  | 2nd |  | Completed | 2012-06-23
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Tagbacan Ilaya | 045610041 | Improvements of 2.448 Km. FMR | 1 | Basic Access Infrastructure | Road | 2.448 | kms | 1779754.61 | 675245.39 | 2455000 | 2012-02-23 | 2012-07-15 | 1779754.61 |  | 2nd |  | Completed | 2012-06-23
M1 | IV-A | 04 | Quezon | 0456 | Catanauan | 045610 | Tagbacan Silangan | 045610044 | Improvements of 2.823 Km. FMR | 1 | Basic Access Infrastructure | Road | 2.823 | kms | 2112915.74 | 722084.26 | 2835000 | 2012-03-01 | 2012-07-15 | 2112915.74 |  | 2nd |  | Completed | 2012-06-23
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Antonino (Ayusan) | 045615001 | Concreting of 300 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 898442 | 260466 | 1158908 | 2012-03-23 | 2012-06-15 | 886219.28 |  | 3rd |  | Completed | 2012-04-28
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bagong Anyo | 045615002 | Construction of Line Canal and Concreting of Shoulder | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 735106 | 304073 | 1039179 | 2012-01-24 | 2012-05-15 | 697555.5 |  | 3rd |  | Completed | 2012-03-06
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bulakin 1 | 045615004 | Concreting of 300 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 866821 | 275073 | 1141894 | 2012-03-16 | 2012-06-15 | 866677.75 |  | 3rd |  | Completed | 2012-04-21
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bungoy | 045615005 | Concreting of 400 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 939401 | 244530 | 1183931 | 2012-02-29 | 2012-06-15 | 921614 | No movement as of May 31, 2012 reports | 3rd |  | Completed | 2012-04-29
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Cabatang | 045615006 | Improvement of Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 8 | ln.m | 491723 | 137859 | 629582 | 2012-01-30 | 2012-06-15 | 442550.7 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-03-15
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Maligaya | 045615009 | Construction of Drainage Structure | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 118.5 | ln.m | 471532 | 104530 | 576062 | 2012-02-06 | 2012-05-15 | 424379.25 |  | 2nd |  | Completed | 2012-03-22
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Manggahan | 045615010 | Concreting of 350 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.35 | kms | 1179660 | 276916 | 1456576 | 2012-04-20 | 2012-06-15 | 1171871.3 |  | 3rd |  | Completed | 2012-06-07
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Pinagdanlayan | 045615011 | Concreting of 300 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 758631 | 259244 | 1017875 | 2012-03-14 | 2012-06-15 | 750529.5 |  | 3rd |  | Completed | 2012-04-19
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Putol | 045615012 | Concreting of 300 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 876207 | 200081 | 1076288 | 2012-05-01 | 2012-06-15 | 832697 |  | 3rd |  | Completed | 2012-06-06
M1 | IV-A | 04 | Quezon | 0456 | Dolores | 045615 | San Mateo | 045615013 | Concreting of 287.5 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.287 | kms | 782477 | 255162 | 1037639 | 2012-04-24 | 2012-06-15 | 782476.4 |  | 3rd |  | Completed | 2012-05-28
M1 | IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Apad | 045621005 | Concreting of 2m x 600m Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 845157 | 200280 | 1045437 | 2012-01-22 | 2012-07-15 | 760641.3 |  | 2nd |  | Completed | 2012-02-17
M1 | IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Bukal | 045621001 | Construction of Pathway w/ Concreting of Critical Areas | 1 | Basic Access Infrastructure | Access Trail | 1.2 | kms | 819027 | 222510 | 1041537 | 2012-02-09 | 2012-07-15 | 737124.3 |  | 2nd |  | Completed | 2012-03-16
M1 | IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Gango | 045621003 | Concreting of 2m x 600 Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 718529 | 300139 | 1018668 | 2012-02-09 | 2012-07-15 | 646676.1 |  | 2nd |  | Completed | 2012-03-17
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Buyao | 045625003 | Improvement of FMR with 400 Ln.m Concreting | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 1201713 | 382787 | 1584500 | 2012-01-19 | 2012-07-15 | 1201713 |  | 3rd |  | Completed | 2012-04-18
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Castillo | 045625019 | Construction of 243 Ln.m River Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 243 | ln.m | 4376754 | 1401146 | 5777900 | 2012-03-27 |  | 2626052.4 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-08-24
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Lahing | 045625006 | Construction of RCBC (2 Locations) | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 10 | ln.m | 369385 | 131115 | 500500 | 2012-01-19 | 2012-06-15 | 369385 |  | 3rd |  | Completed | 2012-04-18
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Mambog | 045625011 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 845255 | 334125 | 1179380 | 2012-01-30 | 2012-06-15 | 845255 |  | 3rd |  | Completed | 2012-04-29
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Olongtao Ilaya | 045625013 | Construction of FMR with 210 Ln.m Concreting | 1 | Basic Access Infrastructure | Road | 0.21 | kms | 2641936 | 844024 | 3485960 | 2012-03-23 |  | 2377742.4 |  | 2nd |  | On-going | 2012-06-21
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Pajarillo | 045625015 | Improvement of FMR with 1,200 Ln.m Concreting | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 1702290 | 549687 | 2251977 | 2012-01-30 |  | 1702290 |  | 3rd |  | On-going | 2012-04-29
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | San Isidro | 045625023 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1005899 | 352470 | 1358369 | 2012-01-26 | 2012-06-15 | 990965.2 |  | 3rd |  | Completed | 2012-04-25
M1 | IV-A | 04 | Quezon | 0456 | Macalelon | 045625 | Vista Hermosa | 045625030 | Construction of 1,600 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 1.6 | kms | 1230018.62 | 411938.38 | 1641957 | 2012-02-28 |  | 1230018.62 |  | 3rd |  | On-going | 2012-05-28
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Amuguis | 045628002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 469837.12 | 209583.88 | 679421 | 2011-03-23 | 2011-09-15 | 469837.12 |  | 3rd |  | Completed | 2011-04-27
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | F. Nanadiego | 045628017 | Extension of Electrical Power Main Line 2.91 Km | 1 | Basic Social Services | Electrification | 42 | HH | 1385382.13 | 782555.87 | 2167938 | 2011-06-14 | 2011-07-30 | 1385382.13 |  | 2nd |  | Completed | 2011-07-30
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Ilayang Yuni | 045628021 | Construction of 1 Unit CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq.m | 1086626.29 | 292815.71 | 1379442 | 2011-03-21 | 2011-09-15 | 1086626.29 |  | 3rd | Elem | Completed | 2011-06-03
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Latangan | 045628022 | Construction of 2.0 Km. FMR | 1 | Basic Access Infrastructure | Road | 2 | kms | 2044467.03 | 395861.97 | 2440329 | 2011-07-18 | 2012-05-23 | 1717408.4 |  | 2nd |  | Completed | 2011-07-30
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Mabini (Ilayang Cambuga ) | 045628020 | Construction of Double Barrel Box Culvert with Concreting of 200 Ln.m Critical Slope | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 1925670.92 | 505090.08 | 2430761 | 2011-05-17 | 2011-12-15 | 1540536.74 |  | 1st |  | Completed | 2011-07-30
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Matataja | 045628025 | Construction of 1 Km. FMR with 300 Ln.m Concreting | 1 | Basic Access Infrastructure | Road | 1 | kms | 1899656.53 | 752498.47 | 2652155 | 2011-07-13 | 2011-11-15 | 1670421.51 |  | 2nd |  | Completed | 2011-07-30
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion 3 | 045628009 | Construction of 124LM Line Canal w/ 1 Unit Catch Basin | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 124 | ln.m | 477532.82 | 267053.75 | 744586.57 | 2011-07-31 | 2011-10-15 | 399802.06 |  | 2nd |  | Completed | 2011-10-15
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion 4 | 045628010 | Construction of 217 Ln.m Covered Line Canal with 3 Unit Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 217 | ln.m | 1466322.93 | 384237.07 | 1850560 | 2011-03-19 | 2011-09-15 | 1466322.93 |  | 3rd |  | Completed | 2011-05-17
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sagongon | 045628028 | Rehabilitation of 700 Meters FMR with Concreting of 300 Ln.m Critical Slope | 1 | Basic Access Infrastructure | Road | 0.7 | kms | 1545615.18 | 281400.82 | 1827016 | 2011-03-30 | 2011-09-15 | 1321269.86 |  | 2nd |  | Completed | 2011-09-15
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | San Isidro | 045628029 | Upgrading of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 360168.03 | 200072.28 | 560240.31 | 2011-07-30 | 2011-11-15 | 334948.72 |  | 3rd |  | Completed | 2011-09-06
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | San Pedro | 045628030 | Upgrading of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 874256.1 | 255846.9 | 1130103 | 2011-07-30 | 2011-10-15 | 817157.63 |  | 2nd |  | Completed | 2011-10-15
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sta. Rosa | 045628031 | Construction of 1 Unit CL Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq.m | 497648.03 | 298759.97 | 796408 | 2011-03-19 | 2011-09-15 | 497648.03 |  | 3rd | PS | Completed | 2011-05-02
M1 | IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sto. Niño |  | Upgrading of 500 Meters Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.5 | kms | 804517.74 | 186151.26 | 990669 | 2011-03-28 | 2011-07-31 | 804517.73 |  | 3rd |  | Completed | 2011-05-11
M1 | IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Bato | 045631002 | Construction of 900 Ln.m Pathway w/ 2mx900 Ln.m PCCP w/ 3 Ln.m RCPC w/ Head Wall | 1 | Basic Access Infrastructure | Access Trail | 0.9 | kms | 1396300 | 273700 | 1670000 | 2012-01-27 | 2012-06-15 | 1256670 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-04-24
M1 | IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Bonbon | 045631003 | Extension of 44.5 Ln.m Wharf w/ Construction of 6x8m Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 44.5 | ln.m | 1401921.74 | 269348.26 | 1671270 | 2012-03-01 |  | 1261729.57 |  | 2nd |  | On-going | 2012-03-31
M1 | IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Kinalagti | 045631005 | Construction of Pathway w/ 2mx 646 Ln.m PCCP w/ 3 Ln.m RCPC w/ Headwall | 1 | Basic Access Infrastructure | Access Trail | 0.646 | kms | 546162.6 | 660837.4 | 1207000 | 2012-01-30 | 2012-06-15 | 491546.34 |  | 2nd |  | Completed | 2012-03-29
M1 | IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Libo | 045631006 | Improvement of 1.2 Km. Pathway w/ 2mx900 Ln.m PCCP w/ 12 Ln.m RCPC | 1 | Basic Access Infrastructure | Access Trail | 1.2 | kms | 1326089.57 | 264013.43 | 1590103 | 2012-01-24 | 2012-06-15 | 1193480.61 |  | 2nd |  | Completed | 2012-04-24
M1 | IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Pandan | 045631011 | Construction of 500m Pathway w/ 2mx500 Ln.m PCCP w/ 3 Ln.m RCPC | 1 | Basic Access Infrastructure | Access Trail | 0.5 | kms | 1329526.09 | 259473.91 | 1589000 | 2012-01-30 | 2012-07-15 | 1196573.48 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-03-30
M1 | IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Amaga | 045632001 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 666716 | 204575 | 871291 | 2012-02-06 | 2012-04-15 | 600044.4 |  | 2nd |  | Completed | 2012-03-25
M1 | IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Kilogan | 045632003 | Construction of 4m Width x 19 Ln.m. 1 Unit Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 19 | ln.m | 327542 | 541649 | 869191 | 2012-02-15 | 2012-04-15 | 294787.8 |  | 2nd |  | Completed | 2012-04-05
M1 | IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Norte | 045632005 | Construction of 4m Width x 18 Ln.m Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 18 | ln.m | 912797 | 286097 | 1198894 | 2012-02-06 | 2012-05-15 | 821517.3 |  | 2nd |  | Completed | 2012-04-21
M1 | IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Poblacion | 045632006 | Construction of 2 Units 0.90 RCPC Cross Drain | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 20 | ln.m | 1092945 | 241271 | 1334216 | 2012-01-23 | 2012-04-15 | 983650.5 |  | 2nd |  | Completed | 2012-04-06
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Bagong Pag-asa | 045633009 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 372 | ln.m | 372125.15 | 323674.85 | 695800 | 2012-05-08 | 2012-07-15 | 334912.64 |  | 2nd |  | Completed | 2012-07-07 | 0
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Bagong Silang | 045633010 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 472162.12 | 224737.88 | 696900 | 2011-06-15 | 2011-08-15 | 472162.12 |  | 3rd |  | Completed | 2011-07-31
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Bagong Silang | 045633010 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1126393.29 | 248696.71 | 1375090 | 2012-05-04 |  | 1013753.96 |  | 2nd | Elem | On-going | 2012-08-02
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Maabot | 045633001 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1043196.04 | 349803.96 | 1393000 | 2011-06-27 | 2011-08-15 | 1008641.04 |  | 3rd | Elem | Completed | 2011-07-31
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Mainit Norte | 045633002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 543928.68 | 152971.32 | 696900 | 2011-06-20 | 2011-08-15 | 543928.68 |  | 3rd |  | Completed | 2011-07-31
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Mainit Sur | 045633003 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 544468.59 | 152431.41 | 696900 | 2011-06-06 | 2011-07-30 | 544468.59 |  | 3rd |  | Completed | 2011-07-31
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Mainit Sur | 045633003 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1126213.51 | 255666.49 | 1381880 | 2012-05-04 | 2012-07-15 | 1126213.51 |  | 3rd | Elem | Completed | 2012-08-02
G1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Pagkakaisa | 045633007 | Rip-rapping of Paranas Creek | 1 | Environmental Protection and Conservation | River Control/Flood Control | 151 | ln.m | 897346.59 | 217407.41 | 1114754 | 2012-05-28 |  | 717877.27 |  | 1st |  | On-going | 2012-08-11
G1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Pambuhan | 045633004 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1115555.22 | 259774.78 | 1375330 | 2012-05-03 |  | 1003999.7 |  | 2nd | Elem | On-going | 2012-08-01
G1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Pinagtubigan Este | 045633005 | Construcion of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1043196.04 | 349803.96 | 1393000 | 2011-06-08 | 2011-09-15 | 938876.43 |  | 2nd | Elem | Completed | 2011-07-31
G1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Rizal | 045633011 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 528237.77 | 235312.23 | 763550 | 2011-06-06 | 2011-08-15 | 528237.77 |  | 3rd |  | Completed | 2011-07-31
G1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Sangirin | 045633012 | Construction of 30 Ln.m. Cable Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 30 | ln.m | 806552.36 | 297447.64 | 1104000 | 2011-06-22 | 2011-08-15 | 806552.36 |  | 3rd |  | Completed | 2011-07-31
G1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Saringin | 045633012 | Construction of 410 ln.m Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.41 | kms | 705889.91 | 168110.09 | 874000 | 2012-04-23 | 2012-07-15 | 705889.91 |  | 3rd |  | Completed | 2012-06-22
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Villa Manzano Norte | 045633013 | Concreting of 385 Meters Brgy Road | 1 | Basic Access Infrastructure | Road | 0.385 | kms | 759314.27 | 265685.73 | 1025000 | 2011-06-27 | 2011-07-30 | 752183.29 |  | 3rd |  | Completed | 2011-07-31
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Villa Manzano Sur | 045633014 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 558944.13 | 204605.87 | 763550 | 2011-06-15 | 2011-08-15 | 558944.12 |  | 3rd |  | Completed | 2011-07-31
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Villamanzano Norte & villamanzano Sur | 045633013 | Construction of Drainage Canal w/ 600sq.m PCCP & Intermittent Re-gravelling | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 956476.33 | 211973.67 | 1168450 | 2012-05-14 |  | 765181.06 |  | 1st |  | On-going | 2012-07-13
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Cawayan II | 045642005 | Concreting of 396 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 0.396 | kms | 763478 | 903456 | 1666934 | 2012-02-23 | 2012-06-15 | 687130.2 |  | 2nd |  | Completed | 2012-05-11
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Don Juan Vercelos | 045642015 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1131371 | 385276 | 1516647 | 2012-02-27 | 2012-06-15 | 1018233.9 |  | 2nd | HS | Completed | 2012-03-08
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Ilayang Tayuman | 045642008 | Construction of 1,437.29 Ln.m FMR | 1 | Basic Access Infrastructure | Road | 1.437 | kms | 1065408 | 450687 | 1516095 | 2012-02-27 | 2012-06-15 | 958867.2 |  | 2nd |  | Completed | 2012-04-11
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Nasalaan | 045642010 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2147244 | 506877 | 2654121 |  |  | 1717795.2 |  | 1st |  | Not yet started
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Pagsangahan | 045642011 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 540925 | 306008 | 846933 | 2012-03-07 | 2012-06-15 | 486832.5 |  | 2nd |  | Completed | 2012-05-26
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Poblacion | 045642012 | Construction of 500 Ln.m Covered Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 500 | ln.m | 828503 | 533951 | 1362454 | 2012-02-21 | 2012-05-15 | 745652.7 |  | 2nd |  | Completed | 2012-04-24
M1 | IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Silongin | 045642014 | Concreting of 1,200 Ln.m FMR w/ Line Canal | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 1523071 | 469762 | 1992833 | 2012-03-19 |  | 1370763.9 |  | 2nd |  | On-going | 2012-04-25
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Bani | 045644003 | Construction of 1.8 Km. FMR w/ 80 sq.m PCCP 36 Ln.m RCPC & 20m Spillway | 1 | Basic Access Infrastructure | Road | 1.8 | kms | 2689826.08 | 531373.92 | 3221200 | 2012-05-15 |  | 2151860.87 |  | 1st |  | On-going | 2012-07-14
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Binay | 045644004 | Construction of Level II Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 2761652.17 | 583947.83 | 3345600 | 2012-06-25 |  | 2209321.74 |  | 1st |  | On-going | 2012-09-23
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Calwit | 045644008 | Improvement of 600m FMR w/ 1,200 sq.m PCCP | 1 | Basic Access Infrastructure | Road | 0.6 | kms | 1344434.78 | 342665.22 | 1687100 | 2012-05-21 |  | 1209991.3 |  | 2nd |  | On-going | 2012-07-20
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Guinhalinan | 045644009 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1046343.48 | 368956.52 | 1415300 | 2012-02-07 | 2012-07-15 | 941123.08 |  | 2nd | Elem | Completed | 2012-04-27
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Lacdayan | 045644010 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 638486.96 | 193013.04 | 831500 | 2012-05-14 |  | 574637.88 |  | 2nd |  | On-going | 2012-08-02
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Manlampong | 045644012 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 622526.09 | 198878.91 | 821405 | 2012-02-06 | 2012-07-15 | 560259.19 |  | 2nd |  | Completed | 2012-04-26
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Rizal | 045644018 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1005817.39 | 668539.13 | 1674356.52 | 2012-03-08 | 2012-07-15 | 1005817.39 |  | 3rd | Elem | Completed | 2012-05-27
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | San Vicente | 045644021 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 599826.09 | 247673.91 | 847500 | 2012-05-15 |  | 479860.87 |  | 1st |  | On-going | 2012-08-03
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Vigo Central | 045644022 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 642000 | 199800 | 841800 | 2012-04-28 |  | 575134.13 |  | 2nd |  | On-going | 2012-07-17
M1 | IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Villa Aurin (Pinagsama) | 045644023 | Construction of Level II Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 649086.96 | 170113.04 | 819200 | 2012-04-16 |  | 584178.27 |  | 2nd |  | On-going | 2012-06-15
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bacong | 097223012 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 64 | ln.m | 1046101.42 | 307527.78 | 1353629.2 |  |  | 836881.14 |  | 1st |  | Not yet started
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Banganon | 097223001 | Construction of 1 Unit CL Pre-School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 604132.01 | 166685.39 | 770817.4 | 2012-05-01 |  | 483281.61 |  | 1st | PS | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Canupong | 097223008 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 164.04 | sq. m | 1032328.5 | 295097 | 1327425.5 | 2012-04-01 |  | 825862.8 |  | 1st | Elem | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Cocob | 097223002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 556057.91 | 149123 | 705180.91 | 2012-05-01 |  | 444870.33 |  | 1st |  | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Datagan | 097223016 | Construction of Water System Level II (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 1186397.57 | 305379.73 | 1491777.3 |  |  | 851248 |  | 1st |  | Not yet started
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Immaculada Concepcion | 097223032 | Construction of 1 Unit CL School Building (HS) | 1 | Basic Social Services | School | 166.5 | sq. m | 1028926.5 | 294527 | 1323453.5 | 2012-04-01 |  | 823141.2 | No movement as of May 31, 2012 reports | 1st | HS | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Mamawan | 097223009 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1027732.5 | 294610 | 1322342.5 | 2012-05-01 |  | 822186 |  | 1st | Elem | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Map | 097223020 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 608489.81 | 167275.39 | 775765.2 | 2012-05-01 |  | 486767.85 |  | 1st | PS | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | New Dapitan | 097223022 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1030500.5 | 294842 | 1325342.5 | 2012-04-01 |  | 824400.4 |  | 1st | Elem | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Panganuran | 097223006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 574922.91 | 137258 | 712180.91 | 2012-05-01 |  | 460966.91 |  | 1st |  | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Pitawe | 097223007 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 574922.91 | 137258 | 712180.91 | 2012-06-01 |  | 459938.33 |  | 1st |  | On-going
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Salvador | 097223024 | Construction of Brgy. Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 10 | ln.m | 825997.1 | 177069.36 | 1003066.46 |  |  | 412918.23 |  | 1st |  | Not yet started
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Isidro | 097223025 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 268875.1 | 103410 | 372285.1 | 2012-07-01 |  | 215100.08 |  | 1st |  | On-going
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Juan | 097223026 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 166.5 | sq. m | 1028080.5 | 294262 | 1322342.5 | 2012-05-01 |  | 822464.4 |  | 1st | HS | On-going
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sas | 097223030 | Road Construction | 1 | Basic Access Infrastructure | Road | 2.95 | kms | 2511395.29 | 581774.79 | 3093170.08 |  |  | 1255697.64 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sibalic | 097223010 | Road Construction | 1 | Basic Access Infrastructure | Road | 1.8 | kms | 1382659.9 | 564989.53 | 1947649.43 |  |  | 1106127.92 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sto. Niño | 097223029 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 166.5 | sq. m | 1028760.5 | 294582 | 1323342.5 | 2012-05-01 |  | 823008.4 |  | 1st | HS | On-going
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Botong | 097227002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 572275.82 | 97142.85 | 669418.67 | 2011-01-25 | 2011-05-31 | 571122.56 |  | 2nd |  | Completed | 2011-04-10
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Daniel Maing | 097227004 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 159.72 | sq. m | 925793.65 | 129680.35 | 1055474 | 2011-02-24 | 2011-05-31 | 863771.3 |  | 2nd | Elem | Completed | 2011-06-24
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Fatima | 097227005 | Construction of Multi-Purpose Trading Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 77.7 | sq.m | 507981.15 | 125780.35 | 633761.5 | 2011-02-14 | 2011-06-30 | 507492.07 |  | 2nd |  | Completed | 2011-04-30
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Gatas | 097227006 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 120 | sq. m | 930793.15 | 124680.35 | 1055473.5 | 2011-01-31 | 2011-06-30 | 845997.02 |  | 2nd | HS | Completed | 2011-05-31
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Marcelo | 097227008 | Construction of Spill Way | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 80 | ln.m | 339990.11 | 104955.35 | 444945.46 | 2011-02-15 | 2011-06-30 | 305991.1 |  | 2nd |  | Completed | 2011-04-01
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | New Calamba | 097227009 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 558810.15 | 163892.85 | 722703 | 2011-01-28 | 2011-07-30 | 550889.15 |  | 2nd |  | Completed | 2011-04-18
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Palalian | 097227010 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 120 | sq. m | 880793.15 | 174680.35 | 1055473.5 | 2011-02-23 | 2011-05-31 | 804717.65 |  | 2nd | Elem | Completed | 2011-06-23
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Paraiso | 097227011 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 120 | sq. m | 927953.15 | 144680.35 | 1072633.5 | 2011-02-22 | 2011-05-31 | 901588.25 |  | 2nd | Elem | Completed | 2011-06-22
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Pianon | 097227012 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 608810.15 | 113892.85 | 722703 | 2011-02-11 | 2011-07-30 | 600922.65 |  | 2nd |  | Completed | 2011-05-02
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | San Jose | 097227013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 507275.82 | 157142.85 | 664418.67 | 2011-02-11 | 2011-05-31 | 503182.01 |  | 2nd |  | Completed | 2011-04-26
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Balok | 097203001 | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 663971.6 | 303323.59 | 967295.19 | 2011-06-01 | 2011-07-30 | 622589.45 | From F1-M1 | 2nd |  | Completed | 2011-07-01
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Biniray | 097203003 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 572747.4 | 127452.6 | 700200 | 2011-07-12 | 2011-07-30 | 543363 | From F1-M1 | 1st |  | Completed | 2011-09-10
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Brgy. Dos | 097203017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 543056.29 | 112943.71 | 656000 | 2011-05-17 | 2011-07-30 | 515301.19 | From F1-M1 | 2nd |  | Completed | 2011-07-16
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Carupay | 097203025 | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 507563.62 | 168166.5 | 675730.12 | 2011-06-04 | 2011-08-15 | 471566.21 | From F1-M1 | 2nd |  | Completed | 2011-06-24
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Dabiak | 097203006 | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 489412.16 | 173166.5 | 662578.66 | 2011-06-04 | 2011-07-30 | 453414.75 | From F1-M1 | 2nd |  | Completed | 2011-06-24
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Dr. Jose Rizal | 097203007 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 998342.31 | 114035.12 | 1112377.43 | 2011-05-30 | 2011-07-30 | 963901 | From F1-M1 | 2nd | Elem | Completed | 2011-08-22
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Fimagas | 097203008 | Construction of Hanging Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 42 | ln.m | 1667242.74 | 330757.26 | 1998000 | 2011-06-08 | 2011-07-30 | 1598792.96 | From F1-M1 | 1st |  | Completed | 2011-07-31
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Malasay | 097203010 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 572747.4 | 156452.61 | 729200.01 | 2011-05-24 | 2011-07-30 | 543363 | From F1(KC 1 Savings) to M1 (WB-AF) | 2nd |  | Completed | 2011-07-23
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Malugas | 097203009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 543056.3 | 131943.7 | 675000 | 2011-05-19 | 2011-08-15 | 515301.2 | From F1-M1 | 2nd |  | Completed | 2011-07-18
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Matam | 097203011 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 998342.31 | 123185.12 | 1121527.43 | 2011-05-31 | 2011-08-23 | 963901 | From F1-M1 | 2nd | Elem | Completed | 2011-08-23
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Miatan | 097203013 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 998342.31 | 124335.12 | 1122677.43 | 2011-05-18 | 2011-08-10 | 998342.31 | From F1-M1 | 3rd | Elem | Completed | 2011-08-10
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Nanginan | 097203014 | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 424412.16 | 196166.5 | 620578.66 | 2011-06-02 | 2011-07-30 | 388414.75 | From F1-M1 | 2nd |  | Completed | 2011-06-22
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Patik | 097203028 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 160.2 | sq. m | 998250.92 | 120335.12 | 1118586.04 | 2011-05-30 | 2011-08-22 | 963901 | From F1-M1 | 1st | HS | Completed | 2011-08-22
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | San Antonio | 097203018 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 572747.4 | 117452.6 | 690200 | 2011-03-22 | 2011-06-30 | 543363 | From F1-M1 | 2nd |  | Completed | 2011-05-31
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | San Vicente | 097203030 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 160.95 | sq. m | 998342.31 | 118610.12 | 1116952.43 | 2011-05-31 | 2011-07-30 | 963901 | From F1-M1 | 2nd | HS | Completed | 2011-08-23
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sanao | 097203029 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 543056.3 | 131943.7 | 675000 | 2011-05-17 | 2011-07-30 | 515301.11 | From F1-M1 | 2nd |  | Completed | 2011-07-16
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Seroan | 097203020 | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 424412.16 | 228166.5 | 652578.66 | 2011-06-03 | 2011-07-30 | 388414.75 | From F1-M1 | 2nd |  | Completed | 2011-06-23
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sinuyak | 097203022 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 572747.4 | 141452.6 | 714200 | 2011-05-18 | 2011-07-30 | 543363 | From F1-M1 | 2nd |  | Completed | 2011-07-19
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sto. Niño | 097203031 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 998250.92 | 119865.12 | 1118116.04 | 2011-05-23 | 2011-08-15 | 963901 | From F1-M1 | 2nd | Elem | Completed | 2011-08-15
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Tuburan | 097203024 | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 912956 | 366556.9 | 1279512.9 | 2011-05-24 | 2011-07-30 | 867549.5 | From F1-M1 | 2nd |  | Completed | 2011-07-03
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Leon Postigo ( Bacungan) | 097226 | Midatag | 097226007 | Road Improvement | 1 | Basic Access Infrastructure | Road | 1.6 | kms | 3351028 | 707550 | 4058578 |  |  | 0 |  |  |  | Not yet started
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Leon Postigo ( Bacungan) | 097226 | Bacungan Poblacion | 097226001 | Construction of 2 Units 2 CL School Building (Elem) | 1 | Basic Social Services | School | 333 | sq. m | 1673730 | 935290 | 2609020 | 2012-02-02 | 2012-06-15 | 1673730 |  | 2nd | Elem | Completed | 2012-06-01
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Leon Postigo ( Bacungan) | 097226 | Tiogan | 097226016 | Road Improvement | 1 | Basic Access Infrastructure | Road | 3.5 | kms | 3075242 | 563719 | 3638961 |  |  | 0 |  |  |  | Not yet started
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Alvenda | 097208001 | Construction of Trading Post (Multi-Purpose Building) | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 96 | sq.m | 640197 | 252763 | 892960 | 2012-03-01 |  | 512157.6 |  | 1st |  | On-going | 2012-05-15
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Diolen | 097208004 | Construction of 1 Unit 2 CL Primary School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1087933 | 346595 | 1434528 | 2012-02-27 |  | 870395 |  | 1st | Elem | On-going | 2012-05-21 | 0
M1 | IV-A | 04 | Quezon | 0456 | Perez | 045633 | Villamanzano Norte & villamanzano Sur | 045633014 | Construction of Drainage Canal w/ 600sq.m PCCP & Intermittent Re-gravelling | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 956476.33 | 211973.67 | 1168450 | 2012-05-14 |  | 765181.06 |  | 1st |  | On-going | 2012-07-13
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | G. Bergado |  | Brgy. Road Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.48 | kms | 2473275 | 567981 | 3041256 | 2012-06-01 |  | 0 | No movement as of July 31, 2012 |  |  | On-going |  | 0
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Newland | 097208007 | Construction of Women's Center (Multi- Purpose Building) | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 96 | sq.m | 637690 | 252763 | 890453 | 2012-03-03 |  | 510152 |  | 1st |  | On-going | 2012-05-17
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Paso Rio | 097208009 | Construction of Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 500 | ln.m | 980607.5 | 349400 | 1330007.5 | 2012-03-05 | 2012-05-15 | 490303.75 |  | 1st |  | Completed | 2012-06-03 | 0
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Poblacion | 097208010 | Construction of Training Center (Mulit-Purpose Building) | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 63 | sq.m | 497628 | 300760 | 798388 | 2012-03-02 |  | 398102 |  | 1st |  | On-going | 2012-05-29 | 0
M1 | IX | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Totongon | 097208013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 549566 | 250345 | 799911 | 2012-03-06 |  | 439332 |  | 1st |  | On-going | 2012-05-20 | 0
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Balok | 097215001 | Brgy. Road Concreting of Critical Slope w/ Line Canal | 1 | Basic Access Infrastructure | Road | 0.28 | kms | 1612622.75 | 283093.5 | 1895716.25 | 2012-04-23 |  | 806311.38 |  | 1st |  | On-going | 2012-05-28
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Denoyan | 097215004 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 130 | ln.m | 2313210.26 | 513137.74 | 2826348 |  |  | 1850568.21 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Diongan | 097215005 | Construction of Barangay Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 45 | ln.m | 1660745.15 | 296173.5 | 1956918.65 | 2012-06-06 |  | 830372.58 |  | 1st |  | On-going | 2012-08-22
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Dumpilas | 097215007 | Brgy. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1220102.89 | 278847 | 1498949.89 | 2012-06-19 |  | 610051.44 |  | 1st |  | On-going | 2012-08-18
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Gunyan | 097215011 | Construction of Line Canal w/ Gravelling | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 380 | ln.m | 1169715.47 | 207513.81 | 1377229.28 |  |  | 584857.74 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Litolet | 097215012 | Brgy. Road Concreting w/ Line Canal | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 2118403.86 | 389440 | 2507843.86 |  |  | 1059201.93 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Pange | 097215016 | Construction of 2 Units Single Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 905199.62 | 161073.6 | 1066273.22 | 2012-04-19 |  | 452599.81 |  | 1st |  | On-going | 2012-06-01
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Baking | 097303001 | Construction of Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 90 | ln.m | 1612944.8 | 369345 | 1982289.8 | 2012-07-23 |  | 806472.4 |  | 1st |  | On-going | 2012-10-21
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Balukbahan | 097303002 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 648408 | 147700 | 796108 | 2012-05-14 |  | 518726.4 |  | 1st |  | On-going | 2012-07-13 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Bantal | 097303004 | Road Improvement (Gravelling) | 1 | Basic Access Infrastructure | Road | 0.65 | kms | 538845.5 | 151575 | 690420.5 |  |  | 269422.75 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Bobuan | 097303005 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 637643 | 151740 | 789383 | 2012-02-17 |  | 510112 |  | 1st |  | On-going | 2012-04-17 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Camp Blessing | 097303006 | Road Improvement w/ Concreting | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 558006.5 | 114582.5 | 672589 | 2012-07-08 |  | 279003.25 |  | 1st |  | On-going | 2012-08-14
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Canoayan | 097303007 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 649469 | 145365 | 794834 | 2012-06-20 |  | 519575.2 |  | 1st | Elem | On-going | 2012-08-19 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Conacon | 097303008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 634433 | 146595 | 781028 | 2012-03-13 |  | 507546.4 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-05-12 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Damit | 097303010 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 645792 | 243617.5 | 889409.5 | 2012-06-01 |  | 516633.6 |  | 1st |  | On-going
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Datagan | 097303011 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 639949 | 151740 | 791689 | 2012-06-26 |  | 511959 |  | 1st |  | On-going | 2012-08-25 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Deporehan | 097303013 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 661986 | 172200 | 834186 | 2012-02-28 |  | 529588 |  | 1st |  | On-going | 2012-04-28 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Dimalinao | 097303015 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 644457 | 145825 | 790282 | 2012-02-29 |  | 515565.6 |  | 1st | Elem | On-going | 2012-04-29 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Depili | 097303016 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 648408 | 147700 | 796108 | 2012-02-29 |  | 499544 |  | 1st |  | On-going | 2012-04-29 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Kahayagan | 097303017 | Construction of Trading Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 180 | sq.m | 835768 | 228755 | 1064523 |  |  | 668614.4 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Kanipaan | 097303018 | Sectional Road Concreting | 1 | Basic Access Infrastructure | Road | 0.22 | kms | 703733 | 144780 | 848513 | 2012-06-09 |  | 351866.5 |  | 1st |  | On-going | 2012-07-16
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Lamare | 097303019 | Sectional Road Concreting | 1 | Basic Access Infrastructure | Road | 0.174 | kms | 662277.5 | 156292.5 | 818570 | 2012-06-02 |  | 331138.75 |  | 1st |  | On-going | 2012-07-17
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Matin-ao | 097303021 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 647635 | 148700 | 796335 | 2012-05-21 |  | 518108 |  | 1st |  | On-going | 2012-07-20 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Matun-og | 097303022 | Road Improvement w/ Sectional Concreting | 1 | Basic Access Infrastructure | Road | 0.55 | kms | 731667.5 | 192240 | 923907.5 | 2012-07-17 |  | 365833.75 |  | 1st |  | On-going | 2012-08-24
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Pulang Bato | 097303024 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 642280 | 174240 | 816520 | 2012-02-28 |  | 513824 |  | 1st |  | On-going | 2012-04-28
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Sigacad | 097303026 | Improvement Barangay Corn Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 448411 | 130660 | 579071 | 2012-06-05 |  | 358728.8 |  | 1st |  | On-going | 2012-08-04
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Supon | 097303027 | Sectional Road Concreting | 1 | Basic Access Infrastructure | Road | 0.248 | kms | 678456.5 | 147625 | 826081.5 | 2012-07-17 |  | 339228.25 |  | 1st |  | On-going | 2012-09-01
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Bacawan | 097306001 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 737494 | 137030.8 | 874524.8 | 2012-05-28 |  | 532732 |  | 1st | PS | On-going | 2012-07-23
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Benuatan | 097306002 | Construction of 1 Unit 1 CL School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 722894 | 134830.8 | 857724.8 | 2012-06-23 |  | 520104.16 |  | 1st | PS | On-going | 2012-07-18
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Beray | 097306003 | Brgy. Road Improvement w/ Concreting in Critical Slope | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 729865 | 122081.23 | 851946.23 | 2012-04-30 |  | 364932.5 |  | 1st |  | On-going | 2012-06-15
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Don Jose | 097306032 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 652669 | 124027.34 | 776696.34 | 2012-02-08 | 2012-06-15 | 522135.2 |  | 1st |  | Completed | 2012-04-04
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Dongos | 097306004 | Brgy. Road Concreting 200 Ln.m in Critical Slope | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 774641.4 | 137130.49 | 911771.89 | 2012-06-01 |  | 387320.7 | No movement as of July 31, 2012 | 1st |  | On-going
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | East Migpulao | 097306015 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 645696.86 | 116420 | 762116.86 | 2012-02-29 | 2012-07-15 | 516557.49 |  | 1st |  | Completed | 2012-04-29
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Guinicolalay | 097306005 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1189314.53 | 187872.93 | 1377187.46 | 2012-05-28 |  | 951451.62 |  | 1st |  | On-going | 2012-07-31
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Ignacio Garrata | 097306018 | Brgy. Road Improvement w/ Concreting in Critical Slope | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 638426.4 | 108701.89 | 747128.29 | 2012-03-23 |  | 319213.2 |  | 1st |  | On-going | 2012-04-29
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Kinacap | 097306006 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.7 | kms | 644071.35 | 105000 | 749071.35 | 2012-05-04 |  | 322035.67 |  | 1st |  | On-going | 2012-06-12
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Legarda Tres | 097306008 | Brgy. Road Improvement w/ Line Canal | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1146788.38 | 215950 | 1362738.38 | 2012-06-01 |  | 534835.19 |  | 1st |  | On-going | 2012-07-03
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Legardo Uno | 097306009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 652669 | 124027.34 | 776696.34 | 2012-02-16 |  | 522135.2 |  | 1st |  | On-going | 2012-04-12
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Lower Dimaya | 097306013 | Road Improvement w/ 300 Ln.m Line Canal | 1 | Basic Access Infrastructure | Road | 0.22 | kms | 661104.47 | 133700 | 794804.47 | 2012-04-27 | 2012-07-15 | 309922.74 |  | 1st |  | Completed | 2012-06-05
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Ludiong | 097306014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 682020 | 128427.34 | 810447.34 | 2012-02-27 |  | 545616 |  | 1st |  | On-going | 2012-04-23
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Nangka | 097306017 | Construction of Water System Level II (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 409885.24 | 75800 | 485685.24 | 2012-06-29 |  | 331937.41 |  | 1st |  | On-going | 2012-08-07
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Nian | 097306034 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 670470 | 126433.62 | 796903.62 | 2012-02-13 |  | 603423 |  | 2nd |  | On-going | 2012-04-09
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Old Mirapao | 097306019 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 543439.15 | 88389.34 | 631828.49 | 2012-04-19 | 2012-07-15 | 501621.21 |  | 2nd |  | Completed | 2012-06-16
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Poblacion | 097306020 | Brgy. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.26 | kms | 986728.78 | 172360 | 1159088.78 | 2012-04-10 |  | 493364.39 |  | 1st |  | On-going | 2012-06-15
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Proper Dimaya | 097306021 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 626365.25 | 99990 | 726355.25 | 2012-04-25 | 2012-06-15 | 571698.14 |  | 2nd |  | Completed | 2012-06-13
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Upper Dimaya | 097306029 | Brgy. Road Improvement w/ Concreting in Critical Slope | 1 | Basic Access Infrastructure | Road | 0.72 | kms | 1009071.12 | 163909.08 | 1172980.2 | 2012-04-30 |  | 504535.56 |  | 1st |  | On-going | 2012-07-03
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Upper Sibul | 097306030 | Road Improvement w/ 174 Ln.m Tirepath | 1 | Basic Access Infrastructure | Road | 0.6 | kms | 870989.2 | 142609.95 | 1013599.15 | 2012-06-01 |  | 435494.6 |  | 1st |  | On-going
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Bagong Kauswagan | 097308030 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 583461.56 | 197920 | 781381.56 | 2012-02-14 |  | 466769.24 |  | 1st |  | On-going | 2012-04-14
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Bagong Silang | 097308047 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 579119.9 | 195020 | 774139.9 | 2012-03-30 |  | 463295.92 |  | 1st |  | On-going | 2012-05-29
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Bag-ong Valencia | 097308002 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 217943 | 126732.5 | 344675.5 | 2012-02-08 | 2012-03-15 | 174354.4 |  | 1st |  | Completed | 2012-03-01
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Calumanggi | 097308004 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 593480.06 | 197920 | 791400.06 | 2012-04-18 |  | 474784.04 |  | 1st |  | On-going | 2012-06-17
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Danlungan | 097308006 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 598472 | 197975 | 796447 |  |  | 483244 |  | 1st | Elem | Not yet started |  | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Dapiwak | 097308048 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 550501.6 | 210184.4 | 760686 | 2012-04-19 |  | 440401.28 |  | 1st |  | On-going | 2012-06-18
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Datu Totocan | 097308007 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 598022 | 193490 | 791512 | 2012-06-25 |  | 478417.6 | Steel Truss | 1st | Elem | On-going | 2012-08-29 | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Ditulan | 097308009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 587840.56 | 197920 | 785760.56 | 2012-07-07 |  | 470272.44 | Steel Truss | 1st |  | On-going | 2012-10-03
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Dulop | 097308011 | Construction of Water System Level II (Gravity Type) | 1 | Basic Social Services | Water System | 1 | system | 1491349 | 1168656 | 2660005 | 2012-05-25 |  | 1058896 |  | 1st |  | On-going | 2012-09-11
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Guintananan | 097308012 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 210626.36 | 139073.14 | 349699.5 | 2012-03-21 | 2012-05-20 | 197061.36 |  | 2nd |  | Completed | 2012-05-20
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Gumpingan | 097308014 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 600887.56 | 197920 | 798807.56 | 2012-02-27 |  | 480710.04 |  | 1st |  | On-going | 2012-04-27
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Labangon | 097308049 | Construction of 1 Unit 1 CL School Building (HS) (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 574316 | 203807 | 778123 |  |  | 459452.8 | Steel Truss | 1st | HS | Not yet started |  | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Libertad | 097308016 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 302315 | 133525 | 435840 | 2012-02-07 | 2012-04-15 | 301764.88 |  | 2nd |  | Completed | 2012-02-29
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Lipawan | 097308018 | Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.95 | kms | 921450.96 | 205455.68 | 1126906.64 |  |  | 460725.48 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Lower Landing | 097308019 | Construction of Brgy. Health Station (Steel Truss) | 1 | Basic Social Services | Health Station | 51 | sq.m | 572814.06 | 204475 | 777289.06 | 2012-04-23 |  | 458251.24 |  | 1st |  | On-going | 2012-06-22
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Lower Timonan | 097308020 | Construction of 1 Unit 1 CL Secondary School Building (HS) | 1 | Basic Social Services | School | 63 | sq. m | 602165 | 196545 | 798710 | 2012-06-01 |  | 481732 | Steel Truss | 1st | HS | On-going |  | 0
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Macasing | 097308021 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 611338.56 | 197920 | 809258.56 | 2012-05-31 |  | 489070.84 |  | 1st |  | On-going | 2012-07-30
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Mahayahay | 097308022 | Sectional Road Concreting @ Critical Slope | 1 | Basic Access Infrastructure | Road | 0.32 | kms | 1219066.85 | 347059.24 | 1566126.09 |  |  | 609533.42 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Malagalad | 097308023 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 660926.7 | 201545 | 862471.7 | 2012-03-15 |  | 528741.36 |  | 1st | Elem | On-going | 2012-05-19
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Maralag | 097308025 | Improvement of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 40 | ln.m | 445830.05 | 165097.14 | 610927.19 | 2012-03-14 |  | 356664.05 |  | 1st |  | On-going | 2012-04-03
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Marangan | 097308026 | Sectional Road Concreting @ Critical Slope | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 696759.68 | 182128.1 | 878887.78 |  |  | 348379.84 |  | 1st |  | Not yet started
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | New Basak | 097308027 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 270733.43 | 128680.07 | 399413.5 | 2012-02-07 | 2012-05-15 | 216586.75 |  | 1st |  | Completed | 2012-02-29
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Salvador | 097308033 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 565428.56 | 247920 | 813348.56 | 2012-05-12 |  | 452342.84 |  | 1st |  | On-going | 2012-07-11
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Juan | 097308050 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 533472 | 229425.4 | 762897.4 | 2012-07-16 |  | 426777.6 |  | 1st |  | On-going | 2012-09-14
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Pablo | 097308034 | Improvement of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 334777.35 | 205580 | 540357.35 | 2012-02-06 |  | 301299.61 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-03-01
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Pedro | 097308035 | Improvement of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 280 | ln.m | 220542.6 | 193610 | 414152.6 | 2012-03-26 |  | 198488.34 |  | 2nd |  | On-going | 2012-04-19
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Vicente | 097308037 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 597543.56 | 197920 | 795463.56 | 2012-02-27 |  | 478034.84 |  | 1st |  | On-going | 2012-04-27
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Senote | 097308038 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 595291.56 | 197920 | 793211.56 | 2012-03-16 |  | 476233.24 |  | 1st |  | On-going | 2012-05-15
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Sinonok | 097308039 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 723007.7 | 201545 | 924552.7 | 2012-05-19 |  | 578406.16 |  | 1st | Elem | On-going | 2012-07-23
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Sunop | 097308041 | Construction of Brgy. Road (Opening) | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 2773505.56 | 640404.94 | 3413910.5 |  |  | 1323875.5 |  | 1st |  | Not yet started
M1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Tagun | 097308042 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 620744.56 | 197920 | 818664.56 | 2012-04-16 |  | 496595.64 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-15
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Upper Landing | 097308045 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 562421.56 | 208200 | 770621.56 | 2012-05-04 |  | 449937.24 | Steel Truss | 1st |  | On-going | 2012-07-31
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Upper Timonan | 097308046 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 631166.3 | 201545 | 832711.3 | 2012-02-16 |  | 504933.04 |  | 1st | Elem | On-going
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bagong Kahayag | 097333002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 599890 | 128510 | 728400 | 2011-03-23 | 2011-08-15 | 541927.14 |  | 2nd |  | Completed | 2011-06-06
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bululawan | 097333004 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 160.95 | sq. m | 1081386.35 | 216244.65 | 1297631 | 2011-03-25 | 2011-10-15 | 1038555.23 |  | 2nd | HS | Completed | 2011-06-13
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Dagum | 097333005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 618690 | 131210 | 749900 | 2011-03-24 | 2011-07-30 | 582690 |  | 2nd |  | Completed | 2011-06-08
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Gasa | 097333006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 618165 | 131735 | 749900 | 2011-03-18 | 2011-08-15 | 602755.21 |  | 2nd |  | Completed | 2011-06-01
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Gatub | 097333007 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 628312.5 | 136937.5 | 765250 | 2011-03-22 | 2011-08-15 | 628312.5 |  | 3rd |  | Completed | 2011-06-10
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Matalang | 097333010 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 1287043.65 | 134982.35 | 1422026 | 2011-03-21 | 2011-10-15 | 1287043.66 |  | 2nd | Elem | Completed | 2011-06-09
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Sapang Pinoles | 097333011 | Construction of Sitio Libas Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 957350 | 193650 | 1151000 | 2011-03-28 | 2011-08-15 | 765880 |  | 1st |  | Completed | 2011-05-29
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Tiwales | 097333013 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 609272.5 | 133577.5 | 742850 | 2011-03-23 | 2011-08-15 | 590512.94 |  | 3rd |  | Completed | 2011-06-11
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Tubod | 097333014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 599890 | 128510 | 728400 | 2011-03-22 | 2011-07-31 | 539901 |  | 2nd |  | Completed | 2011-06-05
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Bulawan | 097313002 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 537999 | 125866 | 663865 | 2011-03-07 | 2011-07-30 | 533778.33 |  | 3rd | Elem | Completed | 2011-05-16
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Carpoc | 097313003 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 565439 | 104053 | 669492 | 2011-03-15 | 2011-08-15 | 562925.43 |  | 3rd |  | Completed | 2011-05-10
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Danganan | 097313004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 585439 | 104053 | 689492 | 2011-03-17 | 2011-09-15 | 579222.04 |  | 3rd |  | Completed | 2011-05-12
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Dansal | 097313005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 570439 | 104053 | 674492 | 2011-03-10 | 2011-08-15 | 550949.93 |  | 3rd |  | Completed | 2011-05-05
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Dumara | 097313007 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 598000 | 100864 | 698864 | 2011-02-01 | 2011-08-15 | 572598.07 |  | 2nd | Elem | Completed | 2011-04-12
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Lenokmadalum | 097313010 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.5 | kms | 630299 | 139446 | 769745 | 2011-02-17 | 2011-07-30 | 630299 |  | 3rd |  | Completed | 2011-04-18
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Luanan | 097313011 | Construction of Multi-Purpose Trading Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 120 | sq.m | 719130 | 117669 | 836799 | 2011-02-09 | 2011-08-15 | 718608.49 |  | 2nd |  | Completed | 2011-04-06
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Lubusan | 097313012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 570439 | 104053 | 674492 | 2011-03-11 | 2011-08-15 | 570439 |  | 3rd |  | Completed | 2011-05-06
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Mahalingeb | 097313013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 575439 | 104053 | 679492 | 2011-03-21 | 2011-08-15 | 574951.09 |  | 3rd |  | Completed | 2011-05-16
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Mandeg | 097313014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 599299 | 104053 | 703352 | 2011-02-15 | 2011-08-15 | 596527 |  | 3rd |  | Completed | 2011-04-12
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Maralag | 097313015 | Construction of Multi-Purpose Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 449766 | 82043 | 531809 | 2011-03-03 | 2011-04-30 | 449765.4 |  | 2nd |  | Completed | 2011-04-07
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Maruing | 097313016 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 548036 | 115098 | 663134 | 2011-04-30 | 2011-09-15 | 548036 |  | 3rd | Elem | Completed | 2011-05-31
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Molum | 097313017 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 542999 | 120866 | 663865 | 2011-03-06 | 2011-07-30 | 542999 |  | 3rd | Elem | Completed | 2011-05-15
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pampang | 097313018 | Construction of 1 Unit 1 Cl School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 588000 | 100864 | 688864 | 2011-03-26 | 2011-07-30 | 588000 |  | 3rd | Elem | Completed | 2011-06-04
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pantad | 097313019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 565439 | 129053 | 694492 | 2011-03-17 | 2011-07-30 | 542247.91 |  | 3rd |  | Completed | 2011-05-12
G1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pingalay | 097313020 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 217960 | 463887 | 681847 | 2011-02-23 | 2011-07-30 | 217960 |  | 3rd | Elem | Completed | 2011-05-04
M1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | San Jose | 097313024 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 598000 | 100864 | 698864 | 2011-03-25 | 2011-06-30 | 597997.45 |  | 3rd | Elem | Completed | 2011-06-03
M1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tabon | 097313027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 615439 | 104053 | 719492 | 2011-03-16 | 2011-07-30 | 597636 |  | 3rd |  | Completed | 2011-05-11
M1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Talabab | 097313028 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 588000 | 100864 | 688864 | 2011-03-18 | 2011-09-15 | 588000 |  | 3rd | Elem | Completed | 2011-05-27
M1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tiguha | 097313029 | Construction of 1 Unit 1 CL School Building (HS) | 1 | Basic Social Services | School | 87.35 | sq. m | 588000 | 100864 | 688864 | 2011-03-17 | 2011-07-30 | 588000 |  | 3rd | HS | Completed | 2011-05-26
M1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tininghalang | 097313030 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 588000 | 100864 | 688864 | 2011-03-16 | 2011-07-30 | 588000 |  | 3rd | Elem | Completed | 2011-05-25
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tipasan | 097313031 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 570439 | 104053 | 674492 | 2011-03-12 | 2011-09-15 | 569711.54 |  | 3rd |  | Completed | 2011-05-07
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tugaya | 097313033 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 588000 | 100864 | 688864 | 2011-03-07 | 2011-07-30 | 588000 |  | 3rd | Elem | Completed | 2011-05-16
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Bacahan | 097318001 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 874459.89 | 256745 | 1131204.89 | 2012-07-01 |  | 699567.91 |  | 1st |  | On-going
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Buloron | 097318005 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 971983.46 | 265318.71 | 1237302.17 | 2012-01-25 | 2012-05-15 | 777586.76 |  | 1st | Elem | Completed | 2012-03-18
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Cabaloran | 097318030 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 660608 | 152682.54 | 813290.54 | 2012-01-31 | 2012-05-15 | 657553.43 |  | 2nd | Elem | Completed | 2012-03-16
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Canipay Norte | 097318007 | Concrete Pavement w/ Storage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 492 | sq.m | 214962.65 | 320605 | 535567.65 | 2012-05-08 | 2012-07-15 | 171970.13 | 492 sq.m including storage room (4x4=16 sq.m) | 1st |  | Completed | 2012-06-18
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Dumalinao | 097318033 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 909873.66 | 272330.34 | 1182204 | 2012-05-03 |  | 818886.29 |  | 2nd | Elem | On-going | 2012-06-25
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Golictop | 097318011 | Sectional Road Concreting | 1 | Basic Access Infrastructure | Road | 1.18 | kms | 2709939.36 | 571293.5 | 3281232.86 | 2012-02-29 |  | 1354969.68 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-17
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Guinabot | 097318035 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 618740.17 | 204722.58 | 823462.75 |  |  | 500385.28 |  | 1st |  | Not yet started
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Guma | 097318041 | Construction of Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 23 | ln.m | 802522.2 | 185275 | 987797.2 | 2012-05-01 |  | 642017.76 | No movment as of May 31, 2012 reports | 1st |  | On-going
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Kahayagan | 097318012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 625404.49 | 167445 | 792849.49 | 2012-03-10 | 2012-06-15 | 500323.59 |  | 1st |  | Completed | 2012-04-29
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Licuro-an | 097318038 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 590229 | 153185 | 743414 | 2012-06-01 |  | 472183.2 |  | 1st |  | On-going
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Lumpunid | 097318016 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1594232 | 449690 | 2043922 | 2012-05-02 |  | 1275385.6 |  | 1st |  | On-going | 2012-08-03
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | New Katipunan | 097318018 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 660928.94 | 312385.24 | 973314.18 | 2012-07-01 |  | 515170.77 |  | 1st | Elem | On-going
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Pili | 097318042 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 612734.6 | 167927 | 780661.6 | 2012-06-01 | 2012-07-15 | 551461.14 |  | 2nd |  | Completed | 2012-07-15
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Piwan | 097318021 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 402031.05 | 414611.2 | 816642.25 | 2012-04-11 |  | 309840.26 |  | 1st | Elem | On-going | 2012-05-26
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Poblacion A | 097318022 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1978462 | 575595 | 2554057 | 2012-02-23 |  | 1582769 |  | 1st |  | On-going | 2012-06-03
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Timbaboy | 097318026 | Road Construction | 1 | Basic Access Infrastructure | Road | 0.96 | kms | 1627590.83 | 381990 | 2009580.83 |  |  | 813745.42 |  | 1st |  | Not yet started
F2 | IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Tulbong | 097318027 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 645297.7 | 153565 | 798862.7 | 2012-02-21 | 2012-06-15 | 516238.16 |  | 1st |  | Completed | 2012-04-08
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Bag-ong Misamis | 097325001 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 524836 | 210256 | 735092 | 2011-06-01 | 2011-09-15 | 526846.83 |  | 3rd |  | Completed | 2011-07-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Bubual | 097325002 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204256 | 736243 | 2011-03-02 | 2011-09-15 | 526926.1 |  | 3rd |  | Completed | 2011-05-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Buton | 097325003 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 466836 | 204256 | 671092 | 2011-02-28 | 2011-07-30 | 456902.21 |  | 3rd |  | Completed | 2011-05-14
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Daplayan | 097325005 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq. m | 471212 | 202237 | 673449 | 2011-03-28 | 2011-07-30 | 456722.57 |  | 3rd | Elem | Completed | 2011-05-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kalilangan | 097325006 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq. m | 471212 | 202237 | 673449 | 2011-04-11 | 2011-09-15 | 467300 |  | 3rd | Elem | Completed | 2011-05-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kapamanok | 097325007 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204256 | 736243 | 2011-06-14 | 2011-08-15 | 504958.25 |  | 3rd |  | Completed | 2011-07-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kondum | 097325008 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-03-14 | 2011-09-15 | 509020.22 |  | 3rd |  | Completed | 2011-05-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Lumbayao | 097325009 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-04-26 | 2011-08-15 | 520283.5 |  | 3rd |  | Completed | 2011-07-10
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Mabuhay | 097325010 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-02-01 | 2011-08-15 | 494824 |  | 3rd |  | Completed | 2011-04-15
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Marcos Village | 097325011 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 471212 | 202237 | 673449 | 2011-05-24 | 2011-09-15 | 465926.5 |  | 3rd | Elem | Completed | 2011-07-31
F2 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Miasin | 097325012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 466836 | 204256 | 671092 | 2011-03-31 | 2011-07-30 | 435159.34 |  | 3rd |  | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Molansong | 097325013 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-05-02 | 2011-09-15 | 507862.01 |  | 3rd |  | Completed | 2011-07-16
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pantad | 097325014 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-02-01 | 2011-08-15 | 524574.45 |  | 3rd |  | Completed | 2011-04-17
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pao | 097325015 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-02-26 | 2011-08-15 | 505362.2 |  | 3rd |  | Completed | 2011-05-12
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Payag | 097325016 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-02-01 | 2011-08-15 | 499577.6 |  | 3rd |  | Completed | 2011-04-17
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Poblacion (San Pablo) | 097325017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 466836 | 204256 | 671092 | 2011-03-22 | 2011-07-30 | 421494.9 |  | 3rd |  | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pongapong | 097325018 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 471212 | 202237 | 673449 | 2011-05-02 | 2011-09-15 | 463795 |  | 3rd | Elem | Completed | 2011-07-11
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Sacbulan | 097325021 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 501370 | 214704 | 716074 | 2011-05-24 | 2011-10-15 | 497332 |  | 3rd | Elem | Completed | 2011-08-02
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Sagasan | 097325020 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 471212 | 202237 | 673449 | 2011-03-21 | 2011-09-15 | 450929.5 |  | 3rd | Elem | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | San Juan | 097325029 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 498682 | 208237 | 706919 | 2011-06-07 | 2011-09-15 | 488724.18 |  | 3rd | Elem | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Senior | 097325022 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 471212 | 202237 | 673449 | 2011-06-24 | 2011-10-15 | 451229.75 |  | 3rd | Elem | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Songgoy | 097325023 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 471212 | 202237 | 673449 | 2011-06-07 | 2011-09-15 | 471161.72 |  | 3rd | Elem | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Tandubuay | 097325024 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 466836 | 204256 | 671092 | 2011-03-24 | 2011-08-15 | 462924.8 |  | 3rd |  | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Teniapan | 097325026 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 59.37 | sq.m | 471212 | 202237 | 673449 | 2011-03-24 | 2011-09-15 | 471212 |  | 3rd | Elem | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Ticala Island | 097325025 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 525836 | 204256 | 730092 | 2011-03-29 | 2011-07-30 | 518810.13 |  | 3rd |  | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Tubo-pait | 097325027 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-02-28 | 2011-08-15 | 491323.39 |  | 3rd |  | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Villakapa | 097325028 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 531987 | 204508 | 736495 | 2011-03-10 | 2011-08-15 | 512021.09 |  | 3rd |  | Completed | 2011-05-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Bag-ong Baroy | 097340001 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 641738.5 | 153500 | 795238.5 | 2012-06-08 |  | 513390.8 |  | 1st |  | On-going | 2012-07-28 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Barubuhan | 097340003 | Sectional Road Concreting w/ 2 Spillways & Line Ditch | 1 | Basic Access Infrastructure | Road | 0.24 | kms | 1771064 | 355230.38 | 2126294.38 | 2012-07-05 |  | 855532 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-08-21 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Bulanay | 097340004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 610034.25 | 146153.58 | 756187.83 | 2012-05-26 |  | 488027.4 |  | 1st |  | On-going | 2012-07-15 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Clustered Brgys |  | Water System Level II (Gravity Type) | 1 | Basic Social Services | Water System | 1 | system | 2885298.4 | 1237390 | 4122688.4 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Datagan | 097340005 | Construction of Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 115 | ln.m | 1085930.5 | 206500 | 1292430.5 | 2011-05-26 | 2011-07-31 | 977337.45 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Datagan | 097340005 | Road Concreting of 1.5 Ln.m Wide w/ Line Ditch | 1 | Basic Access Infrastructure | Road |  | kms | 3509602.73 | 1504910 | 5014512.73 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Eastern Poblacion | 097340006 | Road Improvement w/ Hanging Foot Bridge | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 1909817.25 | 501442.26 | 2411259.51 | 2012-05-01 |  | 954908.62 |  | 1st |  | On-going |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Lantawan | 097340007 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 944478.15 | 405959 | 1350437.15 |  |  | 0 |  |  | Elem | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Libertad | 097340008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 537915 | 161700 | 699615 | 2011-04-25 | 2011-06-30 | 518160 |  | 3rd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Lumangoy | 097340009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 253846.65 | 465568.35 | 719415 | 2011-04-28 | 2011-07-31 | 228461.48 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | New Carmen | 097340010 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 632201 | 148500 | 780701 | 2012-06-04 |  | 505760.8 |  | 1st |  | On-going | 2012-07-24 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | New Oroquieta ( Bag-ong Oroquieta) | 097340002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 514715 | 188700 | 703415 | 2011-04-25 | 2011-06-30 | 506187.86 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | New Oroquieta ( Bag-ong Oroquieta) | 097340002 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 614482.75 | 144000 | 758482.75 | 2012-05-26 |  | 491586.2 |  | 1st |  | On-going | 2012-07-15 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Picturan | 097340011 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 575655 | 168450 | 744105 | 2011-04-28 | 2011-09-15 | 518089.5 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Picturan | 097340011 | Sectional Road Concreting w/ Line Ditch | 1 | Basic Access Infrastructure | Road |  | kms | 1603494 | 689838.25 | 2293332.25 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Poblacion | 097340012 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 1003809 | 191700 | 1195509 | 2011-06-01 | 2011-07-31 | 903428.1 |  | 2nd | Elem | Completed | 2011-08-20
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Poblacion | 097340012 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control |  | ln.m | 1925781.55 | 828269 | 2754050.55 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Rizal | 097340013 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 965709 | 254800 | 1220509 | 2011-04-27 | 2011-07-31 | 869138.1 |  | 2nd | Elem | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Rizal | 097340013 | Construction of Water System Level II (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 1602351.38 | 704580.33 | 2306931.71 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | San Miguel | 097340014 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 160.2 | sq. m | 791289.85 | 439219.15 | 1230509 | 2011-05-02 | 2011-07-31 | 712160.85 |  | 2nd | Elem | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | San Miguel | 097340014 | Sectional Road Concreting w/ Line Ditch | 1 | Basic Access Infrastructure | Road |  | kms | 2723438 | 1170814.5 | 3894252.5 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Sawa | 097340016 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 599480 | 146625 | 746105 | 2011-04-28 | 2011-09-15 | 539532 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Sto. Niño | 097340015 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 542105 | 187000 | 729105 | 2011-04-26 | 2011-08-15 | 542105 |  | 3rd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Tungawan | 097340017 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 635265.64 | 145635.11 | 780900.75 | 2012-05-26 |  | 508212.51 |  | 1st |  | On-going | 2012-07-15 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Upper Sicpao | 097340018 | Construction of Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 190 | ln.m | 1229545 | 199000 | 1428545 | 2011-06-10 | 2011-07-31 | 1106590.5 |  | 2nd |  | Completed | 2011-08-29
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Sominot (Don Mariano Marcos) | 097340 | Upper Sicpao | 097340018 | Sectional Road Concreting w/ Line Ditch | 1 | Basic Access Infrastructure | Road | 0.36 | kms | 1908967 | 368122.78 | 2277089.78 | 2012-07-06 |  | 954483.11 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-08-22 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Ambulon | 097341014 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 685134 | 156392 | 841526 | 2012-07-24 |  | 513997.6 |  | 1st |  | On-going | 2012-09-15 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Biu-os | 097341001 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 590933 | 148592 | 739525 | 2011-06-01 | 2011-08-15 | 531839.7 |  | 2nd | Elem | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Biu-os | 097341001 | Construction of 1 Unit 4 Lines & 1 Unit 3 Lines Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 35 | ln.m | 1202309 | 279731 | 1482040 | 2012-07-28 |  | 919478.4 |  | 1st |  | On-going | 2012-11-05 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Cogon | 097341002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 480056 | 205739 | 685795 | 2011-04-25 | 2011-07-31 | 432050.4 |  | 2nd |  | Completed | 2011-07-09
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Cogon | 097341002 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 80.28 | sq. m | 589892 | 226394 | 816286 | 2012-05-24 |  | 491151.6 |  | 2nd | PS | On-going | 2012-07-21 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Danan | 097341003 | Road Improvement of Danan Brgy. Road w/ 192 ln.m Sectional Concreting & Line Canal | 1 | Basic Access Infrastructure | Road | 0.809 | kms | 1393688 | 597296 | 1990984 | 2011-06-01 | 2011-11-15 | 1254319.2 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Danan | 097341003 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 684284 | 156242 | 840526 | 2012-07-16 |  | 514117.6 |  | 1st |  | On-going | 2012-09-21 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Kabatan | 097341004 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 552437 | 179675 | 732112 | 2011-06-11 | 2011-07-31 | 497193.3 |  | 2nd |  | Completed | 2011-08-30
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Kapatagan | 097341005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 473056 | 202739 | 675795 | 2011-05-05 | 2011-07-31 | 425750.4 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Kapatagan | 097341005 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 80.28 | sq. m | 665273 | 151013 | 816286 | 2012-06-08 |  | 558994.5 |  | 2nd | PS | On-going | 2012-08-05 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Limason | 097341006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 589925 | 92653 | 682578 | 2011-06-08 | 2011-08-22 | 530932.5 |  | 2nd |  | Completed | 2011-08-22
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Limason | 097341006 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 690280 | 151418 | 841698 | 2012-06-14 |  | 516544 |  | 1st |  | On-going | 2012-08-08 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Linoguayan | 097341007 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 80.28 | sq. m | 579769 | 248473 | 828242 | 2012-06-19 |  | 432480.8 |  | 1st | PS | On-going | 2012-08-16 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Lumbal | 097341008 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 532924 | 228397 | 761321 | 2011-06-30 | 2011-07-31 | 479631.6 |  | 2nd |  | Completed | 2011-07-31
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Lunib | 097341009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 600701 | 188112.85 | 788813.85 | 2012-05-22 |  | 540630.9 |  | 2nd |  | On-going | 2012-07-24 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Maculay | 097341010 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 87.35 | sq. m | 590058 | 140827 | 730885 | 2011-07-09 | 2011-09-15 | 531052.2 | Waiting of delivery of materials | 2nd | Elem | Completed | 2011-09-22
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Maraya | 097341011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 602358 | 188527 | 790885 | 2012-05-18 |  | 542122.2 |  | 2nd |  | On-going | 2012-07-20 | 0
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Sagucan | 097341012 | Construction of 1 Unit 1 CL Secondary School Building (HS) | 1 | Basic Social Services | School | 87.35 | sq. m | 612872 | 136361 | 749233 | 2011-07-08 | 2011-10-15 | 551584.8 |  | 2nd | HS | Completed | 2011-09-21
H1 | IX | 09 | Zamboanga Del Sur | 0973 | Vincenzo Sagun | 097341 | Waling-Waling | 097341013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 484051 | 207451 | 691502 | 2011-06-10 | 2011-07-31 | 435645.9 |  | 2nd |  | Completed | 2011-08-24
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Abunda | 098307001 | Construction of Livelihood Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 474352.35 | 185124 | 959476.35 |  |  | 0 | With PAMANA - 300,000 TPC 959,476.35 |  |  | Not yet started |  | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Bagong Silang | 098307002 | Construction of Warehouse w/ Storage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 568 | sq.m | 452533.5 | 166697.34 | 919230.84 | 2012-06-18 |  | 362026.8 | With PAMANA - 300,000 TPC 919,230.84 | 1st |  | On-going | 2012-09-06 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Bangkaw-Bangkaw | 098307003 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 708191.05 | 169183.78 | 877374.83 | 2012-07-02 |  | 530651.2 |  | 1st |  | On-going | 2012-09-20
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Caliran | 098307007 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 407670.8 | 164158.68 | 871829.48 |  |  | 296540 | With PAMANA - 300,000 TPC 871,829.48 | 1st |  | Not yet started |  | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Kauswagan | 098307011 | Construction of Livelihood Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 504202.24 | 172426.41 | 976628.65 | 2012-03-18 |  | 0 | With PAMANA - 300,000 TPC 976,628.65 (No movement as of May 31, 2012 reports) |  |  | On-going | 2012-06-06 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Ligaya | 098307013 | Construction of Livelihood Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 423483.52 | 167155.13 | 890638.65 | 2012-04-12 |  | 338786.82 | With PAMANA - 300,000 TPC 890,638.65 | 1st |  | On-going | 2012-07-01 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Looc-Barlak | 098307014 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 414816.47 | 159214.9 | 874031.37 | 2012-04-13 |  | 331853.18 | With PAMANA - 300,000 TPC 874,031.37 | 1st |  | On-going | 2012-07-02 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Malinao | 098307015 | Construction of Mini Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 117.7 | ln.m | 617171.5 | 363541 | 1280712.5 | 2012-04-26 |  | 453598.74 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-15 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Pamansaan | 098307017 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 410762.37 | 154558.35 | 865320.72 | 2012-07-02 |  | 323927.26 | With PAMANA - 300,000 TPC 865,320.72 | 1st |  | On-going | 2012-09-20 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Poblacion | 098307019 | Construction of Livelihood Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 421563.52 | 169075.13 | 890638.65 |  |  | 0 | With PAMANA - 300,000 TPC 890,638.65 |  |  | Not yet started |  | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Punawan | 098307020 | Construction of Livelihood Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 424123.52 | 166515.13 | 890638.65 |  |  | 0 | With PAMANA - 300,000 TPC 890,638.65 |  |  | Not yet started |  | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | San Roque (Pinalim) | 098307018 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 893648.15 | 242533.23 | 1436181.38 | 2012-06-01 |  | 0 | No movement as of July 31, 2012 |  |  | On-going |  | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Sioton | 098307025 | Construction of Livelihood Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 504202.24 | 172426.41 | 976628.65 | 2012-07-02 |  | 0 | With PAMANA - 300,000 TPC 976,628.65 |  |  | On-going | 2012-09-20 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Sto. Niño (Caliran) | 098307023 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.468 | kms | 819791.61 | 224495 | 1344286.61 | 2012-04-28 |  | 595833.28 | With PAMANA - 300,000 TPC 1,344,286.61 | 1st |  | On-going | 2012-07-17 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Taguisian | 098307026 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.487 | kms | 879932 | 271244.88 | 1451176.88 | 2012-03-19 |  | 644145.6 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-07 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Tandu-Comot (Katipunan) | 098307010 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 403825.55 | 168696.93 | 872522.48 | 2012-07-13 |  | 227210.2 | With PAMANA - 300,000 TPC 872,522.48 | 1st |  | On-going | 2012-10-01 | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Balian | 098311001 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1388076.83 | 207475 | 1595551.83 |  |  | 951183.2 | Steel Truss | 1st | Elem | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Binangonan (San Vicente) | 098311017 | Proposed Multi-Purpose Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 535098.55 | 135750 | 670848.55 | 2012-06-01 |  | 428078.84 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Bulawan | 098311004 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1300482.38 | 207475 | 1507957.38 | 2012-06-01 |  | 780289.43 | No movement as of July 31, 2012 | 1st | Elem | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Calape | 098311005 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 675348.7 | 136300 | 811648.7 | 2012-06-01 |  | 540278.96 | No movement as of July 31, 2012 | 1st | Elem | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Fatima | 098311007 | Concreting of Road on Steep Slope | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 859751.34 | 132500 | 992251.34 |  |  | 429875.67 |  | 1st |  | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Guiwan | 098311023 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 672.2 | ln.m | 681146.5 | 152500 | 1133646.5 |  |  | 0 | With PAMANA - 300,000 TPC 1,133,646.50 |  |  | Not yet started |  | 300000
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Kima | 098311010 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 635486.85 | 132500 | 767986.85 |  |  | 317743.48 |  | 1st |  | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Kulasian | 098311011 | Construction of 1 Unit Flea Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 120 | sq.m | 570071.85 | 133187.5 | 703259.35 | 2012-06-01 |  | 0 | No movement as of July 31, 2012 |  |  | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Kulisap | 098311024 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1267482.38 | 240475 | 1507957.38 | 2012-06-01 |  | 760489.43 | Steel Truss Roofing | 1st | Elem | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | La Fortuna | 098311025 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 674884 | 138995 | 813879 | 2012-06-01 |  | 337442 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Labatan | 098311012 | Construction of 1 Unit Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 80.62 | sq.m | 510862.04 | 393617.16 | 904479.2 |  |  | 0 |  |  |  | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Lower Sumilong | 098311028 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 675348.7 | 136300 | 811648.7 | 2012-06-01 |  | 513265 |  | 1st | Elem | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Mayabo (Sta. Maria) | 098311018 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 717630 | 140400 | 858030 |  |  | 522535.6 |  | 1st |  | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Minundas (Sto. Niño) | 098311019 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 737839 | 140495 | 878334 |  |  | 532805.6 | Less 0.50 from the KC Grant to exact the Grant 14,500,000 | 1st |  | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Nanan | 098311014 | Construction of Brgy. Health Station (Steel Truss) | 1 | Basic Social Services | Health Station | 51 | sq.m | 674884 | 138995 | 813879 | 2012-05-07 |  | 337422 |  | 1st |  | On-going | 2012-07-26
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | San Isidro | 098311026 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1266482.38 | 241475 | 1507957.38 | 2012-06-01 |  | 759889.43 |  | 1st | Elem | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | San Vicente (Binangonan) | 098311017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 664562.25 | 135400 | 799962.25 | 2012-06-01 |  | 531649.8 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Silal | 098311027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 664562.25 | 135400 | 799962.25 | 2012-06-12 |  | 505067.73 |  | 1st |  | On-going | 2012-08-26
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Baluran | 098316001 | Construction of Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1202141 | 180365.37 | 1382506.37 | 2012-02-09 |  | 841498 |  | 1st | Elem | On-going | 2012-05-29 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Cayamcam | 098316002 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 705135 | 138088.55 | 843223.55 | 2012-02-01 |  | 493594.5 | No movement as of may 31, 2012 reports | 1st | PS | On-going | 2012-05-21
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Gaycon | 098316020 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 658786 | 131612 | 790398 | 2012-02-17 |  | 461150 |  | 1st |  | On-going | 2012-05-12 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Linguisan | 098316006 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 595607 | 159615 | 755222 | 2012-02-15 |  | 356904 |  | 1st |  | On-going | 2012-05-10 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Little Margos | 098316021 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 627957 | 160600 | 788557 | 2012-02-07 |  | 444607 |  | 1st |  | On-going | 2012-05-02 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Loboc | 098316016 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 671646 | 147112.49 | 818758.49 | 2012-02-13 |  | 470152 |  | 1st |  | On-going | 2012-05-08
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Looc Labuan | 098316007 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 166.5 | sq. m | 1249991 | 239506.37 | 1489497.37 | 2012-02-17 |  | 874993 |  | 1st | Elem | On-going | 2012-06-06 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Lower Tungawan | 098316008 | Farmers Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq. m | 654000 | 133885 | 787885 | 2012-03-21 |  | 455663 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-06-14 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | San Isidro | 098316017 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 663324 | 131498 | 794822 | 2012-02-17 |  | 464327 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-12 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Sto. Niño | 098316022 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 710955 | 140188.55 | 851143.55 | 2012-02-20 |  | 497668.5 | No movement as of July 31, 2012 | 1st | PS | On-going | 2012-05-05
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Taglibas | 098316023 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1623129.6 | 347167.4 | 1970297 |  |  | 858325.4 |  | 1st |  | Not yet started
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigbanuang | 098316011 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 700635 | 136688.55 | 837323.55 | 2012-02-06 |  | 490445 |  | 1st | PS | On-going | 2012-04-21
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigbucay | 098316012 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | 83.25 | sq. m | 615486 | 144811 | 760297 | 2012-02-08 |  | 442054 | No movement as of May 31, 2012 reports | 1st | PS | On-going | 2012-04-23 | 0
H1 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Timbabauan | 098316026 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 83.25 | sq. m | 715455 | 140728.55 | 856183.55 | 2012-02-06 |  | 500818 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-04-21
F2 | IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Upper Tungawan | 098316013 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 654306 | 134202 | 788508 | 2012-01-31 | 2012-07-15 | 458014 | No movement as of May 31, 2012 reports | 1st |  | Completed | 2012-04-25 | 0
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | Bagacay | 050505003 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | 48 | sq.m | 625000 | 125000 | 750000 |  |  | 0 |  |  |  | Not yet started
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | Florista & Del Rosario | 050505015 | Improvement of Barangay Road | 2 | Basic Access Infrastructure | Road |  | kms | 3416948.79 | 683389.76 | 4100338.55 |  |  | 0 |  |  |  | Not yet started
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | Magsaysay et.al | 050505007 | Construction of Erosion Control | 8 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 281 | ln.m | 9106549.21 | 1821309.84 | 10927859.05 | 2012-06-01 |  | 7285239.37 | Magsaysay, Cabraran, Rizal, Calzada, Plaza, Mabini, Sto. Niño & Aurora | 1st |  | On-going
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | San Isidro et.al | 050505020 | Improvement of Barangay Road | 4 | Basic Access Infrastructure | Road |  | kms | 1586567.71 | 317313.54 | 1903881.25 |  |  | 0 | San Isidro, Quintinday, Salvacion & San Roque |  |  | Not yet started
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | Villa Paz et.al | 050505024 | Improvement of Brgy. Road | 7 | Basic Access Infrastructure | Road | 2.517 | kms | 2393283.21 | 478656.64 | 2871939.85 | 2012-06-01 |  | 1435969.93 | Villapaz, Maogog, Bautista, San Vicente, Estrella, Sinagaran & Mamlad | 1st |  | On-going
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | White Deer | 050505010 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 777404.67 | 155480.93 | 932885.6 |  |  | 0 |  |  |  | Not yet started
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Alongong | 050507001 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.703 | kms | 1026700 | 205300 | 1232000 | 2012-01-23 | 2012-05-15 | 924030 |  | 2nd |  | Completed | 2012-04-05
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Apud | 050507002 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 176 | ln.m | 1904500 | 381000 | 2285500 | 2012-02-17 |  | 1714050 | No movement as of July 2012 | 2nd |  | On-going | 2012-05-09
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Bariw | 050507011 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 472500 | 94500 | 567000 | 2012-02-28 | 2012-05-15 | 425250 |  | 2nd |  | Completed | 2012-03-28
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Bonbon | 050507012 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.78 | kms | 1020800 | 204200 | 1225000 | 2012-02-27 | 2012-06-15 | 918720 |  | 2nd |  | Completed | 2012-04-30
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Buga | 050507013 | Consreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.329 | kms | 648400 | 129600 | 778000 | 2012-01-23 | 2012-05-15 | 583560 |  | 2nd |  | Completed | 2012-03-05
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Bulusan | 050507014 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.383 | kms | 541700 | 108300 | 650000 | 2012-01-21 | 2012-05-15 | 487530 |  | 2nd |  | Completed | 2012-02-25
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Burabod | 050507015 | Construction of 1 Unit School Building | 1 | Basic Social Services | School | 63 | sq. m | 640500 | 131500 | 772000 | 2012-01-21 |  | 576450 | 335 students/pupils (No movement as of May 31, 2012 reports | 2nd | Elem | On-going | 2012-03-03
F2 | V | 05 | Albay | 0505 | Libon | 050507 | East Carisac | 050507017 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 640600 | 131400 | 772000 | 2012-02-11 | 2012-06-15 | 576540 | No movement as of may 31, 2012 reports | 2nd |  | Completed | 2012-03-21
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Harigue | 050507019 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.96 | kms | 1512500 | 302500 | 1815000 | 2012-01-23 |  | 1361250 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-04-02
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Libtong | 050507020 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.457 | kms | 664200 | 132800 | 797000 | 2012-01-21 |  | 597780 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-03-13
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Macabugos | 050507023 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.62 | kms | 1137500 | 227500 | 1365000 | 2012-04-09 |  | 910000 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-06-12
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Natasan | 050507029 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.45 | kms | 690000 | 138000 | 828000 | 2012-02-06 | 2012-05-15 | 621000 |  | 2nd |  | Completed | 2012-03-23
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Rawis | 050507033 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 1698400 | 339600 | 2038000 | 2012-02-13 |  | 1528560 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-05-04
F2 | V | 05 | Albay | 0505 | Libon | 050507 | San Agustin | 050507037 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 131 | ln.m | 1678800 | 336200 | 2015000 | 2012-03-05 |  | 1510920 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-05-26
F2 | V | 05 | Albay | 0505 | Libon | 050507 | San Antonio | 050507038 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.416 | kms | 671700 | 134300 | 806000 | 2012-05-02 | 2012-07-15 | 537360 |  | 1st |  | Completed | 2012-07-01
F2 | V | 05 | Albay | 0505 | Libon | 050507 | San Isidro | 050507039 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1309 | sq.m | 975000 | 195000 | 1170000 | 2012-01-16 | 2012-07-15 | 877500 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-03-26
F2 | V | 05 | Albay | 0505 | Libon | 050507 | San Ramon | 050507042 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.695 | kms | 1258400 | 251600 | 1510000 | 2012-04-12 |  | 629200 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-22
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Sta. Cruz | 050507044 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 865800 | 173200 | 1039000 | 2012-02-29 | 2012-07-15 | 692640 |  | 1st |  | Completed | 2012-05-08
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Talin-Talin | 050507046 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 733400 | 146600 | 880000 | 2012-05-01 |  | 500320 | No movement as of July 31, 2012) | 1st |  | On-going
F2 | V | 05 | Albay | 0505 | Libon | 050507 | West Carisac | 050507018 | Construction of 1 Unit Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 640600 | 131400 | 772000 | 2012-01-12 | 2012-06-15 | 576540 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-03-22
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Zone 1 | 050507004 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 900 | sq.m | 700000 | 140000 | 840000 | 2012-01-21 | 2012-07-15 | 630000 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-03-09
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Zone 2 | 050507005 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 121 | ln.m | 804200 | 160800 | 965000 | 2012-04-13 | 2012-07-15 | 723780 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-05-19
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Zone 3 | 050507006 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 90 | ln.m | 616700 | 123300 | 740000 | 2012-01-23 | 2012-06-15 | 555030 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-02-05
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Zone 4 | 050507007 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 1342500 | 268500 | 1611000 | 2012-02-01 |  | 1208250 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-04-10
F2 | V | 05 | Albay | 0505 | Libon | 050507 | Zone 5 | 050507008 | Construction of Small Impounding System (SWIP) 12.35 Ln.m | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | 12.35 | ln.m | 564600 | 112900 | 677500 | 2012-03-05 |  | 508140 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-04-24
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Bagatangki | 050510002 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.6 | kms | 831344.27 | 356283.23 | 1187627.5 | 2012-03-27 | 2012-07-15 | 745420 |  | 2nd |  | Completed | 2012-06-01
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Bagumbayan et.al | 050510022 | Construction of Flood Control | 9 | Environmental Protection and Conservation | River Control/Flood Control | 296.6 | ln.m | 2032905.06 | 871369.54 | 2904274.6 | 2012-05-02 |  | 1626324.05 |  | 1st |  | On-going | 2012-06-15
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Bulang | 050510007 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1476625.55 | 369142.93 | 1845768.48 | 2012-04-01 |  | 1332666.78 |  | 2nd |  | On-going
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Labnig et.al | 050510014 | Construction of Flood Control | 8 | Environmental Protection and Conservation | River Control/Flood Control | 140 | ln.m | 2667220.48 | 772357.6 | 3439578.08 |  |  | 2133776.38 |  | 1st |  | Not yet started
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Matalipni | 050510017 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.75 | kms | 384222.19 | 164648.31 | 548870.5 | 2012-03-04 |  | 384222.19 | No movement as of July 31, 2012 | 2nd |  | On-going
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Quinarabasahan | 050510023 | Concreting of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.899 | kms | 1623930.34 | 487875.16 | 2111805.5 | 2012-03-13 |  | 1299144.27 |  | 1st |  | On-going
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Sta. Elena et.al | 050510024 | Construction of Flood Control | 5 | Environmental Protection and Conservation | River Control/Flood Control | 110 | ln.m | 2999115.71 | 1283363.29 | 4282479 | 2012-06-01 |  | 2399292.56 |  | 1st |  | On-going
F2 | V | 05 | Albay | 0505 | Malinao | 050510 | Tanawan et.al | 050510028 | Construction of Flood Control | 3 | Environmental Protection and Conservation | River Control/Flood Control | 225 | ln.m | 2484596.4 | 1070499.6 | 3555096 | 2012-04-25 |  | 1987677.12 |  | 1st |  | On-going | 2012-06-23
F2 | V | 05 | Albay | 0505 | Manito | 050511 | Balasbas | 050511002 | Construction of 1 Unit School Building (HS) | 1 | Basic Social Services | School | 63 | sq. m | 454394.45 | 311468.15 | 765862.6 | 2012-02-01 | 2012-07-15 | 451256.99 |  | 2nd | HS | Completed | 2012-07-01
F2 | V | 05 | Albay | 0505 | Manito | 050511 | Cabacongan | 050511005 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 609905.48 | 152476.37 | 762381.85 | 2012-02-23 | 2012-05-15 | 609905.48 |  | 2nd | Elem | Completed | 2012-05-15
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Cabit | 050511006 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 631072.32 | 157768.08 | 788840.4 | 2012-01-25 | 2012-06-15 | 624449.92 |  | 2nd | Elem | Completed | 2012-06-01
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Cawit | 050511008 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1152084.26 | 288021.07 | 1440105.33 | 2012-03-01 |  | 921667.36 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Holugan | 050511009 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 624547.86 | 156136.97 | 780684.83 | 2012-01-24 | 2012-07-15 | 562093.07 |  | 2nd |  | Completed | 2012-07-01
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Malobago | 050511011 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 628738.48 | 157184.62 | 785923.1 | 2012-01-31 | 2012-06-15 | 502990.78 |  | 1st |  | Completed | 2012-06-01
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Manumbalay | 050511012 | Rehab./Improvement of FMR | 1 | Basic Access Infrastructure | Road | 2 | kms | 2010956.4 | 504314.1 | 2515270.5 | 2012-05-04 |  | 1467998.17 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Nagotgot | 050511013 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1086108.78 | 271527.2 | 1357635.98 | 2012-01-31 | 2012-06-15 | 1067470.7 | No movement as of May 31, 2012 reports | 2nd | Elem | Completed | 2012-06-01
H1 | V | 05 | Albay | 0505 | Manito | 050511 | Tinapian | 050511018 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 431 | sq.m | 302191.96 | 75547.99 | 377739.95 | 2012-02-20 | 2012-04-15 | 302142.61 |  | 2nd |  | Completed | 2012-04-15
F2 | V | 05 | Albay | 0505 | Jovellar | 050505 | Florista & Del Rosario | 050505013 | Improvement of Barangay Road | 2 | Basic Access Infrastructure | Road |  | kms | 3416948.79 | 683389.76 | 4100338.55 |  |  | 0 |  |  |  | Not yet started
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Agol - Nablangbulod | 050513001 | Rehabilitation/Improvement of Agol-Nablangbulod FMR | 2 | Basic Access Infrastructure | Road | 2.226 | kms | 2950254.25 | 590050.85 | 3540305.1 | 2012-06-01 |  | 2360203.4 |  | 1st |  | On-going
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Barangay 1 | 050513023 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 122 | ln.m | 1389774.72 | 277954.94 | 1667729.66 | 2012-04-24 | 2012-06-15 | 1111837.29 |  | 1st |  | Completed | 2012-07-02
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Barangay 3 | 050513025 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 400 | ln.m | 422592.58 | 84518.52 | 507111.1 | 2012-03-24 | 2012-05-11 | 338074.06 |  | 1st |  | Completed | 2012-05-11
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Barangay 4 | 050513026 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 250 | ln.m | 1772950.6 | 354590.12 | 2127540.72 | 2012-02-07 | 2012-06-15 | 1594845.48 |  | 2nd |  | Completed | 2012-04-16
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Barangay 5 | 050513027 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 277 | ln.m | 2221861.51 | 444372.3 | 2666233.81 | 2012-03-16 | 2012-05-24 | 1777489.21 |  | 1st |  | Completed | 2012-05-24
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Basicao Coastal | 050513003 | Construction of Concrete Pavement | 1 | Basic Access Infrastructure | Access Trail | 1.5 | kms | 1373935.78 | 274787.16 | 1648722.94 | 2012-01-24 | 2012-05-15 | 1236542.2 |  | 2nd |  | Completed | 2012-03-09
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Binodegahan | 050513006 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1220873.49 | 244174.7 | 1465048.19 | 2012-04-30 | 2012-06-15 | 976698.79 | 2,535 Ln.m | 1st |  | Completed | 2012-07-08
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Agol - Nablangbulod | 050513019 | Rehabilitation/Improvement of Agol-Nablangbulod FMR | 2 | Basic Access Infrastructure | Road | 2.226 | kms | 2950254.25 | 590050.85 | 3540305.1 | 2012-06-01 |  | 2360203.4 |  | 1st |  | On-going
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Malapay - Salvacion | 050513014 | Rehab./Improvement of Malapay - Salvacion FMR | 2 | Basic Access Infrastructure | Road | 1.34 | kms | 2850831.42 | 570166.28 | 3420997.7 | 2012-07-01 |  | 2280665.14 |  | 1st |  | On-going
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Palapas | 050513021 | Construction of Cable Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 50 | ln.m | 1504195.61 | 300839.12 | 1805034.73 | 2012-05-11 |  | 1154585.67 |  | 1st |  | On-going | 2012-07-12
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Rawis | 050513028 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.7 | kms | 772577.43 | 154552.57 | 927130 | 2012-01-20 | 2012-05-15 | 695319.68 |  | 2nd |  | Completed | 2012-03-05
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Bagaobawan | 050515003 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 788447.46 | 186489.24 | 974936.7 | 2012-06-01 |  | 527685.5 |  | 1st |  | On-going
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Buhatan | 050515009 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1370213.87 | 305646.21 | 1675860.08 | 2012-05-19 |  | 927715.3 | 91 children ages 7-10 y.o | 1st | Elem | On-going | 2012-06-30
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Calanaga | 050515010 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.13 | kms | 2069673.99 | 448909.13 | 2518583.12 | 2012-02-12 | 2012-06-15 | 1657650 |  | 1st |  | Completed | 2012-04-30
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Dap-Dap | 050515013 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1316494.9 | 294643.53 | 1611138.43 | 2012-02-20 | 2012-06-15 | 1181040.22 | 74 children ages 7-8 y.o | 2nd | Elem | Completed | 2012-04-30
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Gaba | 050515014 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1320538.19 | 295471.68 | 1616009.87 | 2012-05-19 |  | 904922.9 | 66 students ages 12-13 y.o | 1st | Elem | On-going | 2012-06-30
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Liguan | 050515019 | Construction of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 206 | ln.m | 2032301.85 | 441254.59 | 2473556.44 | 2012-04-18 | 2012-07-15 | 1819163.18 |  | 2nd |  | Completed | 2012-06-10
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Masaga | 050515025 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 685887.42 | 165482.97 | 851370.39 | 2012-03-12 |  | 545427 | 26 children ages 3-5 y.o | 1st |  | On-going | 2012-04-30
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Nagcalsot | 050515027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 675051.81 | 163263.62 | 838315.43 | 2012-04-18 |  | 530347.7 | 25 children ages 3-5 y.o | 1st |  | On-going | 2012-06-15
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Sagrada | 050515030 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1428710.19 | 317627.39 | 1746337.58 | 2012-02-27 |  | 1283944.11 | 60 children ages 7-8 y.o | 2nd | Elem | On-going | 2012-04-30
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Sta. Barbara | 050515032 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.611 | kms | 1480607.42 | 328256.94 | 1808864.36 | 2012-02-12 | 2012-07-15 | 1182707.2 |  | 1st |  | Completed | 2012-04-15
H1 | V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Villahermosa | 050515036 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 2.16 | kms | 3813317.06 | 806040.84 | 4619357.9 | 2012-02-27 |  | 3450081.2 |  | 2nd |  | On-going | 2012-04-30
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Cañares | 054104002 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 280 | ln.m | 1024502.93 | 180794.64 | 1205297.57 | 2012-03-26 | 2012-05-15 | 819602.34 |  | 1st |  | Completed | 2012-06-26
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Costa Rica | 054104004 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 450 | ln.m | 804860.28 | 142034.17 | 946894.45 | 2012-03-29 |  | 643888.22 |  | 1st |  | On-going | 2012-06-29
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Danao | 054104005 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 734211.72 | 129566.81 | 863778.53 | 2012-03-19 | 2012-05-18 | 567922.69 |  | 1st |  | Completed | 2012-05-18
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Gibraltar | 054104006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 601338.5 | 197829.5 | 799168 | 2012-04-23 | 2012-07-15 | 481070.8 | Additional SP encoded at (May 31, 2012 report) | 1st |  | Completed | 2012-06-22 | 0
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Nasandig et.al | 054104009 | Construction of Pathway | 2 | Basic Access Infrastructure | Access Trail | 2.11 | kms | 2595798.91 | 458082.16 | 3053881.07 | 2012-05-05 |  | 2086109.84 |  | 1st |  | On-going | 2012-07-03
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Panisihan | 054104010 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 659192.31 | 112209.69 | 771402 | 2012-04-02 | 2012-05-15 | 524947.65 |  | 1st |  | Completed | 2012-06-01 | 0
H1 | V | 05 | Masbate | 0541 | Batuan | 054104 | Rizal | 054104013 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 520 | ln.m | 500675.97 | 88354.58 | 589030.55 | 2012-03-26 | 2012-05-15 | 400540.78 |  | 1st |  | Completed | 2012-06-26
H1 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Dalipe | 054106007 | Construction of 1 Unit 3 CL School Building (HS) | 1 | Basic Social Services | School | 189 | sq. m | 1492223.69 | 435680.39 | 1927904.08 | 2011-12-21 |  | 1343001.32 |  | 2nd | HS | On-going | 2012-04-04
H1 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Divisoria | 054106008 | Construction of 2 Units Day Care Center | 1 | Basic Social Services | Day Care Center | 96 | sq.m | 1312784.62 | 395315.01 | 1708099.63 | 2012-01-24 | 2012-07-15 | 1181506.16 | 2 DCC SP Purok 1 Proper Purok 6 Bongalon | 2nd |  | Completed | 2012-03-23
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Gilotongan | 054106010 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 772093.5 | 223684.85 | 995778.35 | 2012-02-14 |  | 555907.32 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-04-28
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Iraya | 054106036 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1545085.91 | 447185.49 | 1992271.4 | 2012-02-07 |  | 1390577.32 |  | 2nd | Elem | On-going | 2012-06-05
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Mahayahay | 054106017 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 700548.93 | 177590.68 | 878139.61 | 2012-04-13 |  | 490384.25 |  | 1st |  | On-going | 2012-06-11
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Maihao | 054106018 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1486881.68 | 434478.69 | 1921360.37 | 2012-01-17 | 2012-07-15 | 1338193.52 |  | 2nd | Elem | Completed | 2012-04-30
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Naro | 054106020 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1574158.71 | 449111.93 | 2023270.64 | 2012-01-17 | 2012-07-15 | 1416742.84 |  | 2nd | Elem | Completed | 2012-05-15
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Palobandera | 054106033 | Construction of 1 Unit Warehouse Building & Concrete Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 1055264.93 | 287385.15 | 1342650.08 | 2012-01-11 | 2012-07-15 | 949738.44 |  | 2nd |  | Completed | 2012-03-05
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Poblacion | 054106022 | Construction of Concrete Lined Canal with Cover | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 390 | ln.m | 410746.74 | 1137628.32 | 1548375.06 | 2012-02-10 | 2012-07-15 | 287552.71 | (No movement as of May 31, 2012 reports) 692,541.57 (Total Grant+LCC) - 281,794.83 (LCC MLGU) = 410,746.74 KC Grant | 1st |  | Completed | 2012-03-11
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | R.M. Magbalon | 054106016 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1575003.94 | 404302.06 | 1979306 | 2012-01-27 |  | 1417503.55 |  | 2nd | Elem | On-going | 2012-05-05
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | San Jose | 054106025 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 665603.59 | 204779.61 | 870383.2 | 2012-01-04 | 2012-07-15 | 599043.23 |  | 2nd |  | Completed | 2012-03-04
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Taberna | 054106027 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 683650.93 | 203789.42 | 887440.35 | 2012-01-10 | 2012-07-15 | 615285.84 |  | 2nd |  | Completed | 2012-03-09
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Talisay | 054106028 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1595302.38 | 458868.26 | 2054170.64 | 2012-01-23 | 2012-07-15 | 1435772.14 |  | 2nd | Elem | Completed | 2012-05-21
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Tubog | 054106038 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 707458.37 | 159144.98 | 866603.35 | 2012-01-05 | 2012-07-15 | 636712.53 |  | 2nd |  | Completed | 2012-03-05
F2 | V | 05 | Masbate | 0541 | Cawayan | 054106 | Tuburan | 054106029 | Construction of 1 Unit Warehouse Building & Concrete Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 420 | sq.m | 1073192.08 | 291417.92 | 1364610 | 2012-01-13 |  | 965872.87 | No movement as of may 31, 2012 reports | 2nd |  | On-going | 2012-03-07
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Albasan | 054107001 | Rehabilitation/Improvement of Junction Albasan Barangay Road | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 898136.65 | 300295 | 1198431.65 | 2011-05-22 | 2011-07-31 | 898136.65 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Boca Engaño | 054107002 | Rehab./Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 744403.5 | 169685 | 914088.5 | 2011-03-25 | 2011-07-31 | 684783.73 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Calpi | 054107004 | Rehab./Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.8 | kms | 938122.15 | 721501 | 1659623.15 | 2011-05-19 | 2011-08-15 | 844309.95 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Canomay | 054107005 | Rehab./Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.05 | kms | 865794.5 | 212115 | 1077909.5 | 2011-04-11 | 2011-07-31 | 775713.43 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Cawayan | 054107006 | Rehab./Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 2.9 | kms | 1496997.05 | 685066 | 2182063.05 | 2011-06-17 | 2011-10-15 | 1396875 |  | 2nd |  | Completed | 2011-10-30
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Mababang Baybay | 054107009 | Rehab./Improvement of Junction Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.775 | kms | 934305.3 | 283250 | 1217555.3 | 2011-05-03 | 2011-07-31 | 840874.77 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Mabiton | 054107010 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.555 | kms | 853686 | 227162.45 | 1080848.45 | 2011-04-14 | 2011-07-31 | 792419.72 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Nabasagan | 054107012 | Construction/Opening of Brgy. Road | 1 | Basic Access Infrastructure | Road | 2.95 | kms | 841061.9 | 897625 | 1738686.9 | 2011-04-14 | 2011-11-15 | 756955.71 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Nonoc | 054107013 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.17 | kms | 290939.4 | 196448 | 487387.4 | 2011-04-06 | 2011-07-31 | 216880 |  | 1st |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Osmeña | 054107014 | Rehab./Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 1141626 | 582343.15 | 1723969.15 | 2011-03-08 | 2011-10-15 | 858318 |  | 1st |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | Pasig | 054107015 | Construction/Opening of Brgy. Road | 1 | Basic Access Infrastructure | Road | 3 | kms | 774958.3 | 1061902.55 | 1836860.85 | 2011-05-26 | 2012-04-15 | 691274.45 | 100% as per text of IA Jeb (May 15) as of April 2012 | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | San Isidro | 054107018 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.8 | kms | 666228.9 | 528050 | 1194278.9 | 2011-03-27 | 2011-07-31 | 613208.03 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Masbate | 0541 | Claveria | 054107 | San Ramon | 054107019 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.53 | kms | 553740.35 | 192807 | 746547.35 | 2011-05-18 | 2011-07-31 | 543166.58 |  | 2nd |  | Completed | 2011-07-31
H1 | V | 05 | Albay | 0505 | Pio Duran | 050513 | Malapay - Salvacion | 050513029 | Rehab./Improvement of Malapay - Salvacion FMR | 2 | Basic Access Infrastructure | Road | 1.34 | kms | 2850831.42 | 570166.28 | 3420997.7 | 2012-07-01 |  | 2280665.14 |  | 1st |  | On-going
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Baang-Sawmill | 054113001 | Improvement of Umabay Interior-Baang-Sawmill Road | 2 | Basic Access Infrastructure | Road | 3.1 | kms | 3663817 | 1230424 | 4894241 | 2011-06-14 | 2012-05-15 | 3453609.37 | 100% completed as per IA Jeb (May 31, 2012 reports) | 3rd |  | Completed | 2011-09-12
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Bagacay | 054113002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 569351 | 225082.5 | 794433.5 | 2011-06-08 | 2011-09-15 | 569348.93 |  | 3rd |  | Completed | 2011-08-07
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Barag | 054113004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 573328 | 278786.47 | 852114.47 | 2012-06-11 |  | 392938.42 |  | 1st |  | On-going | 2012-08-09
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Dacu | 054113005 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 533701.91 | 233201.08 | 766902.99 | 2012-04-30 |  | 426961.52 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-01
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Fabrica | 054113006 | Construction of Brgy. Water Supply System L-II | 1 | Basic Social Services | Water System | 1 | system | 620225.9 | 187787.47 | 808013.37 | 2012-06-18 |  | 496180.72 |  | 1st |  | On-going | 2012-08-17
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Guintorelan | 054113007 | Construction of Water System Level I | 1 | Basic Social Services | Water System | 1 | system | 740207 | 122982.2 | 863189.2 | 2011-06-03 | 2011-09-15 | 726187.24 |  | 3rd |  | Completed | 2011-08-02
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Lalaguna | 054113009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 477127.92 | 313923.29 | 791051.21 | 2012-04-30 |  | 381702.33 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-01
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Lomocloc | 054113010 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1437895.25 | 417978.39 | 1855873.64 | 2012-05-11 |  | 1006526.67 |  | 1st | Elem | On-going | 2012-08-28
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Luyong Catungan | 054113011 | Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.24 | kms | 1704717.24 | 447831.78 | 2152549.02 |  |  | 1193302.07 |  | 1st |  | Not yet started
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Mabuhay | 054113012 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 751543 | 172312.99 | 923855.99 | 2011-07-25 | 2011-11-15 | 712263.01 |  | 3rd |  | Completed | 2011-09-24
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Mabuhay | 054113012 | Construction of Foot Bridge with Pathway | 1 | Basic Access Infrastructure | Foot/Small Bridges | 200 | ln.m | 609528.92 | 187313.88 | 796842.8 | 2012-05-11 |  | 487623.14 |  | 1st |  | On-going | 2012-07-12
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Mandali | 054113013 | Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.9 | kms | 1885198 | 121960 | 2007158 | 2011-06-14 | 2011-10-15 | 1694768.49 |  | 2nd |  | Completed | 2011-07-28
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Mapuyo | 054113014 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq.m | 1435006 | 475151.8 | 1910157.8 | 2011-07-01 | 2011-10-15 | 1435006 | 39 HH (180 students) | 3rd | Elem | Completed | 2011-09-28
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Mapuyo | 054113014 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 2.512 | kms | 1620943.57 | 437276.04 | 2058219.61 | 2012-05-11 |  | 1134660.5 |  | 1st |  | On-going | 2012-08-28
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Marintoc | 054113015 | Construction of Water Supply System L-II | 1 | Basic Social Services | Water System | 1 | system | 1252140.75 | 365597.25 | 1617738 | 2012-06-08 |  | 1001712.68 |  | 1st |  | On-going | 2012-08-07
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Pinamalatican | 054113017 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 512335.46 | 206835.59 | 719171.05 | 2012-04-30 |  | 409868.68 | No movement as of July 31, 2012 | 1st | PS | On-going | 2012-07-02
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Polot | 054113021 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 747484 | 154222.2 | 901706.2 | 2011-08-12 | 2011-11-15 | 705156.93 |  | 3rd |  | Completed | 2011-10-10
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Sambulawan | 054113022 | Improvement of Cross Drainage Canal Along Sambulawan-Sinalongan Road | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 207 | ln.m | 1802565.97 | 497358.52 | 2299924.49 | 2012-07-23 |  | 1171667.88 |  | 1st |  | On-going | 2012-10-21
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Sawmill | 054113024 | Improvement of Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 1340695.12 | 460893.92 | 1801589.04 | 2012-06-25 |  | 1072556.09 |  | 1st |  | On-going | 2012-08-24
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Tabuc | 054113025 | Construction of 1 Unit 2 CL & 1 Unit CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq.m | 1950948 | 264825 | 2215773 | 2011-06-13 | 2011-10-15 | 1755853.2 |  | 2nd | Elem | Completed | 2011-08-17
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Tugbo | 054113027 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1306446 | 470279 | 1776725 | 2011-06-03 | 2011-10-15 | 1301445.45 |  | 3rd | Elem | Completed | 2011-09-01
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Tugbo | 054113027 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 564793.99 | 198181.09 | 762975.08 | 2012-05-07 |  | 451835.19 |  | 1st |  | On-going | 2012-07-09
H1 | V | 05 | Masbate | 0541 | Monreal | 054114 | Famosa | 054114002 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 2.745 | kms | 2401501.33 | 380202.96 | 2781704.29 | 2012-04-15 |  | 2165792.04 |  | 2nd |  | On-going | 2012-05-20
H1 | V | 05 | Masbate | 0541 | Monreal | 054114 | Morocborocan | 054114005 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.075 | kms | 1574931.26 | 268179.1 | 1843110.36 | 2012-02-23 | 2012-06-15 | 1416005.58 |  | 2nd |  | Completed | 2012-05-03
H1 | V | 05 | Masbate | 0541 | Monreal | 054114 | Real | 054114008 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 716482.22 | 153763.13 | 870245.35 | 2012-03-14 |  | 534280.87 |  | 1st |  | On-going | 2012-05-16
H1 | V | 05 | Masbate | 0541 | Monreal | 054114 | Rizal | 054114009 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 676086.49 | 150731.93 | 826818.42 |  |  | 500532.37 | Steel Truss | 1st | Elem | Not yet started
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Alin | 056207001 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.398 | kms | 1970103 | 295515.05 | 2265618.05 | 2012-01-18 | 2012-05-03 | 1950296.51 |  | 2nd |  | Completed | 2012-05-03
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Awai | 056207002 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 110 | ln.m | 294763.66 | 156009.19 | 450772.85 | 2012-03-27 | 2012-05-03 | 265287.3 |  | 2nd |  | Completed | 2012-05-03 | 0
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Baras | 056207006 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.1 | kms | 1854326 | 278149 | 2132475 | 2012-01-25 | 2012-05-11 | 1854326 |  | 2nd |  | Completed | 2012-05-11
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Cabugao | 056207009 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 2.98 | kms | 4209337 | 631400 | 4840737 | 2012-02-06 |  | 3788403.3 |  | 2nd |  | On-going | 2012-05-20
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Cristo | 056207011 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.278 | kms | 1851908 | 277786.5 | 2129694.5 | 2012-01-18 | 2012-05-03 | 1760319.24 |  | 2nd |  | Completed | 2012-05-03
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | De Vera | 056207013 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.567 | kms | 2054863 | 308229.8 | 2363092.8 | 2012-01-18 | 2012-05-03 | 1849376.7 |  | 2nd |  | Completed | 2012-05-03
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Gimagaan | 056207014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 656077.54 | 130048.21 | 786125.75 | 2012-03-03 | 2012-06-15 | 626263.91 |  | 2nd |  | Completed | 2012-05-10 | 0
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Pinamanaan | 056207031 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.212 | kms | 1820922 | 273138.44 | 2094060.44 | 2012-02-13 |  | 1638829.8 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-05-07
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Rawis | 056207034 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 342 | ln.m | 1136182.89 | 169774.46 | 1305957.35 | 2012-03-26 | 2012-06-15 | 908946.54 |  | 1st |  | Completed | 2012-05-31 | 0
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | San Isidro | 056207036 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.984 | kms | 1579326 | 236898.9 | 1816224.9 | 2012-01-23 | 2012-05-12 | 1460804.65 |  | 2nd |  | Completed | 2012-05-12
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Sevilla | 056207042 | Construction of Water System (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 624747 | 93712.05 | 718459.05 | 2012-01-30 | 2012-06-15 | 562272.3 |  | 2nd |  | Completed | 2012-03-30
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Sta. Cruz | 056207041 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 629.6 | ln.m | 1225130.91 | 183065.54 | 1408196.45 | 2012-02-03 | 2012-05-16 | 1224317.13 |  | 2nd |  | Completed | 2012-05-16 | 0
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Tinanogan | 056207046 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.508 | kms | 3415969 | 512395.55 | 3928364.55 | 2012-02-04 | 2012-05-18 | 2732775.2 |  | 1st |  | Completed | 2012-05-18
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Tupas | 056207050 | Construction of Productivity Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 48 | sq.m | 678306 | 101745.96 | 780051.96 | 2012-02-28 | 2012-05-08 | 651140.34 |  | 2nd |  | Completed | 2012-05-08
H1 | V | 05 | Sorsogon | 0562 | Donsol | 056207 | Vinisitahan | 056207051 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.3 | kms | 2128038 | 319206 | 2447244 | 2012-02-17 | 2012-06-15 | 2127976.88 |  | 2nd |  | Completed | 2012-05-31
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Aglimocon | 061907001 | Supply & Installation of 1 Unit Biomass-Fed Flat Bed Dryer 6 Tons Capacity Including Site Preparation | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 122.925 | sq.m | 890710.44 | 157622.56 | 1048333 |  |  | 712568.35 |  | 1st |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Alasaging | 061907002 | Supply & Installation of 1 Unit Biomass-Fed Flat Bed Dryer 6 Tons Capacity Including Site Preparation | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 122.925 | sq.m | 890710.44 | 157622.56 | 1048333 |  |  | 683941.35 |  | 1st |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Alayunan | 061907003 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 66.36 | sq. m | 635918.8 | 156432.2 | 792351 | 2012-06-11 |  | 317959.4 |  | 1st | PS | On-going | 2012-08-09 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Batabat | 061907005 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 66.36 | sq. m | 638168.7 | 158320.3 | 796489 | 2012-06-16 |  | 319084.35 |  | 1st | PS | On-going | 2012-08-14 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Bongbongan | 061907006 | Road Upgrading og 0.310 Km. FMR w/ 3mx130 Ln.m PCCP | 1 | Basic Access Infrastructure | Road | 0.31 | kms | 487863.22 | 157851.78 | 645715 | 2012-05-17 |  | 390290.58 |  | 1st |  | On-going | 2012-06-30
F2 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Canapian | 061907008 | Supply & Installation of 1 Unit Biomass-Fed Flat Bed Dryer 6 Tons Capacity Including Site Preparation | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 122.925 | sq.m | 890710.44 | 157622.56 | 1048333 | 2012-06-30 |  | 712568.35 |  | 1st |  | On-going | 2012-08-28
F2 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Carataya | 061907009 | Construction of CL Pre-School Building (PS) | 1 | Basic Social Services | School | 66.36 | sq. m | 607562.78 | 184820.22 | 792383 | 2012-07-16 |  | 303781.39 |  | 1st | PS | On-going | 2012-09-13 | 0
F2 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Duluan | 061907010 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 639772.19 | 157640.81 | 797413 | 2012-06-05 |  | 319886.1 |  | 1st | Elem | On-going | 2012-08-03 | 0
F2 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Fernandez | 061907012 | Road Protection & Embankment of 0.260 Km. | 1 | Basic Access Infrastructure | Road | 0.26 | kms | 535785.22 | 161953.78 | 697739 |  |  | 267892.61 |  | 1st |  | Not yet started
F2 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Guinbi- alan | 061907013 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1116467.74 | 353505.26 | 1469973 | 2012-05-21 |  | 558233.87 |  | 1st | Elem | On-going | 2012-08-18
F2 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Jebaca | 061907015 | Road Upgrading of 0.200 Km. FMR 3mx160 Ln.m Spot Concreting & 2 Station RCPC | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 491103.3 | 163926.7 | 655030 | 2012-05-23 |  | 392882.64 |  | 1st |  | On-going | 2012-07-21
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | New Guia | 061907018 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 620442.19 | 177262.81 | 797705 |  |  | 310221.09 |  | 1st | Elem | Not yet started |  | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Old Guia | 061907020 | Spot Concreting 2.60m Widthx120 Ln.m FMR w/ PCCP | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 341076.39 | 121025.61 | 462102 |  |  | 272861.11 |  | 1st |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Palaguian | 061907021 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 654788.44 | 141509.56 | 796298 | 2012-05-08 |  | 327394.22 |  | 1st | Elem | On-going | 2012-07-06 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Parallan | 061907022 | Construction of 400mx12.00 Ln.m Spillway RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 12 | ln.m | 303446.96 | 110723.04 | 414170 |  |  | 242757.56 |  | 1st |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Piña | 061907023 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 63 | sq. m | 657781.74 | 139087.26 | 796869 | 2012-05-22 |  | 328890.87 |  | 1st | Elem | On-going | 2012-07-20 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Poblacion Ilawod | 061907024 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 659934.65 | 136732.35 | 796667 | 2012-06-18 |  | 329967.33 |  | 1st | Elem | On-going | 2012-08-16 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Poblacion Ilaya | 061907025 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 66.36 | sq. m | 637036.96 | 159078.04 | 796115 | 2012-06-06 |  | 318518.48 |  | 1st | Elem | On-going | 2012-08-04 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Quevedo | 061907019 | Supply & Installation of 1 Unit Biomass-Fed Flat Bed Dryer 6 Tons Capacity Including Site Preparation | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 122.925 | sq.m | 889810.43 | 158522.57 | 1048333 |  |  | 683221.34 |  | 1st |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Quinabonglan | 061907028 | Tirepath Concreting of 0.800 Km. FMR | 1 | Basic Access Infrastructure | Access Trail | 0.8 | kms | 1070128.18 | 309182.82 | 1379311 | 2012-05-31 |  | 856102.53 |  | 1st |  | On-going | 2012-08-28
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Quinat-uyan | 061907029 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 66.36 | sq. m | 634215.9 | 162512.1 | 796728 | 2012-06-16 |  | 317107.95 |  | 1st | PS | On-going | 2012-08-14 | 0
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | Salgan | 061907030 | Road Upgrading of 0.148 Km. & 300mx90.00Ln.m PCCP | 1 | Basic Access Infrastructure | Road | 0.148 | kms | 360611.07 | 87917.93 | 448529 | 2012-05-27 |  | 288488.85 |  | 1st |  | On-going | 2012-07-22
H1 | VI | 06 | Capiz | 0619 | Ma- Ayon | 061907 | West Villaflores | 061907034 | Construction of 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | 66.36 | sq. m | 600915.27 | 191440.73 | 792356 | 2012-07-20 |  | 300457.64 |  | 1st | PS | On-going | 2012-09-17 | 0
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Agcococ | 061917003 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1169506.81 | 272376.19 | 1441883 | 2012-04-18 |  | 584753.41 |  | 1st | Elem | On-going | 2012-07-17
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Bag- Ong Barrio | 061917009 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1159662.46 | 280299.54 | 1439962 | 2012-04-10 |  | 1043696.21 | No movement as of July 31, 2012 | 2nd | HS | On-going | 2012-07-09
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Buri | 061917011 | Construction of Foottrail | 1 | Basic Access Infrastructure | Access Trail | 11.607 | kms | 1308209.54 | 268382.27 | 1576591.81 | 2012-06-13 |  | 1046567.63 | Revised TPC from 1,711,798.40 to 1,576,591.81 | 1st |  | On-going | 2012-09-21 | 0
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Camburanan | 061917012 | Construction of 1 Unit 5 Stall Mini Trading | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 51.6 | sq.m | 998126.09 | 215413.86 | 1213539.95 |  |  | 0 |  |  |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Carida | 061917014 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1164410.29 | 274111.71 | 1438522 | 2012-04-02 |  | 1047969.26 | No movement as of July 31, 2012 | 2nd | Elem | On-going | 2012-07-01
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Da-an Sur | 061917018 | Road Rehabilitation w/ Spot Concreting | 1 | Basic Access Infrastructure | Road | 3.4 | kms | 4139600 | 772423 | 4912023 |  |  | 2069800 |  | 1st |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Hilwan | 061917021 | Pre & Post Harvest Facilities | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 24 | sq.m | 455170.4 | 117396.6 | 572567 |  |  | 0 |  |  |  | Not yet started
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Maliao | 061917028 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 931414.58 | 228435.42 | 1159850 | 2012-05-16 |  | 465707.29 |  | 1st | Elem | On-going | 2012-07-15
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Malitbog | 061917029 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1112606.37 | 327835.63 | 1440442 | 2012-05-16 |  | 556303.18 |  | 1st | Elem | On-going | 2012-08-14
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Poblacion | 061917032 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1164992.9 | 273049.1 | 1438042 | 2012-06-13 |  | 582496.45 |  | 1st | Elem | On-going | 2012-09-11
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Rizal Sur | 061917034 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 986947.82 | 287783.27 | 1274731.09 | 2012-05-15 |  | 493473.91 |  | 1st | Elem | On-going | 2012-08-30
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Roxas | 061917036 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1176206.37 | 264236.63 | 1440443 | 2012-05-05 |  | 588103.18 |  | 1st | HS | On-going | 2012-06-04
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Francisco | 061917039 | Road Improvement w/ Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.7 | kms | 942454.2 | 197422.8 | 1139877 | 2012-05-20 |  | 471227.1 |  | 1st |  | On-going | 2012-07-24
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Jose | 061917041 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1165232.46 | 272810.54 | 1438043 | 2012-04-03 |  | 1048709.21 |  | 2nd | Elem | On-going | 2012-07-02
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Julian | 061917042 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1166585.07 | 271937.93 | 1438523 | 2012-06-20 |  | 583292.53 |  | 1st | Elem | Not yet started | 2012-09-18
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Nicolas | 061917045 | Road Improvement w/ Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.7 | kms | 1004299.5 | 209628.5 | 1213928 | 2012-06-04 |  | 502149.75 |  | 1st |  | On-going | 2012-07-24
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Roque | 061917047 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1170419.85 | 273863.15 | 1444283 | 2012-06-21 |  | 585209.92 |  | 1st | Elem | Not yet started | 2012-09-19
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Vicente | 061917048 | Road Improvement w/ Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.534 | kms | 1480461.5 | 298714.5 | 1779176 | 2012-05-04 |  | 740230.75 |  | 1st |  | On-going | 2012-07-25
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Miguel Ilawod | 061917043 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1146592.9 | 295289.1 | 1441882 | 2012-06-21 |  | 573296.45 |  | 1st | Elem | On-going | 2012-09-19
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Sta. Ana | 061917049 | Construction of Spillway w/ Eight Lines RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 50 | ln.m | 319809.19 | 294437.81 | 614247 | 2012-07-10 |  | 255847.35 |  | 1st |  | Not yet started | 2012-08-15
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Sta. Petronila | 061917050 | Road Improvement w/ Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.675 | kms | 906492.22 | 187414.78 | 1093907 | 2012-06-06 |  | 453246 |  | 1st |  | On-going | 2012-07-17
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Tabon | 061917054 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 683302.12 | 139521.09 | 822823.21 | 2012-07-09 |  | 536480.3 |  | 1st |  | On-going | 2012-09-27
H1 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Tacayan | 061917055 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 706120.2 | 157264.8 | 863385 | 2012-07-10 |  | 516743.98 |  | 1st |  | Not yet started | 2012-09-28
F2 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Taft | 061917056 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1168294.46 | 272149.34 | 1440443.8 | 2012-03-31 |  | 1051465.01 | No movement as of July 31, 2012 | 2nd | HS | On-going | 2012-06-30
F2 | VI | 06 | Capiz | 0619 | Tapaz | 061917 | Taslan | 061917058 | Road Improvement w/ Spot Concreting | 1 | Basic Access Infrastructure | Road | 1 | kms | 1263010.46 | 258478.54 | 1521489 | 2012-06-04 |  | 631505.23 |  | 1st |  | On-going | 2012-07-03
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Bugnay | 063008002 | Construction of Health Station w/ Birthing Facilities & Water Tank | 1 | Basic Social Services | Health Station | 51 | sq.m | 760378.27 | 256171.53 | 1016549.8 | 2012-05-22 |  | 380189.13 |  | 1st |  | On-going | 2012-08-01
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | California | 063008004 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 642239 | 192688.84 | 834927.84 | 2012-05-02 |  | 321119.5 |  | 1st |  | On-going | 2012-07-12
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Del Pilar | 063008005 | Construction of Warehouse w/ Post harvest Facilities & Water Tank | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 96 | sq.m | 882035.65 | 243412.27 | 1125447.92 |  |  | 705628.52 |  | 1st |  | Not yet started
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Dela Peña | 063008006 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 646281.07 | 188646.77 | 834927.84 | 2012-05-16 |  | 323140.53 |  | 1st |  | On-going | 2012-07-26
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | General Luna | 063008007 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 642460.67 | 192467.17 | 834927.84 | 2012-05-14 |  | 321230.33 |  | 1st |  | On-going | 2012-07-24
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | La Fortuna | 063008009 | Construction of Health Station w/ Birthing Facilities & Water Tank | 1 | Basic Social Services | Health Station | 51 | sq.m | 789252.77 | 227297.03 | 1016549.8 | 2012-05-30 |  | 394626.38 |  | 1st |  | On-going | 2012-08-09
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Lipata | 063008010 | Construction of 1 Unit 2 CL School Building w/ Water Tank (Elem) | 1 | Basic Social Services | School | 133.2 | sq. m | 1045914.78 | 319949.56 | 1365864.34 | 2012-02-19 |  | 522957.39 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-05-12
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Nueva Invencion | 063008012 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 711740.7 | 216269.61 | 928010.31 | 2012-06-11 |  | 355870.35 |  | 1st |  | On-going | 2012-08-21
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Nueva Sevilla | 063008013 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 631809.47 | 200955.37 | 832764.84 | 2012-03-25 |  | 568628.52 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-06-04
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Rizal | 063008017 | Construction of Health Station w/ Birthing Facilities & Water Tank | 1 | Basic Social Services | Health Station | 51 | sq.m | 759527.13 | 257022.66 | 1016549.79 | 2012-05-21 |  | 379763.57 |  | 1st |  | On-going | 2012-07-31
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | San Antonio | 063008019 | Construction of 1 Unit 2 CL School Building w/ Water Tank (Elem) | 1 | Basic Social Services | School | 133.2 | sq. m | 748398.97 | 617465.37 | 1365864.34 | 2012-02-26 |  | 374199.48 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-05-19
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | San Fernando | 063008021 | Construction of 1 Unit 1 CL School Building w/ Water Tank (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 617963.6 | 261112.1 | 879075.7 | 2012-07-02 |  | 308981.8 |  | 1st | Elem | On-going | 2012-09-11
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | San Geronimo | 063008024 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 635967.17 | 198960.67 | 834927.84 | 2012-07-01 |  | 317983.58 |  | 1st |  | On-going | 2012-09-10
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | San Juan | 063008025 | Construction of Health Station w/ Birthing Facilities & Water Tank | 1 | Basic Social Services | Health Station | 51 | sq.m | 792465.77 | 224084.03 | 1016549.8 | 2012-05-17 |  | 713219.19 |  | 2nd |  | On-going | 2012-07-27
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | San Miguel | 063008027 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 642793.23 | 192134.6 | 834927.83 | 2012-05-21 |  | 578513.91 |  | 2nd |  | On-going | 2012-07-31
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | San Roque | 063008029 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 642362.57 | 190402.27 | 832764.84 | 2012-05-13 |  | 578126.31 |  | 2nd |  | On-going | 2012-07-23
H1 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Santiago | 063008030 | Construction of Day Care Center w/ Facilities & Water Tank | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 616963.43 | 217964.4 | 834927.83 | 2012-05-12 |  | 308481.72 |  | 1st |  | On-going | 2012-07-22
F2 | VI | 06 | Iloilo | 0630 | Barotac Viejo | 063008 | Santo Tomas | 063008032 | Construction of Health Station w/ Birthing Facilities & Water Tank | 1 | Basic Social Services | Health Station | 51 | sq.m | 791445.77 | 225104.03 | 1016549.8 | 2012-05-15 |  | 395722.88 |  | 1st |  | On-going | 2012-07-25
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Agba-o | 063010001 | Road Improvement of 0.543 Km. FMR | 1 | Basic Access Infrastructure | Road | 0.543 | kms | 534904.35 | 110095.65 | 645000 | 2012-03-26 |  | 481419.92 |  | 2nd |  | On-going | 2012-05-24
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Alabidhan | 063010002 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1157913.04 | 232366.96 | 1390280 | 2012-04-04 |  | 1042121.74 |  | 2nd | Elem | On-going | 2012-07-02
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Cairohan | 063010004 | Road Concreting of 0.12 Km. FMR | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 413586.96 | 226413.04 | 640000 | 2012-03-26 | 2012-06-15 | 206793.48 |  | 1st |  | Completed | 2012-05-24
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Guinhulacan | 063010005 | Construction of 1 Unit 2 Classroom School Building with Facilities | 1 | Basic Social Services | School | 144 | sq. m | 1177522.46 | 104025 | 1281547.46 |  |  | 0 |  |  | Elem | Not yet started
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Guinhulucan | 063010005 | Road Concreting of 0.20 Km. Grouted Riprap & Side Ditches FMR | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 783304.35 | 146755.65 | 930060 | 2012-04-23 | 2012-06-15 | 391652.17 |  | 1st |  | Completed | 2012-06-11
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Inamyungan | 063010006 | Construction of 1 Unit 2 CL Primary School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1157913.04 | 232366.96 | 1390280 | 2012-04-11 |  | 1042121.74 |  | 2nd | Elem | On-going | 2012-07-10
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Malitbog Ilawod | 063010007 | Road Construction of 1.26 Km. FMR | 1 | Basic Access Infrastructure | Road | 1.26 | kms | 970530.43 | 179469.57 | 1150000 | 2012-04-17 |  | 485265.22 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-15
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Poblacion | 063010010 | Construction of Day Care Center w/ Facilities | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 613604.35 | 138680.65 | 752285 | 2012-04-03 |  | 552243.92 |  | 2nd |  | On-going | 2012-06-02
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Tapacon | 063010013 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 649017.39 | 141282.61 | 790300 | 2012-04-16 |  | 584115.65 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-06-15
F2 | VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Tubod | 063010014 | Road Improvement of 1.25 Km. FMR | 1 | Basic Access Infrastructure | Road | 1.25 | kms | 719226.09 | 137773.91 | 857000 | 2012-04-20 |  | 359613.04 |  | 1st |  | On-going | 2012-06-19
F2 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Agcalaga | 063013002 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 610181.32 | 155960.57 | 766141.89 | 2012-06-04 |  | 549163.18 |  | 2nd | Elem | On-going | 2012-08-03 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Aglonok | 063013004 | Construction of (1) Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 716103.12 | 137381.81 | 853484.93 | 2012-05-10 |  | 572882.5 |  | 1st |  | On-going | 2012-07-12 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Alibunan | 063013006 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 199.08 | sq. m | 1564312.94 | 452341.06 | 2016654 | 2012-04-05 |  | 1407881.65 |  | 2nd | Elem | On-going | 2012-07-03 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badlan Grande | 063013007 | Construction of (1) Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 625060.02 | 159000.98 | 784061 | 2012-06-04 |  | 562554.02 |  | 2nd |  | On-going | 2012-08-03 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badlan Pequeño | 063013008 | Construcion of Flood Control (Dike) | 1 | Environmental Protection and Conservation | River Control/Flood Control | 40 | ln.m | 1045905.33 | 367928.75 | 1413834.08 |  |  | 836724.27 |  | 1st |  | Not yet started |  | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Baje San Julian | 063013062 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 596206.5 | 187362 | 783568.5 | 2012-05-28 |  | 540392.85 |  | 2nd | Elem | On-going | 2012-07-27 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Banban Grande | 063013012 | Improvement of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 350 | ln.m | 551245.38 | 140665.62 | 691911 | 2012-04-16 |  | 479984.96 | No movement as of Jul 31, 2012 | 2nd |  | On-going | 2012-06-14 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Banban Pequeño | 063013013 | Construction of 1 CL Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 629139.55 | 163667.5 | 792807.05 | 2012-05-08 |  | 566225.59 |  | 2nd | Elem | On-going | 2012-07-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Binolosan Grande | 063013015 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 803391.53 | 152243.73 | 955635.26 | 2012-06-19 |  | 648179.64 |  | 2nd | Elem | On-going | 2012-08-18 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Cabagiao | 063013017 | Pre & Post Harvest Facilities | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 824553.87 | 181346.13 | 1005900 | 2012-05-28 |  | 659643.09 |  | 1st |  | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Cahigon | 063013020 | Construction of (1) Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 666077.64 | 128213.72 | 794291.36 | 2012-05-08 |  | 599469.87 |  | 2nd |  | On-going | 2012-07-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Camalongo | 063013023 | Post Harvest Facilities with Garage (Travelling Rice Mill) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 749394.8 | 177505.2 | 926900 | 2012-06-03 |  | 599515.84 |  | 1st |  | On-going | 2012-07-13 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Caratagan | 063013025 | Pre & Post Harvest Facilities with Garage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 936626.4 | 203505.6 | 1140132 | 2012-05-18 |  | 749301.12 |  | 1st |  | On-going | 2012-06-26 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Carvasana | 063013026 | Post Harvest Facilities (Mechanical Dryer) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 915026.5 | 191773.5 | 1106800 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Dalid | 063013027 | Road Improvement of 0.97 km. FMR | 1 | Basic Access Infrastructure | Road | 0.97 | kms | 1050293.05 | 245488.95 | 1295782 | 2012-04-16 |  | 630175.83 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-08-03 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Datagan | 063013028 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 640730.15 | 147492.51 | 788222.66 | 2012-06-01 |  | 576657.14 |  | 2nd | Elem | On-going | 2012-07-31 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Garangan | 063013032 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 733221.4 | 189167.5 | 922388.9 | 2012-05-21 |  | 467101.6 |  | 1st | Elem | On-going | 2012-07-19 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Guinbonyugan | 063013034 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.6 | sq.m | 759506.1 | 139227.5 | 898733.6 | 2012-07-17 |  | 571378.53 |  | 1st |  | On-going | 2012-09-15 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Hilwan | 063013037 | Construction of (1) Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 715450.56 | 129156.72 | 844607.28 | 2012-05-11 |  | 643905.51 |  | 2nd |  | On-going | 2012-07-09 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Impalidan | 063013038 | Road Improvement of 0.25 km. FMR | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 858174.91 | 197186.09 | 1055361 | 2012-06-22 |  | 429087.46 |  | 1st |  | On-going | 2012-09-20 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Jamin-ay | 063013041 | Construction of (1) Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 646397 | 137525.7 | 783922.7 | 2012-05-08 |  | 581757.3 |  | 2nd |  | On-going | 2012-07-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Libot | 063013043 | Road Improvement of 0.12 km. FMR | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 471061.51 | 106262.49 | 577324 | 2012-04-30 |  | 333984.5 |  | 1st |  | On-going | 2012-07-08 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Lonoy | 063013044 | Construction of Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 634220.02 | 152380.98 | 786601 | 2012-05-28 |  | 570798.02 |  | 2nd |  | On-going | 2012-07-27 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Mambiranan | 063013049 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 617084.5 | 160084.5 | 777169 | 2012-05-21 |  | 555376.05 |  | 2nd | Elem | On-going | 2012-07-19 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Marandig | 063013051 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.6 | sq.m | 760865.55 | 188134.45 | 949000 | 2012-06-25 |  | 574817.28 |  | 1st |  | On-going | 2012-08-24 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Masaroy | 063013052 | Construction of (2) Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 2620 | ln.m | 2016035.41 | 399121.71 | 2415157.12 |  |  | 1616904.46 |  | 1st |  | Not yet started |  | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Owak | 063013056 | Road Improvement of 1.32 km. FMR | 1 | Basic Access Infrastructure | Road | 1.32 | kms | 1345379.18 | 319673.82 | 1665053 | 2012-04-16 |  | 672689.59 |  | 1st |  | On-going | 2012-08-13 | 0
H1 | V | 05 | Masbate | 0541 | Mobo | 054113 | Baang-Sawmill | 054113024 | Improvement of Umabay Interior-Baang-Sawmill Road | 2 | Basic Access Infrastructure | Road | 3.1 | kms | 3663817 | 1230424 | 4894241 | 2011-06-14 | 2012-05-15 | 3453609.37 | 100% completed as per IA Jeb (May 31, 2012 reports) | 3rd |  | Completed | 2011-09-12
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Pob. Delgado, Barrio Calinog, Gama Grande | 063013058 | Construction of (1) Hanging Foot Bridge | 3 | Basic Access Infrastructure | Foot/Small Bridges | 100 | ln.m | 2721853.5 | 682098.17 | 3403951.67 |  |  | 2357184.45 |  | 1st |  | Not yet started |  | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | San Nicolas | 063013063 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 632646.5 | 138207.5 | 770854 | 2012-04-18 |  | 569381.85 |  | 2nd | Elem | On-going | 2012-06-16 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Simsiman | 063013064 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 132.72 | sq. m | 1125225.75 | 253260.5 | 1378486.25 | 2012-05-29 |  | 1003336.95 |  | 2nd | HS | On-going | 2012-08-17 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Supanga | 063013074 | Construction of (1) Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 680570.06 | 118638.13 | 799208.19 | 2012-05-14 |  | 612513.05 |  | 2nd |  | On-going | 2012-07-12 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tibiao | 063013068 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1182952.73 | 209308.9 | 1392261.63 | 2012-04-23 |  | 1064657.46 |  | 2nd | Elem | On-going | 2012-07-11 | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tigbayog | 063013069 | Post Harvest Facilities with Garage (Rice Mill) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 675107.22 | 155492.78 | 830600 | 2012-06-20 |  | 607596.5 |  | 2nd |  | On-going | 2012-07-30 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Alipata | 063014002 | Construction of 1 Unit 2 CL School Building w/ Hauling (HS) | 1 | Basic Social Services | School | 133.2 | sq. m | 1214872.77 | 263359.5 | 1478232.27 | 2012-05-05 |  | 607436.38 | Island Brgy | 1st | HS | On-going | 2012-07-04 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Bancal | 063014004 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 555140.09 | 190775 | 745915.09 | 2012-05-08 |  | 277570.04 | Mainland Brgy | 1st | Elem | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Barosbos | 063014006 | Construction of Health Station | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 588908.09 | 195395 | 784303.09 | 2012-05-02 |  | 294454.05 | Mainland Brgy | 1st |  | On-going | 2012-07-01 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Bolo | 063014011 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 562845.09 | 184250 | 747095.09 | 2012-05-07 |  | 281422.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Buenavista | 063014013 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 133.2 | sq. m | 1193463.27 | 300765 | 1494228.27 | 2012-05-04 |  | 596731.64 | Island Brgy | 1st | Elem | On-going | 2012-07-03 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabilao Grande | 063014016 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 563217.09 | 183758 | 746975.09 | 2012-05-08 |  | 281608.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabuguana | 063014018 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 550375.09 | 194560 | 744935.09 | 2012-04-28 |  | 275187.54 | Mainland Brgy | 1st | Elem | On-going | 2012-06-27 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Cawayan | 063014019 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 561910.09 | 0 | 745695.09 | 2012-05-07 |  | 280955.04 | Mainland Brgy | 1st | Elem | On-going | 2012-07-06 | 183785
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Dayhagan | 063014020 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 560071.09 | 186544 | 746615.09 | 2012-05-07 |  | 280035.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Gabi | 063014021 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 133.2 | sq. m | 1167838.27 | 320640 | 1488478.27 | 2012-05-18 |  | 583919.13 | Island Brgy | 1st | Elem | On-going | 2012-07-17 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Granada | 063014022 | Construction of 1 Unit 1 CL School Building w/ Hauling (HS) | 1 | Basic Social Services | School | 66.6 | sq. m | 503448.14 | 371925.72 | 875373.86 | 2012-05-24 |  | 251724.07 | Island Brgy | 1st | HS | On-going | 2012-07-23 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Guinticgan | 063014023 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 562625.09 | 187650 | 750275.09 | 2012-05-03 |  | 281312.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-02 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Isla de Cana | 063014014 | Construction of Health Station w/ Amenities & Hauling | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 778904.76 | 150769.83 | 929674.59 | 2012-05-26 |  | 389452.38 | Island Brgy | 1st |  | On-going | 2012-07-25 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Lantangan | 063014024 | Construction of 1 Unit 2 CL School Building w/ Hauling (HS) | 1 | Basic Social Services | School | 133.2 | sq. m | 1145492.27 | 342640 | 1488132.27 | 2012-05-10 |  | 572746.13 | Island Brgy | 1st | HS | On-going | 2012-07-09 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Nalumsan | 063014026 | Construction of 1 Unit Day Care Center w/ Facilities | 1 | Basic Social Services | Day Care Center | 52.5 | sq.m | 547667.67 | 186729.45 | 734397.12 | 2012-05-08 |  | 273833.83 | Mainland Brgy | 1st |  | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Pantalan | 063014027 | Construction of 1 Unit Day Care Center w/ Amenities & Hauling | 1 | Basic Social Services | Day Care Center | 52.5 | sq.m | 641519.62 | 173970 | 815489.62 | 2012-05-15 |  | 320759.81 | Island Brgy | 1st |  | On-going | 2012-07-14 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Poblacion | 063014028 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 553635.09 | 191140 | 744775.09 | 2012-05-30 |  | 276817.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-29 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta (Bolocawe) | 063014029 | Construction of 1 Unit 1 CL School Building (HS) | 1 | Basic Social Services | School | 66.6 | sq. m | 563385.09 | 183210 | 746595.09 | 2012-04-28 |  | 281692.54 | Mainland Brgy | 1st | HS | On-going | 2012-06-27 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta Batuanan | 063014007 | Construction of 1 Unit Health Station w/ Amenities & Hauling | 1 | Basic Social Services | Health Station | 55.5 | sq.m | 747839.67 | 141734.92 | 889574.59 | 2012-05-08 |  | 373919.83 | Island Brgy | 1st |  | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Tabugon | 063014031 | Construction of 1 Unit 1 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 637208.86 | 211845 | 849053.86 | 2012-05-08 |  | 318604.43 | Island Brgy | 1st | Elem | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Talingting | 063014032 | Construction of 1 Unit 2 CL School Building w/ Hauling (HS) | 1 | Basic Social Services | School | 133.2 | sq. m | 1184322.87 | 303809.4 | 1488132.27 | 2012-05-08 |  | 592161.43 | Island Brgy | 1st | HS | On-going | 2012-07-07 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Tarong | 063014033 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 554245.09 | 195230 | 749475.09 | 2012-05-07 |  | 277122.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Carles | 063014 | Tupaz | 063014035 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 560635.09 | 186360 | 746995.09 | 2012-05-11 |  | 280317.54 | Mainland Brgy | 1st | Elem | On-going | 2012-07-10 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Agsirab | 063025001 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1189996 | 222005 | 1412001 | 2012-04-30 |  | 713997.6 |  | 1st | Elem | On-going | 2012-07-19
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bagongbong | 063025005 | Road Improvement of 0.62 km. FMR | 1 | Basic Access Infrastructure | Road | 0.62 | kms | 1485969 | 265365 | 1751334 |  |  | 1173385.63 |  | 1st |  | Not yet started
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Pob. Delgado, Barrio Calinog, Gama Grande | 063013030 | Construction of (1) Hanging Foot Bridge | 3 | Basic Access Infrastructure | Foot/Small Bridges | 100 | ln.m | 2721853.5 | 682098.17 | 3403951.67 |  |  | 2357184.45 |  | 1st |  | Not yet started |  | 0
H1 | VI | 06 | Iloilo | 0630 | Calinog | 063013 | Pob. Delgado, Barrio Calinog, Gama Grande | 063013030 | Construction of (1) Hanging Foot Bridge | 3 | Basic Access Infrastructure | Foot/Small Bridges | 100 | ln.m | 2721853.5 | 682098.17 | 3403951.67 |  |  | 2357184.45 |  | 1st |  | Not yet started |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Balagiao, Pasig & Natividad | 063025006 | Construction of 73 Ln.m Hanging Bridge | 3 | Basic Access Infrastructure | Foot/Small Bridges | 73 | ln.m | 2363553 | 423375 | 2786928 | 2012-04-14 |  | 1890842.4 | Balagiao, Pasig & Natividad | 1st |  | On-going | 2012-09-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bansag | 063025008 | Road Improvement of 0.99 km. FMR | 1 | Basic Access Infrastructure | Road | 0.99 | kms | 1502802 | 261510 | 1764312 | 2012-04-23 |  | 1051961.4 |  | 1st |  | On-going | 2012-07-21
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bayuco | 063025009 | Construction of Health Station w/ Amenities & Hauling | 1 | Basic Social Services | Health Station | 51 | sq.m | 645734.5 | 151225 | 796959.5 | 2012-05-10 |  | 581161.05 |  | 2nd |  | On-going | 2012-07-09 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Binaba-an Tirador | 063025014 | Road Improvement of 0.53 km. FMR | 1 | Basic Access Infrastructure | Road | 0.53 | kms | 451215 | 75750 | 526965 | 2012-04-21 |  | 360972 |  | 1st |  | On-going | 2012-05-21
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bonbon | 063025015 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1168889 | 221775 | 1390664 | 2012-04-23 |  | 583194.5 |  | 1st | Elem | On-going | 2012-07-12 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bontoc | 063025016 | Construction of Day Care Center w/ Facilities & Hauling | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 646279 | 133410 | 779689 | 2012-04-19 |  | 581651.1 |  | 2nd |  | On-going | 2012-05-18
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Burirao | 063025018 | Road Improvement of 0.70 km. FMR | 1 | Basic Access Infrastructure | Road | 0.7 | kms | 932861 | 152440 | 1085301 | 2012-05-14 |  | 653002.7 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-28
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cabugao | 063025021 | Road Improvement of 0.365 km. FMR | 1 | Basic Access Infrastructure | Road | 0.365 | kms | 901963 | 152840 | 1054803 | 2012-04-07 |  | 631374.1 |  | 1st |  | On-going | 2012-05-30
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Caloy-Ahan | 063025024 | Construction of Day Care Center w/ Facilities | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 653764 | 123965 | 777729 | 2012-04-12 |  | 588387.6 |  | 2nd |  | On-going | 2012-06-11
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Caninguan | 063025025 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1100503.75 | 246625 | 1347128.75 | 2012-05-12 |  | 990453.38 |  | 2nd | Elem | On-going | 2012-07-21 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cayan Oeste | 063025028 | Road Improvement of 1.60 km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.6 | kms | 1443034 | 287025 | 1730059 | 2012-04-27 |  | 1010123.8 |  | 1st |  | On-going | 2012-07-21
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Corot-on | 063025029 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 667551.75 | 132345 | 799896.75 | 2012-05-02 |  | 600796.58 |  | 2nd | Elem | On-going | 2012-07-01 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cubay | 063025031 | Road Opening of 0.90 km. | 1 | Basic Access Infrastructure | Road | 0.9 | kms | 2312337 | 386910 | 2699247 | 2012-05-22 |  | 1618635.9 |  | 1st |  | On-going | 2012-09-06
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cunarum | 063025032 | Construction of 1 Unit 1 CL Primary School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 677114 | 122730 | 799844 | 2012-05-01 |  | 609402.6 |  | 2nd | Elem | On-going | 2012-06-30 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Daanbanwa | 063025033 | Road Improvement of 1 Km. FMR | 1 | Basic Access Infrastructure | Road | 1 | kms | 1882961 | 340815 | 2223776 | 2012-05-14 |  | 1506368.8 |  | 1st |  | On-going | 2012-07-28
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Gines | 063025034 | Road Improvement of 1.10 Km. FMR | 1 | Basic Access Infrastructure | Road | 1.1 | kms | 1511354 | 263065 | 1774419 | 2012-05-23 |  | 1209083.2 |  | 1st |  | On-going | 2012-08-16
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Hipgos | 063025035 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1168869 | 222775 | 1391644 | 2012-01-09 |  | 1051982.1 |  | 2nd | Elem | On-going | 2012-03-29
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Legayada | 063025040 | Construction of 1 Unit 1 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 666621.75 | 133345 | 799966.75 | 2012-04-24 |  | 599959.58 |  | 2nd | Elem | On-going | 2012-06-23 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Lumanay | 063025041 | Construction of Health Station w/ Amenities & Hauling | 1 | Basic Social Services | Health Station | 51 | sq.m | 662948 | 127080 | 790028 | 2012-05-24 |  | 397768.8 |  | 1st |  | On-going | 2012-07-23 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Madarag | 063025042 | Construction of 1 Unit 1 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 666056.75 | 133630 | 799686.75 | 2012-05-05 |  | 599451.07 |  | 2nd | Elem | On-going | 2012-07-03 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Maite Grande | 063025044 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1080551.5 | 261885 | 1342436.5 | 2012-06-18 |  | 540275.75 |  | 1st | Elem | On-going | 2012-09-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Maite Pequeno | 063025045 | Road Opening of 0.50 km. | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 843215 | 130585 | 973800 | 2012-05-13 |  | 674572 |  | 1st |  | On-going | 2012-06-12
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Malag-it | 063025046 | Road Improvement of 0.22 Km. FMR | 1 | Basic Access Infrastructure | Road | 0.22 | kms | 477095.25 | 177389.75 | 654485 | 2012-06-02 |  | 429385.73 |  | 2nd |  | On-going | 2012-07-02 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Manaulan | 063025047 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1172459 | 218205 | 1390664 | 2012-04-20 |  | 1055213.1 |  | 2nd | Elem | On-going | 2012-07-10
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Maribong | 063025048 | Construction of 0.24 km. Drainage System w/ Cross Drain | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 0.24 | ln.m | 746024 | 145920 | 891944 | 2012-04-20 |  | 671421.6 |  | 2nd |  | On-going | 2012-07-02
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Marong | 063025049 | Construction of Day Care Center w/ Facilities & Hauling | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 610078 | 188540 | 798618 | 2012-05-11 |  | 549070.2 |  | 2nd |  | On-going | 2012-07-10 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Pandan | 063025053 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1077912 | 272625 | 1350537 | 2012-04-23 |  | 991391.04 |  | 2nd | Elem | On-going | 2012-07-12 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Panuran | 063025054 | Construction of Community Market w/ Hauling | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 369.25 | sq.m | 1226188 | 248075 | 1474263 | 2012-05-28 |  | 735712.8 |  | 1st |  | On-going | 2012-08-26
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Poblacion Ilawod | 063025057 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 705116 | 126230 | 831346 | 2012-01-17 |  | 629523.9 | No movement as of July 31, 2012 | 2nd | Elem | On-going | 2012-03-17 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Poong | 063025059 | Construction of 1 Unit 1 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 66.36 | sq. m | 678121.75 | 121775 | 799896.75 | 2012-05-10 |  | 610309.58 |  | 2nd | Elem | On-going | 2012-07-09 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Sibaguan | 063025066 | Road Improvement of 0.50 km. FMR | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 770564 | 113910 | 884474 | 2012-04-12 |  | 537935.58 |  | 1st |  | On-going | 2012-05-22 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Simsiman | 063025067 | Construction of 1 Unit 2 CL School Building w/ Hauling (Elem) | 1 | Basic Social Services | School | 132.72 | sq. m | 1167289 | 223375 | 1390664 | 2012-01-09 |  | 1049930.1 | No movement as of May 31, 2012 reports | 2nd | Elem | On-going | 2012-03-29 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Tranghawan | 063025070 | Construction of Health Station w/ Amenities | 1 | Basic Social Services | Health Station | 51 | sq.m | 650033 | 140075 | 790108 | 2012-04-11 |  | 585029.7 |  | 2nd |  | On-going | 2012-06-10 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Tubungan | 063025071 | Road Improvement of 0.46 Km. FMR | 1 | Basic Access Infrastructure | Road | 0.46 | kms | 592977 | 107780 | 700757 | 2012-01-18 |  | 474381.6 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-02-20
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Agpipili | 063027001 | Construction of 1 CL School Building w/ Facilities (Elem) | 1 | Basic Social Services | School | 84.14 | sq. m | 654694 | 144315.36 | 799009.36 | 2012-05-15 |  | 327347 |  | 1st | Elem | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Alcantara | 063027002 | Travelling Rice Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 531336 | 87451.5 | 618787.5 |  |  | 425068.8 |  | 1st |  | Not yet started
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Almeñana | 063027003 | Travelling Rice Mill w/ Garage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 599524 | 396541.48 | 996065.48 | 2012-07-15 |  | 423804.8 | Note: Revised KC & LCC Cost | 1st |  | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Anabo | 063027004 | Construction of 1 CL School Building w/ Facilities (Elem) | 1 | Basic Social Services | School | 84.14 | sq. m | 689329 | 149969.76 | 839298.76 | 2012-01-24 |  | 620396.1 | No movement as of May 31, 2012 reports | 2nd | Elem | On-going | 2012-03-24
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Buenavista | 063027006 | Construction of 2 Units Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 49.21 | ln.m | 627975 | 145601.11 | 773576.11 | 2012-05-15 |  | 422380 | No movement as of July 31, 2012 /Note: Revised KC & LCC Cost | 1st |  | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Cabantohan | 063027007 | Construction of 2 Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 584421 | 127421.57 | 711842.57 | 2012-05-15 |  | 525978.9 |  | 2nd |  | On-going
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Capiñahan | 063027008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 644149 | 126521.83 | 770670.83 | 2012-05-15 |  | 579734.1 |  | 2nd |  | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Dalipe | 063027009 | Construction of 2 Unit Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 96 | sq.m | 950647 | 201225.96 | 1151872.96 | 2012-05-15 |  | 475323.5 |  | 1st |  | On-going
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Layogbato | 063027013 | Road Concreting of 0.395 Km. FMR | 1 | Basic Access Infrastructure | Road | 0.395 | kms | 887228 | 166818.13 | 1054046.13 | 2012-05-15 |  | 709782.4 |  | 1st |  | On-going
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Nagsulang | 063027016 | Construction of 2 CL School Building w/ Facilities (Elem) | 1 | Basic Social Services | School | 162 | sq. m | 1094894 | 398954.2 | 1493848.2 | 2012-01-10 |  | 985404.6 | No movement as of May 31, 2012 reports | 2nd | Elem | On-going | 2012-04-03
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Nasapahan | 063027017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 665773 | 126905.07 | 792678.07 | 2012-05-15 |  | 599195.7 |  | 2nd |  | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Pacuan | 063027019 | Road Concreting of 0.30 Km. FMR w/ Line Ditch Canal | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1091536 | 199098.56 | 1290634.56 | 2012-05-15 |  | 764075.2 |  | 1st |  | On-going
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Poblacion South East Zone | 063027021 | Construction of 2 CL School Building w/ Facilities (HS) | 1 | Basic Social Services | School | 162 | sq. m | 1254910 | 267545.15 | 1522455.15 | 2012-01-16 |  | 1129419 | No movement as of July 31, 2012 | 2nd | HS | On-going | 2012-04-09
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Pontoc | 063027022 | Construction of 2 CL School Building w/ Facilities (Elem) | 1 | Basic Social Services | School | 162 | sq. m | 1231584 | 253473.64 | 1485057.64 | 2012-04-17 |  | 1108425.6 | No movement as of May 31, 2012 reports | 2nd | Elem | On-going | 2012-07-10 | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | San Diego | 063027024 | Road Improvement of 2.45 Km. FMR w/ Line Ditch Canal | 1 | Basic Access Infrastructure | Road | 2.45 | kms | 1352600 | 236960.73 | 1589560.73 | 2012-03-19 |  | 1082080 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2012-06-11
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | San Jose Moto | 063027025 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 689992 | 137751.61 | 827743.61 | 2012-07-15 |  | 344996 |  | 1st |  | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Sincua | 063027027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 669698 | 124432.04 | 794130.04 | 2012-05-15 |  | 334849 |  | 1st |  | On-going |  | 0
H1 | VI | 06 | Iloilo | 0630 | Lemery | 063027 | Yawyawan | 063027031 | Road Improvement of 0.488 Km. FMR w/ Line Ditch Canal | 1 | Basic Access Infrastructure | Road | 0.488 | kms | 1279710 | 232631.1 | 1512341.1 | 2012-05-15 |  | 895797 |  | 1st |  | On-going
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Alim | 064512001 | Road Improvement of 1.0 Km. | 1 | Basic Access Infrastructure | Road | 1 | kms | 1795127.16 | 168588.84 | 1963716 | 2012-05-21 |  | 1436101.72 |  | 1st |  | On-going | 2012-07-22
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Culipapa | 064512007 | Construction of 140 Ln.m Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 140 | ln.m | 863241.18 | 315132.82 | 1178374 | 2012-05-03 |  | 776917.06 |  | 2nd |  | On-going | 2012-07-02
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Damutan | 064512008 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 1058690.95 | 332098.05 | 1390789 | 2012-04-30 |  | 846952.75 |  | 1st | HS | On-going | 2012-07-02
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Daug | 064512009 | Construction of 16 Ln.m Flood Control and 59 Ln.m Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 59 | ln.m | 261113.21 | 139837.79 | 400951 | 2012-05-08 |  | 235001.89 |  | 2nd |  | On-going | 2012-06-27
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Poblacion 2 | 064512005 | Road Improvement of 0.377 Km. | 1 | Basic Access Infrastructure | Road | 0.377 | kms | 702024.26 | 423013.74 | 1125038 | 2012-05-21 |  | 561619.4 |  | 1st |  | On-going | 2012-07-30
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Po-ok | 064512010 | Road Improvement of 1.24 Km. | 1 | Basic Access Infrastructure | Road | 1.24 | kms | 812065.28 | 242633.72 | 1054699 | 2012-05-21 |  | 649652.22 |  | 1st |  | On-going | 2012-07-22
H1 | VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | San Rafael | 064512011 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1007737.96 | 317185.04 | 1324923 | 2012-02-06 |  | 906964.16 |  | 2nd | Elem | On-going | 2012-04-26
H1 | VI | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Cabagnagan | 064517004 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 133.2 | sq. m | 998987.7 | 293120.3 | 1292108 | 2012-03-08 |  | 899088.93 |  | 2nd | HS | On-going | 2012-06-16
H1 | VI | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Camandag | 064517005 | Road Improvement of 1.820 Km. FMR | 1 | Basic Access Infrastructure | Road | 1.82 | kms | 1483847.14 | 359841.86 | 1843689 | 2012-04-26 |  | 1038693 |  | 1st |  | On-going | 2012-08-04
H1 | VI | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Mansalanao | 064517008 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 66.6 | sq. m | 602827.45 | 155404.55 | 758232 | 2012-03-19 |  | 542544.71 | No movement as of July 31, 2012 | 2nd | Elem | On-going | 2012-05-28
H1 | VI | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Masulog | 064517009 | Road Improvement of 2.20 Km. FMR | 1 | Basic Access Infrastructure | Road | 2.2 | kms | 1423258.99 | 357757.01 | 1781016 | 2012-04-16 |  | 1280933.09 |  | 2nd |  | On-going | 2012-07-25
H1 | VI | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Sag-Ang | 064517013 | Road Improvement of 1.8754 Km. FMR | 1 | Basic Access Infrastructure | Road | 1.875 | kms | 868829.78 | 333733.22 | 1202563 | 2012-07-15 |  | 608180.85 |  | 1st |  | On-going
H1 | VI | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Talaptap | 064517016 | Construction of 6m X 16m Mini Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 96 | sq.m | 472248.95 | 262010.05 | 734259 |  |  | 330574.26 |  | 1st |  | Not yet started
H1 | VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Bago (Lalung) | 064532001 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 611528 | 131249.61 | 742777.61 | 2012-06-18 |  | 428069.6 |  | 1st |  | On-going | 2012-09-03 | 0
H1 | VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Bagong Silang | 064532002 | Construction of 1 Unit School Building | 1 | Basic Social Services | School | 66.6 | sq. m | 644020 | 137520.82 | 781540.82 | 2012-06-07 |  | 450814 |  | 1st | Elem | On-going | 2012-08-23 | 0
H1 | VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Igmaya-an | 064532004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 619074 | 131278.41 | 750352.41 | 2012-06-15 |  | 433351.8 |  | 1st |  | On-going | 2012-08-31 | 0
H1 | VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Kumaliskis | 064532005 | Construction of 1 Unit School Building | 1 | Basic Social Services | School | 66.6 | sq. m | 641150 | 140390.82 | 781540.82 | 2012-06-08 |  | 448805 |  | 1st | Elem | On-going | 2012-08-24 | 0
H1 | VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Pinowayan | 064532007 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 611290 | 131213.91 | 742503.91 | 2012-06-05 |  | 427903 |  | 1st |  | On-going | 2012-08-21 | 0
H1 | VI | 06 | Negros Occidental | 0645 | Toboso | 064529 | Bandila | 064529001 | Construction of Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 29.1 | ln.m | 980000 | 210000 | 1190000 | 2011-07-19 |  | 882000 |  | 2nd |  | On-going | 2011-11-01
H1 | VI | 06 | Negros Occidental | 0645 | Toboso | 064529 | Bug-ang | 064529002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 542000 | 168000 | 710000 | 2011-06-22 |  | 487800 |  | 2nd |  | On-going | 2011-09-20
H1 | VI | 06 | Negros Occidental | 0645 | Toboso | 064529 | Magticol | 064529004 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1098000 | 199000 | 1297000 | 2011-06-21 |  | 988200 |  | 2nd | Elem | On-going | 2011-10-04
H1 | VI | 06 | Negros Occidental | 0645 | Toboso | 064529 | Poblacion | 064529005 | Artificial Coral Reef | 1 | Environmental Protection and Conservation | Environmental Preservation (Artificial Coral Reef/Marine Sanctuary) | 100 | unit | 230000 | 184000 | 414000 | 2011-10-15 |  | 115000 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-01-12
H1 | VI | 06 | Negros Occidental | 0645 | Toboso | 064529 | San Isidro | 064529007 | Post Harvest Facility | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 118.5 | sq.m | 1200000 | 140000 | 1340000 | 2011-08-02 |  | 1080000 |  | 2nd |  | On-going | 2011-11-14
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Bacjao | 082602001 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 71 | unit | 429931 | 382712 | 812643 | 2011-03-21 | 2011-07-31 | 386937.9 |  | 2nd |  | Completed | 2011-05-09
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cag-olango | 082602002 | Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.48 | kms | 406022 | 216662 | 622684 | 2011-04-18 | 2011-12-15 | 396986.6 |  | 2nd |  | Completed | 2011-07-06
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cansumangkay | 082602003 | Construction of Level 2 Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 449215 | 312389 | 761604 | 2011-04-25 |  | 404293.5 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2011-07-25
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Guinmaayohan | 082602004 | Construction of Level 2 Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 733322 | 315740 | 1049062 | 2011-04-25 | 2011-07-31 | 733322 |  | 3rd |  | Completed | 2011-07-02
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Maybunga | 082602013 | Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 177035 | 245158 | 422193 | 2011-04-04 | 2011-12-15 | 173628 |  | 2nd |  | Completed | 2011-06-04
F2 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 1 | 082602005 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 118 | unit | 680749 | 593792 | 1274541 | 2011-04-08 | 2012-03-15 | 612674.1 |  | 2nd |  | Completed | 2011-05-26
F2 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 2 | 082602006 | Road Opening | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 401682 | 185086 | 586768 | 2011-03-10 |  | 321345.6 | No movement as of May 31, 2012 reports | 1st |  | On-going | 2011-03-26
F2 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 3 | 082602007 | Drainage Canal & Reinforced Concrete Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 330 | ln.m | 285533 | 200760 | 486293 | 2011-04-11 | 2011-12-15 | 256979.7 |  | 2nd |  | Completed | 2011-06-14
F2 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 4 | 082602008 | Rehabilitation of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 33 | ln.m | 742447 | 316695 | 1059142 | 2011-06-30 | 2011-12-15 | 593957.6 |  | 1st |  | Completed | 2011-08-26
F2 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 5 | 082602009 | Rehabilitation of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 24 | ln.m | 470606 | 327511 | 798117 | 2011-06-27 | 2012-03-15 | 376484.8 |  | 1st |  | Completed | 2011-08-27
F2 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 6 | 082602010 | Rehabilitation of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 24 | ln.m | 468607 | 329510 | 798117 | 2011-06-30 | 2012-02-15 | 374885.6 |  | 1st |  | Completed | 2011-08-17
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | San Miguel | 082602011 | Drainage Canal & Reinforced Concrete Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 374.18 | ln.m | 547301 | 225820 | 773121 | 2011-04-14 | 2011-12-15 | 547300.8 |  | 2nd |  | Completed | 2011-06-30
H1 | VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Sta. Rosa | 082602012 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 158 | unit | 707550 | 981147 | 1688697 | 2011-06-30 | 2012-01-15 | 694040 | Actual Completion 99.93% (100% Completed) | 2nd |  | Completed | 2011-08-02
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Balagon | 082605001 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 515954 | 127111 | 643065 | 2012-06-01 |  | 412763.2 | No movement as of July 31, 2012 | 1st | Elem | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 1 | 082605018 | Construction of Stone Masonry Riverbank Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | 98.5 | ln.m | 421215 | 102221 | 523436 | 2012-05-01 |  | 336972 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 10 | 082605019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 547402 | 142632 | 690034 | 2012-05-01 |  | 437921 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 2 | 082605020 | Construction of Drainage Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 333 | ln.m | 298812 | 82166 | 380978 | 2012-05-01 | 2012-05-31 | 239049.6 |  | 1st |  | Completed | 2012-05-31
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 3 | 082605021 | Construction of Drainage Canal w/ RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 220 | ln.m | 325424 | 93042 | 418466 | 2012-03-21 |  | 260339.2 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-04-13
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 4 | 082605022 | Construction of Concrete Drainage Canal w/ RCBC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 380 | ln.m | 520491 | 137044 | 657535 | 2012-03-22 | 2012-05-17 | 416392 |  | 1st |  | Completed | 2012-05-17
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 5 | 082605023 | Construction & Improvement of Drainage Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 194 | ln.m | 274930 | 80629 | 355559 | 2012-03-30 | 2012-05-11 | 219944 |  | 1st |  | Completed | 2012-05-11
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 7 | 082605025 | Construction of Water System L-II (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 752582 | 168843 | 921425 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Barangay 8 | 082605026 | Improvement & Construction of Drainage Lined Canal w/ 13 pcs. RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 247 | ln.m | 305514 | 90044 | 395558 | 2012-03-20 | 2012-05-03 | 244411 |  | 1st |  | Completed | 2012-05-03
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Baruk | 082605002 | Construction of R.C Sheet Pile & Grouted Riprap Riverbank Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | 50 | ln.m | 592596 | 151647 | 744243 |  |  | 474077 |  | 1st |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Boco | 082605003 | Improvement of L-II Water System (Gravity Flow) | 1 | Basic Social Services | Water System | 1 | system | 366440 | 100486 | 466926 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Caghalong | 082605004 | Construction of R.C Sheet Pile & Grouted Riprap Riverbank Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | 50 | ln.m | 579181 | 149280 | 728461 |  |  | 463344.8 |  | 1st |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Camaantang | 082605005 | Improvement of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.39 | kms | 444785 | 96463 | 541248 | 2012-05-01 | 2012-05-31 | 355828 |  | 1st |  | Completed | 2012-05-31
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Can-ilay | 082605007 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 883042 | 238348 | 1121390 | 2012-05-01 |  | 719369.6 | No movement as of July 31, 2012 | 1st | Elem | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Cansangaya | 082605008 | Construction of Drainage Lined Canal w/ 18 pcs RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 243 | ln.m | 357788 | 100812 | 458600 | 2012-03-12 | 2012-05-15 | 286230 |  | 1st |  | Completed | 2012-04-21
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Canteros | 082605009 | Improvement & Construction of Drainage Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 182 | ln.m | 363961 | 104992 | 468953 | 2012-03-12 | 2012-05-19 | 291168.8 |  | 1st |  | Completed | 2012-05-19
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Carolina | 082605010 | Construction of Concrete Drainage Canal w/ RCBC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 390 | ln.m | 543066 | 133818 | 676884 | 2012-03-12 |  | 434452 |  | 1st |  | On-going | 2012-05-14
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Guibuangan | 082605011 | Construction of R.C Sheet Pile & Grouted Riprap Riverbank Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | 50 | ln.m | 598224 | 152641 | 750865 |  |  | 484433.6 |  | 1st |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Jepaco | 082605012 | Improvement of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.302 | kms | 1110101 | 223401 | 1333502 |  |  | 871988 |  | 1st |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Mabuhay | 082605013 | Construction of Water System L-II (Gravity Flow) | 1 | Basic Social Services | Water System | 1 | system | 690108 | 157114 | 847222 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Malogo | 082605014 | Improvement of L-II Water System (Gravity Flow) | 1 | Basic Social Services | Water System | 1 | system | 587458 | 136320 | 723778 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Obong | 082605015 | Farm Mechanization Project (15 Units Tractor & 2 Trailers) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 15 | unit | 771534 | 154571 | 926105 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Pandol | 082605016 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 511760 | 113400 | 625160 | 2012-05-01 |  | 409408 |  | 1st | Elem | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Rawis | 082605033 | Construction/Installation of 12 Sets Artificial Fish Shelter & 6 Motor Boats | 1 | Environmental Protection and Conservation | Environmental Preservation (Artificial Coral Reef/Marine Sanctuary) | 12 | unit | 641759 | 125509 | 767268 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Salvacion | 082605028 | Construction of Water System L-II (Gravity Flow) | 1 | Basic Social Services | Water System | 1 | system | 445794 | 107461 | 553255 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Can-Avid | 082605 | Solong | 082605032 | Improvement of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.297 | kms | 300431 | 71224 | 371655 | 2012-05-01 |  | 240344.8 |  | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Batang | 082610001 | Construction of 1 Classroom Elem. School Building (Elem) | 1 | Basic Social Services | School |  | sq. m | 623031 | 127269 | 750300 |  |  | 0 |  |  | Elem | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Batang | 082610001 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 623031 | 127269 | 750300 | 2012-02-13 |  | 560727.3 | No movement as of July 31, 2012 | 2nd | Elem | On-going | 2012-05-29
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Cacatmonan | 082610002 | Brgy. Base Reforestation | 1 | Environmental Protection and Conservation | Environmental Preservation (Artificial Coral Reef/Marine Sanctuary) |  | HH | 344370 | 71060 | 415430 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Cacatmonan | 082610002 | Brgy. Base Reforestation (2 Hectares) | 1 | Environmental Protection and Conservation | Environmental Preservation (Artificial Coral Reef/Marine Sanctuary) |  | unit | 344370 | 71060 | 415430 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Cancilides | 082610004 | Conctruction of 414 Ln.m Draiange Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 414 | ln.m | 615943 | 127857 | 743800 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Cancilides | 082610004 | Construction of 414 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 414 | ln.m | 615943 | 127857 | 743800 | 2012-01-31 |  | 615943 | No movement as of July 31, 2012 | 3rd |  | On-going | 2012-04-30
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Garawon | 082610003 | Construction of 2mX256 Ln.m Concrete Pathwalk w/ Grouted Rip-rap | 1 | Basic Access Infrastructure | Access Trail | 0.256 | kms | 663969 | 134481 | 798450 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Garawon | 082610003 | Construction of 2mX256 Ln.m Concrete Pathwalk w/ Grouted Rip-Rap | 1 | Basic Access Infrastructure | Access Trail | 0.256 | kms | 663969 | 134481 | 798450 | 2012-02-20 |  | 597572 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-04-26
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Nagaja | 082610006 | Construction of 1 Classroom Elem. School Building (Elem) | 1 | Basic Social Services | School |  | sq. m | 623234 | 127066 | 750300 |  |  | 0 |  |  | Elem | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Nagaja | 082610006 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 623234 | 127066 | 750300 | 2012-02-07 |  | 560910 | No movement as of July 31, 2012 | 2nd | Elem | On-going | 2012-05-23
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Padang | 082610007 | Construction of 2mX272 Ln.m Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.272 | kms | 516127 | 104323 | 620450 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Padang | 082610007 | Construction of 2mX272 Ln.m Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.272 | kms | 516127 | 104323 | 620450 | 2012-02-16 |  | 464515 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-04-18
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 1 | 082610008 | Construction of 21 Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 21 | unit | 300684 | 63316 | 364000 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 1 | 082610008 | Construction of 21 Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 21 | unit | 300684 | 63316 | 364000 | 2012-02-07 |  | 270615 | No movement as of Juy 31, 2012 | 2nd |  | On-going | 2012-03-23
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 2 | 082610009 | Construction of 2mx190Ln.m Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.19 | kms | 390038 | 140862 | 530900 | 2012-04-26 |  | 351034 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-06-11
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 3 | 082610010 | Construction of 265 Ln.m Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 265 | ln.m | 821911 | 164789 | 986700 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 3 | 082610010 | Construction of 265 Ln.m Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 265 | ln.m | 821911 | 164789 | 986700 | 2012-02-02 |  | 739720 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-04-26
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 4 | 082610011 | Construction of 220 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 220 | ln.m | 435988 | 89312 | 525300 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 4 | 082610011 | Construction of 220 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 220 | ln.m | 435988 | 89312 | 525300 | 2012-02-13 |  | 435988 | No movement as of May 31, 2012 reports | 3rd |  | On-going | 2012-04-17
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | San Miguel | 082610013 | Construction of 259 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 259 | ln.m | 514705 | 103295 | 618000 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Hernani | 082610 | San Miguel | 082610013 | Construction of 259 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 259 | ln.m | 514705 | 103295 | 618000 | 2012-02-16 |  | 463235 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-05-16
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Agsaman | 082611001 | Construction of 0.219 Km. Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.219 | kms | 504017 | 108736 | 612753 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Cagmanaba | 082611007 | Construction of 16 Ln.m. Reinforced Concrete Foot Bridge w/ 24 Ln.m Concrete Pathway | 1 | Basic Access Infrastructure | Foot/Small Bridges | 16 | ln.m | 391854 | 108913 | 500767 | 2012-05-01 |  | 313483 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-22
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Dorillo | 082611009 | Construction of 0.223 Km. Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.223 | kms | 461424 | 95185 | 556609 | 2012-05-01 |  | 369139 |  | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Jerawan | 082611012 | Construction of Gravity Driven Water Supply System Level II | 1 | Basic Social Services | Water System | 1 | system | 379772.5 | 83643 | 463415.5 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Mabuhay | 082611013 | Construction of 26 Ln.m Reinforced Concrete Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 26 | ln.m | 462059 | 101474 | 563533 |  |  | 369647.2 |  | 1st |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Magsaysay | 082611014 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 677821 | 149774 | 827595 |  |  | 0 |  |  | Elem | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 1 | 082611015 | Construction of 450 Ln.m Concrete Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 450 | ln.m | 443090 | 111774 | 554864 |  |  | 354472 |  | 1st |  | On-going | 2012-06-01
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 2 | 082611016 | Construction of 309 Ln.m Concrete Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 309 | ln.m | 320887 | 107200 | 428087 |  |  | 256709 | No movement as f July 31, 2012 | 1st |  | On-going | 2012-06-16
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 3 | 082611017 | Construction of 443 Ln.m Concrete Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 443 | ln.m | 447586 | 113319 | 560905 |  |  | 358068 |  | 1st |  | On-going | 2012-06-02
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 4 | 082611018 | Construction of 650 Ln.m Concrete Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 650 | ln.m | 597035 | 133750 | 730785 | 2012-05-01 |  | 477628 |  | 1st |  | On-going | 2012-07-01
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Recare | 082611019 | Construction of 0.322 Km. Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.322 | kms | 496673 | 108312 | 604985 | 2012-06-01 |  | 397338 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Roxas | 082611020 | Construction of 0.115 Km Concrete Pathway w/ 236 Ln.m Concrete Canal | 1 | Basic Access Infrastructure | Access Trail | 0.115 | kms | 718334 | 148181 | 866515 | 2012-05-01 |  | 574667.2 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | San Roque | 082611021 | Construction of Gravity Drive Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 581248.5 | 118331 | 699579.5 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Barangay Poblacion 1 | 082614008 | Construction of Concrete Pathwalk with Concrete Canal | 1 | Basic Access Infrastructure | Access Trail | 0.25 | kms | 772462 | 103869 | 876331 | 2011-04-25 | 2011-08-15 | 695215.2 |  | 2nd |  | Completed | 2011-06-29
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Barangay Poclacion 2 | 082614009 | Construction of Concrete Pathwalk with Concrete Canal | 1 | Basic Access Infrastructure | Access Trail | 0.407 | kms | 624324 | 88953 | 713277 | 2011-03-14 | 2011-07-31 | 538163.1 |  | 2nd |  | Completed | 2011-05-07
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Bulawan | 082614001 | Construction of Rice Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | unit | 616335 | 69658 | 685993 | 2011-04-25 | 2011-08-15 | 493068 |  | 1st |  | Completed | 2011-05-27
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Carayacay | 082614003 | Construction of River Landing | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 30 | ln.m | 418081 | 62859 | 480940 | 2011-04-25 | 2011-08-15 | 376272.9 |  | 2nd |  | Completed | 2011-05-28
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Libertad | 082614005 | Repair of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 496868 | 70802 | 567670 | 2011-04-27 | 2011-08-15 | 447181.2 |  | 2nd | Elem | Completed | 2011-06-27
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Malobago | 082614006 | Construction of River Landing | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 80 | ln.m | 280183 | 51335 | 331518 | 2011-03-14 | 2012-04-04 | 242803.35 |  | 2nd |  | Completed | 2011-04-04
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Maputi | 082614007 | Construction of Access Road | 1 | Basic Access Infrastructure | Road | 0.434 | kms | 606634 | 96368 | 703002 | 2011-06-01 | 2011-08-15 | 545970.54 |  | 2nd |  | Completed | 2011-07-23
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Miguel | 082614010 | Construction of School Building (1 Room) (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 655898 | 89358 | 745256 | 2011-04-25 | 2011-12-15 | 590307.9 |  | 2nd | Elem | Completed | 2011-06-27
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Roque | 082614011 | Brgy. Electrification (14 Street Light) | 1 | Basic Social Services | Electrification | 43 | HH | 410500 | 59130 | 469630 | 2011-04-25 | 2011-08-15 | 328400 |  | 1st |  | Completed | 2011-05-02
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tangbo | 082614012 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 690023 | 93354 | 783377 | 2011-04-13 | 2011-11-15 | 621020.7 |  | 2nd | Elem | Completed | 2011-06-27
H1 | VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tugas | 082614014 | Brgy. Electrificaion | 1 | Basic Social Services | Electrification | 37 | HH | 428692 | 43544 | 472236 | 2011-04-13 | 2011-08-15 | 342953.6 | 14 Street Lights | 1st |  | Completed | 2011-06-27
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Alugan | 082621001 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 723394 | 193006 | 916400 | 2012-04-09 |  | 502864 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-20
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Bahay | 082621002 | Construction of 0.115 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.115 | kms | 245776 | 81024 | 326800 | 2012-04-10 | 2012-05-30 | 199904 |  | 1st |  | Completed | 2012-05-30
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Barangay 1 | 082621010 | Construction of 4 Units Hand Pump Water System | 1 | Basic Social Services | Water System | 1 | system | 152750 | 43250 | 196000 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Barangay 2 | 082621011 | Construction of 109 Ln.m CHB Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 109 | ln.m | 406755 | 102445 | 509200 | 2012-04-30 |  | 277931 | No movement as of Juy 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Barangay 3 | 082621012 | Construction of 434 ln.m CHB Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 434 | ln.m | 1311466 | 356534 | 1668000 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Barangay 4 | 082621013 | Construction of 0.242 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.242 | kms | 462030 | 185070 | 647100 | 2012-04-09 |  | 343908 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-30
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Barangay 5 | 082621014 | Construction of 0.251 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.251 | kms | 413030 | 250170 | 663200 | 2012-03-16 | 2012-05-27 | 357452 |  | 1st |  | Completed | 2012-05-27
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Baras (Lipata) | 082621004 | Construction of 0.181 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.181 | kms | 337280 | 188420 | 525700 | 2012-04-09 |  | 269824 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-30
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Binogawan | 082621005 | Construction of 100 ln.m Reinforced Concrete Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 481840 | 820060 | 1301900 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Cajagwayan | 082621006 | Construction of 0.167 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.167 | kms | 322108 | 121192 | 443300 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Japunan | 082621007 | Construction of 0.28 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.28 | kms | 670921 | 315379 | 986300 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Natividad | 082621008 | Construction of 0.12 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.12 | kms | 260636 | 154864 | 415500 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Pangpang | 082621009 | Construction of 0.25 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.25 | kms | 375240 | 232960 | 608200 | 2012-04-09 |  | 336192 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-30
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Sta. Cruz | 082621015 | Construction of 0.12 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.12 | kms | 212504 | 148396 | 360900 | 2012-04-12 |  | 170003.2 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-28
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Tabo | 082621016 | Construction of 0.125 Km. Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.125 | kms | 199576 | 131124 | 330700 | 2012-04-09 |  | 177774 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-18
H1 | VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Tan-awan | 082621017 | Constrcution of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail |  | kms | 558490 | 372710 | 931200 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Abucay | 082622018 | Rehabilitation of Concrete Hollowblock Lined Draiange Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 376561 | 114390 | 490951 | 2012-02-08 |  | 338904.8 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-06-01
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | A-et | 082622001 | Construction of Cable Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 63 | ln.m | 1489158.18 | 301315.82 | 1790474 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Baybay | 082622002 | Construction of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 432 | ln.m | 251446.69 | 274647.31 | 526094 | 2012-03-20 |  | 201157 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Del Remedio | 082622004 | Rehabilitation of Concrete Draiange Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 604 | ln.m | 689714 | 154299 | 844013 | 2012-02-06 |  | 620742 | No movement as of July 31, 2012 | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Kandalakit | 082622003 | Construction of Concrete Footbridge and Concrete Pathway | 1 | Basic Access Infrastructure | Foot/Small Bridges | 36 | ln.m | 183112.38 | 81125 | 264237.38 |  |  | 146489.6 |  | 1st |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Loyola Heights | 082622005 | Rehabilitation of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 605 | ln.m | 638171 | 171000 | 809171 | 2012-02-20 |  | 574353.1 | No movement as of July 31, 2012 | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Mabini | 082622006 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 413321.98 | 116383.34 | 529705.32 | 2012-02-20 |  | 330657.59 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Maglipay | 082622007 | Construction of 1 Unit Concrete School Building | 1 | Basic Social Services | School | 63 | sq. m | 446508 | 119100 | 565608 | 2012-02-20 |  | 357206 | No movement as of July 31, 2012 | 1st | Elem | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Maramara | 082622008 | Rehabilitation & Construction of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 390 | ln.m | 481561 | 115566 | 597127 | 2012-02-08 |  | 433404.9 |  | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Riverside | 082622009 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.149 | kms | 350552 | 114551 | 465103 | 2012-02-13 |  | 311944.5 | No movement as of July 31, 2012 | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Isidro | 082622011 | Construction of Gravel Filled Barangay Road | 1 | Basic Access Infrastructure | Road | 0.155 | kms | 535586.13 | 117050 | 652636.13 | 2012-02-06 |  | 428468.8 | No movement as of Juy 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Juan | 082622012 | Construction of Concrete Hollowblock Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 690 | ln.m | 494699 | 118457 | 613156 | 2012-05-01 |  | 395759.2 |  | 1st |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Mateo | 082622013 | Construction of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 835 | ln.m | 504439 | 133991 | 638430 | 2012-02-13 |  | 453995.1 |  | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Vicente | 082622014 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 742421.63 | 184350 | 926771.63 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Sto. Niño | 082622015 | Construction & Rehabilitation of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 432.3 | ln.m | 504367 | 117823 | 622190 | 2012-02-06 |  | 453930.3 | No movement as of July 31, 2012 | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Sto. Tomas | 082622016 | Construction of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 1058 | ln.m | 514186 | 118641 | 632827 | 2012-02-13 |  | 462767.4 | No movement as of July 31, 2012 | 2nd |  | On-going
H1 | VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Tabi | 082622017 | Rehabilitation of Concrete Hollowblock Lined Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 384195 | 115625 | 499820 | 2012-02-14 |  | 345775.5 | No movement as of July 31, 2012 | 2nd |  | On-going
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Balagiao, Pasig & Natividad | 063025055 | Construction of 73 Ln.m Hanging Bridge | 3 | Basic Access Infrastructure | Foot/Small Bridges | 73 | ln.m | 2363553 | 423375 | 2786928 | 2012-04-14 |  | 1890842.4 | Balagiao, Pasig & Natividad | 1st |  | On-going | 2012-09-06 | 0
H1 | VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Balagiao, Pasig & Natividad | 063025051 | Construction of 73 Ln.m Hanging Bridge | 3 | Basic Access Infrastructure | Foot/Small Bridges | 73 | ln.m | 2363553 | 423375 | 2786928 | 2012-04-14 |  | 1890842.4 | Balagiao, Pasig & Natividad | 1st |  | On-going | 2012-09-06 | 0
H1 | VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Tanauan |  | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail |  | kms | 558490 | 372710 | 931200 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Abaton | 084808001 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.7 | kms | 640144 | 113056 | 753200 | 2011-04-12 | 2011-09-15 | 576129.6 |  | 2nd |  | Completed | 2011-06-13
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aguadahan | 084808002 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq.m | 730868 | 70232 | 801100 | 2011-04-23 | 2012-03-15 | 657781.2 |  | 2nd | Elem | Completed | 2011-06-25
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aroganga | 084808003 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 36 | unit | 928308 | 109392 | 1037700 | 2011-04-30 | 2011-10-15 | 757879.2 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Atipolo | 084808004 | Construction 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1238008 | 104292 | 1342300 | 2011-04-04 | 2012-04-15 | 1114207.2 |  | 2nd | Elem | Completed | 2011-07-13
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bawang | 084808005 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 751896 | 88304 | 840200 | 2011-04-30 |  | 676706.4 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Binatiklan | 084808007 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 649404 | 68496 | 717900 | 2011-03-28 | 2011-12-15 | 584013.6 |  | 2nd |  | Completed | 2011-05-30
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bobolosan | 084808008 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1242426 | 165174 | 1407600 | 2011-09-01 |  | 993940.8 | No movement as of May 31, 2012 reports | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bongliw | 084808009 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.255 | kms | 310080 | 71420 | 381500 | 2011-04-07 | 2011-09-15 | 279072 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Burabud | 084808010 | Installation of Street Lights (25 Units) | 1 | Basic Social Services | Electrification | 202 | HH | 241486 | 54514 | 296000 | 2011-04-05 | 2011-08-15 | 217337 | 25 Units Street Lights | 2nd |  | Completed | 2011-05-30
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabadiangan | 084808011 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq.m | 1223324 | 128976 | 1352300 | 2011-04-04 | 2012-03-15 | 1196418 |  | 2nd | HS | Completed | 2011-06-15
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabulaloan | 084808014 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.19 | kms | 820028 | 71672 | 891700 | 2011-04-30 | 2011-10-15 | 738025.2 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagaasan | 084808015 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 489150 | 109528 | 598678 | 2011-04-11 | 2011-09-15 | 440235 |  | 2nd |  | Completed | 2011-05-26
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagdara-o | 084808016 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1212008 | 129292 | 1341300 | 2011-04-04 |  | 1090807.2 | No movement as of May 31, 2012 reports | 2nd | Elem | On-going | 2011-07-13
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Candawid | 084808020 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1202324 | 148976 | 1351300 | 2011-05-10 | 2012-03-15 | 1082091.6 |  | 2nd | Elem | Completed | 2011-07-21
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cangcahipos | 084808021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 669016 | 70084 | 739100 | 2011-04-14 | 2011-10-15 | 602114.4 |  | 2nd |  | Completed | 2011-07-16
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Catigbian | 084808023 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 134 | ln.m | 242572 | 96928 | 339500 | 2011-04-13 | 2011-09-15 | 218314.8 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Doña Luisa (Onay) | 084808040 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1143924 | 128976 | 1272900 | 2011-04-07 | 2012-01-15 | 1029531.6 |  | 2nd | Elem | Completed | 2011-06-13
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | E.J. Dulay | 084808026 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.203 | kms | 201342 | 64458 | 265800 | 2011-04-13 | 2011-09-15 | 186960 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Inamlan | 084808030 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.82 | kms | 1222716 | 131984 | 1354700 | 2011-04-04 | 2011-09-15 | 1100444.4 |  | 2nd |  | Completed | 2011-06-09
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | La Perla | 084808031 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 600 | ln.m | 1199940 | 140260 | 1340200 | 2011-03-23 | 2011-09-15 | 1079946 |  | 2nd |  | Completed | 2011-05-12
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Langob | 084808032 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 316.7 | ln.m | 726064 | 122236 | 848300 | 2011-04-11 | 2011-09-15 | 653457.6 |  | 2nd |  | Completed | 2011-05-28
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Lawaan | 084808033 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 303 | ln.m | 694256 | 76744 | 771000 | 2011-04-12 | 2011-10-15 | 624830.4 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Magsaysay | 084808035 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 614924 | 102676 | 717600 | 2011-04-11 | 2012-03-15 | 553431.6 |  | 2nd |  | Completed | 2011-06-13
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Marubay | 084808036 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.32 | kms | 886308 | 124492 | 1010800 | 2011-04-29 | 2011-11-15 | 837374.46 |  | 2nd |  | Completed | 2011-06-17
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Mualbual | 084808037 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1190924 | 128976 | 1319900 | 2011-04-19 | 2011-10-15 | 1071831.6 |  | 2nd | Elem | Completed | 2011-07-01
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Napotiocan (Salvacion) | 084808038 | Construction of Pier (Step Landing) | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 60 | ln.m | 353224 | 95376 | 448600 | 2011-03-29 | 2011-08-15 | 337617 |  | 2nd |  | Completed | 2011-05-05
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Oleras | 084808039 | Construction of Concrete Pathwalk with Box Culvert | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 712454 | 129966 | 842420 | 2011-08-15 | 2011-09-15 | 569963.2 |  | 1st |  | Completed | 2011-10-15
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Palmera | 084808041 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.501 | kms | 640670 | 90630 | 731300 | 2011-04-30 | 2011-10-15 | 576603 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Pangdan | 084808042 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 32 | unit | 988448 | 109242 | 1097690 | 2011-04-30 | 2011-12-15 | 749268 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Rombang | 084808044 | Construction of Concrete Pathwalk with Box Culvert | 1 | Basic Access Infrastructure | Access Trail | 0.11 | kms | 268909 | 82391 | 351300 | 2011-04-11 | 2011-12-15 | 215127.2 |  | 1st |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | San Antonio | 084808045 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1234324 | 106976 | 1341300 | 2011-04-04 | 2012-01-15 | 1110891.6 |  | 2nd | Elem | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Sibunot | 084808049 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.27 | kms | 343080 | 59920 | 403000 | 2011-04-20 | 2011-09-15 | 308772 |  | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Talisay | 084808061 | Installation of Street Lights (27 Units) | 1 | Basic Social Services | Electrification | 303 | HH | 249547 | 54864 | 304411 | 2011-04-04 | 2011-08-15 | 224592.3 | 27 Units Street Lights | 2nd |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tan-awan | 084808054 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.613 | kms | 867044 | 72656 | 939700 | 2011-04-04 | 2011-08-15 | 693635.2 |  | 1st |  | Completed | 2011-05-19
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tumaguingting | 084808057 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 151.1 | ln.m | 415100 | 84696 | 499796 | 2011-03-28 | 2011-06-30 | 357592.86 |  | 2nd |  | Completed | 2011-05-26
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Vigo | 084808058 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 346 | ln.m | 863130 | 77908 | 941038 | 2011-04-04 | 2011-08-15 | 828775 |  | 2nd |  | Completed | 2011-05-24
H1 | VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Yabyaban | 084808059 | Construction of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.374 | kms | 592630 | 99000 | 691630 | 2011-04-30 | 2012-03-15 | 474104 |  | 1st |  | Completed | 2011-07-31
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Bagasbas | 084813001 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 584391 | 112464 | 696855 | 2011-02-01 | 2011-04-30 | 525952 |  | 2nd |  | Completed | 2011-04-29
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Bugko | 084813002 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 230 | ln.m | 1036233 | 399980 | 1436213 | 2011-02-10 | 2011-05-31 | 1036012 |  | 2nd |  | Completed | 2011-04-19
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Cablangan | 084813003 | Construction of FMR | 1 | Basic Access Infrastructure | Road | 0.38 | kms | 1205984 | 221770 | 1427754 | 2011-02-07 | 2011-05-17 | 1085385.6 |  | 2nd |  | Completed | 2011-05-18
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Cahicsan | 084813005 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 600998 | 106214 | 707212 | 2011-02-09 | 2011-08-15 | 541832 |  | 2nd |  | Completed | 2011-05-07
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Chitongco | 084813006 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 545780 | 144974 | 690754 | 2011-02-07 | 2011-04-30 | 491202 |  | 2nd |  | Completed | 2011-05-05
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | De Maria | 084813007 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 621787 | 145240 | 767027 | 2011-02-21 | 2011-04-30 | 520223.06 |  | 2nd |  | Completed | 2011-05-19
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Doña Lucia | 084813008 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 627825 | 131500 | 759325 | 2011-02-07 | 2011-04-30 | 565043 |  | 2nd |  | Completed | 2011-05-07
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Hinabangan | 084813011 | Construction of School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 670484 | 102569 | 773053 | 2011-02-28 | 2011-08-15 | 603436 |  | 2nd | Elem | Completed | 2011-05-16
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Mirador | 084813015 | Construction of Road Re-Gravelling | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 647829 | 161000 | 808829 | 2011-02-05 | 2011-07-31 | 518263.2 |  | 1st |  | Completed | 2011-04-05
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Nenita | 084813016 | Construction of 3 CL School Building (HS) | 1 | Basic Social Services | School | 189 | sq. m | 1243289 | 216920 | 1460209 | 2011-01-31 | 2011-04-30 | 1223277 |  | 2nd | HS | Completed | 2011-04-30
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Antonio | 084813019 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 230 | ln.m | 530367 | 129039 | 659406 | 2011-02-09 | 2011-06-01 | 439316.56 |  | 2nd |  | Completed | 2011-04-02
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Isidro | 084813020 | Construction of Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 50 | ln.m | 1245659 | 179960 | 1425619 | 2011-09-12 |  | 1087343 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2011-12-12
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Juan | 084813022 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 450 | ln.m | 779531 | 181980 | 961511 | 2011-02-14 | 2011-06-30 | 650513.36 |  | 2nd |  | Completed | 2011-04-30
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Sta. Catalina | 084813023 | Construction of Road Re-Gravelling | 1 | Basic Access Infrastructure | Road | 0.35 | kms | 988845 | 174080 | 1162925 | 2011-06-30 | 2011-09-15 | 889961 |  | 2nd |  | Completed | 2011-09-28
H1 | VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Talolora | 084813024 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 536370 | 126420 | 662790 | 2011-01-17 | 2011-04-30 | 520516.5 |  | 2nd |  | Completed | 2011-05-17
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Bagacay | 084814002 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 796 | ln.m | 736453 | 232853 | 969306 | 2011-06-30 | 2011-12-15 | 662808 |  | 2nd |  | Completed | 2011-08-29
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Bagacay | 084814002 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1037340 | 297025 | 1334365 |  |  | 518670 |  | 1st | Elem | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Bangon | 084814003 | Construction of Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 110 | ln.m | 771836 | 312169 | 1084005 | 2011-10-01 |  | 617469 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Binay | 084814004 | Construction of Causeway | 1 | Basic Access Infrastructure | Foot/Small Bridges | 0.168 | ln.m | 1056307 | 288292 | 1344599 | 2011-07-18 | 2012-07-15 | 1009548 | (No movement as of May 31, 2012 reports) From RR to bridge as per RIE Gerry it’s a (Bridge) | 3rd |  | Completed | 2011-09-06
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Cabariwan | 084814005 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.32 | kms | 1064601 | 252805 | 1317406 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Cabatuan | 084814006 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 380 | ln.m | 368692 | 229815 | 598507 | 2011-06-28 | 2011-12-15 | 331824 |  | 2nd |  | Completed | 2011-08-27
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Cabatuan | 084814006 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.61 | kms | 755341 | 185046 | 940387 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Campedico | 084814007 | Construction of Tire Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.73 | kms | 672147 | 235505 | 907652 | 2011-06-27 | 2012-01-15 | 604933 |  | 2nd |  | Completed | 2011-08-26
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Campedico | 084814007 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1040772 | 284522 | 1325294 | 2012-07-01 |  | 520386 |  | 1st | Elem | On-going |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Capacujan | 084814008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 599839 | 180656 | 780495 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Jangtud | 084814009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 614609 | 193868 | 808477 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Mabaras | 084814011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 537491 | 187887 | 725378 | 2011-07-04 | 2012-02-15 | 483742 |  | 2nd |  | Completed | 2011-09-02
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Mabaras | 084814011 | Construction of Reinforce Concrete Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 456 | ln.m | 611661 | 187251 | 798912 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Magsaysay | 084814012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 502454 | 211982 | 714436 | 2011-06-24 | 2012-07-15 | 452209 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2011-08-23
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Manajao | 084814013 | Construction of Water Supply System L-II | 1 | Basic Social Services | Water System | 1 | system | 631906 | 240101 | 872007 | 2012-01-15 |  | 0 | No movement as of May 31, 2012 reports |  |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Mapno | 084814014 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1075291.5 | 236478.5 | 1311770 |  |  | 537645.75 |  | 1st | Elem | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Maragano | 084814015 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 634340 | 180623 | 814963 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Matambag | 084814016 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.513 | kms | 645451 | 237259 | 882710 | 2011-06-27 | 2012-01-15 | 516361 |  | 1st |  | Completed | 2011-08-26
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Matambag | 084814016 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 605682 | 177484 | 783166 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Monbon | 084814017 | Construction of Monbon Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 30 | ln.m | 808183 | 204766 | 1012949 | 2011-10-15 |  | 646547 | No movement as of May 31, 2012 reports | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Nagbobtac | 084814018 | Construction of Water Supply System L-II | 1 | Basic Social Services | Water System | 1 | system | 405578 | 213363 | 618941 | 2012-01-15 |  | 365020 |  | 2nd |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Napo | 084814019 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 521697 | 174100 | 695797 | 2011-06-29 | 2012-07-15 | 487605 | No maovement as of May 31, 2012 reports | 3rd | Elem | Completed | 2011-08-27
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Natawo | 084814020 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.228 | kms | 548485 | 211678 | 760163 | 2011-06-18 | 2011-12-15 | 493636 |  | 2nd |  | Completed | 2011-08-17
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Natawo | 084814020 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1029765 | 304628 | 1334393 |  |  | 514883 |  | 1st | Elem | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Nipa | 084814021 | Improvement of Water Supply System L-II | 1 | Basic Social Services | Water System | 1 | system | 116000 | 80796 | 196796 | 2011-07-09 | 2012-01-15 | 104401 |  | 2nd |  | Completed | 2011-09-07
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Osmeña | 084814022 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 640 | ln.m | 663747 | 201978 | 865725 | 2011-07-04 | 2012-01-15 | 597372 |  | 2nd |  | Completed | 2011-09-09
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Osmeña | 084814022 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1103811 | 248798 | 1352609 |  |  | 551906 |  | 1st | Elem | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Pangpang | 084814023 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 592923 | 184628 | 777551 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Paysud | 084814024 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.277 | kms | 527321 | 134313 | 661634 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Sangay | 084814026 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 140 | ln.m | 819954 | 423646 | 1243600 | 2011-06-28 |  | 737959.2 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2011-08-27
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Simora | 084814028 | Construction of Water Supply System L-II | 1 | Basic Social Services | Water System | 1 | system | 451650 | 196707 | 648357 | 2012-06-01 |  | 361320 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Sinalaran | 084814029 | Construction/Improvement of Causeway w/ Concrete Pathway | 1 | Basic Access Infrastructure | Foot/Small Bridges | 123 | ln.m | 1112405 | 302731 | 1415136 |  |  | 0 | As per Engr Gerry it's a Bridge (Causeway is a major pay item) |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Sumoroy | 084814030 | Construction of River Landing w/ Reinforce Concrete Sheet Pile | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 86 | ln.m | 1136202 | 326522 | 1462724 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Talolora | 084814031 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 641341 | 146222 | 787563 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Tinampo, Laniwan, Tambangan, B. Aquino Jr. & Asum | 084814033 | Construction of Drainage Canal | 5 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4800 | ln.m | 4141969 | 2040709 | 6182678 | 2011-12-01 |  | 2070984 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 1 (Poblacion District 1) | 084815019 | Construction of Community Learning Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq. m | 589314 | 133760 | 723074 | 2012-02-15 | 2012-07-15 | 530382 | Venue for non-formal education & training for OSY | 2nd |  | Completed | 2012-05-22
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 3 (Poblacion District 3) | 084815021 | Construction of Drainage Canal w/ Cover | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 617885 | 145278 | 763163 | 2012-02-27 |  | 556097 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-05-05
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 4 (Poblacion District 4) | 084815022 | Construction of Draiange Canal w/ Cover | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 230 | ln.m | 531404 | 126223 | 657627 | 2012-04-09 |  | 478264 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-06-16
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 5 (Poblacion District 5) | 084815023 | Construction of Community Learning Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq. m | 589314 | 133760 | 723074 | 2012-06-02 |  | 471451 | Venue for non-formal education & training for OSY | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 6(Poblacion District 6) | 084815024 | Construction of Community Learning Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq. m | 589314 | 133760 | 723074 | 2012-02-06 |  | 530382.2 | Venue for non-formal education & training for OSY | 2nd |  | On-going | 2012-05-19
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 7 (Poblacion District 7) | 084815025 | Construction of Water System Level I | 1 | Basic Social Services | Water System | 1 | system | 176845 | 41948 | 218793 | 2012-04-19 |  | 141476 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-05-16
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Barangay 8 (Poblacion District 8) | 084815026 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 542986 | 123749 | 666735 | 2012-02-13 | 2012-07-15 | 488686 |  | 2nd |  | Completed | 2012-05-26
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Cababto-an | 084815002 | Construction of Street Light w/ Generator Set | 1 | Basic Social Services | Electrification | 353 | HH | 371459 | 85678 | 457137 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Cabari-an | 084815004 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 713307 | 157020 | 870327 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Cagbigajo | 084815005 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 395652 | 86952 | 482604 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Camparanga | 084815009 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 583668 | 132764 | 716432 | 2012-02-22 | 2012-07-15 | 525301.6 |  | 2nd | Elem | Completed | 2012-05-30
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Canjumadal | 084815007 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.76 | kms | 689854 | 157699 | 847553 | 2012-06-01 |  | 413912 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Sixto T. Balanguit, Sr.(Don Sixto) | 084815029 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 428322 | 191482 | 619804 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Doña Anecita | 084815008 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 583668 | 132764 | 716432 |  |  | 466934 |  | 1st | Elem | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ginulgan | 084815011 | Construction of Suspended Cable Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges |  | ln.m | 969531 | 209856 | 1179387 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Giparayan | 084815012 | Construction of Draiange Canal w/ Cover | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 821945 | 175989 | 997934 | 2012-04-23 |  | 493167 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-12
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Igot | 084815013 | Construction of Street Light w/ Generator Set | 1 | Basic Social Services | Electrification | 115 | HH | 344028 | 75765 | 419793 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Inanahawan | 084815015 | Construction of Concrete Pathwalk w/ Concrete Footbridge | 1 | Basic Access Infrastructure | Access Trail | 1.2 | kms | 1027674 | 213090 | 1240764 | 2012-05-01 |  | 513837 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Manahao | 084815016 | Road Rehabilitation | 1 | Basic Access Infrastructure | Road | 1.08 | kms | 651214 | 147933 | 799147 | 2012-06-01 |  | 325607 | No movement as of July 31, 2012 | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Senonogan | 084815028 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.35 | kms | 514866 | 112752 | 627618 | 2012-03-19 | 2012-07-15 | 411892.8 | No movement as of May 31, 2012 reports | 1st |  | Completed | 2012-05-03
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Tula | 084815030 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.8 | kms | 597391 | 121794 | 719185 | 2012-03-12 | 2012-07-15 | 477912.8 |  | 1st |  | Completed | 2012-04-26
H1 | VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ynaguingayan | 084815014 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 670359 | 148062 | 818421 | 2012-06-01 |  | 536287 |  | 1st | Elem | On-going
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Balnasan | 084820001 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail |  | kms | 846429 | 117720 | 964149 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Coroconog | 084820004 | Construction of 1 Unit 2 Classroom School Building | 1 | Basic Social Services | School |  | sq. m | 1211413 | 221420 | 1432833 |  |  | 0 |  |  | Elem | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Dale | 084820005 | Construction of 1 Unit 2 Classroom School Building | 1 | Basic Social Services | School |  | sq. m | 1276148 | 151680 | 1427828 |  |  | 0 |  |  | Elem | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Lao-angan | 084820007 | Construction of 1 Unit 2 Classroom School Building | 1 | Basic Social Services | School |  | sq. m | 1276148 | 151680 | 1427828 |  |  | 0 |  |  | Elem | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 1 | 084820011 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 697126 | 92700 | 789826 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 2 | 084820012 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 491086 | 81960 | 573046 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 3 | 084820013 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 828210 | 121760 | 949970 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 4 | 084820014 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 664584 | 91880 | 756464 |  |  | 0 |  |  |  | Not yet started
H1 | VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 6 | 084820016 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control |  | ln.m | 708856 | 143004 | 851860 |  |  | 0 |  |  |  | Not yet started
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Alegria | 103501001 | Construction of Water System Level 2 | 1 | Basic Social Services | Water System | 1 | system | 1087415.42 | 364533.16 | 1451948.58 | 2011-03-15 | 2011-08-12 | 1087415.42 |  | 2nd |  | Completed | 2011-07-13
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Babalaya | 103501002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 570723.71 | 124978.78 | 695702.49 | 2011-02-14 | 2011-06-30 | 570723.71 |  | 2nd |  | Completed | 2011-05-15
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Debalayan West | 103501020 | Construction of Water System Level 2 | 1 | Basic Social Services | Water System | 1 | system | 961324.52 | 219772.13 | 1181096.65 | 2011-02-22 | 2011-06-30 | 961324.52 |  | 2nd |  | Completed | 2011-06-22
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Demologan | 103501006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 570723.71 | 119978.78 | 690702.49 | 2011-02-14 | 2011-07-28 | 570723.71 |  | 2nd |  | Completed | 2011-05-15
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Kahayag | 103501009 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 754629.2 | 154367.36 | 908996.56 | 2011-03-07 | 2011-07-28 | 754629.2 |  | 2nd |  | Completed | 2011-05-06
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Liangan East | 103501010 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 856082.32 | 177124.901 | 1033207.221 | 2011-02-05 | 2011-06-30 | 856082.32 |  | 2nd |  | Completed | 2011-04-06
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Mati | 103501013 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq.m | 584115.66 | 129315.02 | 713430.68 | 2011-02-23 | 2011-06-30 | 584115.66 |  | 2nd | Elem | Completed | 2011-05-24
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Minaulon | 103501016 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq.m | 1009505.13 | 176671.15 | 1186176.28 | 2011-02-21 | 2011-06-30 | 1009505.13 |  | 2nd | Elem | Completed | 2011-05-22
H1 | X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Pagayawan | 103501017 | Construction of Water System Level 2 | 1 | Basic Social Services | Water System | 1 | system | 1605480.35 | 524504.62 | 2129984.97 | 2011-03-15 | 2011-08-12 | 1605480.35 |  | 2nd |  | Completed | 2011-07-13
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Bansarvil 1 | 103505005 | Contruction of Potable Water System Level 2 (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 1358965.3 | 582413.7 | 1941379 | 2012-01-23 | 2012-05-15 | 1358965.3 |  | 2nd |  | Completed | 2012-04-23
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | De Asis | 103505016 | Construction of FMR (Opening) | 1 | Basic Access Infrastructure | Road | 0.727 | kms | 1216376.7 | 521304.3 | 1737681 | 2012-01-19 | 2012-06-15 | 1216376.7 |  | 2nd |  | Completed | 2012-05-19
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Kahayagan | 103505021 | Construction of Potable Water System Level 2 (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 1594617.5 | 683407.5 | 2278025 | 2012-01-17 | 2012-05-17 | 1594617.5 |  | 2nd |  | Completed | 2012-05-17
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Lapinig | 103505028 | Construction of Potable Water System Level 2 (Gravity Driven) | 1 | Basic Social Services | Water System | 1 | system | 1552082 | 665178 | 2217260 | 2012-01-23 | 2012-05-15 | 1552082 |  | 2nd |  | Completed | 2012-04-23
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Malinas | 103505031 | Construction of Brgy. Suso-Malinas Farm to Market Road | 1 | Basic Access Infrastructure | Road | 3.291 | kms | 2981421.1 | 1618209.9 | 4599631 | 2012-01-12 | 2012-06-15 | 2981421.1 |  | 2nd |  | Completed | 2012-06-12
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Poblacion | 103505036 | Construction of 1,641.5 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 1641.5 | ln.m | 1793562.2 | 979923.8 | 2773486 | 2012-01-24 | 2012-05-24 | 1793562.2 |  | 2nd |  | Completed | 2012-05-24
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | San Isidro | 103505039 | Construction of Potable Water System Level 2 (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 1236410 | 529890 | 1766300 | 2012-01-21 | 2012-05-15 | 1236410 |  | 2nd |  | Completed | 2012-04-21
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Sto. Tomas | 103505042 | Construction of FMR (Opening) | 1 | Basic Access Infrastructure | Road | 0.561 | kms | 1040050.2 | 445735.8 | 1485786 | 2012-01-23 | 2012-05-23 | 1040050.2 |  | 2nd |  | Completed | 2012-05-23
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Suso | 103505043 | Construction of Potable Water System Level 2 (Gravity Driven) | 1 | Basic Social Services | Water System | 1 | system | 1507787.4 | 646194.6 | 2153982 | 2012-01-25 | 2012-05-15 | 1507787.4 |  | 2nd |  | Completed | 2012-04-25
H1 | X | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Tulatulahan | 103505049 | Construction of 51 sq.m Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 568727.6 | 243740.4 | 812468 | 2012-01-23 | 2012-05-15 | 568727.6 |  | 2nd |  | Completed | 2012-04-23
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Abaga | 103509001 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 569495.5 | 215928.66 | 785424.16 | 2012-07-09 |  | 455596.4 |  | 1st |  | On-going | 2012-10-08 | 0
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Andil | 103509002 | Upgrading/Rehabilitation of FMR | 1 | Basic Access Infrastructure | Road | 2 | kms | 1926961.16 | 782431.72 | 2709392.88 | 2011-06-30 | 2011-08-15 | 1926961.16 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Andil | 103509002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 579187.82 | 220812.18 | 800000 | 2012-07-09 |  | 463350.26 |  | 1st |  | On-going | 2012-10-08 | 0
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Cabasagan | 103509005 | Rehabilitation of FMR | 1 | Basic Access Infrastructure | Road | 1.6 | kms | 1423967.07 | 496032.93 | 1920000 | 2012-06-30 |  | 1139173.66 |  | 1st |  | On-going | 2012-09-20
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Camalan | 103509006 | Construction of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 150 | ln.m | 1772604.16 | 796065.84 | 2568670 | 2011-05-23 | 2011-08-30 | 1772604.16 |  | 2nd |  | Completed | 2011-08-30
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Darumawang Bucana | 103509004 | Concreting of Elevated Footpath | 1 | Basic Access Infrastructure | Access Trail | 0.666 | kms | 2217170.85 | 689800 | 2906970.85 | 2011-06-30 | 2011-09-15 | 2217170.85 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | El Salvador | 103509009 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 595648.02 | 204351.98 | 800000 | 2012-07-09 |  | 476518.42 |  | 1st |  | On-going | 2012-10-08 | 0
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Gumagamot | 103509010 | Construction of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | 180 | ln.m | 2069673.53 | 860864.47 | 2930538 | 2012-07-13 |  | 1655738.82 |  | 1st |  | On-going | 2012-11-03
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Lanipao | 103509013 | Upgrading/Rehabilitation of FMR | 1 | Basic Access Infrastructure | Road | 1.6 | kms | 1066113.49 | 985886.51 | 2052000 | 2011-06-14 | 2011-08-15 | 1066113.48 |  | 2nd |  | Completed | 2011-07-31
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Matampay Bucana | 103509003 | Upgrading/Rehabilitation of FMR | 1 | Basic Access Infrastructure | Road | 1.71 | kms | 2082815.68 | 703662.02 | 2786477.7 | 2011-06-30 | 2011-10-15 | 2082815.68 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Matampay Bucana | 103509003 | Construction of FMR | 1 | Basic Access Infrastructure | Road | 0.85 | kms | 2521469.22 | 833530.78 | 3355000 | 2012-07-30 |  | 2017175.38 |  | 1st |  | On-going | 2012-10-30
F2 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Matampay Ilaya | 103509016 | Construction of FMR | 1 | Basic Access Infrastructure | Road | 0.48 | kms | 1606006.92 | 593993.08 | 2200000 | 2012-06-26 |  | 1284805.54 |  | 1st |  | On-going | 2012-09-16
F2 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Pinoyak | 103509019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 579107.12 | 220892.88 | 800000 | 2012-07-05 |  | 463285.7 |  | 1st |  | On-going | 2012-10-04 | 0
F2 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Rebe | 103509021 | Rehabilitation of FMR | 1 | Basic Access Infrastructure | Road | 1.3 | kms | 1619569.8 | 576730.2 | 2196300 | 2012-07-30 |  | 1295655.84 |  | 1st |  | On-going | 2012-10-30
F2 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | San Manuel | 103509024 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 585875 | 213897.52 | 799772.52 | 2012-07-03 |  | 468700 |  | 1st |  | On-going | 2012-10-03 | 0
F2 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Sta. Cruz Lower | 103509025 | Upgrading/Rehabilitation of FMR | 1 | Basic Access Infrastructure | Road | 1.865 | kms | 1928301.79 | 791698.21 | 2720000 | 2011-06-13 | 2011-09-15 | 1928301.79 |  | 2nd |  | Completed | 2011-07-31
F2 | X | 10 | Lanao Del Norte | 1035 | Lala | 103509 | Tuna-an | 103509029 | Construction of Solar Dryer with Warehouse and Rice Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 408 | sq.m | 1156032.87 | 297967.13 | 1454000 | 2011-05-23 | 2011-08-20 | 1156032.87 |  | 2nd |  | Completed | 2011-08-20
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Tinampo, Laniwan, Tambangan, B. Aquino Jr. & Asum | 084814010 | Construction of Drainage Canal | 5 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4800 | ln.m | 4141969 | 2040709 | 6182678 | 2011-12-01 |  | 2070984 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Tinampo, Laniwan, Tambangan, B. Aquino Jr. & Asum | 084814032 | Construction of Drainage Canal | 5 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4800 | ln.m | 4141969 | 2040709 | 6182678 | 2011-12-01 |  | 2070984 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Tinampo, Laniwan, Tambangan, B. Aquino Jr. & Asum | 084814034 | Construction of Drainage Canal | 5 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4800 | ln.m | 4141969 | 2040709 | 6182678 | 2011-12-01 |  | 2070984 |  | 1st |  | On-going
H1 | VIII | 08 | Northern Samar | 0848 | Palapag | 084814 | Tinampo, Laniwan, Tambangan, B. Aquino Jr. & Asum | 084814001 | Construction of Drainage Canal | 5 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4800 | ln.m | 4141969 | 2040709 | 6182678 | 2011-12-01 |  | 2070984 |  | 1st |  | On-going
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Barandia, Pagalongan & Pagayawan | 103518001 | Construction of Potable Water System Level II | 3 | Basic Social Services | Water System | 1 | system | 2300000 | 553750 | 2853750 | 2012-05-02 |  | 1840000 |  | 1st |  | On-going | 2012-08-31
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Bulacon | 103518002 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1090000 | 252480 | 1342480 | 2012-03-08 | 2012-07-15 | 872000 |  | 1st | Elem | Completed | 2012-06-21
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Calimodan | 103518004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 610000 | 158570 | 768570 | 2012-03-02 | 2012-07-15 | 488300 |  | 1st |  | Completed | 2012-05-15
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Curva Miagao | 103518006 | Installation of Water System Level I (Hand Pumps) | 1 | Basic Social Services | Water System | 1 | system | 320000 | 85840 | 405840 | 2012-03-17 | 2012-07-15 | 256000 |  | 1st |  | Completed | 2012-06-24
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Inasagan | 103518025 | Brgy. Submarine Bridge | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 3 | ln.m | 470000 | 126940 | 596940 | 2012-07-02 |  | 376000 |  | 1st |  | On-going | 2012-09-29
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Kilala | 103518008 | Construction of Submarine Bridge Extension | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 40 | ln.m | 2200000 | 490100 | 2690100 | 2012-05-01 |  | 1760000 |  | 1st |  | On-going | 2012-08-30
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mabatao | 103518009 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1590000 | 356130 | 1946130 | 2012-03-07 | 2012-07-15 | 1272000 |  | 1st | Elem | Completed | 2012-06-22
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Madaya | 103518010 | Installation of Water System Level I (Hand Pumps) | 1 | Basic Social Services | Water System | 1 | system | 250000 | 71500 | 321500 | 2012-03-10 | 2012-07-15 | 200000 |  | 1st |  | Completed | 2012-05-18
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mamaanon | 103518011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 610000 | 158570 | 768570 | 2012-03-05 | 2012-07-15 | 488000 |  | 1st |  | Completed | 2012-05-18
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mapantao | 103518012 | Installation of Water System Level I (Hand Pumps) | 1 | Basic Social Services | Water System | 1 | system | 180000 | 56910 | 236910 | 2012-03-08 | 2012-07-15 | 144000 |  | 1st |  | Completed | 2012-04-26
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mindalano | 103518013 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 450 | sq.m | 460000 | 134520 | 594520 | 2012-02-06 | 2012-07-15 | 368000 |  | 1st |  | Completed | 2012-05-05
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Pangantapan | 103518018 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 610000 | 158570 | 768570 | 2012-03-03 | 2012-07-15 | 488000 |  | 1st |  | Completed | 2012-05-16
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Patidon | 103518020 | Installation of Water System Level I (Hand Pumps) | 1 | Basic Social Services | Water System | 1 | system | 250000 | 71500 | 321500 | 2012-02-09 | 2012-07-15 | 200000 |  | 1st |  | Completed | 2012-04-18
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Poblacion | 103518022 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 610000 | 158570 | 768570 | 2012-03-08 | 2012-07-15 | 488000 |  | 1st |  | Completed | 2012-05-23
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Saumay | 103518023 | Installation of Water System Level I (Hand Pumps) | 1 | Basic Social Services | Water System | 1 | system | 250000 | 71500 | 321500 | 2012-03-01 | 2012-05-09 | 200000 |  | 1st |  | Completed | 2012-05-09
H1 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Sudlon | 103518024 | Brgy. Road Improvement (Regravelling w/ Concreting) | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 700000 | 166410 | 866410 | 2012-01-31 | 2012-07-15 | 560000 | No movement as of May 31, 2012 reports | 1st |  | Completed | 2012-05-31
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Dansalan | 103519004 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 633662 | 204211 | 837873 | 2012-03-01 | 2012-06-15 | 633662 |  | 2nd |  | Completed | 2012-05-14
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Inudaran I | 103519006 | Rehab./Upgrading of FMR | 1 | Basic Access Infrastructure | Road | 1.1 | kms | 1043819.31 | 716812.23 | 1760631.54 | 2012-03-14 | 2012-06-15 | 1043819.31 |  | 2nd |  | Completed | 2012-06-21
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Inudaran II | 103519007 | Rehab./Upgrading of FMR | 1 | Basic Access Infrastructure | Road | 1.1 | kms | 1113926.19 | 586925.81 | 1700852 | 2012-03-09 |  | 891141 |  | 1st |  | On-going | 2012-06-16
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Katipunan | 103519009 | Regravelling of FMR w/ Concreting | 1 | Basic Access Infrastructure | Road | 1.4 | kms | 996290.79 | 1067002.21 | 2063293 | 2012-03-07 | 2012-07-15 | 996290.79 |  | 2nd |  | Completed | 2012-06-19
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mala Salug | 103519012 | Rehab./Upgrading of FMR | 1 | Basic Access Infrastructure | Road | 1.9 | kms | 1004667.98 | 922472.77 | 1927140.75 | 2012-03-15 | 2012-06-15 | 1004667.98 |  | 2nd |  | Completed | 2012-07-13
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mama-anon | 103519013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 546086 | 221524 | 767610 | 2012-03-01 | 2012-05-14 | 546086 |  | 2nd |  | Completed | 2012-05-14
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Pancilan | 103519016 | Expansion of Pancilan Bridge w/ 2 Barriers | 1 | Basic Access Infrastructure | Foot/Small Bridges | 48.6 | sq.m | 309601.01 | 141391.99 | 450993 | 2012-02-22 | 2012-05-15 | 309601.01 |  | 2nd |  | Completed | 2012-04-22
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Panoloon | 103519017 | Rehab./Upgrading of FMR | 1 | Basic Access Infrastructure | Road | 1 | kms | 1428676.45 | 657336.87 | 2086013.32 | 2012-03-08 | 2012-07-15 | 1428676.45 |  | 2nd |  | Completed | 2012-06-06
H1 | X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Buriasan (Poblacion) | 103519002 | Construction of Open Drainage Open Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 700 | ln.m | 1423270.27 | 608311.73 | 2031582 | 2012-03-08 | 2012-06-15 | 1423270.27 |  | 2nd |  | Completed | 2012-06-06
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Bagong Nayon | 104206001 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 288 | sq.m | 319006.87 | 102917.26 | 421924.13 | 2011-04-01 | 2011-06-30 | 319006.87 |  | 2nd |  | Completed | 2011-05-31
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Guiban | 104206004 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 288 | sq.m | 281377.98 | 117481.17 | 398859.15 | 2011-04-30 | 2011-09-15 | 281377.98 |  | 2nd |  | Completed | 2011-05-31
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Laya-an | 104206005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 539199.5 | 182422.65 | 721622.15 | 2011-03-25 | 2011-08-15 | 539199.5 |  | 2nd |  | Completed | 2011-06-08
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Mantukoy | 104206008 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 288 | sq.m | 285024.05 | 115525.11 | 400549.16 | 2011-04-01 | 2011-09-15 | 285024.05 |  | 2nd |  | Completed | 2011-05-31
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | New Casul | 104206003 | Farm to Market Road | 1 | Basic Access Infrastructure | Road | 2.177 | kms | 4753511.46 | 282776.71 | 5036288.17 |  |  | 0 |  |  |  | Not yet started
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Small Potongan | 104206013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 559199.5 | 164422.65 | 723622.15 | 2011-03-16 | 2011-09-15 | 559199.5 |  | 2nd |  | Completed | 2011-05-30
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Dioyo | 104206016 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 632857.89 | 121722.38 | 754580.27 | 2011-03-08 | 2011-08-15 | 632857.83 |  | 2nd |  | Completed | 2011-06-06
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Potongan | 104206017 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 288 | sq.m | 280767.97 | 99493.58 | 380261.55 | 2011-02-28 | 2011-03-31 | 280767.97 |  | 2nd |  | Completed | 2011-04-29
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Salimpuno | 104206018 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 716196.89 | 128106.11 | 844303 | 2011-02-21 | 2011-05-31 | 716196.89 |  | 2nd |  | Completed | 2011-05-22
H1 | X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Virayan | 104206019 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 632857.89 | 121772.38 | 754630.27 | 2011-03-15 | 2011-10-15 | 632857.89 |  | 2nd |  | Completed | 2011-06-18
H1 | X | 10 | Misamis Occidental | 1042 | Don Victoriano Chiongbian | 104217 | Liboron | 104217006 | Concreting of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.55 | kms | 1674056.39 | 421560.61 | 2095617 | 2012-07-20 |  | 1339245.11 |  | 1st |  | On-going | 2012-10-19
H1 | X | 10 | Misamis Occidental | 1042 | Don Victoriano Chiongbian | 104217 | Napangan | 104217008 | Concreting of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.42 | kms | 1866305.2 | 402551.8 | 2268857 | 2012-06-24 |  | 1493044.16 |  | 1st |  | On-going | 2012-10-24
H1 | X | 10 | Misamis Occidental | 1042 | Don Victoriano Chiongbian | 104217 | Nueva Vista | 104217009 | Concreting of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.6 | kms | 1959638.41 | 421487.59 | 2381126 | 2012-07-16 |  | 1567710.73 |  | 1st |  | On-going | 2012-11-15
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Bagong Silang | 104208002 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.433 | kms | 451211 | 178789 | 630000 | 2011-06-01 | 2011-08-15 | 451211 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Burgos | 104208005 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 713144 | 136856 | 850000 | 2011-05-01 | 2011-07-28 | 713144 |  | 2nd |  | Completed | 2011-07-02
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Dalacon | 104208006 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.9 | kms | 1248038.24 | 234821 | 1482859.24 | 2011-06-19 | 2011-09-15 | 1248038.24 |  | 2nd |  | Completed | 2011-07-31
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Don Andres Soriano | 104208027 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 1.439 | kms | 1971074.3 | 182816 | 2153890.3 | 2011-05-23 | 2011-09-15 | 1971074.3 |  | 2nd |  | Completed | 2011-07-31
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Jasa-an | 104208010 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 1.05 | kms | 1186261.05 | 153738.95 | 1340000 | 2011-04-08 | 2011-08-15 | 1186261.05 |  | 2nd |  | Completed | 2011-07-10
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Katipa | 104208011 | Brgy. Road Improvement/Gravelling | 1 | Basic Access Infrastructure | Road | 0.792 | kms | 888487 | 181513 | 1070000 | 2011-04-01 | 2011-09-15 | 888487 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mabas | 104208028 | Road Improvement (Foot Trail) | 1 | Basic Access Infrastructure | Access Trail | 0.9 | kms | 1127997.65 | 257002.35 | 1385000 | 2011-04-01 | 2011-06-20 | 1127997.65 |  | 2nd |  | Completed | 2011-06-20
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Macalibre Bajo | 104208014 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 1440857 | 222591 | 1663448 | 2011-04-09 | 2011-09-15 | 1440857 |  | 2nd |  | Completed | 2011-07-15
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mahayahay | 104208015 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 551602.88 | 198138 | 749740.88 | 2011-03-07 | 2011-09-15 | 551602.88 |  | 2nd |  | Completed | 2011-05-26
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Manguehan | 104208016 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 601602.88 | 148138 | 749740.88 | 2011-02-23 | 2011-06-30 | 601602.88 |  | 2nd |  | Completed | 2011-05-14
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mansabay Bajo | 104208017 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.915 | kms | 937824 | 282176 | 1220000 | 2011-04-02 | 2011-07-28 | 937824 |  | 2nd |  | Completed | 2011-07-31
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Peniel | 104208021 | Brgy. Road Improvement | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 648144 | 206856 | 855000 | 2011-06-01 | 2011-09-15 | 648144 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Rizal | 104208024 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 609422 | 139138 | 748560 | 2011-02-23 | 2011-06-30 | 609422 |  | 2nd |  | Completed | 2011-05-14
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Sibugon | 104208025 | Construction of 1 Unit 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq.m | 1023912 | 193073 | 1216985 | 2011-04-07 | 2011-09-15 | 1023912 |  | 2nd | HS | Completed | 2011-06-21
H1 | X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Western Poblacion | 104208030 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 600422 | 148138 | 748560 | 2011-03-07 | 2011-08-18 | 600422 |  | 2nd |  | Completed | 2011-05-26
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Camanse | 104214002 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 1170740.6 | 486733.4 | 1657474 | 2012-07-08 |  | 936592.48 |  | 1st |  | On-going | 2012-11-07 | 0
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Colupan Alto | 104214004 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 1064604.7 | 456000.3 | 1520605 | 2012-07-02 |  | 0 |  |  |  | On-going | 2012-11-01 | 0
F2 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Dinas | 104214006 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.21 | kms | 756704.2 | 294751.8 | 1051456 | 2011-05-02 | 2011-09-15 | 756704.2 |  | 2nd |  | Completed | 2011-08-13
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Estrella | 104214007 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1142972.1 | 509330.9 | 1652303 | 2012-07-08 |  | 0 |  |  |  | On-going | 2012-11-07 | 0
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Katipunan | 104214008 | Road Improvement | 1 | Basic Access Infrastructure | Road | 2.15 | kms | 2507422.4 | 1074609.6 | 3582032 | 2011-06-23 | 2011-12-15 | 2005937.92 | Completed (as-built) - community waived to avail 2nd tranch RFR due delayed SPI | 1st |  | Completed | 2011-07-31
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Katipunan | 104214008 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1155819.9 | 472941.1 | 1628761 | 2012-07-10 |  | 0 |  |  |  | On-going | 2012-11-09 | 0
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Poblacion | 104214013 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.32 | kms | 1398496.4 | 599355.6 | 1997852 | 2011-05-02 | 2011-09-15 | 1398496.4 |  | 2nd |  | Completed | 2011-08-13
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | San Isidro Alto | 104214014 | Construction of Trading Post | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 96 | sq.m | 467255.6 | 217352.4 | 684608 | 2011-05-02 | 2011-08-15 | 467255.6 |  | 2nd |  | Completed | 2011-07-23
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | San Lorenzo Ruiz (Sungan) | 104214019 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 995462.3 | 407515.7 | 1402978 | 2012-07-06 |  | 796369.84 |  | 1st |  | On-going | 2012-11-05 | 0
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | San Vicente | 104214016 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1054320.3 | 552734.7 | 1607055 | 2012-07-08 |  | 843456.24 |  | 1st |  | On-going | 2012-11-07 | 0
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Señor | 104214017 | Road Improvement | 1 | Basic Access Infrastructure | Road | 1.15 | kms | 1275640.8 | 546703.2 | 1822344 | 2011-06-23 | 2011-09-15 | 1275640.8 |  | 2nd |  | Completed | 2011-07-31
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Sinonoc | 104214018 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 674.55 | ln.m | 1228234 | 526386 | 1754620 | 2011-05-02 | 2011-08-15 | 1228234 |  | 2nd |  | Completed | 2011-07-30
H1 | X | 10 | Misamis Occidental | 1042 | Sinacaban | 104214 | Tipan | 104214020 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 1001166.9 | 506384.1 | 1507551 | 2012-07-09 |  | 800933.52 |  | 1st |  | On-going | 2012-11-08 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Aurora | 118201016 | Construction of Potable Water System - Underground Source | 1 | Basic Social Services | Water System | 1 | system | 1007582 | 189880 | 1197462 | 2011-06-20 | 2011-08-19 | 1007582 |  | 2nd |  | Completed | 2011-08-19
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Bagongon | 118201001 | Construction of Hanging Cable Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 68 | ln.m | 2052476 | 380634 | 2433110 | 2011-07-29 | 2011-11-15 | 2052476 |  | 2nd |  | Completed | 2011-10-27
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Gabi | 118201002 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 168 | sq. m | 1275450 | 244341 | 1519791 | 2011-06-15 | 2011-08-14 | 1275450 |  | 2nd | Elem | Completed | 2011-08-14
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Gabi | 118201002 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 419363 | 1015957 | 1435320 | 2012-07-05 |  | 0 |  |  |  | On-going | 2012-09-03 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Lagab | 118201003 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1049315 | 283385 | 1332700 |  |  | 839452 |  | 1st |  | Not yet started |  | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Mangayon | 118201004 | Construction of Potable Water System - Spring Source | 1 | Basic Social Services | Water System | 1 | system | 337598 | 566943 | 904541 | 2011-06-17 | 2011-07-31 | 337598 |  | 2nd |  | Completed | 2011-08-16
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Maparat | 118201006 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1387744 | 336019 | 1723763 | 2012-06-15 |  | 971420.8 |  | 1st | Elem | On-going | 2012-08-29 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Ngan | 118201008 | Construction of Potable Water System - Spring Source | 1 | Basic Social Services | Water System | 1 | system | 1216085 | 326593 | 1542678 | 2011-06-13 | 2011-07-31 | 1216085 |  | 2nd |  | Completed | 2011-08-12
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Panansalan | 118201010 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 759434 | 131464 | 890898 |  |  | 387500.4 |  | 1st |  | Not yet started |  | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | San Jose | 118201012 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 576648 | 122279 | 698927 | 2011-06-13 | 2011-08-12 | 576648 |  | 2nd |  | Completed | 2011-08-12
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | San Miguel | 118201013 | Construction of Potable Water System - Spring Source | 1 | Basic Social Services | Water System | 1 | system | 734161 | 259140 | 993301 | 2011-06-13 | 2011-07-31 | 734161 |  | 2nd |  | Completed | 2011-08-12
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | San Miguel | 118201013 | Construction of Hanging Cable Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 68 | ln.m | 1544580 | 646253 | 2190833 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Siocon | 118201014 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 126 | sq. m | 911357 | 246877 | 1158234 | 2012-06-22 |  | 637949.9 |  | 1st | HS | On-going | 2012-08-21 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Compostela | 118201 | Tamia | 118201015 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1128207 | 216729 | 1344936 | 2012-07-05 |  | 902565.6 |  | 1st |  | On-going | 2012-09-03 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Anitapan | 118203012 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 578876 | 111238 | 690114 | 2012-05-25 | 2012-07-24 | 463100.8 |  | 1st | Elem | Completed | 2012-07-24 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Cabuyuan | 118203013 | Improvement of 2 Km. Barangay Road | 1 | Basic Access Infrastructure | Road | 2 | kms | 424855 | 698224 | 1123079 | 2012-05-15 | 2012-07-16 | 339884 |  | 1st |  | Completed | 2012-07-16 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Cadunan | 118203002 | Construction of Potable Water System L-2 | 1 | Basic Social Services | Water System | 1 | system | 394872 | 72576 | 467448 | 2012-04-20 | 2012-05-31 | 315897.6 |  | 1st |  | Completed | 2012-06-19 | 0
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Barandia, Pagalongan & Pagayawan | 103518015 | Construction of Potable Water System Level II | 3 | Basic Social Services | Water System | 1 | system | 2300000 | 553750 | 2853750 | 2012-05-02 |  | 1840000 |  | 1st |  | On-going | 2012-08-31
F2 | X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Barandia, Pagalongan & Pagayawan | 103518016 | Construction of Potable Water System Level II | 3 | Basic Social Services | Water System | 1 | system | 2300000 | 553750 | 2853750 | 2012-05-02 |  | 1840000 |  | 1st |  | On-going | 2012-08-31
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Candinuyan |  | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 571686 | 108829 | 680515 | 2012-05-10 | 2012-07-09 | 457348.8 |  | 1st |  | Completed | 2012-07-09 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Cuambog | 118203007 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 546956 | 104879 | 651835 | 2012-04-20 | 2012-06-15 | 437564.8 |  | 1st |  | Completed | 2012-06-19 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Del Pilar | 118203014 | Construction of Potable Water System L-2 | 1 | Basic Social Services | Water System | 1 | system | 407436 | 74599 | 482035 | 2012-05-02 | 2012-06-15 | 325948.8 |  | 1st |  | Completed | 2012-07-01 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Golden Vallley | 118203016 | Construction of 24 Ln.m Steeldeck Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 24 | ln.m | 610082 | 106976 | 717058 | 2012-05-20 |  | 488065.6 |  | 1st |  | On-going | 2012-07-19 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Libodon | 118203015 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 550326 | 106688 | 657014 | 2012-05-15 |  | 440260.8 |  | 1st | Elem | On-going | 2012-07-14 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Mambatang |  | Construction of 18 Ln.m Steeldeck Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 18 | ln.m | 542415 | 96046 | 638461 | 2012-05-10 | 2012-07-09 | 433932 |  | 1st |  | Completed | 2012-07-09 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Manasa |  | Improvement of 2.2 km. Brgy. Road | 1 | Basic Access Infrastructure | Road | 2.2 | kms | 611050 | 900645 | 1511695 | 2012-05-15 |  | 488840 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-14 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Mascareg |  | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 580286 | 110229 | 690515 | 2012-05-10 | 2012-07-09 | 464228.8 |  | 1st |  | Completed | 2012-07-09 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Pangibiran | 118203017 | Construction of 100m Grouted Riprap | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 100 | ln.m | 437621 | 131224 | 568845 | 2012-05-25 |  | 350096.8 |  | 1st |  | On-going | 2012-07-24 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Pindasan | 118203006 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 544726 | 105788 | 650514 | 2012-05-10 |  | 435780.8 |  | 1st | Elem | On-going | 2012-07-09 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | San Antonio | 118203018 | Improvement of 1.5 Km. Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 460315 | 646522 | 1106837 | 2012-05-10 | 2012-07-09 | 368252 |  | 1st |  | Completed | 2012-07-09 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Singapore |  | Capability Building on Abaca Fiber Processing Technology | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | 1 | unit | 422650 | 76985 | 499635 | 2012-05-18 |  | 338120 |  | 1st |  | On-going | 2012-07-17 | 0
H1 | XI | 11 | Compostela Valley | 1182 | Mabini (Doña Alicia) | 118203 | Tagnanan | 118203011 | Improvement of Existing Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 315848 | 59949 | 375797 | 2012-05-05 | 2012-06-15 | 252678.4 |  | 1st |  | Completed | 2012-06-09 | 0
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Cabidianan | 112314001 | Construction of Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 1212312 | 233710 | 1446022 | 2012-06-20 |  | 969849.6 |  | 1st |  | On-going | 2012-10-18
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Carcor | 112314002 | Upgrading of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.12 | kms | 412961 | 519434 | 932395 | 2012-02-06 | 2012-07-15 | 412961 |  | 2nd |  | Completed | 2012-06-05
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | El Salvador | 112314005 | Construction of Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 1110364 | 208573 | 1318937 | 2012-02-14 | 2012-05-15 | 1110364 |  | 2nd |  | Completed | 2012-06-13
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Macgum | 112314007 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1091630 | 244074 | 1335704 | 2012-02-01 | 2012-05-15 | 1091630 |  | 2nd | Elem | Completed | 2012-05-31
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Mambing | 112314008 | Upgrading of Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 706196 | 162997 | 869193 | 2012-02-13 |  | 706196 | No movement as of July 31, 2012 | 2nd |  | On-going | 2012-06-12
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Mesaoy | 112314009 | Upgrading of Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 1255057 | 589096 | 1844153 | 2012-06-20 |  | 753034.2 |  | 1st |  | On-going | 2012-10-18
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | New Bohol | 112314010 | Construction of School Facility: Productivity Skill Learning Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 56 | sq. m | 782585 | 139928 | 922513 | 2012-02-06 | 2012-06-15 | 782585 |  | 2nd |  | Completed | 2012-06-05
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | New Cortez | 112314011 | Upgrading of Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 1718689 | 430346 | 2149035 | 2012-07-01 |  | 1374951.2 |  | 1st |  | On-going | 2012-09-29
H1 | XI | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Sta. Cruz | 112314016 | Upgrading of Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 710206 | 163595 | 873801 | 2012-02-13 | 2012-06-15 | 710206 |  | 2nd |  | Completed | 2012-06-12
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Balagunan | 112318001 | Construction of Productivity Learning Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 48 | sq.m | 542634 | 92937 | 635571 | 2012-03-02 |  | 434107.2 |  | 1st |  | On-going | 2012-05-31 | 0
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Bobongon | 112318002 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 24.5 | ln.m | 362503 | 165725 | 528228 | 2012-03-06 |  | 290002.4 |  | 1st |  | On-going | 2012-06-04
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Casig-ang | 112318016 | Construction of Drainage Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 482638 | 96258 | 578896 | 2012-03-07 |  | 386110.4 |  | 1st |  | On-going | 2012-06-05
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Esperanza | 112318003 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 508732 | 131165 | 639897 | 2012-03-08 | 2012-07-15 | 508732 |  | 2nd |  | Completed | 2012-06-06
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Kimamon | 112318004 | Construction of Technological & Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 48 | sq. m | 445670 | 111464 | 557134 | 2012-03-03 |  | 356536 |  | 1st |  | On-going | 2012-06-01
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Kinamayan | 112318005 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 526873 | 111740 | 638613 | 2012-03-01 | 2012-06-15 | 421498.4 |  | 1st | Elem | Completed | 2012-05-30
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | La Libertad | 112318006 | Construction of Drainage Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 454105 | 122526 | 576631 | 2012-03-08 | 2012-07-15 | 454105 |  | 2nd |  | Completed | 2012-06-06
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Lungaog | 112318007 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | 190 | ln.m | 394229 | 93125 | 487354 | 2012-03-01 | 2012-07-15 | 315383.2 |  | 1st |  | Completed | 2012-05-30
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Magwawa | 112318008 | Construction of Technological & Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 48 | sq. m | 495487 | 77469 | 572956 | 2012-03-02 | 2012-07-15 | 396389.6 |  | 1st |  | Completed | 2012-05-31
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | New Katipunan | 112318009 | Construction of 1 Unit School Building w/ 2 Classroom (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 899338 | 279497 | 1178835 | 2012-02-27 | 2012-07-15 | 719470.4 |  | 1st | Elem | Completed | 2012-05-27
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | New Visayas | 112318017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 503295 | 94705 | 598000 | 2012-06-09 |  | 402636 | From School Fence to DCC | 1st |  | On-going | 2012-07-19 | 0
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Pantaron | 112318010 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 550557 | 87164 | 637721 | 2012-03-09 | 2012-07-15 | 440445.6 |  | 1st |  | Completed | 2012-06-07
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Salvacion | 112318018 | Construction of 1 Unit School Building w/ 1 Classroom (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 529304 | 109309 | 638613 | 2012-03-07 | 2012-06-15 | 529304 |  | 2nd | Elem | Completed | 2012-06-05
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | San Miguel | 112318014 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | 150 | ln.m | 378997 | 111023 | 490020 | 2012-03-06 | 2012-07-15 | 303197.6 |  | 1st |  | Completed | 2012-06-04
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | San Vicente | 112318019 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 981769 | 463206 | 1444975 | 2012-03-05 | 2012-07-15 | 785415.2 |  | 1st |  | Completed | 2012-06-03
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Tibal-og | 112318011 | Improvement of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 302869 | 151779 | 454648 | 2012-02-23 | 2012-04-15 | 302869 |  | 2nd |  | Completed | 2012-04-23
H1 | XI | 11 | Davao Del Norte | 1123 | Sto. Tomas | 112318 | Tulalian | 112318020 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1141000 | 203696 | 1344696 | 2012-03-02 | 2012-06-15 | 912800 |  | 1st |  | Completed | 2012-05-31
H1 | XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Barobo |  | Construction of Tribal Housing | 1 | Basic Social Services | Tribal Housing/Shelter | 29 | unit | 1301000 | 249000 | 1550000 | 2011-03-01 | 2011-04-30 | 1301000 |  | 2nd |  | Completed | 2011-04-30
H1 | XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Dagohoy | 112322001 | Construction of Tribal Housing | 1 | Basic Social Services | Tribal Housing/Shelter | 28 | unit | 1248500 | 239700 | 1488200 | 2011-03-01 | 2011-07-31 | 1248500 |  | 2nd |  | Completed | 2011-04-30
H1 | XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Mesolong |  | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 168 | sq. m | 1282250 | 175600 | 1457850 | 2011-03-01 | 2011-07-31 | 1282250 |  | 2nd | Elem | Completed | 2011-04-30
H1 | XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Nasilaban |  | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 796300 | 110400 | 906700 | 2011-03-01 | 2011-07-31 | 796300 |  | 2nd | Elem | Completed | 2011-04-30
H1 | XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Pongpong |  | Construction of Tribal Housing | 1 | Basic Social Services | Tribal Housing/Shelter | 30 | unit | 1344285 | 254400 | 1598685 | 2011-05-01 | 2011-07-31 | 1344285 |  | 2nd |  | Completed | 2011-06-30
H1 | XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Salawao |  | Construction of Tribal Housing | 1 | Basic Social Services | Tribal Housing/Shelter | 28 | unit | 1254000 | 242300 | 1496300 | 2011-03-01 | 2011-04-30 | 1254000 |  | 2nd |  | Completed | 2011-04-30
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Anitap | 112506001 | Construction of Drainage Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 431526 | 95697 | 527223 | 2012-01-27 |  | 431526 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-05-16
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Don Aurelio Chicote | 112506003 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 47.04 | ln.m | 570162 | 143463 | 713625 | 2012-02-27 | 2012-06-15 | 570162 | No movement as of May 31, 2012 reports | 2nd |  | Completed | 2012-05-27
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Crispin Dela Cruz | 112506020 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1289884 | 301825 | 1591709 | 2012-05-14 |  | 1031907.2 |  | 1st |  | On-going | 2012-09-11
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Lavigan | 112506004 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 569724 | 164907 | 734631 | 2012-01-25 | 2012-04-15 | 569724 |  | 2nd |  | Completed | 2012-05-14
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Luzon | 112506005 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 567115 | 164516 | 731631 | 2012-01-24 | 2012-04-15 | 567115 |  | 2nd |  | Completed | 2012-05-13
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Magdug | 112506006 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | 875 | ln.m | 573278 | 174160 | 747438 | 2012-02-15 | 2012-05-15 | 573278 |  | 2nd |  | Completed | 2012-06-04
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Manuel Roxas | 112506002 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | 312.5 | ln.m | 405803 | 110319 | 516122 | 2012-01-24 | 2012-05-13 | 405803 |  | 2nd |  | Completed | 2012-05-13
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Monserrat | 112506007 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | 450 | ln.m | 674473 | 148109 | 822582 | 2012-01-25 |  | 674473 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-05-14
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Poblacion | 112506010 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | 600 | ln.m | 773848 | 335955 | 1109803 | 2012-02-20 |  | 773848 | No movement as of May 31, 2012 reports | 2nd |  | On-going | 2012-06-09
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Pundaguitan | 112506011 | Construction of Food Terminal | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 112 | sq.m | 1162777 | 229871 | 1392648 | 2012-06-06 |  | 697666.2 |  | 1st |  | On-going | 2012-09-24
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Tiblawan | 112506018 | Construction of Potable Water System Level II (Spring) | 1 | Basic Social Services | Water System | 1 | system | 1375573 | 321992 | 1697565 | 2012-06-07 | 2012-07-15 | 1100458 |  | 1st |  | Completed | 2012-09-25
H1 | XI | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Upper Tibanban | 112506019 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 605837 | 110324 | 716161 | 2012-01-24 | 2012-04-15 | 605837 |  | 2nd |  | Completed | 2012-05-13
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Capasnan | 112508001 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 237804 | 93175 | 330979 | 2012-03-21 | 2012-06-15 | 237804 |  | 2nd |  | Completed | 2012-06-09
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Cayawan | 112508002 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 971426 | 324657 | 1296083 | 2012-03-21 |  | 971426 |  | 2nd | Elem | On-going | 2012-07-09
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Concepcion | 112508004 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 566997 | 170054 | 737051 | 2012-03-19 |  | 453597.6 |  | 1st |  | On-going | 2012-06-07
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Del Pilar | 112508006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 503976 | 161612 | 665588 | 2012-03-26 | 2012-07-15 | 403180.8 |  | 1st |  | Completed | 2012-06-14
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Holy Cross | 112508008 | Construction of Food Terminal | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 90 | sq.m | 961393 | 309225 | 1270618 | 2012-03-12 | 2012-06-15 | 961393 |  | 2nd |  | Completed | 2012-06-30
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Lambog | 112508018 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 972276 | 325807 | 1298083 | 2012-03-29 |  | 777820.8 |  | 1st | Elem | On-going | 2012-07-09
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Mabini | 112508009 | Improvement of 5.0 Km. Brgy. Road | 1 | Basic Access Infrastructure | Road | 5 | kms | 811810 | 221743 | 1033553 | 2012-04-23 | 2012-06-15 | 811810 |  | 2nd |  | Completed | 2012-07-12
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | San Fermin | 112508013 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 251217 | 333789 | 585006 | 2012-04-23 | 2012-06-15 | 200973.6 |  | 1st |  | Completed | 2012-07-12
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | San Ignacio | 112508014 | Construction of Brgy. Health Station w/ Safe Birthing Facility | 1 | Basic Social Services | Health Station | 140 | sq.m | 1056052 | 428460 | 1484512 | 2012-03-14 | 2012-07-15 | 1056052 |  | 2nd |  | Completed | 2012-06-12
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | San Isidro | 112508015 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 565342 | 169558 | 734900 | 2012-03-19 |  | 282671 |  | 1st |  | On-going | 2012-06-07
H1 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | New Taokanga | 112508016 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 367268 | 151089 | 518357 | 2012-03-26 | 2012-06-15 | 367268 |  | 2nd |  | Completed | 2012-06-24
G2 | XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Zaragosa | 112508017 | Improvement of 1.9 Km. Brgy. Road | 1 | Basic Access Infrastructure | Road | 1.9 | kms | 1234439 | 352193 | 1586632 | 2012-04-12 | 2012-06-15 | 1234439 |  | 2nd |  | Completed | 2012-07-01
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Baon | 112510001 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1064200 | 228529 | 1292729 | 2011-06-10 | 2011-08-15 | 1064200 |  | 2nd | Elem | Completed | 2011-07-30
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Batobato | 112510012 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 978403 | 273517 | 1251920 | 2012-06-26 |  | 587041.8 |  | 1st |  | On-going | 2012-10-14 | 0
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Bitaogan | 112510003 | Construction of Trading Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 112 | sq. m | 899658 | 199035 | 1098693 | 2011-07-12 | 2011-09-15 | 899658 |  | 2nd |  | Completed | 2011-10-10
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Cambaleon | 112510004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 541423 | 121274 | 662697 | 2011-06-01 | 2011-08-29 | 541423 |  | 2nd |  | Completed | 2011-07-31
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Dugmanon | 112510005 | Constrcution of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 984838 | 275247 | 1260085 | 2012-06-19 |  | 0 | No movement as of July 31, 2012 |  |  | On-going | 2012-10-07 | 0
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Iba | 112510006 | Construction of Double Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 12 | ln.m | 459786 | 392324 | 852110 | 2011-07-12 | 2011-08-15 | 459786 |  | 2nd |  | Completed | 2011-10-10
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | La Union | 112510007 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1900833 | 529621 | 2430454 |  |  | 0 |  |  |  | Not yet started |  | 0
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Lapu-Lapu | 112510008 | Upgrading of 240 Ln.m Concreting of Brgy. Road | 1 | Basic Access Infrastructure | Road | 0.24 | kms | 538590 | 114660 | 653250 | 2011-07-12 | 2011-08-15 | 538590 |  | 2nd |  | Completed | 2011-10-10
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Maag | 112510009 | Contruction of Double Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 12 | ln.m | 699519 | 144176 | 843695 | 2011-07-04 | 2011-08-15 | 699519 |  | 2nd |  | Completed | 2011-10-02
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Manikling | 112510010 | Construction of 200 Ln.m Flood Control Facility w/ Dredging | 1 | Environmental Protection and Conservation | River Control/Flood Control | 200 | ln.m | 1244107 | 435834 | 1679941 | 2012-06-22 |  | 746464.2 |  | 1st |  | On-going | 2012-09-30 | 0
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Maputi | 112510011 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 1064200 | 228529 | 1292729 | 2011-05-27 | 2011-08-15 | 1064200 |  | 2nd | Elem | Completed | 2011-07-31
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | San Miguel | 112510013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 541423 | 121274 | 662697 | 2011-05-26 | 2011-08-15 | 541423 |  | 2nd |  | Completed | 2011-07-31
G2 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | San Roque | 112510014 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1172692 | 327300 | 1499992 |  |  | 0 |  |  |  | Not yet started |  | 0
H1 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Sto. Rosario | 112510015 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 919127 | 257210 | 1176337 | 2012-06-21 |  | 551476.2 |  | 1st |  | On-going | 2012-09-19 | 0
H1 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Sudlon | 112510016 | Construction of Double Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 12 | ln.m | 702319 | 142576 | 844895 | 2011-07-04 | 2011-08-15 | 702319 |  | 2nd |  | Completed | 2011-10-02
H1 | XI | 11 | Davao Oriental | 1125 | San Isidro | 112510 | Talisay | 112510017 | Contruction of Double Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 12 | ln.m | 688882 | 141513 | 830395 | 2011-07-16 | 2011-08-15 | 688882 |  | 2nd |  | Completed | 2011-09-13
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Central | 112511002 | Construction of 250 Ln.m Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 250 | ln.m | 482459 | 99038 | 581497 | 2012-03-27 | 2012-06-15 | 482459 |  | 2nd |  | Completed | 2012-06-15
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Dadong | 112511003 | Upgrading of Sagasa-Butayan Road Section | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 389841 | 450055 | 839896 | 2012-03-02 | 2012-06-15 | 311872.8 |  | 1st |  | Completed | 2012-05-21
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Jovellar | 112511004 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 624889 | 117593 | 742482 | 2012-03-01 | 2012-06-15 | 499911.2 |  | 1st |  | Completed | 2012-05-20
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Limot | 112511005 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 621715 | 119227 | 740942 | 2012-03-12 | 2012-06-15 | 621715 |  | 2nd |  | Completed | 2012-05-21
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Lucatan | 112511006 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 625000 | 118653 | 743653 | 2012-03-15 | 2012-06-15 | 500000 |  | 1st |  | Completed | 2012-06-03
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Maganda | 112511007 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 584669 | 113729 | 698398 | 2012-03-27 | 2012-06-15 | 584669 |  | 2nd |  | Completed | 2012-06-15
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Ompao | 112511008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 405414 | 288751 | 694165 | 2012-04-15 | 2012-06-15 | 324331.2 |  | 1st |  | Completed | 2012-07-04
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tomoaong | 112511010 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 621003 | 117825 | 738828 | 2012-03-27 |  | 496802.4 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-06-15
H1 | XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tubaon | 112511011 | Construction of 30 Ln.m Steel Deck Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 30 | ln.m | 645010 | 240372 | 885382 | 2012-04-15 |  | 516008 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-04
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Abaga | 124705001 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 417709.62 | 106475 | 524184.62 | 2012-05-03 |  | 334167.7 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-07-17
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Baguer | 124705003 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 424138.36 | 86614.04 | 510752.4 | 2012-05-29 |  | 339310.69 |  | 1st |  | On-going | 2012-07-13
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Barongis | 124705004 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 900 | ln.m | 769700.8 | 151820 | 921520.8 | 2012-07-17 |  | 615760.64 |  | 1st |  | On-going | 2012-09-16
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Batiocan | 124705005 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 408111.42 | 108945 | 517056.42 | 2012-05-07 |  | 326489.14 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-06-14
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Cabaruyan | 124705006 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 126 | sq. m | 680054.93 | 170045 | 850099.93 | 2012-05-08 |  | 544043.94 |  | 1st | Elem | On-going | 2012-07-07
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Cabpangi | 124705007 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 505052.8 | 109640 | 614692.8 | 2012-07-04 |  | 404042.24 |  | 1st |  | On-going | 2012-09-18
H1 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Demapaco | 124705010 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 300 | sq.m | 270263.2 | 73610 | 343873.2 | 2012-07-28 |  | 216210.56 |  | 1st |  | On-going | 2012-09-12
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Grebona | 124705011 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 649681.95 | 133192 | 782873.95 |  |  | 519745.56 |  | 1st |  | Not yet started
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Gumaga | '124705013 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 3.6 | ln.m | 444550.6 | 102660 | 547210.6 |  |  | 355640.48 |  | 1st |  | Not yet started
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kapayawi | 124705014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 381330.12 | 109395 | 490725.12 | 2012-05-01 |  | 305064.1 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-29
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kiloyao | 124705015 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 300 | sq.m | 265912.2 | 74810 | 340722.2 | 2012-05-14 |  | 212729.76 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-28
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kitubod | 124705017 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 530109.48 | 127323 | 657432.48 | 2012-07-20 |  | 424087.58 |  | 1st |  | On-going
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Malengen | 124705019 | Rehabilitation of Farm To Market Road | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 709929.56 | 151278 | 861207.56 | 2012-07-26 |  | 567943.65 |  | 1st |  | On-going | 2012-09-05
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Montay | 124705023 | Construction of 1 CL School Building (HS) | 1 | Basic Social Services | School | 63 | sq. m | 408427.52 | 108195 | 516622.52 | 2012-05-09 |  | 326742.02 |  | 1st | HS | On-going | 2012-06-23
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Nica-an | 124705024 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 513632.67 | 126130 | 639762.67 | 2012-05-09 |  | 410906.14 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-08
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Palao | 124705025 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 434610.89 | 112900 | 547510.89 | 2012-05-05 |  | 347688.71 | No movement as of July 31, 2012 | 1st | Elem | On-going | 2012-06-19
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Poblacion | 124705029 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 520 | ln.m | 573143.2 | 113530 | 686673.2 | 2012-07-27 |  | 458514.56 |  | 1st |  | On-going | 2012-09-11
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Sinapangan | 124705032 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 494614.12 | 105276 | 599890.12 | 2012-04-28 |  | 395691.3 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-06-11
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Sinawingan | 124705033 | Electrification Expansion | 1 | Basic Social Services | Electrification | 108 | HH | 435132.56 | 88050 | 523182.56 |  |  | 348106.05 | 1,900 Ln.m | 1st |  | Not yet started
G2 | XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Ulamian | 124705034 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 2.9 | kms | 683839.16 | 136098 | 819937.16 | 2012-05-08 |  | 547071.33 | No movement as of July 31, 2012 | 1st |  | On-going | 2012-07-07
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Bagumbayan | 124706005 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 135 | sq. m | 1178661.8 | 283156.2 | 1461818 | 2011-07-18 | 2011-09-15 | 1134865.28 |  | 2nd | Elem | Completed | 2011-09-22
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Balete | 124706049 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 135 | sq. m | 1292191.92 | 179741.08 | 1471933 | 2011-06-20 | 2012-01-15 | 1246965 |  | 2nd | HS | Completed | 2011-09-07
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Basak | 124706008 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 135 | sq. m | 1207621.11 | 257990.89 | 1465612 | 2011-06-20 | 2011-09-15 | 1165172 |  | 2nd | Elem | Completed | 2011-09-07
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Bongolanon | 124706010 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 135 | sq. m | 1249815.41 | 210002.59 | 1459818 | 2011-06-29 | 2011-09-15 | 1205709 |  | 2nd | Elem | Completed | 2011-09-16
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Datu Celo | 124706014 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 617026 | 135213 | 752239 | 2011-06-20 | 2012-01-15 | 600980 |  | 2nd |  | Completed | 2011-09-07
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Del Pilar | 124706015 | Construction of Mini School Library | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | 63 | sq.m | 415483 | 256103 | 671586 | 2011-07-18 | 2011-09-15 | 395450 |  | 2nd |  | Completed | 2011-09-16
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Doles | 124706016 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 135 | sq. m | 1311775 | 223724 | 1535499 | 2011-05-31 | 2011-09-15 | 1275325.61 |  | 2nd | Elem | Completed | 2011-08-19
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Gubatan | 124706021 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 581841.63 | 162397.37 | 744239 | 2011-06-20 | 2011-09-15 | 566548 |  | 2nd |  | Completed | 2011-09-07
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Ilian | 124706022 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 619174.35 | 132064.65 | 751239 | 2011-06-20 | 2011-09-15 | 603051 |  | 2nd |  | Completed | 2011-09-07
G2 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kamada | 124706024 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 135 | sq. m | 1317224.03 | 218132.97 | 1535357 | 2011-06-28 | 2011-08-15 | 1280625 |  | 2nd | Elem | Completed | 2011-09-15
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kinarum | 124706052 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 698505 | 144884 | 843389 | 2011-06-20 | 2011-09-15 | 596636.91 |  | 2nd |  | Completed | 2011-09-02
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kisandal | 124706027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 598080.12 | 141746.88 | 739827 | 2011-06-20 | 2011-09-15 | 598080.12 |  | 2nd |  | Completed | 2011-09-02
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Magcaalam | 124706029 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 621512.47 | 126726.53 | 748239 | 2011-06-20 | 2011-09-15 | 605264 |  | 2nd |  | Completed | 2011-09-07
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Mahongcog | 124706030 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 628258.03 | 127220.97 | 755479 | 2011-06-20 | 2011-09-15 | 611990 |  | 2nd |  | Completed | 2011-09-07
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Pangao-an | 124706039 | Construction of Water System Level II - (Spring Source) | 1 | Basic Social Services | Water System | 1 | system | 1823451 | 231433 | 2054884 | 2011-05-23 | 2011-09-15 | 1458760.8 |  | 1st |  | Completed | 2011-09-23
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Poblacion | 124706040 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 135 | sq. m | 1304896.38 | 230460.62 | 1535357 | 2011-06-27 | 2011-09-15 | 1302569.24 |  | 2nd | Elem | Completed | 2011-09-14
H1 | XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Temporan | 124706044 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 620390.23 | 128986.77 | 749377 | 2011-06-27 | 2011-09-15 | 620390.23 |  | 2nd |  | Completed | 2011-09-09
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Alegria | 124713001 | Construction of Solar Dryer with 1 Unit Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 520 | sq.m | 797018.05 | 124141.97 | 921160.02 | 2011-05-25 | 2011-09-15 | 797018.05 | 450sq.m Solar Dryer 70sq.m Warehouse Building | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Bato-Bato | 124713002 | Construction of Solar Dryer with 1 Unit Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 520 | sq.m | 797018.05 | 124141.97 | 921160.02 | 2011-06-13 | 2011-11-15 | 797018.05 | 450sq.m solar drier 70sq.m warehouse building | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Cabangbangan | 124713031 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4.6 | ln.m | 444904.7 | 72219.02 | 517123.72 | 2011-05-30 | 2011-07-31 | 432638.49 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Camasi | 124713009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 65 | sq.m | 651205.5 | 97998.4 | 749203.9 | 2011-06-30 | 2011-10-15 | 621219.92 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Datu-Indang | 124713032 | Construction of Solar Dryer with 1 Unit Warehouse Building | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 520 | sq.m | 797018.05 | 124141.97 | 921160.02 | 2011-05-18 | 2011-09-15 | 796211.29 | 450sq.m Solar Drier & 70sq.m Warehouse Building | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Datu-Sundongan | 124713033 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 637614.31 | 101213.56 | 738827.87 | 2011-05-20 | 2011-09-15 | 635870.79 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Del Carmen | 124713003 | Construction of 1 Unit CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 648524.15 | 92581.45 | 741105.6 | 2011-06-22 | 2011-10-15 | 643287.45 |  | 2nd | Elem | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Ilustre | 124713007 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 570340.52 | 84561.4 | 654901.92 | 2011-05-22 | 2011-09-15 | 534057.19 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Kamarahan | 124713008 | Construction of Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 24 | ln.m | 706030.61 | 105197.39 | 811228 | 2011-05-23 | 2012-01-15 | 706030.61 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Kimahuring | 124713034 | Construction of Solar Dryer with 1 Unit Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 520 | sq.m | 797018.05 | 124141.97 | 921160.02 | 2011-05-20 | 2011-11-15 | 795531.24 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Kisupaan | 124713011 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 579971.81 | 92228.19 | 672200 | 2011-05-24 | 2011-11-15 | 568209.4 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | La Esperanza | 124713012 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4.6 | ln.m | 414274.9 | 67930.4 | 482205.3 | 2011-05-31 | 2011-08-15 | 403711.2 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Labu-o | 124713013 | Construction of Electrification Extensionm (1.80 km) | 1 | Basic Social Services | Electrification | 118 | HH | 588396.97 | 308041.01 | 896437.98 | 2011-05-13 | 2011-07-31 | 562536.26 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Lamalama | 124713014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 634673.67 | 96103.12 | 730776.79 | 2011-06-30 | 2011-10-15 | 623661.63 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Lomonay | 124713016 | Construction of 1 Unit CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 648524.15 | 92581.45 | 741105.6 | 2011-06-27 | 2011-12-15 | 648239.37 |  | 2nd | Elem | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Mabuhay | 124713035 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 50 | ln.m | 463938.74 | 71428.46 | 535367.2 | 2011-06-01 | 2011-08-15 | 443614.6 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | New Cebu | 124713022 | Construction of 1 Unit CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 648524.15 | 92581.45 | 741105.6 | 2011-06-27 | 2011-12-15 | 643954.7 |  | 2nd | Elem | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Sagcungan | 124713026 | Construction of 1 Unit Learning Center (Training Center) | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 63 | sq.m | 648524.15 | 92581.45 | 741105.6 | 2011-06-21 | 2011-12-15 | 640542.58 | Note: from SB to MPB | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Sarayan | 124713028 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 633912.41 | 92372.75 | 726285.16 | 2011-05-22 | 2011-11-15 | 620738.46 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | North Cotabato | 1247 | Pres. Roxas | 124713 | Tuael | 124713029 | Construction of Overflow Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 10.6 | ln.m | 392567.06 | 55159.99 | 447727.05 | 2011-08-04 | 2011-09-15 | 392567.06 |  | 2nd |  | Completed | 2011-09-15
H1 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Badtasan | 128003001 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 214.8 | sq. m | 1348875.94 | 316368.56 | 1665244.5 | 2011-07-07 | 2011-12-15 | 1213988.34 |  | 2nd | Elem | Completed | 2011-09-29
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Gasi | 128003003 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | 143.2 | sq. m | 983144.75 | 240163.25 | 1223308 | 2011-07-06 | 2012-01-15 | 884830.28 |  | 2nd | Elem | Completed | 2011-09-17
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Kapate | 128003004 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1222921.97 | 272398.05 | 1495320.02 | 2012-07-16 |  | 978337.58 |  | 1st |  | On-going | 2012-10-07
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Kayupo | 128003006 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1346325.07 | 298128.65 | 1644453.72 | 2012-07-20 |  | 1077060.06 |  | 1st |  | On-going | 2012-10-11
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Kling (Lumit) | 128003007 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 214.8 | sq. m | 1338298.13 | 314257.37 | 1652555.5 | 2011-07-14 | 2012-03-15 | 1259468.32 |  | 3rd | Elem | Completed | 2011-10-08
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Lagundi | 128003008 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 242.1 | sq. m | 1428698.88 | 317656.82 | 1746355.7 | 2012-07-18 |  | 1142959.1 |  | 1st | Elem | On-going | 2012-10-09
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Lebe | 128003009 | Construction of 300 Ln.m Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 309556.97 | 312127.36 | 621684.33 | 2012-07-23 |  | 247645.58 |  | 1st |  | On-going | 2012-09-09
H1 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Lomuyon | 128003010 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 214.8 | sq. m | 1353062.38 | 317204.12 | 1670266.5 | 2011-07-20 | 2011-12-15 | 1307179.8 |  | 3rd | Elem | Completed | 2011-10-14
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Luma | 128003011 | Construction of Flood Control Along Pangi River | 1 | Environmental Protection and Conservation | River Control/Flood Control | 180 | ln.m | 2558357 | 607185.68 | 3165542.68 | 2011-08-01 | 2012-01-15 | 2302521.3 |  | 2nd |  | Completed | 2011-10-26
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Maligang | 128003012 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1220148.64 | 271000.91 | 1491149.55 | 2012-07-16 |  | 976118.91 |  | 1st |  | On-going | 2012-10-07
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Salakit | 128003015 | Construction of 1 Unit 3 CL School Building (Elem) | 1 | Basic Social Services | School | 214.8 | sq. m | 968261.8 | 716290.7 | 1684552.5 | 2011-07-26 | 2012-03-15 | 871435.62 |  | 2nd | Elem | Completed | 2011-10-20
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Tablao | 128003017 | Construction of 12 Ln.m Triple Barrel RCBC with Access Road on both Approaches | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 12 | ln.m | 1200404.25 | 284924.44 | 1485328.69 | 2012-07-30 |  | 960323.4 |  | 1st |  | On-going | 2012-10-10
G2 | XII | 12 | Sarangani | 1280 | Kiamba | 128003 | Tambilil | 128003019 | Construction of 1 Unit 4 CL School Building (HS) | 1 | Basic Social Services | School | 322.8 | sq. m | 1821944.22 | 404532.61 | 2226476.83 | 2012-07-12 |  | 1457555.37 |  | 1st | HS | On-going | 2012-10-03
G2 | XII | 12 | Sarangani | 1280 | Maasim | 128004 | Daliao | 128004004 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 143.2 | sq. m | 1097087.56 | 253317.44 | 1350405 | 2012-07-05 |  | 548567.5 |  | 1st | Elem | On-going | 2012-09-15
G2 | XII | 12 | Sarangani | 1280 | Maasim | 128004 | Kabatiol | 128004005 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 214.8 | sq. m | 1525616.79 | 342143.21 | 1867760 | 2012-07-04 |  | 762816.5 |  | 1st | Elem | On-going | 2012-09-29
G2 | XII | 12 | Sarangani | 1280 | Maasim | 128004 | Kablacan | 128004006 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 214.8 | sq. m | 1510363.45 | 339181.55 | 1849545 | 2012-06-29 |  | 755184 |  | 1st | Elem | On-going | 2012-09-24
G2 | XII | 12 | Sarangani | 1280 | Maasim | 128004 | Nomoh | 128004012 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 143.2 | sq. m | 1147917.56 | 263397.44 | 1411315 | 2012-07-18 |  | 573955 |  | 1st | Elem | On-going | 2012-09-30
H1 | XII | 12 | Sarangani | 1280 | Maasim | 128004 | Pananag | 128004013 | Construction of Community Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 143.2 | sq.m | 633609.79 | 195276.96 | 828886.75 | 2012-07-01 |  | 316785 |  | 1st |  | On-going | 2012-09-08
H1 | XII | 12 | Sarangani | 1280 | Maasim | 128004 | Seven Hills | 128004015 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 143.2 | sq. m | 1071787.55 | 247567.45 | 1319355 | 2012-06-14 |  | 535902.5 |  | 1st | Elem | On-going | 2012-09-15
H1 | XII | 12 | Sarangani | 1280 | Maitum | 128005 | Maguling | 128005007 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1473306 | 356694 | 1830000 | 2012-07-02 |  | 883983.6 |  | 1st | Elem | On-going | 2012-11-18
H1 | XII | 12 | Sarangani | 1280 | Maitum | 128005 | New La Union | 128005010 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1469142.22 | 360857.78 | 1830000 | 2012-06-25 |  | 954942.44 |  | 1st | Elem | On-going | 2012-11-11
H1 | XII | 12 | Sarangani | 1280 | Maitum | 128005 | Pangi (Linao) | 128005012 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1464978.64 | 355021.36 | 1820000 | 2012-07-02 |  | 952236.12 |  | 1st | Elem | On-going | 2012-11-18
H1 | XII | 12 | Sarangani | 1280 | Maitum | 128005 | Ticulab | 128005015 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1473306 | 356694 | 1830000 | 2012-06-20 |  | 883983.6 |  | 1st | Elem | On-going | 2012-11-06
H1 | XII | 12 | Sarangani | 1280 | Maitum | 128005 | Tuanadatu | 128005016 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1352113 | 345512 | 1697625 | 2012-07-08 |  | 811267.8 |  | 1st | Elem | On-going | 2012-11-22
H1 | XII | 12 | Sarangani | 1280 | Maitum | 128005 | Wali (Kambuhan) | 128005018 | Construction of 3 CL School Building (Elem) | 1 | Basic Social Services | School | 189 | sq. m | 1317154.13 | 507845.87 | 1825000 | 2012-06-22 |  | 856150.19 |  | 1st | Elem | On-going | 2012-11-08
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Alkikan | 128007001 | Construction of WS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 569600.47 | 158702.78 | 728303.25 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Banahaw | 128007004 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 484322.14 | 175395.96 | 659718.1 |  |  | 0 |  |  | Elem | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Banate | 128007005 | Construction of WS Level II (Submerscible Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 480425.47 | 176501.44 | 656926.91 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Datal Batong | 128007007 | Construction of WS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 473494.9 | 156217.32 | 629712.22 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Datal Bila | 128007008 | Construction of WS Level II Spring Dev't (Ramp Pump) | 1 | Basic Social Services | Water System | 1 | system | 457177.63 | 130697.4 | 587875.03 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Datal Tampal | 128007009 | Construction of WS Level II (Spring Dev't) | 1 | Basic Social Services | Water System | 1 | system | 444827.09 | 135679.63 | 580506.72 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | JP Laurel | 128007010 | Expansion of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 452783.64 | 146209.99 | 598993.63 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Kawayan | 128007011 | Construction of WS Level II (Submercible Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 581235.9 | 133157.05 | 714392.95 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Kibala | 128007012 | Construction of 1 Unit 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 521001.78 | 148859.32 | 669861.1 |  |  | 0 |  |  | Elem | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Kiblat | 128007013 | Construction of Water System Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 437899.34 | 109283.07 | 547182.41 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Kinabalan | 128007014 | Construction of WS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 488268.08 | 181858.79 | 670126.87 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Lower Mainit | 128007015 | Construction of Brgy. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.33 | kms | 848878.73 | 1077017.07 | 1925895.8 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Lutay | 128007016 | Construction of FMR Road Opening | 1 | Basic Access Infrastructure | Road | 3.3 | kms | 586063.98 | 944777.08 | 1530841.06 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Malabod | 128007017 | Construction of WS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 586757.65 | 167870.44 | 754628.09 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Malalag Cogon | 128007018 | Construction of WS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 424765.22 | 140304.2 | 565069.42 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Malandag | 128007019 | Construction of WS Level II (Submerscible Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 657200.45 | 139816.52 | 797016.97 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Malungon Gamay | 128007020 | Construction of 2 Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 4.7 | ln.m | 698056.65 | 146111.3 | 844167.95 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Nagpan | 128007021 | Construction of WS Level II (Submerscible Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 718911.69 | 212171.3 | 931082.99 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Poblacion | 128007023 | Construction of Bangkal-Napla Road Upgrading (Gravelling) | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 364784.87 | 791731.83 | 1156516.7 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | San Juan | 128007024 | Construction of Maygatong Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 40 | ln.m | 1257912.33 | 166292.42 | 1424204.75 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | San Miguel | 128007025 | Construction of WS Level II (Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 476389.02 | 156256.12 | 632645.14 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | San Roque | 128007026 | Conctruction of Lower Lagas Road Upgrading (Graveling) | 1 | Basic Access Infrastructure | Road | 2.5 | kms | 535333.54 | 746361.26 | 1281694.8 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Talus | 128007027 | Construction of WS Level II (Submerscible Pump Driven) | 1 | Basic Social Services | Water System | 1 | system | 536487.77 | 135066.8 | 671554.57 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Tamban | 128007028 | Road Upgrading Malinis to Nihan | 1 | Basic Access Infrastructure | Road | 1.4 | kms | 639841.88 | 431259.43 | 1071101.31 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Upper Biangan | 128007029 | Construction of WS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 589574.55 | 163433.27 | 753007.82 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Upper Lumabat | 128007030 | Construction of Brgy. Road Concreting | 1 | Basic Access Infrastructure | Road | 0.205 | kms | 633837.3 | 431972 | 1065809.3 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | Sarangani | 1280 | Malungon | 128007 | Upper Mainit | 128007031 | Construction of Sto Nino-Taclobo Road Upgrading (Gravelling) | 1 | Basic Access Infrastructure | Road | 2 | kms | 554115.26 | 482780.38 | 1036895.64 |  |  | 0 |  |  |  | Not yet started
G2 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Bacdulong | 126319001 | Brgy. Electrification Extension (700 ln.m) | 1 | Basic Social Services | Electrification | 112 | HH | 517543.31 | 21075 | 538618.31 | 2011-06-20 | 2011-09-15 | 517543.31 |  | 2nd |  | Completed | 2011-07-31
G2 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Denlag | 126319002 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 56 | sq. m | 593002 | 107646 | 700648 | 2011-06-15 | 2011-10-15 | 593002 |  | 2nd | Elem | Completed | 2011-07-31
G2 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Halilan | 126319003 | Construction of Solar Dryer (600 sq.m) with Mini Warehouse (73.5 sq.m) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 560288.87 | 163325 | 723613.87 | 2011-06-02 | 2011-10-15 | 560288.96 |  | 2nd |  | Completed | 2011-07-31
G2 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Hanoon | 126319004 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 650369.3 | 41911.7 | 692281 | 2011-06-10 | 2011-10-15 | 650369.3 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Klubi | 126319005 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 56 | sq. m | 579667 | 82842 | 662509 | 2011-06-08 | 2011-10-15 | 579667 |  | 2nd | Elem | Completed | 2011-07-31
G2 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lake Lahit | 126319006 | Brgy. Electrification (605 ln.m) | 1 | Basic Social Services | Electrification | 115 | HH | 450171.74 | 15944 | 466115.74 | 2011-06-20 | 2011-09-15 | 450171.74 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Siluton | 126319015 | Construction of Single Barrel Box Culvert with Embankment and Gravelling | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 36 | ln.m | 479685 | 105637 | 585322 | 2011-06-02 | 2011-09-15 | 479685 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamcade | 126319007 | Brgy. Electrification Extension (1,350 ln.m) | 1 | Basic Social Services | Electrification | 379 | HH | 780242.32 | 16636 | 796878.32 | 2011-06-20 | 2011-09-15 | 780242.32 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamfugon | 126319009 | Construction of Single Barrel Box Culvert with Embankment and Gravelling | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 46 | ln.m | 506985 | 122773 | 629758 | 2011-06-02 | 2011-09-15 | 506985 |  | 2nd |  | Completed | 2011-07-01
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamlahak | 126319010 | Brgy. Electrification Extension (1,045 ln.m) | 1 | Basic Social Services | Electrification | 68 | HH | 588896.08 | 16235 | 605131.08 | 2011-06-20 | 2011-09-15 | 588896.08 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lower Maculan | 126319011 | Conctruction of Livelihood and Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 73.5 | sq. m | 566782 | 77148 | 643930 | 2011-05-31 | 2011-09-15 | 566782 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Luhib | 126319012 | Brgy. Electrification (853 ln.m) | 1 | Basic Social Services | Electrification | 60 | HH | 609225.39 | 16150 | 625375.39 | 2011-06-20 | 2011-09-15 | 609225.39 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Ned | 126319013 | Construction of Solar Dryer (600 sq.m) with Mini Warehouse (73.5 sq.m) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 566420 | 158632 | 725052 | 2011-05-13 | 2011-11-15 | 566420 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Talisay | 126319016 | Construction of 1 CL School Building (Elem) | 1 | Basic Social Services | School | 63 | sq. m | 556692 | 107571 | 664263 | 2011-05-26 | 2011-10-15 | 541692 |  | 2nd | Elem | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Tasiman | 126319019 | Construction of Solar Dryer with Corn Sheller and Engine | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 422110 | 144687 | 566797 | 2011-05-29 | 2011-09-15 | 422110 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Takunel | 126319017 | Construction of Solar Dryer with Corn Sheller and Engine | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 417110 | 144476 | 561586 | 2011-05-29 | 2011-09-15 | 417110 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Upper Maculan | 126319018 | Construction of Solar Dryer (600 sq.m) with Mini Warehouse (73.5 sq.m) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 654810 | 149393 | 804203 | 2011-05-30 | 2011-09-15 | 654810 |  | 2nd |  | Completed | 2011-07-31
H1 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Aflek | 126316024 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 106.56 | sq. m | 1048756.64 | 90000 | 1138756.64 | 2011-07-25 | 2012-04-15 | 1003004.24 |  | 2nd | HS | Completed | 2011-10-25
H1 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Afus | 126316017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.69 | sq.m | 686334.14 | 49816.35 | 736150.49 | 2011-06-14 | 2011-09-15 | 644187.68 |  | 2nd |  | Completed | 2011-08-29
H1 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Basag | 126316001 | Construction of 2 CL School Building (HS) | 1 | Basic Social Services | School | 106.56 | sq. m | 965756.64 | 173000 | 1138756.64 | 2011-07-25 | 2012-05-15 | 920004.24 |  | 3rd | HS | Completed | 2011-10-25
H1 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Dlanag | 126316027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.69 | sq.m | 403164.25 | 325986.24 | 729150.49 |  |  | 0 |  |  |  | Not yet started
H1 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Edwards | 126316002 | Construction of Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 80.28 | sq. m | 648671.39 | 120159.85 | 768831.24 | 2011-06-14 | 2011-09-15 | 615966.24 |  | 2nd |  | Completed | 2011-08-14
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Kematu | 126316004 | Construction of Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 80.28 | sq. m | 708671.36 | 60659.85 | 769331.21 | 2011-06-14 | 2012-04-15 | 675966.21 |  | 2nd |  | Completed | 2011-08-14
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Lamhako | 126316019 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 106.56 | sq. m | 1058756.64 | 80000 | 1138756.64 | 2011-06-14 | 2012-03-15 | 980906.72 |  | 3rd | Elem | Completed | 2011-09-14
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Lambangan | 126316014 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 106.56 | sq. m | 1028756.64 | 110000 | 1138756.64 | 2011-07-25 | 2012-05-15 | 978584.43 |  | 3rd | Elem | Completed | 2011-10-25
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Lambuling | 126316018 | Construction of Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 80.28 | sq. m | 746241.54 | 41623.09 | 787864.63 | 2011-06-20 | 2012-03-15 | 713536.39 |  | 2nd |  | Completed | 2011-08-20
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Lemsnolon | 126316028 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.69 | sq.m | 537334.14 | 186917.48 | 724251.62 | 2011-06-18 | 2012-03-15 | 519413.4 | Adjusted TPC from 754,334.14 - 724,150.49 (Less Contingency) | 2nd |  | Completed | 2011-09-03
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Malugong | 126316029 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.69 | sq.m | 689334.14 | 39816.35 | 729150.49 | 2011-07-25 | 2011-09-15 | 659150.49 |  | 2nd |  | Completed | 2011-10-08
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Mongocayo | 126316030 | Construction of 2 CL School Building (Elem) | 1 | Basic Social Services | School | 106.56 | sq. m | 953756.64 | 185000 | 1138756.64 | 2011-07-25 | 2012-04-15 | 908004.24 |  | 3rd | Elem | Completed | 2011-10-25
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Salacafe | 126316031 | Construction of Water System Level - II (Spring Source) | 1 | Basic Social Services | Water System | 1 | system | 512700 | 80000 | 592700 | 2011-08-29 | 2012-05-15 | 497099 |  | 3rd |  | Completed | 2011-10-15
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Sinolon | 126316012 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 562625 | 39375 | 602000 | 2011-08-29 | 2011-11-15 | 524000 |  | 2nd |  | Completed | 2011-10-15
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Talcon | 126316021 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 734250 | 80000 | 814250 | 2011-08-29 | 2012-03-15 | 721589.04 |  | 3rd |  | Completed | 2011-10-15
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Talufo | 126316022 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 51.69 | sq.m | 674334.14 | 54816.35 | 729150.49 | 2011-07-18 | 2012-07-15 | 644150.29 | (No movement as of May 31, 2012 reports) Adjusted TPC from 754,334.14 - 724,150.49 (Less Contingency) | 3rd |  | Completed | 2011-09-02
G2 | XII | 12 | South Cotabato | 1263 | TBoli | 126316 | Tudok | 126316023 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51.69 | sq.m | 540396.33 | 70000 | 610396.33 | 2011-07-14 | 2011-09-15 | 540396.32 |  | 2nd |  | Completed | 2011-09-02
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Datalblao | 126502009 | Construction of 1 Unit 20x40m Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 800 | sq.m | 437565.68 | 81643.64 | 519209.32 | 2012-07-10 |  | 350052.54 |  | 1st |  | On-going | 2012-09-10
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Eday | 126502010 | Construction of PWS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 710928 | 67908.12 | 778836.12 | 2012-07-02 |  | 538722.8 |  | 1st |  | On-going | 2012-09-10
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Elbebe | 126502011 | Construction of 1 Unit 20x30m Solar Dryer with Corn Sheller | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 483513.16 | 111272.88 | 594786.04 | 2012-06-26 |  | 386810.52 |  | 1st |  | On-going | 2012-08-10
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Lasak | 126502032 | Construction of 0.62 Km. FMR | 1 | Basic Access Infrastructure | Road | 0.62 | kms | 236653.41 | 716430.47 | 953083.88 | 2012-06-06 |  | 181172.83 |  | 1st |  | On-going | 2012-07-23
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Libertad | 126502015 | Construction of PWS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 989822.88 | 266837.4 | 1256660.28 | 2012-06-11 |  | 830027.8 |  | 1st |  | On-going | 2012-08-20
H1 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Lomoyon | 126502016 | Construction of 1 Unit 20x30m Solar Dyer with Corn Sheller | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 413621.38 | 201005.86 | 614627.24 | 2012-06-25 |  | 330897.1 |  | 1st |  | On-going | 2012-08-09
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Makat | 126502017 | Construction of 1 Unit 20x20m Solar Dryer with Machine Facilities | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 400 | sq.m | 464390.68 | 65638.34 | 530029.02 | 2012-06-20 | 2012-07-24 | 371512.55 |  | 1st |  | Completed | 2012-07-24
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Maligaya | 126502019 | Construction of 1 Unit 7x10.5m Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 73.5 | sq.m | 538939 | 54302 | 593241 | 2012-07-09 |  | 431151.2 |  | 1st |  | On-going | 2012-10-23
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Mayo | 126502021 | Construction of 20x20m Solar Dryer with Mini-Rice Mill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 400 | sq.m | 409613.28 | 90694.64 | 500307.92 | 2012-07-11 |  | 327690.62 |  | 1st |  | On-going | 2012-09-11
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Natividad | 126502022 | Construction of 1 Unit 8.1x9.65m School Building (Elem) | 1 | Basic Social Services | School | 78.165 | sq. m | 576163.59 | 65351.05 | 641514.64 | 2012-06-06 |  | 460930.87 |  | 1st | Elem | On-going | 2012-08-14
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Bantangan (Lasak) | 126502002 | Construction 1 Unit 20x40m Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 800 | sq.m | 441378.68 | 64484.84 | 505863.52 | 2012-06-27 | 2012-07-15 | 353102.94 |  | 1st |  | Completed | 2012-08-13
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Poblacion | 126502023 | Construction of 20x30m Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 400836.96 | 95515.81 | 496352.77 | 2012-07-06 |  | 320669.57 |  | 1st |  | On-going | 2012-08-21
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Polomolok | 126502024 | Construction of 1 Unit 20x30m Solar Dryer with Corn Sheller | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 600 | sq.m | 393333.25 | 184940.95 | 578274.2 | 2012-06-26 |  | 314666.6 |  | 1st |  | On-going | 2012-08-10
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Sinapulan | 126502027 | Improvement of PWS Level II (Spring Development) | 1 | Basic Social Services | Water System | 1 | system | 341203.68 | 62295.7 | 403499.38 | 2012-07-06 |  | 272962.94 |  | 1st |  | On-going | 2012-09-22
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Sucob | 126502028 | Cosntruction of 1 Unit 20x20m Solar Dryer with 7x10.5 Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 473.5 | sq.m | 708593.69 | 123248.34 | 831842.03 | 2012-07-02 |  | 566874.95 |  | 1st |  | On-going | 2012-09-15
G2 | XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Telafas | 126502030 | Construction of 1 Unit 20x40m Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 800 | sq.m | 453442.68 | 59436.84 | 512879.52 | 2012-07-31 |  | 362754.14 |  | 1st |  | On-going | 2012-09-30
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Basag | 126512002 | Construction of Water System L-II | 1 | Basic Social Services | Water System | 1 | system | 612132 | 181408 | 793540 | 2011-07-06 | 2011-11-15 | 611807.3 |  | 2nd |  | Completed | 2011-09-14
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Buenaflores | 126512003 | Construction of Brgy. Health Station with Basic Amenities | 1 | Basic Social Services | Health Station | 51 | sq.m | 590680 | 165852.92 | 756532.92 | 2011-06-27 | 2011-09-30 | 590151.36 |  | 2nd |  | Completed | 2011-08-10
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Bugso | 126512004 | Construction of Water System L-II | 1 | Basic Social Services | Water System | 1 | system | 1048409 | 299021 | 1347430 | 2011-07-13 | 2011-09-30 | 1039892.1 |  | 2nd |  | Completed | 2011-10-19
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Buklod | 126512005 | Construction of Brgy. Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 629027 | 195311 | 824338 | 2012-07-04 |  | 311485.06 |  | 1st |  | On-going | 2012-08-18 | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Gapok | 126512006 | Construction of Water System L-II | 1 | Basic Social Services | Water System | 1 | system | 1191348 | 327410.95 | 1518758.95 | 2011-07-13 | 2011-12-15 | 1188437.55 |  | 2nd |  | Completed | 2011-10-19
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Kadi | 126512007 | Construction of 2 CL School Building with Amenities (Elem) | 1 | Basic Social Services | School | 160 | sq. m | 1061214 | 292442 | 1353656 | 2011-06-24 | 2011-09-15 | 1061214 |  | 2nd | Elem | Completed | 2011-09-15
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Kapatagan | 126512008 | Rural Electrification | 1 | Basic Social Services | Electrification | 205 | HH | 1265547 | 395222 | 1660769 | 2011-09-01 | 2011-09-30 | 1263663.36 | 2.5 km. | 2nd |  | Completed | 2011-10-30
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Kapatagan | 126512008 | Provision of Corn Sheller w/ Shed House (1 Unit) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 21 | sq.m | 218090 | 136982.32 | 355072.32 | 2012-07-23 |  | 0 |  |  |  | On-going | 2012-09-06 | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Kiadsam | 126512009 | Construction of 12 Ln.m Slab Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 12 | ln.m | 1693821 | 440020.7 | 2133841.7 | 2011-08-25 | 2012-06-15 | 1683003.78 |  | 2nd |  | Completed | 2011-11-30
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Kuden | 126512010 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1257741 | 365614.84 | 1623355.84 |  |  | 1005997.5 |  | 1st |  | Not yet started |  | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Lagubang | 126512012 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1163680 | 285747 | 1449427 |  |  | 931990.64 |  | 1st |  | Not yet started |  | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Langgal | 126512013 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 949240 | 319950 | 1269190 | 2012-07-17 |  | 758940 |  | 1st |  | On-going | 2012-09-19 | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Limuhay | 126512014 | Construction of Day Care Center with Amenities | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 566096 | 184285.67 | 750381.67 | 2011-06-24 | 2012-02-15 | 565848.33 |  | 2nd |  | Completed | 2011-09-08
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Malegdeg | 126512015 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1099912 | 323244 | 1423156 | 2012-06-22 |  | 549794 |  | 1st | Elem | On-going | 2012-09-15 | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Midtungok | 126512016 | Construction of 1 Unit Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 43.2 | ln.m | 947858 | 246652 | 1194510 |  |  | 758250 |  | 1st |  | Not yet started |  | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Nati | 126512017 | Construction of Solar Drier w/ Warehouse (300 sq.m/70 sq.m) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 300 | sq.m | 695828 | 241472 | 937300 | 2012-07-23 |  | 0 |  |  |  | On-going | 2012-10-10 | 0
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Sewod | 126512018 | Construction of Solar Drier with Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 370 | sq.m | 699091 | 225589 | 924680 | 2011-06-17 | 2011-12-15 | 691260 |  | 2nd |  | Completed | 2011-09-04
G2 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Tacupis | 126512019 | Constrcution of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 680918 | 190867 | 871785 |  |  | 544540 |  | 1st |  | Not yet started |  | 0
H1 | XII | 12 | Sultan Kudarat | 1265 | Sen. Ninoy Aquino | 126512 | Tinalon | 126512020 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1357703 | 328502 | 1686205 |  |  | 1085990 |  | 1st |  | Not yet started |  | 0
Note on F96: Stata_User01 Province -Dinagat Island 168500000
Note on G96: Stata_User01: Loreto Code - 168505000
Note on H99: Stata_User01: Municipality- CITY OF BAYUGAN
Note on F138: Stata_User01: Province - Dinagat Island
Note on F195: Stata_User01: Province - Agusan del sur
Note on H1405: Saeapph005: Davao del sur -sta maria-pongpong 112413010

## KC1
Region |  | Province |  | Municipality |  | Barangay |  | Project Name | 6583 | Committed |  |  | Downloaded |  |  | Utilized |  |  | Percentages |  |  |  |  | Dates |  |  |  |  | Duration of SP Construction (Calendar Days) | No. of Direct HH Beneficiaries | Remarks | 5470 | Cluster
Region |  | Province |  | Municipality |  | Barangay |  | Project Name | # of Brgys. | Estimated Total Cost (P) 2nd MIBF | KALAHI GRANT | Community & LGU Counterpart Commitments (LCC) | Grant Funds Released | Tranches | LCC Delivered | Total Utilized | Grant Funds Utilized | LCC Utilized | % Utilized from Grant released* | % LCC utilized over delivered | % LCC delivered over committed | % Financial Accomplishment (Grant + LCC) | % Physical Progress as of June 2010 | 1st MIBF / MIBF-PDPRA Date | 2nd MIBF / MIBF-EC Date | Start Date (SPI) | Completion Date | Inauguration Date | Duration of SP Construction (Calendar Days) | No. of Direct HH Beneficiaries | Remarks | # of SPs | Cluster
CAR | 14 | Abra | 1401 | Danglas | 140106 | Cabaruan | 140106003 | Const. of Water System | 1 | 1629560 | 1077232.63 | 552327.37 | 1033129.48 |  | 240108.56 | 1273238.04 | 1033129.48 | 240108.56 | 100% | 100% | 43.47% | 78.13% | 100% | 2008-04-08 | n/a | 2009-01-26 | 2009-12-05 | n/a | 313 | 106 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Danglas | 140106 | Caupasan | 140106004 | Concreting of Caupasan Proper to Sitio Payong FMR | 1 | 592300 | 336079.88 | 256220.12 | 302582.99 |  | 201348.13 | 503931.12 | 302582.99 | 201348.13 | 100% | 100% | 78.58% | 85.08% | 100% | 2009-03-17 | no data | 2009-05-18 | 2009-12-05 | n/a | 201 | 231 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Danglas | 140106 | Danglas - C2 | 140106005 | Const. of Water System | 2 | 1231665 | 857396.34 | 374268.66 | 804634.08 |  | 274418.42 | 1079052.5 | 804634.08 | 274418.42 | 100% | 100% | 73.32% | 87.61% | 100% | 2008-04-08 | n/a | 2008-10-22 | 2009-03-04 | no data | 133 | 169 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Danglas | 140106 | Abaquid - C2 | 140106001 | Const. of Water System | 2 | 1231665 | 857396.34 | 374268.66 | 804634.08 |  | 274418.42 | 1079052.5 | 804634.08 | 274418.42 | 100% | 100% | 73.32% | 87.61% | 100% | 2008-04-08 | n/a | 2008-10-22 | 2009-03-04 | no data | 133 | 169 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Danglas | 140106 | Nagaparan | 140106006 | Const. of Water System | 1 | 331840 | 218133.29 | 113706.71 | 218133.29 |  | 126022.97 | 344156.26 | 218133.29 | 126022.97 | 100% | 100% | 110.8% | 103.7% | 100% | 2008-04-08 | n/a | 2008-08-06 | 2008-11-30 | no data | 116 | 160 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Danglas | 140106 | Padangitan | 140106007 | Construction of Sitio Dalaguisen, Padangitan Flood Control | 1 | 1666200 | 932543 | 733657 | 839288.7 |  | 567750.87 | 1407039.57 | 839288.7 | 567750.87 | 100% | 100% | 77.39% | 84.45% | 100% | 2009-03-17 | no data | 2009-06-11 | 2009-12-05 | n/a | 177 | 65 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Danglas | 140106 | Pangal | 140106008 | Construction of Pangal Footbridge | 1 | 1217900 | 831377.12 | 386522.88 | 749329.84 |  | 304565.97 | 1053895.81 | 749329.84 | 304565.97 | 100% | 100% | 78.8% | 86.53% | 100% | 2009-03-17 | no data | 2009-05-16 | completed as built | n/a | #VALUE! | 161 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Lacub | 140109 | Bacag | 140109001 | Construction of Water System | 1 | 954862.5 | 757134 | 197728.5 | 705029 |  | 210728.5 | 915757.5 | 705029 | 210728.5 | 100% | 100% | 106.6% | 95.9% | 100% | 2008-09-01 | no data | 2009-01-21 | 2009-02-25 | no data | 35 | 48 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Lacub | 140109 | Buneg | 140109002 | Improvement of Buneg Water Supply System-Level II | 1 | 1096000 | 773892 | 322108 | 619113.6 |  | 323108 | 942221.6 | 619113.6 | 323108 | 100% | 100% | 100.3% | 85.97% | 100% | 2009-03-13 | no data | 2009-06-21 | 2009-07-30 | n/a | 39 | 66 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Lacub | 140109 | Guinguinabang | 140109003 | Construction of Concrete Footbridge | 1 | 960405 | 702243 | 258162 | 632018.92 |  | 268160.89 | 900179.81 | 632018.92 | 268160.89 | 100% | 100% | 103.9% | 93.73% | 100% | 2008-09-01 | no data | 2009-01-23 | 2009-04-29 | n/a | 96 | 55 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Lacub | 140109 | Lan-ag | 140109004 | Construction of Water System | 1 | 381459 | 221985 | 159474 | 207009.16 |  | 160473.8 | 367482.96 | 207009.16 | 160473.8 | 100% | 100% | 100.6% | 96.34% | 100% | 2008-09-01 | no data | 2009-01-22 | 2009-02-13 | no data | 22 | 13 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Lacub | 140109 | Pacoc | 140109005 | Cable Footbridge | 1 | 1482616 | 1091104 | 391512 | 1091104 |  | 390705.5 | 1481809.5 | 1091104 | 390705.5 | 100% | 100% | 99.79% | 99.95% | 100% | 2007-07-08 | n/a | 2007-12-19 | 2009-04-30 | n/a | 498 | 99 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Lacub | 140109 | Poblacion (Talampac) | 140109006 | Improvement of Water Supply System | 1 | 1010240 | 708896 | 301344 | 708896 |  | 292894 | 1001790 | 708896 | 292894 | 100% | 100% | 97.2% | 99.16% | 100% | 2007-07-08 | n/a | 2007-09-25 | 2008-03-31 | no data | 188 | 154 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Dalimag | 140121002 | Const. of Concrete Footbridge with footpath | 1 | 640000 | 587970 | 52030 | 529173 |  | 51330 | 580503 | 529173 | 51330 | 100% | 100% | 98.65% | 90.7% | 100% | 2007-04-30 | n/a | 2007-11-19 | 2008-02-28 | no data | 101 | 131 | Excess funds | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Cabayogan- C2 | 140121001 | Construction of 1 Unit (3 classroom) Elementary School Building | 2 | 1495000 | 1150000 | 345000 | 1035000 |  | 224203.19 | 1259203.19 | 1035000 | 224203.19 | 100% | 100% | 64.99% | 84.23% | 100% | 2008-09-10 | no data | 2008-12-12 | 2009-06-30 | no data | 200 | 200 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Dalimag - C2 | 140121002 | Construction of 1 Unit (3 classroom) Elementary School Building | 2 | 1495000 | 1150000 | 345000 | 1035000 |  | 224203.19 | 1259203.19 | 1035000 | 224203.19 | 100% | 100% | 64.99% | 84.23% | 100% | 2008-09-10 | no data | 2008-12-12 | 2009-06-30 | no data | 200 | 200 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Langbaban - C3 | 140121003 | Impr. of Water System - C3 | 3 | 1800000 | 1295193 | 504807 | 1141246.91 |  | 598217 | 1739463.91 | 1141246.91 | 598217 | 100% | 100% | 118.5% | 96.64% | 100% | 2007-04-30 | n/a | 2007-11-19 | 2008-09-15 | no data | 301 | 264 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Manayday | 140121004 | Improvement of Manayday-Linasin Farm to Market Road | 1 | 1400000 | 1076923 | 323077 | 969230.7 |  | 212872.68 | 1182103.38 | 969230.7 | 212872.68 | 100% | 100% | 65.89% | 84.44% | 100% | 2008-09-10 | no data | 2009-02-16 | 2009-06-10 | no data | 114 | 131 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Olo | 140121010 | Improvement of Sabtan Baba-Sabtan Olo FMR | 1 | 1180000 | 816837 | 363163 | 816837 |  | 369717 | 1067420.57 | 816837 | 250583.57 | 100% | 67.78% | 101.8% | 90.46% | 100% | 2007-04-30 | n/a | 2007-12-10 | 2008-09-10 | no data | 275 | 77 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Olo | 140121010 | Construction of Multi-Purpose Pavement with Storage Area | 1 | 550000 | 423077 | 126923 | 380769.3 |  | 98056.27 | 478825.57 | 380769.3 | 98056.27 | 100% | 100% | 77.26% | 87.06% | 100% | 2008-09-10 | no data | 2009-02-16 | 2009-05-12 | no data | 85 | 75 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Isidro | 140121 | Poblacion | 140121008 | Upgrading/Enhancement of the ECCD Services of Barangay Poblacion | 1 | 70000 | 49000 | 21000 | 39000 |  | 21000 | 60000 | 39000 | 21000 | 100% | 100% | 100% | 85.71% | 100% | 2008-09-10 | no data | 2009-05-13 | 2009-06-05 | n/a | 23 | 122 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Labaan | 140123001 | Improvement of Water Supply System | 1 | 421415 | 261395 | 160020 | 261395 |  | 171430 | 432825 | 261395 | 171430 | 100% | 100% | 107.1% | 102.7% | 100% | 2007-03-13 | n/a | 2007-08-22 | 2009-01-27 | n/a | 524 | 187 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Labaan | 140123001 | Construction of 3 Units Artesian Well | 1 | 311990 | 201593 | 110397 | 201593 |  | 110429 | 312022 | 201593 | 110429 | 100% | 100% | 100% | 100% | 100% | 2008-09-16 | no data | 2009-02-01 | 2009-04-23 | n/a | 81 | 32 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Palang | 140123002 | Const. of 3 units artesian deepwell | 1 | 265355 | 173075 | 92280 | 172300 |  | 142080 | 314380 | 172300 | 142080 | 100% | 100% | 154% | 118.5% | 100% | 2007-03-13 | n/a | 2007-06-10 | 2007-08-29 | no data | 80 | 44 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Palang | 140123002 | Construction of 1 Unit Day Care Center | 1 | 571571 | 400100 | 171471 | 382330.34 |  | 172571 | 554901.34 | 382330.34 | 172571 | 100% | 100% | 100.6% | 97.08% | 100% | 2008-09-16 | no data | 2009-01-29 | 2009-05-31 | no data | 122 | 44 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Palang | 140123002 | Construction of Palang Proper Water System | 1 | 682946.95 | 478948.13 | 203998.82 | 384708.68 |  | 203998.82 | 588707.5 | 384708.68 | 203998.82 | 100% | 100% | 100% | 86.2% | 100% | 2009-03-25 | no data | 2009-05-23 | 2009-06-15 | no data | 23 | 136 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Pantoc | 140123003 | Improvement of Water Supply System | 1 | 577621 | 404891 | 172730 | 404891 |  | 184142 | 589033 | 404891 | 184142 | 100% | 100% | 106.6% | 102% | 100% | 2007-03-13 | n/a | 2008-01-03 | 2008-06-30 | no data | 179 | 91 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Pantoc | 140123003 | Construction of 2 Classroom Building | 1 | 881100 | 616770 | 264330 | 555570 |  | 264330 | 819900 | 555570 | 264330 | 100% | 100% | 100% | 93.05% | 100% | 2008-09-16 | no data | 2009-01-28 | 2009-05-29 | 2009-06-04 | 121 | 75 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Pantoc | 140123003 | Construction of Barangay Road Riprap | 1 | 674230 | 473460.47 | 200769.53 | 380703.6 |  | 200769.53 | 581473.13 | 380703.6 | 200769.53 | 100% | 100% | 100% | 86.24% | 100% | 2009-03-25 | no data | 2009-05-21 | 2009-06-17 | 2009-06-18 | 27 | 137 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Poblacion | 140123004 | Const. of ECCD Center | 1 | 503454 | 362494 | 140960 | 362494 |  | 246315.24 | 608809.24 | 362494 | 246315.24 | 100% | 100% | 174.7% | 120.9% | 100% | 2007-03-13 | n/a | 2007-08-22 | 2008-05-28 | no data | 280 | 190 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Poblacion | 140123004 | Improvement of Poblacion 3 Classroom Building | 1 | 575708 | 402996 | 172712 | 365720.51 |  | 122712 | 488432.51 | 365720.51 | 122712 | 100% | 100% | 71.05% | 84.84% | 100% | 2008-09-16 | no data | 2009-01-28 | 2009-03-12 | 2009-03-23 | 43 | 163 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Poblacion | 140123004 | Improvement of 4-Units High School Building | 1 | 632120 | 444146.43 | 187973.57 | 444041.32 |  | 187973.77 | 632015.09 | 444041.32 | 187973.77 | 100% | 100% | 100% | 99.98% | 100% | 2009-03-25 | no data | 2009-05-11 | 2009-06-02 | 2009-06-10 | 22 | 204 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Tangadan | 140123005 | Improvement of Water Supply System | 1 | 464560 | 313810 | 150750 | 313810 |  | 231437.48 | 545247.48 | 313810 | 231437.48 | 100% | 100% | 153.5% | 117.4% | 100% | 2007-03-13 | n/a | 2008-02-20 | 2008-12-22 | no data | 306 | 168 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Villa Mercedes | 140123006 | Improvement of Water Supply System | 1 | 407635 | 284335 | 123300 | 284335 |  | 124300 | 408635 | 284335 | 124300 | 100% | 100% | 100.8% | 100.2% | 100% | 2007-03-13 | n/a | 2008-02-15 | 2008-07-15 | no data | 151 | 146 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Villa Mercedes | 140123006 | Construction of Purok Water System | 1 | 310619 | 178541 | 132078 | 170151 |  | 132078 | 302229 | 170151 | 132078 | 100% | 100% | 100% | 97.3% | 100% | 2008-09-16 | no data | 2009-01-28 | 2009-03-15 | n/a | 46 | 74 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Agsimao - C7 | 140125001 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Alaoa - C7 | 140125002 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Lapat-Balantay - C7 | 140125009 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Naglibacan- C7 | 140125010 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Anayan - C7 | 140125003 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Balaat - C7 | 140125005 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Cogon - C7 | 140125007 | Road Improvement - C7 | 7 | 5510000 | 3000000 | 2510000 | 3000000 |  | 2510000 | 5510000 | 3000000 | 2510000 | 100% | 100% | 100% | 100% | 100% | 2005-03-16 | 2005-06-24 | 2005-09-01 | 2006-08-30 | no data | 363 | 471 |  | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Agsimao - C9 | 140125001 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Alaoa - C9 | 140125002 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Lapat-Balantay - C9 | 140125009 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Naglibacan - C9 | 140125010 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Anayan - C9 | 140125003 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Belaat - C9 | 140125005 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Cogon - C9 | 140125007 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Caganayan - C9 | 140125006 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Lanec - C9 | 140125008 | Road Improvement - C9 | 9 | 4264880 | 2800000 | 1464880 | 2520000 |  | 846340 | 3363540.24 | 2520000 | 843540.24 | 100% | 99.67% | 57.78% | 78.87% | 100% | 2006-06-13 | 2006-07-10 | 2007-11-06 | completed as built | no data | #VALUE! | 626 | completed as built | 1 | LUZON
CAR | 14 | Abra | 1401 | Tineg | 140125 | Apao | 140125004 | Water System | 1 | 407602 | 200000 | 207602 | 160000 |  | 185092.58 | 345092.58 | 160000 | 185092.58 | 100% | 100% | 89.16% | 84.66% | 100% | 2006-06-13 | 2006-07-10 | 2006-10-25 | 2008-01-25 | no data | 457 | 25 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Amduntog | 142711001 | Inomili-Kinabba Concrete Pathway | 1 | 299012 | 173797.8 | 125214.2 | 173797.8 |  | 126214.2 | 300012 | 173797.8 | 126214.2 | 100% | 100% | 100.8% | 100.3% | 100% | 2005-02-17 | 2005-04-07 | 2005-05-15 | 2005-08-15 | 2005-08-30 | 92 | 215 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Amduntog | 142711001 | Nalnay-Bahag FMR Improvement | 1 | 564512 | 499598 | 64914 | 491698 |  | 80876 | 572574 | 491698 | 80876 | 100% | 100% | 124.6% | 101.4% | 100% | 2008-11-19 | no data | 2009-05-09 | 2009-08-26 | no data | 109 | 79 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Antipolo | 142711002 | Napayew Multi Purpose Solar Drier | 1 | 234869 | 121908 | 112961 | 121908 |  | 184047.3 | 305955.3 | 121908 | 184047.3 | 100% | 100% | 162.9% | 130.3% | 100% | 2003-11-26 | 2004-02-05 | 2004-05-07 | 2004-07-15 | 2004-07-15 | 69 | 183 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Antipolo | 142711002 | Habengan-Antipolo Concrete Footbridge | 1 | 175794.6 | 101527 | 74267.6 | 101527 |  | 75267.6 | 176794.6 | 101527 | 75267.6 | 100% | 100% | 101.3% | 100.6% | 100% | 2005-02-17 | 2005-04-07 | 2005-07-04 | 2005-12-15 | 2005-12-20 | 164 | 195 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Antipolo | 142711002 | Day Care Center Const. | 1 | 1177570.71 | 455000 | 722570.71 | 455000 |  | 725570.71 | 1180570.71 | 455000 | 725570.71 | 100% | 100% | 100.4% | 100.3% | 100% | 2006-02-10 | 2006-04-25 | 2006-07-19 | 2006-12-29 | 2006-12-30 | 163 | 183 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Antipolo | 142711002 | Proper Antipolo to Hipat Pathway Construction | 1 | 524049 | 437749 | 86300 | 419228 |  | 114204.6 | 533432.6 | 419228 | 114204.6 | 100% | 100% | 132.3% | 101.8% | 100% | 2008-11-19 | no data | 2009-04-16 | 2009-05-29 | no data | 43 | 70 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Camandag | 142711003 | Improvement of Camandag Communal Irrigation System | 1 | 434020 | 379992 | 54028 | 303993.6 |  | 56848 | 360841.6 | 303993.6 | 56848 | 100% | 100% | 105.2% | 83.14% | 100% | 2008-11-19 | no data | 2009-03-25 | 2009-08-28 | no data | 156 | 37 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Camandag - C2 | 142711003 | Towel cable Bridge - C2c | 2 | 747435.16 | 526227 | 221208.16 | 526227 |  | 223503.22 | 749730.22 | 526227 | 223503.22 | 100% | 100% | 101% | 100.3% | 100% | 2003-11-26 | 2004-02-05 | 2004-06-25 | 2004-10-18 | 2004-10-26 | 115 | 205 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Camandag - C5 | 142711003 | Farm to Market Road Improvement - C5 | 5 | 1321281 | 792085 | 529196 | 792085 |  | 529196 | 1321281 | 792085 | 529196 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-05-29 | 2006-08-31 | 2005-11-20 | 94 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Cawayan - C2 | 142711004 | Pula-Cawayan FMR Improvement - C2d | 2 | 1553535.9 | 598383 | 955152.9 | 598383 |  | 849005.12 | 1447388.12 | 598383 | 849005.12 | 100% | 100% | 88.89% | 93.17% | 100% | 2005-02-17 | 2005-04-07 | 2005-06-28 | 2005-07-20 | 2005-08-16 | 22 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Cawayan - C5 | 142711004 | Farm to Market Road Improvement - C5 | 5 | 1321281 | 792085 | 529196 | 792085 |  | 529196 | 1321281 | 792085 | 529196 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-05-29 | 2006-08-31 | 2005-11-20 | 94 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Duli |  | Lanak-Hamhamaan FMR Improvement | 1 | 1158636.8 | 515631 | 643005.8 | 515631 |  | 461757.3 | 977388.3 | 515631 | 461757.3 | 100% | 100% | 71.81% | 84.36% | 100% | 2005-02-17 | 2005-04-07 | 2005-05-20 | 2005-11-18 | 2005-11-20 | 182 | 207 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Duli - C2 |  | Towel cable Bridge - C2c | 2 | 747435.16 | 526227 | 221208.16 | 526227 |  | 223503.22 | 749730.22 | 526227 | 223503.22 | 100% | 100% | 101% | 100.3% | 100% | 2003-11-26 | 2004-02-05 | 2004-06-25 | 2004-10-18 | 2004-10-26 | 115 | 205 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Duli - C5 |  | Farm to Market Road Improvement - C5 | 5 | 1321281 | 792085 | 529196 | 792085 |  | 529196 | 1321281 | 792085 | 529196 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-05-29 | 2006-08-31 | 2005-11-20 | 94 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Duli SEZ |  | Hamhamaan to Tadyukong FMR Improvement | 1 | 358260 | 318860 | 39400 | 255088 |  | 61080 | 316168 | 255088 | 61080 | 100% | 100% | 155% | 88.25% | 100% | 2008-11-19 | no data | 2009-06-06 | 2009-08-20 | no data | 75 | 212 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Haliap | 142711005 | Haliap Water System | 1 | 814447.3 | 334690 | 479757.3 | 334690 |  | 361290.67 | 695980.67 | 334690 | 361290.67 | 100% | 100% | 75.31% | 85.45% | 100% | 2005-02-17 | 2005-04-07 | 2005-06-21 | 2005-10-31 | 2005-11-14 | 132 | 166 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Liwon |  | Water Supply System Rehabilitation and Extension | 1 | 224011.73 | 150062 | 73949.73 | 150062 |  | 100199.73 | 250261.73 | 150062 | 100199.73 | 100% | 100% | 135.5% | 111.7% | 100% | 2003-11-26 | 2004-02-05 | 2004-05-25 | 2004-07-13 | 2004-07-13 | 49 | 126 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Liwon - C3 |  | Bahag-Liwon Farm to Market Road Improvement - C3 | 3 | 1124195.68 | 699900 | 424295.68 | 699900 |  | 334412.5 | 1034312.5 | 699900 | 334412.5 | 100% | 100% | 78.82% | 92% | 100% | 2005-02-17 | 2005-04-07 | 2005-05-20 | 2005-08-20 | 2005-08-22 | 92 | 355 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Liwon SEZ |  | Improvement Along Bawi to Liwon Road | 1 | 500002.2 | 465415 | 34587.2 | 454584 |  | 53593 | 508177 | 454584 | 53593 | 100% | 100% | 155% | 101.6% | 100% | 2008-11-19 | no data | 2009-05-21 | 2009-06-19 | no data | 29 | 114 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Namal | 142711006 | Guinambang-Takak Footpath and Foot Bridge | 1 | 288874.2 | 178543 | 110331.2 | 178543 |  | 111330.7 | 289873.7 | 178543 | 111330.7 | 100% | 100% | 100.9% | 100.3% | 100% | 2003-11-26 | 2004-02-05 | 2004-03-30 | 2004-10-15 | 2004-11-13 | 199 | 142 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Namal- C3 | 142711006 | Bahag-Liwon Farm to Market Road Improvement - C3 | 3 | 1124195.68 | 699900 | 424295.68 | 699900 |  | 334412.5 | 1034312.5 | 699900 | 334412.5 | 100% | 100% | 78.82% | 92% | 100% | 2005-02-17 | 2005-04-07 | 2005-05-20 | 2005-08-20 | 2005-08-22 | 92 | 355 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nampaling |  | Brgy Health Station | 1 | 524735.2 | 351222 | 173513.2 | 351222 |  | 180532.14 | 531754.14 | 351222 | 180532.14 | 100% | 100% | 104% | 101.3% | 100% | 2003-11-26 | 2004-02-05 | 2004-03-30 | 2004-10-20 | 2004-11-12 | 204 | 143 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nampaling - C3 |  | Bahag-Liwon Farm to Market Road Improvement - C3 | 3 | 1124195.68 | 699900 | 424295.68 | 699900 |  | 334412.5 | 1034312.5 | 699900 | 334412.5 | 100% | 100% | 78.82% | 92% | 100% | 2005-02-17 | 2005-04-07 | 2005-05-20 | 2005-08-20 | 2005-08-22 | 92 | 355 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Natcak |  | Pah-Duan Cable Bridge | 1 | 537106.22 | 346536 | 190570.22 | 346536 |  | 144442.47 | 490978.47 | 346536 | 144442.47 | 100% | 100% | 75.79% | 91.41% | 100% | 2003-11-26 | 2004-02-05 | 2004-08-10 | 2004-10-11 | 2004-10-28 | 62 | 106 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Natcak - C5 |  | Farm to Market Road Improvement - C5 | 5 | 1321281 | 792085 | 529196 | 792085 |  | 529196 | 1321281 | 792085 | 529196 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-05-29 | 2006-08-31 | 2005-11-20 | 94 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Natcak SEZ |  | Construction of Banihal-Bunalan Sledge Trail | 1 | 406680 | 316000 | 90680 | 312936.17 |  | 107885 | 420821.17 | 312936.17 | 107885 | 100% | 100% | 119% | 103.5% | 100% | 2008-11-19 | no data | 2009-03-14 | 2009-08-19 | no data | 158 | 258 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nungawa | 142711007 | Boco-Nungawa Concrete Foot Path | 1 | 395948.18 | 221807 | 174141.18 | 221807 |  | 165245.48 | 387052.48 | 221807 | 165245.48 | 100% | 100% | 94.89% | 97.75% | 100% | 2003-11-26 | 2004-02-05 | 2004-04-01 | 2004-07-17 | 2004-07-17 | 107 | 90 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nungawa | 142711007 | Ayuhip-Bocco Farm to Market Road Improvement | 1 | 339317.05 | 203319.6 | 135997.45 | 203319.5 |  | 125737.6 | 329057.1 | 203319.5 | 125737.6 | 100% | 100% | 92.46% | 96.98% | 100% | 2005-02-17 | 2005-04-07 | 2005-05-16 | 2005-06-24 | 2005-08-11 | 39 | 90 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nungawa | 142711007 | Communal Irrigation System | 1 | 855412.22 | 452856 | 402556.22 | 452856 |  | 402556.22 | 855412.22 | 452856 | 402556.22 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-07-08 | 2006-11-20 | 2006-11-23 | 135 | 94 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nungawa | 142711007 | Baggu-Witig FMR Construction | 1 | 931546 | 856386 | 75160 | 854284.8 |  | 101070 | 955354.8 | 854284.8 | 101070 | 100% | 100% | 134.5% | 102.6% | 100% | 2008-11-19 | no data | 2009-03-26 | 2009-06-23 | no data | 89 | 85 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Panubtuban | 142711008 | Road Concreting | 1 | 697703 | 308117 | 389586 | 308117 |  | 416883.9 | 725000.9 | 308117 | 416883.9 | 100% | 100% | 107% | 103.9% | 100% | 2003-11-26 | 2004-02-05 | 2004-05-18 | 2004-07-18 | 2004-09-13 | 61 | 130 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Panubtuban | 142711008 | Solar Drying Pavement | 1 | 182489.5 | 72751.9 | 109737.6 | 72751 |  | 678152.9 | 750903.9 | 72751 | 678152.9 | 100% | 100% | 618% | 411.5% | 100% | 2005-02-17 | 2005-04-07 | 2005-06-18 | 2005-09-20 | 2005-09-30 | 94 | 128 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Panubtuban | 142711008 | Farm to Market Road Improvement | 1 | 1807266 | 999570 | 807696 | 999570 |  | 807723 | 1807293 | 999570 | 807723 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-06-13 | 2006-12-31 | 2007-03-27 | 201 | 130 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Panubtuban | 142711008 | Construction of 3 units Multipurpose Pavement | 1 | 740574 | 670000 | 70574 | 662362 |  | 75499.64 | 737861.64 | 662362 | 75499.64 | 100% | 100% | 107% | 99.63% | 100% | 2008-11-19 | no data | 2009-03-23 | 2009-06-23 | no data | 92 | 125 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Pula | 142711009 | Brgy Health Station | 1 | 896681.12 | 495578 | 401103.12 | 495578 |  | 378482.75 | 874060.75 | 495578 | 378482.75 | 100% | 100% | 94.36% | 97.48% | 100% | 2003-11-26 | 2004-02-05 | 2004-05-04 | 2004-08-15 | 2004-09-14 | 103 | 195 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Pula | 142711009 | Concreting of Intermittent Sections from Dakkel Danum to Sitio Hegpit | 1 | 699136 | 556000 | 143136 | 550144 |  | 200502.49 | 750646.49 | 550144 | 200502.49 | 100% | 100% | 140.1% | 107.4% | 100% | 2008-11-19 | no data | 2009-03-19 | 2009-05-26 | no data | 68 | 233 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Pula - C2 | 142711009 | Pula-Cawayan FMR Improvement - C2d | 2 | 1553535.9 | 598383 | 955152.9 | 598383 |  | 849005.12 | 1447388.12 | 598383 | 849005.12 | 100% | 100% | 88.89% | 93.17% | 100% | 2005-02-17 | 2005-04-07 | 2005-06-28 | 2005-07-20 | 2005-08-16 | 22 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Pula - C5 | 142711009 | Farm to Market Road Improvement - C5 | 5 | 1321281 | 792085 | 529196 | 792085 |  | 529196 | 1321281 | 792085 | 529196 | 100% | 100% | 100% | 100% | 100% | 2006-02-10 | 2006-04-25 | 2006-05-29 | 2006-08-31 | 2005-11-20 | 94 | 411 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Anao | 142709001 | Road Concreting | 1 | 472859 | 330000 | 142859 | 330000 |  | 185269.45 | 515269.45 | 330000 | 185269.45 | 100% | 100% | 129.7% | 109% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-01-01 | 2004-04-19 | 153 | 97 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Anao | 142709001 | Rehab/Improvt. Of Bulhi-Pugo Road | 1 | 1875421.03 | 1217400 | 658021.03 | 1217400 |  | 214818 | 1432218 | 1217400 | 214818 | 100% | 100% | 32.65% | 76.37% | 100% | 2005-01-14 | 2005-02-24 | 2005-06-13 | 2007-10-31 | no data | 870 | 100 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Bangtinon | 142709002 | Water System | 1 | 452041.96 | 275000 | 177041.96 | 275000 |  | 121692 | 396692 | 275000 | 121692 | 100% | 100% | 68.74% | 87.76% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-06-01 | 2004-07-01 | 305 | 65 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Bangtinon | 142709002 | Rehab/Improvt. Of Habian-Bangtinon Road | 1 | 1014872 | 563000 | 451872 | 563000 |  | 470582 | 1033582 | 563000 | 470582 | 100% | 100% | 104.1% | 101.8% | 100% | 2005-01-14 | 2005-02-24 | 2005-06-20 | 2005-12-30 | no data | 193 | 68 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Bitu | 142709003 | Road Opening & Concreting | 1 | 505019.5 | 325000 | 180019.5 | 325000 |  | 105718 | 430718 | 325000 | 105718 | 100% | 100% | 58.73% | 85.29% | 100% | 2003-05-09 | 2003-06-26 | 2003-09-01 | 2003-12-01 | 2004-04-26 | 91 | 75 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Cababuyan North | 142709012 | Road Concreting | 1 | 417596 | 310000 | 107596 | 310000 |  | 105881.8 | 415881.8 | 310000 | 105881.8 | 100% | 100% | 98.41% | 99.59% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-03-01 | 2004-04-29 | 213 | 153 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Cababuyan North | 142709012 | Capability Building and Support Facility | 1 | 653668 | 370000 | 283668 | 370000 |  | 133500 | 503500 | 370000 | 133500 | 100% | 100% | 47.06% | 77.03% | 100% | 2005-12-06 | 2006-02-06 | 2006-10-15 | 2007-04-30 | no data | 197 | 153 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Cababuyan South | 142709004 | Water System | 1 | 453675.28 | 300000 | 153675.28 | 300000 |  | 93093.15 | 393093.15 | 300000 | 93093.15 | 100% | 100% | 60.58% | 86.65% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-07-01 | 2004-08-17 | 335 | 109 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Cababuyan South | 142709004 | Communal Irrigation System | 1 | 177910 | 108000 | 69910 | 86400 |  | 120910 | 207310 | 86400 | 120910 | 100% | 100% | 173% | 116.5% | 100% | 2005-12-06 | 2006-02-06 | 2006-05-01 | 2006-08-30 | no data | 121 | 160 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Mompolia | 142709005 | Road Opening | 1 | 476404.5 | 320000 | 156404.5 | 320000 |  | 160708.73 | 480708.73 | 320000 | 160708.73 | 100% | 100% | 102.8% | 100.9% | 100% | 2003-05-09 | 2003-06-26 | 2003-09-01 | 2004-03-01 | 2004-05-24 | 182 | 198 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Mompolia | 142709005 | Guintinan-Ibawat Road Construction | 1 | 898200 | 641700 | 256500 | 639221 |  | 242500 | 881721 | 639221 | 242500 | 100% | 100% | 94.54% | 98.17% | 100% | 2005-12-06 | 2006-02-06 | 2006-05-05 | 2008-09-30 | no data | 879 | 198 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Namulditan | 142709006 | Water System | 1 | 463678.67 | 270000 | 193678.67 | 270000 |  | 122866 | 392866 | 270000 | 122866 | 100% | 100% | 63.44% | 84.73% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-07-12 | 2004-07-01 | 346 | 171 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Namulditan | 142709006 | Shreding Machine with housing | 1 | 637872.5 | 395000 | 242872.5 | 389336.5 |  | 378872 | 768208.5 | 389336.5 | 378872 | 100% | 100% | 156% | 120.4% | 100% | 2005-12-06 | 2006-02-06 | 2006-10-15 | 2007-04-25 | no data | 192 | 171 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | O-ong | 142709007 | Road Opening | 1 | 418558 | 285000 | 133558 | 285000 |  | 130190.5 | 415190.5 | 285000 | 130190.5 | 100% | 100% | 97.48% | 99.2% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-07-01 | 2004-08-01 | 335 | 168 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | O-ong | 142709007 | Market Linkage Post | 1 | 703762.46 | 493700 | 210062.46 | 488036.5 |  | 184405 | 672441.5 | 488036.5 | 184405 | 100% | 100% | 87.79% | 95.55% | 100% | 2005-12-06 | 2006-02-06 | 2006-10-15 | 2008-09-30 | no data | 716 | 168 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Piwong | 142709008 | Road Opening and Gravelling | 1 | 649547.5 | 300000 | 349547.5 | 300000 |  | 251689.75 | 551689.75 | 300000 | 251689.75 | 100% | 100% | 72% | 84.93% | 100% | 2003-05-09 | 2003-06-26 | 2003-09-01 | 2004-07-01 | 2004-07-01 | 304 | 160 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Piwong | 142709008 | Daligi-Panadan Road Improvement | 1 | 1079500 | 396600 | 682900 | 396600 |  | 80300 | 476900 | 396600 | 80300 | 100% | 100% | 11.76% | 44.18% | 100% | 2005-12-06 | 2006-02-06 | 2006-10-01 | 2008-09-30 | no data | 730 | 212 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Poblacion | 142709009 | Water System | 1 | 561037.43 | 315000 | 246037.43 | 315000 |  | 282112.71 | 597112.71 | 315000 | 282112.71 | 100% | 100% | 114.7% | 106.4% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2004-05-07 | 2004-05-07 | 280 | 166 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Poblacion | 142709009 | Allac-Pumtang Road Improvement | 1 | 766300 | 545000 | 221300 | 545000 |  | 219700 | 764700 | 545000 | 219700 | 100% | 100% | 99.28% | 99.79% | 100% | 2005-12-06 | 2006-02-06 | 2006-05-10 | 2006-05-15 | no data | 5 | 132 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Ubuag | 142709010 | Road Opening | 1 | 510499.5 | 280000 | 230499.5 | 280000 |  | 268221.75 | 548221.75 | 280000 | 268221.75 | 100% | 100% | 116.4% | 107.4% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-01 | 2003-12-01 | 2004-04-24 | 122 | 104 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Ubuag | 142709010 | Rehab/Improvt. Of Tiggihan-Ibaat Road | 1 | 2848915 | 1819600 | 1029315 | 1819600 |  | 999315 | 2818915 | 1819600 | 999315 | 100% | 100% | 97.09% | 98.95% | 100% | 2005-01-14 | 2005-02-24 | 2005-06-29 | 2006-10-28 | no data | 486 | 100 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Umalbong | 142709011 | Water System | 1 | 445821.1 | 290000 | 155821.1 | 290000 |  | 139922 | 429922 | 290000 | 139922 | 100% | 100% | 89.8% | 96.43% | 100% | 2003-05-09 | 2003-06-26 | 2003-08-18 | 2004-05-01 | 2004-06-17 | 257 | 149 |  | 1
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Umalbong | 142709011 | Bocoh Road Construction | 1 | 921000 | 650000 | 271000 | 650000 |  | 161000 | 811000 | 650000 | 161000 | 100% | 100% | 59.41% | 88.06% | 100% | 2005-12-06 | 2006-02-06 | 2006-05-01 | 2008-09-30 | no data | 883 | 149 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ahin | 142710001 | Road Construction | 1 | 1086000 | 642000 | 444000 | 642000 |  | 423792 | 1065792 | 642000 | 423792 | 100% | 100% | 95.45% | 98.14% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-25 | 2007-02-28 | no data | 156 | 120 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Tulludan - C2 | 142710011 | Const. of Tulludan Proper-Ahin FMR - C2g | 2 | 1758000 | 1230000 | 528000 | 1230000 |  | 521174.88 | 1751174.88 | 1230000 | 521174.88 | 100% | 100% | 98.71% | 99.61% | 100% | 2005-02-21 | 2005-06-13 | 2005-07-18 | 2006-02-28 | 2006-03-22 | 225 | 270 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ahin - C2 | 142710001 | Const. of Tulludan Proper-Ahin FMR - C2g | 2 | 1758000 | 1230000 | 528000 | 1230000 |  | 521174.88 | 1751174.88 | 1230000 | 521174.88 | 100% | 100% | 98.71% | 99.61% | 100% | 2005-02-21 | 2005-06-13 | 2005-07-18 | 2006-02-28 | 2006-03-22 | 225 | 270 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ap-apid | 142710002 | Construction of 1 Unit School Building | 1 | 291500 | 175000 | 116500 | 175000 |  | 121842 | 296842 | 175000 | 121842 | 100% | 100% | 104.6% | 101.8% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-25 | 2007-02-20 | no data | 148 | 160 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ap-apid | 142710002 | Ap-apid- Impugong Road Improvement | 1 | 760522 | 475000 | 285522 | 459109.8 |  | 285522 | 744631.8 | 459109.8 | 285522 | 100% | 100% | 100% | 97.91% | 100% | 2009-02-06 | no data | 2009-05-18 | 2009-06-30 | no data | 43 | 172 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ap-apid - C2 | 142710002 | Road Opening - C2a | 2 | 1079666 | 726762 | 352904 | 726762 |  | 378921.33 | 1105683.33 | 726762 | 378921.33 | 100% | 100% | 107.4% | 102.4% | 100% | 2003-10-22 | 2003-12-29 | 2004-03-01 | 2004-06-15 | 2004-06-17 | 106 | 240 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Gumhang - C2 | 142710006 | Road Opening - C2a | 2 | 1079666 | 726762 | 352904 | 726762 |  | 378921.33 | 1105683.33 | 726762 | 378921.33 | 100% | 100% | 107.4% | 102.4% | 100% | 2003-10-22 | 2003-12-29 | 2004-03-01 | 2004-06-15 | 2004-06-17 | 106 | 240 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Binablayan | 142710003 | Road Improvement | 1 | 1805826.05 | 1227186 | 578640.05 | 1227186 |  | 562263.05 | 1789449.05 | 1227186 | 562263.05 | 100% | 100% | 97.17% | 99.09% | 100% | 2003-10-22 | 2003-12-29 | 2004-03-01 | 2004-06-30 | 2004-07-13 | 121 | 221 |  | 1
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Binablayan | 142710003 | Hablang-Huykok Road rerouting | 1 | 1141590 | 750000 | 391590 | 750000 |  | 392490 | 1142490 | 750000 | 392490 | 100% | 100% | 100.2% | 100.1% | 100% | 2009-02-06 | no data | 2009-05-25 | 2009-06-30 | no data | 36 | 241 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Danggo | 142710004 | Road Construction | 1 | 654000 | 229000 | 425000 | 229000 |  | 414608 | 643608 | 229000 | 414608 | 100% | 100% | 97.55% | 98.41% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-01 | 2006-10-31 | no data | 60 | 242 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Dango | 142710004 | Wakallan-Dango FMR construction | 1 | 1646810 | 910000 | 736810 | 907334.09 |  | 741460 | 1648794.09 | 907334.09 | 741460 | 100% | 100% | 100.6% | 100.1% | 100% | 2009-02-06 | no data | 2009-05-19 | 2009-06-30 | no data | 42 | 165 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Dango- C2 | 142710004 | Const. of Baay-Proper Luhong FMR - C2f | 2 | 2388500 | 1650000 | 738500 | 1650000 |  | 738566 | 2388566 | 1650000 | 738566 | 100% | 100% | 100% | 100% | 100% | 2005-02-21 | 2005-06-13 | 2005-07-04 | 2006-03-30 | 2006-07-19 | 269 | 304 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Luhong- C2 | 142710008 | Const. of Baay-Proper Luhong FMR - C2f | 2 | 2388500 | 1650000 | 738500 | 1650000 |  | 738566 | 2388566 | 1650000 | 738566 | 100% | 100% | 100% | 100% | 100% | 2005-02-21 | 2005-06-13 | 2005-07-04 | 2006-03-30 | 2006-07-19 | 269 | 304 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Eheb | 142710005 | Road Improvement | 1 | 1250000 | 850000 | 400000 | 850000 |  | 420279 | 1270279 | 850000 | 420279 | 100% | 100% | 105.1% | 101.6% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-01 | 2007-01-20 | no data | 141 | 85 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Eheb | 142710005 | Eheb-Palas FMR Construction | 1 | 1500830 | 1000000 | 500830 | 999940.4 |  | 500830 | 1500770.4 | 999940.4 | 500830 | 100% | 100% | 100% | 100% | 100% | 2009-02-06 | no data | 2009-05-13 | 2009-08-31 | no data | 110 | 80 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Gumhang | 142710006 | Road Construction | 1 | 1308000 | 904000 | 404000 | 904000 |  | 361696 | 1265696 | 904000 | 361696 | 100% | 100% | 89.53% | 96.77% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-28 | 2006-10-31 | no data | 33 | 24 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Gumhang | 142710006 | Balihong-Pitekan FMR construction | 1 | 1284969 | 825000 | 459969 | 824970 |  | 460620 | 1285590 | 824970 | 460620 | 100% | 100% | 100.1% | 100% | 100% | 2009-02-06 | no data | 2009-05-18 | 2009-06-30 | no data | 43 | 162 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Impugong | 142710007 | Const. of Taba-Tullibeng FMR | 1 | 1219000 | 720000 | 499000 | 720000 |  | 534620 | 1254620 | 720000 | 534620 | 100% | 100% | 107.1% | 102.9% | 100% | 2005-02-21 | 2005-06-13 | 2005-06-15 | 2005-09-30 | 2005-11-10 | 107 | 162 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Impugong | 142710007 | Road Construction | 1 | 372000 | 180000 | 192000 | 180000 |  | 194255 | 374255 | 180000 | 194255 | 100% | 100% | 101.2% | 100.6% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-01 | 2007-02-10 | no data | 162 | 20 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Impugong | 142710007 | Impugong-Poblacion Road Improvement | 1 | 1405218.05 | 950000 | 455218.05 | 914315.77 |  | 516977.07 | 1431292.84 | 914315.77 | 516977.07 | 100% | 100% | 113.6% | 101.9% | 100% | 2009-02-06 | no data | 2009-05-17 | 2009-08-07 | no data | 82 | 214 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Poblacion (Tinoc) | 142710009 | Road Improvement | 1 | 1120879 | 772239 | 348640 | 772239 |  | 323103.35 | 1095342.35 | 772239 | 323103.35 | 100% | 100% | 92.68% | 97.72% | 100% | 2003-10-22 | 2003-12-29 | 2004-03-01 | 2004-06-27 | 2004-06-28 | 118 | 303 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Poblacion (Tinoc) | 142710009 | Road Construction | 1 | 340000 | 120000 | 220000 | 120000 |  | 217600 | 337600 | 120000 | 217600 | 100% | 100% | 98.91% | 99.29% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-01 | 2006-10-31 | no data | 60 | 70 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Tukucan - C2 | 142710010 | Road Opening - C2b | 2 | 1274125 | 873813 | 400312 | 873813 |  | 414486.3 | 1288299.3 | 873813 | 414486.3 | 100% | 100% | 103.5% | 101.1% | 100% | 2003-10-22 | 2003-12-29 | 2004-03-01 | 2004-06-26 | 2004-06-27 | 117 | 248 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Eheb - C2 | 142710005 | Road Opening - C2b | 2 | 1274125 | 873813 | 400312 | 873813 |  | 414486.3 | 1288299.3 | 873813 | 414486.3 | 100% | 100% | 103.5% | 101.1% | 100% | 2003-10-22 | 2003-12-29 | 2004-03-01 | 2004-06-26 | 2004-06-27 | 117 | 248 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Tulludan | 142710011 | Cocoy-Telep FMR construction | 1 | 1469445.5 | 900000 | 569445.5 | 899935.72 |  | 570095.5 | 1470031.22 | 899935.72 | 570095.5 | 100% | 100% | 100.1% | 100% | 100% | 2009-02-06 | no data | 2009-05-27 | 2009-06-30 | no data | 34 | 112 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Wangwang | 142710012 | Road Improvement | 1 | 712000 | 500000 | 212000 | 492000 |  | 202100 | 694100 | 492000 | 202100 | 100% | 100% | 95.33% | 97.49% | 100% | 2006-02-22 | 2006-05-22 | 2006-09-01 | 2007-02-25 | no data | 177 | 133 |  | 1 | LUZON
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Wangwang | 142710012 | Higib-Amueg Road Concreting | 1 | 445672 | 190000 | 255672 | 187029.5 |  | 256322 | 443351.5 | 187029.5 | 256322 | 100% | 100% | 100.3% | 99.48% | 100% | 2009-02-06 | no data | 2009-05-25 | 2009-06-30 | no data | 36 | 162 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Aciga | 143209001 | Construction of Village Water System | 1 | 825928 | 595928 | 230000 | 593518.2 |  | 211525.79 | 803590.2 | 593518.2 | 210072 | 100% | 99.31% | 91.97% | 97.3% | 100% | 2008-07-28 | no data | 2009-03-10 | 2009-05-30 | n/a | 81 | 172 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Allaguia | 143209002 | Rehab. of Brgy. Road | 1 | 898856.06 | 629246.06 | 269610 | 578675.5 |  | 270609.15 | 849284.65 | 578675.5 | 270609.15 | 100% | 100% | 100.4% | 94.49% | 100% | 2007-05-23 | n/a | 2008-03-05 | 2008-09-30 | no data | 209 | 224 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Allaguia | 143209002 | Construction of 12 Meters Slab Footbridge | 1 | 265000 | 171998.59 | 93001.41 | 137598.86 |  | 93709.04 | 230600.27 | 137598.86 | 93001.41 | 100% | 99.24% | 100.8% | 87.02% | 100% | 2008-07-28 | no data | 2009-01-03 | 2009-03-21 | n/a | 77 | 255 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Allaguia | 143209002 | Construction of 1-unit MPP | 1 | 180000 | 130400 | 49600 | 104625 |  | 39600 | 144225 | 104625 | 39600 | 100% | 100% | 79.84% | 80.12% | 100% | 2009-03-31 | no data | 2009-07-01 | 2009-08-05 | n/a | 35 | 255 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Ammacian | 143209003 | Construction of 2-Units Flood Control | 1 | 1480000 | 1062850 | 417150 | 1008933.47 |  | 417150 | 1426083.47 | 1008933.47 | 417150 | 100% | 100% | 100% | 96.36% | 100% | 2008-07-28 | no data | 2009-01-24 | 2009-06-18 | no data | 145 | 273 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Apatan | 143209004 | Const. of 1 unit cable bridge | 1 | 1755000 | 1213037.84 | 541962.16 | 1152547.65 |  | 541962.16 | 1694509.81 | 1152547.65 | 541962.16 | 100% | 100% | 100% | 96.55% | 100% | 2007-05-23 | n/a | 2008-07-05 | 2008-09-30 | no data | 87 | 384 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Asibanglan | 143209013 | Energizing Off Grid through Alternative Power Source | 1 | 1122355 | 805854.11 | 316500.89 | 767303.59 |  | 316500.89 | 1083804.48 | 767303.59 | 316500.89 | 100% | 100% | 100% | 96.57% | 100% | 2008-07-28 | no data | 2009-03-26 | 2009-04-07 | n/a | 12 | 184 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Asibanglan | 143209013 | Construction of Footpath | 1 | 200000 | 138323 | 61677 | 110658.4 |  | 60677 | 171335.4 | 110658.4 | 60677 | 100% | 100% | 98.38% | 85.67% | 100% | 2009-03-31 | no data | 2009-07-02 | 2009-09-30 | no data | 90 | 115 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Baay | 143209005 | Const. of 1 unit Brgy. Health Station | 1 | 711200 | 487976 | 223224 | 390380 |  | 223027 | 613407 | 390380 | 223027 | 100% | 100% | 99.91% | 86.25% | 100% | 2007-05-23 | n/a | 2008-02-03 | 2009-01-20 | n/a | 352 | 120 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Baay | 143209005 | Energizing Off Grid through Alternative Power Source | 1 | 874155 | 631116.55 | 243038.45 | 505298.88 |  | 380708.45 | 886007.33 | 505298.88 | 380708.45 | 100% | 100% | 156.6% | 101.4% | 100% | 2008-07-28 | no data | 2009-06-20 | 2009-06-25 | n/a | 5 | 120 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Ballayangon | 143209006 | Const. of 4 units MPP | 1 | 480000 | 365000 | 115000 | 292000 |  | 116000 | 408000 | 292000 | 116000 | 100% | 100% | 100.9% | 85% | 100% | 2007-05-23 | n/a | 2008-07-05 | 2008-09-30 | no data | 87 | 186 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Ballayangon | 143209006 | Construction of Concrete Tirepath | 1 | 644818 | 451392.91 | 193425.09 | 361114.33 |  | 168427.52 | 529539.33 | 361114.33 | 168425 | 100% | 100% | 87.08% | 82.12% | 100% | 2009-03-31 | no data | 2009-07-02 | 2009-09-30 | no data | 90 | 221 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Bayao | 143209007 | Construction of Barangay Health Station | 1 | 945000 | 674783 | 270217 | 540132.76 |  | 271057 | 811189.76 | 540132.76 | 271057 | 100% | 100% | 100.3% | 85.84% | 100% | 2008-07-28 | no data | 2009-01-22 | 2009-06-09 | no data | 138 | 242 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Bayao | 143209007 | Construction of 1-unit MPP | 1 | 226000 | 203400 | 22600 | 162720 |  | 17394 | 178720 | 162720 | 16000 | 100% | 91.99% | 76.96% | 79.08% | 100% | 2009-03-31 | no data | 2009-07-02 | 2009-10-07 | no data | 97 | 242 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Camalog | 143209009 | Construction of 24-Units Deep Well | 1 | 629660 | 438933 | 190727 | 438933 |  | 190727 | 629660 | 438933 | 190727 | 100% | 100% | 100% | 100% | 100% | 2008-07-28 | no data | 2008-12-02 | 2009-01-15 | n/a | 44 | 150 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Camalog | 143209009 | Construction of BHS | 1 | 510123 | 357085.8 | 153037.2 | 285668.64 |  | 376037 | 406705.64 | 285668.64 | 121037 | 100% | 32.19% | 245.7% | 79.73% | 100% | 2009-03-31 | no data | 2009-06-01 | 2009-07-31 | n/a | 60 | 159 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Cawagayan | 143209012 | Const. of 1 unit deepwell with water tank | 1 | 493500 | 343896.72 | 149603.28 | 336662.38 |  | 150603.1 | 487265.48 | 336662.38 | 150603.1 | 100% | 100% | 100.7% | 98.74% | 100% | 2007-05-22 | n/a | 2008-02-02 | 2008-04-05 | 2008-06-13 | 63 | 197 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Cawagayan | 143209012 | Construction of 8 Units Intersection Drainage | 1 | 635000 | 464500 | 170500 | 358912.33 |  | 148750 | 507662.33 | 358912.33 | 148750 | 100% | 100% | 87.24% | 79.95% | 100% | 2009-03-31 | no data | 2009-07-25 | 2009-08-30 | n/a | 36 | 210 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Dugpa | 143209011 | Const. of 1 unit village water system | 1 | 455400 | 313545 | 141855 | 307588.86 |  | 142073 | 449661.86 | 307588.86 | 142073 | 100% | 100% | 100.2% | 98.74% | 100% | 2007-05-22 | n/a | 2008-04-10 | 2008-06-20 | no data | 71 | 140 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Dugpa | 143209011 | Construction of 3-Units MPP | 1 | 666942 | 466860.4 | 200081.6 | 368860.4 |  | 158388.4 | 527248.8 | 368860.4 | 158388.4 | 100% | 100% | 79.16% | 79.05% | 100% | 2009-03-31 | no data | 2009-07-02 | 2009-09-20 | no data | 80 | 144 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Junction | 143209020 | Const. of 1 unit Market Center | 1 | 1013935 | 707800 | 306135 | 698697 |  | 302311.14 | 984356 | 698697 | 285659 | 100% | 94.49% | 98.75% | 97.08% | 100% | 2007-05-24 | n/a | 2008-01-15 | 2008-07-31 | 2008-09-15 | 198 | 507 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Kattabogan | 143209010 | Const. of 1 unit DCC | 1 | 579000 | 395216 | 183784 | 385764.24 |  | 179724 | 565488.24 | 385764.24 | 179724 | 100% | 100% | 97.79% | 97.67% | 100% | 2007-05-24 | n/a | 2007-10-25 | 2008-03-31 | 2008-06-12 | 158 | 295 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Kattabogan | 143209010 | Construction of 2 Units Deepwell | 1 | 330000 | 296125 | 33875 | 238125 |  | 10000.18 | 248125 | 238125 | 10000 | 100% | 100% | 29.52% | 75.19% | 100% | 2009-03-31 | no data | 2009-09-07 | 2009-09-30 | no data | 23 | 121 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Limos | 143209014 | Energizing Off Grid through Alternative Power Source | 1 | 937626 | 688031.75 | 249594.25 | 550425.4 |  | 257863.25 | 808288.65 | 550425.4 | 257863.25 | 100% | 100% | 103.3% | 86.21% | 100% | 2008-07-28 | no data | 2009-03-26 | 2009-06-20 | no data | 86 | 136 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Limos | 143209014 | Construction of 1-unit MPP | 1 | 246000 | 171518 | 74482 | 137214.4 |  | 56895.32 | 184696.4 | 137214.4 | 47482 | 100% | 83.46% | 76.39% | 75.08% | 100% | 2009-03-31 | no data | 2009-07-01 | 2009-07-31 | n/a | 30 | 148 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Magaogao | 143209015 | Const. of FMR | 1 | 533500 | 373428 | 160072 | 298742.4 |  | 178972.38 | 468813.97 | 298742.4 | 170071.57 | 100% | 95.03% | 111.8% | 87.88% | 100% | 2007-05-22 | n/a | 2007-08-20 | 2008-02-12 | 2008-06-11 | 176 | 109 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Magaogao | 143209015 | Construction of 1-unit Daycare Center | 1 | 601719 | 421206 | 180513 | 337187.98 |  | 250428 | 487615.98 | 337187.98 | 150428 | 100% | 60.07% | 138.7% | 81.04% | 100% | 2009-03-31 | no data | 2009-07-29 | 2009-09-30 | no data | 63 | 136 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Malagnat | 143209016 | Const. of 2 unit, 2 classrooms elem. sch. bldg. | 1 | 640300 | 429291 | 211009 | 426102.14 |  | 210998.42 | 637100.56 | 426102.14 | 210998.42 | 100% | 100% | 99.99% | 99.5% | 100% | 2007-05-24 | n/a | 2007-09-05 | 2008-02-12 | 2008-06-01 | 160 | 280 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Malagnat | 143209016 | Construction of 1-unit school building | 1 | 500000 | 448881.53 | 51118.47 | 351564.93 |  | 26118.47 | 377683.4 | 351564.93 | 26118.47 | 100% | 100% | 51.09% | 75.54% | 100% | 2009-03-31 | no data | 2009-07-29 | 2009-09-30 | no data | 63 | 150 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Mapaco | 143209018 | Const. of 2 units deepwell & 1u shallow well | 1 | 604400 | 419567.41 | 184832.59 | 390200.77 |  | 184932.59 | 573033.36 | 390200.77 | 182832.59 | 100% | 98.86% | 100.1% | 94.81% | 100% | 2007-05-22 | n/a | 2008-02-22 | 2008-08-10 | 2008-10-03 | 170 | 153 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Mapaco | 143209018 | Construction of 2-Units MPP | 1 | 415000 | 292161 | 122839 | 292161 |  | 142080 | 434241 | 292161 | 142080 | 100% | 100% | 115.7% | 104.6% | 100% | 2008-07-28 | no data | 2008-12-08 | 2009-01-30 | n/a | 53 | 130 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Mapaco | 143209018 | Construction of Pathway with RCPC | 1 | 225000 | 152729.39 | 72270.61 | 122429.39 |  | 62300.75 | 184700 | 122429.39 | 62270.61 | 100% | 99.95% | 86.2% | 82.09% | 100% | 2009-03-31 | no data | 2009-07-01 | 2009-07-31 | n/a | 30 | 102 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Pakawit | 143209019 | Const. of FMR | 1 | 426765.4 | 285867 | 140898.4 | 228693.6 |  | 142080 | 370773.6 | 228693.6 | 142080 | 100% | 100% | 100.8% | 86.88% | 100% | 2007-05-22 | n/a | 2008-04-01 | 2008-07-21 | 2008-10-02 | 111 | 163 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Pakawit | 143209019 | Construction of Village Water System | 1 | 689501 | 611768.47 | 77732.53 | 489414.78 |  | 28781.53 | 518196.31 | 489414.78 | 28781.53 | 100% | 100% | 37.03% | 75.16% | 100% | 2009-03-31 | no data | 2009-07-02 | 2009-12-30 | no data | 181 | 120 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Pinococ | 143209023 | Construction of DCC | 1 | 805932 | 592932 | 213000 | 562315.51 |  | 213000 | 775315.51 | 562315.51 | 213000 | 100% | 100% | 100% | 96.2% | 100% | 2008-07-28 | no data | 2009-01-19 | 2009-06-19 | n/a | 151 | 120 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Sucbot | 143209021 | Const. of 1 unit 2 classrooms elem. sch. bldg. | 1 | 677300 | 468038 | 209262 | 421234.2 |  | 209334.06 | 630568.26 | 421234.2 | 209334.06 | 100% | 100% | 100% | 93.1% | 100% | 2007-05-22 | n/a | 2007-12-01 | 2008-03-29 | 2008-06-11 | 119 | 254 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Sucbot | 143209021 | Construction of 2-units MPP | 1 | 467100 | 327049.97 | 140050.03 | 263254.8 |  | 120050.03 | 383304.83 | 263254.8 | 120050.03 | 100% | 100% | 85.72% | 82.06% | 100% | 2009-03-31 | no data | 2009-07-01 | 2009-09-30 | no data | 91 | 150 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Taga | 143209022 | Construction of 3-Units MPP | 1 | 654000 | 450450 | 203550 | 449578.19 |  | 203550 | 653128.19 | 449578.19 | 203550 | 100% | 100% | 100% | 99.87% | 100% | 2008-07-28 | no data | 2008-12-22 | 2009-01-31 | n/a | 40 | 300 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Taga | 143209022 | Construction of Footpath | 1 | 488000 | 340400 | 147600 | 272320 |  | 127600 | 399920 | 272320 | 127600 | 100% | 100% | 86.45% | 81.95% | 100% | 2009-03-31 | no data | 2009-07-01 | 2009-07-31 | n/a | 30 | 145 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Taggay | 143209024 | Const. of 1 unit Brgy. Health Station | 1 | 667200 | 438534 | 228666 | 427176.65 |  | 228721.57 | 655898.22 | 427176.65 | 228721.57 | 100% | 100% | 100% | 98.31% | 100% | 2007-05-24 | n/a | 2007-09-05 | 2008-02-09 | 2008-06-02 | 157 | 159 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Taggay | 143209024 | Construction of 2-units MPP | 1 | 476287 | 333676.75 | 142610.25 | 266941.4 |  | 96610.25 | 363551.65 | 266941.4 | 96610.25 | 100% | 100% | 67.74% | 76.33% | 100% | 2009-03-31 | no data | 2009-07-01 | 2009-07-31 | n/a | 30 | 159 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Wagud | 143209008 | Construction of Irrigation Canal | 1 | 890000 | 567925 | 322075 | 498038.06 |  | 324761.99 | 777402.1 | 454327.1 | 323075 | 91.22% | 99.48% | 100.8% | 87.35% | 100% | 2008-07-28 | no data | 2009-03-10 | 2009-05-30 | n/a | 81 | 105 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Anggacan | 143214001 | Butubut Village Water System | 1 | 499167.5 | 353524 | 145643.5 | 350571.35 |  | 155620.5 | 506191.85 | 350571.35 | 155620.5 | 100% | 100% | 106.9% | 101.4% | 100% | 2006-05-25 | 2006-08-16 | 2007-06-02 | 2008-08-03 | no data | 428 | 48 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Anggacan | 143214001 | Construction of Multi-purpose Pavement | 1 | 415690 | 277203 | 138487 | 221762.4 |  | 66418.39 | 282262.4 | 221762.4 | 60500 | 100% | 91.09% | 47.96% | 67.9% | 100% | 2009-03-13 | no data | 2009-07-20 | 2009-11-30 | no data | 133 | 53 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Anggacan Sur | 143214014 | Anggacan Sur Concrete Slab Footbridge | 1 | 276893.5 | 194392 | 82501.5 | 192767.66 |  | 109137 | 288488.65 | 179351.65 | 109137 | 93.04% | 100% | 132.3% | 104.2% | 100% | 2006-05-25 | 2006-08-16 | 2008-06-20 | 2008-08-03 | no data | 44 | 178 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Anggacan Sur | 143214014 | Cosntruction of Footstep/Drainage Canal | 1 | 476551 | 340003.2 | 136547.8 | 270405.2 |  | 87054 | 330405.2 | 270405.2 | 60000 | 100% | 68.92% | 63.75% | 69.33% | 100% | 2009-03-13 | no data | 2009-07-20 | 2009-11-30 | n/a | 133 | 41 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Babbanoy | 143214002 | Construction of Sewerage and Water System | 1 | 1799012 | 1208243.2 | 590768.8 | 968070 |  | 556268.8 | 1506120 | 968070 | 538050 | 100% | 96.72% | 94.16% | 83.72% | 100% | 2009-03-13 | no data | 2009-07-20 | completed as built | n/a | #VALUE! | 92 | completed as built | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Dacalan | 143214003 | CIS Improvement | 1 | 1001820 | 728000 | 273820 | 728000 |  | 335626.38 | 1062626.38 | 728000 | 334626.38 | 100% | 99.7% | 122.6% | 106.1% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-15 | 2006-12-14 | no data | 486 | 81 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Dacalan | 143214003 | Construction of Bila-o Slab Footbridge | 1 | 373910.5 | 248953 | 124957.5 | 199162.4 |  | 80802.5 | 196193.5 | 196193.5 | 0 | 98.51% | 0% | 64.66% | 52.47% | 100% | 2009-03-13 | no data | 2009-07-25 | 2009-12-02 | n/a | 130 | 79 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Dupligan | 143214015 | Darulog-Bawac Farm to Market Road Improvement | 1 | 2614363.29 | 1644517.8 | 969845.49 | 1644517.8 |  | 1471517.22 | 3114998.8 | 1643481.58 | 1471517.22 | 99.94% | 100% | 151.7% | 119.1% | 100% | 2006-05-25 | 2006-08-16 | 2007-05-12 | 2008-11-10 | no data | 548 | 318 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Gaang | 143214004 | Cable Bridge | 1 | 1067392.94 | 541500 | 525892.94 | 541500 |  | 487473.95 | 1027856.54 | 541500 | 486356.54 | 100% | 99.77% | 92.69% | 96.3% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-20 | 2007-03-03 | no data | 560 | 149 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Ga-ang | 143214004 | Construction of Communal Septic Tank | 1 | 437476 | 313489.6 | 123986.4 | 252129.6 |  | 98186.4 | 307836 | 224336 | 83500 | 88.98% | 85.04% | 79.19% | 70.37% | 100% | 2009-03-13 | no data | 2008-07-20 | 2009-11-30 | n/a | 498 | 87 |  | 1
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Lay-asan | 143214016 | Multi-Purpose Pavement | 1 | 739419 | 540000 | 199419 | 540000 |  | 117554 | 629763.76 | 540000 | 89763.76 | 100% | 76.36% | 58.95% | 85.17% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-02 | 2007-01-31 | no data | 547 | 99 |  | 1
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Lower Lubo | 143214007 | Foot Bridge | 1 | 1159603 | 661500 | 498103 | 529200 |  | 371926.62 | 901126.62 | 529200 | 371926.62 | 100% | 100% | 74.67% | 77.71% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-03 | n/a | n/a | #VALUE! | 375 | completed as built | 1
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Lower Mangali | 143214005 | Lower Mangali Micro Hydro Electric Power Generation | 1 | 1520378.2 | 903324.7 | 617053.5 | 903324.7 |  | 804050.8 | 1598938.54 | 894887.74 | 704050.8 | 99.07% | 87.56% | 130.3% | 105.2% | 100% | 2006-05-25 | 2006-08-16 | 2007-06-04 | completed as built | n/a | #VALUE! | 110 | completed as built | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Lower Taloctoc | 143214006 | Kamanga-Pattikian Communal Irrigation System | 1 | 733864.5 | 523037 | 210827.5 | 523037 |  | 256361 | 674790 | 418429 | 256361 | 80% | 100% | 121.6% | 91.95% | 100% | 2006-05-25 | 2006-08-16 | 2007-07-10 | 2008-10-02 | no data | 450 | 71 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Mabaca | 143214009 | CIS Improvement | 1 | 862158.45 | 712500 | 149658.45 | 641250 |  | 68835 | 706860.43 | 641250 | 65610.43 | 100% | 95.32% | 45.99% | 81.99% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-15 | 2009-02-21 | no data | 1286 | 102 | completed as built | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Mangali Centro | 143214017 | Centro Mangali School Building | 1 | 497722.13 | 326087.96 | 171634.17 | 326087.96 |  | 353974.09 | 514664.55 | 326087.96 | 188576.59 | 100% | 53.27% | 206.2% | 103.4% | 100% | 2006-05-25 | 2006-08-16 | 2007-06-20 | 2008-09-06 | no data | 444 | 54 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Mangali Centro | 143214017 | Construction of Drainage Canal | 1 | 432395 | 285731.5 | 146663.5 | 228147.25 |  | 87478.78 | 307547.25 | 228147.25 | 79400 | 100% | 90.76% | 59.65% | 71.13% | 100% | 2009-03-13 | no data | 2009-07-20 | 2009-11-30 | no data | 133 | 87 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Pangol | 143214010 | Pangol Farm to Market Road Improvement | 1 | 1427532 | 997500 | 430032 | 997500 |  | 360470 | 1357970 | 997500 | 360470 | 100% | 100% | 83.82% | 95.13% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-03 | 2007-03-05 | no data | 579 | 114 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Poblacion | 143214011 | Water System | 1 | 603270.5 | 466000 | 137270.5 | 466000 |  | 175718 | 641718 | 466000 | 175718 | 100% | 100% | 128% | 106.4% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-17 | 2006-10-03 | no data | 412 | 65 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Poblacion | 143214011 | Construction of Pigpen and Water Works | 1 | 1249638.44 | 987523.44 | 262115 | 789292 |  | 136476.98 | 925112.75 | 789292 | 135820.75 | 100% | 99.52% | 52.07% | 74.03% | 100% | 2009-03-13 | no data | 2009-07-20 | 2010-01-15 | no data | 179 | 75 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Upper Lubo | 143214008 | Foot Bridge | 1 | 246170 | 153000 | 93170 | 153000 |  | 94170 | 247170 | 153000 | 94170 | 100% | 100% | 101.1% | 100.4% | 100% | 2005-02-25 | 2005-05-13 | 2005-08-20 | 2006-05-31 | no data | 284 | 226 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Upper Lubo | 143214008 | Dorag-Ambatkan Communal Irrigation System | 1 | 450490.04 | 231664.54 | 218825.5 | 231664.54 |  | 219485.5 | 451150.04 | 231664.54 | 219485.5 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-05-25 | 2006-08-16 | 2007-07-10 | 2007-10-10 | no data | 92 | 92 |  | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Upper Lubo | 143214008 | Construction of Sewerage and Water System | 1 | 1367656 | 909735.6 | 457920.4 | 727788.48 |  | 422620 | 1149788.48 | 727788.48 | 422000 | 100% | 99.85% | 92.29% | 84.07% | 100% | 2009-03-13 | no data | 2009-07-20 | completed as built | n/a | #VALUE! | 98 | completed as built | 1 | LUZON
CAR | 14 | Kalinga | 1432 | Tanudan | 143214 | Upper Taloctoc | 143214013 | Dinattagan-Tappo Communal Irrigation System | 1 | 881423 | 623452 | 257971 | 622743.6 |  | 772982 | 1271716.85 | 514378.25 | 757338.6 | 82.6% | 97.98% | 299.6% | 144.3% | 100% | 2006-05-25 | 2006-08-16 | 2007-06-04 | 2008-10-08 | no data | 492 | 68 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Alunogan | 144405001 | Impr. Of Yebyeb-Apat CIS | 1 | 782100 | 575609 | 206491 | 541978.73 |  | 172024.39 | 714003.12 | 541978.73 | 172024.39 | 100% | 100% | 83.31% | 91.29% | 100% | 2006-06-19 | 2006-10-17 | 2007-06-11 | 2007-08-13 | 2008-03-19 | 63 | 129 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Alunogan | 144405001 | Improvement of Tuchoy-Agayam CIS | 1 | 780652 | 540982 | 239670 | 528369.99 |  | 239670 | 768039.99 | 528369.99 | 239670 | 100% | 100% | 100% | 98.38% | 100% | 2008-08-05 | n/a | 2008-10-15 | 2008-12-30 | 2008-12-30 | 76 | 119 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Balangao | 144405002 | Impr. of Acho-ot Communal Irrigation System | 1 | 722943 | 505420 | 217523 | 495851.63 |  | 216843 | 712694.63 | 495851.63 | 216843 | 100% | 100% | 99.69% | 98.58% | 100% | 2007-12-19 | n/a | 2007-11-16 | 2008-03-26 | 2008-05-26 | 131 | 176 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Banao | 144405003 | Const. of Pappatay Footbridge & Footpath | 1 | 151000 | 79723 | 71277 | 70294.4 |  | 71277 | 141571.4 | 70294.4 | 71277 | 100% | 100% | 100% | 93.76% | 100% | 2006-06-19 | 2006-10-17 | 2007-03-20 | 2007-04-14 | 2008-03-15 | 25 | 71 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Banao | 144405003 | Improvement of Manangar Amfusac CIS | 1 | 503547 | 348367 | 155180 | 337428.63 |  | 155180 | 492608.63 | 337428.63 | 155180 | 100% | 100% | 100% | 97.83% | 100% | 2008-08-05 | n/a | 2008-10-13 | 2008-12-12 | 2008-12-12 | 60 | 73 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Banawal | 144405004 | Day Care Center Const. | 1 | 775258 | 547478 | 227780 | 539720.01 |  | 227780 | 767500.01 | 539720.01 | 227780 | 100% | 100% | 100% | 99% | 100% | 2007-12-19 | n/a | 2008-08-15 | 2008-10-11 | 2008-10-28 | 57 | 327 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Butac | 144405005 | Const. of Butac Water System | 1 | 651500 | 351960 | 299540 | 351960 |  | 299540 | 651500 | 351960 | 299540 | 100% | 100% | 100% | 100% | 100% | 2006-06-19 | 2006-10-17 | 2007-07-27 | 2007-12-27 | 2008-02-03 | 153 | 113 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Butac | 144405005 | Improvement of Butac to Opet Footpath | 1 | 805020 | 553830 | 251190 | 532932.9 |  | 250990 | 783922.9 | 532932.9 | 250990 | 100% | 100% | 99.92% | 97.38% | 100% | 2008-08-05 | n/a | 2008-10-20 | 2008-12-15 | 2008-12-15 | 56 | 113 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Maducayan | 144405006 | Improvement of Saliok-Maducayan Road | 1 | 1157070 | 688169 | 468901 | 680174.4 |  | 462831 | 1143005.4 | 680174.4 | 462831 | 100% | 100% | 98.71% | 98.78% | 100% | 2006-06-19 | 2006-10-17 | 2007-07-09 | 2008-03-26 | 2008-05-24 | 261 | 61 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Maducayan | 144405006 | Improvement of Maducayan FMR | 1 | 792498.71 | 554385 | 238113.71 | 537509.85 |  | 238115 | 775624.85 | 537509.85 | 238115 | 100% | 100% | 100% | 97.87% | 100% | 2007-12-19 | n/a | 2008-04-14 | 2008-06-03 | 2008-06-21 | 50 | 61 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Poblacion | 144405007 | Impr. of Poblacion Footpath | 1 | 770458 | 536758 | 233700 | 508749.09 |  | 246315.24 | 755064.33 | 508749.09 | 246315.24 | 100% | 100% | 105.4% | 98% | 100% | 2007-12-19 | n/a | 2007-11-26 | 2008-04-19 | 2008-05-20 | 145 | 268 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Pudo | 144405011 | Impr. Of Pudo-Ogtong-Naulingan-Awayan Footpath | 1 | 494500 | 397852 | 96648 | 370706.55 |  | 87140 | 457846.55 | 370706.55 | 87140 | 100% | 100% | 90.16% | 92.59% | 100% | 2006-06-19 | 2006-10-17 | 2007-02-26 | 2007-07-31 | 2008-03-17 | 155 | 125 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Pudo | 144405011 | Improvement of Lamayan Naulingan Tomfiar Footpath | 1 | 765201 | 558584.5 | 206616.5 | 542814.3 |  | 206616.5 | 749430.8 | 542814.3 | 206616.5 | 100% | 100% | 100% | 97.94% | 100% | 2008-08-05 | n/a | 2008-10-11 | 2008-12-13 | 2008-12-13 | 63 | 129 |  | 1
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Saliok | 144405008 | Construction of Saliok Water System | 1 | 1178743 | 806001 | 372742 | 806001 |  | 372742.4 | 1178743.4 | 806001 | 372742.4 | 100% | 100% | 100% | 100% | 100% | 2008-08-05 | n/a | 2008-11-27 | 2008-12-28 | 2008-12-28 | 31 | 123 |  | 1
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Sta. Isabel | 144405009 | Const. of 1 Unit National High School Bldg. | 1 | 1163000 | 756797 | 406203 | 756797 |  | 406204 | 1163001 | 756797 | 406204 | 100% | 100% | 100% | 100% | 100% | 2006-06-19 | 2006-10-17 | 2007-06-12 | 2008-04-20 | 2008-05-13 | 313 | 108 |  | 1
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Sta. Isabel | 144405009 | Const. of 1 unit school bldg. | 1 | 632469.01 | 442037 | 190432.01 | 437064.54 |  | 210332 | 647396.54 | 437064.54 | 210332 | 100% | 100% | 110.4% | 102.4% | 100% | 2007-12-19 | n/a | 2008-07-15 | 2008-11-16 | 2008-11-18 | 124 | 108 |  | 1
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Tonglayan | 144405010 | Improvement of Paparong-Tonglayan & Manangar Tonglayan CIS | 1 | 706000 | 449890 | 256110 | 410013 |  | 256110 | 666123 | 410013 | 256110 | 100% | 100% | 100% | 94.35% | 100% | 2006-06-19 | 2006-10-17 | 2007-07-02 | 2007-08-15 | 2008-03-01 | 44 | 202 |  | 1
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Tonglayan | '144405010 | Improvement of Penged-porah CIS | 1 | 940000 | 658000 | 282000 | 644886 |  | 282000 | 926886 | 644886 | 282000 | 100% | 100% | 100% | 98.6% | 100% | 2007-12-19 | n/a | 2008-04-15 | 2008-09-06 | 2008-09-10 | 144 | 202 |  | 1
CAR | 14 | Mountain Province | 1444 | Natonin | 144405 | Tonglayan | 144405010 | Improvement of Ufo-ub Pora Concrete Footpath | 1 | 710000 | 490000 | 220000 | 470594 |  | 220000 | 690594 | 470594 | 220000 | 100% | 100% | 100% | 97.27% | 100% | 2008-08-05 | n/a | 2008-10-21 | 2008-12-19 | 2008-12-29 | 59 | 205 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Anonat | 144406001 | Construction of FMR | 1 | 1379100 | 864900 | 514200 | 864900 |  | 615200 | 1480100 | 864900 | 615200 | 100% | 100% | 119.6% | 107.3% | 100% | 2006-06-08 | 2006-07-21 | 2006-11-21 | 2008-11-30 | no data | 740 | 403 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Anonat | 144406001 | Improvement of Dannal FMR | 1 | 294882.95 | 170000 | 124882.95 | 136000 |  | 640000 | 256000 | 136000 | 120000 | 100% | 18.75% | 512.5% | 86.81% | 100% | 2008-09-03 | no data | 2009-03-12 | 2009-05-28 | no data | 77 | 403 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bacarri | 144406002 | Const. of MPP | 1 | 547596 | 285100 | 262496 | 285100 |  | 366580.2 | 651680.2 | 285100 | 366580.2 | 100% | 100% | 139.7% | 119% | 100% | 2006-06-08 | 2006-07-21 | 2006-11-21 | 2007-03-30 | 2008-05-30 | 129 | 336 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bacarri | 144406002 | Const. of Water System | 1 | 587099.69 | 350000 | 237099.69 | 350000 |  | 238099.69 | 588099.69 | 350000 | 238099.69 | 100% | 100% | 100.4% | 100.2% | 100% | 2007-07-24 | n/a | 2008-01-25 | 2008-06-25 | no data | 152 | 344 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bacarri | 144406002 | Construction of 2 Units MPP | 1 | 751085.67 | 448000 | 303085.67 | 358400 |  | 284000 | 642400 | 358400 | 284000 | 100% | 100% | 93.7% | 85.53% | 100% | 2008-09-03 | no data | 2008-11-28 | 2009-04-30 | n/a | 153 | 206 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bananao | 144406003 | Improvement of Water System | 1 | 848779.13 | 482000 | 366779.13 | 482000 |  | 368859.13 | 850859.13 | 482000 | 368859.13 | 100% | 100% | 100.6% | 100.2% | 100% | 2007-07-24 | n/a | 2008-02-25 | 2008-03-15 | 2008-05-06 | 19 | 280 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bananao | 144406003 | Construction of 1 Unit MPP | 1 | 561528.48 | 280000 | 281528.48 | 224000 |  | 282994.09 | 426994.09 | 224000 | 202994.09 | 100% | 71.73% | 100.5% | 76.04% | 100% | 2008-09-03 | no data | 2008-11-23 | 2008-12-30 | no data | 37 | 259 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bantay | 144406004 | Const. of 2 units MPP | 1 | 668326.61 | 300000 | 368326.61 | 285960.4 |  | 369326.61 | 655287.01 | 285960.4 | 369326.61 | 100% | 100% | 100.3% | 98.05% | 100% | 2007-07-24 | n/a | 2008-02-15 | 2008-07-15 | no data | 151 | 276 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bantay | 144406004 | Improvement of Bato-Pagga FMR | 1 | 476861.27 | 250000 | 226861.27 | 200000 |  | 226861.27 | 426861.27 | 200000 | 226861.27 | 100% | 100% | 100% | 89.51% | 100% | 2008-09-03 | no data | 2009-02-17 | 2009-03-30 | n/a | 41 | 318 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bunot | 144406006 | Const. of MPP | 1 | 1205950 | 800000 | 405950 | 791048.8 |  | 323860.9 | 1114909.7 | 791048.8 | 323860.9 | 100% | 100% | 79.78% | 92.45% | 100% | 2006-06-08 | 2006-07-21 | 2006-11-21 | 2007-07-28 | no data | 249 | 304 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bunot | 144406006 | Improvement of Bacarri-Bunot FMR | 1 | 666795.81 | 355000 | 311795.81 | 355000 |  | 312795.89 | 667795.89 | 355000 | 312795.89 | 100% | 100% | 100.3% | 100.1% | 100% | 2007-07-24 | n/a | 2008-01-25 | 2008-06-25 | no data | 152 | 314 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Bunot | 144406006 | Construction of 2 Units MPP | 1 | 790756.13 | 455000 | 335756.13 | 449232 |  | 335756.13 | 784988.13 | 449232 | 335756.13 | 100% | 100% | 100% | 99.27% | 100% | 2008-09-03 | no data | 2008-11-24 | 2008-12-30 | n/a | 36 | 190 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Buringal | 144406007 | Improvement of FMR | 1 | 1403767 | 750000 | 653767 | 600000 |  | 636234 | 1216834 | 600000 | 616834 | 100% | 96.95% | 97.32% | 86.68% | 100% | 2006-06-08 | 2006-07-21 | 2006-11-21 | 2009-03-04 | no data | 834 | 324 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Buringal | 144406007 | Improvement Of Buringal FMR | 1 | 442975.38 | 220000 | 222975.38 | 176000 |  | 180000 | 356000 | 176000 | 180000 | 100% | 100% | 80.73% | 80.37% | 100% | 2008-09-03 | no data | 2009-03-15 | 2009-05-15 | no data | 61 | 290 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Butigue | 144406005 | Const. of 2 units MPP | 1 | 657774.72 | 250000 | 407774.72 | 250000 |  | 407374.72 | 657374.72 | 250000 | 407374.72 | 100% | 100% | 99.9% | 99.94% | 100% | 2007-07-24 | n/a | 2008-01-25 | 2008-02-25 | 2008-05-13 | 31 | 250 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Butigue | 144406005 | Construction of Water System | 1 | 850000 | 500000 | 350000 | 400000 |  | 270000 | 670000 | 400000 | 270000 | 100% | 100% | 77.14% | 78.82% | 100% | 2008-09-03 | no data | 2009-04-15 | 2009-08-30 | n/a | 137 | 250 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Palitod | 144406008 | Const. of 4 units MPP | 1 | 1083638.77 | 590000 | 493638.77 | 590000 |  | 495893.49 | 1085893.49 | 590000 | 495893.49 | 100% | 100% | 100.5% | 100.2% | 100% | 2007-07-24 | n/a | 2008-02-01 | 2008-03-25 | no data | 53 | 480 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Palitod | 144406008 | Construction of 1 Unit MPP | 1 | 353395.51 | 127000 | 226395.51 | 101600 |  | 183395.51 | 284995.51 | 101600 | 183395.51 | 100% | 100% | 81.01% | 80.64% | 100% | 2008-09-03 | no data | 2008-11-30 | 2008-12-30 | no data | 30 | 254 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Poblacion | 144406009 | Const. of 2 units MPP | 1 | 882466.74 | 380000 | 502466.74 | 373000 |  | 554346.76 | 883092.24 | 373000 | 510092.24 | 100% | 92.02% | 110.3% | 100.1% | 100% | 2007-07-24 | n/a | 2008-01-25 | 2008-02-25 | 2008-05-09 | 31 | 309 |  | 1
CAR | 14 | Mountain Province | 1444 | Paracelis | 144406 | Poblacion | 144406009 | Improvement of Marrat-Baba FMR | 1 | 422170.2 | 250000 | 172170.2 | 249489.82 |  | 172170.2 | 421660.02 | 249489.82 | 172170.2 | 100% | 100% | 100% | 99.88% | 100% | 2008-09-03 | no data | 2008-12-02 | 2008-12-30 | no data | 28 | 317 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Anabel | 144408001 | Improvement of Mannab-Lilit Road | 1 | 647724 | 471429 | 176295 | 471429 |  | 176295 | 647724 | 471429 | 176295 | 100% | 100% | 100% | 100% | 100% | 2005-01-31 | 2005-03-22 | 2005-05-24 | 2005-11-14 | 2005-11-20 | 174 | 129 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Anabel | 144408001 | Completion of Machomay Foot Bridge | 1 | 215350 | 150000 | 65350 | 150000 |  | 86205 | 236205 | 150000 | 86205 | 100% | 100% | 131.9% | 109.7% | 100% | 2005-12-20 | 2006-03-23 | 2006-07-15 | 2006-10-31 | no data | 108 | 126 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Anabel | 144408001 | Improvement of Ampakchad-Sacko CIS | 1 | 232747.29 | 132098.61 | 100648.68 | 132098.61 |  | 100648.68 | 232747.29 | 132098.61 | 100648.68 | 100% | 100% | 100% | 100% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-06-02 | no data | 48 | 136 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Bekigan | 144408004 | Chadchaingan-Kapitak Irrigation System | 1 | 848987 | 618460 | 230527 | 618100 |  | 173255.5 | 791355.5 | 618100 | 173255.5 | 100% | 100% | 75.16% | 93.21% | 100% | 2004-02-20 | 2004-02-23 | 2004-03-27 | 2004-10-15 | no data | 202 | 78 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Bekigan | 144408004 | Const. of Kabobo-Faang Communal Irrigation | 1 | 634091 | 463699 | 170392 | 463699 |  | 175392 | 639091 | 463699 | 175392 | 100% | 100% | 102.9% | 100.8% | 100% | 2005-01-31 | 2005-03-22 | 2005-06-25 | 2005-09-15 | 2005-09-28 | 82 | 90 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Bekigan | 144408004 | Anoling-Marwa CIS Improvement | 1 | 434253 | 320613 | 113640 | 288551.3 |  | 113640 | 402191.3 | 288551.3 | 113640 | 100% | 100% | 100% | 92.62% | 100% | 2005-12-20 | 2006-03-23 | 2006-07-20 | 2007-02-26 | no data | 221 | 88 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Bekigan | 144408004 | Improvement of Liang-Dauran CIS | 1 | 635240.05 | 437999.35 | 197240.7 | 437832.07 |  | 197240.7 | 635072.77 | 437832.07 | 197240.7 | 100% | 100% | 100% | 99.97% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-06-30 | no data | 76 | 95 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Belwang | 144408002 | Improvement of Toktok-Chinakragan Communal Irrigation System | 1 | 784043 | 550000 | 234043 | 550000 |  | 234353 | 784353 | 550000 | 234353 | 100% | 100% | 100.1% | 100% | 100% | 2005-01-31 | 2005-03-22 | 2005-05-24 | 2006-05-22 | 2006-02-05 | 363 | 134 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Belwang | 144408002 | Maba-ew High School Building Construction | 1 | 612563 | 460110 | 152453 | 460110 |  | 152453 | 612563 | 460110 | 152453 | 100% | 100% | 100% | 100% | 100% | 2005-12-20 | 2006-03-23 | 2006-07-20 | 2007-03-30 | no data | 253 | 112 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Belwang | 144408002 | Improvement of Chinakragan-Forayang CIS | 1 | 612058.35 | 400113.08 | 211945.27 | 400113.08 |  | 211945.27 | 612058.35 | 400113.08 | 211945.27 | 100% | 100% | 100% | 100% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-06-01 | no data | 47 | 153 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Betwagan | 144408003 | Improvement of Shaliwater Chittar CIS | 1 | 692636 | 425464 | 267172 | 382917.6 |  | 269702 | 652619.6 | 382917.6 | 269702 | 100% | 100% | 100.9% | 94.22% | 100% | 2005-01-31 | 2005-03-22 | 2005-06-30 | 2005-12-10 | 2005-12-15 | 163 | 250 | 3rd tranche will not be requested | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Betwagan | 144408003 | Improvement of Tabrak-Sabfang Barangay Road | 1 | 501227 | 399998 | 101229 | 399998 |  | 101226 | 501224 | 399998 | 101226 | 100% | 100% | 100% | 100% | 100% | 2005-12-20 | 2006-03-23 | 2006-09-01 | 2007-02-16 | 2007-10-12 | 168 | 105 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Betwagan | 144408003 | Construction of Tengrey-Chagchag foot trail | 1 | 370637.32 | 182637.32 | 188000 | 182637.32 |  | 192000 | 374637.32 | 182637.32 | 192000 | 100% | 100% | 102.1% | 101.1% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-06-01 | no data | 47 | 404 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Demang | 144408008 | Magoron Flood/Erosion Control | 1 | 1071975 | 635585 | 436390 | 635585 |  | 249600 | 885185 | 635585 | 249600 | 100% | 100% | 57.2% | 82.58% | 100% | 2004-02-20 | 2004-02-23 | 2004-03-23 | 2004-08-10 | 2004-09-15 | 140 | 201 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Demang | 144408008 | Upgrading of Demang-Poblacion Potable Water System | 1 | 2132815.19 | 1507511.09 | 625304.1 | 1507423.29 |  | 627460.1 | 2134883.39 | 1507423.29 | 627460.1 | 100% | 100% | 100.3% | 100.1% | 100% | 2008-12-19 | n/a | 2009-04-28 | 2009-12-30 | no data | 246 | 168 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Poblacion | 144408005 | Tap-ag Day Care Center | 1 | 705278 | 467734 | 237544 | 467734 |  | 227530 | 695264 | 467734 | 227530 | 100% | 100% | 95.78% | 98.58% | 100% | 2004-02-20 | 2004-02-23 | 2004-03-23 | 2004-08-10 | 2004-09-15 | 140 | 60 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Poblacion | 144408005 | CIS Improvement | 1 | 203997 | 120164 | 83833 | 120164 |  | 84833 | 204997 | 120164 | 84833 | 100% | 100% | 101.2% | 100.5% | 100% | 2005-01-31 | 2005-03-22 | 2005-09-26 | 2005-12-05 | 2005-12-10 | 70 | 80 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Poblacion | 144408005 | Makamkamar-Sangey Mun. Road Improvement | 1 | 692250 | 508901 | 183349 | 508901 |  | 186076.46 | 694977.46 | 508901 | 186076.46 | 100% | 100% | 101.5% | 100.4% | 100% | 2005-12-20 | 2006-03-23 | 2006-07-20 | 2007-02-21 | no data | 216 | 228 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Poblacion | 144408005 | Improvement of Fangek-Faragtey Gingaw Footpath | 1 | 429591.03 | 300739.53 | 128851.5 | 300739.53 |  | 113699 | 414438.53 | 300739.53 | 113699 | 100% | 100% | 88.24% | 96.47% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-06-30 | no data | 76 | 257 |  | 1
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Sacasacan | 144408006 | Maballi At-ator Village Water System | 1 | 916925 | 677453 | 239472 | 677453 |  | 280358.05 | 957811.05 | 677453 | 280358.05 | 100% | 100% | 117.1% | 104.5% | 100% | 2004-02-20 | 2004-02-23 | 2004-04-14 | 2004-09-20 | no data | 159 | 123 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Sacasacan | 144408006 | Improvement of Fansag-Cabacongan Communal Irrigation System | 1 | 534060 | 369244.2 | 164815.8 | 369244.18 |  | 164815.8 | 534059.98 | 369244.18 | 164815.8 | 100% | 100% | 100% | 100% | 100% | 2005-01-31 | 2005-03-22 | 2005-05-20 | 2005-09-15 | 2005-09-29 | 118 | 123 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Sacasacan | 144408006 | Kok-o-Rong-odan Road Improvement | 1 | 524348 | 378598 | 145750 | 378598 |  | 145754.64 | 524352.64 | 378598 | 145754.64 | 100% | 100% | 100% | 100% | 100% | 2005-12-20 | 2006-03-23 | 2006-07-15 | 2006-10-31 | 2006-12-07 | 108 | 105 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Sacasacan | 144408006 | Improvement of Sacasacan Barangay Road | 1 | 1212143.1 | 844878.41 | 367264.69 | 837725.08 |  | 369489.69 | 1207214.77 | 837725.08 | 369489.69 | 100% | 100% | 100.6% | 99.59% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-08-30 | no data | 137 | 118 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Saclit | 144408007 | Improvement of Community Sanitary Drainage System | 1 | 285947 | 181780 | 104167 | 181780 |  | 104167 | 285947 | 181780 | 104167 | 100% | 100% | 100% | 100% | 100% | 2005-12-20 | 2006-03-23 | 2006-07-15 | 2006-10-31 | no data | 108 | 130 |  | 1 | LUZON
CAR | 14 | Mountain Province | 1444 | Sadanga | 144408 | Saclit | 144408007 | Construction of Abfaweg Concrete Footbridge with Concrete Pathway | 1 | 358594.87 | 194022.61 | 164572.26 | 188759.91 |  | 164572.26 | 353332.17 | 188759.91 | 164572.26 | 100% | 100% | 100% | 98.53% | 100% | 2008-12-19 | n/a | 2009-04-15 | 2009-06-30 | no data | 76 | 126 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Cahayagan | 160204001 | Const. of Water System L-II (Pump Driven) | 1 | 1341749.4 | 943679.4 | 398070 | 943679.4 | 3rd Tranche | 474312.25 | 1417991.65 | 943679.4 | 474312.25 | 100% | 100% | 119.2% | 105.7% | 100% | 2003-11-04 | 2003-12-10 | 2004-02-06 | 2004-07-30 | 2004-03-06 | 175 | 396 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Gosoon | 160204002 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1222072 | 899740 | 322332 | 899740 | 3rd Tranche | 280326.11 | 1180066.11 | 899740 | 280326.11 | 100% | 100% | 86.97% | 96.56% | 100% | 2006-03-10 | 2006-03-18 | 2006-06-26 | 2006-11-15 | no data | 142 | 318 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Manoligao | 160204004 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1520506 | 639162 | 881344 | 575246 | 2nd Tranche | 150182.4 | 725428.4 | 575246 | 150182.4 | 100% | 100% | 17.04% | 47.71% | 100% | 2006-03-10 | 2006-03-18 | 2006-06-16 | 2006-10-01 | 2006-12-29 | 107 | 320 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Poblacion | 160204009 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1836607.6 | 861098 | 975509.6 | 861098 | 3rd Tranche | 277569.6 | 1138667.6 | 861098 | 277569.6 | 100% | 100% | 28.45% | 62% | 100% | 2006-03-10 | 2006-03-18 | 2006-06-26 | 2006-11-15 | no data | 142 | 826 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Rojales | 160204010 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1295889 | 844580 | 451309 | 844580 | 3rd Tranche | 521188.9 | 1365768.9 | 844580 | 521188.9 | 100% | 100% | 115.5% | 105.4% | 100% | 2005-03-28 | 2005-07-26 | 2005-10-01 | 2006-02-20 | 2006-08-28 | 142 | 320 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | San Agustin | 160204011 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1329418 | 891682 | 437736 | 891682 | 3rd Tranche | 490763.68 | 1382445.68 | 891682 | 490763.68 | 100% | 100% | 112.1% | 104% | 100% | 2005-03-28 | 2005-07-26 | 2005-09-21 | 2006-02-10 | 2006-08-28 | 142 | 331 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Tagcatong | 160204012 | Const. of Water System L-II (Gravity Driven) | 1 | 1071313.38 | 802273.65 | 269039.73 | 802273.65 | 3rd Tranche | 338239.13 | 1140512.78 | 802273.65 | 338239.13 | 100% | 100% | 125.7% | 106.5% | 100% | 2003-11-04 | 2003-12-10 | 2004-02-06 | 2004-07-30 | 2004-03-06 | 175 | 610 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Tagcatong | 160204012 | Const. of 1 Unit Brgy. Health Station | 1 | 515462 | 398779 | 116683 | 398779 | 3rd Tranche | 125156 | 523935 | 398779 | 125156 | 100% | 100% | 107.3% | 101.6% | 100% | 2005-03-28 | 2005-07-26 | 2005-10-28 | 2005-12-27 | 2006-02-23 | 60 | 610 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Carmen | 160204 | Vinapor | 160204014 | Const. of 2 Class Room High School Building | 1 | 968751.55 | 654046.95 | 314704.6 | 654046.945 | 3rd Tranche | 389248.61 | 1043295.555 | 654046.945 | 389248.61 | 100% | 100% | 123.7% | 107.7% | 100% | 2003-11-04 | 2003-12-10 | 2004-02-04 | 2004-06-30 | 2004-07-30 | 147 | 341 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | A. Beltran | 160205003 | 1 CL Elem School Building | 1 | 680460 | 517149 | 163311 | 479135.79 | 3rd Tranche | 190985.84 | 670121.63 | 479135.79 | 190985.84 | 100% | 100% | 116.9% | 98.48% | 100% | no data | no data | 2009-03-16 | 2009-06-16 | 2009-06-22 | 92 | 270 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | A. Beltran (Camalig) | 160205003 | Construction of 1 unit Day Care Center | 1 | 523732.47 | 340069.15 | 183663.32 | 340069.15 | 3rd Tranche | 191383.83 | 531452.98 | 340069.15 | 191383.83 | 100% | 100% | 104.2% | 101.5% | 100% | 2005-08-29 | 2005-09-01 | 2005-11-28 | 2006-02-11 | 2006-06-22 | 75 | 159 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Baleguian | 160205001 | Multi-Purpose Center | 1 | 1324354 | 1006509 | 317845 | 1006509 | 3rd Tranche | 318386.63 | 1324895.63 | 1006509 | 318386.63 | 100% | 100% | 100.2% | 100% | 100% | no data | no data | 2009-03-16 | 2009-06-09 | 2009-06-15 | 85 | 435 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Bangonay | 160205002 | Road Rehabilitation | 1 | 2430666.09 | 1261727 | 1168939.09 | 1261727 | 3rd Tranche | 1010890 | 2272617 | 1261727 | 1010890 | 100% | 100% | 86.48% | 93.5% | 100% | 2003-04-25 | 2003-07-09 | 2003-09-04 | 2004-08-04 | 2005-10-26 | 335 | 479 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Bangonay | 160205002 | 2 CL Elem School Building | 1 | 1136660 | 863861 | 272799 | 777474.9 | 2nd Tranche | 275425.22 | 1052900.12 | 777474.9 | 275425.22 | 100% | 100% | 101% | 92.63% | 100% | no data | no data | 2009-03-16 | 2009-06-09 | 2009-06-22 | 85 | 522 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Bunga | 160205004 | Construction of 1 unit Day Care Center | 1 | 532343.47 | 348364.15 | 183979.32 | 348364.15 | 3rd Tranche | 175035.18 | 523399.33 | 348364.15 | 175035.18 | 100% | 100% | 95.14% | 98.32% | 100% | 2005-08-29 | 2005-09-01 | 2005-11-21 | 2006-02-04 | 2006-05-13 | 75 | 124 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Bunga | 160205004 | Human Devt Center | 1 | 857437 | 651652 | 205785 | 610978.32 | 3rd Tranche | 196300 | 807278.32 | 610978.32 | 196300 | 100% | 100% | 95.39% | 94.15% | 100% | no data | no data | 2009-03-06 | 2009-06-02 | 2009-06-15 | 88 | 146 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Colorado | 160205005 | Const. of 1 Unit Brgy. Health Station | 1 | 519023.67 | 358821.15 | 160202.52 | 358821.15 | 3rd Tranche | 186251.23 | 545072.38 | 358821.15 | 186251.23 | 100% | 100% | 116.3% | 105% | 100% | 2005-08-29 | 2005-09-01 | 2005-12-01 | 2006-02-14 | 2006-06-28 | 75 | 274 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Cuyago | 160205006 | Construction of 2 CL HS School Building | 1 | 977726.19 | 734695.55 | 243030.64 | 661225.44 | 2nd Tranche | 296024.11 | 957249.55 | 661225.44 | 296024.11 | 100% | 100% | 121.8% | 97.91% | 100% | 2005-08-29 | 2005-09-01 | 2006-01-05 | 2006-03-24 | 2006-06-28 | 78 | 336 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Libas | 160205007 | Improvement/Upgrading of FMR | 1 | 4125157.5 | 2425152.5 | 1700005 | 2425152.5 | 3rd Tranche | 1271454 | 3696606.5 | 2425152.5 | 1271454 | 100% | 100% | 74.79% | 89.61% | 100% | 2004-10-04 | 2004-12-17 | 2005-05-31 | 2005-10-17 | 2005-10-27 | 139 | 315 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Libas | 160205007 | Improvement of Water System | 1 | 930430.66 | 240660 | 689770.66 | 192528 | 1st Tranche | 660645.05 | 853173.05 | 192528 | 660645.05 | 100% | 100% | 95.78% | 91.7% | 100% | no data | no data | 2009-03-25 | 2009-06-29 | 2009-07-07 | 96 | 360 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magdagooc | 160205008 | Construction of 2 CL Elem. School Building | 1 | 985879.39 | 742549.55 | 243329.84 | 668295 | 2nd Tranche | 259509.91 | 927804.91 | 668295 | 259509.91 | 100% | 100% | 106.6% | 94.11% | 100% | 2005-08-29 | 2005-09-01 | 2005-11-25 | 2006-02-23 | 2006-06-22 | 90 | 254 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magdagooc | 160205008 | Health Station | 1 | 728565 | 553709 | 174856 | 527560.89 | 3rd Tranche | 215936.86 | 743497.75 | 527560.89 | 215936.86 | 100% | 100% | 123.5% | 102% | 100% | no data | no data | 2009-03-04 | 2009-05-27 | 2009-06-22 | 84 | 303 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magsaysay | 160205009 | Construction of 2 CL Elem. School Building | 1 | 977726.19 | 734695.55 | 243030.64 | 661225 | 2nd Tranche | 257397.11 | 918622.11 | 661225 | 257397.11 | 100% | 100% | 105.9% | 93.95% | 100% | 2005-08-29 | 2005-09-01 | 2005-11-30 | 2006-02-18 | 2006-06-15 | 80 | 200 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Magsaysay | 160205009 | Health Station | 1 | 713565 | 542309 | 171256 | 542309 | 3rd Tranche | 173146.86 | 715455.86 | 542309 | 173146.86 | 100% | 100% | 101.1% | 100.3% | 100% | no data | no data | 2009-03-16 | 2009-06-09 | 2009-06-19 | 85 | 217 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Maraiging | 160205010 | Rehabilitation of Brgy. Road (Road Concreting) | 1 | 2531811.6 | 2064300 | 467511.6 | 2064300 | 3rd Tranche | 687624 | 2751924 | 2064300 | 687624 | 100% | 100% | 147.1% | 108.7% | 100% | 2003-04-25 | 2003-07-09 | 2003-09-01 | 2004-01-21 | 2004-03-09 | 142 | 69 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Maraiging | 160205010 | Construction of 1 unit Day Care Center | 1 | 523732.47 | 340069.15 | 183663.32 | 340069.15 | 3rd Tranche | 132937.08 | 473006.23 | 340069.15 | 132937.08 | 100% | 100% | 72.38% | 90.31% | 100% | 2005-08-29 | 2005-09-01 | 2005-12-05 | 2006-02-18 | 2006-03-09 | 75 | 69 |  | 1
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Maraiging | 160205010 | 2 CL Elem School Building | 1 | 1146660 | 871461 | 275199 | 784314.9 | 2nd Tranche | 271077.22 | 1055392.12 | 784314.9 | 271077.22 | 100% | 100% | 98.5% | 92.04% | 100% | no data | no data | 2009-03-11 | 2009-05-12 | 2009-05-15 | 62 | 88 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Poblacion | 160205011 | Construction of 1 unit Day Care Center | 1 | 523732.47 | 340069.15 | 183663.32 | 340069.15 | 3rd Tranche | 175903.73 | 515972.88 | 340069.15 | 175903.73 | 100% | 100% | 95.78% | 98.52% | 100% | 2005-08-29 | 2005-09-01 | 2005-12-28 | 2006-02-11 | 2006-06-22 | 45 | 567 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Poblacion (Jabonga) | 160205011 | Human Devt Center | 1 | 857437 | 651652 | 205785 | 614098.24 | 3rd Tranche | 208539.5 | 822637.74 | 614098.24 | 208539.5 | 100% | 100% | 101.3% | 95.94% | 100% | no data | no data | 2009-03-16 | 2009-06-16 | 2009-06-22 | 92 | 558 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Pablo | 160205013 | Construction of 2 Classroom Elem School Building and 2 unit Day Care Centers | 1 | 1331678.76 | 892416 | 439262.76 | 892416 | 3rd Tranche | 423897 | 1316313 | 892416 | 423897 | 100% | 100% | 96.5% | 98.85% | 100% | 2003-04-25 | 2003-07-09 | 2003-09-01 | 2003-12-17 | 2004-03-09 | 107 | 154 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Pablo | 160205013 | Const. of 1 Unit Brgy. Health Station | 1 | 519023.67 | 358821.15 | 160202.52 | 358821.15 | 3rd Tranche | 256773.23 | 615594.38 | 358821.15 | 256773.23 | 100% | 100% | 160.3% | 118.6% | 100% | 2005-08-29 | 2005-09-01 | 2005-01-08 | 2006-03-24 | 2006-03-09 | 440 | 154 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Pablo | 160205013 | Multi-Purpose Center | 1 | 1438362 | 1093155 | 345207 | 983839.5 | 2nd Tranche | 347142.48 | 1330981.98 | 983839.5 | 347142.48 | 100% | 100% | 100.6% | 92.53% | 100% | no data | no data | 2009-03-05 | 2009-05-12 | 2009-05-14 | 68 | 180 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | San Vicente | 160205014 | Const. of Marketing Center | 1 | 416129.16 | 281557 | 134572.16 | 281557 | 3rd Tranche | 200836.38 | 482393.38 | 281557 | 200836.38 | 100% | 100% | 149.2% | 115.9% | 100% | 2003-04-25 | 2003-07-09 | 2003-08-08 | 2003-10-17 | 2003-10-28 | 70 | 285 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Sto. Niño | 160205015 | Improvement/Upgrading of FMR | 1 | 3544950 | 2074847.5 | 1470102.5 | 2074847.5 | 3rd Tranche | 1654737.5 | 3729585 | 2074847.5 | 1654737.5 | 100% | 100% | 112.6% | 105.2% | 100% | 2004-10-04 | 2004-12-17 | 2005-05-24 | 2005-10-17 | 2005-10-28 | 146 | 167 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Jabonga | 160205 | Sto. Niño | 160205015 | Day Care Center | 1 | 668268 | 507883 | 160385 | 466774.32 | 2nd Tranche | 162986.03 | 629760.35 | 466774.32 | 162986.03 | 100% | 100% | 101.6% | 94.24% | 100% | no data | no data | 2009-03-14 | 2009-05-27 | 2009-06-19 | 74 | 179 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Ambacon | 160207001 | Construction of Brgy. Health Station | 1 | 769728.54 | 592464 | 177264.54 | 440112 | 1st Tranche | 216686.78 | 656798.78 | 440112 | 216686.78 | 100% | 100% | 122.2% | 85.33% | 100% | no data | no data | 2009-04-29 | 2009-06-30 | 2009-07-02 | 62 | 375 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Balungagan | 160207015 | Rehab of Lingayao-Balungagan-Ibuan Road | 1 | 3046932.04 | 2497218.54 | 549713.5 | 2497218.536 | 3rd Tranche | 488150.53 | 2985369.066 | 2497218.536 | 488150.53 | 100% | 100% | 88.8% | 97.98% | 100% | 2003-10-24 | 2003-12-05 | 2004-03-08 | 2004-09-30 | 2004-12-07 | 206 | 93 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Balungagan | 160207015 | Construction of Day Care Center | 1 | 777460 | 592851 | 184609 | 528039 | 2nd Tranche | 183155.52 | 711194.52 | 528039 | 183155.52 | 100% | 100% | 99.21% | 91.48% | 100% | no data | no data | 2009-04-17 | 2009-06-27 | 2009-06-29 | 71 | 112 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Bonifacio | 160207002 | Construction of Corn Mill | 1 | 1207703.53 | 907512 | 300191.53 | 816760.8 | 2nd Tranche | 292371.5 | 1109132.3 | 816760.8 | 292371.5 | 100% | 100% | 97.39% | 91.84% | 100% | no data | no data | 2009-04-06 | 2009-06-30 | 2009-07-08 | 85 | 194 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Casiklan | 160207021 | Improvement/Upgrading of FMR | 1 | 1471422 | 1115038 | 356384 | 1115038 | 3rd Tranche | 353075.28 | 1468113.28 | 1115038 | 353075.28 | 100% | 100% | 99.07% | 99.78% | 100% | 2005-05-10 | 2005-07-27 | 2005-10-26 | 2006-09-30 | 2006-07-25 | 339 | 223 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Casiklan | 160207021 | Construction of Health Station | 1 | 775374.84 | 598888 | 176486.84 | 500000.8 | 2nd Tranche | 197017.14 | 697017.94 | 500000.8 | 197017.14 | 100% | 100% | 111.6% | 89.89% | 100% | no data | no data | 2009-04-30 | 2009-06-27 | 2009-06-29 | 58 | 400 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Consorcia | 160207003 | Construction of Rice & Corn Mill | 1 | 1367304 | 1054573 | 312731 | 843658.4 | 1st Tranche | 330991 | 1174649.4 | 843658.4 | 330991 | 100% | 100% | 105.8% | 85.91% | 100% | no data | no data | 2009-04-13 | 2009-06-30 | 2009-09-18 | 78 | 253 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Durian | 160207017 | Improvement/Upgrading of FMR w/ 300 m concreting | 1 | 4278000 | 3199000 | 1079000 | 3199000 | 3rd Tranche | 993217.04 | 4192217.04 | 3199000 | 993217.04 | 100% | 100% | 92.05% | 97.99% | 100% | 2005-03-06 | 2006-03-25 | 2006-11-13 | 2008-06-30 | n/a | 595 | 119 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Eduardo G. Montilla (Camboayon) | 160207016 | Construction of 2CL High School Building | 1 | 1264182 | 925183 | 338999 | 740146.4 | 1st Tranche | 272934.7 | 1013081.1 | 740146.4 | 272934.7 | 100% | 100% | 80.51% | 80.14% | 100% | no data | no data | 2009-04-17 | 2009-06-30 | 2009-07-08 | 74 | 178 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Eduardo G. Montilla (Camboayon) | 160207016 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1112439 | 529327 | 583112 | 529327 | 3rd Tranche | 571922 | 1101249 | 529327 | 571922 | 100% | 100% | 98.08% | 98.99% | 100% | 2005-05-10 | 2005-07-27 | 2005-09-12 | 2005-12-30 | 2006-04-20 | 109 | 166 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Ibuan | 160207018 | Improvement/Upgrading of FMR | 1 | 1018375 | 775500 | 242875 | 775500 | 3rd Tranche | 235442.15 | 1010942.15 | 775500 | 235442.15 | 100% | 100% | 96.94% | 99.27% | 100% | 2005-05-10 | 2005-07-27 | 2005-11-10 | 2006-06-30 | 2006-07-25 | 232 | 235 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Katipunan - C2 | 160207004 | Impvt of Katimali Water System Level II (Pump Driven) | 2 | 1605366 | 1217539 | 387827 | 1095785.1 | 2nd Tranche | 417158.05 | 1512943.15 | 1095785.1 | 417158.05 | 100% | 100% | 107.6% | 94.24% | 100% | no data | no data | 2009-04-16 | 2009-06-30 | 2009-07-08 | 75 | 356 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Lingayao | 160207005 | Construction of Day Care Center | 1 | 771126 | 537582 | 233544 | 430065.6 | 1st Tranche | 222255 | 652320.6 | 430065.6 | 222255 | 100% | 100% | 95.17% | 84.59% | 100% | no data | no data | 2009-04-23 | 2009-06-27 | 2009-07-01 | 65 | 378 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Marcos Calo | 160207008 | Const. Of Potable Water System L-II (Spring Dev.) | 1 | 700060 | 563800 | 136260 | 563800 | 3rd Tranche | 156207.44 | 720007.44 | 563800 | 156207.44 | 100% | 100% | 114.6% | 102.8% | 100% | 2005-05-10 | 2005-07-27 | 2005-09-19 | 2005-12-03 | 2006-04-20 | 75 | 160 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Marcos Calo | 160207008 | Construction of Barangay Health Station | 1 | 796053 | 607894 | 188159 | 547104.6 | 2nd Tranche | 205115.7 | 752220.3 | 547104.6 | 205115.7 | 100% | 100% | 109% | 94.49% | 100% | no data | no data | 2009-04-29 | 2009-06-27 | 2009-06-29 | 59 | 161 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Mat-i | 160207009 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1898000 | 1326500 | 571500 | 1326500 | 3rd Tranche | 455357.15 | 1781857.15 | 1326500 | 455357.15 | 100% | 100% | 79.68% | 93.88% | 100% | 2005-03-06 | 2006-03-25 | 2006-07-01 | 2006-11-30 | no data | 152 | 363 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Pinana-an | 160207010 | Construction of Day Care Center | 1 | 771126.2 | 563177.5 | 207948.7 | 450542 | 1st Tranche | 200575.2 | 651117.2 | 450542 | 200575.2 | 100% | 100% | 96.45% | 84.44% | 100% | no data | no data | 2009-04-14 | 2009-06-17 | 2009-06-29 | 64 | 242 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Pinana-an | 160207010 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 932035 | 732700 | 199335 | 732700 | 3rd Tranche | 211663.8 | 944363.8 | 732700 | 211663.8 | 100% | 100% | 106.2% | 101.3% | 100% | 2005-05-10 | 2005-07-27 | 2005-09-12 | 2005-12-30 | 2006-02-24 | 109 | 197 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Poblacion | 160207011 | Expansion L-II WS (Pump Driven) | 1 | 1771840.9 | 1381518.88 | 390322.02 | 1381518.88 | 3rd Tranche | 454790.22 | 1836309.1 | 1381518.88 | 454790.22 | 100% | 100% | 116.5% | 103.6% | 100% | 2003-10-24 | 2003-12-05 | 2004-03-08 | 2004-09-30 | 2004-12-07 | 206 | 216 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Rosario | 160207019 | Road Opening/Const of FMR | 1 | 2971760 | 2283635 | 688125 | 2283635 | 3rd Tranche | 565298.2 | 2848933.2 | 2283635 | 565298.2 | 100% | 100% | 82.15% | 95.87% | 100% | 2005-05-10 | 2005-07-27 | 2005-10-01 | 2006-10-31 | 2006-12-22 | 395 | 231 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | San Isidro | 160207013 | Road Opening/Const. of Farm to Market Road | 1 | 2555729.81 | 2120580.31 | 435149.5 | 2120580.309 | 3rd Tranche | 731135 | 2851715.309 | 2120580.309 | 731135 | 100% | 100% | 168% | 111.6% | 100% | 2003-10-24 | 2003-12-05 | 2004-03-08 | 2004-09-05 | 2004-09-09 | 181 | 191 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | San Isidro | 160207013 | Inst. Of Rice and Corn Mill | 1 | 1440375 | 1067100 | 373275 | 1067100 | 3rd Tranche | 357713.99 | 1424813.99 | 1067100 | 357713.99 | 100% | 100% | 95.83% | 98.92% | 100% | 2005-03-06 | 2006-03-25 | 2006-07-01 | 2006-11-30 | 2006-12-15 | 152 | 196 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | San Isidro | 160207013 | Construction of Box Culvert | 1 | 1536121.5 | 1211467 | 324654.5 | 969173.6 | 1st Tranche | 270779.8 | 1239953.4 | 969173.6 | 270779.8 | 100% | 100% | 83.41% | 80.72% | 100% | no data | no data | 2009-04-17 | 2009-06-30 | 2009-07-02 | 74 | 212 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | San Roque | 160207020 | Construction of Brgy. Health Station | 1 | 779128.94 | 591131 | 187997.94 | 496025.1 | 2nd Tranche | 223635.5 | 719660.6 | 496025.1 | 223635.5 | 100% | 100% | 119% | 92.37% | 100% | no data | no data | 2009-04-21 | 2009-06-30 | 2009-07-08 | 70 | 114 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Tinocuran | 160207014 | Construction of Flat Bed Drier | 1 | 625000 | 434229 | 190771 | 390806.1 | 2nd Tranche | 232270 | 623076.1 | 390806.1 | 232270 | 100% | 100% | 121.8% | 99.69% | 100% | no data | no data | 2009-04-14 | 2009-06-27 | 2009-06-29 | 74 | 167 |  | 1 | LUZON
Caraga | 16 | Agusan Del Norte | 1602 | Las Nieves | 160207 | Tinucoran | 160207014 | Construction of Solar Drier | 1 | 587000 | 407400 | 179600 | 407400 | 3rd Tranche | 405149.18 | 812549.18 | 407400 | 405149.18 | 100% | 100% | 225.6% | 138.4% | 100% | 2005-03-06 | 2006-03-25 | 2006-10-04 | 2006-11-22 | 2006-12-15 | 49 | 160 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Agsabu | 160303031 | Const. Of Potable Water System L-II (Spring Dev.) | 1 | 822731.6 | 602843 | 219888.6 | 482274 | 1st Tranche | 222758.6 | 705032.6 | 482274 | 222758.6 | 100% | 100% | 101.3% | 85.69% | 100% | 2005-07-19 | 2005-08-24 | 2005-10-18 | 2006-03-30 | 2006-08-14 | 163 | 80 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Aguinaldo | 160303032 | Construction of 1 unit Day Care Center | 1 | 605513 | 453507.83 | 152005.17 | 453507.83 | 3rd Tranche | 121511.17 | 575019 | 453507.83 | 121511.17 | 100% | 100% | 79.94% | 94.96% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-10 | 2007-11-09 | n/a | 91 | 109 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Anolingan | 160303001 | Improvement of Farm to Market Road | 1 | 2885734 | 2211008.79 | 674725.21 | 2211002.79 | 1st Tranche | 649919.76 | 2860922.55 | 2211002.79 | 649919.76 | 100% | 100% | 96.32% | 99.14% | 100% | 2007-04-27 | 2007-05-18 | 2007-10-17 | 2009-05-30 | n/a | 591 | 279 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Bakingking | 160303002 | Construction of 1 unit Day Care Center | 1 | 681011 | 475067.5 | 205943.5 | 427560.75 | 2nd Tranche | 155013.5 | 582574.25 | 427560.75 | 155013.5 | 100% | 100% | 75.27% | 85.55% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-23 | 2007-10-22 | n/a | 60 | 75 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Balubo | 160303033 | Electrification (Single Phase) | 1 | 1872265 | 1437812 | 434453 | 1383907 | 3rd Tranche | 360562.4 | 1744469.4 | 1383907 | 360562.4 | 100% | 100% | 82.99% | 93.17% | 100% | 2007-04-27 | 2007-05-18 | 2007-12-21 | 2008-04-19 | n/a | 120 | 110 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Bentahon | 160303003 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 916401.2 | 671091 | 245310.2 | 671091 | 3rd Tranche | 242224.1 | 913315.1 | 671091 | 242224.1 | 100% | 100% | 98.74% | 99.66% | 100% | 2005-07-19 | 2005-08-24 | 2005-10-29 | 2006-06-30 | 2006-06-29 | 244 | 187 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Bunaguit | 160303004 | Construction of 1 unit Day Care Center | 1 | 648277 | 481122.5 | 167154.5 | 433010.25 | 2nd Tranche | 136224.5 | 569234.75 | 433010.25 | 136224.5 | 100% | 100% | 81.5% | 87.81% | 100% | 2007-04-27 | 2007-05-18 | 2007-09-16 | 2007-12-14 | n/a | 89 | 184 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Catmonon | 160303006 | Improvement/Upgrading of FMR | 1 | 3854420.03 | 3129443 | 724977.03 | 3129443 | 2nd Tranche | 693930.35 | 3823373.35 | 3129443 | 693930.35 | 100% | 100% | 95.72% | 99.19% | 100% | 2005-07-19 | 2005-08-24 | 2006-04-07 | 2006-10-31 | 2007-06-27 | 207 | 299 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Cebulan | 160303034 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 972018 | 724140 | 247878 | 724140 | 3rd Tranche | 194834 | 918974 | 724140 | 194834 | 100% | 100% | 78.6% | 94.54% | 100% | 2006-05-16 | 2006-05-16 | 2006-08-24 | 2006-11-22 | 2007-05-03 | 90 | 65 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Concordia | 160303007 | Const. Of 1 unit Solar Drier | 1 | 373602 | 281018.33 | 92583.67 | 262655.87 | 3rd Tranche | 86283.67 | 348939.54 | 262655.87 | 86283.67 | 100% | 100% | 93.2% | 93.4% | 100% | 2007-04-27 | 2007-05-18 | 2007-09-01 | 2007-11-14 | no data | 74 | 147 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Crossing Luna | 160303035 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1033760 | 763150 | 270610 | 763150 | 3rd Tranche | 224438.6 | 987588.6 | 763150 | 224438.6 | 100% | 100% | 82.94% | 95.53% | 100% | 2005-07-19 | 2005-08-24 | 2005-10-05 | 2006-09-30 | 2007-02-14 | 360 | 262 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Cubo | 160303036 | Construction of Solar Drier | 1 | 528183 | 377718.04 | 150464.96 | 377718.04 | 3rd Tranche | 110153.61 | 487871.65 | 377718.04 | 110153.61 | 100% | 100% | 73.21% | 92.37% | 100% | 2006-05-16 | 2006-05-16 | 2006-09-09 | 2006-11-30 | 2006-12-23 | 82 | 143 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Dakutan | 160303008 | Const. Of 2 units Solar Drier | 1 | 1163546 | 882455 | 281091 | 794209.5 | 2nd Tranche | 235221 | 1029430.5 | 794209.5 | 235221 | 100% | 100% | 83.68% | 88.47% | 100% | 2007-04-27 | 2007-05-18 | 2007-09-01 | 2007-11-29 | n/a | 89 | 193 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Duangan | 160303009 | Construction of 1 unit Day Care Center | 1 | 647285.94 | 359540.82 | 287745.12 | 359540.82 | 3rd Tranche | 205259.16 | 564799.98 | 359540.82 | 205259.16 | 100% | 100% | 71.33% | 87.26% | 100% | 2006-05-16 | 2006-05-16 | 2006-09-11 | 2006-12-10 | 2006-10-19 | 90 | 240 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Guadalupe | 160303011 | Const. of 1 Unit Brgy. Health Station | 1 | 769158.83 | 582632.36 | 186526.47 | 582632.36 | 3rd Tranche | 222676.47 | 805308.83 | 582632.36 | 222676.47 | 100% | 100% | 119.4% | 104.7% | 100% | 2005-07-19 | 2005-08-24 | 2005-11-14 | 2006-06-30 | 2006-06-29 | 228 | 600 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Guibonon | 160303037 | Improvement/Upgrading of FMR | 1 | 5173144.62 | 3862244.39 | 1310900.23 | 3089795.51 | 1st Tranche | 820017.82 | 3909813.33 | 3089795.51 | 820017.82 | 100% | 100% | 62.55% | 75.58% | 100% | 2006-05-16 | 2006-05-16 | 2007-01-29 | 2007-06-28 | n/a | 150 | 98 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Hawilian | 160303012 | Construction of 4 CL HS School Building | 1 | 1919244 | 1341636.4 | 577607.6 | 1341636.4 | 3rd Tranche | 578845.77 | 1920482.17 | 1341636.4 | 578845.77 | 100% | 100% | 100.2% | 100.1% | 100% | 2006-05-16 | 2006-05-16 | 2006-09-04 | 2007-01-01 | 2007-06-18 | 119 | 364 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Kalabuan | 160303038 | Improvement/Upgrading of FMR | 1 | 4887051.34 | 3396840.64 | 1490210.7 | 3396840.64 | 2nd Tranche | 1485178.18 | 4882018.82 | 3396840.64 | 1485178.18 | 100% | 100% | 99.66% | 99.9% | 100% | 2005-07-19 | 2005-08-24 | 2006-03-01 | 2006-11-30 | 2007-10-02 | 274 | 148 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Kinamaybay | 160303039 | Improvement/Upgrading of FMR | 1 | 3754620 | 2659275 | 1095345 | 2659275 | 3rd Tranche | 1080855 | 3740130 | 2659275 | 1080855 | 100% | 100% | 98.68% | 99.61% | 100% | 2006-05-16 | 2006-05-16 | 2006-09-05 | 2007-01-03 | 2006-12-06 | 120 | 90 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Kinamaybay | 160303039 | Construction of 1 unit Day Care Center | 1 | 634473 | 477119.17 | 157353.83 | 429406.9 | 2nd Tranche | 126423.83 | 555830.73 | 429406.9 | 126423.83 | 100% | 100% | 80.34% | 87.61% | 100% | 2007-04-27 | 2007-05-18 | 2007-09-01 | 2007-11-09 | n/a | 69 | 92 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Langag | 160303040 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 2402917 | 1837972.5 | 564944.5 | 1654175.25 | 2nd Tranche | 463294.5 | 2117469.75 | 1654175.25 | 463294.5 | 100% | 100% | 82.01% | 88.12% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-01 | 2008-06-30 | n/a | 334 | 220 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Maasin | 160303014 | Improvement/Upgrading of FMR | 1 | 6758520 | 4954000 | 1804520 | 4954000 | 3rd Tranche | 1785200 | 6739200 | 4954000 | 1785200 | 100% | 100% | 98.93% | 99.71% | 100% | 2005-07-19 | 2005-08-24 | 2006-03-01 | 2006-10-31 | 2006-11-17 | 244 | 168 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Mac- Arthur | 160303010 | Const. Of 1 unit Solar Drier | 1 | 661024 | 267357.37 | 393666.63 | 213886 | 1st Tranche | 352006.63 | 565892.63 | 213886 | 352006.63 | 100% | 100% | 89.42% | 85.61% | 100% | 2007-04-27 | 2007-05-18 | 2007-10-01 | 2008-01-29 | n/a | 120 | 48 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Mahagkot | 160303015 | Const. of 1 Unit Brgy. Health Station | 1 | 567400 | 404791.67 | 162608.33 | 404791.34 | 3rd Tranche | 162576.33 | 567367.67 | 404791.34 | 162576.33 | 100% | 100% | 99.98% | 99.99% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-22 | 2008-05-01 | n/a | 253 | 156 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Maliwanag | 160303041 | Construction of 1 unit Day Care Center | 1 | 571554 | 432286.67 | 139267.33 | 389057.62 | 2nd Tranche | 108457.33 | 497514.95 | 389057.62 | 108457.33 | 100% | 100% | 77.88% | 87.05% | 100% | 2007-04-27 | 2007-05-18 | 2007-09-29 | 2008-05-01 | n/a | 215 | 34 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Nato | 160303017 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 2173088 | 1679769 | 493319 | 1679769 | 3rd Tranche | 428407 | 2108176 | 1679769 | 428407 | 100% | 100% | 86.84% | 97.01% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-01 | 2008-05-01 | n/a | 274 | 303 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | New Gingoog | 160303042 | Construction of Solar Drier | 1 | 528183 | 366051.38 | 162131.62 | 366051.38 | 3rd Tranche | 162131.62 | 528183 | 366051.38 | 162131.62 | 100% | 100% | 100% | 100% | 100% | 2006-05-16 | 2006-05-16 | 2006-10-01 | 2007-02-25 | 2007-04-30 | 147 | 86 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Oro | 160303018 | Construction of 2 CL Elem School Building | 1 | 1170956 | 889646.67 | 281309.33 | 800682.01 | 2nd Tranche | 233059.33 | 1033741.34 | 800682.01 | 233059.33 | 100% | 100% | 82.85% | 88.28% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-26 | 2008-05-01 | n/a | 249 | 250 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Remedios | 160303020 | Inst. Of Rice and Corn Mill | 1 | 1787487 | 1250091.29 | 537395.71 | 1250091.29 | 3rd Tranche | 466018.26 | 1716109.55 | 1250091.29 | 466018.26 | 100% | 100% | 86.72% | 96.01% | 100% | 2006-05-16 | 2006-05-16 | 2006-08-16 | 2007-02-28 | 2007-03-10 | 196 | 244 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Salug | 160303021 | Construction of 2 CL Elem School Building | 1 | 975634 | 733425.87 | 242208.13 | 733425.87 | 3rd Tranche | 244367.7 | 977793.57 | 733425.87 | 244367.7 | 100% | 100% | 100.9% | 100.2% | 100% | 2006-05-16 | 2006-05-16 | 2006-12-01 | 2007-02-28 | 2007-06-26 | 89 | 195 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | San Isidro | 160303045 | Construction of 1 unit Day Care Center | 1 | 569249 | 424390.83 | 144858.17 | 424390.83 | 3rd Tranche | 115546.17 | 539937 | 424390.83 | 115546.17 | 100% | 100% | 79.77% | 94.85% | 100% | 2007-04-27 | 2007-05-18 | 2007-08-16 | 2007-11-16 | n/a | 92 | 52 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | San Vicente | 160303047 | Construction of 1 unit Day Care Center | 1 | 675471 | 512117.5 | 163353.5 | 409694 | 1st Tranche | 132423.5 | 542117.5 | 409694 | 132423.5 | 100% | 100% | 81.07% | 80.26% | 100% | 2007-04-27 | 2007-05-18 | 2007-11-21 | 2008-03-20 | n/a | 120 | 104 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Sta. Fe | 160303023 | Const. Of 2 units Solar Drier | 1 | 642293 | 490344.17 | 151948.83 | 441309.75 | 2nd Tranche | 123068.83 | 564378.58 | 441309.75 | 123068.83 | 100% | 100% | 80.99% | 87.87% | 100% | 2007-04-27 | 2007-05-18 | 2007-10-01 | 2008-05-01 | n/a | 213 | 235 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Tagabase | 160303026 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1233046 | 872082.83 | 360963.17 | 872082.83 | 3rd Tranche | 309396.57 | 1181479.4 | 872082.83 | 309396.57 | 100% | 100% | 85.71% | 95.82% | 100% | 2006-05-16 | 2006-05-16 | 2006-08-01 | 2007-02-28 | 2007-04-30 | 211 | 117 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Taganahaw | 160303027 | Const. of 1 Unit Brgy. Health Station | 1 | 540114.8 | 392258.8 | 147856 | 392258.8 | 3rd Tranche | 108456 | 500714.8 | 392258.8 | 108456 | 100% | 100% | 73.35% | 92.71% | 100% | 2006-05-16 | 2006-05-16 | 2006-08-01 | 2006-10-30 | 2006-12-04 | 90 | 60 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Tagbibili | 160303028 | Construction of 1 unit Day Care Center | 1 | 593268.6 | 412794.07 | 180474.53 | 412794.07 | 3rd Tranche | 177844.53 | 590638.6 | 412794.07 | 177844.53 | 100% | 100% | 98.54% | 99.56% | 100% | 2006-05-16 | 2006-05-16 | 2006-11-23 | 2007-02-12 | 2007-06-13 | 81 | 85 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Tahina | 160303029 | Const. of 1 Unit Brgy. Health Station | 1 | 620435 | 462212.5 | 158222.5 | 462212.5 | 3rd Tranche | 117878.5 | 580091 | 462212.5 | 117878.5 | 100% | 100% | 74.5% | 93.5% | 100% | 2007-04-27 | 2007-05-18 | 2007-09-10 | 2008-06-15 | n/a | 279 | 128 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | Esperanza | 160303 | Valentina | 160303049 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1000000 | 748741.11 | 251258.89 | 748741.11 | 3rd Tranche | 323048.23 | 1071789.34 | 748741.11 | 323048.23 | 100% | 100% | 128.6% | 107.2% | 100% | 2006-05-16 | 2006-05-16 | 2006-08-23 | 2007-01-15 | 2007-06-27 | 145 | 52 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Angeles | 160304009 | Jetmatic Pump L-I | 1 | 163800 | 127240 | 36560 | 127240 | 3rd Tranche | 86210 | 213450 | 127240 | 86210 | 100% | 100% | 235.8% | 130.3% | 100% | 2003-10-28 | 2003-12-09 | 2004-03-17 | 2004-08-31 | 2005-03-02 | 167 | 121 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Bataan | 160304001 | Drainage 3 Barrels Box Culvert | 1 | 568141.1 | 442801.1 | 125340 | 442801.1 | 3rd Tranche | 202890.75 | 645691.85 | 442801.1 | 202890.75 | 100% | 100% | 161.9% | 113.6% | 100% | 2003-10-28 | 2003-12-09 | 2004-02-26 | 2005-01-31 | 2005-03-02 | 340 | 102 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Halapitan | 160304003 | Construction of Hanging foot Bridge | 1 | 2323162.91 | 1876638 | 446524.91 | 1876638 | 3rd Tranche | 465457.48 | 2342095.48 | 1876638 | 465457.48 | 100% | 100% | 104.2% | 100.8% | 100% | 2006-04-20 | 2006-04-20 | 2006-06-26 | 2006-10-24 | 2006-12-15 | 120 | 144 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Langasian | 160304004 | Const of Hanging Foot Bridge | 1 | 1920933.38 | 1571410 | 349523.38 | 1571410 | 3rd Tranche | 398607.38 | 1970017.38 | 1571410 | 398607.38 | 100% | 100% | 114% | 102.6% | 100% | 2003-10-28 | 2003-12-09 | 2004-03-18 | 2005-05-12 | 2005-06-22 | 420 | 137 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Lydia | 160304011 | Const. of 1 Unit Brgy. Health Station | 1 | 380000 | 287348 | 92652 | 287348 | 3rd Tranche | 106363.65 | 393711.65 | 287348 | 106363.65 | 100% | 100% | 114.8% | 103.6% | 100% | 2003-10-28 | 2003-12-09 | 2004-04-20 | 2004-11-15 | 2005-03-04 | 209 | 68 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Panagangan | 160304012 | Construction of 4 CL High School Building | 1 | 2094262 | 1611298 | 482964 | 1611298 | 3rd Tranche | 475454.1 | 2086752.1 | 1611298 | 475454.1 | 100% | 100% | 98.45% | 99.64% | 100% | 2005-06-10 | 2005-07-27 | 2005-09-01 | 2005-12-01 | 2005-12-22 | 91 | 329 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Poblacion | 160304006 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 3313997.53 | 2623362 | 690635.53 | 2623362 | 3rd Tranche | 765258.53 | 3388620.53 | 2623362 | 765258.53 | 100% | 100% | 110.8% | 102.3% | 100% | 2006-04-20 | 2006-04-20 | 2006-06-15 | 2006-10-13 | no data | 120 | 705 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | San Patricio | 160304014 | Improvement/Upgrading of FMR | 1 | 1984806.2 | 1623488 | 361318.2 | 1623488 | 3rd Tranche | 437734.2 | 2061222.2 | 1623488 | 437734.2 | 100% | 100% | 121.1% | 103.9% | 100% | 2003-10-28 | 2003-12-09 | 2004-03-26 | 2005-06-16 | 2005-06-22 | 447 | 119 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Valentina | 160304015 | Const. of Water System L-II (Pump Driven) | 1 | 580000 | 447712.8 | 132287.2 | 447712.8 | 3rd Tranche | 152759.4 | 600472.2 | 447712.8 | 152759.4 | 100% | 100% | 115.5% | 103.5% | 100% | 2003-10-28 | 2003-12-09 | 2004-02-26 | 2005-01-26 | 2005-03-03 | 335 | 345 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | La Paz | 160304 | Villa Paz | 160304008 | Improvement/Upgrading of FMR | 1 | 3559283 | 2888702 | 670581 | 2888702 | 2nd Tranche | 664528.78 | 3553230.78 | 2888702 | 664528.78 | 100% | 100% | 99.1% | 99.83% | 100% | 2005-06-10 | 2005-07-27 | 2005-09-09 | 2006-09-30 | no data | 386 | 281 |  | 1 | LUZON
Caraga | 16 | Agusan del Sur | 1603 | Loreto | 160305 | Sto. Nino | 160305016 | Acquisition of Pre-Post Harvest Equipment | 1 | 250000 | 208400 | 41600 | 208400 | 2nd Tranche | 55000 | 263400 | 208400 | 55000 | 100% | 100% | 132.2% | 105.4% | 100% | 2008-07-13 | no data | 2008-11-03 | 2008-11-20 | 2008-12-12 | 17 | 186 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Anislagan | 160309001 | Improvement of Farm to Market Road | 1 | 1899583 | 1413565 | 486018 | 1130852 | 1st Tranche | 412484.5 | 1543336.5 | 1130852 | 412484.5 | 100% | 100% | 84.87% | 81.25% | 100% | 2007-04-17 | 2007-05-23 | 2007-08-16 | 2007-12-15 | n/a | 121 | 448 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Baylo | 160309002 | Pre-Harvest Facility (Purchase of Farm Tractor) | 1 | 1998704.57 | 1573956 | 424748.57 | 1573956 | 3rd Tranche | 425998.7 | 1999954.7 | 1573956 | 425998.7 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-04-28 | 2006-05-12 | 2006-11-15 | 2006-12-30 | 2007-02-20 | 45 | 200 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Binicalan | 160309009 | Inst. Of Rice and Corn Mill | 1 | 965202.74 | 629141.74 | 336061 | 629141.74 | 3rd Tranche | 414700.35 | 1043842.09 | 629141.74 | 414700.35 | 100% | 100% | 123.4% | 108.1% | 100% | 2005-04-12 | 2005-07-26 | 2005-09-15 | 2006-02-20 | 2006-08-18 | 158 | 256 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Binicalan | 160309009 | Const. of 1 Unit Brgy. Health Station | 1 | 509029 | 344509 | 164520 | 310058 | 2nd Tranche | 148902 | 458960 | 310058 | 148902 | 100% | 100% | 90.51% | 90.16% | 100% | 2007-04-17 | 2007-05-23 | 2007-08-16 | 2007-11-15 | n/a | 91 | 256 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Cecilia | 160309010 | Construction of 1 CL HS School Building | 1 | 516181.01 | 370933.01 | 145248 | 370933.01 | 3rd Tranche | 189994 | 560927.01 | 370933.01 | 189994 | 100% | 100% | 130.8% | 108.7% | 100% | 2005-04-12 | 2005-07-26 | 2005-10-16 | 2006-06-30 | 2006-08-16 | 257 | 191 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Coalicion | 160309003 | Inst. Of Rice and Corn Mill | 1 | 1500000 | 1115352.49 | 384647.51 | 1115352.49 | 1st Tranche | 343946.68 | 1459299.17 | 1115352.49 | 343946.68 | 100% | 100% | 89.42% | 97.29% | 100% | 2006-04-28 | 2006-05-12 | 2006-11-08 | 2007-01-30 | no data | 83 | 221 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Coalicion | 160309003 | Construction of Slab Bridge | 1 | 1550550 | 1155940 | 394610 | 1155940 | 1st Tranche | 349768 | 1505708 | 1155940 | 349768 | 100% | 100% | 88.64% | 97.11% | 100% | 2007-04-17 | 2007-05-23 | 2007-09-16 | 2007-12-15 | n/a | 90 | 221 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Don Alejandro | 160309012 | Inst. Of Rice and Corn Mill | 1 | 1788952.22 | 1389825.22 | 399127 | 1389825.22 | 3rd Tranche | 388069 | 1777894.22 | 1389825.22 | 388069 | 100% | 100% | 97.23% | 99.38% | 100% | 2005-04-12 | 2005-07-26 | 2005-09-15 | 2006-06-30 | 2006-08-16 | 288 | 408 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Don Alejandro | 160309012 | Improvement of Farm to Market Road | 1 | 1487894 | 1126952 | 360942 | 1126952 | 1st Tranche | 331140 | 1458092 | 1126952 | 331140 | 100% | 100% | 91.74% | 98% | 100% | 2007-04-17 | 2007-05-23 | 2007-07-24 | 2008-05-01 | n/a | 282 | 516 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Doña Flavia | 160309014 | Const. of Brgy. Health Station w/ birthing home | 1 | 1027162.42 | 761350.42 | 265812 | 761350.09 | 3rd Tranche | 267373.24 | 1028723.33 | 761350.09 | 267373.24 | 100% | 100% | 100.6% | 100.2% | 100% | 2005-04-12 | 2005-07-26 | 2005-09-21 | 2005-12-15 | 2006-07-06 | 85 | 535 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Doña Maxima | 160309025 | Improvement/Upgrading of FMR | 1 | 1667562.88 | 1170743.33 | 496819.55 | 1170743.33 | 3rd Tranche | 360157.02 | 1530900.35 | 1170743.33 | 360157.02 | 100% | 100% | 72.49% | 91.8% | 100% | 2006-04-28 | 2006-05-12 | 2006-06-01 | 2006-11-30 | 2007-02-20 | 182 | 225 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Doña Maxima | 160309025 | Construction of 1 unit Day Care Center | 1 | 496183 | 354763 | 141420 | 354763 | 3rd Tranche | 161803 | 516566 | 354763 | 161803 | 100% | 100% | 114.4% | 104.1% | 100% | 2007-04-17 | 2007-05-23 | 2007-07-25 | 2008-05-01 | n/a | 281 | 139 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Mahapag - C2 | 160309016 | Const. Of Potable Water System L-II (Pump Driven) | 2 | 1470697.62 | 1089536.62 | 381161 | 1089536.62 | 3rd Tranche | 408752.75 | 1498289.37 | 1089536.62 | 408752.75 | 100% | 100% | 107.2% | 101.9% | 100% | 2005-04-12 | 2005-07-26 | 2006-01-19 | 2006-08-31 | 2006-08-18 | 224 | 184 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Santiago - C2 | 160309023 | Const. Of Potable Water System L-II (Pump Driven) | 2 | 1470697.62 | 1089536.62 | 381161 | 1089536.62 | 3rd Tranche | 408752.75 | 1498289.37 | 1089536.62 | 408752.75 | 100% | 100% | 107.2% | 101.9% | 100% | 2005-04-12 | 2005-07-26 | 2006-01-19 | 2006-08-31 | 2006-08-18 | 224 | 184 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Mahayahay | 160309017 | Rehabilitation of FMR w/ Drainage | 1 | 1076588.62 | 819682.62 | 256906 | 819682.62 | 3rd Tranche | 259641.44 | 1079324.06 | 819682.62 | 259641.44 | 100% | 100% | 101.1% | 100.3% | 100% | 2005-04-12 | 2005-07-26 | 2005-09-16 | 2006-09-30 | no data | 379 | 108 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Muritula | 160309018 | Construction of 1 unit Day Care Center | 1 | 398083.53 | 302048.53 | 96035 | 302048.53 | 3rd Tranche | 144153.37 | 446201.9 | 302048.53 | 144153.37 | 100% | 100% | 150.1% | 112.1% | 100% | 2005-04-12 | 2005-07-26 | 2005-10-31 | 2006-08-31 | 2006-08-18 | 304 | 130 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Nuevo Trabajo | 160309005 | Inst. Of Rice and Corn Mill | 1 | 1501910.77 | 1069786.5 | 432124.27 | 1069786.3 | 3rd Tranche | 341177 | 1410963.3 | 1069786.3 | 341177 | 100% | 100% | 78.95% | 93.94% | 100% | 2006-04-28 | 2006-05-12 | 2006-10-16 | 2007-01-14 | no data | 90 | 267 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Poblacion | 160309006 | Improvement/Upgrading of FMR | 1 | 1128219.91 | 898945.91 | 229274 | 898945.91 | 3rd Tranche | 214914.26 | 1113860.17 | 898945.91 | 214914.26 | 100% | 100% | 93.74% | 98.73% | 100% | 2005-04-12 | 2005-07-26 | 2005-09-16 | 2006-08-31 | 2006-09-21 | 349 | 315 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Policarpo | 160309019 | Construction of 1 unit Day Care Center | 1 | 433674.72 | 292827.09 | 140847.63 | 292827.09 | 3rd Tranche | 115669.92 | 408497.01 | 292827.09 | 115669.92 | 100% | 100% | 82.12% | 94.19% | 100% | 2006-04-28 | 2006-05-12 | 2006-08-11 | 2006-11-11 | 2007-02-20 | 92 | 77 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Policarpo | 160309019 | Construction of 1 unit 2 Classroom Elem. Sch. Building | 1 | 1007463 | 730338 | 277125 | 723512.03 | 3rd Tranche | 262538 | 986050.03 | 723512.03 | 262538 | 100% | 100% | 94.74% | 97.87% | 100% | 2007-04-17 | 2007-05-23 | 2007-07-25 | 2008-05-01 | n/a | 281 | 83 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | San Isidro | 160309020 | Construction of 1 unit Day Care Center | 1 | 481268.81 | 345586.9 | 135681.91 | 345586.9 | 3rd Tranche | 118886.31 | 464473.21 | 345586.9 | 118886.31 | 100% | 100% | 87.62% | 96.51% | 100% | 2006-04-28 | 2006-05-12 | 2006-10-20 | 2007-01-18 | no data | 90 | 113 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | San Pedro | 160309021 | Improvement/Upgrading of FMR | 1 | 1994578.56 | 1431621.88 | 562956.68 | 1431621.88 | 3rd Tranche | 431216.17 | 1862838.05 | 1431621.88 | 431216.17 | 100% | 100% | 76.6% | 93.4% | 100% | 2006-04-28 | 2006-05-12 | 2006-08-17 | 2006-12-15 | 2007-02-20 | 120 | 86 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | San Pedro | 160309021 | Construction of 1 unit 2 Classroom Elem. Sch. Building | 1 | 1041340 | 761651 | 279689 | 761651 | 3rd Tranche | 254540 | 1016191 | 761651 | 254540 | 100% | 100% | 91.01% | 97.58% | 100% | 2007-04-17 | 2007-05-23 | 2007-07-24 | 2008-05-01 | n/a | 282 | 104 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Sta. Ines | 160309007 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1473311 | 1102331 | 370980 | 1020883.18 | 1st Tranche | 346618.5 | 1367501.68 | 1020883.18 | 346618.5 | 100% | 100% | 93.43% | 92.82% | 100% | 2007-04-17 | 2007-05-23 | 2007-07-24 | 2008-05-01 | n/a | 282 | 231 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Sta. Rita | 160309022 | Const. Of Potable Water System L-I (Spring Dev) | 1 | 503055.68 | 332263.8 | 170791.88 | 332263.8 | 3rd Tranche | 135002.76 | 467266.56 | 332263.8 | 135002.76 | 100% | 100% | 79.05% | 92.89% | 100% | 2006-04-28 | 2006-05-12 | 2006-09-22 | 2006-12-21 | 2006-11-28 | 90 | 50 |  | 1 | LUZON
Caraga | 16 | Agusan Del Sur | 1603 | San Luis | 160309 | Wegguam | 160309024 | Improvement/Upgrading of FMR | 1 | 1552279.93 | 1238535.93 | 313744 | 1238535.93 | 3rd Tranche | 283914.18 | 1522450.11 | 1238535.93 | 283914.18 | 100% | 100% | 90.49% | 98.08% | 100% | 2005-04-12 | 2005-07-26 | 2005-09-16 | 2006-09-30 | 2006-09-21 | 379 | 52 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Binucayan | 160305001 | Construction of 2 CL HS School Building ( Wooden) | 1 | 910000 | 685450 | 224550 | 685450 | 1st Tranche | 224804 | 910254 | 685450 | 224804 | 100% | 100% | 100.1% | 100% | 100% | 2008-07-13 | no data | 2008-09-22 | 2008-12-31 | 2009-06-29 | 100 | 348 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Johnson | 160305002 | Improvement/Upgrading of FMR | 1 | 1989420.03 | 1514491.6 | 474928.43 | 1514491.6 | 3rd Tranche | 373998.32 | 1888489.92 | 1514491.6 | 373998.32 | 100% | 100% | 78.75% | 94.93% | 100% | 2006-05-12 | 2006-05-20 | 2006-12-01 | 2007-03-31 | n/a | 120 | 292 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Katipunan | 160305014 | Const. Of Potable Water System L-I (Rain Collector) | 1 | 228319.73 | 175266.44 | 53053.29 | 175266.44 | 3rd Tranche | 57608.3 | 232874.74 | 175266.44 | 57608.3 | 100% | 100% | 108.6% | 102% | 100% | 2006-05-12 | 2006-05-20 | 2006-08-09 | 2006-11-27 | 2007-03-26 | 110 | 348 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Katipunan | 160305014 | Provision of Motorized Banca | 1 | 228829.27 | 165691 | 63138.27 | 165690.1 | 3rd Tranche | 61638.27 | 227328.37 | 165690.1 | 61638.27 | 100% | 100% | 97.62% | 99.34% | 100% | 2007-04-11 | 2007-06-07 | 2007-11-10 | 2008-05-01 | 2008-07-16 | 173 | 348 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Kauswagan | 160305015 | Construction of 1 unit 2 Classroom HS Building | 1 | 1019141.96 | 746764 | 272377.96 | 746764 | 3rd Tranche | 262289.96 | 1009053.96 | 746764 | 262289.96 | 100% | 100% | 96.3% | 99.01% | 100% | 2007-04-11 | 2007-06-07 | 2007-10-15 | 2008-01-14 | 2008-07-16 | 91 | 348 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Kauswagan | 160305015 | Construction of 2 CL HS School Building | 1 | 1297000 | 1000000 | 297000 | 1000000 | 2nd Tranche | 297691 | 1297691 | 1000000 | 297691 | 100% | 100% | 100.2% | 100.1% | 100% | 2008-07-13 | no data | 2008-09-22 | 2008-12-30 | 2009-05-15 | 99 | 348 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Nueva Gracia | 160305004 | Construction of 2 CL HS School Building | 1 | 1297000 | 990800 | 306200 | 990800 | 2nd Tranche | 293510 | 1284310 | 990800 | 293510 | 100% | 100% | 95.86% | 99.02% | 100% | 2008-07-13 | no data | 2008-09-22 | 2008-12-31 | 2009-05-15 | 100 | 331 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Poblacion | 160305005 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 2100000 | 1627211 | 472789 | 1627211 | 2nd Tranche | 471550.61 | 2098761.61 | 1627211 | 471550.61 | 100% | 100% | 99.74% | 99.94% | 100% | 2008-07-13 | no data | 2008-09-15 | 2008-12-08 | 2008-12-16 | 84 | 613 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | San Isidro | 160305006 | Improvement/Upgrading of FMR | 1 | 1136484.27 | 844803.02 | 291681.25 | 844803.02 | 3rd Tranche | 262460.6 | 1107263.62 | 844803.02 | 262460.6 | 100% | 100% | 89.98% | 97.43% | 100% | 2006-05-12 | 2006-05-20 | 2006-08-01 | 2006-11-30 | 2007-03-26 | 121 | 219 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | San Isidro | 160305006 | Construction of 1-unit Solar Drier with Warehouse | 1 | 1046000 | 770000 | 276000 | 770000 | 3rd Tranche | 236790 | 1006790 | 770000 | 236790 | 100% | 100% | 85.79% | 96.25% | 100% | 2008-07-13 | no data | 2008-09-23 | 2008-11-30 | 2008-12-12 | 68 | 219 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | San Mariano | 160305007 | Const. of 1 Unit Brgy. Health Station | 1 | 527068.41 | 394608 | 132460.41 | 394608 | 3rd Tranche | 154396.53 | 549004.53 | 394608 | 154396.53 | 100% | 100% | 116.6% | 104.2% | 100% | 2007-04-11 | 2007-06-07 | 2007-10-15 | 2008-05-01 | 2009-06-09 | 199 | 238 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | San Vicente | 160305008 | Construction of 2 CL HS School Building | 1 | 1053158 | 796600 | 256558 | 716940 | 2nd Tranche | 264207.5 | 981147.5 | 716940 | 264207.5 | 100% | 100% | 103% | 93.16% | 100% | 2006-05-12 | 2006-05-20 | 2006-10-10 | 2006-12-04 | 2007-03-26 | 55 | 246 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | San Vicente | 160305008 | Construction of 1 unit 2 Classroom HS Building | 1 | 1009765.75 | 737888 | 271877.75 | 737888 | 3rd Tranche | 257142.03 | 995030.03 | 737888 | 257142.03 | 100% | 100% | 94.58% | 98.54% | 100% | 2007-04-11 | 2007-06-07 | 2007-09-04 | 2008-05-01 | 2009-07-16 | 240 | 385 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Sta. Theresa | 160305009 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1726131.5 | 1299877 | 426254.5 | 1299877 | 2nd Tranche | 457081.99 | 1756958.99 | 1299877 | 457081.99 | 100% | 100% | 107.2% | 101.8% | 100% | 2007-04-11 | 2007-06-07 | 2007-10-16 | 2008-02-13 | 2008-07-16 | 120 | 402 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Sto.Niño - C2 | 160305016 | Const. Of Potable Water System L-II (Pump Driven) Cluster | 2 | 2351512.43 | 1755172 | 596340.43 | 1579655 | 2nd Tranche | 560007.4 | 2139662.4 | 1579655 | 560007.4 | 100% | 100% | 93.91% | 90.99% | 100% | 2007-04-11 | 2007-06-07 | 2007-07-26 | 2008-05-01 | 2008-07-16 | 280 | 402 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Violanta | 160305011 | Const. of 1 Unit Brgy. Health Station | 1 | 549788.22 | 395020.92 | 154767.3 | 355518.84 | 2nd Tranche | 155004.18 | 510523.02 | 355518.84 | 155004.18 | 100% | 100% | 100.2% | 92.86% | 100% | 2006-05-12 | 2006-05-20 | 2006-09-15 | 2006-11-15 | 2007-03-26 | 61 | 197 |  | 1 | LUZON
Caraga | 16 | Augusan del Sur | 1603 | Loreto | 160305 | Waloe | 160305012 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1787454.29 | 1373818.02 | 413636.27 | 1236436.22 | 2nd Tranche | 428352.43 | 1664788.65 | 1236436.22 | 428352.43 | 100% | 100% | 103.6% | 93.14% | 100% | 2006-05-12 | 2006-05-20 | 2006-09-23 | 2007-01-26 | 2007-07-16 | 125 | 305 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Albor | 168504001 | Construction of 1 unit 2 CL HS Building | 1 | 1160193.59 | 862263.76 | 297929.83 | 862263.76 | 3rd Tranche | 335712.49 | 1197976.25 | 862263.76 | 335712.49 | 100% | 100% | 112.7% | 103.3% | 100% | 2008-04-24 | no data | 2008-07-19 | 2008-10-31 | no data | 104 | 275 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Arellano | 168504002 | Const. of Shoreline Protection (Seawall) | 1 | 533733.41 | 375427.36 | 158306.05 | 375427.36 | 3rd Tranche | 165920.26 | 541347.62 | 375427.36 | 165920.26 | 100% | 100% | 104.8% | 101.4% | 100% | 2007-02-19 | 2007-03-22 | 2007-09-09 | 2007-11-09 | n/a | 61 | 140 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Bayanihan | 168504003 | Construction of 2 CL Elem School Building | 1 | 1121042.78 | 784729.95 | 336312.83 | 784729.95 | 3rd Tranche | 266567.6 | 1051297.55 | 784729.95 | 266567.6 | 100% | 100% | 79.26% | 93.78% | 100% | 2007-02-19 | 2007-03-22 | 2007-09-24 | 2008-06-06 | 2008-09-03 | 256 | 107 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Doña Helen | 168504004 | Construction of 2 Classroom Elem School Builiding | 1 | 1333871.68 | 1072258 | 261613.68 | 1072258 | 3rd Tranche | 345942.29 | 1418200.29 | 1072258 | 345942.29 | 100% | 100% | 132.2% | 106.3% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-03-31 | 2009-05-20 | 43 | 82 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Doña Helen | 168504004 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 868581.11 | 608006.78 | 260574.33 | 547206.3 | 2nd Tranche | 227533.8 | 774740.1 | 547206.3 | 227533.8 | 100% | 100% | 87.32% | 89.2% | 100% | 2007-02-19 | 2007-03-22 | 2007-10-08 | 2008-08-31 | 2008-09-03 | 328 | 82 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Garcia | 168504005 | Construction of 1 unit Day Care Center | 1 | 588455.12 | 418758.33 | 169696.79 | 418758.33 | 3rd Tranche | 242761.35 | 661519.68 | 418758.33 | 242761.35 | 100% | 100% | 143.1% | 112.4% | 100% | 2008-04-24 | no data | 2008-07-02 | 2008-10-31 | no data | 121 | 243 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Garcia | 168504005 | Construction of 1 unit Day Care Center | 1 | 694019.06 | 523849 | 170170.06 | 523849 | 3rd Tranche | 165442.14 | 689291.14 | 523849 | 165442.14 | 100% | 100% | 97.22% | 99.32% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-03-14 | 2009-05-19 | 26 | 243 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | General Aguinaldo | 168504006 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 2446836.4 | 1838780.34 | 608056.06 | 1654902.31 | 2nd Tranche | 590230.71 | 2245133.02 | 1654902.31 | 590230.71 | 100% | 100% | 97.07% | 91.76% | 100% | 2008-04-24 | no data | 2008-09-17 | 2009-02-28 | no data | 164 | 325 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Kahinaan | 168504007 | Construction of 1 unit Day Care Center | 1 | 646395.2 | 472926.2 | 173469 | 425633 | 2nd Tranche | 179294.06 | 604927.06 | 425633 | 179294.06 | 100% | 100% | 103.4% | 93.58% | 100% | 2007-02-19 | 2007-03-22 | 2007-09-24 | 2007-11-24 | 2008-09-03 | 61 | 30 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Kanihaan | 168504007 | Construction of Level 2 Potable Water System | 1 | 459639.18 | 356119.15 | 103520.03 | 356119.15 | 3rd Tranche | 125166.2 | 481285.35 | 356119.15 | 125166.2 | 100% | 100% | 120.9% | 104.7% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-02-28 | 2009-04-02 | 12 | 48 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Llamera | 168504015 | Construction of 1 unit Day Care Center | 1 | 588455.12 | 427374.45 | 161080.67 | 427374.45 | 3rd Tranche | 217365.25 | 644739.7 | 427374.45 | 217365.25 | 100% | 100% | 134.9% | 109.6% | 100% | 2008-04-24 | no data | 2008-07-02 | 2008-10-31 | no data | 121 | 200 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Llamera | 168504015 | Construction of Barangay Health Station | 1 | 773657.59 | 588689 | 184968.59 | 588689 | 3rd Tranche | 179479.61 | 768168.61 | 588689 | 179479.61 | 100% | 100% | 97.03% | 99.29% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-03-14 | 2009-05-19 | 26 | 69 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Magsaysay | 168504008 | Const. of Shoreline Protection | 1 | 1483184 | 1110580.39 | 372603.61 | 1110580.39 | 3rd Tranche | 380164.22 | 1490744.61 | 1110580.39 | 380164.22 | 100% | 100% | 102% | 100.5% | 100% | 2007-02-19 | 2007-03-22 | 2007-09-10 | 2008-11-01 | 2008-10-03 | 418 | 136 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Osmeña | 168504009 | Const. of Shoreline Protection (Seawall) | 1 | 589898.32 | 412979.35 | 176918.97 | 412979.35 | 3rd Tranche | 211578.8 | 624558.15 | 412979.35 | 211578.8 | 100% | 100% | 119.6% | 105.9% | 100% | 2007-02-19 | 2007-03-22 | 2007-09-10 | 2008-08-31 | 2008-09-02 | 356 | 107 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Plaridel | 168504010 | Construction of 2 CL HS School Building w/ Basic Facilities | 1 | 1293996.58 | 1006218.04 | 287778.54 | 1006218.04 | 3rd Tranche | 306868.76 | 1313086.8 | 1006218.04 | 306868.76 | 100% | 100% | 106.6% | 101.5% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-03-31 | 2009-05-20 | 43 | 366 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Quezon | 168504011 | Construction of 1 unit Barangay Health Station | 1 | 671188.38 | 489274.48 | 181913.9 | 489274.48 | 3rd Tranche | 221724.82 | 710999.3 | 489274.48 | 221724.82 | 100% | 100% | 121.9% | 105.9% | 100% | 2008-04-24 | no data | 2008-07-15 | 2008-10-30 | no data | 107 | 130 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Quezon | 168504011 | Construction of 99.00 ln.m Drainage Canal | 1 | 391242.53 | 303741.26 | 87501.27 | 303741.26 | 3rd Tranche | 92774.02 | 396515.28 | 303741.26 | 92774.02 | 100% | 100% | 106% | 101.3% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-04-07 | no data | 50 | 141 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Rosita | 168504016 | Construction of 3 CL HS School Building | 1 | 1497280 | 1035349.97 | 461930.03 | 1035349.97 | 3rd Tranche | 462191.26 | 1497541.23 | 1035349.97 | 462191.26 | 100% | 100% | 100.1% | 100% | 100% | 2007-02-19 | 2007-03-22 | 2007-07-18 | 2009-02-28 | n/a | 591 | 78 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | San Antonio | 168504012 | Construction of 2 Clasroom Elem School Building | 1 | 1305389.91 | 1023629.23 | 281760.68 | 1023629.23 | 3rd Tranche | 297529.85 | 1321159.08 | 1023629.23 | 297529.85 | 100% | 100% | 105.6% | 101.2% | 100% | 2008-11-20 | no data | 2009-02-16 | 2009-03-31 | 2009-05-20 | 43 | 366 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | San Jose | 168504013 | Construction of 1-unit Solar Drier with Warehouse | 1 | 463679.6 | 329284.41 | 134395.19 | 329284.41 | 3rd Tranche | 151508.02 | 480792.43 | 329284.41 | 151508.02 | 100% | 100% | 112.7% | 103.7% | 100% | 2008-04-24 | no data | 2008-08-04 | 2008-09-26 | no data | 53 | 331 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Libjo | 168504 | Sto. Niño | 168504014 | Construction of 1 unit Day Care Center | 1 | 568409.32 | 407758.34 | 160650.98 | 407758.34 | 3rd Tranche | 229495.86 | 637254.2 | 407758.34 | 229495.86 | 100% | 100% | 142.9% | 112.1% | 100% | 2008-04-24 | no data | 2008-07-09 | 2008-10-31 | no data | 114 | 223 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Asinan | 166716008 | Construction of Solar Drier w/ Warehouse | 1 | 1161076 | 908391.51 | 252684.49 | 908391.51 | 2nd Tranche | 228618 | 1137009.51 | 908391.51 | 228618 | 100% | 100% | 90.48% | 97.93% | 100% | 2008-02-15 | no data | 2008-05-21 | 2009-02-13 | 2009-03-27 | 268 | 104 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Asinan - C6 | 166716008 | Const. Of Potable Water System L-II (Gravity Driven) | 6 | 4021180.19 | 3144781.93 | 876398.26 | 2830303.73 | 2nd Tranche | 1032024.67 | 3862328.4 | 2830303.73 | 1032024.67 | 100% | 100% | 117.8% | 96.05% | 100% | 2007-02-07 | 2007-02-20 | 2007-04-23 | 2007-06-14 | n/a | 52 | 551 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Dayaohay | 166716014 | Const. Of Potable Water System L-II (Gravity Driven) | 6 | 4021180.19 | 3144781.93 | 876398.26 | 2830303.73 | 2nd Tranche | 1032024.67 | 3862328.4 | 2830303.73 | 1032024.67 | 100% | 100% | 117.8% | 96.05% | 100% | 2007-02-07 | 2007-02-20 | 2007-04-23 | 2007-06-14 | n/a | 52 | 551 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Caridad | 166716001 | Const. Of Potable Water System L-II | 1 | 1193225 | 999817 | 193408 | 989820.03 | 3rd Tranche | 245380.7 | 1235200.73 | 989820.03 | 245380.7 | 100% | 100% | 126.9% | 103.5% | 100% | 2008-12-02 | no data | 2009-02-18 | 2009-04-30 | 2009-05-23 | 71 | 304 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Centro | 166716009 | Construction of Day Care Center | 1 | 556945 | 410797 | 146148 | 410797 | 3rd Tranche | 137856 | 548653 | 410797 | 137856 | 100% | 100% | 94.33% | 98.51% | 100% | 2008-02-15 | no data | 2008-06-13 | 2008-10-31 | 2009-03-27 | 140 | 78 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Consolacion | 166716012 | Construction of 1 unit Day Care Center | 1 | 556945 | 410797 | 146148 | 410797 | 3rd Tranche | 132602.8 | 543399.8 | 410797 | 132602.8 | 100% | 100% | 90.73% | 97.57% | 100% | 2008-02-15 | no data | 2008-04-23 | 2008-09-30 | 2009-03-27 | 160 | 42 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Datu | 166716013 | Const. Of Potable Water System L-II | 1 | 1295438 | 1084858 | 210580 | 975746.8 | 2nd Tranche | 254522.4 | 1230269.2 | 975746.8 | 254522.4 | 100% | 100% | 120.9% | 94.97% | 100% | 2008-12-02 | no data | 2009-03-10 | 2009-06-04 | 2009-06-22 | 86 | 80 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Jaboy | 166716015 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 573719.14 | 445377.53 | 128341.61 | 400839.77 | 2nd Tranche | 141686.16 | 542525.93 | 400839.77 | 141686.16 | 100% | 100% | 110.4% | 94.56% | 100% | 2007-02-07 | 2007-02-20 | 2007-05-01 | 2007-07-30 | 2007-10-23 | 90 | 46 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Katipunan | 166716002 | Const. of 2 Units Footbridge | 1 | 590666.46 | 371591.58 | 219074.88 | 371591.26 | 3rd Tranche | 174597.84 | 546189.1 | 371591.26 | 174597.84 | 100% | 100% | 79.7% | 92.47% | 100% | 2007-02-07 | 2007-02-20 | 2007-05-25 | 2008-05-01 | 2009-03-27 | 342 | 86 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Katipunan | 166716002 | Construction of Sea wall | 1 | 468059.85 | 341562.14 | 126497.71 | 341562 | 3rd Tranche | 125505.6 | 467067.6 | 341562 | 125505.6 | 100% | 100% | 99.22% | 99.79% | 100% | 2008-02-15 | no data | 2008-06-13 | 2008-08-16 | 2009-03-27 | 64 | 87 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Maasin | 166716003 | Water System Level II (Pump Driven) | 1 | 1182982.11 | 933208.08 | 249774.03 | 933208.07 | 2nd Tranche | 225031 | 1158239.07 | 933208.07 | 225031 | 100% | 100% | 90.09% | 97.91% | 100% | 2008-02-15 | no data | 2008-06-20 | 2008-12-28 | 2009-03-27 | 191 | 190 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Mabini | 166716004 | Water System Level II (Pump Driven) | 1 | 730485.63 | 579307.07 | 151178.56 | 579307.05 | 3rd Tranche | 158942 | 738249.05 | 579307.05 | 158942 | 100% | 100% | 105.1% | 101.1% | 100% | 2008-02-15 | no data | 2008-06-18 | 2008-12-28 | 2009-03-27 | 193 | 58 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Mabuhay | 166716005 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 704144.22 | 538248.96 | 165895.26 | 484424.06 | 2nd Tranche | 189611.33 | 674035.39 | 484424.06 | 189611.33 | 100% | 100% | 114.3% | 95.72% | 100% | 2007-02-07 | 2007-02-20 | 2007-05-03 | 2007-08-27 | 2007-10-22 | 116 | 66 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Pilaring | 166716010 | Construction of Day Care Center | 1 | 556945 | 410797 | 146148 | 410796.41 | 3rd Tranche | 163050 | 573846.41 | 410796.41 | 163050 | 100% | 100% | 111.6% | 103% | 100% | 2008-02-15 | no data | 2008-05-21 | 2008-10-30 | 2009-03-27 | 162 | 168 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Punta | 166716011 | Construction of Solar Drier pavement w/ storage house | 1 | 1482934 | 1236472 | 246462 | 1089649.52 | 2nd Tranche | 281470.42 | 1371119.94 | 1089649.52 | 281470.42 | 100% | 100% | 114.2% | 92.46% | 100% | 2008-12-02 | no data | 2009-02-09 | 2009-04-13 | 2009-05-23 | 63 | 78 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | Salvacion | 166716006 | Const. Of Potable Water System L-II | 1 | 1047252 | 857631 | 189621 | 771867.9 | 2nd Tranche | 219195.6 | 991063.5 | 771867.9 | 219195.6 | 100% | 100% | 115.6% | 94.63% | 100% | 2008-12-02 | no data | 2009-02-12 | 2009-03-28 | 2009-05-23 | 44 | 159 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | Pilar | 166716 | San Roque | 166716007 | Construction of Day Care Center | 1 | 556945 | 410797 | 146148 | 410795.7 | 3rd Tranche | 156670 | 567465.7 | 410795.7 | 156670 | 100% | 100% | 107.2% | 101.9% | 100% | 2008-02-15 | no data | 2008-04-23 | 2008-10-31 | 2009-03-27 | 191 | 119 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Benito | 166718 | Bongdo | 166718001 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 930116.01 | 651081.21 | 279034.8 | 643331.4 | 3rd Tranche | 310466.04 | 953797.44 | 643331.4 | 310466.04 | 100% | 100% | 111.3% | 102.5% | 100% | 2007-01-25 | 2007-02-22 | 2007-04-30 | 2007-07-30 | 2007-11-30 | 91 | 110 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Benito | 166718 | Maribojoc | 166718002 | Const. of Shoreline Protection (Seawall) | 1 | 1403758.22 | 982630.75 | 421127.47 | 982630.75 | 3rd Tranche | 437548.23 | 1420178.98 | 982630.75 | 437548.23 | 100% | 100% | 103.9% | 101.2% | 100% | 2007-01-25 | 2007-02-22 | 2007-04-12 | 2007-07-12 | 2007-11-30 | 91 | 291 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Benito | 166718 | Nuevo Campo | 166718003 | const. of Drainage canal w/ Road Impvt. | 1 | 837252.31 | 625000 | 212252.31 | 625000 | 3rd Tranche | 193782.73 | 818782.73 | 625000 | 193782.73 | 100% | 100% | 91.3% | 97.79% | 100% | 2008-02-26 | no data | 2008-09-08 | 2009-05-18 | 2009-05-22 | 252 | 86 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Benito | 166718 | San Juan | 166718005 | Construction of Sea Wall | 1 | 1299119 | 1020847 | 278272 | 1020847 | 3rd Tranche | 230803.5 | 1251650.5 | 1020847 | 230803.5 | 100% | 100% | 82.94% | 96.35% | 100% | 2008-12-04 | no data | 2009-02-02 | 2009-05-16 | 2009-05-23 | 103 | 113 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Benito | 166718 | Sta Cruz | 166718006 | Construction of Drainage Canal | 1 | 1007632 | 807265 | 200367 | 807265 | 3rd Tranche | 203348.5 | 1010613.5 | 807265 | 203348.5 | 100% | 100% | 101.5% | 100.3% | 100% | 2008-12-04 | no data | 2009-02-03 | 2009-04-04 | 2009-05-23 | 60 | 97 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Benito | 166718 | Talisay | 166718007 | Const . Of Drainage Canal | 1 | 1551140.45 | 1198026.41 | 353114.04 | 1198026.41 | 3rd Tranche | 366507.34 | 1564533.75 | 1198026.41 | 366507.34 | 100% | 100% | 103.8% | 100.9% | 100% | 2008-02-26 | no data | 2008-09-22 | 2008-12-31 | 2009-05-22 | 100 | 302 |  | 1
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Buhing Calipay | 166720001 | Improvement/Upgrading of FMR | 1 | 987296 | 780619 | 206677 | 780619 | 3rd Tranche | 262548.8 | 1043167.8 | 780619 | 262548.8 | 100% | 100% | 127% | 105.7% | 100% | 2005-04-25 | 2005-07-28 | 2005-11-21 | 2006-02-19 | 2006-07-12 | 90 | 65 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Isidro | 166720 | Del Carmen | 166720002 | Construction of 500m from Del Carmen to Bituon FMR | 1 | 925581.39 | 695969.41 | 229611.98 | 695969.41 | 3rd Tranche | 179848.88 | 875818.29 | 695969.41 | 179848.88 | 100% | 100% | 78.33% | 94.62% | 100% | 2007-03-08 | 2007-03-23 | 2007-12-10 | 2008-02-08 | n/a | 60 | 336 |  | 1
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Macapagal | 166720004 | Improvement/Upgrading of FMR | 1 | 467703.34 | 370498 | 97205.34 | 370498 | 3rd Tranche | 84704.55 | 455202.55 | 370498 | 84704.55 | 100% | 100% | 87.14% | 97.33% | 100% | 2006-04-28 | 2006-04-28 | 2006-06-22 | 2006-08-21 | 2006-12-15 | 60 | 32 |  | 1
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Pacifico | 166720006 | Const. Of Potable Water System L-I (5 units jetmatic) | 1 | 198848.42 | 142540.42 | 56308 | 114032 | 1st Tranche | 62743.08 | 176775.08 | 114032 | 62743.08 | 100% | 100% | 111.4% | 88.9% | 100% | 2005-04-25 | 2005-07-28 | 2005-10-14 | 2006-01-12 | 2006-07-13 | 90 | 63 |  | 1
Caraga | 16 | Surigao del Norte | 1667 | San Isidro | 166720 | Pacifico | 166720006 | Construction of 1 unit Day Care Center | 1 | 525888 | 409087.86 | 116800.14 | 409087.85 | 3rd Tranche | 93257.55 | 502345.4 | 409087.85 | 93257.55 | 100% | 100% | 79.84% | 95.52% | 100% | no data | no data | 2008-05-19 | 2008-08-02 | no data | 75 | 52 |  | 1
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Pelaez | 166720007 | Improvement/Upgrading of FMR | 1 | 869302.33 | 698701.33 | 170601 | 698701.33 | 3rd Tranche | 159740.27 | 858441.6 | 698701.33 | 159740.27 | 100% | 100% | 93.63% | 98.75% | 100% | 2005-04-25 | 2005-07-28 | 2005-10-26 | 2006-01-24 | 2006-07-12 | 90 | 97 |  | 1
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Roxas | 166720008 | Improvement/Upgrading of FMR | 1 | 1397397.2 | 1135331 | 262066.2 | 1135331 | 3rd Tranche | 351996.13 | 1487327.13 | 1135331 | 351996.13 | 100% | 100% | 134.3% | 106.4% | 100% | 2006-04-28 | 2006-04-28 | 2006-07-20 | 2006-10-31 | 2006-12-15 | 103 | 192 |  | 1
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | San Miguel | 166720009 | Road Opening/Const of FMR | 1 | 1898494.4 | 1565412 | 333082.4 | 1565412 | 3rd Tranche | 334647.4 | 1900059.4 | 1565412 | 334647.4 | 100% | 100% | 100.5% | 100.1% | 100% | 2006-04-28 | 2006-04-28 | 2006-09-28 | 2007-02-28 | no data | 153 | 39 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | San Isidro | 166720 | San Miguel | 166720009 | Construction of 1 unit Day Care Center | 1 | 536628.98 | 406017.38 | 130611.6 | 396449.26 | 3rd Tranche | 155658.48 | 552107.74 | 396449.26 | 155658.48 | 100% | 100% | 119.2% | 102.9% | 100% | 2007-03-08 | 2007-03-23 | 2007-06-25 | 2007-09-08 | 2007-10-23 | 75 | 37 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | San Isidro | 166720 | Sta. Paz | 166720010 | Improvement of 2.5 km from Ntl Hi-way junction to Brgy Sta Paz FMR | 1 | 2209447.8 | 1688328.33 | 521119.47 | 1688328.32 | 3rd Tranche | 382515.73 | 2070844.05 | 1688328.32 | 382515.73 | 100% | 100% | 73.4% | 93.73% | 100% | 2007-03-08 | 2007-03-23 | 2007-12-10 | 2008-03-09 | n/a | 90 | 128 |  | 1 | LUZON
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Sto. Niño | 166720011 | Const. Of Potable Water System L-II (Spring Dev.) | 1 | 1087359.33 | 852803.33 | 234556 | 767522.33 | 2nd Tranche | 373030.67 | 1140553 | 767522.33 | 373030.67 | 100% | 100% | 159% | 104.9% | 100% | 2005-04-25 | 2005-07-28 | 2005-10-14 | 2006-01-12 | 2006-10-23 | 90 | 88 |  | 1 | LUZON
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Tambacan | 166720012 | Construction of 1 unit Day Care Center | 1 | 478468.82 | 363125.82 | 115343 | 363125.82 | 3rd Tranche | 248550.16 | 611675.98 | 363125.82 | 248550.16 | 100% | 100% | 215.5% | 127.8% | 100% | 2005-04-25 | 2005-07-28 | 2005-11-23 | 2006-02-23 | 2006-07-13 | 92 | 37 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | San Isidro | 166720 | Tambacan | 166720012 | Cons. Of 250m Flood Control Dike | 1 | 430279.67 | 309218.28 | 121061.39 | 301572.08 | 3rd Tranche | 163900.16 | 465472.24 | 301572.08 | 163900.16 | 100% | 100% | 135.4% | 108.2% | 100% | 2007-03-08 | 2007-03-23 | 2007-07-29 | 2007-09-27 | n/a | 60 | 62 |  | 1 | LUZON
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Tigasao | 166720013 | Improvement/Upgrading of FMR | 1 | 971134.33 | 755112.33 | 216022 | 755112.33 | 3rd Tranche | 201080.28 | 956192.61 | 755112.33 | 201080.28 | 100% | 100% | 93.08% | 98.46% | 100% | 2005-04-25 | 2005-07-28 | 2005-11-21 | 2006-02-19 | 2006-11-30 | 90 | 130 |  | 1 | LUZON
Caraga | 16 | Surigao Del Norte | 1667 | San Isidro | 166720 | Tigasao | 166720013 | Construction of 2 CL Elem School Building | 1 | 691491.37 | 523593 | 167898.37 | 523593 | 3rd Tranche | 162483.6 | 686076.6 | 523593 | 162483.6 | 100% | 100% | 96.77% | 99.22% | 100% | 2006-04-28 | 2006-04-28 | 2006-07-03 | 2006-10-01 | 2006-12-15 | 90 | 85 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Del Pilar | 166723001 | Const . of Barangay Health Station | 1 | 739278 | 593190 | 146088 | 593190 | 3rd Tranche | 210208.29 | 803398.29 | 593190 | 210208.29 | 100% | 100% | 143.9% | 108.7% | 100% | 2008-12-05 | no data | 2009-02-13 | 2009-04-02 | 2009-05-26 | 48 | 95 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Doña Helene | 166723002 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 700842.27 | 539110 | 161732.27 | 539110 | 3rd Tranche | 217472.98 | 756582.98 | 539110 | 217472.98 | 100% | 100% | 134.5% | 108% | 100% | 2007-03-02 | 2007-03-02 | 2007-07-18 | 2008-04-30 | 2008-06-30 | 287 | 146 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Honrado | 166723003 | Const . of Barangay Health Station | 1 | 744278 | 597456 | 146822 | 597456 | 3rd Tranche | 142276.62 | 739732.62 | 597456 | 142276.62 | 100% | 100% | 96.9% | 99.39% | 100% | 2008-12-05 | no data | 2009-02-14 | 2009-03-31 | 2009-05-27 | 45 | 91 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Navarro | 166723004 | Cons. Of 399.80 LM drainage Canal w/ RCPC | 1 | 1235926 | 998583 | 237343 | 978144.76 | 3rd Tranche | 329607.54 | 1307752.3 | 978144.76 | 329607.54 | 100% | 100% | 138.9% | 105.8% | 100% | 2008-12-05 | no data | 2009-02-24 | 2009-04-30 | 2009-05-26 | 65 | 468 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Pamosaingan | 166723006 | Const. of Shoreline Protection | 1 | 2242396.93 | 1741742 | 500654.93 | 1741742 | 3rd Tranche | 661043.45 | 2402785.45 | 1741742 | 661043.45 | 100% | 100% | 132% | 107.2% | 100% | 2007-03-02 | 2007-03-02 | 2007-05-03 | 2008-03-30 | 2008-04-15 | 332 | 292 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Rizal | 166723007 | Construction of 1 unit Day Care Center | 1 | 475550.75 | 365808.17 | 109742.58 | 365808.17 | 3rd Tranche | 126803.83 | 492612 | 365808.17 | 126803.83 | 100% | 100% | 115.5% | 103.6% | 100% | 2007-03-02 | 2007-03-02 | 2007-04-24 | 2007-07-22 | 2008-04-15 | 89 | 69 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Rizal | 166723007 | Const. Riza-Navarro FootPathway w/ RCPC | 1 | 2450000 | 1947550 | 502450 | 1752795 | 2nd Tranche | 466658 | 2219453 | 1752795 | 466658 | 100% | 100% | 92.88% | 90.59% | 100% | 2008-03-14 | no data | 2008-09-22 | 2008-12-12 | 2009-05-26 | 81 | 123 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Salog | 166723008 | Const. of 3 Barrels Reinforce Conrete Box Culvert (RCBC) | 1 | 482504.43 | 371238 | 111266.43 | 334114.4 | 2nd Tranche | 129452.28 | 463566.68 | 334114.4 | 129452.28 | 100% | 100% | 116.3% | 96.08% | 100% | 2007-03-02 | 2007-03-02 | 2007-04-28 | 2007-07-27 | 2007-10-15 | 90 | 130 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | San Roque | 166723009 | Const. of San Roque to Tugbungan Pathway | 1 | 1536733.04 | 1182102 | 354631.04 | 1182102 | 3rd Tranche | 291549.81 | 1473651.81 | 1182102 | 291549.81 | 100% | 100% | 82.21% | 95.9% | 100% | 2007-03-02 | 2007-03-02 | 2008-09-01 | 2009-02-08 | 2009-05-27 | 160 | 83 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Slog | 166723008 | Concreting og 430 LM Footpath way | 1 | 1230268 | 823562 | 406706 | 823562 | 3rd Tranche | 89204.62 | 912766.62 | 823562 | 89204.62 | 100% | 100% | 21.93% | 74.19% | 100% | 2008-12-05 | no data | 2009-03-16 | 2009-05-28 | 2009-06-08 | 73 | 131 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Songkoy | 166723012 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 1060000 | 815371 | 244629 | 733833.9 | 2nd Tranche | 270119.5 | 1003953.4 | 733833.9 | 270119.5 | 100% | 100% | 110.4% | 94.71% | 100% | 2008-03-14 | no data | 2008-08-23 | 2008-10-28 | 2008-12-14 | 66 | 129 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Sudlon | 166723013 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 1780000 | 1369165 | 410835 | 1296409.62 | 3rd Tranche | 387868.63 | 1684316.25 | 1296389.62 | 387926.63 | 100% | 100% | 94.41% | 94.62% | 100% | 2008-03-14 | no data | 2008-09-02 | 2008-11-20 | 2009-03-24 | 79 | 183 |  | 1 | LUZON
Caraga | 16 | Surigao del Norte | 1667 | Socorro | 166723 | Albino Taruc | 166723014 | Imp of Drainage Canal | 1 | 1687538 | 1373783 | 313755 | 1236404.7 | 2nd Tranche | 202409.3 | 1438814 | 1236404.7 | 202409.3 | 100% | 100% | 64.51% | 85.26% | 100% | 2008-12-05 | no data | 2009-02-24 | 2009-05-15 | 2009-05-26 | 80 | 488 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Amag | 166802001 | Construction of 2 CL Elem School Building | 1 | 998176.46 | 811483.35 | 186693.11 | 811483.02 | 3rd Tranche | 184889.11 | 996372.13 | 811483.02 | 184889.11 | 100% | 100% | 99.03% | 99.82% | 100% | 2007-02-16 | 2007-02-23 | 2007-05-18 | 2007-12-10 | 2007-12-14 | 206 | 173 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Amag | 166802001 | Construction of 3 Classroom School Building | 1 | 1501752 | 1249596 | 252156 | 1249596 | 3rd Tranche | 251853.36 | 1501449.36 | 1249596 | 251853.36 | 100% | 100% | 99.88% | 99.98% | 100% | 2007-12-17 | no data | 2008-06-04 | 2008-09-30 | 2008-10-22 | 118 | 253 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Balete | 166802002 | Construction of 1 unit One Classroom Elem School | 1 | 778265 | 629022 | 149243 | 566119.8 | 2nd Tranche | 153522 | 719641.8 | 566119.8 | 153522 | 100% | 100% | 102.9% | 92.47% | 100% | 2008-11-22 | no data | 2009-02-16 | 2009-04-21 | 2009-05-13 | 64 | 767 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Cabugo | 166802003 | Construction of 1 unit Box Culvert | 1 | 594467 | 439397 | 155070 | 395457.3 | 2nd Tranche | 154174 | 549631.3 | 395457.3 | 154174 | 100% | 100% | 99.42% | 92.46% | 100% | 2008-11-22 | no data | 2009-02-17 | 2009-04-29 | 2009-05-13 | 71 | 401 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Cagbaoto | 166802004 | Construction of1 Unit Two Classroom Elem School | 1 | 660813 | 523630 | 137183 | 471267 | 2nd Tranche | 143447 | 614714 | 471267 | 143447 | 100% | 100% | 104.6% | 93.02% | 100% | 2008-11-22 | no data | 2009-02-17 | 2009-04-21 | 2009-05-12 | 63 | 780 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | La Paz | 166802005 | Construction of CL Elementary School Building | 1 | 1040649 | 850322 | 190327 | 850322 | 3rd Tranche | 200872.02 | 1051194.02 | 850322 | 200872.02 | 100% | 100% | 105.5% | 101% | 100% | 2007-12-17 | no data | 2008-06-05 | 2008-09-30 | 2008-10-22 | 117 | 420 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Magobawok | 166802006 | Construction of1 Unit Two Classroom Elem School | 1 | 643040 | 507715 | 135325 | 456943.5 | 2nd Tranche | 135264 | 592207.5 | 456943.5 | 135264 | 100% | 100% | 99.95% | 92.09% | 100% | 2008-11-22 | no data | 2009-02-16 | 2009-04-21 | 2009-05-12 | 64 | 969 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Bayabas | 166802 | Panaosawon | 166802007 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1514647.34 | 1243257.29 | 271390.05 | 1243257.29 | 3rd Tranche | 276304.21 | 1519561.5 | 1243257.29 | 276304.21 | 100% | 100% | 101.8% | 100.3% | 100% | 2007-02-16 | 2007-02-23 | 2007-05-09 | 2008-03-31 | 2008-04-22 | 327 | 245 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Alegria | 166814001 | Construction of Day Care Center | 1 | 592100 | 451357.33 | 140742.67 | 451357.33 | 3rd Tranche | 163080.31 | 614437.64 | 451357.33 | 163080.31 | 100% | 100% | 115.9% | 103.8% | 100% | 2008-05-16 | no data | 2008-08-18 | 2008-10-30 | no data | 73 | 141 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Amontay | 166814002 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1586419 | 1104500 | 481919 | 994050 | 2nd Tranche | 260094.85 | 1254144.85 | 994050 | 260094.85 | 100% | 100% | 53.97% | 79.06% | 100% | 2007-02-22 | 2007-03-09 | 2007-05-10 | 2008-10-30 | 2009-05-07 | 539 | 133 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Antipolo | 166814003 | Construction of1 Unit Two Classroom Elem School | 1 | 1342758 | 1074967 | 267791 | 967506.5 | 2nd Tranche | 229911 | 1197417.5 | 967506.5 | 229911 | 100% | 100% | 85.85% | 89.18% | 100% | 2008-11-20 | no data | 2009-02-08 | 2009-04-26 | 2009-05-07 | 77 | 273 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Arorogan | 166814004 | Construction of Day Care Center | 1 | 714182 | 552320 | 161862 | 497078.5 | 2nd Tranche | 149410 | 646488.5 | 497078.5 | 149410 | 100% | 100% | 92.31% | 90.52% | 100% | 2008-11-20 | no data | 2009-02-05 | 2009-03-31 | 2009-05-07 | 54 | 299 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Bayan | 166814005 | Construction of Day Care Center | 1 | 592100 | 451357.33 | 140742.67 | 451357.33 | 3rd Tranche | 168205.21 | 619562.54 | 451357.33 | 168205.21 | 100% | 100% | 119.5% | 104.6% | 100% | 2008-05-16 | no data | 2008-07-21 | 2008-10-30 | 2009-02-19 | 101 | 23 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Mahaba | 166814006 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 1545057 | 1081540 | 463517 | 973386 | 2nd Tranche | 336214.85 | 1309600.85 | 973386 | 336214.85 | 100% | 100% | 72.54% | 84.76% | 100% | 2007-02-22 | 2007-03-09 | 2008-08-22 | 2008-11-10 | 2009-05-08 | 80 | 83 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Mararag | 166814007 | Construction of Day Care Center | 1 | 592100 | 451357.33 | 140742.67 | 451357.33 | 2nd Tranche | 168117.21 | 619474.54 | 451357.33 | 168117.21 | 100% | 100% | 119.5% | 104.6% | 100% | 2008-05-16 | no data | 2008-07-21 | 2008-10-30 | 2009-02-24 | 101 | 40 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Mararag | 166814007 | Construction of Barangay Health Station | 1 | 828081 | 665688 | 162393 | 579880.67 | 2nd Tranche | 138658 | 718538.67 | 579880.67 | 138658 | 100% | 100% | 85.38% | 86.77% | 100% | 2008-11-20 | no data | 2009-02-10 | 2009-04-17 | 2009-05-08 | 66 | 380 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Poblacion | 166814008 | Construction of 3 CL HS School Building | 1 | 1495437.89 | 1046800 | 448637.89 | 1046800 | 3rd Tranche | 248026.9 | 1294826.9 | 1046800 | 248026.9 | 100% | 100% | 55.28% | 86.59% | 100% | 2007-02-22 | 2007-03-09 | 2007-04-10 | 2007-10-15 | 2007-10-16 | 188 | 633 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Poblacion | 166814008 | Construction of 1 Unit Two Classroom Elem School | 1 | 1262382 | 1013522 | 248860 | 912144.75 | 2nd Tranche | 232780 | 1144924.75 | 912144.75 | 232780 | 100% | 100% | 93.54% | 90.7% | 100% | 2008-11-20 | no data | 2009-02-08 | 2009-03-31 | 2009-05-07 | 51 | 747 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | San Antonio | 166814009 | Construction of 1 unit Day Care Center | 1 | 499933.9 | 349960 | 149973.9 | 338479.37 | 3rd Tranche | 127513.6 | 465992.97 | 338479.37 | 127513.6 | 100% | 100% | 85.02% | 93.21% | 100% | 2007-02-22 | 2007-03-09 | 2007-04-10 | 2007-06-24 | 2007-10-22 | 75 | 40 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | San Isidro | 166814010 | Construction of Water System Level II | 1 | 1545716.54 | 1213162 | 332554.54 | 1091845.8 | 2nd Tranche | 345871.4 | 1437717.2 | 1091845.8 | 345871.4 | 100% | 100% | 104% | 93.01% | 100% | 2008-05-16 | no data | 2007-05-10 | 2008-10-30 | 2009-05-08 | 539 | 321 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | San Pedro | 166814011 | Construction of Day Care Center | 1 | 592100 | 451357.33 | 140742.67 | 451322.23 | 3rd Tranche | 142495.21 | 593817.44 | 451322.23 | 142495.21 | 100% | 100% | 101.2% | 100.3% | 100% | 2008-05-16 | no data | 2008-08-14 | 2008-10-30 | 2009-03-26 | 77 | 40 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Marihatag | 166814 | Sta. Cruz | 166814012 | Construction of 1 CL School Building | 1 | 709020.1 | 535177.66 | 173842.44 | 535177.66 | 3rd Tranche | 141931.08 | 677108.74 | 535177.66 | 141931.08 | 100% | 100% | 81.64% | 95.5% | 100% | 2008-05-16 | no data | 2008-08-22 | 2008-11-10 | no data | 80 | 141 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Bolhoon | 166816004 | Construction of Hanging foot Bridge | 1 | 2355837.11 | 1822371.11 | 533466 | 1822371.11 | 3rd Tranche | 561998.75 | 2384369.86 | 1822371.11 | 561998.75 | 100% | 100% | 105.3% | 101.2% | 100% | 2005-04-08 | 2005-07-26 | 2005-10-05 | 2006-02-02 | 2006-01-20 | 120 | 570 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | San Miguel | 166816 | Bolhoon | 166816004 | Const. of 1 Unit Brgy. Health Station | 1 | 574123 | 386448 | 187675 | 375637.72 | 3rd Tranche | 127289.65 | 502927.37 | 375637.72 | 127289.65 | 100% | 100% | 67.82% | 87.6% | 100% | 2007-03-26 | 2007-04-24 | 2007-05-28 | 2007-08-10 | no data | 74 | 769 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Caromata | 166816006 | Construction of 3 CL Elem School Building | 1 | 1347337 | 951007 | 396330 | 951007 | 3rd Tranche | 448946.75 | 1399953.75 | 951007 | 448946.75 | 100% | 100% | 113.3% | 103.9% | 100% | 2005-04-08 | 2005-07-26 | 2005-09-07 | 2005-12-05 | 2005-11-29 | 89 | 205 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | San Miguel | 166816 | Caromata | 166816006 | Improvement of Carromata - Umalag Junction FMR | 1 | 2569453 | 1624417 | 945036 | 1624417 | 3rd Tranche | 536227.07 | 2160644.07 | 1624417 | 536227.07 | 100% | 100% | 56.74% | 84.09% | 100% | 2007-03-26 | 2007-04-24 | 2007-06-01 | 2007-09-28 | n/a | 119 | 344 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | San Miguel | 166816 | Castillo | 166816007 | Construction of 1 unit Day Care Center | 1 | 574123 | 386448 | 187675 | 380918.16 | 3rd Tranche | 137289.65 | 518207.81 | 380918.16 | 137289.65 | 100% | 100% | 73.15% | 90.26% | 100% | 2007-03-26 | 2007-04-24 | 2007-05-28 | 2007-08-10 | no data | 74 | 60 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Libas Gua | 166816008 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 2961174.13 | 2072710.13 | 888464 | 2072710.13 | 3rd Tranche | 608042 | 2680752.13 | 2072710.13 | 608042 | 100% | 100% | 68.44% | 90.53% | 100% | 2006-03-24 | 2006-04-17 | 2006-05-24 | 2006-11-30 | 2007-03-05 | 190 | 204 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Magroyong | 166816010 | Construction of Retaining Wall | 1 | 1311947.12 | 898457.12 | 413490 | 808611.41 | 2nd Tranche | 309691.42 | 1118302.83 | 808611.41 | 309691.42 | 100% | 100% | 74.9% | 85.24% | 100% | 2006-03-24 | 2006-04-17 | 2006-05-17 | 2006-09-13 | 2006-08-18 | 119 | 267 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Mahayag | 166816011 | Construction of 4 CL HS School Building | 1 | 1603401 | 1148551 | 454850 | 1148551 | 3rd Tranche | 602261.37 | 1750812.37 | 1148551 | 602261.37 | 100% | 100% | 132.4% | 109.2% | 100% | 2005-04-08 | 2005-07-26 | 2005-09-12 | 2006-01-09 | 2005-11-29 | 119 | 272 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | San Miguel | 166816 | Patong | 166816012 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 2894740 | 1805044 | 1089696 | 1805044 | 3rd Tranche | 645690 | 2428026.45 | 1782336.45 | 645690 | 98.74% | 100% | 59.25% | 83.88% | 100% | 2007-03-26 | 2007-04-24 | 2007-06-01 | 2008-04-28 | n/a | 332 | 223 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Poblacion | 166816013 | Improvement of Drainage System | 1 | 1556606.95 | 1089666.95 | 466940 | 1089666.95 | 3rd Tranche | 317933.39 | 1407600.34 | 1089666.95 | 317933.39 | 100% | 100% | 68.09% | 90.43% | 100% | 2006-03-24 | 2006-04-17 | 2006-05-18 | 2006-10-31 | no data | 166 | 511 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Sagbayan | 166816014 | Construction of 2 CL HS School Building | 1 | 856093.54 | 454640 | 401453.54 | 454640 | 3rd Tranche | 532928 | 987568 | 454640 | 532928 | 100% | 100% | 132.7% | 115.4% | 100% | 2006-03-24 | 2006-04-17 | 2006-05-15 | 2006-08-12 | 2006-12-13 | 89 | 261 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | San Miguel | 166816 | San Roque | 166816016 | Construction of 3 CL HS School Building | 1 | 1717620 | 1197643 | 519977 | 1197643 | 3rd Tranche | 419028.63 | 1616671.63 | 1197643 | 419028.63 | 100% | 100% | 80.59% | 94.12% | 100% | 2007-03-26 | 2007-04-24 | 2007-05-28 | 2007-09-24 | n/a | 119 | 155 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Siagao | 166816017 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 2123280.89 | 1478070.89 | 645210 | 1478070.89 | 3rd Tranche | 661987.75 | 2140058.64 | 1478070.89 | 661987.75 | 100% | 100% | 102.6% | 100.8% | 100% | 2005-04-08 | 2005-07-26 | 2005-09-19 | 2006-01-17 | 2006-04-20 | 120 | 274 |  | 1 | LUZON
Caraga | 16 | Surigao Del Sur | 1668 | San Miguel | 166816 | Tina | 166816019 | Construction of Solar Drier w/ Warehouse | 1 | 1263680.96 | 884525.8 | 379155.16 | 884525.8 | 3rd Tranche | 276905.16 | 1161430.96 | 884525.8 | 276905.16 | 100% | 100% | 73.03% | 91.91% | 100% | 2006-03-24 | 2006-04-17 | 2006-05-16 | 2006-09-12 | 2006-10-20 | 119 | 425 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Batunan | 166817001 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 945041.02 | 737671.23 | 207369.79 | 663904.1 | 2nd Tranche | 250848.87 | 914752.97 | 663904.1 | 250848.87 | 100% | 100% | 121% | 96.8% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-03 | 2007-10-30 | 2008-06-24 | 180 | 79 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Carpenito | 166817002 | Imp of Hanging Bridge | 1 | 1512397 | 1218105 | 294292 | 1096294 | 2nd Tranche | 281887 | 1378181 | 1096294 | 281887 | 100% | 100% | 95.78% | 91.13% | 100% | 2008-11-21 | no data | 2009-03-10 | 2009-05-29 | 2009-06-05 | 80 | 209 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Hinagdanan | '166817026 | Construction of 1 Unit Health Station | 1 | 666564.91 | 517345.08 | 149219.83 | 517345 | 3rd Tranche | 174765.2 | 692110.2 | 517345 | 174765.2 | 100% | 100% | 117.1% | 103.8% | 100% | 2008-03-17 | 2008-04-02 | 2008-08-12 | 2008-11-29 | 2009-02-23 | 109 | 189 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Kahayagan | 166817003 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 1630363.8 | 1224233.7 | 406130.1 | 1101810.33 | 2nd Tranche | 405136.21 | 1506946.54 | 1101810.33 | 405136.21 | 100% | 100% | 99.76% | 92.43% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-08 | 2008-03-20 | 2008-06-24 | 317 | 315 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Lago | 166817004 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 658117.12 | 494305.11 | 163812.01 | 444874.6 | 2nd Tranche | 157290.86 | 602165.46 | 444874.6 | 157290.86 | 100% | 100% | 96.02% | 91.5% | 100% | 2007-02-15 | 2007-02-26 | 2007-06-22 | 2007-11-20 | 2008-11-25 | 151 | 140 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Maglambing | 166817006 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1219817.94 | 915724.49 | 304093.45 | 824152.04 | 2nd Tranche | 322277.46 | 1146429.5 | 824152.04 | 322277.46 | 100% | 100% | 106% | 93.98% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-05 | 2008-01-18 | 2008-07-29 | 258 | 133 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Maglatab | 166817007 | Const. Of Potable Water System L-II | 1 | 1659749.12 | 890023.26 | 769725.86 | 890023.26 | 3rd Tranche | 777411.4 | 1667434.66 | 890023.26 | 777411.4 | 100% | 100% | 101% | 100.5% | 100% | 2008-03-17 | 2008-04-02 | 2008-09-08 | 2008-11-24 | 2009-02-23 | 77 | 183 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Magsaysay | 166817008 | Const. Of Potable Water System L-II | 1 | 1400327.06 | 1094685.82 | 305641.24 | 1094685.82 | 3rd Tranche | 320629.84 | 1415315.66 | 1094685.82 | 320629.84 | 100% | 100% | 104.9% | 101.1% | 100% | 2008-03-17 | 2008-04-02 | 2008-06-25 | 2008-11-19 | 2009-02-24 | 147 | 156 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Malixi | 166817009 | Const. Of Potable Water System L-II | 1 | 1799300.73 | 1395408.78 | 403891.95 | 1325638.07 | 3rd Tranche | 433777.86 | 1759415.93 | 1325638.07 | 433777.86 | 100% | 100% | 107.4% | 97.78% | 100% | 2008-03-17 | 2008-04-02 | 2008-08-16 | 2009-02-11 | 2009-03-19 | 179 | 151 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Manambia | 166817010 | Imp of USA Bridge | 1 | 3117891 | 1290775 | 1827116 | 1232988.18 | 3rd Tranche | 153592.54 | 1386580.72 | 1232988.18 | 153592.54 | 100% | 100% | 8.406% | 44.47% | 100% | 2008-11-21 | no data | 2009-03-10 | 2009-06-22 | 2009-06-22 | 104 | 160 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Osmeña | 166817011 | Const. Of Potable Water System L-II | 1 | 1325514 | 1132391 | 193123 | 1019152.3 | 2nd Tranche | 167316.52 | 1186468.82 | 1019152.3 | 167316.52 | 100% | 100% | 86.64% | 89.51% | 100% | 2008-11-21 | no data | 2009-02-11 | 2009-04-17 | 2009-06-05 | 65 | 156 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Quezon | 166817013 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1161026.4 | 871354.32 | 289672.08 | 784218.89 | 2nd Tranche | 307856.83 | 1092075.72 | 784218.89 | 307856.83 | 100% | 100% | 106.3% | 94.06% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-10 | 2008-01-16 | 2008-07-29 | 251 | 140 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Quezon | 166817013 | Const . of Barangay Health Station | 1 | 711194 | 522433 | 188761 | 522433 | 3rd Tranche | 248066 | 770499 | 522433 | 248066 | 100% | 100% | 131.4% | 108.3% | 100% | 2008-11-21 | no data | 2009-02-06 | 2009-04-08 | 2009-04-28 | 61 | 312 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | San Vicente | 166817014 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 1655301.77 | 1304140.19 | 351161.58 | 1304140.19 | 3rd Tranche | 391808.94 | 1695949.13 | 1304140.19 | 391808.94 | 100% | 100% | 111.6% | 102.5% | 100% | 2008-03-17 | 2008-04-02 | 2008-06-26 | 2008-11-28 | 2009-03-19 | 155 | 199 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Sayon | 166817019 | Const. Of Potable Water System L-II (Pump Driven) | 1 | 1001943.42 | 753543.75 | 248399.67 | 678189.38 | 2nd Tranche | 239339.2 | 917528.58 | 678189.38 | 239339.2 | 100% | 100% | 96.35% | 91.57% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-17 | 2007-10-30 | no data | 166 | 91 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Soriano | 166817020 | Construction of 1 unit Day Care Center | 1 | 568753.85 | 399486.97 | 169266.88 | 359538.2 | 2nd Tranche | 167704.26 | 527242.46 | 359538.2 | 167704.26 | 100% | 100% | 99.08% | 92.7% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-21 | 2007-10-30 | 2008-07-29 | 162 | 176 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Sta Cruz | 166817015 | Inst Of Rice and Corn Mill | 1 | 1639089 | 1430000 | 209089 | 1382360 | 3rd Tranche | 355981 | 1738341 | 1382360 | 355981 | 100% | 100% | 170.3% | 106.1% | 100% | 2008-11-21 | no data | 2009-02-25 | 2009-05-14 | 2009-06-19 | 78 | 153 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Sta Fe. | 166817016 | Const. Of Potable Water System L-II | 1 | 1187070.66 | 926498.02 | 260572.64 | 926498.02 | 1st Tranche | 304779.27 | 1231277.29 | 926498.02 | 304779.27 | 100% | 100% | 117% | 103.7% | 100% | 2008-03-17 | 2008-04-02 | 2008-06-21 | 2008-12-17 | 2009-02-23 | 179 | 34 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Sta. Juana | 166817017 | Construction of 4 CL HS School Building | 1 | 1583096.77 | 1193944.43 | 389152.34 | 1193944.43 | 3rd Tranche | 399965.35 | 1593909.78 | 1193944.43 | 399965.35 | 100% | 100% | 102.8% | 100.7% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-21 | 2007-11-16 | 2007-11-26 | 179 | 405 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Sta. Maria | 166817018 | Const. Of Potable Water System L-II | 1 | 1749658.34 | 1371898.85 | 377759.49 | 1371898.85 | 3rd Tranche | 422077.14 | 1793975.99 | 1371898.85 | 422077.14 | 100% | 100% | 111.7% | 102.5% | 100% | 2008-03-17 | 2008-04-02 | 2008-06-28 | 2008-11-20 | 2009-02-24 | 145 | 375 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Tagongon | 166817021 | Const . of Barangay Health Station | 1 | 716194 | 586573 | 129621 | 527916.3 | 2nd Tranche | 295674.38 | 823590.68 | 527916.3 | 295674.38 | 100% | 100% | 228.1% | 115% | 100% | 2008-11-21 | no data | 2009-02-16 | 2009-03-28 | 2009-04-28 | 40 | 469 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Trinidad | 166817022 | Inst Of Rice and Corn Mill | 1 | 1639089 | 1319723 | 319366 | 1295149 | 3rd Tranche | 1817117 | 3112266 | 1295149 | 1817117 | 100% | 100% | 569% | 189.9% | 100% | 2008-11-21 | no data | 2009-02-17 | 2009-06-15 | 2009-06-19 | 118 | 100 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Ugoban | 166817023 | Const. Of Potable Water System L-II (Gravity Driven) | 1 | 1210562 | 909736 | 300826 | 818762.4 | 2nd Tranche | 322816.42 | 1141578.82 | 818762.4 | 322816.42 | 100% | 100% | 107.3% | 94.3% | 100% | 2007-02-15 | 2007-02-26 | 2007-05-22 | 2007-09-14 | 2007-11-26 | 115 | 176 |  | 1 | LUZON
Caraga | 16 | Surigao del Sur | 1668 | Tagbina | 166817 | Villaverde | 166817024 | Const . of Barangay Health Station | 1 | 721195 | 630605 | 90590 | 611482 | 3rd Tranche | 200367.66 | 811849.66 | 611482 | 200367.66 | 100% | 100% | 221.2% | 112.6% | 100% | 2008-11-21 | no data | 2009-02-12 | 2009-04-04 | 2009-04-28 | 51 | 360 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Bagong Silang | 045605002 | Day Care Center | 1 | 713489.5 | 435439.5 | 278050 | 435439.5 | 3rd Tranche | 295749 | 731188.5 | 435439.5 | 295749 | 100% | 100% | 106.4% | 102.5% | 100% | 2005-08-19 | 2005-09-12 | 2005-12-07 | 2006-03-31 | no data | 114 | 199 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Bagong Silang | 045605002 | 1 Classroom School Building | 1 | 523341 | 360262.31 | 163078.69 | 360262.3 | 3rd Tranche | 162078.69 | 522340.99 | 360262.3 | 162078.69 | 100% | 100% | 99.39% | 99.81% | 100% | 2006-03-30 | 2006-03-30 | 2006-07-08 | 2006-12-30 | no data | 175 | 199 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Buenavista | 045605006 | Re-Gravelling of 2.2 km FMR | 1 | 5085529 | 3473406.92 | 1612122.08 | 3473406.91 |  | 1451709.25 | 4925116.16 | 3473406.91 | 1451709.25 | 100% | 100% | 90.05% | 96.85% | 100% | 2006-03-30 | 2006-03-30 | 2007-05-15 | 2009-06-10 | n/a | 757 | 66 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Bukal | 045605007 | Level II Water Supply System | 1 | 965488 | 396082.91 | 569405.09 | 396082.91 | 3rd Tranche | 232109.26 | 628192.17 | 396082.91 | 232109.26 | 100% | 100% | 40.76% | 65.06% | 100% | 2005-08-19 | 2005-09-12 | 2006-01-16 | 2006-07-01 | no data | 166 | 288 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Bulo | 045605008 | Road Concreting | 1 | 1782663.8 | 1063588.31 | 719075.49 | 1063588.31 | 3rd Tranche | 601239.44 | 1664827.75 | 1063588.31 | 601239.44 | 100% | 100% | 83.61% | 93.39% | 100% | 2003-11-19 | 2003-12-22 | 2004-06-18 | 2004-08-21 | no data | 64 | 117 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cabong | 045605009 | 2 Classroom School Building | 1 | 890000 | 582000 | 308000 | 582000 | 3rd Tranche | 339078 | 921078 | 582000 | 339078 | 100% | 100% | 110.1% | 103.5% | 100% | 2003-11-19 | 2003-12-22 | 2004-09-16 | 2005-05-05 | no data | 231 | 150 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cabong | 045605009 | Re-Gravelling & Widening of 2.5 km FMR | 1 | 3420779.5 | 2416291.92 | 1004487.58 | 2416291.92 |  | 807887.58 | 3224179.5 | 2416291.92 | 807887.58 | 100% | 100% | 80.43% | 94.25% | 100% | 2006-03-30 | 2006-03-30 | 2007-01-26 | 2007-03-26 | n/a | 59 | 150 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cadlit | 045605010 | 432m Line Canal | 1 | 842861.25 | 538487.11 | 304374.14 | 538487.11 | 3rd Tranche | 334082.89 | 872570 | 538487.11 | 334082.89 | 100% | 100% | 109.8% | 103.5% | 100% | 2003-11-19 | 2003-12-22 | 2004-06-15 | 2004-10-05 | no data | 112 | 118 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Catulin | 045605011 | Day Care Center | 1 | 400000 | 234615.4 | 165384.6 | 234615.4 | 3rd Tranche | 153238.35 | 387853.75 | 234615.4 | 153238.35 | 100% | 100% | 92.66% | 96.96% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-24 | 2005-03-20 | no data | 300 | 86 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cawa | 045605012 | Level II Water Supply System | 1 | 416636 | 247258.5 | 169377.5 | 247258.5 | 3rd Tranche | 174759.85 | 422018.35 | 247258.5 | 174759.85 | 100% | 100% | 103.2% | 101.3% | 100% | 2003-11-19 | 2003-12-22 | 2004-04-26 | 2004-10-15 | no data | 172 | 124 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Cawa | 045605012 | 2.8 km Road upgrading | 1 | 3389304.5 | 1666080.38 | 1723224.12 | 1666080.38 | 3rd Tranche | 655149.12 | 2321229.5 | 1666080.38 | 655149.12 | 100% | 100% | 38.02% | 68.49% | 100% | 2005-08-19 | 2005-09-12 | 2006-02-20 | 2006-08-30 | no data | 191 | 124 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Del Rosario | 045605014 | 1.8 km FMR upgrading | 1 | 2628271 | 1659484 | 968787 | 1659484 | 3rd Tranche | 727828.56 | 2387312.56 | 1659484 | 727828.56 | 100% | 100% | 75.13% | 90.83% | 100% | 2005-08-19 | 2005-09-12 | 2006-03-24 | 2007-05-22 | no data | 424 | 105 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Mabutag | 045605021 | 2.05 km Road upgrading | 1 | 2925265 | 1586934.62 | 1338330.38 | 1586934.62 | 3rd Tranche | 562530.38 | 2149465 | 1586934.62 | 562530.38 | 100% | 100% | 42.03% | 73.48% | 100% | 2005-08-19 | 2005-09-12 | 2006-02-09 | 2006-03-31 | no data | 50 | 137 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Maligaya (Esperanza) | 045605023 | 4 Classroom School Building with CR | 1 | 1779999.1 | 1087128.1 | 692871 | 1087128.1 | 3rd Tranche | 598184.94 | 1685313.04 | 1087128.1 | 598184.94 | 100% | 100% | 86.33% | 94.68% | 100% | 2003-11-19 | 2003-12-22 | 2004-06-07 | 2005-06-29 | 2005-01-16 | 387 | 135 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Manlana | 045605024 | Health Station | 1 | 441000 | 260307.69 | 180692.31 | 260307.69 | 3rd Tranche | 180259.56 | 440567.25 | 260307.69 | 180259.56 | 100% | 100% | 99.76% | 99.9% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-20 | 2005-03-01 | no data | 285 | 118 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Manlana | 045605024 | Re-Gravelling & Widening of 2.14 km FMR | 1 | 2972836.04 | 2121989.26 | 850846.78 | 2121989.26 | 3rd Tranche | 722201.18 | 2844190.44 | 2121989.26 | 722201.18 | 100% | 100% | 84.88% | 95.67% | 100% | 2006-03-30 | 2006-03-30 | 2006-06-15 | 2006-11-30 | no data | 168 | 118 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Masaya - C2 | 045605025 | 3.895 km joint FMR upgrading | 2 | 5521582.43 | 3740515 | 1781067.43 | 3740515 | 3rd Tranche | 1362276 | 5102791 | 3740515 | 1362276 | 100% | 100% | 76.49% | 92.42% | 100% | 2005-08-19 | 2005-09-12 | 2006-03-26 | 2006-11-30 | no data | 249 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Villa Aurora | 045605038 | 3.895 km joint FMR upgrading | 2 | 5521582.43 | 3740515 | 1781067.43 | 3740515 | 3rd Tranche | 1362276 | 5102791 | 3740515 | 1362276 | 100% | 100% | 76.49% | 92.42% | 100% | 2005-08-19 | 2005-09-12 | 2006-03-26 | 2006-11-30 | no data | 249 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Pinamasagan (Sabang) | 045605028 | Day Care Center | 1 | 400000 | 249107.7 | 150892.3 | 249107.7 | 3rd Tranche | 306781.3 | 555889 | 249107.7 | 306781.3 | 100% | 100% | 203.3% | 139% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-20 | 2005-03-01 | no data | 285 | 61 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Sabang Piris | 045605029 | 100m Seawall | 1 | 461895 | 257765.35 | 204129.65 | 257765.35 | 3rd Tranche | 287581.8 | 545347.15 | 257765.35 | 287581.8 | 100% | 100% | 140.9% | 118.1% | 100% | 2003-11-19 | 2003-12-22 | 2004-04-21 | 2004-10-28 | no data | 190 | 86 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Sabang Piris | 045605029 | 300 m Retaining wall | 1 | 1602535 | 666630 | 935905 | 666630 | 3rd Tranche | 857640 | 1524270 | 666630 | 857640 | 100% | 100% | 91.64% | 95.12% | 100% | 2005-08-19 | 2005-09-12 | 2006-01-14 | 2006-03-31 | no data | 76 | 86 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | San Diego | 045605030 | Health Station | 1 | 441000 | 231538.45 | 209461.55 | 231538.45 | 3rd Tranche | 95762.78 | 327301.23 | 231538.45 | 95762.78 | 100% | 100% | 45.72% | 74.22% | 100% | 2003-11-19 | 2003-12-22 | 2004-06-01 | 2005-04-01 | 2005-04-11 | 304 | 124 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | San Isidro Ibaba | 045605031 | Health Station | 1 | 441000 | 262307.7 | 178692.3 | 262307.7 | 3rd Tranche | 181961.05 | 444268.75 | 262307.7 | 181961.05 | 100% | 100% | 101.8% | 100.7% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-27 | 2005-06-10 | no data | 379 | 81 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | San Isidro Ilaya | 045605032 | Health Station | 1 | 441000 | 230297.88 | 210702.12 | 230297.88 | 3rd Tranche | 211173.56 | 441471.44 | 230297.88 | 211173.56 | 100% | 100% | 100.2% | 100.1% | 100% | 2003-11-19 | 2003-12-22 | 2004-06-01 | 2005-08-05 | no data | 430 | 92 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | San Pablo | 045605033 | Upgrading of 1.6 km FMR | 1 | 1961131.5 | 1328505 | 632626.5 | 1195654.5 | 2nd Tranche | 601763.55 | 1797418.05 | 1195654.5 | 601763.55 | 100% | 100% | 95.12% | 91.65% | 100% | 2006-03-30 | 2006-03-30 | 2006-06-15 | 2006-09-29 | no data | 106 | 82 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | San Pedro (Villa Rodrigo) | 045605034 | Farm To Market Road | 1 | 1439271.55 | 966385.73 | 472885.82 | 966385.73 | 3rd Tranche | 39564.3 | 1005950.03 | 966385.73 | 39564.3 | 100% | 100% | 8.367% | 69.89% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-19 | 2004-07-10 | no data | 52 | 121 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Siain | 045605036 | 2.23 km Farm To Market Road | 1 | 2214948.75 | 1363045.38 | 851903.37 | 1226740.84 | 2nd Tranche | 499236.37 | 1725977.21 | 1226740.84 | 499236.37 | 100% | 100% | 58.6% | 77.92% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-13 | 2006-07-10 | no data | 788 | 56 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Villa Batabat | 045605039 | Level II Water Supply System | 1 | 574826 | 360677.1 | 214148.9 | 360677.1 | 3rd Tranche | 231359.26 | 592036.36 | 360677.1 | 231359.26 | 100% | 100% | 108% | 103% | 100% | 2003-11-19 | 2003-12-22 | 2004-07-01 | 2005-07-01 | 2005-08-01 | 365 | 114 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Villa Batabat | 045605039 | 6.825 km Electrification | 1 | 1460942.82 | 948833.21 | 512109.61 | 948833.21 | 3rd Tranche | 525254.58 | 1474087.79 | 948833.21 | 525254.58 | 100% | 100% | 102.6% | 100.9% | 100% | 2005-08-19 | 2005-09-12 | 2006-02-17 | 2006-03-31 | no data | 42 | 114 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Villa Magsaysay | 045605040 | 2.06 km Farm To Market Road | 1 | 1590844.5 | 1056138.85 | 534705.65 | 950525.03 | 2nd Tranche | 385478.83 | 1336003.86 | 950525.03 | 385478.83 | 100% | 100% | 72.09% | 83.98% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-24 | 2005-07-22 | no data | 424 | 121 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Villa Veronica | 045605042 | Farm To Market Road | 1 | 2176083 | 1327424.6 | 848658.4 | 1327424.6 | 3rd Tranche | 898157.5 | 2225582.1 | 1327424.6 | 898157.5 | 100% | 100% | 105.8% | 102.3% | 100% | 2003-11-19 | 2003-12-22 | 2004-06-22 | 2005-11-01 | no data | 497 | 71 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Ibabang Wasay | 045605017 | 200m Seawall | 1 | 893004 | 519618.45 | 373385.55 | 519618.45 | 3rd Tranche | 376606.55 | 896225 | 519618.45 | 376606.55 | 100% | 100% | 100.9% | 100.4% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-03 | 2004-09-23 | no data | 143 | 126 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Ilayang Wasay | 045605018 | Health Station | 1 | 441000.01 | 262307.7 | 178692.31 | 262307.7 | 3rd Tranche | 214234.47 | 476542.17 | 262307.7 | 214234.47 | 100% | 100% | 119.9% | 108.1% | 100% | 2003-11-19 | 2003-12-22 | 2004-05-20 | 2005-03-01 | no data | 285 | 119 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Buenavista | 045605 | Ilayang Wasay | 045605018 | Spring Development Water System Level II | 1 | 1908295 | 1344073.08 | 564221.92 | 1344073.08 | 3rd Tranche | 564221.92 | 1908295 | 1344073.08 | 564221.92 | 100% | 100% | 100% | 100% | 100% | 2006-03-30 | 2006-03-30 | 2006-07-15 | 2006-11-30 | no data | 138 | 119 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Aluyon | 045606001 | 5.72 km Road rehabilitation | 1 | 4650000 | 2636716.1 | 2013283.9 | 2636716.1 | 3rd Tranche | 2014283.9 | 4651000 | 2636716.1 | 2014283.9 | 100% | 100% | 100% | 100% | 100% | 2005-06-25 | 2005-08-30 | 2006-03-26 | 2006-10-31 | no data | 219 | 400 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Amot | 045606002 | 3.70 km Road rehabilitation | 1 | 2176000 | 1563283.9 | 612716.1 | 1563283.9 | 3rd Tranche | 612629.09 | 2175912.99 | 1563283.9 | 612629.09 | 100% | 100% | 99.99% | 100% | 100% | 2005-06-25 | 2005-08-30 | 2006-03-06 | 2006-06-01 | no data | 87 | 132 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Amot | 045606002 | Bridge | 1 | 379000 | 232615.38 | 146384.62 | 232615.38 | 3rd Tranche | 145384.62 | 378000 | 232615.38 | 145384.62 | 100% | 100% | 99.32% | 99.74% | 100% | 2006-05-09 | 2006-05-09 | 2006-08-15 | 2006-11-30 | no data | 107 | 132 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Anibawan | 045606003 | Day Care Center | 1 | 400000 | 201180.77 | 198819.23 | 201180.77 | 3rd Tranche | 167781.08 | 368961.85 | 201180.77 | 167781.08 | 100% | 100% | 84.39% | 92.24% | 100% | 2003-10-28 | 2003-12-18 | 2004-02-28 | 2005-04-19 | 2005-04-20 | 416 | 256 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Bonifacio | 045606004 | Light House | 1 | 187247.32 | 119082.55 | 68164.77 | 119082.55 | 3rd Tranche | 75463.46 | 194546.01 | 119082.55 | 75463.46 | 100% | 100% | 110.7% | 103.9% | 100% | 2003-10-28 | 2003-12-18 | 2004-05-30 | 2005-05-05 | no data | 340 | 178 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Bonifacio | 045606004 | Pathway concreting | 1 | 1123000 | 689230.77 | 433769.23 | 689230.77 | 3rd Tranche | 431169.23 | 1120400 | 689230.77 | 431169.23 | 100% | 100% | 99.4% | 99.77% | 100% | 2006-05-09 | 2006-05-09 | 2006-09-10 | 2006-11-30 | no data | 81 | 178 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Cabugao | 045606005 | Farm To Market Road | 1 | 1998900 | 1373144.31 | 625755.69 | 1373144.31 | 3rd Tranche | 533521.2 | 1906665.51 | 1373144.31 | 533521.2 | 100% | 100% | 85.26% | 95.39% | 100% | 2003-10-28 | 2003-12-18 | 2004-03-29 | 2005-03-15 | 2005-06-26 | 351 | 189 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Cabugao | 045606005 | Rehab. CIS | 1 | 457000 | 280615.38 | 176384.62 | 280615.38 | 3rd Tranche | 175684.62 | 456300 | 280615.38 | 175684.62 | 100% | 100% | 99.6% | 99.85% | 100% | 2006-05-09 | 2006-05-09 | 2006-08-10 | 2006-11-30 | no data | 112 | 189 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Cabungalunan | 045606006 | Elevated Potable Water System | 1 | 650000 | 376434.62 | 273565.38 | 376434.62 | 3rd Tranche | 163940.24 | 540374.86 | 376434.62 | 163940.24 | 100% | 100% | 59.93% | 83.13% | 100% | 2003-10-28 | 2003-12-18 | 2004-05-06 | 2006-01-31 | no data | 635 | 290 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Calutcot | 045606007 | Health Station | 1 | 750000 | 424168.52 | 325831.48 | 424168.52 | 3rd Tranche | 345140 | 769308.52 | 424168.52 | 345140 | 100% | 100% | 105.9% | 102.6% | 100% | 2003-10-28 | 2003-12-18 | 2004-04-21 | 2004-08-15 | no data | 116 | 321 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Caniwan | 045606008 | Concreting of Pathway | 1 | 1256000 | 771323.08 | 484676.92 | 771323.08 | 3rd Tranche | 395680.87 | 1167003.95 | 771323.08 | 395680.87 | 100% | 100% | 81.64% | 92.91% | 100% | 2006-05-09 | 2006-05-09 | 2006-10-16 | 2006-11-30 | no data | 45 | 147 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Carlagan | 045606009 | 2 Cl School Building | 1 | 929000 | 570856.14 | 358143.86 | 570856.14 | 1st Tranche | 323113.98 | 893970.12 | 570856.14 | 323113.98 | 100% | 100% | 90.22% | 96.23% | 100% | 2006-05-09 | 2006-05-09 | 2006-09-18 | 2006-12-07 | no data | 80 | 391 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Mabini | 045606010 | Health Station | 1 | 811000 | 498461.54 | 312538.46 | 498461.54 | 1st Tranche | 311860.61 | 810322.15 | 498461.54 | 311860.61 | 100% | 100% | 99.78% | 99.92% | 100% | 2006-05-09 | 2006-05-09 | 2006-09-18 | 2006-12-02 | no data | 75 | 186 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Palasan | 045606011 | School Building 2 CL | 1 | 921000 | 566153.85 | 354846.15 | 509538.47 | 1st Tranche | 353846.89 | 863385.36 | 509538.47 | 353846.89 | 100% | 100% | 99.72% | 93.74% | 100% | 2006-05-09 | 2006-05-09 | 2006-09-18 | 2006-12-07 | no data | 80 | 219 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | Poblacion | 045606012 | Concreting of Pathway | 1 | 1034247.02 | 590743.86 | 443503.16 | 590743.86 | 3rd Tranche | 743976.14 | 1334720 | 590743.86 | 743976.14 | 100% | 100% | 167.7% | 129.1% | 100% | 2006-05-09 | 2006-05-09 | 2006-08-22 | 2006-11-30 | no data | 100 | 720 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Burdeos | 045606 | San Rafael | 045606014 | Farm To Market Road | 1 | 2382900 | 1705989.23 | 676910.77 | 1705989.23 | 3rd Tranche | 738062.77 | 2444052 | 1705989.23 | 738062.77 | 100% | 100% | 109% | 102.6% | 100% | 2003-10-28 | 2003-12-18 | 2004-04-19 | 2005-02-28 | 2005-05-10 | 315 | 258 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Antonino (Ayusan) | 045615001 | Spring Development & Upgrading of Pipeline | 1 | 324709 | 224970 | 99739 | 224970 | 3rd Tranche | 127310.5 | 352280.5 | 224970 | 127310.5 | 100% | 100% | 127.6% | 108.5% | 100% | 2003-05-12 | 2003-06-16 | 2003-09-04 | 2003-10-27 | 2004-02-07 | 53 | 168 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Antonino (Ayusan) | 045615001 | Rehabilitation/Improvement Of Antonino Road | 1 | 1382600 | 595210 | 787390 | 595210 | 3rd Tranche | 1008565 | 1603775 | 595210 | 1008565 | 100% | 100% | 128.1% | 116% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-14 | 2006-04-10 | no data | 270 | 168 |  | 1
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bagong Anyo | 045615002 | Day Care Center | 1 | 375005.4 | 240624 | 134381.4 | 240624 | 3rd Tranche | 134887 | 375511 | 240624 | 134887 | 100% | 100% | 100.4% | 100.1% | 100% | 2003-05-12 | 2003-06-16 | 2003-09-01 | 2003-10-23 | 2003-11-15 | 52 | 202 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bulakin I | 045615004 | Health Station | 1 | 657649 | 414209 | 243440 | 414209 | 3rd Tranche | 141430 | 555639 | 414209 | 141430 | 100% | 100% | 58.1% | 84.49% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-26 | 2006-05-28 | no data | 91 | 460 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bulakin II | 045615016 | Multi Purpose Training Center | 1 | 1291275.44 | 598566.6 | 692708.84 | 598566.6 | 3rd Tranche | 750420.38 | 1348986.98 | 598566.6 | 750420.38 | 100% | 100% | 108.3% | 104.5% | 100% | 2003-05-12 | 2003-06-16 | 2003-09-01 | 2003-12-27 | 2004-01-17 | 117 | 350 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bungoy | 045615005 | Health Station | 1 | 395770.05 | 276570.05 | 119200 | 276570.05 | 3rd Tranche | 122810 | 399380.05 | 276570.05 | 122810 | 100% | 100% | 103% | 100.9% | 100% | 2003-05-12 | 2003-06-16 | 2003-09-02 | 2003-10-29 | 2003-11-25 | 57 | 737 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Bungoy | 045615005 | Multi-Purpose Pavement | 1 | 744235 | 419176 | 325059 | 419176 | 3rd Tranche | 354469.5 | 773645.5 | 419176 | 354469.5 | 100% | 100% | 109% | 104% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-13 | 2006-05-30 | no data | 106 | 737 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Cabatang | 045615006 | Concreting of Cabatang Road | 1 | 980800 | 686560 | 294240 | 686560 | 3rd Tranche | 211587 | 898147 | 686560 | 211587 | 100% | 100% | 71.91% | 91.57% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-13 | 2005-11-16 | no data | 126 | 79 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Kinabuhayan | 045615008 | Riprapping Wall | 1 | 387910 | 245310 | 142600 | 245310 | 3rd Tranche | 112445.5 | 357755.5 | 245310 | 112445.5 | 100% | 100% | 78.85% | 92.23% | 100% | 2003-05-12 | 2003-06-16 | 2003-09-08 | 2003-12-20 | 2003-12-17 | 103 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Kinabuhayan | 045615008 | Construction of Day Care Center | 1 | 669900 | 468930 | 200970 | 468930 | 3rd Tranche | 197709 | 666639 | 468930 | 197709 | 100% | 100% | 98.38% | 99.51% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-11 | 2005-11-21 | no data | 133 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Kinabuhayan | 045615008 | Road Concreting | 1 | 1123450 | 748150 | 375300 | 748150 | 3rd Tranche | 390450 | 1138600 | 748150 | 390450 | 100% | 100% | 104% | 101.3% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-14 | 2006-05-31 | no data | 106 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Manggahan | 045615010 | Road Concreting | 1 | 689585 | 446485 | 243100 | 446485 | 3rd Tranche | 212124 | 658609 | 446485 | 212124 | 100% | 100% | 87.26% | 95.51% | 100% | 2003-05-12 | 2003-06-16 | 2003-10-20 | 2003-11-26 | 2004-01-16 | 37 | 230 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Manggahan | 045615010 | Concreting of Manggahan Road | 1 | 920535 | 628005 | 292530 | 628005 | 3rd Tranche | 183942 | 811947 | 628005 | 183942 | 100% | 100% | 62.88% | 88.2% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-18 | 2005-11-18 | no data | 123 | 230 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Manggahan | 045615010 | Road Concreting | 1 | 992180 | 681710 | 310470 | 681710 | 3rd Tranche | 269453 | 951163 | 681710 | 269453 | 100% | 100% | 86.79% | 95.87% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-21 | 2006-05-26 | no data | 94 | 230 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Pinagdanlayan | 045615011 | Spring Development | 1 | 545790 | 374790 | 171000 | 374790 | 3rd Tranche | 155986 | 530776 | 374790 | 155986 | 100% | 100% | 91.22% | 97.25% | 100% | 2003-05-12 | 2003-06-16 | 2003-09-08 | 2003-12-20 | 2004-02-21 | 103 | 503 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Pinagdanlayan | 045615011 | Concreting of Pinagdanlayan Road | 1 | 1331145 | 894775 | 436370 | 894775 | 3rd Tranche | 371028.4 | 1265803.4 | 894775 | 371028.4 | 100% | 100% | 85.03% | 95.09% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-08 | 2005-11-20 | no data | 135 | 503 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Pinagdanlayan | 045615011 | Road Concreting | 1 | 906860 | 556320 | 350540 | 556320 | 3rd Tranche | 223200 | 779520 | 556320 | 223200 | 100% | 100% | 63.67% | 85.96% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-14 | 2006-05-31 | no data | 106 | 503 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Putol | 045615012 | Road Concreting | 1 | 542979 | 349939 | 193040 | 349939 | 3rd Tranche | 160595 | 510534 | 349939 | 160595 | 100% | 100% | 83.19% | 94.02% | 100% | 2003-05-12 | 2003-06-16 | 2003-10-10 | 2003-11-16 | 2003-11-05 | 37 | 220 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Putol | 045615012 | Concreting of Putol Road | 1 | 1042700 | 719880 | 322820 | 719880 | 3rd Tranche | 314288.94 | 1034168.94 | 719880 | 314288.94 | 100% | 100% | 97.36% | 99.18% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-19 | 2005-10-26 | no data | 99 | 220 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Putol | 045615012 | Road Concreting | 1 | 859330 | 549830 | 309500 | 549830 | 3rd Tranche | 249446.6 | 799276.6 | 549830 | 249446.6 | 100% | 100% | 80.6% | 93.01% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-16 | 2006-05-25 | no data | 98 | 220 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | San Mateo | 045615013 | Rehab Of Water Lines | 1 | 542695 | 436059 | 106636 | 436059 | 3rd Tranche | 71345 | 507404 | 436059 | 71345 | 100% | 100% | 66.91% | 93.5% | 100% | 2003-05-12 | 2003-06-16 | 2003-08-25 | 2003-10-24 | 2004-07-13 | 60 | 316 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | San Mateo | 045615013 | Concreting of San Mateo Road | 1 | 1318000 | 806640 | 511360 | 806640 | 3rd Tranche | 475696 | 1282336 | 806640 | 475696 | 100% | 100% | 93.03% | 97.29% | 100% | 2005-02-18 | 2005-03-30 | 2005-07-20 | 2005-10-29 | no data | 101 | 316 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | San Mateo | 045615013 | Road Concreting | 1 | 1056055 | 671445 | 384610 | 671445 | 3rd Tranche | 443597.5 | 1115042.5 | 671445 | 443597.5 | 100% | 100% | 115.3% | 105.6% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-15 | 2006-05-30 | no data | 104 | 316 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Sta. Lucia | 045615014 | School Building | 1 | 1093411 | 668149 | 425262 | 668149 | 3rd Tranche | 717017.5 | 1385166.5 | 668149 | 717017.5 | 100% | 100% | 168.6% | 126.7% | 100% | 2003-05-12 | 2003-06-16 | 2003-08-28 | 2003-12-18 | 2003-12-18 | 112 | 856 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Dolores | 045615 | Sta. Lucia | 045615014 | Road Concreting | 1 | 1183110 | 759160 | 423950 | 759160 | 3rd Tranche | 368750 | 1127910 | 759160 | 368750 | 100% | 100% | 86.98% | 95.33% | 100% | 2005-12-09 | 2005-12-20 | 2006-02-26 | 2006-05-31 | no data | 94 | 856 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Apad | 045621005 | 3-Classroom School Building | 1 | 780647.3 | 482421 | 298226.3 | 482421 | 3rd Tranche | 649228.8 | 1131649.8 | 482421 | 649228.8 | 100% | 100% | 217.7% | 145% | 100% | 2003-10-10 | no data | 2004-04-22 | 2004-06-12 | no data | 51 | 173 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Bukal | 045621001 | Water Supply with Elevated Water Tank | 1 | 302870 | 160750 | 142120 | 160750 | 3rd Tranche | 79926.85 | 240676.85 | 160750 | 79926.85 | 100% | 100% | 56.24% | 79.47% | 100% | 2003-10-10 | no data | 2004-05-17 | 2004-11-09 | 2005-01-15 | 176 | 208 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Casuguran | 045621002 | Pathway 1.4 Kms | 1 | 2165520 | 1500000 | 665520 | 1500000 | 3rd Tranche | 1127860 | 2627860 | 1500000 | 1127860 | 100% | 100% | 169.5% | 121.4% | 100% | 2006-03-29 | 2006-03-29 | 2006-05-05 | 2006-11-30 | no data | 209 | 199 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Gango | 045621003 | Pathway Concreting | 1 | 504450.01 | 312881.31 | 191568.7 | 312881.31 | 3rd Tranche | 137539.39 | 450420.7 | 312881.31 | 137539.39 | 100% | 100% | 71.8% | 89.29% | 100% | 2003-10-10 | no data | 2004-03-29 | 2004-11-04 | 2005-01-14 | 220 | 102 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Talisoy | 045621004 | Road Concreting | 1 | 893632 | 543947.69 | 349684.31 | 543947.69 | 3rd Tranche | 98432.31 | 642380 | 543947.69 | 98432.31 | 100% | 100% | 28.15% | 71.88% | 100% | 2003-10-10 | no data | 2004-03-04 | 2004-09-27 | 2005-01-12 | 207 | 360 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Jomalig | 045621 | Talisoy | 045621004 | Water System Level II | 1 | 1991804.52 | 1498404.52 | 493400 | 1498404.5 | 3rd Tranche | 503380 | 2001784.5 | 1498404.5 | 503380 | 100% | 100% | 102% | 100.5% | 100% | 2005-05-06 | 2005-06-15 | 2005-10-01 | 2006-04-12 | 2006-05-08 | 193 | 360 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Anonang | 045628003 | 4.56 km Farm To Market Road | 1 | 4042025.26 | 1973404.05 | 2068621.21 | 1973404.05 | 3rd Tranche | 1559239.17 | 3532643.22 | 1973404.05 | 1559239.17 | 100% | 100% | 75.38% | 87.4% | 100% | 2003-11-06 | 2003-12-16 | 2004-03-27 | 2004-08-31 | no data | 157 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Anonang | 045628003 | Upgrading / Concredint of Farm to Market Road | 1 | 1474944.1 | 1268571.45 | 206372.65 | 1268571.45 | 3rd Tranche | 364887.79 | 1633459.24 | 1268571.45 | 364887.79 | 100% | 100% | 176.8% | 110.7% | 100% | n/a | n/a | 2009-03-27 | 2009-06-20 | n/a | 85 | 119 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Bagong Silang | 045628004 | Upgrading 1.95 Kms FMR | 1 | 4009860 | 1873700 | 2136160 | 1873700 | 1st Tranche | 618110 | 2491810 | 1873700 | 618110 | 100% | 100% | 28.94% | 62.14% | 100% | 2006-03-28 | 2006-03-28 | 2006-08-03 | 2007-04-22 | no data | 262 | 62 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Bagupaye | 045628005 | Upgrading / Concreting of Farm to Market Road | 1 | 1322170.56 | 977760.33 | 344410.23 | 977760.33 | 3rd Tranche | 374010.23 | 1342470.56 | 977760.33 | 364710.23 | 100% | 97.51% | 108.6% | 101.5% | 100% | n/a | n/a | 2009-03-23 | 2009-05-30 | n/a | 68 | 300 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Bolo | 045628012 | 2.5 km Farm To Market Road | 1 | 2210113 | 1291625.4 | 918487.6 | 1291625.4 | 3rd Tranche | 925650.43 | 2217275.83 | 1291625.4 | 925650.43 | 100% | 100% | 100.8% | 100.3% | 100% | 2003-11-06 | 2003-12-16 | 2004-03-22 | 2004-08-28 | 2004-08-31 | 159 | 197 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Bolo | 045628012 | 2 Classroom Elementary School | 1 | 871100 | 514000 | 357100 | 514000 | 3rd Tranche | 423526.75 | 937526.75 | 514000 | 423526.75 | 100% | 100% | 118.6% | 107.6% | 100% | 2005-02-16 | 2005-04-22 | 2005-07-12 | 2006-03-10 | 2006-03-14 | 241 | 197 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Buenavista | 045628013 | Upgrading / Concreting of Farm to Market Road | 1 | 1423936.56 | 1199004.37 | 224932.19 | 1199004.32 | 3rd Tranche | 323894.69 | 1533249.01 | 1199004.32 | 334244.69 | 100% | 103.2% | 144% | 107.7% | 100% | n/a | n/a | 2009-03-23 | 2009-06-13 | n/a | 82 | 195 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Burgos | 045628014 | Farm to Market Road | 1 | 4558569.25 | 2723692 | 1834877.25 | 2723692 | 2nd Tranche | 1369907.96 | 4093599.96 | 2723692 | 1369907.96 | 100% | 100% | 74.66% | 89.8% | 100% | 2005-02-16 | 2005-04-22 | 2005-09-09 | 2006-11-08 | no data | 425 | 303 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Burgos | 045628014 | Upgrading / Concreting of Farm to Market Road | 1 | 800000 | 800000 | 0 | 800000 | 3rd Tranche | 338242 | 800000 | 800000 | 0 | 100% | 0% | #DIV/0! | 100% | 100% | n/a | n/a | 2009-04-27 | 2009-06-20 | n/a | 54 | 282 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Butanyog | 045628015 | Level II Water Supply System | 1 | 200210.7 | 101854.2 | 98356.5 | 101854.2 | 3rd Tranche | 106506.26 | 208360.46 | 101854.2 | 106506.26 | 100% | 100% | 108.3% | 104.1% | 100% | 2003-11-06 | 2003-12-16 | 2004-03-08 | 2004-08-21 | 2004-08-30 | 166 | 224 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Canuyep | 045628016 | Electrification Extension | 1 | 954819.84 | 471007.25 | 483812.59 | 471007.25 | 3rd Tranche | 411855.66 | 882862.91 | 471007.25 | 411855.66 | 100% | 100% | 85.13% | 92.46% | 100% | 2006-03-28 | 2006-03-28 | 2006-06-09 | 2006-06-23 | no data | 14 | 372 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | F. Nanadiego | 045628017 | Farm to Market Road | 1 | 4527629 | 2424307.7 | 2103321.3 | 2424307.7 | 3rd Tranche | 877292.3 | 3301600 | 2424307.7 | 877292.3 | 100% | 100% | 41.71% | 72.92% | 100% | 2005-02-16 | 2005-04-22 | 2005-09-13 | 2007-06-06 | no data | 631 | 325 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Ibabang Yuni | 045628019 | 8.5 km Farm To Market Road | 1 | 4161421.04 | 1639862.34 | 2521558.7 | 1639862.34 | 3rd Tranche | 1758387.94 | 3398250.28 | 1639862.34 | 1758387.94 | 100% | 100% | 69.73% | 81.66% | 100% | 2003-12-09 | 2003-12-16 | 2004-03-23 | 2004-10-20 | no data | 211 | 393 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Ibabang Yuni | 045628019 | Health Station | 1 | 609700 | 334269.23 | 275430.77 | 334269.23 | 3rd Tranche | 256830.77 | 591100 | 334269.23 | 256830.77 | 100% | 100% | 93.25% | 96.95% | 100% | 2005-02-16 | 2005-04-22 | 2005-07-08 | 2006-03-24 | no data | 259 | 393 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Ibabang Yuni | 045628019 | Extention of Power Mainline | 1 | 1925442.93 | 1198018.65 | 727424.28 | 1198018.65 | 3rd Tranche | 711956.07 | 1909974.72 | 1198018.65 | 711956.07 | 100% | 100% | 97.87% | 99.2% | 100% | n/a | n/a | 2009-04-07 | 2009-05-04 | n/a | 27 | 152 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Ilayang Cambuga (Mabini) | 045628020 | Upgrading / Concreting of Farm to Market Road, 380m | 1 | 2610109.05 | 1996568.51 | 613540.54 | 1996568.51 | 3rd Tranche | 607988.19 | 2679056.7 | 1996568.51 | 682488.19 | 100% | 112.3% | 99.1% | 102.6% | 100% | n/a | n/a | 2009-03-26 | 2009-06-13 | n/a | 79 | 687 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Lantangan | 045628022 | Upgrading 2.075 Kms FMR | 1 | 2382880 | 954523 | 1428357 | 954523 | 3rd Tranche | 406357 | 1360880 | 954523 | 406357 | 100% | 100% | 28.45% | 57.11% | 100% | 2006-03-28 | 2006-03-28 | 2006-06-23 | 2006-12-15 | no data | 175 | 247 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Latangan | 045628022 | Extension of Power Main Line | 1 | 1724851.18 | 1063980.28 | 660870.9 | 1063980.28 | 3rd Tranche | 630731.59 | 1695211.87 | 1063980.28 | 631231.59 | 100% | 100.1% | 95.44% | 98.28% | 100% | n/a | n/a | 2009-04-06 | 2009-05-25 | n/a | 49 | 220 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Mabini | 045628020 | Upgrading 3 kms FMR | 1 | 5758600 | 2649385 | 3109215 | 2634406.2 | 1st Tranche | 954615 | 3589021.2 | 2634406.2 | 954615 | 100% | 100% | 30.7% | 62.32% | 100% | 2006-03-28 | 2006-03-28 | 2006-07-06 | 2007-04-26 | no data | 294 | 294 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Magsaysay | 045628024 | 3 Classroom Elementary School | 1 | 1292100 | 774692.31 | 517407.69 | 774692.31 | 3rd Tranche | 382407.69 | 1157100 | 774692.31 | 382407.69 | 100% | 100% | 73.91% | 89.55% | 100% | 2005-02-16 | 2005-04-22 | 2006-05-01 | 2006-11-30 | no data | 213 | 154 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Magsaysay | 045628024 | Upgrading of Spring Water Source | 1 | 945094.5 | 669368.83 | 275725.67 | 669368.83 | 3rd Tranche | 264638.17 | 932607 | 669368.83 | 263238.17 | 100% | 99.47% | 95.98% | 98.68% | 100% | n/a | n/a | 2009-03-31 | 2009-06-13 | n/a | 74 | 180 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Matataja | 045628025 | Upgrading of Farm to Market Road | 1 | 1909897.5 | 1625727.65 | 284169.85 | 1625727.65 | 3rd Tranche | 284569.85 | 1928597.5 | 1625727.65 | 302869.85 | 100% | 106.4% | 100.1% | 101% | 100% | n/a | n/a | 2009-03-25 | 2009-05-28 | n/a | 64 | 226 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Patabog | 045628027 | 4 km Farm To Market Road | 1 | 2496894.7 | 905880.54 | 1591014.16 | 905880.54 | 3rd Tranche | 1206830.05 | 2112710.59 | 905880.54 | 1206830.05 | 100% | 100% | 75.85% | 84.61% | 100% | 2003-12-09 | 2003-12-16 | 2004-03-26 | 2004-12-08 | no data | 257 | 676 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion (Brgy 1) | 045628006 | Construction of 2m by 270m Pathway | 1 | 585547.06 | 368882.35 | 216664.71 | 368882.35 | 3rd Tranche | 183489.71 | 552372.06 | 368882.35 | 183489.71 | 100% | 100% | 84.69% | 94.33% | 100% | 2003-11-06 | 2003-12-16 | 2004-02-27 | 2004-09-02 | no data | 188 | 287 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion (Brgy 1) | 045628006 | Upgrading 150mx2m Pathway | 1 | 694955 | 472042 | 222913 | 472042 | 3rd Tranche | 270100 | 742142 | 472042 | 270100 | 100% | 100% | 121.2% | 106.8% | 100% | 2006-03-28 | 2006-03-28 | 2006-05-22 | 2006-10-15 | no data | 146 | 287 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion (Brgy 2) | 045628008 | Construction 300m Line Canal | 1 | 1454854 | 849401.54 | 605452.46 | 849401.54 | 3rd Tranche | 202631.32 | 1052032.86 | 849401.54 | 202631.32 | 100% | 100% | 33.47% | 72.31% | 100% | 2006-03-28 | 2006-03-28 | 2006-05-23 | 2006-10-15 | no data | 145 | 781 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion (Brgy 3) | 045628009 | Day Care Center | 1 | 418703 | 223079 | 195624 | 223079 | 3rd Tranche | 211433.45 | 434512.45 | 223079 | 211433.45 | 100% | 100% | 108.1% | 103.8% | 100% | 2003-11-06 | 2003-12-16 | 2004-03-15 | 2004-09-26 | 2004-08-31 | 195 | 247 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion (Brgy 4) | 045628010 | Sea Wall | 1 | 1669300 | 1156807.7 | 512492.3 | 1156807.7 | 3rd Tranche | 635416.05 | 1792223.75 | 1156807.7 | 635416.05 | 100% | 100% | 124% | 107.4% | 100% | 2005-02-16 | 2005-04-22 | 2005-07-19 | 2006-11-08 | no data | 477 | 174 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion 1 | 045628006 | Concreting of Line Canal with Cover | 1 | 1353206.92 | 944352.38 | 408854.54 | 944352.38 | 3rd Tranche | 410232.87 | 1354585.25 | 944352.38 | 410232.87 | 100% | 100% | 100.3% | 100.1% | 100% | n/a | n/a | 2009-03-23 | 2009-06-20 | n/a | 89 | 164 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion II | 045628008 | Concreting of Line Canal with Cover and Cross Drainage | 1 | 1710913.6 | 1093440.4 | 617473.2 | 1093440.4 | 3rd Tranche | 643357.58 | 1736797.98 | 1093440.4 | 643357.58 | 100% | 100% | 104.2% | 101.5% | 100% | n/a | n/a | 2009-03-23 | 2009-06-13 | n/a | 82 | 350 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion III | 045628009 | Fab. Of Stl Casement Cover of Flood Cont. Open Line Canal | 1 | 960186.67 | 723779.09 | 236407.58 | 723779.09 | 3rd Tranche | 256228.83 | 886380.92 | 723779.09 | 162601.83 | 100% | 63.46% | 108.4% | 92.31% | 100% | n/a | n/a | 2009-03-23 | 2009-06-20 | n/a | 89 | 200 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Poblacion IV | 045628010 | Const. of Prop. Ext. of Flood Control w/ Wingwall | 1 | 1411554.05 | 956818.72 | 454735.33 | 956818.72 | 3rd Tranche | 460616.58 | 1417435.3 | 956818.72 | 460616.58 | 100% | 100% | 101.3% | 100.4% | 100% | n/a | n/a | 2009-03-23 | 2009-06-13 | n/a | 82 | 159 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sagongon | 045628028 | 3.7 km Farm To Market Road | 1 | 3139433.68 | 1654256.68 | 1485177 | 1654256.68 | 3rd Tranche | 679691.85 | 2333948.53 | 1654256.68 | 679691.85 | 100% | 100% | 45.77% | 74.34% | 100% | 2003-11-06 | 2003-12-16 | 2004-03-29 | 2005-02-02 | no data | 310 | 92 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sagongon | 045628028 | Day Care Center | 1 | 573700 | 413000 | 160700 | 413000 | 3rd Tranche | 163750 | 576750 | 413000 | 163750 | 100% | 100% | 101.9% | 100.5% | 100% | 2005-02-16 | 2005-04-22 | 2005-08-15 | 2006-03-24 | no data | 221 | 92 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | San Isidro | 045628029 | Upgrading of Spring Water Source (Level II Water System) | 1 | 653916.9 | 282609.36 | 371307.54 | 282609.36 | 3rd Tranche | 404707.54 | 687316.9 | 282609.36 | 404707.54 | 100% | 100% | 109% | 105.1% | 100% | n/a | n/a | 2009-04-28 | 2009-06-13 | n/a | 46 | 74 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sta. Rosa | 045628031 | Health Station | 1 | 483701 | 241155 | 242546 | 241155 | 3rd Tranche | 135382 | 376537 | 241155 | 135382 | 100% | 100% | 55.82% | 77.84% | 100% | 2003-11-06 | 2003-12-16 | 2004-03-01 | 2005-02-01 | no data | 337 | 604 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sta. Rosa | 045628031 | 48 Sq.m Day Care Center | 1 | 837690 | 497454 | 340236 | 497454 | 3rd Tranche | 286236 | 783690 | 497454 | 286236 | 100% | 100% | 84.13% | 93.55% | 100% | 2006-03-28 | 2006-03-28 | 2006-05-29 | 2006-10-15 | no data | 139 | 604 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Mulanay | 045628 | Sto. Niño |  | 5 units Banca | 1 | 835810 | 529629 | 306181 | 529629 | 3rd Tranche | 371781 | 901410 | 529629 | 371781 | 100% | 100% | 121.4% | 107.8% | 100% | 2006-03-28 | 2006-03-28 | 2006-07-05 | 2006-11-30 | no data | 148 | 311 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Balungay | 045631001 | Pathway Concreting | 1 | 389097 | 196861.6 | 192235.4 | 196861.6 | 3rd Tranche | 120880.4 | 317742 | 196861.6 | 120880.4 | 100% | 100% | 62.88% | 81.66% | 100% | 2003-11-23 | 2003-12-01 | 2004-03-15 | 2004-10-10 | 2004-10-28 | 209 | 142 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Balungay | 045631001 | Wharf extension | 1 | 2171973.77 | 1443565.85 | 728407.92 | 1443565.85 | 3rd Tranche | 713600 | 2157165.85 | 1443565.85 | 713600 | 100% | 100% | 97.97% | 99.32% | 100% | 2005-07-20 | 2005-08-31 | 2005-12-05 | 2006-11-08 | no data | 338 | 142 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Bato | 045631002 | Solar Drier | 1 | 258781.6 | 112952.93 | 145828.67 | 112952.93 | 3rd Tranche | 148506.66 | 261459.59 | 112952.93 | 148506.66 | 100% | 100% | 101.8% | 101% | 100% | 2003-11-23 | 2003-12-01 | 2004-03-18 | 2004-04-01 | no data | 14 | 80 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Bato | 045631002 | Wharf extension | 1 | 958507 | 712557.42 | 245949.58 | 712557.42 | 3rd Tranche | 493439.19 | 1205996.61 | 712557.42 | 493439.19 | 100% | 100% | 200.6% | 125.8% | 100% | 2005-07-20 | 2005-08-31 | 2005-09-17 | 2006-04-20 | no data | 215 | 80 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Bato | 045631002 | Concreting of 2 Bridges | 1 | 884968 | 358381.48 | 526586.52 | 358381.48 | 2nd Tranche | 510119.52 | 868501 | 358381.48 | 510119.52 | 100% | 100% | 96.87% | 98.14% | 100% | 2006-05-04 | 2006-05-05 | 2006-07-05 | 2006-10-31 | no data | 118 | 80 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Calasumanga | 045631004 | Potable Water System | 1 | 1325979.6 | 908152.18 | 417827.42 | 908152.18 | 3rd Tranche | 379478.99 | 1287631.17 | 908152.18 | 379478.99 | 100% | 100% | 90.82% | 97.11% | 100% | 2003-11-23 | 2003-12-01 | 2004-03-30 | 2005-10-01 | no data | 550 | 100 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Kinalagti | 045631005 | Potable Water System | 1 | 922171.82 | 637738.06 | 284433.76 | 637738.06 | 3rd Tranche | 229162.4 | 866900.46 | 637738.06 | 229162.4 | 100% | 100% | 80.57% | 94.01% | 100% | 2003-11-23 | 2003-12-01 | 2004-04-18 | 2005-07-01 | 2005-09-03 | 439 | 113 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Libo | 045631006 | Pier Extension | 1 | 316264.39 | 216427.57 | 99836.82 | 216427.57 | 3rd Tranche | 94620.62 | 311048.19 | 216427.57 | 94620.62 | 100% | 100% | 94.78% | 98.35% | 100% | 2003-11-23 | 2003-12-01 | 2004-04-20 | 2004-11-16 | no data | 210 | 205 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Libo | 045631006 | Pathway Concreting | 1 | 1213248 | 857861.54 | 355386.46 | 857861.54 | 3rd Tranche | 363860.89 | 1221722.43 | 857861.54 | 363860.89 | 100% | 100% | 102.4% | 100.7% | 100% | 2005-07-20 | 2005-08-31 | 2005-11-24 | 2006-07-31 | no data | 249 | 205 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Lipata | 045631007 | Pathway Concreting | 1 | 679966.77 | 463835.24 | 216131.53 | 463835.24 | 3rd Tranche | 168550 | 632385.24 | 463835.24 | 168550 | 100% | 100% | 77.98% | 93% | 100% | 2003-11-23 | 2003-12-01 | 2004-03-30 | 2005-05-09 | 2005-06-10 | 405 | 115 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Lipata | 045631007 | Pathway Concreting | 1 | 798014 | 577625.85 | 220388.15 | 577625.85 | 3rd Tranche | 327043.85 | 904669.7 | 577625.85 | 327043.85 | 100% | 100% | 148.4% | 113.4% | 100% | 2005-07-20 | 2005-08-31 | 2005-12-18 | 2006-06-30 | no data | 194 | 115 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Matangkap | 045631008 | Construction/Extension Wharf | 1 | 1615122.8 | 1114902.8 | 500220 | 1114902.8 | 3rd Tranche | 454621 | 1569523.8 | 1114902.8 | 454621 | 100% | 100% | 90.88% | 97.18% | 100% | 2006-05-04 | 2006-05-05 | 2006-06-14 | 2006-12-30 | no data | 199 | 155 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Milawid | 045631008 | Concreting Pathway | 1 | 1418992.05 | 1013804.05 | 405188 | 1013804.05 | 2nd Tranche | 376988.8 | 1390792.85 | 1013804.05 | 376988.8 | 100% | 100% | 93.04% | 98.01% | 100% | 2006-05-04 | 2006-05-05 | 2006-06-15 | 2006-10-28 | no data | 135 | 187 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Pagitan | 045631010 | Potable Water System | 1 | 684691.97 | 413207.75 | 271484.22 | 413207.75 | 3rd Tranche | 202216.72 | 615424.47 | 413207.75 | 202216.72 | 100% | 100% | 74.49% | 89.88% | 100% | 2003-11-23 | 2003-12-01 | 2004-04-25 | 2005-05-01 | no data | 371 | 117 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Pandan | 045631010 | Potable Water System | 1 | 793047.9 | 537247.98 | 255799.92 | 537247.98 | 3rd Tranche | 2757.66 | 540005.64 | 537247.98 | 2757.66 | 100% | 100% | 1.078% | 68.09% | 100% | 2003-11-23 | 2003-12-01 | 2004-04-07 | 2005-07-01 | 2005-09-07 | 450 | 142 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Panukulan | 045631 | Pandan | 045631011 | Concreting Pathway | 1 | 1573751.61 | 1112911.67 | 460839.94 | 1112911.67 | 2nd Tranche | 390987.82 | 1503899.49 | 1112911.67 | 390987.82 | 100% | 100% | 84.84% | 95.56% | 100% | 2006-05-04 | 2006-05-05 | 2006-06-12 | 2006-10-31 | no data | 141 | 142 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Amaga | 045632001 | Construction of 3 Classroom Building | 1 | 909952.1 | 607040.08 | 302912.02 | 607040.08 | 3rd Tranche | 299239.37 | 906279.45 | 607040.08 | 299239.37 | 100% | 100% | 98.79% | 99.6% | 100% | 2003-11-13 | 2004-02-06 | 2004-05-25 | 2005-04-30 | 2005-05-25 | 340 | 93 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Amaga | 045632001 | Level II Water System | 1 | 1057612.54 | 707203.49 | 350409.05 | 707203.49 | 3rd Tranche | 442544.08 | 1149747.57 | 707203.49 | 442544.08 | 100% | 100% | 126.3% | 108.7% | 100% | 2005-07-07 | 2005-08-25 | 2005-11-20 | 2006-04-03 | no data | 134 | 93 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Busdak | 045632002 | Water Supply System | 1 | 983147.61 | 553736.92 | 429410.69 | 553736.92 | 3rd Tranche | 423967.59 | 977704.51 | 553736.92 | 423967.59 | 100% | 100% | 98.73% | 99.45% | 100% | 2003-11-13 | 2004-02-06 | 2004-06-23 | 2005-04-30 | 2005-05-27 | 311 | 372 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Kilogan | 045632003 | 3 Classroom school building | 1 | 1278604.98 | 898926.92 | 379678.06 | 898926.92 | 3rd Tranche | 440178.08 | 1339105 | 898926.92 | 440178.08 | 100% | 100% | 115.9% | 104.7% | 100% | 2005-07-07 | 2005-08-25 | 2005-11-20 | 2006-11-08 | no data | 353 | 279 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Kilogan - C4 | 045632003 | Circumferential Road | 4 | 2973517 | 639223 | 2334294 | 575300.7 | 2nd Tranche | 951510.25 | 1526810.95 | 575300.7 | 951510.25 | 100% | 100% | 40.76% | 51.35% | 100% | 2003-11-13 | 2004-02-06 | 2004-04-30 | 2005-07-28 | no data | 454 | 2011 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Luod | 045632004 | Rehabilitation of Water System | 1 | 1040496.76 | 701323.66 | 339173.1 | 701323.66 | 3rd Tranche | 374673.12 | 1075996.78 | 701323.66 | 374673.12 | 100% | 100% | 110.5% | 103.4% | 100% | 2006-04-28 | 2006-04-28 | 2006-07-30 | 2006-11-30 | no data | 123 | 183 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | Patnanungan | 045632 | Patnanungan Sur & Patnanungan Norte | 045632006 & 045632005 | Drainage/Canal | 1 | 1493479.24 | 1098676.34 | 394802.9 | 1098676.34 | 3rd Tranche | 411269.05 | 1509945.39 | 1098676.34 | 411269.05 | 100% | 100% | 104.2% | 101.1% | 100% | 2006-04-28 | 2006-04-28 | 2006-07-30 | 2006-11-30 | no data | 123 | 696 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Andres | 045640 | Alibihaban | 045640001 | Footbridge | 1 | 1580759.77 | 1330759.77 | 250000 | 1330759.77 | 3rd Tranche | 239047 | 1569806.77 | 1330759.77 | 239047 | 100% | 100% | 95.62% | 99.31% | 100% | 2005-08-12 | 2005-07-26 | 2006-06-29 | 2006-11-30 | no data | 154 | 246 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Andres | 045640 | Pansoy | 045640004 | 2 Classroom School Building | 1 | 766739.94 | 506507.63 | 260232.31 | 506507.63 | 3rd Tranche | 289151.34 | 795658.97 | 506507.63 | 289151.34 | 100% | 100% | 111.1% | 103.8% | 100% | 2003-11-27 | 2003-12-14 | 2004-01-17 | 2005-04-22 | no data | 461 | 948 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Andres | 045640 | Pansoy | 045640004 | Level II Water System | 1 | 849240.23 | 769240.23 | 80000 | 769240.23 | 2nd Tranche | 19125 | 788365.23 | 769240.23 | 19125 | 100% | 100% | 23.91% | 92.83% | 100% | 2005-08-12 | 2005-07-26 | 2006-10-20 | 2007-06-07 | no data | 230 | 948 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Andres | 045640 | Poblacion | 045640007 | Water Reservoir | 1 | 256866.45 | 157820.34 | 99046.11 | 157820.34 | 3rd Tranche | 123778.28 | 281598.62 | 157820.34 | 123778.28 | 100% | 100% | 125% | 109.6% | 100% | 2003-11-27 | 2003-12-14 | 2004-04-21 | 2004-08-31 | 2004-09-12 | 132 | 778 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Andres | 045640 | Tala | 045640005 | Level II Water Supply System | 1 | 451802 | 298971.43 | 152830.57 | 298971.43 | 3rd Tranche | 168070 | 467041.43 | 298971.43 | 168070 | 100% | 100% | 110% | 103.4% | 100% | 2003-11-27 | 2003-12-14 | 2004-05-03 | 2005-04-22 | no data | 354 | 752 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Andres | 045640 | Talisay | 045640006 | 4-Classroom School Building | 1 | 1074341 | 716936.92 | 357404.08 | 716936.92 | 3rd Tranche | 1579815.59 | 2296752.51 | 716936.92 | 1579815.59 | 100% | 100% | 442% | 213.8% | 100% | 2003-11-27 | 2003-12-14 | 2004-04-21 | 2005-04-22 | no data | 366 | 891 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Casay | 045642003 | Rehabilitation of Water Supply System | 1 | 957525 | 578743.92 | 378781.08 | 578743.92 | 3rd Tranche | 345433.57 | 924177.49 | 578743.92 | 345433.57 | 100% | 100% | 91.2% | 96.52% | 100% | no data | no data | 2004-05-20 | 2005-06-18 | no data | 394 | 540 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Casay | 045642003 | 1. Km Farm to Market Road | 1 | 1223400 | 592711.53 | 630688.47 | 556132.78 | 1st Tranche | 150587.5 | 706720.28 | 556132.78 | 150587.5 | 100% | 100% | 23.88% | 57.77% | 100% | 2006-04-07 | 2006-04-07 | 2006-07-03 | 2007-04-15 | no data | 286 | 540 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Cawayan 1 | 045642004 | 1.75 Km FMR | 1 | 1995000 | 987870 | 1007130 | 901432.75 | 1st Tranche | 0 | 901432.75 | 901432.75 | 0 | 100% | #DIV/0! | 0% | 45.18% | 100% | 2006-04-07 | 2006-04-07 | 2006-06-15 | 2007-05-07 | no data | 326 | 605 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Cawayan 2 | 045642005 | 1 km Farm-to-Market Road | 1 | 1591600 | 843549 | 748051 | 843549 | 3rd Tranche | 344340 | 1187889 | 843549 | 344340 | 100% | 100% | 46.03% | 74.63% | 100% | 2005-07-14 | 2005-09-16 | 2005-11-28 | 2006-04-06 | no data | 129 | 434 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Cawayan 2 | 045642005 | 1. Km Farm to Market Road | 1 | 1481200 | 740593 | 740607 | 740593 | 1st Tranche | 325788.7 | 1066381.7 | 740593 | 325788.7 | 100% | 100% | 43.99% | 71.99% | 100% | 2006-04-07 | 2006-04-07 | 2006-06-05 | 2006-09-08 | no data | 95 | 434 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Don Juan Vercelos | 045642015 | Water System rehabilitation | 1 | 1551400 | 738910.45 | 812489.55 | 738910.45 | 3rd Tranche | 555515.97 | 1294426.42 | 738910.45 | 555515.97 | 100% | 100% | 68.37% | 83.44% | 100% | 2005-07-14 | 2005-09-16 | 2006-01-16 | 2006-11-08 | no data | 296 | 751 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Ibabang Tayuman | 045642007 | 1 Classroom High School Building | 1 | 801200 | 450557.69 | 350642.31 | 405501.93 | 3rd Tranche | 272757.3 | 678259.23 | 405501.93 | 272757.3 | 100% | 100% | 77.79% | 84.66% | 100% | 2005-07-14 | 2005-09-16 | 2005-11-14 | 2006-04-01 | no data | 138 | 362 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Ibabang Tayuman | 045642007 | 1 Cl School building (HS) | 1 | 466955 | 359196 | 107759 | 323276.4 | 2nd Tranche | 171124 | 494400.4 | 323276.4 | 171124 | 100% | 100% | 158.8% | 105.9% | 100% | 2006-04-07 | 2006-04-07 | 2006-07-03 | 2006-09-08 | no data | 67 | 362 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Ilayang Tayuman | 045642008 | 1 km. FMR | 1 | 1519400 | 733009 | 786391 | 705479 | 1st Tranche | 596254 | 1301733 | 705479 | 596254 | 100% | 100% | 75.82% | 85.67% | 100% | 2006-04-07 | 2006-04-07 | 2006-07-03 | 2006-09-08 | no data | 67 | 701 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Inabuan | 045642009 | Intermittent Brgy. Road Rehabilitation | 1 | 1363500 | 839076.92 | 524423.08 | 839076.92 | 3rd Tranche | 45015.58 | 884092.5 | 839076.92 | 45015.58 | 100% | 100% | 8.584% | 64.84% | 100% | no data | no data | 2004-05-24 | 2005-07-07 | no data | 409 | 586 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Inabuan | 045642009 | Health Station | 1 | 724800 | 354769 | 370031 | 354769 | 3rd Tranche | 287681 | 642450 | 354769 | 287681 | 100% | 100% | 77.75% | 88.64% | 100% | 2006-04-07 | 2006-04-07 | 2006-05-20 | 2006-11-30 | no data | 194 | 586 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Mabuñga | 045642016 | Intermittent Brgy. Road Rehabilitation | 1 | 841452 | 517816.52 | 323635.48 | 517816.52 | 3rd Tranche | 255076.5 | 772893.02 | 517816.52 | 255076.5 | 100% | 100% | 78.82% | 91.85% | 100% | no data | no data | 2004-06-10 | 2005-03-23 | no data | 286 | 496 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Nasalaan | 045642010 | Rehabilitation of Water Supply System | 1 | 1020950 | 668423.08 | 352526.92 | 668423.08 | 3rd Tranche | 317611.6 | 986034.68 | 668423.08 | 317611.6 | 100% | 100% | 90.1% | 96.58% | 100% | no data | no data | 2004-05-22 | 2005-07-10 | no data | 414 | 502 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Pagsangahan | 045642011 | School Building | 1 | 1622200 | 885845.38 | 736354.62 | 885845.38 | 3rd Tranche | 564576.52 | 1450421.9 | 885845.38 | 564576.52 | 100% | 100% | 76.67% | 89.41% | 100% | no data | no data | 2005-08-24 | 2006-04-05 | no data | 224 | 1205 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Pagsangahan | 045642011 | 2 Cl School Building(HS) | 1 | 1019900 | 485535 | 534365 | 485535 | 3rd Tranche | 379061 | 864596 | 485535 | 379061 | 100% | 100% | 70.94% | 84.77% | 100% | 2006-04-07 | 2006-04-07 | 2006-06-02 | 2006-11-30 | no data | 181 | 1204 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Poblacion | 045642012 | 425 m Sea Wall | 1 | 4475700 | 2183231 | 2292469 | 2183231 | 3rd Tranche | 905875 | 3089106 | 2183231 | 905875 | 100% | 100% | 39.52% | 69.02% | 100% | 2005-07-14 | 2005-09-16 | 2005-11-24 | 2006-10-31 | no data | 341 | 1148 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Pugon | 045642012 | Rehabilitation of Water Supply System | 1 | 769999.23 | 473846.15 | 296153.08 | 473846.15 | 3rd Tranche | 271911.82 | 745757.97 | 473846.15 | 271911.82 | 100% | 100% | 91.81% | 96.85% | 100% | no data | no data | 2004-05-22 | 2005-07-21 | no data | 425 | 505 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Pugon | 045642013 | Health Station | 1 | 879900 | 391725.38 | 488174.62 | 391725.38 | 3rd Tranche | 364108.37 | 755833.75 | 391725.38 | 364108.37 | 100% | 100% | 74.59% | 85.9% | 100% | 2005-07-14 | 2005-09-16 | 2005-11-26 | 2006-03-28 | no data | 122 | 505 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Pugon | 045642013 | 2 Cl School Building(HS&ES) | 1 | 1000800 | 531563.62 | 469236.38 | 531563.62 | 3rd Tranche | 441856.58 | 973420.2 | 531563.62 | 441856.58 | 100% | 100% | 94.17% | 97.26% | 100% | 2006-04-07 | 2006-04-07 | 2006-05-10 | 2006-11-30 | no data | 204 | 505 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Silongin | 045642014 | Construction of 2 Classroom Building | 1 | 597114 | 374332.31 | 222781.69 | 374332.31 | 3rd Tranche | 207919.7 | 582252.01 | 374332.31 | 207919.7 | 100% | 100% | 93.33% | 97.51% | 100% | no data | no data | 2004-05-14 | 2005-12-05 | no data | 570 | 502 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Francisco | 045642 | Sto. Niño | 045642017 | Construction of 3 Deepwell with Elevated Water Tank | 1 | 482000 | 302307.69 | 179692.31 | 302307.69 | 3rd Tranche | 378168.2 | 680475.89 | 302307.69 | 378168.2 | 100% | 100% | 210.5% | 141.2% | 100% | no data | no data | 2004-04-17 | 2005-11-05 | no data | 567 | 456 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Abuyon | 045644001 | Spring Development | 1 | 1498026.01 | 966517.7 | 531508.31 | 966517.7 | 3rd Tranche | 520832.31 | 1487350.01 | 966517.7 | 520832.31 | 100% | 100% | 97.99% | 99.29% | 100% | 2005-06-02 | 2005-07-28 | 2005-12-06 | 2006-10-31 | no data | 329 | 773 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Andres Bonifacio | 045644002 | Day Care Center | 1 | 607260.17 | 388738.59 | 218521.58 | 388738.59 | 3rd Tranche | 68444 | 457182.59 | 388738.59 | 68444 | 100% | 100% | 31.32% | 75.29% | 100% | 2005-06-02 | 2005-07-28 | 2005-10-26 | 2006-05-31 | no data | 217 | 137 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Bani | 045644003 | Spillway (Bridge) | 1 | 1176862.07 | 751432.36 | 425429.71 | 751432.36 | 3rd Tranche | 202228 | 953660.36 | 751432.36 | 202228 | 100% | 100% | 47.53% | 81.03% | 100% | 2003-10-18 | 2003-12-15 | 2004-06-09 | 2005-09-06 | 2005-09-06 | 454 | 195 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Bayanihan | 045644015 | Day Care Center | 1 | 566103.35 | 358541.04 | 207562.31 | 358541.04 | 3rd Tranche | 192284.31 | 550825.35 | 358541.04 | 192284.31 | 100% | 100% | 92.64% | 97.3% | 100% | 2005-06-02 | 2005-07-28 | 2005-10-24 | 2006-03-31 | no data | 158 | 333 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Calwit | 045644008 | Spring Development | 1 | 1081008.5 | 706016.85 | 374991.65 | 706016.85 | 3rd Tranche | 403299.3 | 1109316.15 | 706016.85 | 403299.3 | 100% | 100% | 107.5% | 102.6% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-24 | 2004-06-22 | no data | 90 | 240 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Calwit | 045644008 | 2 Cl School Building | 1 | 1147728.1 | 714854.8 | 432873.3 | 714854.8 | 2nd Tranche | 136016.2 | 850871 | 714854.8 | 136016.2 | 100% | 100% | 31.42% | 74.14% | 100% | 2006-04-06 | 2006-04-06 | 2006-09-02 | 2006-11-30 | no data | 89 | 240 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Guihalinan | 045644009 | Elevated Water Tank and Supply System | 1 | 1139780.57 | 724081.21 | 415699.36 | 724081.21 | 3rd Tranche | 319952.36 | 1044033.57 | 724081.21 | 319952.36 | 100% | 100% | 76.97% | 91.6% | 100% | 2003-10-18 | 2003-12-15 | 2004-05-18 | 2004-08-29 | no data | 103 | 303 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Guihalinan | 045644009 | 2 Classroom School Building | 1 | 1211916.23 | 805320.95 | 406595.28 | 805320.95 | 3rd Tranche | 292291.38 | 1097612.33 | 805320.95 | 292291.38 | 100% | 100% | 71.89% | 90.57% | 100% | 2005-06-02 | 2005-07-28 | 2005-10-26 | 2006-03-31 | no data | 156 | 303 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Guihalinan | 045644009 | 1 Unit Health Station | 1 | 893845.36 | 590265.66 | 303579.7 | 590265.66 | 3rd Tranche | 263579.7 | 853845.36 | 590265.66 | 263579.7 | 100% | 100% | 86.82% | 95.52% | 100% | 2006-04-06 | 2006-04-06 | 2006-07-03 | 2006-11-30 | no data | 150 | 303 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Lacdayan | 045644010 | Spring Development | 1 | 1071550.78 | 697226.41 | 374324.37 | 697226.41 | 3rd Tranche | 369062.34 | 1066288.75 | 697226.41 | 369062.34 | 100% | 100% | 98.59% | 99.51% | 100% | 2005-06-02 | 2005-07-28 | 2005-12-01 | 2006-03-31 | no data | 120 | 411 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Maguiting | 045644011 | Multi-Purpose Training Center | 1 | 597160.42 | 347328.23 | 249832.19 | 347328.23 | 3rd Tranche | 549379.57 | 896707.8 | 347328.23 | 549379.57 | 100% | 100% | 219.9% | 150.2% | 100% | 2003-10-18 | 2003-12-15 | 2004-02-14 | 2004-05-09 | no data | 85 | 293 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Maguiting | 045644011 | Capabilty Building/Training Package | 1 | 381854 | 214980.92 | 166873.08 | 208649.72 | 1st Tranche | 0 | 208649.72 | 208649.72 | 0 | 100% | #DIV/0! | 0% | 54.64% | 100% | 2006-04-06 | 2006-04-06 | 2006-04-05 | 2007-07-31 | n/a | 482 | 293 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Manlampong | 045644012 | Spring Development | 1 | 449350 | 202884.62 | 246465.38 | 202884.62 | 3rd Tranche | 147627.86 | 350512.48 | 202884.62 | 147627.86 | 100% | 100% | 59.9% | 78% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-24 | 2004-06-20 | no data | 88 | 189 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Pagkakaisa | 045644013 | Multi-Purpose Training Center | 1 | 596554.66 | 369657.43 | 226897.23 | 369657.43 | 3rd Tranche | 416735.65 | 786393.08 | 369657.43 | 416735.65 | 100% | 100% | 183.7% | 131.8% | 100% | 2003-10-18 | 2003-12-15 | 2004-02-10 | 2004-05-05 | no data | 85 | 243 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Punta | 045644017 | Day Care Center | 1 | 341286 | 221061.54 | 120224.46 | 221061.54 | 3rd Tranche | 131749.06 | 352810.6 | 221061.54 | 131749.06 | 100% | 100% | 109.6% | 103.4% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-04 | 2004-07-02 | no data | 120 | 303 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | San Isidro | 045644019 | Farm to Market Road | 1 | 6291241.89 | 3983655.31 | 2307586.58 | 3585289.78 | 1st Tranche | 1388572.59 | 4973862.37 | 3585289.78 | 1388572.59 | 100% | 100% | 60.17% | 79.06% | 100% | 2005-06-02 | 2005-07-28 | 2006-04-05 | 2006-11-08 | n/a | 217 | 290 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | San Juan | 045644020 | Health Station | 1 | 411828.02 | 260367.71 | 151460.31 | 260367.71 | 3rd Tranche | 163259.37 | 423627.08 | 260367.71 | 163259.37 | 100% | 100% | 107.8% | 102.9% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-29 | 2004-08-25 | no data | 149 | 493 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | San Vicente | 045644021 | 2 Classroom School Building with CR | 1 | 828830 | 468792.31 | 360037.69 | 468792.31 | 3rd Tranche | 148322.92 | 617115.23 | 468792.31 | 148322.92 | 100% | 100% | 41.2% | 74.46% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-17 | 2004-06-30 | no data | 105 | 276 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Vigo Central | 045644022 | Day Care Center | 1 | 361568.67 | 222822.05 | 138746.62 | 222822.05 | 3rd Tranche | 185810.46 | 408632.51 | 222822.05 | 185810.46 | 100% | 100% | 133.9% | 113% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-16 | 2004-09-17 | 2004-09-17 | 185 | 542 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | Villa Reyes | 045644024 | 4 Classroom School Building with CR | 1 | 1577929 | 966179.23 | 611749.77 | 966179.23 | 3rd Tranche | 832979.27 | 1799158.5 | 966179.23 | 832979.27 | 100% | 100% | 136.2% | 114% | 100% | 2003-10-18 | 2003-12-15 | 2004-02-09 | 2004-08-20 | no data | 193 | 395 |  | 1 | LUZON
IV-A | 04 | Quezon | 0456 | San Narciso | 045644 | White Cliff | 045644025 | Graveling of Farm to Market Road | 1 | 2683829.4 | 1959376.46 | 724452.94 | 1959376.46 | 3rd Tranche | 150461.27 | 2109837.73 | 1959376.46 | 150461.27 | 100% | 100% | 20.77% | 78.61% | 100% | 2003-10-18 | 2003-12-15 | 2004-03-26 | 2006-06-01 | no data | 797 | 395 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bagacay | 174002001 | Water Supply and Distribution System Level II | 1 | 558924.01 | 333018.47 | 225905.54 | 333018.47 | 3rd Tranche | 235905.54 | 568924.01 | 333018.47 | 235905.54 | 100% | 100% | 104.4% | 101.8% | 100% | 2005-04-20 | 2005-05-26 | 2005-09-19 | 2005-12-17 | 2006-01-27 | 89 | 220 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bagacay | 174002001 | Const. of 2-Units 2-CL. HS Bldg. | 1 | 1902099.95 | 1463153.81 | 438946.14 | 1463153.81 | 2nd Tranche | 550632.26 | 2013786.07 | 1463153.81 | 550632.26 | 100% | 100% | 125.4% | 105.9% | 100% | 2006-06-17 | 2006-06-17 | 2006-10-02 | 2008-03-31 | no data | 546 | 150 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bagacay | 174002001 | Improvement of Farm-to-Market Road | 1 | 1924810 | 1481000 | 443810 | 1464237.43 |  | 635910.28 | 2100147.71 | 1464237.43 | 635910.28 | 100% | 100% | 143.3% | 109.1% | 100% | 2008-07-27 | 2008-07-27 | 2007-11-19 | 2008-06-30 | no data | 224 | 230 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bagtingon | 174002002 | Construction of 4-Barrel Box Culvert | 1 | 1843300 | 1418000 | 425300 | 1418000 |  | 642197.06 | 2060197.06 | 1418000 | 642197.06 | 100% | 100% | 151% | 111.8% | 100% | 2008-07-27 | 2008-07-27 | 2007-11-21 | 2008-09-30 | n/a | 314 | 346 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bicas-Bicas | 174002003 | Improvement of FMR | 1 | 2022314.26 | 1555626.35 | 466687.91 | 1555626.35 | 1st Tranche | 616790.84 | 2172417.19 | 1555626.35 | 616790.84 | 100% | 100% | 132.2% | 107.4% | 100% | 2006-06-17 | 2006-06-17 | 2006-10-03 | 2008-03-31 | no data | 545 | 176 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bicas-bicas | 174002003 | Improvement & Expansion of Water Supply System | 1 | 2201924 | 1590000 | 611924 | 1515305 |  | 696791.45 | 2212096.45 | 1515305 | 696791.45 | 100% | 100% | 113.9% | 100.5% | 100% | 2008-07-27 | 2008-07-27 | 2007-12-03 | 2008-09-30 | n/a | 302 | 178 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Caigangan | 174002004 | Water Supply and Distribution System | 1 | 867159.76 | 554538.28 | 312621.48 | 554538.28 | 3rd Tranche | 324173.46 | 878711.74 | 554538.28 | 324173.46 | 100% | 100% | 103.7% | 101.3% | 100% | 2005-04-20 | 2005-05-26 | 2005-09-18 | 2005-12-31 | 2006-01-23 | 104 | 324 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Daykitin | 174002005 | 1-Unit Classroom Bldg. | 1 | 1009513.49 | 688471.92 | 321041.57 | 688471.88 | 3rd Tranche | 332591.57 | 1021063.45 | 688471.88 | 332591.57 | 100% | 100% | 103.6% | 101.1% | 100% | 2005-04-20 | 2005-05-26 | 2005-08-29 | 2006-01-30 | 2006-01-31 | 154 | 438 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Malbog | 174002007 | Spring Development and Distribution System | 1 | 1271771.49 | 793780.18 | 477991.31 | 793780.18 | 3rd Tranche | 507317.05 | 1301097.23 | 793780.18 | 507317.05 | 100% | 100% | 106.1% | 102.3% | 100% | 2005-04-20 | 2005-05-26 | 2005-08-29 | 2005-12-20 | 2006-01-28 | 113 | 324 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Poblacion Uno | 174002015 | Construction of Elevated Water Tank and Distribution System | 1 | 620187.75 | 384759.81 | 235427.94 | 384759.81 | 3rd Tranche | 240759.4 | 625519.21 | 384759.81 | 240759.4 | 100% | 100% | 102.3% | 100.9% | 100% | 2005-04-20 | 2005-05-26 | 2005-08-29 | 2006-01-31 | 2006-01-30 | 155 | 215 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Sihi | 174002011 | Elevated Concrete Water Tank and Distribution Lines (3.942 km) | 1 | 1185586.49 | 775431.92 | 410154.57 | 775431.92 | 3rd Tranche | 462349.57 | 1237781.49 | 775431.92 | 462349.57 | 100% | 100% | 112.7% | 104.4% | 100% | 2005-04-20 | 2005-05-26 | 2005-08-29 | 2006-01-31 | 2006-01-31 | 155 | 320 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Sihi | 174002011 | Const. of 2-Units 2-CL. HS Bldg. | 1 | 1884756.5 | 1449812.69 | 434943.81 | 1449812.69 | 2nd Tranche | 545811.76 | 1995624.45 | 1449812.69 | 545811.76 | 100% | 100% | 125.5% | 105.9% | 100% | 2006-06-17 | 2006-06-17 | 2006-10-03 | 2008-03-31 | no data | 545 | 295 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Timbo-Sanggulong | 174002012 | Construction of Intake Box and Transmission Line | 1 | 215452.99 | 85425.38 | 130027.61 | 85425.38 | 3rd Tranche | 147401.82 | 232827.2 | 85425.38 | 147401.82 | 100% | 100% | 113.4% | 108.1% | 100% | 2005-04-20 | 2005-05-26 | 2005-08-29 | 2005-12-23 | 2006-01-26 | 116 | 147 |  | 1 | LUZON
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Yook | 174002014 | Repair / Rehabilitation of Water System | 1 | 1113258.01 | 790148.47 | 323109.54 | 790148.47 | 3rd Tranche | 371944.53 | 1162093 | 790148.47 | 371944.53 | 100% | 100% | 115.1% | 104.4% | 100% | 2005-04-20 | 2005-05-26 | 2005-09-12 | 2006-01-05 | 2006-02-03 | 115 | 523 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Batong Buhay | 175109001 | Construction of 1 Unit 2-Classroom High School Building | 1 | 1195280.12 | 748740.57 | 446539.55 | 735978.23 | 1st Tranche | 455142.87 | 1191121.1 | 735978.23 | 455142.87 | 100% | 100% | 101.9% | 99.65% | 100% | 2008-05-07 | 2007-05-24 | 2007-08-24 | 2008-04-30 | no data | 250 | 413 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Buenavista | 175109002 | Rehabilitation of Hanging Bridge | 1 | 2250000 | 1712800 | 537200 | 1712800 |  | 537200 | 2250000 | 1712800 | 537200 | 100% | 100% | 100% | 100% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-18 | 2008-10-30 | n/a | 73 | 2810 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Claudio Salgado | 175109004 | Construction of 2 Units 3-Classroom Elementary School Building | 1 | 3231169.45 | 1759148.77 | 1472020.68 | 1734191.61 | 1st Tranche | 996143.68 | 2730335.29 | 1734191.61 | 996143.68 | 100% | 100% | 67.67% | 84.5% | 100% | 2008-05-07 | 2007-05-24 | 2007-08-20 | 2008-04-30 | no data | 254 | 135 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | General Emilio Aguinaldo | 175109005 | 2 Units Solar Dyer | 1 | 1010000 | 781488.8 | 228511.2 | 781488.8 |  | 296585.2 | 1078074 | 781488.8 | 296585.2 | 100% | 100% | 129.8% | 106.7% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-12 | 2008-10-30 | n/a | 79 | 100 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Ibud | 175109006 | Construction of Draiange / Irrigation Canal | 1 | 1480060.65 | 1070219.56 | 409841.09 | 1045230.2 | 1st Tranche | 452965.07 | 1498195.27 | 1045230.2 | 452965.07 | 100% | 100% | 110.5% | 101.2% | 100% | 2008-05-07 | 2007-05-24 | 2007-07-31 | 2007-12-15 | no data | 137 | 300 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Ibud | 175109006 | 1 Units Solar Dyer | 1 | 670000 | 451190.4 | 218809.6 | 451190.4 |  | 286252.03 | 737442.43 | 451190.4 | 286252.03 | 100% | 100% | 130.8% | 110.1% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-01 | 2008-10-30 | n/a | 90 | 47 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Ilvita | 175109007 | Construction 0f 9 Units Multi- Purpose Pavement | 1 | 3023000 | 2365800 | 657200 | 2361527.78 |  | 601437 | 2962964.78 | 2361527.78 | 601437 | 100% | 100% | 91.52% | 98.01% | 100% | 2009-02-05 | 2009-02-05 | 2009-03-16 | 2009-06-30 | n/a | 106 | 450 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Malisbong | 175109023 | Construction of Shallow Tube Well | 1 | 1665151.3 | 1132897.62 | 532253.68 | 1132897.6 | 1st Tranche | 545968.19 | 1678865.79 | 1132897.6 | 545968.19 | 100% | 100% | 102.6% | 100.8% | 100% | 2008-05-07 | 2007-05-24 | 2007-08-13 | 2008-11-30 | n/a | 475 | 210 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Pag-Asa | 175109011 | 1 Units Solar Dyer | 1 | 675000 | 507476 | 167524 | 507476 |  | 214119 | 721595 | 507476 | 214119 | 100% | 100% | 127.8% | 106.9% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-11 | 2008-10-11 | n/a | 61 | 300 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Pag-Asa | 175109011 | Improvement of water System (Construction of Filtration Box) | 1 | 652651.81 | 515000.01 | 137651.8 | 515000 |  | 168601.91 | 683601.91 | 515000 | 168601.91 | 100% | 100% | 122.5% | 104.7% | 100% | 2009-02-05 | 2009-02-05 | 2009-03-18 | 2009-06-30 | n/a | 104 | 341 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Agustin | 175109013 | Construction of 2 Units Solar dryer | 1 | 887905 | 334242.8 | 553662.2 | 329454 |  | 559542.2 | 888996.2 | 329454 | 559542.2 | 100% | 100% | 101.1% | 100.1% | 100% | 2009-02-05 | 2009-02-05 | 2009-03-16 | 2009-05-31 | n/a | 76 | 100 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Francisco | 175109014 | 2 Units Solar Dyer | 1 | 695000 | 525391.2 | 169608.8 | 525391.2 |  | 163429.8 | 688821 | 525391.2 | 163429.8 | 100% | 100% | 96.36% | 99.11% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-14 | 2008-10-30 | n/a | 77 | 529 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Vicente | 175109017 | Construction of 1 Units 2-Classroom School Building | 1 | 1440000 | 1113400 | 326600 | 1113400 |  | 358252.8 | 1471652.8 | 1113400 | 358252.8 | 100% | 100% | 109.7% | 102.2% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-14 | 2008-12-15 | n/a | 123 | 549 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Vicente | 175109017 | Construction of 4 Units Solar Dryer | 1 | 2912300 | 2300000 | 612300 | 2070000 |  | 616000 | 2686000 | 2070000 | 616000 | 100% | 100% | 100.6% | 92.23% | 100% | 2009-02-05 | 2009-02-05 | 2009-03-19 | 2009-06-30 | n/a | 103 | 383 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Sta. Lucia | 175109018 | Construction of 1 Unit 2-Classroom Elementary School Building | 1 | 1157136.12 | 766231.04 | 390905.08 | 752339.99 | 1st Tranche | 404568.98 | 1156908.97 | 752339.99 | 404568.98 | 100% | 100% | 103.5% | 99.98% | 100% | 2008-05-07 | 2007-05-24 | 2007-08-06 | 2007-12-15 | no data | 131 | 657 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Tagumpay | 175109020 | 1 Units Solar Dyer | 1 | 640000 | 489884 | 150116 | 489884 |  | 215156 | 705040 | 489884 | 215156 | 100% | 100% | 143.3% | 110.2% | 100% | 2008-05-19 | 2008-05-19 | 2008-08-14 | 2008-10-30 | n/a | 77 | 93 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Tuban | 175109024 | Construction of 1 Unit 2-Classroom Elementary School Building | 1 | 1193093.43 | 816371.77 | 376721.66 | 805929.21 | 1st Tranche | 386678.75 | 1192607.96 | 805929.21 | 386678.75 | 100% | 100% | 102.6% | 99.96% | 100% | 2008-05-07 | 2007-05-24 | 2007-08-15 | 2007-12-15 | no data | 122 | 485 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Victoria | 175109021 | Construction of 1 Unit Day Care Center | 1 | 639813.83 | 306390.66 | 333423.17 | 306390.66 | 1st Tranche | 338939.17 | 645329.83 | 306390.66 | 338939.17 | 100% | 100% | 101.7% | 100.9% | 100% | 2008-05-07 | 2008-05-24 | 2007-07-29 | 2007-12-15 | no data | 139 | 129 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Victoria | 175109021 | 4 Units Solar Dyer | 1 | 1310000 | 1018369.6 | 291630.4 | 1018369.6 |  | 367994.89 | 1386364.49 | 1018369.6 | 367994.89 | 100% | 100% | 126.2% | 105.8% | 100% | 2008-05-19 | 2008-05-19 | 2008-07-29 | 2008-10-30 | n/a | 93 | 161 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Victoria | 175109021 | Construction of 1 Unit 2 Classroom High School Building | 1 | 1459400 | 1172000 | 287400 | 1172000 |  | 316987 | 1488987 | 1172000 | 316987 | 100% | 100% | 110.3% | 102% | 100% | 2009-02-05 | 2009-02-05 | 2009-03-13 | 2009-05-31 | n/a | 79 | 295 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Alacaak | 175111001 | Construction of Day Care Center | 1 | 486600 | 327757.44 | 158842.56 | 315374.22 |  | 155293.64 | 470667.86 | 315374.22 | 155293.64 | 100% | 100% | 97.77% | 96.73% | 100% | 2007-07-23 | 2007-07-23 | 2007-10-16 | 2008-04-30 | no data | 197 | 520 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Barahan | 175111002 | Construction of Day Care Center | 1 | 504596.15 | 262234.73 | 242361.42 | 262234.72 | 3rd Tranche | 241841.34 | 504076.06 | 262234.72 | 241841.34 | 100% | 100% | 99.79% | 99.9% | 100% | 2005-04-30 | 2005-05-31 | 2005-09-01 | 2006-01-10 | 2006-01-16 | 131 | 299 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Dayap | 175111004 | Const. of Spillway with Concrete Approach | 1 | 730800 | 528527.56 | 202272.44 | 528527.56 | 1st Tranche | 208635.9 | 737163.46 | 528527.56 | 208635.9 | 100% | 100% | 103.1% | 100.9% | 100% | 2006-06-16 | 2006-06-23 | 2006-09-19 | 2007-02-15 | no data | 149 | 400 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Kurtinganan | 175111012 | Contruction of Two-Barrel Box Culvert | 1 | 645000 | 424474.36 | 220525.64 | 424474.36 |  | 270272.7 | 694747.06 | 424474.36 | 270272.7 | 100% | 100% | 122.6% | 107.7% | 100% | 2007-07-23 | 2007-07-23 | 2007-10-13 | 2007-12-05 | no data | 53 | 267 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Lumangbayan | 175111006 | Rehabilitation of Farm to Market Road | 1 | 1759496.33 | 1106471.95 | 653024.38 | 1106471.95 | 3rd Tranche | 555044.18 | 1661516.13 | 1106471.95 | 555044.18 | 100% | 100% | 85% | 94.43% | 100% | 2005-04-30 | 2005-05-31 | 2005-10-03 | 2006-04-03 | 2006-04-04 | 182 | 393 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Lumangbayan | 175111006 | Construction of 2-CL ES Building | 1 | 1060000 | 696034.1 | 363965.9 | 688832.51 |  | 365341.33 | 1054173.84 | 688832.51 | 365341.33 | 100% | 100% | 100.4% | 99.45% | 100% | 2007-07-23 | 2007-07-23 | 2007-11-13 | 2008-04-30 | no data | 169 | 408 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Mulawin | 175111007 | Const. of Concrete Drainage Canal | 1 | 809355.004 | 397075.644 | 412279.36 | 397075.644 | 2nd Tranche | 414956.58 | 812032.224 | 397075.644 | 414956.58 | 100% | 100% | 100.6% | 100.3% | 100% | 2006-06-16 | 2006-06-23 | 2006-09-19 | 2007-02-15 | no data | 149 | 400 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Mulawin | 175111007 | Construction of Day Care Center | 1 | 486600 | 346057.44 | 140542.56 | 333021.42 |  | 140859.19 | 473880.61 | 333021.42 | 140859.19 | 100% | 100% | 100.2% | 97.39% | 100% | 2007-07-23 | 2007-07-23 | 2007-10-09 | 2008-04-30 | no data | 204 | 300 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Pinagturilan | 175111008 | Construction of Health Station | 1 | 582028.58 | 367888.41 | 214140.17 | 367888.41 | 3rd Tranche | 214683.7 | 582572.11 | 367888.41 | 214683.7 | 100% | 100% | 100.3% | 100.1% | 100% | 2005-04-30 | 2005-05-31 | 2005-08-09 | 2006-02-15 | 2006-02-16 | 190 | 1101 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Pinagturilan | 175111008 | Ext. of Level II Water System | 1 | 1532968.86 | 1111187.19 | 421781.67 | 1111187.19 | 1st Tranche | 508329.4 | 1619516.59 | 1111187.19 | 508329.4 | 100% | 100% | 120.5% | 105.6% | 100% | 2006-06-16 | 2006-06-23 | 2006-11-07 | 2007-03-15 | no data | 128 | 258 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Pinagturilan | 175111008 | Construction of 3-CL HS Building | 1 | 1330000 | 871628.21 | 458371.79 | 834615.6 |  | 434012.54 | 1268628.14 | 834615.6 | 434012.54 | 100% | 100% | 94.69% | 95.39% | 100% | 2007-07-23 | 2007-07-23 | 2008-01-07 | 2008-04-30 | no data | 114 | 675 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Poblacion 1 | 175111009 | Construction of Day Care Center | 1 | 534996.15 | 318066.27 | 216929.88 | 318066.27 | 3rd Tranche | 177282.55 | 495348.82 | 318066.27 | 177282.55 | 100% | 100% | 81.72% | 92.59% | 100% | 2005-04-30 | 2005-05-31 | 2005-08-26 | 2005-11-08 | 2005-11-18 | 74 | 299 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Poblacion 1 - C2 | 175111009 | Upgrading of Water System Level II With Elevated Water Tank | 2 | 2416091 | 935903.33 | 1480187.67 | 935903.33 | 1st Tranche | 2187395.75 | 3123299.08 | 935903.33 | 2187395.75 | 100% | 100% | 147.8% | 129.3% | 100% | 2006-06-16 | 2006-06-23 | 2006-11-07 | 2007-03-15 | no data | 128 | 703 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Poblacion 2 | 175111011 | 2 Classroom School Building | 1 | 1100546.72 | 739305.17 | 361241.55 | 739305.17 | 3rd Tranche | 394791.25 | 1134096.42 | 739305.17 | 394791.25 | 100% | 100% | 109.3% | 103% | 100% | 2005-04-30 | 2005-05-31 | 2005-08-29 | 2006-01-13 | 2006-01-16 | 137 | 404 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | San Vicente | 175111010 | Const. of Day Care Center | 1 | 517056.5 | 327306.28 | 189750.22 | 327306.278 | 3rd Tranche | 192236.2 | 519542.478 | 327306.278 | 192236.2 | 100% | 100% | 101.3% | 100.5% | 100% | 2006-06-16 | 2006-06-23 | 2006-09-11 | 2006-11-23 | no data | 73 | 240 |  | 1 | LUZON
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | San Vicente | 175111010 | Construction of Spillway | 1 | 765000 | 520057.69 | 244942.31 | 510098.62 |  | 288445.06 | 798543.68 | 510098.62 | 288445.06 | 100% | 100% | 117.8% | 104.4% | 100% | 2007-07-23 | 2007-07-23 | 2007-11-06 | 2008-05-31 | no data | 207 | 328 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Anilao | 175203001 | Construction of 2 Units 3-Classroom Elementary School Building | 1 | 2550000 | 1905297.91 | 644702.09 | 1905297.9 |  | 583451.1 | 2488749 | 1905297.9 | 583451.1 | 100% | 100% | 90.5% | 97.6% | 100% | 2008-07-04 | 2008-07-04 | 2008-10-20 | 2009-02-28 | n/a | 131 | 503 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Bagong Bayan 1 | 175203034 | Construction of Drainage / Irrigation Canal | 1 | 1629600 | 1402924.54 | 226675.46 | 1402924.54 |  | 210748.15 | 1613672.69 | 1402924.54 | 210748.15 | 100% | 100% | 92.97% | 99.02% | 100% | 2007-06-12 | 2007-06-13 | 2007-12-24 | 2008-05-31 | n/a | 159 | 431 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Batangan | 175203002 | Construction of Health Station | 1 | 758000 | 543586.12 | 214413.88 | 489227.51 |  | 216612.9 | 705840.41 | 489227.51 | 216612.9 | 100% | 100% | 101% | 93.12% | 100% | 2009-01-16 | 2009-01-16 | 2009-05-26 | 2009-07-31 | n/a | 66 | 246 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Carmundo | 175203005 | Construction of 1 Unit 3-Classroom High School Bldg | 1 | 1779000 | 1274161.69 | 504838.31 | 1274161.69 |  | 472324.31 | 1746486 | 1274161.69 | 472324.31 | 100% | 100% | 93.56% | 98.17% | 100% | 2009-01-16 | 2009-01-16 | 2009-03-29 | 2009-06-30 | n/a | 93 | 348 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Cawayan | 175203006 | Construction of 1 Unit 3-Classroom Elementary School Bldg | 1 | 1800000 | 1244921.9 | 555078.1 | 1120429.71 |  | 536395.32 | 1656825.03 | 1120429.71 | 536395.32 | 100% | 100% | 96.63% | 92.05% | 100% | 2009-01-16 | 2009-01-16 | 2009-03-23 | 2009-06-30 | n/a | 99 | 454 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Dayhagan | 175203007 | Proposed Construction of Health Center | 1 | 881000 | 645321.54 | 235678.46 | 641329.23 |  | 250551.11 | 891880.34 | 641329.23 | 250551.11 | 100% | 100% | 106.3% | 101.2% | 100% | 2008-07-04 | 2008-07-04 | 2008-09-15 | 2008-12-15 | n/a | 91 | 433 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Formon | 175203008 | Construction of 2 Units 2-Classroom School Building | 1 | 2442000 | 1822356.77 | 619643.23 | 1822356.77 |  | 628263.23 | 2450620 | 1822356.77 | 628263.23 | 100% | 100% | 101.4% | 100.4% | 100% | 2009-01-16 | 2009-01-16 | 2009-04-27 | 2009-06-30 | n/a | 64 | 288 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Hagan | 175203009 | Construction of Level II Water System | 1 | 2153600 | 1863468.99 | 290131.01 | 1852923.94 | 1st Tranche | 309252.26 | 2162176.2 | 1852923.94 | 309252.26 | 100% | 100% | 106.6% | 100.4% | 100% | 2007-06-12 | 2007-06-13 | 2007-11-20 | 2008-06-30 | no data | 223 | 453 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Hagupit | 175203010 | Construction of 1 Units 3-Classroom Elementary School Building | 1 | 1909900 | 1215895.98 | 694004.02 | 1173072.87 | 1st Tranche | 705715.09 | 1878787.96 | 1173072.87 | 705715.09 | 100% | 100% | 101.7% | 98.37% | 100% | 2007-06-12 | 2007-06-13 | 2007-11-28 | 2008-06-12 | no data | 197 | 104 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Hagupit | 175203010 | Proposed Construction of Health Center | 1 | 883000 | 630699.32 | 252300.68 | 630699.32 |  | 273652.39 | 904351.71 | 630699.32 | 273652.39 | 100% | 100% | 108.5% | 102.4% | 100% | 2008-07-04 | 2008-07-04 | 2008-09-12 | 2008-11-08 | n/a | 57 | 150 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Kaligtasan | 175203011 | Construction of 1 Units 3-Classroom High School Building | 1 | 2147000 | 1576444.7 | 570555.3 | 1484021.96 |  | 600918.2 | 2084940.16 | 1484021.96 | 600918.2 | 100% | 100% | 105.3% | 97.11% | 100% | 2008-07-04 | 2008-07-04 | 2008-09-08 | 2008-11-20 | n/a | 73 | 382 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Labasan | 175203012 | Construction of 1 Unit 2-Classroom High School Building | 1 | 1265000 | 1138100.01 | 126899.99 | 1092915.01 |  | 126899.99 | 1219815 | 1092915.01 | 126899.99 | 100% | 100% | 100% | 96.43% | 100% | 2009-01-16 | 2009-01-16 | 2009-05-25 | 2009-06-30 | n/a | 36 | 830 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Labonan | 175203013 | Construction of 1 Unit 3-Classroom Elementary School Bldg | 1 | 1822000 | 1304150.63 | 517849.37 | 1156920.51 |  | 525223.43 | 1682143.94 | 1156920.51 | 525223.43 | 100% | 100% | 101.4% | 92.32% | 100% | 2009-01-16 | 2009-01-16 | 2009-03-16 | 2009-06-30 | n/a | 106 | 234 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Libertad | 175203014 | Improvement of farm to Market Road with Spillway | 1 | 2078000 | 1577234.96 | 500765.04 | 1577234.96 |  | 482956.89 | 2060191.85 | 1577234.96 | 482956.89 | 100% | 100% | 96.44% | 99.14% | 100% | 2009-01-16 | 2009-01-16 | 2009-03-16 | 2009-05-31 | n/a | 76 | 423 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Luna | 175203016 | Proposed Construction of Health Center | 1 | 870000 | 642493.28 | 227506.72 | 642493.28 |  | 229699.4 | 872192.68 | 642493.28 | 229699.4 | 100% | 100% | 101% | 100.3% | 100% | 2008-07-04 | 2008-07-04 | 2008-09-15 | 2008-11-30 | n/a | 76 | 302 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Masaguisi | 175203019 | Improvement/Expansion of Sea Wall | 1 | 3930000 | 2271028.21 | 1658971.79 | 2271028.2 |  | 1455628.69 | 3726656.89 | 2271028.2 | 1455628.69 | 100% | 100% | 87.74% | 94.83% | 100% | 2008-07-04 | 2008-07-04 | 2008-10-20 | 2009-02-28 | n/a | 131 | 319 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Mina de Oro | 175203037 | Construction of 1 Unit 3-Classroom Elementary School Bldg | 1 | 1911700 | 1573589.54 | 338110.46 | 1573589.54 | 1st Tranche | 286764.71 | 1860354.25 | 1573589.54 | 286764.71 | 100% | 100% | 84.81% | 97.31% | 100% | 2007-06-12 | 2007-06-13 | 2007-10-22 | 2008-05-29 | no data | 220 | 189 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Mina de Oro | 175203037 | Construction of Health Station | 1 | 755000 | 500836.27 | 254163.73 | 500836.27 |  | 263866.23 | 764702.5 | 500836.27 | 263866.23 | 100% | 100% | 103.8% | 101.3% | 100% | 2009-01-16 | 2009-01-16 | 2009-05-04 | 2009-06-30 | n/a | 57 | 300 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Ogbot | 175203021 | Construction of Box Culvert | 1 | 455000 | 329456.35 | 125543.65 | 301855.99 |  | 148846.51 | 450702.5 | 301855.99 | 148846.51 | 100% | 100% | 118.6% | 99.06% | 100% | 2008-07-04 | 2008-07-04 | 2008-08-27 | 2008-10-15 | n/a | 49 | 242 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Orconuma | 175203022 | Construction of 1 Units 3-Classroom Elementary School Building | 1 | 1910500 | 1609549.54 | 300950.46 | 1565416.74 |  | 244970.46 | 1810387.2 | 1565416.74 | 244970.46 | 100% | 100% | 81.4% | 94.76% | 100% | 2007-06-12 | 2007-06-13 | 2007-12-11 | 2008-05-29 | no data | 170 | 236 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Orconuma | 175203022 | Construction of Health Station | 1 | 753000 | 520099.47 | 232900.53 | 468089.53 |  | 226223.28 | 694312.81 | 468089.53 | 226223.28 | 100% | 100% | 97.13% | 92.21% | 100% | 2009-01-16 | 2009-01-16 | 2009-05-04 | 2009-06-30 | n/a | 57 | 352 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Sagana | 175203024 | Construction of 1 Units 3-Classroom Elementary School Building | 1 | 1908600 | 1511292.34 | 397307.66 | 1498625.34 | 1st Tranche | 310520.75 | 1809146.09 | 1498625.34 | 310520.75 | 100% | 100% | 78.16% | 94.79% | 100% | 2007-06-12 | 2007-06-13 | 2007-12-10 | 2008-07-31 | no data | 234 | 284 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | San Isidro | 175203025 | Construction of 1 Units 3-Classroom High School Building | 1 | 2146000 | 1603121.69 | 542878.31 | 1603121.69 |  | 440337.54 | 2043459.23 | 1603121.69 | 440337.54 | 100% | 100% | 81.11% | 95.22% | 100% | 2008-07-04 | 2008-07-04 | 2008-09-08 | 2008-12-31 | n/a | 114 | 273 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | San Jose | 175203026 | Feasibility Study & Topo Survey | 1 | 353800 | 214769.54 | 139030.46 | 150338.68 | 1st Tranche | 140030.92 | 290369.6 | 150338.68 | 140030.92 | 100% | 100% | 100.7% | 82.07% | 100% | 2007-06-12 | 2007-06-13 | 2007-11-25 | 2008-06-25 | no data | 213 | 204 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | San Juan | 175203027 | Upgrading of farm to Market Road | 1 | 1622900 | 1408509.53 | 214390.47 | 1408509.53 |  | 177417.96 | 1585927.49 | 1408509.53 | 177417.96 | 100% | 100% | 82.75% | 97.72% | 100% | 2007-06-12 | 2007-06-13 | 2007-12-26 | 2008-07-31 | no data | 218 | 78 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | San Juan | 175203027 | Construction of 2 units spillway | 1 | 641000 | 432553.42 | 208446.58 | 409082.73 |  | 190337.83 | 599420.56 | 409082.73 | 190337.83 | 100% | 100% | 91.31% | 93.51% | 100% | 2009-01-16 | 2009-01-16 | 2009-03-09 | 2009-05-31 | n/a | 83 | 113 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Sigange | 175203029 | Construction of Day Care Center | 1 | 672900 | 402254.89 | 270645.11 | 362029.4 |  | 222125.09 | 584154.49 | 362029.4 | 222125.09 | 100% | 100% | 82.07% | 86.81% | 100% | 2009-01-16 | 2009-01-16 | 2009-04-23 | 2009-06-30 | n/a | 68 | 202 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Sta. Cruz | 175203028 | Construction of Health Station | 1 | 739000 | 454943 | 284057 | 449737.62 |  | 271027.4 | 720765.02 | 449737.62 | 271027.4 | 100% | 100% | 95.41% | 97.53% | 100% | 2009-01-16 | 2009-01-16 | 2009-04-27 | 2009-06-30 | n/a | 64 | 250 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Tawas | 175203031 | Consttruction of Flood Control(Gabion Type) | 1 | 1478637 | 1196137 | 282500 | 1196137 |  | 58284 | 1254421 | 1196137 | 58284 | 100% | 100% | 20.63% | 84.84% | 100% | 2008-07-04 | 2008-07-04 | 2008-10-22 | 2009-02-28 | n/a | 129 | 259 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Balatasan | 175204002 | Const. of Health Station | 1 | 640000 | 448892.31 | 191107.69 | 448892.3 | 1st Tranche | 182910.39 | 631802.69 | 448892.3 | 182910.39 | 100% | 100% | 95.71% | 98.72% | 100% | 2006-07-11 | 2006-07-28 | 2006-10-31 | 2007-01-15 | no data | 76 | 448 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Benli (Mangyan Settlement) | 175204003 | Rehabilitation of FMR | 1 | 2991000 | 1610000 | 1381000 | 805000 | 1st Tranche | 254414.13 | 1059414.13 | 805000 | 254414.13 | 100% | 100% | 18.42% | 35.42% | 100% | 2005-04-26 | 2005-05-30 | 2006-01-18 | 2008-04-30 | no data | 833 | 451 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Cabugao | 175204005 | Const. of 3-CL School Building | 1 | 1524000 | 1075353.84 | 448646.16 | 1075353.84 | 1st Tranche | 323736.16 | 1399090 | 1075353.84 | 323736.16 | 100% | 100% | 72.16% | 91.8% | 100% | 2006-07-11 | 2006-07-28 | 2006-10-23 | 2007-02-23 | no data | 123 | 171 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Maasin | 175204008 | Construction of Water System Level II | 1 | 431000 | 260681.7 | 170318.3 | 260681.7 | 3rd Tranche | 192951.99 | 453633.69 | 260681.7 | 192951.99 | 100% | 100% | 113.3% | 105.3% | 100% | 2005-04-26 | 2005-05-30 | 2005-09-08 | 2005-11-25 | 2005-11-29 | 78 | 122 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Maasin | 175204008 | Construction of Classroom School Building | 1 | 1493383 | 1009947 | 483436 | 998803.74 |  | 496460 | 1495263.74 | 998803.74 | 496460 | 100% | 100% | 102.7% | 100.1% | 100% | 2007-09-12 | 2007-09-12 | 2007-10-25 | 2008-06-30 | no data | 249 | 77 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Milagrosa | 175204010 | Upgrading of FMR | 1 | 3760000 | 2855323.07 | 904676.93 | 2855323.07 |  | 734636.93 | 3589960 | 2855323.07 | 734636.93 | 100% | 100% | 81.2% | 95.48% | 100% | 2006-07-11 | 2006-07-28 | 2006-12-10 | 2007-03-15 | no data | 95 | 323 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | San Francisco | 175204013 | Construction of 2 Classroom School Building | 1 | 1369791 | 995143 | 374648 | 985916.14 |  | 421455.75 | 1407371.89 | 985916.14 | 421455.75 | 100% | 100% | 112.5% | 102.7% | 100% | 2007-09-12 | 2007-09-12 | 2007-10-16 | 2008-06-30 | no data | 258 | 62 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | San Isidro | 175204014 | Rehabilitation of FMR | 1 | 3991000 | 2627993.85 | 1363006.15 | 2627993.85 | 2nd Tranche | 1587079.25 | 4215073.1 | 2627993.85 | 1587079.25 | 100% | 100% | 116.4% | 105.6% | 100% | 2005-04-26 | 2005-05-30 | 2006-01-12 | 2007-03-31 | no data | 443 | 94 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Balugo | 175207002 | Construction of Day Care Center | 1 | 690000 | 288705.1 | 401294.9 | 259834.59 |  | 401294.9 | 661129.49 | 259834.59 | 401294.9 | 100% | 100% | 100% | 95.82% | 100% | 2007-06-19 | 2007-08-03 | 2008-01-21 | 2008-03-30 | no data | 69 | 58 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Balugo | 175207002 | Construction of Water Supply and Distribution System | 1 | 1680000 | 1269057.9 | 410942.1 | 1142152.11 |  | 466646.45 | 1608798.56 | 1142152.11 | 466646.45 | 100% | 100% | 113.6% | 95.76% | 100% | 2009-01-07 | 2009-01-21 | 2009-03-09 | 2009-04-30 | n/a | 52 | 283 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Bonbon | 175207003 | Spring Development Level II | 1 | 1820000 | 1379237.84 | 440762.16 | 1103390.27 |  | 510784.75 | 1614175.02 | 1103390.27 | 510784.75 | 100% | 100% | 115.9% | 88.69% | 100% | 2009-01-07 | 2009-01-21 | 2009-03-09 | 2009-05-31 | n/a | 83 | 316 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Budburan | 175207004 | Construction of 1 Unit, 2 Classroom School Building | 1 | 1425282 | 1087858.01 | 337423.99 | 1087858.01 |  | 338423.99 | 1426282 | 1087858.01 | 338423.99 | 100% | 100% | 100.3% | 100.1% | 100% | 2008-04-28 | 2008-06-11 | 2008-09-30 | 2008-12-30 | n/a | 91 | 230 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Cabalwa | 175207005 | Construction of Water Supply & Distribution System | 1 | 2000000 | 1543447.02 | 456552.98 | 1487659.39 | 1st Tranche | 450552.98 | 1938212.37 | 1487659.39 | 450552.98 | 100% | 100% | 98.69% | 96.91% | 100% | 2007-06-19 | 2007-08-03 | 2007-11-20 | 2008-04-18 | no data | 150 | 226 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Cabalwa | 175207005 | Improvement of farm to Market Road | 1 | 1728615 | 1307932.41 | 420682.59 | 1307932.41 |  | 419891.59 | 1727824 | 1307932.41 | 419891.59 | 100% | 100% | 99.81% | 99.95% | 100% | 2008-04-28 | 2008-06-11 | 2008-10-27 | 2009-02-28 | n/a | 124 | 230 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Don Pedro | 175207007 | Construction of Day Care Center | 1 | 709354 | 515634.43 | 193719.57 | 464070.98 |  | 191173.47 | 655244.45 | 464070.98 | 191173.47 | 100% | 100% | 98.69% | 92.37% | 100% | 2008-04-28 | 2008-06-11 | 2008-08-04 | 2008-09-27 | n/a | 54 | 105 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Don Pedro | 175207007 | Construction of 1 Unit 2-Classroom High School Building | 1 | 1290000 | 974349.39 | 315650.61 | 876914.45 |  | 361850.61 | 1238765.06 | 876914.45 | 361850.61 | 100% | 100% | 114.6% | 96.03% | 100% | 2009-01-07 | 2009-01-21 | 2009-03-05 | 2009-05-31 | n/a | 87 | 198 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Maliwanag | 175207010 | Water Supply and Distribution System | 1 | 1329537 | 992470.08 | 337066.92 | 992470.08 |  | 331987.04 | 1324457.12 | 992470.08 | 331987.04 | 100% | 100% | 98.49% | 99.62% | 100% | 2008-04-28 | 2008-06-11 | 2008-10-27 | 2009-01-31 | n/a | 96 | 228 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Roma | 175207014 | Community Base Pre School Building | 1 | 847228 | 647631.24 | 199596.76 | 626587.49 |  | 199627.76 | 826215.25 | 626587.49 | 199627.76 | 100% | 100% | 100% | 97.52% | 100% | 2008-04-28 | 2008-06-11 | 2008-10-04 | 2008-11-30 | no data | 57 | 334 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Sta. Maria | 175207017 | Construction of Water Supply & Distribution System | 1 | 2500000 | 1914737.16 | 585262.84 | 1892495.56 | 1st Tranche | 565262.84 | 2457758.4 | 1892495.56 | 565262.84 | 100% | 100% | 96.58% | 98.31% | 100% | 2007-06-19 | 2007-08-03 | 2007-10-17 | 2008-03-30 | no data | 165 | 359 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Sta. Maria | 175207017 | Imrpovement of Farm to Market Road | 1 | 1340122.5 | 1107838.37 | 232284.13 | 997055 |  | 388969.13 | 1386024.13 | 997055 | 388969.13 | 100% | 100% | 167.5% | 103.4% | 100% | 2009-01-07 | 2009-01-21 | 2009-03-06 | 2009-05-31 | n/a | 86 | 368 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Wasig | 175207019 | Construction of Day Care Center | 1 | 709354 | 535318.11 | 174035.89 | 512018.17 |  | 185597.89 | 697616.06 | 512018.17 | 185597.89 | 100% | 100% | 106.6% | 98.35% | 100% | 2008-04-28 | 2008-06-11 | 2008-08-04 | 2008-09-27 | n/a | 54 | 105 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Waygan | 175207021 | Construction of Water Supply & Distribution System | 1 | 1769999.36 | 1353110 | 416889.36 | 1353110 | 1st Tranche | 432893.34 | 1786003.34 | 1353110 | 432893.34 | 100% | 100% | 103.8% | 100.9% | 100% | 2007-06-19 | 2007-08-03 | 2007-12-03 | 2008-05-31 | no data | 180 | 150 |  | 1 | LUZON
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Waygan | 175207021 | Construction of 1 Unit 2-Classroom Elementary School Building | 1 | 749996 | 543251.65 | 206744.35 | 488929.52 |  | 207836.35 | 696765.87 | 488929.52 | 207836.35 | 100% | 100% | 100.5% | 92.9% | 100% | 2009-01-07 | 2009-01-21 | 2009-03-11 | 2009-05-31 | n/a | 81 | 226 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Bonlao | 175901001 | Spring Development | 1 | 1406720 | 959100 | 447620 | 959100 |  | 517676.75 | 1476776.75 | 959100 | 517676.75 | 100% | 100% | 115.7% | 105% | 100% | 2007-08-08 | 2007-08-08 | 2007-10-22 | 2008-02-28 | no data | 129 | 308 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Calagonsao | 175901002 | Upgrading of Water Supply Syst.Level II | 1 | 658123.23 | 432239.23 | 225884 | 432239.23 |  | 214034.18 | 646273.41 | 432239.23 | 214034.18 | 100% | 100% | 94.75% | 98.2% | 100% | 2006-06-22 | 2006-08-03 | 2006-10-09 | 2007-03-15 | no data | 157 | 230 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Calagonsao | 175901002 | Construction of 1unit-3CL Elem. Sch. Bldg. | 1 | 1942600 | 1255076.92 | 687523.08 | 1255076.92 |  | 700408.36 | 1955485.28 | 1255076.92 | 700408.36 | 100% | 100% | 101.9% | 100.7% | 100% | 2007-08-08 | 2007-08-08 | 2007-11-05 | 2008-03-30 | no data | 146 | 216 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Camili | 175901003 | Upgrading of Water Supply System Level II | 1 | 707199.11 | 400571.54 | 306627.57 | 400571.54 |  | 316364.42 | 716935.96 | 400571.54 | 316364.42 | 100% | 100% | 103.2% | 101.4% | 100% | 2006-06-22 | 2006-09-06 | 2006-10-09 | 2007-03-15 | no data | 157 | 95 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Comod-om | 175901004 | Construction of Day Care Center | 1 | 571889 | 439914.62 | 131974.38 | 439914.62 |  | 203084.38 | 642999 | 439914.62 | 203084.38 | 100% | 100% | 153.9% | 112.4% | 100% | 2006-06-22 | 2006-08-03 | 2006-09-25 | 2007-03-15 | no data | 171 | 103 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Comod-om | 175901004 | Construction of 1unit-2CL Elem. Sch. Bldg. | 1 | 1205500 | 747653.85 | 457846.15 | 747653.85 |  | 457346.15 | 1205000 | 747653.85 | 457346.15 | 100% | 100% | 99.89% | 99.96% | 100% | 2007-08-08 | 2007-08-08 | 2007-10-22 | 2008-05-31 | no data | 222 | 111 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Gui-ob | 175901010 | Upgrading of farm to Market Road | 1 | 946620.92 | 782080.92 | 164540 | 782080.92 |  | 410359.28 | 1192440.2 | 782080.92 | 410359.28 | 100% | 100% | 249.4% | 126% | 100% | 2008-06-03 | 2008-06-10 | 2008-07-14 | 2008-11-30 | n/a | 139 | 265 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Lawan | 175901011 | Spring Development Level II | 1 | 1028719.1 | 791323.08 | 237396.02 | 791323.08 |  | 299548.72 | 1090871.8 | 791323.08 | 299548.72 | 100% | 100% | 126.2% | 106% | 100% | 2006-06-22 | 2006-08-03 | 2006-10-16 | 2007-03-15 | no data | 150 | 122 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Madalag | 175901005 | Slope Protection | 1 | 727733.33 | 466460.52 | 261272.81 | 466460.52 |  | 308848.63 | 775309.15 | 466460.52 | 308848.63 | 100% | 100% | 118.2% | 106.5% | 100% | 2007-08-08 | 2007-08-08 | 2007-10-15 | 2008-01-30 | no data | 107 | 195 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | San Isidro | 175901007 | Upgrading of Water Supply System | 1 | 700001 | 416923.85 | 283077.15 | 416923.85 |  | 290762.16 | 707686.01 | 416923.85 | 290762.16 | 100% | 100% | 102.7% | 101.1% | 100% | 2006-06-22 | 2006-08-03 | 2006-10-09 | 2007-03-15 | no data | 157 | 220 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | San Isidro | 175901007 | Construction of Day Care Center | 1 | 606815.12 | 517588.47 | 89226.65 | 517588.47 |  | 244618.19 | 762206.66 | 517588.47 | 244618.19 | 100% | 100% | 274.2% | 125.6% | 100% | 2008-06-03 | 2008-06-10 | 2008-08-11 | 2008-11-30 | n/a | 111 | 67 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | San Roque | 175901012 | Spring Development Level II | 1 | 1454736 | 1119027.69 | 335708.31 | 1119027.69 |  | 461625.23 | 1580652.92 | 1119027.69 | 461625.23 | 100% | 100% | 137.5% | 108.7% | 100% | 2006-06-22 | 2006-08-04 | 2006-10-09 | 2007-03-15 | no data | 157 | 213 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Tugdan | 175901008 | Construction of Water Supply & System Level II | 1 | 2592050.61 | 2300330.61 | 291720 | 2289028.15 |  | 967810.28 | 3256838.43 | 2289028.15 | 967810.28 | 100% | 100% | 331.8% | 125.6% | 100% | 2008-06-03 | 2008-06-10 | 2008-09-15 | 2008-12-31 | n/a | 107 | 464 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Cambajao | 175903002 | Improvement of FMR with Stillway | 1 | 1500000 | 1080165.86 | 419834.14 | 1080165.86 |  | 418485.34 | 1498651.2 | 1080165.86 | 418485.34 | 100% | 100% | 99.68% | 99.91% | 100% | 2008-07-11 | 2008-07-11 | 2008-10-27 | 2008-12-31 | n/a | 65 | 357 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Cambalo | 175903003 | Upgrading of FMR | 1 | 1969911 | 1176123 | 793788 | 1176123 |  | 817522.07 | 1993645.07 | 1176123 | 817522.07 | 100% | 100% | 103% | 101.2% | 100% | 2006-06-28 | 2006-08-01 | 2006-09-11 | 2007-03-31 | no data | 201 | 174 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Cambalo | 175903003 | Upgrading of farm to Market Road | 1 | 1682550 | 1212779 | 469771 | 1212779 |  | 476208 | 1688987 | 1212779 | 476208 | 100% | 100% | 101.4% | 100.4% | 100% | 2007-07-19 | 2007-07-19 | 2007-11-07 | 2008-06-30 | no data | 236 | 110 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Cambijang - C2 | 175903004 | Upgrading of Water Supply System | 2 | 1392273 | 953898 | 438375 | 953898 |  | 642578.79 | 1596476.79 | 953898 | 642578.79 | 100% | 100% | 146.6% | 114.7% | 100% | 2006-06-28 | 2006-08-01 | 2006-09-14 | 2008-04-28 | no data | 592 | 628 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Poblacion | 175903012 | Upgrading of Water Supply System | 2 | 1392273 | 953898 | 438375 | 953898 |  | 642578.79 | 1596476.79 | 953898 | 642578.79 | 100% | 100% | 146.6% | 114.7% | 100% | 2006-06-28 | 2006-08-01 | 2006-09-14 | 2008-04-28 | no data | 592 | 628 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Cantagda | 175903005 | Construction of Barangay Health Station | 1 | 777500 | 526460 | 251040 | 526460 |  | 257562.5 | 784022.5 | 526460 | 257562.5 | 100% | 100% | 102.6% | 100.8% | 100% | 2007-07-19 | 2007-07-19 | 2007-11-05 | 2008-03-30 | no data | 146 | 291 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Gutivan | 175903007 | Upgrading of farm to Market Road | 1 | 1660700 | 1212015 | 448685 | 1212015 |  | 470939.38 | 1682954.38 | 1212015 | 470939.38 | 100% | 100% | 105% | 101.3% | 100% | 2007-07-19 | 2007-07-19 | 2007-10-26 | 2008-03-30 | no data | 156 | 150 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Lico | 175903008 | Construction of Water Supply System | 1 | 1300000 | 897304.62 | 402695.38 | 807574.15 |  | 400414.3 | 1207988.45 | 807574.15 | 400414.3 | 100% | 100% | 99.43% | 92.92% | 100% | 2008-07-11 | 2008-07-11 | 2008-10-27 | 2009-01-31 | n/a | 96 | 113 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Lubang Este | 175903009 | Construction of River Flood Control | 1 | 890000 | 621778.46 | 268221.54 | 621778.46 |  | 270225.53 | 892003.99 | 621778.46 | 270225.53 | 100% | 100% | 100.7% | 100.2% | 100% | 2008-07-11 | 2008-07-11 | 2008-10-20 | 2008-12-31 | n/a | 72 | 50 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Lumbang Weste | 175903010 | Construction of Health Station | 1 | 1290000 | 916467.69 | 373532.31 | 916467.69 |  | 396596.91 | 1313064.6 | 916467.69 | 396596.91 | 100% | 100% | 106.2% | 101.8% | 100% | 2008-07-11 | 2008-07-11 | 2008-09-22 | 2008-11-30 | n/a | 69 | 289 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Lumbang Weste | 175903010 | Const. of 40 lm x 1.5 m Hanging Bridge | 1 | 1718593 | 1177387 | 541206 | 1177387 |  | 655932.05 | 1833319.05 | 1177387 | 655932.05 | 100% | 100% | 121.2% | 106.7% | 100% | 2006-06-28 | 2006-08-01 | 2006-09-18 | 2007-03-31 | no data | 194 | 252 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Marigondon | 175903011 | Upgrading of FMR | 1 | 1310408 | 892592 | 417816 | 892592 |  | 431832 | 1324424 | 892592 | 431832 | 100% | 100% | 103.4% | 101.1% | 100% | 2006-06-28 | 2006-08-01 | 2006-09-12 | 2007-03-31 | no data | 200 | 270 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Marigondon | 175903011 | Construction of 1 Unit, 2 Classroom School Building | 1 | 1440000.1 | 684283.47 | 755716.63 | 684283.47 |  | 643399.77 | 1327683.24 | 684283.47 | 643399.77 | 100% | 100% | 85.14% | 92.2% | 100% | 2008-07-11 | 2008-07-11 | 2008-10-29 | 2009-06-30 | n/a | 244 | 338 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Taguilos | 175903014 | Upgrading of farm to Market Road | 1 | 1716000 | 1248746 | 467254 | 1118631.07 |  | 498214 | 1616845.07 | 1118631.07 | 498214 | 100% | 100% | 106.6% | 94.22% | 100% | 2007-07-19 | 2007-07-19 | 2007-11-02 | 2008-01-23 | no data | 82 | 269 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Agtiwa | 175913001 | Const. of 2-CL School Building | 1 | 1219967.9 | 860844.54 | 359123.36 | 860844.54 |  | 379176.36 | 1240020.9 | 860844.54 | 379176.36 | 100% | 100% | 105.6% | 101.6% | 100% | 2006-06-29 | 2006-08-02 | 2006-09-18 | 2007-01-31 | 2007-02-07 | 135 | 221 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Azagra | 175913002 | Upgrading/Improvement of Existing Water Supply System | 1 | 1374900 | 936519.23 | 438380.77 | 842867.31 |  | 329545.77 | 1172413.08 | 842867.31 | 329545.77 | 100% | 100% | 75.17% | 85.27% | 100% | 2007-07-31 | 2007-07-31 | 2007-10-19 | 2008-09-30 | n/a | 347 | 400 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Campalingo | 175913003 | Const. of Health Station | 1 | 652877.55 | 452601.96 | 200275.59 | 452601.96 |  | 260365.3 | 712967.26 | 452601.96 | 260365.3 | 100% | 100% | 130% | 109.2% | 100% | 2006-06-29 | 2006-08-02 | 2006-09-18 | 2007-01-31 | 2007-02-22 | 135 | 348 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Canjalon | 175913004 | Upgrading/Improvement of Existing Water Supply System | 1 | 1236300 | 775359.38 | 460940.62 | 775359.38 |  | 460488.37 | 1235847.75 | 775359.38 | 460488.37 | 100% | 100% | 99.9% | 99.96% | 100% | 2007-07-31 | 2007-07-31 | 2007-10-22 | 2008-09-30 | n/a | 344 | 310 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | España | 175913005 | Const. of 2-CL School Building | 1 | 1212427.91 | 864544.16 | 347883.75 | 864544.16 |  | 356056.87 | 1220601.03 | 864544.16 | 356056.87 | 100% | 100% | 102.3% | 100.7% | 100% | 2006-06-29 | 2006-08-02 | 2006-09-25 | 2007-01-31 | 2007-03-31 | 128 | 438 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Mabini | 175913006 | Const. of 03-CL Building | 1 | 1900972 | 1366509.23 | 534462.77 | 1366509.23 |  | 547697.77 | 1914207 | 1366509.23 | 547697.77 | 100% | 100% | 102.5% | 100.7% | 100% | 2006-06-29 | 2006-08-02 | 2006-09-25 | 2007-01-31 | 2007-02-07 | 128 | 215 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Mabulo | 175913007 | Construction of 1 Unit 3-Classroom Elementary School Bldg | 1 | 1931400 | 1328846.15 | 602553.85 | 1328846.15 |  | 614113.85 | 1942960 | 1328846.15 | 614113.85 | 100% | 100% | 101.9% | 100.6% | 100% | 2007-07-31 | 2007-07-31 | 2007-11-12 | 2008-11-30 | n/a | 384 | 353 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Otod | 175913008 | Construction of 1 Unit 2-Classroom Elementary School Bldg | 1 | 1212000 | 559275.24 | 652724.76 | 559275.24 |  | 628810.23 | 1188085.47 | 559275.24 | 628810.23 | 100% | 100% | 96.34% | 98.03% | 100% | 2007-07-31 | 2007-07-31 | 2007-11-12 | 2008-04-30 | no data | 170 | 395 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Panangcalan | 175913009 | Construction of 1 Unit 2 Storey 4 Classroom Building | 1 | 4285000 | 2787208.46 | 1497791.54 | 2508487.62 |  | 1492158.98 | 4000646.6 | 2508487.62 | 1492158.98 | 100% | 100% | 99.62% | 93.36% | 100% | 2008-07-14 | 2008-07-14 | 2009-03-16 | 2009-05-31 | n/a | 76 | 211 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Taclobo | 175913012 | Upgrading/Improvement of Existing Water Supply System | 1 | 1590000 | 812791.54 | 777208.46 | 812791.53 |  | 788998.46 | 1601789.99 | 812791.53 | 788998.46 | 100% | 100% | 101.5% | 100.7% | 100% | 2008-07-14 | 2008-07-14 | 2008-09-25 | 2008-12-31 | n/a | 97 | 454 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Busay | 175914001 | Clearing of 2,850m and Concreting of 150m Road | 1 | 260440 | 131459 | 128981 | 131459 | 3rd Tranche | 138356.9 | 269815.9 | 131459 | 138356.9 | 100% | 100% | 107.3% | 103.6% | 100% | 2003-08-11 | 2003-12-18 | 2004-03-30 | 2004-12-15 | 2004-12-19 | 260 | 286 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Busay | 175914001 | Rehab. of Water Supply Syst. | 1 | 991904 | 593765 | 398139 | 593765 | 2nd Tranche | 403249 | 997014 | 593765 | 403249 | 100% | 100% | 101.3% | 100.5% | 100% | 2006-05-24 | 2006-05-24 | 2006-07-10 | 2006-12-15 | no data | 158 | 315 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Combot | 175914002 | Rehabilitation of Combot Water Supply System | 1 | 638888.4 | 443730 | 195158.4 | 443730 | 3rd Tranche | 181140.4 | 624870.4 | 443730 | 181140.4 | 100% | 100% | 92.82% | 97.81% | 100% | 2005-05-05 | 2005-06-14 | 2005-09-27 | 2006-02-24 | 2006-02-16 | 150 | 157 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Lanas | 175914003 | Spring Development Water Supply System Level II | 1 | 510264 | 300000 | 210264 | 300000 | 3rd Tranche | 546020 | 846020 | 300000 | 546020 | 100% | 100% | 259.7% | 165.8% | 100% | 2003-08-11 | 2003-12-18 | 2004-03-30 | 2004-12-15 | 2004-12-19 | 260 | 359 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Lanas | 175914003 | Const. of 4 Units Box Culvert with 15m Approach Slab on Both Sides | 1 | 731101.2 | 401270 | 329831.2 | 401270 | 3rd Tranche | 351063.7 | 752333.7 | 401270 | 351063.7 | 100% | 100% | 106.4% | 102.9% | 100% | 2005-05-05 | 2005-06-14 | 2005-09-15 | 2006-01-04 | 2006-01-06 | 111 | 372 |  | 1
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Lanas | 175914003 | 500 lm concreting of critical slope | 1 | 841376 | 487143 | 354233 | 487143 | 3rd Tranche | 268933 | 756076 | 487143 | 268933 | 100% | 100% | 75.92% | 89.86% | 100% | 2006-05-24 | 2006-05-24 | 2006-07-17 | 2006-12-15 | no data | 151 | 320 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Pinamihagan | 175914004 | Road Concreting of Critical Slope | 1 | 690875 | 408124 | 282751 | 408124 | 3rd Tranche | 285646 | 693770 | 408124 | 285646 | 100% | 100% | 101% | 100.4% | 100% | 2003-08-11 | 2003-12-18 | 2004-04-13 | 2004-12-15 | 2004-12-19 | 246 | 244 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Pinamihagan | 175914004 | Construction of 2-Classroom School Building | 1 | 1014208 | 655000 | 359208 | 655000 | 3rd Tranche | 340400 | 995400 | 655000 | 340400 | 100% | 100% | 94.76% | 98.15% | 100% | 2005-05-05 | 2005-06-14 | 2005-09-16 | 2006-01-04 | 2006-01-06 | 110 | 229 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Pinamihagan | 175914004 | 646 lm concreting of critical slope | 1 | 783100 | 419092 | 364008 | 419092 | 3rd Tranche | 203813.22 | 622905.22 | 419092 | 203813.22 | 100% | 100% | 55.99% | 79.54% | 100% | 2006-05-24 | 2006-05-24 | 2006-07-17 | 2007-02-15 | no data | 213 | 236 |  | 1 | LUZON
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Poblacion | 175914005 | Road Concreting of Poblacion-Lindero Road | 1 | 945000 | 660416.73 | 284583.27 | 660416.73 | 3rd Tranche | 288682.5 | 949099.23 | 660416.73 | 288682.5 | 100% | 100% | 101.4% | 100.4% | 100% | 2003-06-12 | 2003-12-18 | 2004-03-30 | 2004-12-15 | 2004-12-19 | 260 | 484 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Baluno | 097225001 | Rehabilitation of Farm to Market Road | 1 | 2254621.18 | 1412000 | 842621.18 | 1412000 | 3rd Tranche | 623938.12 | 2035938.12 | 1412000 | 623938.12 | 100% | 100% | 74.05% | 90.3% | 100% | 2003-10-24 | 2003-12-11 | 2004-04-01 | 2005-10-03 | 2005-11-29 | 550 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Banuangan | 097225002 | Rehabilitation of Farm to Market Road | 1 | 2575243.84 | 1795000 | 780243.84 | 1615500 | 3rd Tranche | 420775.17 | 2036275.17 | 1615500 | 420775.17 | 100% | 100% | 53.93% | 79.07% | 100% | 2003-10-24 | 2003-12-11 | 2004-07-02 | 2005-08-31 | 2005-12-23 | 425 | 180 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Bunawan | 097225003 | Day Care Center | 1 | 400000 | 200885 | 199115 | 200885 | 3rd Tranche | 143641.5 | 344526.5 | 200885 | 143641.5 | 100% | 100% | 72.14% | 86.13% | 100% | 2006-05-31 | 2006-07-05 | 2006-10-25 | 2007-02-20 | no data | 118 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Dilucot | 097225004 | Rehabilitation of Farm to Market Road | 1 | 1887150 | 1056880 | 830270 | 1056880 | 3rd Tranche | 733485.56 | 1790365.56 | 1056880 | 733485.56 | 100% | 100% | 88.34% | 94.87% | 100% | 2003-10-24 | 2003-12-11 | 2004-06-01 | 2004-12-31 | 2005-11-29 | 213 | 80 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Dilucot | 097225004 | Hanging Bridge | 1 | 1030000 | 721000 | 309000 | 721000 | 3rd Tranche | 255000 | 976000 | 721000 | 255000 | 100% | 100% | 82.52% | 94.76% | 100% | 2006-05-31 | 2006-07-05 | 2005-11-27 | 2006-11-29 | no data | 367 | 142 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Dipopor - C2 | 097225005 | Water System Level II | 2 | 3268883 | 2279447 | 989436 | 1823557.6 | 1st Tranche | 807501.21 | 2631058.81 | 1823557.6 | 807501.21 | 100% | 100% | 81.61% | 80.49% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-15 | 2006-01-31 | 2006-02-13 | 169 | 310 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Rambon | 097225013 | Water System Level II | 2 | 3268883 | 2279447 | 989436 | 1823557.6 | 1st Tranche | 807501.21 | 2631058.81 | 1823557.6 | 807501.21 | 100% | 100% | 81.61% | 80.49% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-15 | 2006-01-31 | 2006-02-13 | 169 | 310 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Guisapong | 097225006 | Water System Level II | 1 | 641347 | 416627 | 224720 | 374964.3 | 3rd Tranche | 173393 | 548357.3 | 374964.3 | 173393 | 100% | 100% | 77.16% | 85.5% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-15 | 2005-12-15 | 2005-12-19 | 122 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Limbonga | 097225007 | Water System Level II | 1 | 1152104 | 710790 | 441314 | 639711 | 3rd Tranche | 402685.75 | 1042396.75 | 639711 | 402685.75 | 100% | 100% | 91.25% | 90.48% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-15 | 2005-12-15 | 2005-12-19 | 122 | 165 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Lomogom | 097225008 | Day Care Center | 1 | 511251 | 297641 | 213610 | 297641 | 3rd Tranche | 190424.5 | 488065.5 | 297641 | 190424.5 | 100% | 100% | 89.15% | 95.46% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-31 | 2005-11-25 | 2005-11-29 | 86 | 63 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Mauswagon | 097225009 | Corn Mill Project | 1 | 1050000 | 735000 | 315000 | 735000 | 3rd Tranche | 283500 | 1018500 | 735000 | 283500 | 100% | 100% | 90% | 97% | 100% | 2006-05-31 | 2006-07-05 | 2006-10-25 | 2007-03-15 | no data | 141 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Miampic | 097225010 | School Building | 1 | 930000 | 651000 | 279000 | 651000 | 3rd Tranche | 227560 | 878560 | 651000 | 227560 | 100% | 100% | 81.56% | 94.47% | 100% | 2006-05-31 | 2006-07-05 | 2006-10-31 | 2007-03-20 | no data | 140 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Poblacion | 097225011 | Construction Slope Protection of Farm to Market Road | 1 | 549882 | 359483 | 190399 | 323534.54 | 3rd Tranche | 210121.96 | 533656.5 | 323534.54 | 210121.96 | 100% | 100% | 110.4% | 97.05% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-11 | 2006-01-31 | 2006-02-14 | 173 | 431 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Poblacion | 097225011 | School Building | 1 | 870000 | 609000 | 261000 | 609000 | 3rd Tranche | 244360 | 853360 | 609000 | 244360 | 100% | 100% | 93.62% | 98.09% | 100% | 2006-05-31 | 2006-07-05 | 2006-10-25 | 2007-03-15 | no data | 141 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | San Pedro | 097225014 | 4 Class Room School Building | 1 | 1204311.9 | 836120 | 368191.9 | 836120 | 3rd Tranche | 408702.83 | 1244822.83 | 836120 | 408702.83 | 100% | 100% | 111% | 103.4% | 100% | 2003-10-24 | 2003-12-11 | 2004-04-15 | 2004-12-18 | 2004-12-23 | 247 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | San Pedro | 097225014 | Health Station | 1 | 370632 | 215465 | 155167 | 172372 | 3rd Tranche | 143272.28 | 315644.28 | 172372 | 143272.28 | 100% | 100% | 92.33% | 85.16% | 100% | 2005-04-21 | 2005-06-09 | 2005-09-10 | 2006-02-28 | 2006-03-12 | 171 | 42 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Sarawagan | 097225015 | Water System Level II | 1 | 1344670 | 820547 | 524123 | 820547 | 3rd Tranche | 418461.65 | 1239008.65 | 820547 | 418461.65 | 100% | 100% | 79.84% | 92.14% | 100% | 2005-04-21 | 2005-06-09 | 2005-08-15 | 2005-12-15 | 2005-12-19 | 122 | 165 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Sianan - C2 | 097225016 | Hanging Bridge | 2 | 1600000 | 1120000 | 480000 | 1120000 | 3rd Tranche | 338000 | 1458000 | 1120000 | 338000 | 100% | 100% | 70.42% | 91.12% | 100% | 2006-05-31 | 2006-07-05 | 2006-11-13 | 2007-07-22 | no data | 251 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Godod | 097225 | Sioran | 097225017 | Rehab FMR | 1 | 1518736 | 1063115 | 455621 | 1063115 | 3rd Tranche | 437707 | 1500822 | 1063115 | 437707 | 100% | 100% | 96.07% | 98.82% | 100% | 2006-05-31 | 2006-07-05 | 2006-10-05 | 2007-01-25 | no data | 112 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bacong | 097223012 | Barangay Health Station | 1 | 270000 | 147378.77 | 122621.23 | 147378.77 | 3rd Tranche | 122600 | 269978.77 | 147378.77 | 122600 | 100% | 100% | 99.98% | 99.99% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-26 | 2005-03-15 | 2005-04-12 | 354 | 85 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bacong | 097223012 | Road Rehabilitation | 1 | 4254310 | 2655130 | 1599180 | 2655130 | 2nd Tranche | 1634253.5 | 4289383.5 | 2655130 | 1634253.5 | 100% | 100% | 102.2% | 100.8% | 100% | 2005-03-31 | 2005-05-12 | 2005-07-28 | 2009-04-30 | for schedule | 1372 | 115 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bacong | 097223012 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 472835.1 | 3rd Tranche | 72548.21 | 545383.31 | 472835.1 | 72548.21 | 100% | 100% | 63.69% | 90.98% | 100% | n/a | n/a | 2009-04-22 | 2009-06-25 | 2009-06-29 | 64 | 42 | a.) No need to request contingency b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bagong Silang | 097223013 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 743044.89 | 3rd Tranche | 151101.81 | 894146.7 | 743044.89 | 151101.81 | 100% | 100% | 84.49% | 94.99% | 100% | n/a | n/a | 2009-04-04 | 2009-06-29 | 2009-07-29 | 86 | 249 | a.) No need to request contingency b. Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Banganon | 097223001 | Day Care Center | 1 | 268000 | 184800 | 83200 | 184800 | 3rd Tranche | 69385 | 254185 | 184800 | 69385 | 100% | 100% | 83.4% | 94.85% | 100% | 2003-10-25 | 2003-12-15 | 2004-04-05 | 2005-03-15 | 2005-03-23 | 344 | 184 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Banganon | 097223001 | Construction of Multi Purpose Bldg | 1 | 791301.82 | 638954.46 | 152347.36 | 585220.39 | 3rd Tranche | 132665.9 | 717886.29 | 585220.39 | 132665.9 | 100% | 100% | 87.08% | 90.72% | 100% | n/a | n/a | 2009-04-15 | 2009-06-19 | 2009-07-30 | 65 | 269 | a.) No need to request contingency b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bayanihan | 097223014 | 4 km. Road Rehabilitation | 1 | 4120000 | 2884000 | 1236000 | 2884000 | 3rd Tranche | 1170600.75 | 4054600.75 | 2884000 | 1170600.75 | 100% | 100% | 94.71% | 98.41% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-22 | 2005-03-15 | 2005-03-15 | 358 | 175 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Bayanihan | 097223014 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 469114.76 | 3rd Tranche | 106778.79 | 575893.55 | 469114.76 | 106778.79 | 100% | 100% | 93.75% | 96.07% | 100% | n/a | n/a | 2009-03-29 | 2009-06-11 | 2009-07-25 | 74 | 30 | a.) No need to request contigency b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Buenavista | 097223015 | Day Care Center | 1 | 264000 | 184800 | 79200 | 184800 | 3rd Tranche | 80890 | 265690 | 184800 | 80890 | 100% | 100% | 102.1% | 100.6% | 100% | 2003-10-25 | 2003-12-15 | 2004-05-26 | 2005-03-15 | 2005-06-08 | 293 | 184 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Buenavista | 097223015 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 739453.7 | 3rd Tranche | 146882.2 | 886335.9 | 739453.7 | 146882.2 | 100% | 100% | 82.13% | 94.16% | 100% | n/a | n/a | 2009-04-04 | 2009-06-24 | 2009-07-29 | 81 | 50 | a.) No need to request contigency b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Canupong | 097223008 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 473535.69 | 3rd Tranche | 101019.51 | 574555.2 | 473535.69 | 101019.51 | 100% | 100% | 88.69% | 95.84% | 100% | n/a | n/a | 2009-05-01 | 2009-06-20 | 2009-07-20 | 50 | 50 | a.) No need to request contigency b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Canuto Enerio |  | Rehabilitation of Water System Level-II | 1 | 284660.36 | 263563.07 | 21097.29 | 240458.51 | 3rd Tranche | 16597.29 | 257055.8 | 240458.51 | 16597.29 | 100% | 100% | 78.67% | 90.3% | 100% | n/a | n/a | 2009-03-28 | 2009-06-21 | 2009-07-11 | 85 | 106 | a.) No need to request contingency b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Canuto Enerio |  | Water System Level II | 1 | 956513 | 669558 | 286955 | 669558 | 3rd Tranche | 216242.1 | 885800.1 | 669558 | 216242.1 | 100% | 100% | 75.36% | 92.61% | 100% | 2005-03-31 | 2005-05-12 | 2005-08-01 | 2006-08-20 | no data | 384 | 257 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Cocob | 097223002 | Water System Level II | 1 | 1816458 | 1271519 | 544939 | 1271519 | 3rd Tranche | 505814.15 | 1777333.15 | 1271519 | 505814.15 | 100% | 100% | 92.82% | 97.85% | 100% | 2005-03-31 | 2005-05-12 | 2005-08-02 | 2006-08-02 | 2006-08-10 | 365 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Cocob | 097223002 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 740464.47 | 3rd Tranche | 146869.2 | 887333.67 | 740464.47 | 146869.2 | 100% | 100% | 82.12% | 94.27% | 100% | n/a | n/a | 2009-04-04 | 2009-06-24 | 2009-07-28 | 81 | 65 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Datagan | 097223016 | 3 CR elementary School | 1 | 990282 | 650858 | 339424 | 650858 | 3rd Tranche | 265999 | 916857 | 650858 | 265999 | 100% | 100% | 78.37% | 92.59% | 100% | 2005-03-31 | 2005-05-12 | 2005-07-26 | 2006-08-20 | 2006-08-30 | 390 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Datagan | 097223016 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 472860.24 | 3rd Tranche | 98588.23 | 571448.47 | 472860.24 | 98588.23 | 100% | 100% | 86.56% | 95.32% | 100% | n/a | n/a | 2008-03-27 | 2009-06-18 | 2009-07-30 | 448 | 100 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Immaculada Concepcion | 097223032 | Barangay Health Station | 1 | 312000 | 218400 | 93600 | 218400 | 3rd Tranche | 95618.5 | 314018.5 | 218400 | 95618.5 | 100% | 100% | 102.2% | 100.6% | 100% | 2003-10-25 | 2003-12-15 | 2004-04-05 | 2004-12-13 | 2005-03-22 | 252 | 114 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Immaculada Concepcion | 097223032 | Const of Brgy I. Conception Multi-Purpose Pavement | 1 | 271895 | 180477 | 91418 | 180477 | 3rd Tranche | 102449 | 282926 | 180477 | 102449 | 100% | 100% | 112.1% | 104.1% | 100% | 2006-06-21 | 2006-07-12 | 2006-11-03 | 2007-10-01 | no data | 332 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Immaculada Concepcion | 097223032 | Construction of Multi Purpose Center | 1 | 791301.82 | 638954.46 | 152347.36 | 622738.49 | 3rd Tranche | 132661.01 | 755399.5 | 622738.49 | 132661.01 | 100% | 100% | 87.08% | 95.46% | 100% | n/a | n/a | 2009-04-04 | 2009-06-20 | 2009-07-25 | 77 | 110 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | La Libertad | 097223004 | Barangay Health Station | 1 | 351000 | 245700 | 105300 | 245700 | 3rd Tranche | 87220 | 332920 | 245700 | 87220 | 100% | 100% | 82.83% | 94.85% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-18 | 2004-12-13 | 2004-12-14 | 270 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | La libertad | 097223004 | Const of Brgy La Libertad 1 unit 4 CL Elem School | 1 | 1758807 | 1231165 | 527642 | 1231165 | 3rd Tranche | 120608.75 | 1351773.75 | 1231165 | 120608.75 | 100% | 100% | 22.86% | 76.86% | 100% | 2006-06-21 | 2006-07-12 | 2007-12-26 | 2007-11-01 | no data | -55 | 130 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | La Libertad | 097223004 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 470906.74 | 3rd Tranche | 101019.51 | 571926.25 | 470906.74 | 101019.51 | 100% | 100% | 88.69% | 95.4% | 100% | n/a | n/a | 2009-03-19 | 2009-04-30 | 2009-05-26 | 42 | 100 | a.) No need to request contigency charged to grant b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Loay | 097223018 | Water system (Level-II) | 1 | 1397936.86 | 978555.81 | 419381.05 | 978555.805 | 3rd Tranche | 327860.13 | 1306415.935 | 978555.805 | 327860.13 | 100% | 100% | 78.18% | 93.45% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-23 | 2005-03-15 | 2005-03-17 | 357 | 180 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Loay | 097223018 | Construction of Day Care Center | 1 | 550999.32 | 446309.48 | 104689.84 | 417787.19 | 3rd Tranche | 95352.28 | 513139.47 | 417787.19 | 95352.28 | 100% | 100% | 91.08% | 93.13% | 100% | n/a | n/a | 2009-03-14 | 2009-04-30 | 2009-05-21 | 47 | 42 | a.) No need to request contingency b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Lower Lux | 097223033 | Water System Level II | 1 | 872250 | 610575 | 261675 | 610575 | 3rd Tranche | 272935.4 | 883510.4 | 610575 | 272935.4 | 100% | 100% | 104.3% | 101.3% | 100% | 2005-03-31 | 2005-05-12 | 2005-08-15 | 2006-10-31 | no data | 442 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Lower Lux | 097223033 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 680200.6 | 2nd Tranche | 136022.03 | 816222.63 | 680200.6 | 136022.03 | 100% | 100% | 76.06% | 86.71% | 100% | n/a | n/a | 2009-04-21 | 2009-06-25 | 2009-07-31 | 65 | 58 | a.) No need to request 3rd tranch b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Lux | 097223005 | Water rehab (Level-II) | 1 | 410000 | 286000 | 124000 | 286000 | 3rd Tranche | 123537.21 | 409537.21 | 286000 | 123537.21 | 100% | 100% | 99.63% | 99.89% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-22 | 2005-01-31 | 2005-02-04 | 315 | 136 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Lux | 097223005 | Const of Brgy Lux Health Station | 1 | 463861.25 | 292986 | 170875.25 | 292986 | 3rd Tranche | 50998 | 343984 | 292986 | 50998 | 100% | 100% | 29.85% | 74.16% | 100% | 2006-06-21 | 2006-07-12 | 2006-11-01 | 2007-04-30 | no data | 180 | 95 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Lux | 097223005 | Construction of Multi Purpose Center | 1 | 791301.82 | 638954.46 | 152347.36 | 623954.47 | 3rd Tranche | 151740.7 | 775695.17 | 623954.47 | 151740.7 | 100% | 100% | 99.6% | 98.03% | 100% | n/a | n/a | 2009-04-04 | 2009-06-22 | 2009-07-24 | 79 | 199 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Malian | 097223019 | Const of 1 unit 2CL Elem School Bldg | 1 | 917828 | 642480 | 275348 | 616892.4 | 3rd Tranche | 97632 | 714524.4 | 616892.4 | 97632 | 100% | 100% | 35.46% | 77.85% | 100% | 2006-06-21 | 2006-07-12 | 2006-10-18 | 2007-05-02 | no data | 196 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Malian | 097223019 | Constrcuction of Barangay Health Station | 1 | 642079.07 | 520084.05 | 121995.02 | 501284.05 | 3rd Tranche | 126412.57 | 627696.62 | 501284.05 | 126412.57 | 100% | 100% | 103.6% | 97.76% | 100% | n/a | n/a | 2009-04-04 | 2009-06-29 | 2009-07-27 | 86 | 192 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Mamawan | 097223009 | 2 Class Room School Building | 1 | 527339.62 | 369324.86 | 158014.76 | 369324.86 | 3rd Tranche | 159093.84 | 528418.7 | 369324.86 | 159093.84 | 100% | 100% | 100.7% | 100.2% | 100% | 2003-10-25 | 2003-12-15 | 2004-04-12 | 2005-03-15 | 2005-07-20 | 337 | 231 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Mamawan | 097223009 | Const of Brgy Manawan Health Station | 1 | 659134 | 461394 | 197740 | 461394 | 3rd Tranche | 38961 | 500355 | 461394 | 38961 | 100% | 100% | 19.7% | 75.91% | 100% | 2006-06-21 | 2006-07-12 | 2006-10-20 | 2007-04-18 | no data | 180 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Map | 097223020 | Const of Brgy Map MPP | 1 | 285025 | 192517 | 92508 | 192517 | 3rd Tranche | 45682 | 238199 | 192517 | 45682 | 100% | 100% | 49.38% | 83.57% | 100% | 2006-06-21 | 2006-07-12 | 2007-02-09 | 2007-05-03 | no data | 83 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Map | 097223020 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 485579.74 | 3rd Tranche | 101619.99 | 587199.73 | 485579.74 | 101619.99 | 100% | 100% | 89.22% | 97.95% | 100% | n/a | n/a | 2009-04-04 | 2009-06-24 | 2009-07-31 | 81 | 55 | Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Matunoy | 097223021 | Day Care Center | 1 | 268800 | 184800 | 84000 | 184800 | 3rd Tranche | 92706 | 277506 | 184800 | 92706 | 100% | 100% | 110.4% | 103.2% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-29 | 2005-01-31 | 2005-02-04 | 308 | 122 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Matunoy | 097223021 | Construction of Multi Purpose Pavement | 1 | 245581 | 198920.61 | 46660.39 | 187181.6 | 3rd Tranche | 54400 | 241581.6 | 187181.6 | 54400 | 100% | 100% | 116.6% | 98.37% | 100% | n/a | n/a | 2009-03-27 | 2009-04-17 | 2009-04-25 | 21 | 50 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | New Dapitan | 097223022 | Const of Brgy New Dapitan Day Care Center | 1 | 457607.16 | 299963 | 157644.16 | 239970.4 | 1st Tranche | 36429 | 276399.4 | 239970.4 | 36429 | 100% | 100% | 23.11% | 60.4% | 100% | 2006-06-21 | 2006-07-12 | 2007-03-19 | 2008-05-06 | no data | 414 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | New Dapitan | 097223022 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 744077.23 | 3rd Tranche | 146872.21 | 890949.44 | 744077.23 | 146872.21 | 100% | 100% | 82.12% | 94.65% | 100% | n/a | n/a | 2009-04-28 | 2009-06-25 | 2009-07-15 | 58 | 64 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Panganuran | 097223006 | Const of Brgy Panganuran 1 unit 2 CL Elem School Building | 1 | 831412 | 652992 | 178420 | 652992 | 3rd Tranche | 181670.6 | 834662.6 | 652992 | 181670.6 | 100% | 100% | 101.8% | 100.4% | 100% | 2006-06-21 | 2006-07-12 | 2007-01-28 | 2007-10-01 | no data | 246 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Panganuran | 097223006 | Construction of 1Unit 2CL High School Building | 1 | 941290.24 | 762445.09 | 178845.15 | 736945.1 | 3rd Tranche | 137666.2 | 874611.3 | 736945.1 | 137666.2 | 100% | 100% | 76.98% | 92.92% | 100% | n/a | n/a | 2009-04-04 | 2009-06-22 | 2009-07-23 | 79 | 214 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Pitawe | 097223007 | Road Rehabilitation | 1 | 6046937 | 3932901 | 2114036 | 3932901 | 3rd Tranche | 148437.5 | 4081338.5 | 3932901 | 148437.5 | 100% | 100% | 7.022% | 67.49% | 100% | 2005-03-31 | 2005-05-12 | 2005-08-01 | 2009-10-31 | no data | 1552 | 290 | completed as built | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Pitogo | 097223023 | Const of Brgy Pitogo 1 unit 2 CL Elem School Bldg | 1 | 965195.77 | 653992 | 311203.77 | 653992 | 3rd Tranche | 142475 | 796467 | 653992 | 142475 | 100% | 100% | 45.78% | 82.52% | 100% | 2006-06-21 | 2006-07-12 | 2007-01-10 | 2008-05-05 | no data | 481 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Poblacion (Gutalac) | 097223003 | Const of Brgy Poblacion Level II Water System(PD) | 1 | 2079269 | 1418418 | 660851 | 1372957.52 | 3rd Tranche | 125956 | 1498913.52 | 1372957.52 | 125956 | 100% | 100% | 19.06% | 72.09% | 100% | 2006-06-21 | 2006-07-12 | 2007-03-19 | 2009-01-25 | no data | 678 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Salvador | 097223024 | Const of Brgy Salvador Level II Water System(PD) | 1 | 2106750.81 | 1342571 | 764179.81 | 1342571 | 3rd Tranche | 121383 | 1463954 | 1342571 | 121383 | 100% | 100% | 15.88% | 69.49% | 100% | 2006-06-21 | 2006-07-12 | 2006-12-01 | 2007-10-08 | no data | 311 | 136 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Salvador | 097223024 | Construction of Day Care Center | 1 | 550999.11 | 446309.27 | 104689.84 | 418594.31 | 3rd Tranche | 95352.28 | 513946.59 | 418594.31 | 95352.28 | 100% | 100% | 91.08% | 93.28% | 100% | n/a | n/a | 2009-03-18 | 2009-04-07 | 2009-04-17 | 20 | 50 | a.) No need to request contigency charged to grant b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Isidro | 097223025 | Construction of Level-II water system | 1 | 1009998.94 | 705002.22 | 304996.72 | 705002.22 | 3rd Tranche | 178415 | 883417.22 | 705002.22 | 178415 | 100% | 100% | 58.5% | 87.47% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-29 | 2006-01-26 | 2006-01-26 | 668 | 160 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Isidro | 097223025 | Construction of Multi Purpose Center | 1 | 731800.75 | 592758.61 | 139042.14 | 560567.61 | 3rd Tranche | 128711.69 | 689279.3 | 560567.61 | 128711.69 | 100% | 100% | 92.57% | 94.19% | 100% | n/a | n/a | 2009-04-17 | 2009-06-11 | 2009-06-24 | 55 | 211 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Juan | 097223026 | 2 Class Room High School Building | 1 | 528000 | 369600 | 158400 | 369600 | 3rd Tranche | 173430 | 543030 | 369600 | 173430 | 100% | 100% | 109.5% | 102.8% | 100% | 2003-10-25 | 2003-12-15 | 2004-04-15 | 2005-03-15 | 2005-04-12 | 334 | 203 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Juan | 097223026 | Construction of Multi Purpose Center | 1 | 791301.82 | 638954.46 | 152347.36 | 575059.04 | 2nd Tranche | 126660.92 | 701719.96 | 575059.04 | 126660.92 | 100% | 100% | 83.14% | 88.68% | 100% | n/a | n/a | 2009-05-01 | 2009-06-25 | 2009-07-05 | 55 | 242 | a.) No need to request remaining contingency b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Roque | 097223027 | Barangay Health Station | 1 | 264000 | 184800 | 79200 | 184800 | 3rd Tranche | 81070 | 265870 | 184800 | 81070 | 100% | 100% | 102.4% | 100.7% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-25 | 2005-03-15 | 2005-03-29 | 355 | 181 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Roque | 097223027 | Construction of Multi Purpose Pavement | 1 | 245581 | 198920.61 | 46660.39 | 186642.99 | 3rd Tranche | 48400 | 235042.99 | 186642.99 | 48400 | 100% | 100% | 103.7% | 95.71% | 100% | n/a | n/a | 2009-03-16 | 2009-03-31 | 2009-04-06 | 15 | 56 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Vicente | 097223028 | Const of Brgy San Vicente 1 unit 2 CL Elem School Building | 1 | 931999.58 | 647892 | 284107.58 | 644015.52 | 3rd Tranche | 103822.54 | 747838.06 | 644015.52 | 103822.54 | 100% | 100% | 36.54% | 80.24% | 100% | 2006-06-21 | 2006-07-12 | 2007-01-10 | 2009-05-12 | no data | 853 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | San Vicente | 097223028 | Construction of Multi Purpose Center | 1 | 791301.82 | 638954.46 | 152347.36 | 623954.46 | 3rd Tranche | 132665.92 | 756620.38 | 623954.46 | 132665.92 | 100% | 100% | 87.08% | 95.62% | 100% | n/a | n/a | 2009-04-05 | 2009-06-17 | 2009-07-24 | 73 | 213 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sibalic | 097223010 | Electrification | 1 | 1257050 | 879863.2 | 377186.8 | 879863.2 | 3rd Tranche | 142716.5 | 1022579.7 | 879863.2 | 142716.5 | 100% | 100% | 37.84% | 81.35% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-29 | 2005-03-15 | 2005-03-17 | 351 | 85 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sibalic | 097223010 | Const of Brgy Sibalic Day Care Center | 1 | 737383 | 516168 | 221215 | 412934.4 | 1st Tranche | 51280 | 464214.4 | 412934.4 | 51280 | 100% | 100% | 23.18% | 62.95% | 100% | 2006-06-21 | 2006-07-12 | 2007-02-14 | 2007-05-07 | no data | 82 | 80 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sibalic | 097223010 | Construction of Multi Purpose Center | 1 | 791301.82 | 638954.46 | 152347.36 | 619410.48 | 3rd Tranche | 134646.31 | 754056.79 | 619410.48 | 134646.31 | 100% | 100% | 88.38% | 95.29% | 100% | n/a | n/a | 2009-04-14 | 2009-06-18 | 2009-07-27 | 65 | 251 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sto. Niño | 097223029 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 743544.78 | 3rd Tranche | 146882.2 | 890426.98 | 743544.78 | 146882.2 | 100% | 100% | 82.13% | 94.6% | 100% | n/a | n/a | 2009-04-04 | 2009-06-21 | 2009-07-28 | 78 | 138 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Sto.Niño | 097223029 | 3 km. Road Rehabilitation | 1 | 3000000 | 2076975.14 | 923024.86 | 2076975.14 | 3rd Tranche | 853453.16 | 2930428.3 | 2076975.14 | 853453.16 | 100% | 100% | 92.46% | 97.68% | 100% | 2003-10-25 | 2003-12-15 | 2004-03-31 | 2005-01-30 | 2005-02-08 | 305 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Tipan | 097223011 | Construction of 1Unit 2CL Elem School Bldg | 1 | 941290.24 | 762445.09 | 178845.15 | 739795.33 | 3rd Tranche | 147516.09 | 887311.42 | 739795.33 | 147516.09 | 100% | 100% | 82.48% | 94.27% | 100% | n/a | n/a | 2009-04-05 | 2009-06-21 | 2009-07-14 | 77 | 78 | a.) No need to request contigency charged to grant b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Upper Gutalac | 097223031 | Const of Upper Gutalac Level II Water System(PD) | 1 | 1952835 | 1366985 | 585850 | 1366985 | 3rd Tranche | 146300 | 1513285 | 1366985 | 146300 | 100% | 100% | 24.97% | 77.49% | 100% | 2006-06-21 | 2006-07-12 | 2006-12-01 | 2007-11-07 | no data | 341 | 130 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Gutalac | 097223 | Upper Gutalac | 097223031 | Construction of Day Care Center | 1 | 599481.17 | 485579.74 | 113901.43 | 472759.51 | 3rd Tranche | 94474.51 | 567234.02 | 472759.51 | 94474.51 | 100% | 100% | 82.94% | 94.62% | 100% | n/a | n/a | 2009-03-28 | 2009-05-15 | 2009-06-19 | 48 | 40 | a.) No need to request contigency charged to grant b.) Closed Account > changes on LCC delivered & utilized are due to double entry of amortization in in-kind | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Balatakan | 097222008 | Road Rehabilitation | 1 | 4666035 | 2471542 | 2194493 | 2471542 | 3rd Tranche | 1958995 | 4430537 | 2471542 | 1958995 | 100% | 100% | 89.27% | 94.95% | 100% | 2005-03-31 | 2005-05-16 | 2005-08-16 | 2006-04-15 | 2006-05-29 | 242 | 184 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Bitoon | 097222009 | 1.8 km. Farm to Market Road | 1 | 3330943.93 | 1552300 | 1778643.93 | 1552300 | 3rd Tranche | 1146275.84 | 2698575.84 | 1552300 | 1146275.84 | 100% | 100% | 64.45% | 81.02% | 100% | 2003-10-23 | 2003-12-12 | 2004-05-18 | 2005-03-20 | 2005-10-06 | 306 | 105 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Dinasan | 097222001 | Day Care Center | 1 | 620010 | 433213 | 186797 | 433213 | 3rd Tranche | 139297 | 572510 | 433213 | 139297 | 100% | 100% | 74.57% | 92.34% | 100% | 2006-05-08 | 2006-06-08 | 2006-06-28 | 2006-08-04 | no data | 37 | 112 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Ilihan | 097222010 | Day Care Center | 1 | 620010 | 433213 | 186797 | 433213 | 3rd Tranche | 140296 | 573509 | 433213 | 140296 | 100% | 100% | 75.11% | 92.5% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-24 | 2006-09-21 | no data | 59 | 70 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Labakid | 097222011 | Day Care Center | 1 | 352623.52 | 179640 | 172983.52 | 179640 | 3rd Tranche | 205325.52 | 384965.52 | 179640 | 205325.52 | 100% | 100% | 118.7% | 109.2% | 100% | 2003-10-23 | 2003-12-12 | 2004-05-20 | 2005-02-26 | 2005-03-28 | 282 | 169 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Labakid | 097222011 | Health Station | 1 | 470698 | 326283 | 144415 | 326283 | 3rd Tranche | 93505 | 419788 | 326283 | 93505 | 100% | 100% | 64.75% | 89.18% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-05 | 2006-08-26 | no data | 52 | 105 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Litalip | 097222013 | Rehab of 1.56 km. Farm to Market Road | 1 | 2201519.121 | 805420 | 1396099.121 | 724878 | 2nd Tranche | 1372090.69 | 2096968.69 | 724878 | 1372090.69 | 100% | 100% | 98.28% | 95.25% | 100% | 2003-10-23 | 2003-12-12 | 2004-07-20 | 2005-02-10 | 2005-03-15 | 205 | 185 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Litalip | 097222013 | 2 CR School Building | 1 | 779765 | 544286 | 235479 | 544286 | 3rd Tranche | 146469 | 690755 | 544286 | 146469 | 100% | 100% | 62.2% | 88.59% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-24 | 2006-09-15 | no data | 53 | 174 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Lopero | 097222014 | 2 km. Farm to Market Road | 1 | 3485188.03 | 1356180 | 2129008.03 | 1356180 | 3rd Tranche | 1350519.51 | 2706699.51 | 1356180 | 1350519.51 | 100% | 100% | 63.43% | 77.66% | 100% | 2003-10-23 | 2003-12-12 | 2004-05-28 | 2005-06-24 | 2005-09-09 | 392 | 108 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Lopero | 097222014 | 2 CR School Building | 1 | 779765 | 545286 | 234479 | 545286 | 3rd Tranche | 141069 | 686355 | 545286 | 141069 | 100% | 100% | 60.16% | 88.02% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-24 | 2006-09-21 | no data | 59 | 50 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Lumaping | 097222015 | Day Care Center | 1 | 608983 | 352734 | 256249 | 352734 | 3rd Tranche | 252328.692 | 605062.692 | 352734 | 252328.692 | 100% | 100% | 98.47% | 99.36% | 100% | 2005-03-31 | 2005-05-16 | 2005-08-22 | 2005-11-30 | 2005-12-27 | 100 | 230 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Manawan | 097222003 | Water System | 1 | 571759 | 361241 | 210518 | 361241 | 3rd Tranche | 210518 | 571759 | 361241 | 210518 | 100% | 100% | 100% | 100% | 100% | 2005-03-31 | 2005-05-16 | 2005-07-18 | 2005-09-14 | 2005-10-05 | 58 | 196 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Manawan | 097222003 | Multi Purpose Building | 1 | 1144115 | 799834 | 344281 | 799834 | 3rd Tranche | 196631 | 996465 | 799834 | 196631 | 100% | 100% | 57.11% | 87.09% | 100% | 2006-05-08 | 2006-06-08 | 2006-06-28 | 2006-10-31 | no data | 125 | 192 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Marupay | 097222016 | Day Care Center | 1 | 608983 | 413256 | 195727 | 413256 | 3rd Tranche | 194156.792 | 607412.792 | 413256 | 194156.792 | 100% | 100% | 99.2% | 99.74% | 100% | 2005-03-31 | 2005-05-16 | 2005-08-22 | 2005-11-30 | 2006-02-28 | 100 | 85 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Poblacion | 097222016 | Water System Level II | 1 | 1559775 | 1090000 | 469775 | 1090000 | 3rd Tranche | 371982 | 1461982 | 1090000 | 371982 | 100% | 100% | 79.18% | 93.73% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-04 | 2006-10-01 | no data | 89 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Siparok | 097222005 | Water System Level II | 1 | 2015206 | 1387970 | 627236 | 1387970 | 3rd Tranche | 572764.86 | 1960734.86 | 1387970 | 572764.86 | 100% | 100% | 91.32% | 97.3% | 100% | 2005-03-31 | 2005-05-16 | 2005-07-05 | 2005-09-30 | 2005-10-21 | 87 | 430 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Tabon | 097222006 | Rural Electrification/Single Phase Lateral line | 1 | 2013414.21 | 798382 | 1215032.21 | 798382 | 3rd Tranche | 1187259.42 | 1985641.42 | 798382 | 1187259.42 | 100% | 100% | 97.71% | 98.62% | 100% | 2003-10-23 | 2003-12-12 | 2004-05-24 | 2005-12-30 | 2006-02-14 | 585 | 112 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Tabon | 097222006 | Multi Purpose Building | 1 | 1432170 | 901602 | 530568 | 901602 | 3rd Tranche | 467138 | 1368740 | 901602 | 467138 | 100% | 100% | 88.04% | 95.57% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-04 | 2006-10-31 | no data | 119 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Tamarok | 097222018 | Day Care Center | 1 | 608983 | 413256 | 195727 | 413256 | 3rd Tranche | 197198.8 | 610454.8 | 413256 | 197198.8 | 100% | 100% | 100.8% | 100.2% | 100% | 2005-03-31 | 2005-05-16 | 2005-08-22 | 2005-11-30 | 2005-12-09 | 100 | 75 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Tamarok | 097222018 | Health Station | 1 | 470698 | 326283 | 144415 | 326283 | 3rd Tranche | 92558.2 | 418841.2 | 326283 | 92558.2 | 100% | 100% | 64.09% | 88.98% | 100% | 2006-05-08 | 2006-06-08 | 2006-07-03 | 2006-08-24 | no data | 52 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Jose Dalman | 097222 | Tamil | 097222007 | Rehab of 2 km. Farm to Market Road | 1 | 1909747.17 | 708078 | 1201669.17 | 708078 | 3rd Tranche | 1208589.53 | 1916667.53 | 708078 | 1208589.53 | 100% | 100% | 100.6% | 100.4% | 100% | 2003-10-23 | 2003-12-12 | 2004-05-21 | 2005-06-15 | 2005-08-31 | 390 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Batayan | 097227001 | Barangay Health Station | 1 | 350000 | 209608.2 | 140391.8 | 209608.2 | 3rd Tranche | 93338 | 302946.2 | 209608.2 | 93338 | 100% | 100% | 66.48% | 86.56% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-05 | 2005-05-20 | 2005-09-23 | 410 | 75 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Botong | 097227002 | Barangay Health Station | 1 | 350000 | 237608.2 | 112391.8 | 237608.2 | 3rd Tranche | 107240 | 344848.2 | 237608.2 | 107240 | 100% | 100% | 95.42% | 98.53% | 100% | 2003-11-07 | 2003-12-16 | 2004-05-15 | 2005-04-15 | 2005-05-01 | 335 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Botong | 097227002 | Improvement of Spill Way | 1 | 319602 | 206402 | 113200 | 206402 | 3rd Tranche | 113200 | 319602 | 206402 | 113200 | 100% | 100% | 100% | 100% | 100% | n/a | n/a | 2009-03-20 | 2009-04-27 | 2009-04-30 | 38 | 487 | a.) Return to CO 15,298.00 b.)Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Concepcion | 097227003 | 2 Class Room School Building | 1 | 350000 | 171608.12 | 178391.88 | 154447.31 | 3rd Tranche | 196313.67 | 350760.98 | 154447.31 | 196313.67 | 100% | 100% | 110% | 100.2% | 100% | 2003-11-07 | 2003-12-16 | 2004-03-23 | 2004-09-30 | 2004-10-15 | 191 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Concepcion | 097227003 | Health Station | 1 | 396000 | 276000 | 120000 | 276000 | 3rd Tranche | 126086.2 | 402086.2 | 276000 | 126086.2 | 100% | 100% | 105.1% | 101.5% | 100% | 2005-04-18 | 2005-06-10 | 2005-07-21 | 2005-11-15 | 2005-12-05 | 117 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Concepcion | 097227003 | Consts. Of Elem. School Bldg. | 1 | 1000000 | 700000 | 300000 | 700000 | 3rd Tranche | 259545 | 959545 | 700000 | 259545 | 100% | 100% | 86.52% | 95.95% | 100% | 2006-05-25 | 2006-06-23 | 2006-08-11 | 2006-10-31 | 2006-12-04 | 81 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Daniel Maing | 097227004 | Barangay Health Station | 1 | 350000 | 202608.2 | 147391.8 | 202608.2 | 3rd Tranche | 170163.51 | 372771.71 | 202608.2 | 170163.51 | 100% | 100% | 115.4% | 106.5% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-06 | 2005-02-12 | 2005-03-15 | 312 | 498 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Daniel Maing | 097227004 | Rehab. Of WS LII | 1 | 985291 | 802891 | 182400 | 741419.1 | 3rd Tranche | 161036 | 902455.1 | 741419.1 | 161036 | 100% | 100% | 88.29% | 91.59% | 100% | n/a | n/a | 2009-04-09 | 2009-06-23 | 2009-06-29 | 75 | 282 | a.) No need to request contingency b.) Return to CO 3,960.00 c.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Fatima | 097227005 | Barangay Health Station | 1 | 350000 | 209408.2 | 140591.8 | 209408.2 | 3rd Tranche | 142700 | 352108.2 | 209408.2 | 142700 | 100% | 100% | 101.5% | 100.6% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-12 | 2005-04-18 | 2005-05-19 | 371 | 152 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Fatima | 097227005 | Day Care Center | 1 | 382286 | 267000 | 115286 | 267000 | 3rd Tranche | 110289 | 377289 | 267000 | 110289 | 100% | 100% | 95.67% | 98.69% | 100% | 2005-04-18 | 2005-06-10 | 2005-07-28 | 2005-10-31 | 2005-11-24 | 95 | 50 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Fatima | 097227005 | Const. of Flea Market | 1 | 569759 | 346773 | 222986 | 312095.7 | 2nd Tranche | 230021 | 542116.7 | 312095.7 | 230021 | 100% | 100% | 103.2% | 95.15% | 100% | n/a | n/a | 2009-03-17 | 2009-06-23 | 2009-07-07 | 98 | 280 | a.) No need to request 3rd tranch b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Gatas | 097227006 | Barangay Health Station | 1 | 350000.09 | 209888.29 | 140111.8 | 209888.29 | 3rd Tranche | 124021.95 | 333910.24 | 209888.29 | 124021.95 | 100% | 100% | 88.52% | 95.4% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-19 | 2004-09-05 | 2004-09-21 | 139 | 162 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Gatas | 097227006 | Multi Purpose Building | 1 | 1192909 | 835338 | 357571 | 835338 | 3rd Tranche | 331302 | 1166640 | 835338 | 331302 | 100% | 100% | 92.65% | 97.8% | 100% | 2006-05-25 | 2006-06-23 | 2006-08-13 | 2006-12-14 | 2006-12-15 | 123 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Gatas | 097227006 | CONST. OF 1 UNIT 2 RMS SCH. BLDG | 1 | 844600 | 693424 | 151176 | 673233.32 | 3rd Tranche | 151176 | 824409.32 | 673233.32 | 151176 | 100% | 100% | 100% | 97.61% | 100% | n/a | n/a | 2009-03-20 | 2009-05-02 | 2009-06-02 | 43 | 170 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Marcelo | 097227008 | 2 Class Room School Building w/ 2 CR | 1 | 700000 | 484922.7 | 215077.3 | 484922.7 | 3rd Tranche | 200140 | 685062.7 | 484922.7 | 200140 | 100% | 100% | 93.05% | 97.87% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-25 | 2004-11-08 | 2005-01-17 | 197 | 173 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Marcelo | 097227008 | Multi-Purpose Building | 1 | 934134 | 646000 | 288134 | 646000 | 3rd Tranche | 365261 | 1011261 | 646000 | 365261 | 100% | 100% | 126.8% | 108.3% | 100% | 2005-04-18 | 2005-06-10 | 2005-07-29 | 2006-03-15 | 2006-04-29 | 229 | 500 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Marcelo | 097227008 | Const. of Slope Protection | 1 | 765073 | 684273 | 80800 | 683480 | 3rd Tranche | 112800 | 796280 | 683480 | 112800 | 100% | 100% | 139.6% | 104.1% | 100% | n/a | n/a | 2009-04-08 | 2009-06-18 | 2009-06-19 | 71 | 230 | a.) No need to request contingency b.) Return to CO 10,040.00 c.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | New Calamba | 097227009 | 2 Class Room School Building w/ 2 CR | 1 | 700000 | 484562.7 | 215437.3 | 484562.7 | 3rd Tranche | 167460 | 652022.7 | 484562.7 | 167460 | 100% | 100% | 77.73% | 93.15% | 100% | 2003-11-07 | 2003-12-16 | 2004-03-22 | 2004-09-06 | 2004-09-16 | 168 | 167 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | New Calamba | 097227009 | Day Care Center | 1 | 382286 | 267000 | 115286 | 267000 | 3rd Tranche | 124416.43 | 391416.43 | 267000 | 124416.43 | 100% | 100% | 107.9% | 102.4% | 100% | 2005-04-18 | 2005-06-10 | 2005-02-28 | 2005-10-05 | 2005-10-18 | 219 | 50 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | New Calamba | 097227009 | Spring Catchment | 1 | 425968 | 312290 | 113678 | 312290 | 3rd Tranche | 103694 | 415984 | 312290 | 103694 | 100% | 100% | 91.22% | 97.66% | 100% | 2006-05-25 | 2006-06-23 | 2006-09-05 | 2006-10-30 | no data | 55 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | New Calamba | 097227009 | Const. of WS LII | 1 | 1259872 | 1154072 | 105800 | 1095718 | 3rd Tranche | 105800 | 1201518 | 1095718 | 105800 | 100% | 100% | 100% | 95.37% | 100% | n/a | n/a | 2009-04-13 | 2009-06-13 | 2009-06-15 | 61 | 240 | a.) No need to request contingency b.) Return to CO 5,000.00 c.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Palalian | 097227010 | Road Regravelling of FMR and Drainage | 1 | 1150000 | 803000 | 347000 | 722700 | 2nd Tranche | 140520 | 863220 | 722700 | 140520 | 100% | 100% | 40.5% | 75.06% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-03 | 2005-04-15 | 2005-05-10 | 377 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Palalian | 097227010 | Water System Level I | 1 | 950755 | 665523 | 285232 | 665523 | 3rd Tranche | 266579 | 932102 | 665523 | 266579 | 100% | 100% | 93.46% | 98.04% | 100% | 2006-05-25 | 2006-06-23 | 2006-09-11 | 2006-11-11 | 2006-10-24 | 61 | 97 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Palalian | 097227010 | Const. of 1 unit 2CL Sch. Bldg. | 1 | 844600 | 668620 | 175980 | 636858.67 | 3rd Tranche | 176160 | 813018.67 | 636858.67 | 176160 | 100% | 100% | 100.1% | 96.26% | 100% | n/a | n/a | 2009-03-19 | 2009-06-22 | 2009-06-25 | 95 | 210 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Paraiso | 097227011 | 2 Class Room School Building w/ 2 CR | 1 | 699999.3 | 489062 | 210937.3 | 489062 | 3rd Tranche | 189603 | 678665 | 489062 | 189603 | 100% | 100% | 89.89% | 96.95% | 100% | 2003-11-07 | 2003-12-16 | 2004-04-29 | 2005-01-15 | 2005-02-28 | 261 | 115 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Paraiso | 097227011 | Rehab of Farm to Market Road | 1 | 2409850 | 1686849 | 723001 | 1518164.1 | 2nd Tranche | 164768 | 1682932.1 | 1518164.1 | 164768 | 100% | 100% | 22.79% | 69.84% | 100% | 2006-05-25 | 2006-06-23 | 2006-12-13 | 2007-02-20 | not conducted | 69 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Paraiso | 097227011 | Const. of 1 unit 2CL Sch. Bldg. | 1 | 844600 | 699120 | 145480 | 661289.79 | 3rd Tranche | 148538.5 | 809828.29 | 661289.79 | 148538.5 | 100% | 100% | 102.1% | 95.88% | 100% | n/a | n/a | 2009-03-12 | 2009-06-23 | 2009-07-08 | 103 | 190 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Pianon | 097227012 | Water System Level II | 1 | 1531975 | 1072481 | 459494 | 1072481 | 3rd Tranche | 232303 | 1304784 | 1072481 | 232303 | 100% | 100% | 50.56% | 85.17% | 100% | 2005-04-18 | 2005-06-10 | 2005-09-01 | 2006-03-15 | 2006-04-13 | 195 | 298 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Pianon | 097227012 | Const. WSII | 1 | 810000 | 628200 | 181800 | 621877.3 | 3rd Tranche | 181800 | 803677.3 | 621877.3 | 181800 | 100% | 100% | 100% | 99.22% | 100% | n/a | n/a | 2009-04-03 | 2009-06-23 | 2009-07-10 | 81 | 280 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Kalawit (Pob.) | 097227007 | Water System Level II | 1 | 1674561 | 1129519 | 545042 | 1129519 | 3rd Tranche | 492659.1 | 1622178.1 | 1129519 | 492659.1 | 100% | 100% | 90.39% | 96.87% | 100% | 2005-04-18 | 2005-06-10 | 2005-08-08 | 2006-03-15 | 2006-04-12 | 219 | 400 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | San Jose | 097227013 | Water Supply w/ 30 units Communal Faucet | 1 | 415000 | 240770.26 | 174229.74 | 240770.26 | 3rd Tranche | 174925.8 | 415696.06 | 240770.26 | 174925.8 | 100% | 100% | 100.4% | 100.2% | 100% | 2003-11-07 | 2003-12-16 | 2004-03-29 | 2005-11-20 | 2005-12-27 | 601 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | San Jose | 097227013 | Const. of 1 unit 1 CL sch. Bldg. | 1 | 844600 | 658120 | 186480 | 625714 | 3rd Tranche | 186480 | 812194 | 625714 | 186480 | 100% | 100% | 100% | 96.16% | 100% | n/a | n/a | 2009-03-18 | 2009-06-10 | 2009-06-11 | 84 | 170 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Tugop | 097227014 | Multi Purpose Building | 1 | 670000 | 456952.52 | 213047.48 | 456952.52 | 3rd Tranche | 174534.72 | 631487.24 | 456952.52 | 174534.72 | 100% | 100% | 81.92% | 94.25% | 100% | 2003-11-07 | 2003-12-16 | 2004-03-09 | 2004-08-23 | 2004-08-29 | 167 | 111 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Tugop | 097227014 | 2 CR School Building | 1 | 787477 | 542000 | 245477 | 542000 | 3rd Tranche | 159050 | 701050 | 542000 | 159050 | 100% | 100% | 64.79% | 89.02% | 100% | 2005-04-18 | 2005-06-10 | 2005-07-28 | 2005-11-08 | 2006-01-17 | 103 | 70 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Kalawit | 097227 | Tugop | 097227014 | Const. of Brgy. Health Station | 1 | 578985 | 458105 | 120880 | 458105 | 3rd Tranche | 120880.01 | 578985.01 | 458105 | 120880.01 | 100% | 100% | 100% | 100% | 100% | n/a | n/a | 2009-03-05 | 2009-05-19 | 2009-06-03 | 75 | 187 | Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Balok | 097203001 | Construction of Brgy. Health Station | 1 | 422650 | 290250 | 132400 | 290250 | 3rd Tranche | 134019.7 | 424269.7 | 290250 | 134019.7 | 100% | 100% | 101.2% | 100.4% | 100% | 2004-11-10 | 2004-12-09 | 2005-05-10 | 2005-07-30 | 2005-08-05 | 81 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Balok | 097203001 | Sectional Road Concreting | 1 | 3326370 | 1814810 | 1511560 | 1814810 | 3rd Tranche | 724267.44 | 2539077.44 | 1814810 | 724267.44 | 100% | 100% | 47.92% | 76.33% | 100% | 2005-10-20 | 2005-12-01 | 2006-02-06 | 2006-08-31 | 2006-09-11 | 206 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Basagan | 097203002 | Brgy. Water System L-II | 1 | 972000 | 583000 | 389000 | 583000 | 3rd Tranche | 361500 | 944500 | 583000 | 361500 | 100% | 100% | 92.93% | 97.17% | 100% | 2003-05-06 | 2003-05-28 | 2003-10-15 | 2004-05-28 | 2004-06-16 | 226 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Biniray | 097203003 | Rehabilitation of Biniray-Nanginan Road | 1 | 2850050 | 1071160 | 1778890 | 1071160 | 3rd Tranche | 1466540 | 2537700 | 1071160 | 1466540 | 100% | 100% | 82.44% | 89.04% | 100% | 2003-05-06 | 2003-05-28 | 2003-08-30 | 2004-08-26 | 2004-08-26 | 362 | 98 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Brgy. Dos | 097203017 | Installation of Shoreline Protection Structure | 1 | 2273170 | 1515970 | 757200 | 1515970 | 3rd Tranche | 922352.5 | 2438322.5 | 1515970 | 922352.5 | 100% | 100% | 121.8% | 107.3% | 100% | 2004-11-10 | 2004-12-09 | 2005-04-25 | 2005-07-31 | 2007-08-06 | 97 | 372 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Brgy. Uno | 097203016 | Concreting of Brgy Road | 1 | 1685835 | 955200 | 730635 | 955200 | 3rd Tranche | 122297.5 | 1077497.5 | 955200 | 122297.5 | 100% | 100% | 16.74% | 63.91% | 100% | 2004-11-10 | 2004-12-09 | 2005-01-31 | 2005-08-15 | 2005-08-26 | 196 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Bulawan | 097203004 | Farm to Market Road Concreting | 1 | 523775.01 | 450000.01 | 73775 | 450000.01 | 3rd Tranche | 328000 | 778000.01 | 450000.01 | 328000 | 100% | 100% | 444.6% | 148.5% | 100% | 2003-05-06 | 2003-05-28 | 2003-12-22 | 2004-08-29 | 2004-09-06 | 251 | 371 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Carupay | 097203025 | Road rehabilitation | 1 | 2496376 | 1500000 | 996376 | 1350000 | 2nd Tranche | 2290000 | 3640000 | 1350000 | 2290000 | 100% | 100% | 229.8% | 145.8% | 100% | 2003-05-06 | 2003-05-28 | 2003-10-09 | 2005-04-30 | 2005-05-16 | 569 | 465 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Daanglungsod | 097203005 | 2 Story Multi Purpose Building | 1 | 816984.4 | 582287.73 | 234696.67 | 582287.73 | 3rd Tranche | 217096.66 | 799384.39 | 582287.73 | 217096.66 | 100% | 100% | 92.5% | 97.85% | 100% | 2003-05-06 | 2003-05-28 | 2003-07-31 | 2004-02-09 | 2004-02-11 | 193 | 367 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Daanglungsod | 097203005 | Flea Market | 1 | 525982 | 334570 | 191412 | 334570 | 3rd Tranche | 181510 | 516080 | 334570 | 181510 | 100% | 100% | 94.83% | 98.12% | 100% | 2005-10-20 | 2005-12-01 | 2006-01-16 | 2006-08-30 | 2006-08-30 | 226 | 377 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Dabiak | 097203006 | Construction of Dabiak Hanging Bridge | 1 | 996393 | 670000 | 326393 | 670000 | 3rd Tranche | 866280 | 1536280 | 670000 | 866280 | 100% | 100% | 265.4% | 154.2% | 100% | 2004-11-10 | 2004-12-09 | 2005-02-28 | 2006-10-31 | 2006-12-01 | 610 | 137 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Dr. Jose Rizal | 097203007 | Multi Purpose Building | 1 | 1237755 | 861355 | 376400 | 861355 | 3rd Tranche | 316750 | 1178105 | 861355 | 316750 | 100% | 100% | 84.15% | 95.18% | 100% | 2005-10-20 | 2005-12-01 | 2006-01-16 | 2006-06-30 | 2006-07-06 | 165 | 191 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Fimagas | 097203008 | Farm to Market Road | 1 | 3111000 | 1770000 | 1341000 | 1593000 | 2nd Tranche | 3170000 | 4763000 | 1593000 | 3170000 | 100% | 100% | 236.4% | 153.1% | 100% | 2003-05-06 | 2003-05-28 | 2003-10-09 | 2005-04-30 | 2005-05-16 | 569 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Loyuran | 097203026 | Restoration/Rehabilitation of brgy Loyuran road | 1 | 1134175 | 772175 | 362000 | 772175 | 3rd Tranche | 285017 | 1057192 | 772175 | 285017 | 100% | 100% | 78.73% | 93.21% | 100% | 2004-11-10 | 2004-12-09 | 2005-02-14 | 2005-09-30 | 2005-11-30 | 228 | 90 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Malasay | 097203010 | Restoration/Rehabilitation of Bulawan-Malasay Road with concreting (500 ln.m) on critical sections | 1 | 1656051 | 1007801 | 648250 | 1007801 | 3rd Tranche | 368360 | 1376161 | 1007801 | 368360 | 100% | 100% | 56.82% | 83.1% | 100% | 2004-11-10 | 2004-12-09 | 2005-02-09 | 2005-05-11 | no data | 91 | 270 | completed as built | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Malugas | 097203009 | 6 Wheeler Isuzu Dump Truck | 1 | 493000 | 450000 | 43000 | 450000 | 3rd Tranche | 59800 | 509800 | 450000 | 59800 | 100% | 100% | 139.1% | 103.4% | 100% | 2003-05-06 | 2003-05-28 | 2003-11-18 | 2004-02-03 | 2004-02-05 | 77 | 267 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Malugas | 097203009 | Multi Purpose Building | 1 | 1508940 | 1038070 | 470870 | 1038070 | 3rd Tranche | 312421.16 | 1350491.16 | 1038070 | 312421.16 | 100% | 100% | 66.35% | 89.5% | 100% | 2005-10-20 | 2005-12-01 | 2006-01-16 | 2006-06-30 | 2006-07-14 | 165 | 257 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Matam | 097203013 | Construction of 1 unit 2 classroom HS School Building (7x16m) | 1 | 845355 | 587849 | 257506 | 587849 | 3rd Tranche | 251425 | 839274 | 587849 | 251425 | 100% | 100% | 97.64% | 99.28% | 100% | 2004-11-10 | 2004-12-09 | 2005-03-09 | 2005-06-30 | 2005-07-05 | 113 | 273 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Mias | 097203012 | Road Rehabilitation | 1 | 1633865.97 | 237023.97 | 1396842 | 237023.97 | 3rd Tranche | 1388842.03 | 1625866 | 237023.97 | 1388842.03 | 100% | 100% | 99.43% | 99.51% | 100% | 2003-05-06 | 2003-05-28 | 2003-08-18 | 2005-05-28 | 2005-05-28 | 649 | 303 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Miatan | 097203013 | Hanging Bridge | 1 | 1399551 | 898270 | 501281 | 898270 | 3rd Tranche | 576000 | 1474270 | 898270 | 576000 | 100% | 100% | 114.9% | 105.3% | 100% | 2005-10-20 | 2005-12-01 | 2006-02-06 | 2006-08-30 | 2006-08-30 | 205 | 210 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Nanginan | 097203014 | Rehabilitation/Improvement & Expansion of Level-II WS | 1 | 840655 | 630000 | 210655 | 630000 | 3rd Tranche | 210655 | 840655 | 630000 | 210655 | 100% | 100% | 100% | 100% | 100% | 2003-05-06 | 2003-05-28 | 2003-09-29 | 2004-08-24 | 2004-08-27 | 330 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | New Tambo | 097203027 | Construction of Day Care Center (6x8m) | 1 | 690500 | 462800 | 227700 | 462800 | 3rd Tranche | 257526 | 720326 | 462800 | 257526 | 100% | 100% | 113.1% | 104.3% | 100% | 2004-11-10 | 2004-12-09 | 2005-03-09 | 2005-06-30 | 2005-08-05 | 113 | 180 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Patik | 097203028 | Multi Purpose Building | 1 | 1115860 | 777760 | 338100 | 777760 | 3rd Tranche | 234500 | 1012260 | 777760 | 234500 | 100% | 100% | 69.36% | 90.72% | 100% | 2005-10-20 | 2005-12-01 | 2006-02-20 | 2006-08-08 | 2006-09-22 | 169 | 176 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | San Antonio | 097203018 | Concreting of Brgy Road | 1 | 2066094 | 1078900 | 987194 | 1078900 | 3rd Tranche | 210429.5 | 1289329.5 | 1078900 | 210429.5 | 100% | 100% | 21.32% | 62.4% | 100% | 2004-11-10 | 2004-12-09 | 2005-02-10 | 2005-09-15 | 2005-10-01 | 217 | 374 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | San Vicente | 097203030 | Multi Purpose Building | 1 | 624604.65 | 428528.29 | 196076.36 | 428528.289 | 3rd Tranche | 245171.71 | 673699.999 | 428528.289 | 245171.71 | 100% | 100% | 125% | 107.9% | 100% | 2003-05-06 | 2003-05-28 | 2003-07-29 | 2003-12-17 | 2004-02-11 | 141 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | San Vicente | 097203030 | Construction of Day Care Center | 1 | 547566 | 378500 | 169066 | 378500 | 3rd Tranche | 1037213.55 | 1415713.55 | 378500 | 1037213.55 | 100% | 100% | 613.5% | 258.5% | 100% | 2004-11-10 | 2004-12-09 | 2005-03-07 | 2005-07-08 | 2005-07-15 | 123 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sanao | 097203029 | Consruction of Level II Water System | 1 | 1035920 | 686000 | 349920 | 686000 | 3rd Tranche | 344420 | 1030420 | 686000 | 344420 | 100% | 100% | 98.43% | 99.47% | 100% | 2003-05-06 | 2003-05-28 | 2003-09-16 | 2004-08-06 | 2004-08-06 | 325 | 40 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Seres | 097203019 | Construction of Multi-Purpose Building | 1 | 1097347 | 764402 | 332945 | 764402 | 3rd Tranche | 182420 | 946822 | 764402 | 182420 | 100% | 100% | 54.79% | 86.28% | 100% | 2004-11-10 | 2004-12-09 | 2005-02-28 | 2005-06-30 | 2005-07-30 | 122 | 385 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Seroan | 097203020 | Construction of Brgy. Health Station (6x8m) | 1 | 433698 | 290000 | 143698 | 290000 | 3rd Tranche | 372837.7 | 662837.7 | 290000 | 372837.7 | 100% | 100% | 259.5% | 152.8% | 100% | 2004-11-10 | 2004-12-09 | 2005-02-28 | 2005-06-15 | 2005-08-10 | 107 | 179 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Singatong | 097203021 | Box Culvert | 1 | 732665 | 475015 | 257650 | 475015 | 3rd Tranche | 150600 | 625615 | 475015 | 150600 | 100% | 100% | 58.45% | 85.39% | 100% | 2005-10-20 | 2005-12-01 | 2006-02-23 | 2006-09-30 | 2006-09-30 | 219 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sinuyak | 097203022 | Multi Purpose Building | 1 | 1115860 | 777760 | 338100 | 777760 | 3rd Tranche | 234000 | 1011760 | 777760 | 234000 | 100% | 100% | 69.21% | 90.67% | 100% | 2005-10-20 | 2005-12-01 | 2006-01-23 | 2006-09-30 | 2006-09-30 | 250 | 270 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sitog | 097203023 | Multi Purpose Building | 1 | 1115860 | 777760 | 338100 | 777760 | 3rd Tranche | 269700 | 1047460 | 777760 | 269700 | 100% | 100% | 79.77% | 93.87% | 100% | 2005-10-20 | 2005-12-01 | 2006-02-20 | 2006-08-30 | 2006-09-06 | 191 | 567 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sto. Niño | 097203031 | Feasibility Study on Construction of Irrigation System | 1 | 193000 | 162000 | 31000 | 162000 | 3rd Tranche | 25000 | 187000 | 162000 | 25000 | 100% | 100% | 80.65% | 96.89% | 100% | 2003-05-06 | 2003-05-28 | 2003-09-08 | 2003-12-24 | 2004-01-11 | 107 | 30 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Sto. Niño | 097203031 | Road Concreting | 1 | 2094350 | 1244630 | 849720 | 1244630 | 3rd Tranche | 668900 | 1913530 | 1244630 | 668900 | 100% | 100% | 78.72% | 91.37% | 100% | 2005-10-20 | 2005-12-01 | 2006-01-16 | 2006-06-30 | 2006-07-12 | 165 | 99 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Katipunan | 097203 | Tuburan | 097203024 | Rehabilitation of WS L-II | 1 | 579300 | 450000 | 129300 | 450000 | 3rd Tranche | 129300 | 579300 | 450000 | 129300 | 100% | 100% | 100% | 100% | 100% | 2003-05-06 | 2003-05-28 | 2003-08-15 | 2004-05-30 | 2004-06-03 | 289 | 250 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Balok | 097215001 | Hanging Bridge | 1 | 1246114 | 872114 | 374000 | 872114 | 3rd Tranche | 340201.37 | 1212315.37 | 872114 | 340201.37 | 100% | 100% | 90.96% | 97.29% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-29 | 2005-11-26 | 2006-12-02 | 120 | 165 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Balunokan | 097215023 | Road Rehabilitation | 1 | 3380259 | 1377462 | 2002797 | 1377462 | 3rd Tranche | 218645.3 | 1596107.3 | 1377462 | 218645.3 | 100% | 100% | 10.92% | 47.22% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-27 | 2005-12-10 | 2006-02-03 | 136 | 195 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Balunokan | 097215023 | Construction of 1 Unit 2 CL School Building | 1 | 1257622.11 | 916520.49 | 341101.62 | 824868.44 | 2nd Tranche | 400308.08 | 1225176.52 | 824868.44 | 400308.08 | 100% | 100% | 117.4% | 97.42% | 100% | n/a | n/a | 2009-03-03 | 2009-06-23 | 2009-06-25 | 112 | 174 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Datagan | 097215003 | Road Rehabilitation | 1 | 1883477 | 1285810 | 597667 | 1285810 | 3rd Tranche | 597667 | 1883477 | 1285810 | 597667 | 100% | 100% | 100% | 100% | 100% | 2003-10-25 | 2003-12-10 | 2004-04-20 | 2005-11-30 | 2005-12-09 | 589 | 169 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Denoyan | 097215004 | Construction of hanging bridge | 1 | 892623 | 527598 | 365025 | 527598 | 3rd Tranche | 379054 | 906652 | 527598 | 379054 | 100% | 100% | 103.8% | 101.6% | 100% | 2003-10-25 | 2003-12-10 | 2004-04-19 | 2005-03-15 | 2005-04-20 | 330 | 180 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Diongan | 097215005 | Hanging Bridge | 1 | 2187310 | 1527755 | 659555 | 1527755 | 3rd Tranche | 659555 | 2187310 | 1527755 | 659555 | 100% | 100% | 100% | 100% | 100% | 2003-10-25 | 2003-12-10 | 2004-04-02 | 2005-09-20 | 2005-11-30 | 536 | 416 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Diongan | 097215005 | Construction of 1 Unit 2 CL School Building | 1 | 1056700.13 | 877374.61 | 179325.52 | 789637.15 | 2nd Tranche | 233194.45 | 1022831.6 | 789637.15 | 233194.45 | 100% | 100% | 130% | 96.79% | 100% | n/a | n/a | 2009-03-12 | 2009-06-23 | 2009-06-25 | 103 | 119 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Domogok | 097215006 | Hanging Bridge | 1 | 2837032 | 1980490 | 856542 | 1980490 | 3rd Tranche | 614314.86 | 2594804.86 | 1980490 | 614314.86 | 100% | 100% | 71.72% | 91.46% | 100% | 2006-05-29 | 2006-06-19 | 2006-10-20 | 2007-01-31 | 2007-03-06 | 103 | 130 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Dumpilas | 097215007 | 4 Class Room School Building | 1 | 1700301 | 1190159 | 510142 | 1190159 | 3rd Tranche | 525493.22 | 1715652.22 | 1190159 | 525493.22 | 100% | 100% | 103% | 100.9% | 100% | 2006-05-29 | 2006-06-19 | 2006-08-01 | 2006-12-15 | 2006-12-18 | 136 | 130 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Dumpilas | 097215007 | Construction of Line Canal | 1 | 1159162.08 | 1011838.92 | 147323.16 | 910655.03 | 2nd Tranche | 339618 | 1250273.03 | 910655.03 | 339618 | 100% | 100% | 230.5% | 107.9% | 100% | n/a | n/a | 2009-02-25 | 2009-06-23 | 2009-06-25 | 118 | 290 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Gonayen | 097215008 | Spring Dev't | 1 | 394961 | 268951 | 126010 | 268951 | 3rd Tranche | 126010 | 394961 | 268951 | 126010 | 100% | 100% | 100% | 100% | 100% | 2003-10-25 | 2003-12-10 | 2004-03-29 | 2004-06-30 | 2005-04-02 | 93 | 162 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Guibo | 097215010 | Construction of Day Care Center | 1 | 676076.36 | 553040.99 | 123035.37 | 497736.9 | 2nd Tranche | 184222.27 | 681959.17 | 497736.9 | 184222.27 | 100% | 100% | 149.7% | 100.9% | 100% | n/a | n/a | 2009-03-11 | 2009-06-23 | 2009-06-25 | 104 | 64 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Gunyan | 097215011 | 2CR School Building | 1 | 932832 | 634771 | 298061 | 634771 | 3rd Tranche | 298061.04 | 932832.04 | 634771 | 298061.04 | 100% | 100% | 100% | 100% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-19 | 2005-11-24 | 2005-11-24 | 128 | 274 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Litolet | 097215012 | Hanging Bridge | 1 | 1467956 | 1024387 | 443569 | 1024387 | 3rd Tranche | 371885.99 | 1396272.99 | 1024387 | 371885.99 | 100% | 100% | 83.84% | 95.12% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-29 | 2007-02-28 | no data | 579 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Litolet | 097215012 | Construction of Line Canal | 1 | 1302113.39 | 1126153.69 | 175959.7 | 1013538.32 | 2nd Tranche | 376455.2 | 1389993.52 | 1013538.32 | 376455.2 | 100% | 100% | 213.9% | 106.7% | 100% | n/a | n/a | 2009-02-25 | 2009-06-22 | 2009-06-24 | 117 | 250 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Macasing | 097215013 | Road Regravelling | 1 | 2303915 | 1279641 | 1024274 | 1279641 | 3rd Tranche | 1024274 | 2303915 | 1279641 | 1024274 | 100% | 100% | 100% | 100% | 100% | 2003-10-25 | 2003-12-10 | 2004-04-10 | 2005-03-25 | 2005-04-20 | 349 | 222 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Macasing | 097215013 | 2CR School Building | 1 | 869426 | 547589 | 321837 | 547589 | 3rd Tranche | 298505 | 846094 | 547589 | 298505 | 100% | 100% | 92.75% | 97.32% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-20 | 2005-12-09 | 2005-12-09 | 142 | 185 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Macasing | 097215013 | Hanging Bridge | 1 | 1664803 | 1163091 | 501712 | 1163091 | 3rd Tranche | 407735.44 | 1570826.44 | 1163091 | 407735.44 | 100% | 100% | 81.27% | 94.36% | 100% | 2006-05-29 | 2006-06-19 | 2006-10-18 | 2007-02-25 | 2007-03-16 | 130 | 136 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Macasing | 097215013 | Construction of Water System Level 2 (gravity-type) | 1 | 488430.26 | 405542.02 | 82888.24 | 395754.35 | 3rd Tranche | 124888.24 | 520642.59 | 395754.35 | 124888.24 | 100% | 100% | 150.7% | 106.6% | 100% | n/a | n/a | 2009-03-03 | 2009-05-26 | 2009-06-22 | 84 | 386 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Mangilay | 097215014 | Construction of 1 Unit 2 CL School Building | 1 | 1123945.26 | 933959.8 | 189985.46 | 840563.82 | 2nd Tranche | 243166.9 | 1083730.72 | 840563.82 | 243166.9 | 100% | 100% | 128% | 96.42% | 100% | n/a | n/a | 2009-03-02 | 2009-05-18 | 2009-06-24 | 77 | 166 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Moyo | 097215015 | Hanging Bridge | 1 | 1679643 | 1175643 | 504000 | 1175643 | 3rd Tranche | 592760.15 | 1768403.15 | 1175643 | 592760.15 | 100% | 100% | 117.6% | 105.3% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-29 | 2006-11-15 | no data | 474 | 183 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Muñoz | 097215024 | Hanging Bridge | 1 | 1660296 | 1157860 | 502436 | 1157860 | 3rd Tranche | 392689.32 | 1550549.32 | 1157860 | 392689.32 | 100% | 100% | 78.16% | 93.39% | 100% | 2006-05-29 | 2006-06-19 | 2006-08-01 | 2006-12-15 | 2007-12-28 | 136 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Muñoz | 097215024 | Improvement of Water System Level 2 (gravity-type) | 1 | 762971.1 | 663303.8 | 99667.3 | 629858.54 | 3rd Tranche | 157285.79 | 787144.33 | 629858.54 | 157285.79 | 100% | 100% | 157.8% | 103.2% | 100% | n/a | n/a | 2009-03-02 | 2009-04-28 | 2009-06-23 | 57 | 196 | a.) No need to request contingency charged to grant b.) Close Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Pange | 097215016 | Hanging Bridge | 1 | 1877263 | 1220308 | 656955 | 1220308 | 3rd Tranche | 656955 | 1877263 | 1220308 | 656955 | 100% | 100% | 100% | 100% | 100% | 2003-10-25 | 2003-12-10 | 2004-04-26 | 2006-01-20 | 2006-02-24 | 634 | 164 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Pange | 097215016 | Construction of Health Station | 1 | 466439.07 | 380104.95 | 86334.12 | 342094.46 | 2nd Tranche | 112921.12 | 455015.58 | 342094.46 | 112921.12 | 100% | 100% | 130.8% | 97.55% | 100% | n/a | n/a | 2009-03-05 | 2009-06-05 | 2009-06-22 | 92 | 286 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Paranglumba | 097215017 | Construction of Water System Level 2 (gravity-type) | 1 | 985331.87 | 846743.67 | 138588.2 | 787822.96 | 3rd Tranche | 194236.37 | 982059.33 | 787822.96 | 194236.37 | 100% | 100% | 140.2% | 99.67% | 100% | n/a | n/a | 2009-02-26 | 2009-06-22 | 2009-06-25 | 116 | 115 | a.) No need to request contingency b.) Closed account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Siayan Proper (Pob.) | 097215022 | Construction of Line Canal | 1 | 1243905.4 | 1032052.32 | 211853.08 | 928847.09 | 2nd Tranche | 361652.08 | 1290499.17 | 928847.09 | 361652.08 | 100% | 100% | 170.7% | 103.7% | 100% | n/a | n/a | 2009-02-25 | 2009-06-23 | 2009-06-25 | 118 | 200 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Siayan Proper (Pob.) | 097215022 | Improvement of Barangay Health Station | 1 | 542000 | 500000 | 42000 | 500000 | 1st Tranche | 42000 | 539500 | 500000 | 39500 | 100% | 94.05% | 100% | 99.54% | 100% | n/a | n/a | 2009-06-08 | 2009-11-04 | 2009-11-06 | 149 | 200 | Bank balance are still for verification | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Polayo | 097215019 | Construction of Brgy. Road | 1 | 1728200 | 1108400 | 619800 | 1108400 | 3rd Tranche | 493240.75 | 1601640.75 | 1108400 | 493240.75 | 100% | 100% | 79.58% | 92.68% | 100% | 2006-05-29 | 2006-06-19 | 2006-12-24 | 2007-02-22 | 2007-03-02 | 60 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Polayo | 097215019 | Construction of Line Canal | 1 | 1243020.67 | 1032075.94 | 210944.73 | 928868.35 | 2nd Tranche | 417491.38 | 1346359.73 | 928868.35 | 417491.38 | 100% | 100% | 197.9% | 108.3% | 100% | n/a | n/a | 2009-02-26 | 2009-06-23 | 2009-06-25 | 117 | 255 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Sayaw | 097215020 | Spring Dev't Level-II | 1 | 700000 | 489937 | 210063 | 489937 | 3rd Tranche | 210063 | 700000 | 489937 | 210063 | 100% | 100% | 100% | 100% | 100% | 2003-10-25 | 2003-12-10 | 2004-04-09 | 2005-02-20 | 2005-03-23 | 317 | 80 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Sayaw | 097215020 | Water System Level II | 1 | 793771 | 555621 | 238150 | 555621 | 3rd Tranche | 209511.61 | 765132.61 | 555621 | 209511.61 | 100% | 100% | 87.97% | 96.39% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-26 | 2006-04-20 | 2006-04-20 | 268 | 150 |  | 1
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Sayaw | 097215020 | Improvement Water System L-2 | 1 | 378392.77 | 305150.11 | 73242.66 | 244120.09 | 1st Tranche | 116278.33 | 360398.42 | 244120.09 | 116278.33 | 100% | 100% | 158.8% | 95.24% | 100% | n/a | n/a | 2009-02-26 | 2009-05-26 | 2009-06-23 | 89 | 200 | a.) No need to request 2nd & 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Seriac | 097215021 | Water System Level II | 1 | 598567 | 412413 | 186154 | 412413 | 3rd Tranche | 167195.26 | 579608.26 | 412413 | 167195.26 | 100% | 100% | 89.82% | 96.83% | 100% | 2005-04-01 | 2005-05-18 | 2005-07-25 | 2006-01-09 | 2006-01-09 | 168 | 165 |  | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Seriac | 097215021 | Construction of Water System Level 2 (gravity-type) | 1 | 424973.15 | 352853.79 | 72119.36 | 282283.03 | 1st Tranche | 103133.62 | 385416.65 | 282283.03 | 103133.62 | 100% | 100% | 143% | 90.69% | 100% | n/a | n/a | 2009-03-02 | 2009-05-26 | 2009-06-23 | 85 | 84 | a.) No need to request 2nd & 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Suguilon | 097215025 | Construction of Day Care Center | 1 | 679192.9 | 563284.9 | 115908 | 506956.41 | 2nd Tranche | 203044.61 | 710001.02 | 506956.41 | 203044.61 | 100% | 100% | 175.2% | 104.5% | 100% | n/a | n/a | 2009-03-02 | 2009-06-22 | 2009-06-24 | 112 | 101 | a.) No need to request 3rd tranche b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Baking | 097303001 | Const. of Water System Level 2 (g) | 1 | 1010000 | 656047.5 | 353952.5 | 656047.5 | 3rd Tranche | 354408 | 1010455.5 | 656047.5 | 354408 | 100% | 100% | 100.1% | 100% | 100% | 2006-05-30 | 2006-07-05 | 2006-10-16 | 2007-07-13 | 2008-11-05 | 270 | 52 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Baking | 097303001 | Const. of MPDP | 1 | 345014 | 241510 | 103504 | 193208 | 1st Tranche | 106504.8 | 299712.8 | 193208 | 106504.8 | 100% | 100% | 102.9% | 86.87% | 100% | 2008-04-30 | 2008-08-28 | 2008-11-12 | 2009-01-06 | 2009-01-17 | 55 | 52 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Balukbahan | 097303002 | Construction of Multi-Purpose Building | 1 | 800000 | 560000 | 240000 | 560000 | 3rd Tranche | 215915.91 | 775915.91 | 560000 | 215915.91 | 100% | 100% | 89.96% | 96.99% | 100% | 2007-06-01 | 2007-09-04 | 2008-01-28 | 2008-04-15 | 2008-10-22 | 78 | 143 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Balukbahan | 097303002 | Const. of Day Care Center | 1 | 660000 | 462000 | 198000 | 462000 | 3rd Tranche | 198000 | 660000 | 462000 | 198000 | 100% | 100% | 100% | 100% | 100% | 2008-04-30 | 2008-08-28 | 2008-11-20 | 2009-02-27 | 2009-03-20 | 99 | 90 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Balumbunan | 097303003 | Improvement to brgy Road | 1 | 2450000 | 1666074.5 | 783925.5 | 1666074.5 | 3rd Tranche | 814525.5 | 2480600 | 1666074.5 | 814525.5 | 100% | 100% | 103.9% | 101.2% | 100% | 2007-06-01 | 2007-09-04 | 2008-06-02 | 2009-04-28 | 2009-04-28 | 330 | 118 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Bantal | 097303004 | Construction of 1 unit 2 CL School Building | 1 | 760000 | 532000 | 228000 | 532000 | 3rd Tranche | 234798.19 | 766798.19 | 532000 | 234798.19 | 100% | 100% | 103% | 100.9% | 100% | 2007-06-01 | 2007-09-04 | 2008-01-19 | 2008-12-16 | 2008-12-17 | 332 | 105 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Bobuan | 097303005 | Construction of Flea Market | 1 | 650000 | 455000 | 195000 | 455000 | 3rd Tranche | 195430 | 650430 | 455000 | 195430 | 100% | 100% | 100.2% | 100.1% | 100% | 2008-04-30 | 2008-05-02 | 2008-08-29 | 2008-12-15 | 2009-03-17 | 108 | 254 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Camp Blessing | 097303006 | Const. of Health Station | 1 | 546000 | 346690 | 199310 | 346690 | 3rd Tranche | 180034 | 526724 | 346690 | 180034 | 100% | 100% | 90.33% | 96.47% | 100% | 2006-05-30 | 2006-07-05 | 2006-11-22 | 2007-01-29 | 2007-04-20 | 68 | 74 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Canoayan | 097303007 | Const. of Health Station | 1 | 746000 | 522200 | 223800 | 417760 | 1st Tranche | 148325.93 | 566085.93 | 417760 | 148325.93 | 100% | 100% | 66.28% | 75.88% | 100% | 2008-04-30 | 2008-08-28 | 2008-10-30 | 2009-03-17 | 2009-03-20 | 138 | 221 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Conacon | 097303008 | Construction of Water System Level II | 1 | 390000 | 266000 | 124000 | 266000 | 3rd Tranche | 114940 | 380940 | 266000 | 114940 | 100% | 100% | 92.69% | 97.68% | 100% | 2007-06-01 | 2007-09-04 | 2007-11-19 | 2008-04-10 | 2008-11-10 | 143 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Dagum | 097303009 | Const. of Water System Level 2 (g) | 1 | 1300000 | 910000 | 390000 | 728000 | 3rd Tranche | 237210 | 965210 | 728000 | 237210 | 100% | 100% | 60.82% | 74.25% | 100% | 2006-05-30 | 2006-07-05 | 2006-10-17 | 2007-11-28 | 2007-12-08 | 407 | 59 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Damit | 097303010 | Const. of Day Care Center | 1 | 470400 | 322280 | 148120 | 322280 | 3rd Tranche | 148601.5 | 470881.5 | 322280 | 148601.5 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-05-30 | 2006-07-05 | 2006-10-17 | 2007-01-05 | 2007-01-15 | 80 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Damit | 097303010 | Construction of Health Station | 1 | 527000 | 364000 | 163000 | 364000 | 3rd Tranche | 163000 | 527000 | 364000 | 163000 | 100% | 100% | 100% | 100% | 100% | 2007-06-01 | 2007-09-04 | 2008-05-04 | 2008-11-11 | 2008-11-12 | 191 | 80 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Datagan | 097303011 | Construction of 1 unit 2 Classroom Elem. Sch. Building | 1 | 964660 | 675262 | 289398 | 675262 | 3rd Tranche | 289358 | 964620 | 675262 | 289358 | 100% | 100% | 99.99% | 100% | 100% | 2008-04-30 | 2008-05-02 | 2008-09-08 | 2009-02-09 | 2009-02-13 | 154 | 92 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Depase | 097303012 | Construction of Water System Level II | 1 | 810000 | 397761.5 | 412238.5 | 318209.2 | 1st Tranche | 412238.5 | 730447.7 | 318209.2 | 412238.5 | 100% | 100% | 100% | 90.18% | 100% | 2007-06-01 | 2007-09-04 | 2008-04-29 | 2008-11-28 | 2008-11-28 | 213 | 173 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Depore | 097303014 | Const. of 1 unit 2 CR Elem. Sch. Building | 1 | 840049.5 | 450000 | 390049.5 | 450000 | 3rd Tranche | 392119.97 | 842119.97 | 450000 | 392119.97 | 100% | 100% | 100.5% | 100.2% | 100% | 2007-06-01 | 2007-09-04 | 2008-05-05 | 2008-11-26 | 2008-11-27 | 205 | 48 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Deporehan | 097303013 | Day Care Center | 1 | 660000 | 462000 | 198000 | 415800 | 2nd Tranche | 196256.8 | 612056.8 | 415800 | 196256.8 | 100% | 100% | 99.12% | 92.74% | 100% | 2008-04-30 | 2008-05-02 | 2008-10-29 | 2008-12-10 | 2008-12-12 | 42 | 71 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Dimalinao | 097303015 | Rehab. Of FRM | 1 | 3199866 | 2239448 | 960418 | 2239448 | 3rd Tranche | 551372.41 | 2790820.41 | 2239448 | 551372.41 | 100% | 100% | 57.41% | 87.22% | 100% | 2006-05-30 | 2006-07-05 | 2006-12-04 | 2008-08-31 | 2008-10-10 | 636 | 93 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Dipili | 097303016 | Construction of Rice Mill | 1 | 876970 | 613879 | 263091 | 613879 | 3rd Tranche | 251145.64 | 865024.64 | 613879 | 251145.64 | 100% | 100% | 95.46% | 98.64% | 100% | 2007-06-01 | 2007-09-04 | 2007-11-08 | 2009-02-23 | 2009-03-05 | 473 | 133 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Kahayagan | 097303017 | Construction of Drainage Canal | 1 | 863870 | 563870 | 300000 | 563870 | 3rd Tranche | 300000 | 863870 | 563870 | 300000 | 100% | 100% | 100% | 100% | 100% | 2007-06-01 | 2007-06-01 | 2007-11-06 | 2008-12-30 | 2009-01-08 | 420 | 307 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Kanipaan - C2 | 097303018 | Road Concreting | 2 | 2223450 | 1556415 | 667035 | 1556415 | 3rd Tranche | 700022.5 | 2256437.5 | 1556415 | 700022.5 | 100% | 100% | 104.9% | 101.5% | 100% | 2007-06-01 | 2007-09-04 | 2008-02-26 | 2009-04-28 | 2009-04-28 | 427 | 214 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Lamare | 097303019 | Reh. Of FMR | 1 | 1261098 | 813315 | 447783 | 813315 | 3rd Tranche | 493048 | 1306363 | 813315 | 493048 | 100% | 100% | 110.1% | 103.6% | 100% | 2006-05-30 | 2006-07-05 | 2006-10-10 | 2007-03-30 | 2007-06-27 | 171 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Lamare | 097303019 | Construction of Health Station | 1 | 530000 | 350000 | 180000 | 350000 | 3rd Tranche | 180990 | 530990 | 350000 | 180990 | 100% | 100% | 100.6% | 100.2% | 100% | 2007-06-01 | 2007-09-04 | 2008-05-02 | 2008-10-30 | 2008-11-04 | 181 | 180 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Liba | 097303020 | Const. of Water System Level 2 (P) | 1 | 1657087 | 1159960 | 497127 | 1159960 | 3rd Tranche | 430907 | 1590867 | 1159960 | 430907 | 100% | 100% | 86.68% | 96% | 100% | 2006-05-30 | 2006-07-05 | 2007-03-01 | 2008-02-15 | 2008-03-15 | 351 | 93 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Liba | 097303020 | Const. of MPDP | 1 | 345014 | 241510 | 103504 | 217105.89 | 3rd Tranche | 105801.07 | 322906.96 | 217105.89 | 105801.07 | 100% | 100% | 102.2% | 93.59% | 100% | 2008-04-30 | 2008-08-28 | 2008-11-13 | 2008-12-11 | 2008-12-13 | 28 | 80 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Matin-Ao | 097303021 | Construction of 2 Units Multi-Purpose Pavement | 1 | 626210 | 438347 | 187863 | 394512.3 | 2nd Tranche | 187863 | 582375.3 | 394512.3 | 187863 | 100% | 100% | 100% | 93% | 100% | 2008-04-30 | 2008-05-02 | 2008-09-22 | 2008-12-17 | 2009-03-27 | 86 | 156 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Matun-og | 097303022 | Const. of Health Station | 1 | 726893 | 508825 | 218068 | 407060 | 1st Tranche | 142417.63 | 549477.63 | 407060 | 142417.63 | 100% | 100% | 65.31% | 75.59% | 100% | 2008-04-30 | 2008-08-28 | 2008-11-18 | 2009-03-06 | 2009-03-13 | 108 | 82 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Poblacion | 097303023 | Purchase of Fire Truck | 1 | 2400000 | 1680000 | 720000 | 1592457.4 | 3rd Tranche | 720942.6 | 2313400 | 1592457.4 | 720942.6 | 100% | 100% | 100.1% | 96.39% | 100% | 2008-04-30 | 2008-05-02 | 2008-09-30 | 2009-04-28 | 2009-04-28 | 210 | 766 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Pulang Bato | 097303024 | Rehab. Of FRM | 1 | 2385162 | 1669612 | 715550 | 1669612 | 3rd Tranche | 552734 | 2222346 | 1669612 | 552734 | 100% | 100% | 77.25% | 93.17% | 100% | 2006-05-30 | 2006-07-05 | 2006-12-14 | 2008-08-31 | 2008-11-05 | 626 | 103 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Salawagan | 097303025 | Construction of Water System Level 2 | 1 | 1450000 | 1015000 | 435000 | 913500 | 2nd Tranche | 435500 | 1349000 | 913500 | 435500 | 100% | 100% | 100.1% | 93.03% | 100% | 2008-04-30 | 2008-05-02 | 2008-10-15 | 2008-12-10 | 2008-12-15 | 56 | 172 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | San Isidro | 097303028 | Const. of Multi-Purpose Drying Pavement | 1 | 200000 | 75000 | 125000 | 75000 | 3rd Tranche | 139718.62 | 214718.62 | 75000 | 139718.62 | 100% | 100% | 111.8% | 107.4% | 100% | 2006-05-30 | 2006-07-05 | 2006-10-19 | 2007-02-15 | 2007-12-15 | 119 | 85 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | San Isidro | 097303028 | Construction of Health Station | 1 | 530000 | 364000 | 166000 | 364000 | 3rd Tranche | 166000 | 530000 | 364000 | 166000 | 100% | 100% | 100% | 100% | 100% | 2007-06-01 | 2007-09-04 | 2008-04-23 | 2008-11-10 | 2008-11-11 | 201 | 88 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Sigacad | 097303026 | Construction of Health Station | 1 | 520000 | 364000 | 156000 | 364000 | 3rd Tranche | 161550.31 | 525550.31 | 364000 | 161550.31 | 100% | 100% | 103.6% | 101.1% | 100% | 2007-06-01 | 2007-09-04 | 2008-01-28 | 2008-04-04 | 2008-10-22 | 67 | 115 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Sigacad | 097303026 | Const. of Rice Mill bldg. fabrication & installation of milling machine & accessories | 1 | 1146300 | 802410 | 343890 | 802410 | 3rd Tranche | 343260 | 1145670 | 802410 | 343260 | 100% | 100% | 99.82% | 99.95% | 100% | 2008-04-30 | 2008-08-28 | 2008-10-30 | 2009-03-20 | 2009-03-27 | 141 | 115 | MDC/ Expanded MIBF Resolution no. 04 dated 8/28/2008 | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Bayog | 097303 | Supon - C2 | 097303027 | Road Concreting | 2 | 2223450 | 1556415 | 667035 | 1556415 | 3rd Tranche | 700022.5 | 2256437.5 | 1556415 | 700022.5 | 100% | 100% | 104.9% | 101.5% | 100% | 2007-06-01 | 2007-09-04 | 2008-02-26 | 2009-04-28 | 2009-04-28 | 427 | 214 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Bacawan | 097306001 | Reh. Of FMR | 1 | 4646000 | 2341000 | 2305000 | 2341000 | 3rd Tranche | 937423.58 | 3278423.58 | 2341000 | 937423.58 | 100% | 100% | 40.67% | 70.56% | 100% | 2005-04-13 | 2005-06-02 | 2005-08-10 | 2007-02-28 | 2007-03-09 | 567 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Bacawan | 097306001 | Construction of Health Station | 1 | 664938.09 | 464155 | 200783.09 | 464155 | 3rd Tranche | 200783.09 | 664938.09 | 464155 | 200783.09 | 100% | 100% | 100% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-08 | 2007-11-30 | 2007-12-18 | 83 | 75 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Beray | 097306003 | Const. of Brgy. Water System 2 (g) | 1 | 1310000 | 904900 | 405100 | 904900 | 3rd Tranche | 409320 | 1314220 | 904900 | 409320 | 100% | 100% | 101% | 100.3% | 100% | 2006-05-30 | 2006-06-30 | 2006-09-29 | 2007-02-28 | no data | 152 | 145 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Beray | 097306003 | Construction of Health Station | 1 | 673576.08 | 433969 | 239607.08 | 433969 | 3rd Tranche | 239607.09 | 673576.09 | 433969 | 239607.09 | 100% | 100% | 100% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-06-14 | 2007-11-30 | 2007-12-18 | 169 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Don Jose | 097306032 | Const. of School Building | 1 | 566118.6 | 396223 | 169895.6 | 396223 | 3rd Tranche | 170095.63 | 566318.63 | 396223 | 170095.63 | 100% | 100% | 100.1% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-10-23 | 2008-01-23 | 2008-05-20 | 92 | 198 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Dongos | 097306004 | Concreting of Brgy. Road | 1 | 1441916 | 917416 | 524500 | 917416 | 3rd Tranche | 505524.4 | 1422940.4 | 917416 | 505524.4 | 100% | 100% | 96.38% | 98.68% | 100% | 2005-04-13 | 2005-06-02 | 2005-10-06 | 2006-06-30 | 2006-09-15 | 267 | 169 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | East Migpulao | 097306015 | Rehab. Of FRM | 1 | 3312112 | 2091528 | 1220584 | 2091528 | 3rd Tranche | 1220583.92 | 3312111.92 | 2091528 | 1220583.92 | 100% | 100% | 100% | 100% | 100% | 2006-05-30 | 2006-06-30 | 2006-10-11 | 2008-03-30 | no data | 536 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Guinicolalay | 097306005 | Rehab. Of FRM | 1 | 1693825 | 1160085 | 533740 | 1160085 | 3rd Tranche | 421564.56 | 1581649.56 | 1160085 | 421564.56 | 100% | 100% | 78.98% | 93.38% | 100% | 2006-05-30 | 2006-06-30 | 2006-10-11 | 2007-08-17 | 2007-11-26 | 310 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Ignacio Garata | 097306018 | Const. of Water System Level 2 (P) | 1 | 1676780 | 1173746 | 503034 | 1173746 | 3rd Tranche | 503034 | 1676780 | 1173746 | 503034 | 100% | 100% | 100% | 100% | 100% | 2006-05-30 | 2006-06-30 | 2006-09-19 | 2007-08-12 | 2007-08-24 | 327 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Kinacap | 097306006 | Rehab. Of Water System Level 2 (G) | 1 | 1030000 | 716657 | 313343 | 716657 | 3rd Tranche | 276138 | 992795 | 716657 | 276138 | 100% | 100% | 88.13% | 96.39% | 100% | 2006-05-30 | 2006-06-30 | 2006-10-18 | 2007-02-02 | 2007-12-19 | 107 | 136 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Legarda 3 | 097306008 | Concreting of Brgy Road | 1 | 738105 | 459250 | 278855 | 459250 | 3rd Tranche | 346480 | 805730 | 459250 | 346480 | 100% | 100% | 124.3% | 109.2% | 100% | 2005-04-13 | 2005-06-02 | 2005-08-12 | 2006-04-27 | 2006-05-19 | 258 | 250 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Legarda Dos | 097306007 | Const. of Flea Market | 1 | 780688.19 | 546459 | 234229.19 | 419302.85 | 1st Tranche | 225536.6 | 644839.45 | 419302.85 | 225536.6 | 100% | 100% | 96.29% | 82.6% | 100% | 2007-05-23 | 2007-06-06 | 2007-11-23 | 2008-03-24 | 2008-04-04 | 122 | 308 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Legarda Uno | 097306009 | Rehab. Of FRM | 1 | 2119176 | 1446257 | 672919 | 1446257 | 3rd Tranche | 690067.21 | 2136324.21 | 1446257 | 690067.21 | 100% | 100% | 102.5% | 100.8% | 100% | 2006-05-30 | 2006-06-30 | 2006-10-11 | 2007-06-30 | 2007-11-08 | 262 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Legarda Uno | 097306009 | Brgy Road Improvement | 1 | 1227449.8 | 858365 | 369084.8 | 858365 | 3rd Tranche | 237641.94 | 1096006.94 | 858365 | 237641.94 | 100% | 100% | 64.39% | 89.29% | 100% | 2007-05-23 | 2007-06-06 | 2007-12-03 | 2009-04-02 | no data | 486 | 30 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Lucoban | 097306012 | Brgy Road Improvement | 1 | 1156045.44 | 803140 | 352905.44 | 803140 | 3rd Tranche | 352905.44 | 1156045.44 | 803140 | 352905.44 | 100% | 100% | 100% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-24 | 2007-12-15 | 2007-12-19 | 82 | 92 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Lower Dimaya | 097306013 | Const. of Day Care Center | 1 | 546765.36 | 379512 | 167253.36 | 365433.41 | 3rd Tranche | 182636.86 | 548070.27 | 365433.41 | 182636.86 | 100% | 100% | 109.2% | 100.2% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-08 | 2007-12-08 | no data | 91 | 50 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Ludiong | 097306014 | Construction of Health Station | 1 | 673576.08 | 470793 | 202783.08 | 470793 | 3rd Tranche | 208683.09 | 679476.09 | 470793 | 208683.09 | 100% | 100% | 102.9% | 100.9% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-12 | 2007-09-22 | 2007-12-17 | 10 | 110 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Nangka | 097306017 | Const. of Multi-Purpose Building | 1 | 701551.63 | 491283 | 210268.63 | 491283 | 3rd Tranche | 210268.63 | 701551.63 | 491283 | 210268.63 | 100% | 100% | 100% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-12 | 2007-12-30 | 2007-12-31 | 109 | 114 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Nian | 097306034 | Const. of School Building | 1 | 601535 | 420939 | 180596 | 420939 | 3rd Tranche | 180595.63 | 601534.63 | 420939 | 180595.63 | 100% | 100% | 100% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-15 | 2007-11-28 | 2007-12-30 | 74 | 206 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Old Mirapao | 097306019 | Const. of Day Care Center | 1 | 560708.36 | 392420 | 168288.36 | 392420 | 3rd Tranche | 183321.36 | 575741.36 | 392420 | 183321.36 | 100% | 100% | 108.9% | 102.7% | 100% | 2007-05-23 | 2007-06-06 | 2007-08-08 | 2007-11-08 | 2008-05-13 | 92 | 258 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Pisa-an | 097306031 | Health Station | 1 | 480000 | 200000 | 280000 | 200000 | 3rd Tranche | 267250 | 467250 | 200000 | 267250 | 100% | 100% | 95.45% | 97.34% | 100% | 2005-04-13 | 2005-06-02 | 2005-08-08 | 2007-11-30 | no data | 844 | 185 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Poblacion | 097306020 | Rehab. Of FRM | 1 | 2169253 | 1506827 | 662426 | 1506827 | 3rd Tranche | 662376.03 | 2169203.03 | 1506827 | 662376.03 | 100% | 100% | 99.99% | 100% | 100% | 2006-05-30 | 2006-06-30 | 2006-10-13 | 2007-01-13 | 2007-12-01 | 92 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Proper Dimaya | 097306021 | Brgy Road Improvement | 1 | 880377.43 | 613517 | 266860.43 | 613517 | 3rd Tranche | 275091.09 | 888608.09 | 613517 | 275091.09 | 100% | 100% | 103.1% | 100.9% | 100% | 2007-05-23 | 2007-06-06 | 2007-12-22 | 2008-03-26 | 2008-04-16 | 95 | 72 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Sagacad | 097306022 | Const. of Barangay Health Station | 1 | 661111.25 | 463099 | 198012.25 | 463099 | 3rd Tranche | 198012 | 661111 | 463099 | 198012 | 100% | 100% | 100% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-12-14 | 2008-03-06 | 2008-06-12 | 83 | 320 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Sambulawan | 097306023 | Expan. Of Water System Level 2 (G) | 1 | 1191000 | 503600 | 687400 | 503600 | 3rd Tranche | 787661.4 | 1291261.4 | 503600 | 787661.4 | 100% | 100% | 114.6% | 108.4% | 100% | 2005-04-13 | 2005-06-02 | 2005-09-21 | 2006-10-30 | 2006-12-14 | 404 | 170 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Sambulawan | 097306023 | Construction of Health Station | 1 | 647663.09 | 453119 | 194544.09 | 436574.15 | 3rd Tranche | 194544.09 | 631118.24 | 436574.15 | 194544.09 | 100% | 100% | 100% | 97.45% | 100% | 2007-05-23 | 2007-06-06 | 2007-07-14 | 2007-11-30 | 2007-12-18 | 139 | 170 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | San Isidro | 097306024 | Reh. Of FMR | 1 | 4241000 | 1685740 | 2555260 | 1685740 | 3rd Tranche | 781056 | 2466796 | 1685740 | 781056 | 100% | 100% | 30.57% | 58.17% | 100% | 2005-04-13 | 2005-06-02 | 2005-08-29 | 2006-11-30 | 2007-02-27 | 458 | 84 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Sumpotan | 097306026 | Construction of Health Station | 1 | 673576.08 | 470593 | 202983.08 | 470593 | 3rd Tranche | 203144 | 673737 | 470593 | 203144 | 100% | 100% | 100.1% | 100% | 100% | 2007-05-23 | 2007-06-06 | 2007-10-30 | 2007-11-30 | 2007-12-18 | 31 | 220 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Tarakan | 097306028 | Const. of Day Care Center | 1 | 602013.91 | 421453 | 180560.91 | 404115.56 | 3rd Tranche | 180560.91 | 584676.47 | 404115.56 | 180560.91 | 100% | 100% | 100% | 97.12% | 100% | 2007-05-23 | 2007-06-06 | 2007-09-22 | 2007-11-30 | 2007-12-03 | 69 | 50 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Upper Dimaya | 097306029 | Reh. Of FMR | 1 | 1791000 | 1014200 | 776800 | 1014200 | 3rd Tranche | 779300 | 1793500 | 1014200 | 779300 | 100% | 100% | 100.3% | 100.1% | 100% | 2005-04-13 | 2005-06-02 | 2005-08-10 | 2007-01-31 | 2007-02-28 | 539 | 196 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Upper Sibul | 097306030 | Reh. Of FMR | 1 | 1991000 | 985000 | 1006000 | 985000 | 3rd Tranche | 459037.25 | 1444037.25 | 985000 | 459037.25 | 100% | 100% | 45.63% | 72.53% | 100% | 2005-04-13 | 2005-06-02 | 2005-08-03 | 2007-01-30 | 2007-02-24 | 545 | 126 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | Upper Sibul | 097306030 | Const of Water System Level 2 | 1 | 1316115.5 | 920961.3 | 395154.2 | 920961.3 | 3rd Tranche | 394659.66 | 1315620.96 | 920961.3 | 394659.66 | 100% | 100% | 99.87% | 99.96% | 100% | 2007-05-23 | 2007-06-06 | 2007-10-30 | 2008-03-01 | 2009-05-08 | 123 | 128 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dinas | 097306 | West Migpulao | 097306016 | Expan. Of Water System Level 2 (P) | 1 | 1462334 | 878739 | 583595 | 878739 | 3rd Tranche | 520382.8 | 1399121.8 | 878739 | 520382.8 | 100% | 100% | 89.17% | 95.68% | 100% | 2005-04-13 | 2005-06-02 | 2005-07-28 | 2006-09-15 | 2006-11-28 | 414 | 102 | With change order | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Bagong Silang | 097308047 | Rehab of brgy. Bagong Silang Road | 1 | 3792667 | 2025984 | 1766683 | 1943441.28 | 3rd Tranche | 1761853 | 3705294.28 | 1943441.28 | 1761853 | 100% | 100% | 99.73% | 97.7% | 100% | 2006-05-22 | 2006-06-30 | 2006-07-24 | 2008-11-08 | 2009-04-30 | 838 | 140 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Bagong Valencia | 097308002 | Rehab./Exp. Of Water System Level 2 | 1 | 2461954 | 1301900 | 1160054 | 1301900 | 3rd Tranche | 1185524 | 2487424 | 1301900 | 1185524 | 100% | 100% | 102.2% | 101% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-08 | 2006-03-21 | 2006-03-25 | 225 | 250 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Bucayan | 097308003 | C onst. Of FMR | 1 | 2472000 | 1189550 | 1282450 | 1189550 | 3rd Tranche | 2050878.2 | 3240428.2 | 1189550 | 2050878.2 | 100% | 100% | 159.9% | 131.1% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-02 | 2006-04-04 | 2006-04-04 | 245 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Canibongan - C2 | 097308051 | Rehab. Of FMR | 2 | 4635000 | 2445000 | 2190000 | 2445000 | 3rd Tranche | 1633351.65 | 4078351.65 | 2445000 | 1633351.65 | 100% | 100% | 74.58% | 87.99% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-04 | 2006-12-30 | 2009-05-18 | 513 | 218 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Danlugan | 097308006 | Improvement/Rehabiliation of Brgy Danlugan Road | 1 | 2439939 | 1230000 | 1209939 | 1107000 | 2nd Tranche | 151000 | 1258000 | 1107000 | 151000 | 100% | 100% | 12.48% | 51.56% | 100% | 2007-05-21 | 2007-06-20 | 2007-10-08 | 2009-10-31 | no data | 754 | 117 | completed as built | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Dapiwak | 097308048 | Construction of Water System L-II (G) | 1 | 1597395 | 974070 | 623325 | 964063.81 | 3rd Tranche | 645790.67 | 1609854.48 | 964063.81 | 645790.67 | 100% | 100% | 103.6% | 100.8% | 100% | 2007-05-21 | 2007-06-20 | 2008-03-17 | 2009-04-23 | 2009-04-29 | 402 | 240 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Datu Totocan | 097308007 | Rehab of brgy. Datu Tutukan Road | 1 | 2431439 | 1230000 | 1201439 | 1230000 | 3rd Tranche | 839651.5 | 2069651.5 | 1230000 | 839651.5 | 100% | 100% | 69.89% | 85.12% | 100% | 2006-05-22 | 2006-06-30 | 2006-08-15 | 2009-04-28 | 2009-04-28 | 987 | 120 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Dilud | 097308008 | Construction of Health Station | 1 | 574594.38 | 313168.88 | 261425.5 | 313168.88 | 3rd Tranche | 174565.73 | 487734.61 | 313168.88 | 174565.73 | 100% | 100% | 66.77% | 84.88% | 100% | 2007-05-21 | 2007-06-20 | 2007-11-07 | 2009-02-27 | 2009-03-23 | 478 | 134 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Dulian | 097308010 | Construction of Day Care Center | 1 | 957879.25 | 412605.23 | 545274.02 | 412605.23 | 3rd Tranche | 284512.77 | 697118 | 412605.23 | 284512.77 | 100% | 100% | 52.18% | 72.78% | 100% | 2007-05-21 | 2007-06-20 | 2008-07-15 | 2009-03-02 | 2009-04-07 | 230 | 75 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Dulop | 097308011 | Construction of Brgy Dulop School Lab Building | 1 | 616419 | 407919 | 208500 | 407919 | 3rd Tranche | 250028 | 657947 | 407919 | 250028 | 100% | 100% | 119.9% | 106.7% | 100% | 2005-04-14 | 2005-06-10 | 2005-09-13 | 2006-04-09 | 2006-04-11 | 208 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Gumpingan | 097308014 | Rehab of Junction road | 1 | 2392485 | 1288000 | 1104485 | 1159200 | 2nd Tranche | 632151.37 | 1791351.37 | 1159200 | 632151.37 | 100% | 100% | 57.23% | 74.87% | 100% | 2006-05-22 | 2006-06-30 | 2006-08-28 | 2007-06-30 | 2008-11-28 | 306 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | La Fortuna | 097308015 | Rehab of Farm to brgy La Fortuna Road | 1 | 2234050 | 1191100 | 1042950 | 1191100 | 3rd Tranche | 750780 | 1941880 | 1191100 | 750780 | 100% | 100% | 71.99% | 86.92% | 100% | 2006-05-22 | 2006-06-30 | 2006-08-28 | 2007-05-30 | 2007-11-05 | 275 | 140 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Labangon | 097308049 | Rehab of brgy. Labangon Road | 1 | 5497502 | 2923800 | 2573702 | 2631420 | 2nd Tranche | 1049821 | 3681241 | 2631420 | 1049821 | 100% | 100% | 40.79% | 66.96% | 100% | 2006-05-22 | 2006-06-30 | 2006-10-17 | 2009-10-29 | no data | 1108 | 165 | completed as built | 1
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Libertad | 097308016 | Construction of Water System L-II (P) | 1 | 2070398.82 | 1429363.82 | 641035 | 1404112.13 | 3rd Tranche | 654353.16 | 2058465.29 | 1404112.13 | 654353.16 | 100% | 100% | 102.1% | 99.42% | 100% | 2007-05-21 | 2007-06-20 | 2008-02-18 | 2009-01-15 | 2009-01-21 | 332 | 240 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Lipawan | 097308018 | Const. of Health Station | 1 | 585551.88 | 287551.88 | 298000 | 287551.88 | 3rd Tranche | 307460.79 | 595012.67 | 287551.88 | 307460.79 | 100% | 100% | 103.2% | 101.6% | 100% | 2007-05-21 | 2007-06-20 | 2007-11-07 | 2009-03-04 | 2009-03-25 | 483 | 134 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Lower Landing | 097308019 | Construction of Water System L-II (P) | 1 | 1413859 | 838084 | 575775 | 838084 | 3rd Tranche | 389109.93 | 1227193.93 | 838084 | 389109.93 | 100% | 100% | 67.58% | 86.8% | 100% | 2007-05-21 | 2007-06-20 | 2007-08-10 | 2009-03-27 | 2009-04-30 | 595 | 320 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Macasing | 097308021 | Rehab. Of FMR | 1 | 1954950 | 1015000 | 939950 | 1015000 | 3rd Tranche | 942178 | 1957178 | 1015000 | 942178 | 100% | 100% | 100.2% | 100.1% | 100% | 2005-04-14 | 2005-06-10 | 2005-10-04 | 2006-02-02 | 2006-02-15 | 121 | 99 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Mahayahay | 097308022 | Const. of Water System Level 2 | 1 | 2269634 | 1445584 | 824050 | 1445584 | 3rd Tranche | 852230 | 2297814 | 1445584 | 852230 | 100% | 100% | 103.4% | 101.2% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-11 | 2006-02-28 | 2006-02-28 | 201 | 180 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Manlabay | 097308024 | Construction of Water System L-II | 1 | 2040398.82 | 1409363.82 | 631035 | 1390968.17 | 3rd Tranche | 632551.81 | 2023519.98 | 1390968.17 | 632551.81 | 100% | 100% | 100.2% | 99.17% | 100% | 2007-05-21 | 2007-06-20 | 2008-02-29 | 2009-05-04 | 2009-05-15 | 430 | 240 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Marangan | 097308026 | Rehab. Of FMR | 1 | 1476880 | 766440 | 710440 | 766440 | 3rd Tranche | 844540 | 1610980 | 766440 | 844540 | 100% | 100% | 118.9% | 109.1% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-11 | 2006-10-31 | 2006-11-10 | 446 | 152 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | New Basak | 097308027 | Const. of Health Station | 1 | 495720 | 223892 | 271828 | 223892 | 3rd Tranche | 277215 | 501107 | 223892 | 277215 | 100% | 100% | 102% | 101.1% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-09 | 2005-12-10 | 2005-12-13 | 123 | 198 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Saad | 097308032 | Const of Brgy Saad Road | 1 | 3850000 | 2230000 | 1620000 | 2229740.37 | 3rd Tranche | 971600 | 3201340.37 | 2229740.37 | 971600 | 100% | 100% | 59.98% | 83.15% | 100% | 2006-05-22 | 2006-06-30 | 2006-09-28 | 2009-08-28 | 2009-09-03 | 1065 | 110 | completed as built | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Salvador | 097308033 | Construction of Water System L-II | 1 | 2336501 | 1610431 | 726070 | 1280344.8 | 1st Tranche | 731246.3 | 2011591.1 | 1280344.8 | 731246.3 | 100% | 100% | 100.7% | 86.09% | 100% | 2007-05-21 | 2007-06-20 | 2007-11-08 | 2009-02-24 | 2009-02-24 | 474 | 90 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Juan | 097308050 | Rehab. Of FMR | 1 | 1686000 | 1006200 | 679800 | 1006200 | 3rd Tranche | 717716.82 | 1723916.82 | 1006200 | 717716.82 | 100% | 100% | 105.6% | 102.2% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-08 | 2006-03-22 | 2006-03-24 | 226 | 165 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Pablo | 097308034 | Const. of MPB | 1 | 2212410 | 1496550 | 715860 | 1496550 | 3rd Tranche | 792721 | 2289271 | 1496550 | 792721 | 100% | 100% | 110.7% | 103.5% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-05 | 2006-01-16 | 2006-04-11 | 164 | 425 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | San Vicente | 097308037 | Barangay Road Improvement | 1 | 2907764.5 | 1689400 | 1218364.5 | 1689258.18 | 3rd Tranche | 939864 | 2629122.18 | 1689258.18 | 939864 | 100% | 100% | 77.14% | 90.42% | 100% | 2007-05-21 | 2007-06-20 | 2007-10-23 | 2009-06-25 | 2009-06-25 | 611 | 75 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Senote | 097308038 | Rehab of brgy. Senote Road | 1 | 3547590 | 1842660 | 1704930 | 1658394 | 2nd Tranche | 1028491.5 | 2686885.5 | 1658394 | 1028491.5 | 100% | 100% | 60.32% | 75.74% | 100% | 2006-05-22 | 2006-06-30 | 2006-08-24 | 2009-04-30 | 2009-04-30 | 980 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Sunop | 097308041 | 2 CR School Building | 1 | 778456 | 468456 | 310000 | 468456 | 3rd Tranche | 463469.86 | 931925.86 | 468456 | 463469.86 | 100% | 100% | 149.5% | 119.7% | 100% | 2006-05-22 | 2006-06-30 | 2006-09-21 | 2007-08-29 | 2007-08-29 | 342 | 120 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Tagun | 097308042 | Const. of Water System Level 2 | 1 | 788120 | 355925 | 432195 | 355925 | 3rd Tranche | 433195 | 789120 | 355925 | 433195 | 100% | 100% | 100.2% | 100.1% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-09 | 2006-03-20 | 2006-03-23 | 223 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Tamurayan | 097308043 | Barangay Tamurayan Road Rehabilitation | 1 | 2310912 | 1447575 | 863337 | 1447575 | 3rd Tranche | 701586.75 | 2149161.75 | 1447575 | 701586.75 | 100% | 100% | 81.26% | 93% | 100% | 2007-05-21 | 2007-06-20 | 2008-03-20 | 2009-06-16 | 2009-06-26 | 453 | 79 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Upper Landing | 097308045 | Const. of Water System Level 2 | 1 | 2505797 | 1546040 | 959757 | 1546040 | 3rd Tranche | 971900 | 2517940 | 1546040 | 971900 | 100% | 100% | 101.3% | 100.5% | 100% | 2005-04-14 | 2005-06-10 | 2005-08-10 | 2006-01-19 | 2006-01-19 | 162 | 160 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Dumingag | 097308 | Upper Timonan | 097308046 | Construction of Multi Purpose Building | 1 | 1053148 | 723740.5 | 329407.5 | 723740.5 | 3rd Tranche | 380540.78 | 1104281.28 | 723740.5 | 380540.78 | 100% | 100% | 115.5% | 104.9% | 100% | 2007-05-21 | 2007-06-20 | 2008-03-21 | 2009-01-23 | 2009-01-27 | 308 | 299 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bagong Kahayag | 097333002 | Const. of 0.51km FMR w/ Concrete Footbridge | 1 | 950846 | 615490 | 335356 | 615490 | 3rd Tranche | 467152 | 1082642 | 615490 | 467152 | 100% | 100% | 139.3% | 113.9% | 100% | 2006-05-25 | 2006-06-26 | 2006-09-04 | 2007-02-28 | 2007-08-14 | 177 | 130 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bagong Kahayag | 097333002 | Const. of concrete footbridge & River Control & Concrete Pathway | 1 | 551330.3 | 385930 | 165400.3 | 354113.3 | 3rd Tranche | 167900.31 | 522013.61 | 354113.3 | 167900.31 | 100% | 100% | 101.5% | 94.68% | 100% | 2007-05-16 | 2007-05-31 | 2007-10-25 | 2008-03-10 | 2008-06-04 | 137 | 379 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bagong Kahayag | 097333002 | Construction of Flea Market | 1 | 1101175 | 763000 | 338175 | 763000 | 3rd Tranche | 339505 | 1102505 | 763000 | 339505 | 100% | 100% | 100.4% | 100.1% | 100% | 2008-04-23 | 2008-04-29 | 2008-08-30 | 2009-07-10 | 2009-08-24 | 314 | 386 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Baking | 097333001 | Const. of Health Station | 1 | 589151.95 | 406000 | 183151.95 | 406000 | 3rd Tranche | 197572.86 | 603572.86 | 406000 | 197572.86 | 100% | 100% | 107.9% | 102.4% | 100% | 2007-05-16 | 2007-05-31 | 2007-11-22 | 2008-06-10 | 2008-10-28 | 201 | 242 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Baking | 097333001 | Construction of Day Care Center | 1 | 616800 | 427000 | 189800 | 384300 | 2nd Tranche | 190900 | 575200 | 384300 | 190900 | 100% | 100% | 100.6% | 93.26% | 100% | 2008-04-23 | 2008-04-29 | 2008-08-30 | 2009-05-20 | 2009-05-20 | 263 | 35 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Biswangan | 097333003 | Improvement to brgy Road | 1 | 1302202.6 | 902000 | 400202.6 | 837070 | 3rd Tranche | 398982.24 | 1236052.24 | 837070 | 398982.24 | 100% | 100% | 99.7% | 94.92% | 100% | 2007-05-16 | 2007-05-31 | 2008-02-25 | 2009-05-10 | 2009-05-11 | 440 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bululawan | 097333004 | Rehab of 2km Bululawan-Sinungan Road | 1 | 1863440 | 1109834 | 753606 | 1109834 | 3rd Tranche | 423886 | 1533720 | 1109834 | 423886 | 100% | 100% | 56.25% | 82.31% | 100% | 2006-05-25 | 2006-06-26 | 2006-09-04 | 2007-01-31 | 2008-03-24 | 149 | 110 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Bululawan | 097333004 | Const. of Health Station | 1 | 596151.95 | 410900 | 185251.95 | 410900 | 3rd Tranche | 196368.12 | 607268.12 | 410900 | 196368.12 | 100% | 100% | 106% | 101.9% | 100% | 2007-05-16 | 2007-05-31 | 2007-10-16 | 2008-03-10 | 2008-06-24 | 146 | 230 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Dagum | 097333005 | Const. of 1.98km Dagum FMR | 1 | 2767787 | 1531715 | 1236072 | 1531715 | 3rd Tranche | 1469312.73 | 3001027.73 | 1531715 | 1469312.73 | 100% | 100% | 118.9% | 108.4% | 100% | 2006-05-25 | 2006-06-26 | 2007-04-02 | 2009-02-25 | 2009-03-18 | 695 | 110 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Gasa | 097333006 | Construction of Hanging FootBridge | 1 | 959000 | 659400 | 299600 | 658758.75 | 3rd Tranche | 283030 | 941788.75 | 658758.75 | 283030 | 100% | 100% | 94.47% | 98.21% | 100% | 2008-04-23 | 2008-04-29 | 2008-08-23 | 2008-11-28 | 2008-12-16 | 97 | 110 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Gatub | 097333007 | Const/Rehab of Gatub Water System | 1 | 805962 | 520562 | 285400 | 520562 | 3rd Tranche | 502900 | 1023462 | 520562 | 502900 | 100% | 100% | 176.2% | 127% | 100% | 2006-05-25 | 2006-06-26 | 2006-09-04 | 2007-02-12 | 2007-09-06 | 161 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Gatub | 097333007 | Const. of Day Care Center | 1 | 559151.95 | 382000 | 177151.95 | 343800 | 2nd Tranche | 176236.76 | 520036.76 | 343800 | 176236.76 | 100% | 100% | 99.48% | 93% | 100% | 2007-05-16 | 2007-05-31 | 2007-12-03 | 2008-09-30 | 2008-11-04 | 302 | 40 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Lukuan | 097333009 | Conts. Of Water System Level ll | 1 | 717431.3 | 497900 | 219531.3 | 478045.77 | 3rd Tranche | 218881.3 | 696927.07 | 478045.77 | 218881.3 | 100% | 100% | 99.7% | 97.14% | 100% | 2007-05-16 | 2007-05-31 | 2007-10-17 | 2008-03-16 | 2008-07-16 | 151 | 81 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Matalang | 097333010 | Construction of Health Station | 1 | 823250 | 570500 | 252750 | 568305.31 | 3rd Tranche | 228100 | 796405.31 | 568305.31 | 228100 | 100% | 100% | 90.25% | 96.74% | 100% | 2008-04-23 | 2008-04-29 | 2008-08-30 | 2008-11-30 | 2008-12-12 | 92 | 104 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Sapang Pinoles | 097333011 | Const/Rehab of Pinoles Water System | 1 | 656399 | 422399 | 234000 | 422399 | 3rd Tranche | 256500 | 678899 | 422399 | 256500 | 100% | 100% | 109.6% | 103.4% | 100% | 2006-05-25 | 2006-06-26 | 2006-09-04 | 2007-03-30 | 2007-10-04 | 207 | 100 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Sapang Pinoles | 097333011 | Construction of Health Station | 1 | 703000 | 492100 | 210900 | 492100 | 3rd Tranche | 212230 | 704330 | 492100 | 212230 | 100% | 100% | 100.6% | 100.2% | 100% | 2008-04-23 | 2008-04-29 | 2008-08-30 | 2008-12-15 | 2009-06-16 | 107 | 110 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Poblacion | 097333008 | Construction of Flea Market | 1 | 419375 | 290500 | 128875 | 290058.3 | 3rd Tranche | 165722.5 | 455780.8 | 290058.3 | 165722.5 | 100% | 100% | 128.6% | 108.7% | 100% | 2008-04-23 | 2008-04-29 | 2008-07-10 | 2008-10-11 | 2008-12-19 | 93 | 759 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Sibuguey | 097333012 | Const/Improvement of Water System Level 2 | 1 | 1243532.6 | 857340 | 386192.6 | 796694.4 | 3rd Tranche | 380302.34 | 1176996.74 | 796694.4 | 380302.34 | 100% | 100% | 98.47% | 94.65% | 100% | 2007-05-16 | 2007-05-31 | 2008-02-27 | 2008-08-15 | 2008-08-27 | 170 | 84 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Tiwales | 097333013 | Const./Improvement of Water System Level 2 | 1 | 517431.3 | 357930 | 159501.3 | 353119.4 | 3rd Tranche | 154301.3 | 507420.7 | 353119.4 | 154301.3 | 100% | 100% | 96.74% | 98.07% | 100% | 2007-05-16 | 2007-05-31 | 2007-10-18 | 2008-03-16 | 2008-08-20 | 150 | 81 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lakewood | 097333 | Tubod | 097333014 | Improvement of Water System Level 2 | 1 | 1428670 | 997500 | 431170 | 993335.1 | 3rd Tranche | 424720 | 1418055.1 | 993335.1 | 424720 | 100% | 100% | 98.5% | 99.26% | 100% | 2008-04-23 | 2008-04-29 | 2008-08-30 | 2008-12-11 | 2008-12-11 | 103 | 75 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Bulawan | 097313002 | School Building | 1 | 361598 | 230162 | 131436 | 230162 | 3rd Tranche | 131551.5 | 361713.5 | 230162 | 131551.5 | 100% | 100% | 100.1% | 100% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-03 | 2004-06-30 | 2004-07-15 | 119 | 150 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Bulawan | 097313002 | Construction of Multi-Purpose Center | 1 | 761300 | 579580 | 181720 | 521622 | 2nd Tranche | 187920 | 709542 | 521622 | 187920 | 100% | 100% | 103.4% | 93.2% | 100% | n/a | n/a | 2009-03-20 | 2009-06-17 | 2009-06-26 | 89 | 252 | a.) No need to request 3rd tranch b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Carpoc | 097313003 | Water System L-II | 1 | 438080.5 | 214175.46 | 223905.04 | 214175.46 | 3rd Tranche | 189484 | 403659.46 | 214175.46 | 189484 | 100% | 100% | 84.63% | 92.14% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-15 | 2005-03-18 | non-functional | 368 | 80 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Carpoc | 097313003 | Construction of Multi-Purpose Center | 1 | 796190 | 623470 | 172720 | 561123 | 2nd Tranche | 199800 | 760923 | 561123 | 199800 | 100% | 100% | 115.7% | 95.57% | 100% | n/a | n/a | 2009-03-14 | 2009-05-30 | 2009-06-28 | 77 | 268 | a.) No need to request 3rd tranch b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Danganan | 097313004 | Spring Development Water System (Level-II) | 1 | 406520.25 | 233271 | 173249.25 | 233271 | 3rd Tranche | 184302.5 | 417573.5 | 233271 | 184302.5 | 100% | 100% | 106.4% | 102.7% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-15 | 2004-09-10 | 2004-09-13 | 179 | 125 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Danganan | 097313004 | Construction of Multi-Purpose Center | 1 | 771800 | 594850 | 176950 | 584378.11 | 2nd Tranche | 206483.63 | 790861.74 | 584378.11 | 206483.63 | 100% | 100% | 116.7% | 102.5% | 100% | n/a | n/a | 2009-03-31 | 2009-06-22 | 2009-07-04 | 83 | 190 | Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Dansal | 097313005 | Road Rehabilitation | 1 | 3820850 | 2636376 | 1184474 | 2636376 | 3rd Tranche | 939026.5 | 3575402.5 | 2636376 | 939026.5 | 100% | 100% | 79.28% | 93.58% | 100% | 2005-05-30 | 2005-07-29 | 2005-11-01 | 2006-09-15 | 2006-12-30 | 318 | 200 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Dansal | 097313005 | Construction of 1 Unit Classroom Bldg | 1 | 613600 | 471979 | 141621 | 424781.1 | 2nd Tranche | 146722 | 571503.1 | 424781.1 | 146722 | 100% | 100% | 103.6% | 93.14% | 100% | n/a | n/a | 2009-03-16 | 2009-05-30 | 2009-07-08 | 75 | 114 | a.) No need to request 3rd tranch b.) Closed Account | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Dumara | 097313007 | Rehab of Farm to Market Road | 1 | 1458924.5 | 729665 | 729259.5 | 729665 | 3rd Tranche | 1278286 | 2007951 | 729665 | 1278286 | 100% | 100% | 175.3% | 137.6% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-01 | 2006-07-30 | 2006-10-16 | 881 | 154 |  | 1 | LUZON
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Dumara | 097313007 | Construction of Day Care Center | 1 | 676700 | 547950 | 128750 | 493155 | 2nd Tranche | 165050 | 658205 | 493155 | 165050 | 100% | 100% | 128.2% | 97.27% | 100% | n/a | n/a | 2009-03-19 | 2009-06-11 | 2009-06-26 | 84 | 35 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Linokmadalum | 097313010 | Construction of Mini Warf | 1 | 316031.3 | 185774.99 | 130256.31 | 185774.99 | 3rd Tranche | 133932 | 319706.99 | 185774.99 | 133932 | 100% | 100% | 102.8% | 101.2% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-21 | 2004-10-17 | 2004-12-27 | 210 | 160 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Linokmadalum | 097313010 | Construction of Pathway Concreting | 1 | 766900 | 536830 | 230070 | 536830 | 3rd Tranche | 303100 | 839930 | 536830 | 303100 | 100% | 100% | 131.7% | 109.5% | 100% | n/a | n/a | 2009-03-11 | 2009-05-30 | 2009-06-29 | 80 | 174 | Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Luanan | 097313011 | Water System L-II | 1 | 438183 | 240323.36 | 197859.64 | 240323.36 | 3rd Tranche | 187205 | 427528.36 | 240323.36 | 187205 | 100% | 100% | 94.62% | 97.57% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-23 | 2004-09-10 | 2004-09-24 | 171 | 142 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Lubusan | 097313012 | Rehabilitation of Level-II Water System | 1 | 1091000 | 755308 | 335692 | 755308 | 3rd Tranche | 633248 | 1388556 | 755308 | 633248 | 100% | 100% | 188.6% | 127.3% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-15 | 2004-10-20 | 2004-10-21 | 219 | 120 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Lubusan | 097313012 | Const. Of FMR (Spill way) | 1 | 2395188 | 1676700 | 718488 | 1676700 | 3rd Tranche | 157500 | 1834200 | 1676700 | 157500 | 100% | 100% | 21.92% | 76.58% | 100% | 2006-05-23 | 2006-06-30 | 2006-10-28 | 2008-04-25 | 2008-11-19 | 545 | 145 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Lubusan | 097313012 | Construction of 1 Unit School Bldg with 3 Classroom | 1 | 1609999.99 | 858979.85 | 751020.14 | 687183.88 | 1st Tranche | 727040 | 1414223.88 | 687183.88 | 727040 | 100% | 100% | 96.81% | 87.84% | 100% | n/a | n/a | 2009-03-10 | 2009-06-15 | 2009-06-27 | 97 | 167 | a.) No need to request 2nd & 3rd tranche b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Mahalingeb | 097313013 | Road Rehabilitation | 1 | 3272500 | 2261310 | 1011190 | 2261310 | 3rd Tranche | 305770.08 | 2567080.08 | 2261310 | 305770.08 | 100% | 100% | 30.24% | 78.44% | 100% | 2005-05-30 | 2005-07-29 | 2005-11-16 | 2006-10-30 | 2006-12-23 | 348 | 165 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Mahalingeb | 097313013 | Construction of Multi-purpose Solar Drier | 1 | 596800 | 473600 | 123200 | 426240 | 2nd Tranche | 150700 | 576940 | 426240 | 150700 | 100% | 100% | 122.3% | 96.67% | 100% | n/a | n/a | 2009-03-14 | 2009-05-30 | 2009-07-06 | 77 | 83 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Mandeg | 097313014 | School Building | 1 | 360965 | 140394.14 | 220570.86 | 140394.14 | 3rd Tranche | 290486.7 | 430880.84 | 140394.14 | 290486.7 | 100% | 100% | 131.7% | 119.4% | 100% | 2003-10-28 | 2003-12-13 | 2004-06-08 | 2004-10-02 | no data | 116 | 75 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Mandeg | 097313014 | Construction of Multi-Purpose Center | 1 | 937300 | 770650 | 166650 | 693585 | 2nd Tranche | 207850 | 901435 | 693585 | 207850 | 100% | 100% | 124.7% | 96.17% | 100% | n/a | n/a | 2009-03-17 | 2009-05-25 | 2009-06-22 | 69 | 106 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Maralag | 097313015 | Spring Development Water System (Level-II) | 1 | 692687 | 224303 | 468384 | 224303 | 3rd Tranche | 342620.5 | 566923.5 | 224303 | 342620.5 | 100% | 100% | 73.15% | 81.84% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-04 | 2005-03-22 | 2005-04-12 | 383 | 126 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Maralag | 097313015 | Construction of Flea Market | 1 | 691000 | 500130 | 190870 | 500130 | 3rd Tranche | 194000 | 694130 | 500130 | 194000 | 100% | 100% | 101.6% | 100.5% | 100% | n/a | n/a | 2009-03-31 | 2009-06-08 | 2009-06-29 | 69 | 119 | Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Maruing | 097313016 | Proposed Overflow Bridge | 1 | 628538.65 | 374877.85 | 253660.8 | 374877.85 | 3rd Tranche | 259214.7 | 634092.55 | 374877.85 | 259214.7 | 100% | 100% | 102.2% | 100.9% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-05 | 2004-09-27 | 2004-09-29 | 206 | 100 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Molum | 097313017 | Construction of Level-II water System | 1 | 584782 | 318851 | 265931 | 318851 | 3rd Tranche | 267110.8 | 585961.8 | 318851 | 267110.8 | 100% | 100% | 100.4% | 100.2% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-12 | 2004-10-30 | 2005-01-03 | 232 | 80 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Molum | 097313017 | Construction of Multi-Purpose Center | 1 | 778871.91 | 611378.91 | 167493 | 550241.02 | 2nd Tranche | 177375 | 727616.02 | 550241.02 | 177375 | 100% | 100% | 105.9% | 93.42% | 100% | n/a | n/a | 2009-04-04 | 2009-06-20 | 2009-06-28 | 77 | 175 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pampang | 097313018 | Spring Developmetn Water System (Level-II) | 1 | 342747.65 | 198551.48 | 144196.17 | 198551.48 | 3rd Tranche | 176914.5 | 375465.98 | 198551.48 | 176914.5 | 100% | 100% | 122.7% | 109.5% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-16 | 2005-07-27 | 2005-07-28 | 498 | 80 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pampang | 097313018 | Construction of Multi-Purpose Center | 1 | 824690 | 665170 | 159520 | 598653 | 2nd Tranche | 170290 | 768943 | 598653 | 170290 | 100% | 100% | 106.8% | 93.24% | 100% | n/a | n/a | 2009-03-31 | 2009-06-18 | 2009-06-27 | 79 | 160 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pantad | 097313019 | Conts. Of Multi-Purpose Solar Drier | 1 | 225707.25 | 132047.3 | 93659.95 | 132047.3 | 3rd Tranche | 95475 | 227522.3 | 132047.3 | 95475 | 100% | 100% | 101.9% | 100.8% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-05 | 2005-02-07 | 2005-02-11 | 339 | 75 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pantad | 097313019 | Construction of Multi-Purpose Center | 1 | 792700 | 605060 | 187640 | 544590 | 2nd Tranche | 197939 | 742529 | 544590 | 197939 | 100% | 100% | 105.5% | 93.67% | 100% | n/a | n/a | 2009-03-19 | 2009-06-23 | 2009-06-29 | 96 | 100 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pingalay | 097313020 | Construction of Mini warf | 1 | 671737.35 | 404811 | 266926.35 | 404811 | 3rd Tranche | 270384 | 675195 | 404811 | 270384 | 100% | 100% | 101.3% | 100.5% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-16 | 2004-09-27 | 2004-11-10 | 195 | 115 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Pingalay | 097313020 | Construction of Flea Market | 1 | 663100 | 493000 | 170100 | 443700 | 2nd Tranche | 168950 | 612650 | 443700 | 168950 | 100% | 100% | 99.32% | 92.39% | 100% | n/a | n/a | 2009-03-24 | 2009-06-17 | 2009-06-22 | 85 | 140 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Poblacion | 097313034 | Const. of CR HS/SC building | 1 | 1367052.46 | 941316 | 425736.46 | 941316 | 3rd Tranche | 304000 | 1245316 | 941316 | 304000 | 100% | 100% | 71.41% | 91.09% | 100% | 2006-05-23 | 2006-06-30 | 2006-08-21 | 2006-12-07 | 2006-12-31 | 108 | 200 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Poblacion | 097313034 | Construction of Day Care Center | 1 | 658755.57 | 495805.57 | 162950 | 446225.01 | 2nd Tranche | 170025 | 616250.01 | 446225.01 | 170025 | 100% | 100% | 104.3% | 93.55% | 100% | n/a | n/a | 2009-03-09 | 2009-05-30 | 2009-06-27 | 82 | 80 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Salambuyan | 097313023 | School Road | 1 | 400000 | 280000 | 120000 | 280000 | 3rd Tranche | 389422.5 | 669422.5 | 280000 | 389422.5 | 100% | 100% | 324.5% | 167.4% | 100% | 2003-10-28 | 2003-12-13 | 2004-09-06 | 2005-02-14 | 2005-03-29 | 161 | 100 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Salambuyan | 097313023 | Const. of MPB (Open Type) | 1 | 553543 | 350464 | 203079 | 350464 | 3rd Tranche | 168300 | 518764 | 350464 | 168300 | 100% | 100% | 82.87% | 93.72% | 100% | 2006-05-23 | 2006-06-30 | 2006-08-14 | 2006-11-30 | 2006-12-08 | 108 | 200 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | San Jose | 097313024 | Brgy. Health Station | 1 | 326657 | 187637 | 139020 | 187637 | 3rd Tranche | 143311 | 330948 | 187637 | 143311 | 100% | 100% | 103.1% | 101.3% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-18 | 2004-11-18 | 2004-12-06 | 245 | 120 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | San Jose | 097313024 | Construction of Multi-Purpose Center | 1 | 815800 | 658050 | 157750 | 591940 | 2nd Tranche | 171750 | 763690 | 591940 | 171750 | 100% | 100% | 108.9% | 93.61% | 100% | n/a | n/a | 2009-03-16 | 2009-06-20 | 2009-06-26 | 96 | 95 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Sayog | 097313025 | Road Rehabilitation | 1 | 1110606 | 672646 | 437960 | 672646 | 3rd Tranche | 877016 | 1549662 | 672646 | 877016 | 100% | 100% | 200.3% | 139.5% | 100% | 2003-10-28 | 2003-12-13 | 2004-10-07 | 2005-02-15 | 2005-04-01 | 131 | 120 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Sayog | 097313025 | Construction of Multi-purpose Solar Drier | 1 | 601800 | 453200 | 148600 | 362560 | 1st Tranche | 144075 | 506635 | 362560 | 144075 | 100% | 100% | 96.95% | 84.19% | 100% | n/a | n/a | 2009-03-13 | 2009-05-30 | 2009-07-04 | 78 | 60 | a.) No need to request 2nd & 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tabon | 097313027 | Road Rehabilitation | 1 | 1365040 | 956750 | 408290 | 956750 | 3rd Tranche | 588951.51 | 1545701.51 | 956750 | 588951.51 | 100% | 100% | 144.2% | 113.2% | 100% | 2003-10-28 | 2003-12-13 | 2004-08-15 | 2006-07-20 | 2008-10-16 | 704 | 154 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tabon | 097313027 | Construction of Multi-Purpose Center | 1 | 804600 | 627650 | 176950 | 564885 | 2nd Tranche | 194530 | 759415 | 564885 | 194530 | 100% | 100% | 109.9% | 94.38% | 100% | n/a | n/a | 2009-03-20 | 2009-06-22 | 2009-07-04 | 94 | 77 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Talabab | 097313028 | Rehab of Level-II water system | 1 | 668188 | 274343 | 393845 | 274343 | 3rd Tranche | 406599.7 | 680942.7 | 274343 | 406599.7 | 100% | 100% | 103.2% | 101.9% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-05 | 2005-04-18 | 2005-04-29 | 409 | 80 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Talabab | 097313028 | Construction of CR School Bldg. | 1 | 603000 | 395886 | 207114 | 395886 | 3rd Tranche | 166126.4 | 562012.4 | 395886 | 166126.4 | 100% | 100% | 80.21% | 93.2% | 100% | 2005-05-30 | 2005-07-29 | 2005-10-19 | 2006-09-15 | 2006-10-17 | 331 | 165 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Talabab | 097313028 | Construction of Multi-purpose Solar Drier | 1 | 400600 | 303400 | 97200 | 273060 | 2nd Tranche | 99800 | 372860 | 273060 | 99800 | 100% | 100% | 102.7% | 93.08% | 100% | n/a | n/a | 2009-03-23 | 2009-05-30 | 2009-06-29 | 68 | 89 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tiguha | 097313029 | Construction of Water System L-II | 1 | 3655000 | 2506428 | 1148572 | 2506428 | 3rd Tranche | 838767 | 3345195 | 2506428 | 838767 | 100% | 100% | 73.03% | 91.52% | 100% | 2005-05-30 | 2005-07-29 | 2005-10-21 | 2006-02-01 | 2006-09-20 | 103 | 175 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tiguha | 097313029 | Construction of Multi-Purpose Center | 1 | 801790 | 664070 | 137720 | 597663 | 2nd Tranche | 142700 | 740363 | 597663 | 142700 | 100% | 100% | 103.6% | 92.34% | 100% | n/a | n/a | 2009-03-18 | 2009-06-20 | 2009-07-08 | 94 | 356 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tininghalang | 097313030 | Water System L-II | 1 | 444448.99 | 260165 | 184283.99 | 260165 | 3rd Tranche | 257215.35 | 517380.35 | 260165 | 257215.35 | 100% | 100% | 139.6% | 116.4% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-08 | 2005-03-19 | 2005-05-26 | 376 | 145 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tininghalang | 097313030 | Const. of 2CR Elem SB | 1 | 1900565.19 | 980385 | 920180.19 | 980385 | 3rd Tranche | 348250 | 1328635 | 980385 | 348250 | 100% | 100% | 37.85% | 69.91% | 100% | 2006-05-23 | 2006-06-30 | 2006-08-28 | 2006-12-31 | May 07 | 125 | 110 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tininghalang | 097313030 | Construction of Health Station | 1 | 707100 | 556596.67 | 150503.33 | 500937 | 2nd Tranche | 158685 | 659622 | 500937 | 158685 | 100% | 100% | 105.4% | 93.29% | 100% | n/a | n/a | 2009-03-12 | 2009-06-17 | 2009-06-26 | 97 | 168 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tipasan | 097313031 | Rehab of Farm to Market Road | 1 | 1453511 | 784047.01 | 669463.99 | 784047.01 | 3rd Tranche | 731097.5 | 1515144.51 | 784047.01 | 731097.5 | 100% | 100% | 109.2% | 104.2% | 100% | 2003-10-28 | 2003-12-13 | 2004-03-01 | 2005-05-27 | 2005-08-27 | 452 | 165 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tipasan | 097313031 | Const. of Water System Level II (G) | 1 | 1623222.21 | 1136225 | 486997.21 | 1136225 | 3rd Tranche | 77000 | 1213225 | 1136225 | 77000 | 100% | 100% | 15.81% | 74.74% | 100% | 2006-05-23 | 2006-06-30 | 2006-08-23 | 2006-12-21 | Dec. 06 | 120 | 150 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tipasan | 097313031 | Construction of Multi-purpose Solar Drier | 1 | 503600 | 365550 | 138050 | 328995 | 2nd Tranche | 149350 | 478345 | 328995 | 149350 | 100% | 100% | 108.2% | 94.99% | 100% | n/a | n/a | 2009-03-30 | 2009-05-30 | 2009-06-29 | 61 | 118 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tugaya | 097313033 | Const. of FMR (Spillway, sectional concreting) | 1 | 3878179.9 | 2714910 | 1163269.9 | 2714910 | 3rd Tranche | 1003230.88 | 3718140.88 | 2714910 | 1003230.88 | 100% | 100% | 86.24% | 95.87% | 100% | 2006-05-23 | 2006-06-30 | 2006-04-28 | 2008-02-26 | 2009-03-13 | 669 | 120 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Lapuyan | 097313 | Tugaya | 097313033 | Construction of Day Care Center | 1 | 641800 | 538050 | 103750 | 484245 | 2nd Tranche | 106875 | 591120 | 484245 | 106875 | 100% | 100% | 103% | 92.1% | 100% | n/a | n/a | 2009-03-13 | 2009-06-23 | 2009-06-28 | 102 | 48 | a.) No need to request 3rd tranch b.) Closed Account | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Balonai | 097318040 | Livelihood Training & Application on Rubber Production | 1 | 333960 | 219250 | 114710 | 175400 | 1st Tranche | 178310 | 353710 | 175400 | 178310 | 100% | 100% | 155.4% | 105.9% | 100% | 2008-04-24 | 2008-05-14 | 2007-03-11 | 2007-07-31 | 2007-08-14 | 142 | 50 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Bibilop | 097318003 | Const. of Multi-Purpose Building | 1 | 1891467 | 1317391 | 574076 | 1317391 | 3rd Tranche | 536836 | 1854227 | 1317391 | 536836 | 100% | 100% | 93.51% | 98.03% | 100% | 2007-05-30 | 2007-06-20 | 2008-01-07 | 2008-10-15 | 2008-10-27 | 282 | 194 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Buloron | 097318005 | Const. of Water System Level II | 1 | 1172807 | 719804 | 453003 | 719804 | 3rd Tranche | 385956 | 1105760 | 719804 | 385956 | 100% | 100% | 85.2% | 94.28% | 100% | 2007-05-30 | 2007-06-20 | 2008-01-16 | 2008-10-29 | 2008-10-29 | 287 | 127 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Cabaloran | 097318030 | Construction of Warehouse | 1 | 747323 | 515345 | 231978 | 463810.5 | 2nd Tranche | 235078 | 698888.5 | 463810.5 | 235078 | 100% | 100% | 101.3% | 93.52% | 100% | 2008-04-24 | 2008-05-14 | 2008-08-28 | 2008-11-30 | 2008-12-11 | 94 | 176 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Canipay Norte | 097318007 | Const. of Day Care Center | 1 | 612923 | 424923 | 188000 | 424923 | 3rd Tranche | 173278.81 | 598201.81 | 424923 | 173278.81 | 100% | 100% | 92.17% | 97.6% | 100% | 2007-05-30 | 2007-06-20 | 2008-03-23 | 2008-11-30 | 2008-12-17 | 252 | 172 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Canipay Sur | 097318008 | Brgy. Road Improvement | 1 | 1084486 | 715595 | 368891 | 715595 | 3rd Tranche | 369948 | 1085543 | 715595 | 369948 | 100% | 100% | 100.3% | 100.1% | 100% | 2007-05-30 | 2007-06-20 | 2007-12-28 | 2008-07-15 | 2008-07-24 | 200 | 136 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Cumaron | 097318009 | Const. of Corn Mill | 1 | 1073838 | 615717 | 458121 | 615717 | 3rd Tranche | 408121 | 1023838 | 615717 | 408121 | 100% | 100% | 89.09% | 95.34% | 100% | 2007-05-30 | 2007-06-20 | 2007-11-09 | 2008-07-01 | for schedule | 235 | 201 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Dakayakan | 097318031 | Construction of Multi-Purpose Pavement | 1 | 440160 | 304110 | 136050 | 304110 | 3rd Tranche | 146850 | 450960 | 304110 | 146850 | 100% | 100% | 107.9% | 102.5% | 100% | 2008-04-24 | 2008-05-14 | 2008-08-14 | 2008-08-26 | 2008-09-11 | 12 | 51 | for inspection | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Duelic | 097318032 | Rehab of Farm to Market Road | 1 | 1962353 | 1041799 | 920554 | 1041799 | 3rd Tranche | 424013.82 | 1465812.82 | 1041799 | 424013.82 | 100% | 100% | 46.06% | 74.7% | 100% | 2006-05-30 | 2006-06-27 | 2006-09-11 | 2007-05-30 | 2007-06-29 | 261 | 160 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Dumalinao | 097318033 | Const. of Water System Level 2(G) | 1 | 1777409 | 1013006 | 764403 | 1013006 | 3rd Tranche | 557400 | 1570406 | 1013006 | 557400 | 100% | 100% | 72.92% | 88.35% | 100% | 2006-05-30 | 2006-06-27 | 2006-07-28 | 2006-12-28 | 2007-01-08 | 153 | 124 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Ecuan | 097318034 | Construction of 1 Unit 1 CL School Building | 1 | 719735 | 508641 | 211094 | 503276.11 | 3rd Tranche | 118350 | 621626.11 | 503276.11 | 118350 | 100% | 100% | 56.07% | 86.37% | 100% | 2008-04-24 | 2008-05-14 | 2008-09-04 | 2008-12-15 | 2009-01-14 | 102 | 70 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Golictop | 097318011 | Construction of Water System Level 2 | 1 | 3598772.44 | 2645721 | 953051.44 | 2116576.8 | 1st Tranche | 662749.13 | 2779325.93 | 2116576.8 | 662749.13 | 100% | 100% | 69.54% | 77.23% | 100% | 2008-04-24 | 2008-05-14 | 2008-11-05 | 2009-06-15 | 2009-06-29 | 222 | 112 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Guma | 097318041 | Construction of Warehouse w/ 1 unit Solar dryer | 1 | 1083406 | 737496 | 345910 | 663746.4 | 2nd Tranche | 320525 | 984271.4 | 663746.4 | 320525 | 100% | 100% | 92.66% | 90.85% | 100% | 2008-04-24 | 2008-05-14 | 2008-07-22 | 2008-12-15 | 2009-01-05 | 146 | 135 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Licuro-an | 097318038 | Construction of 1 Unit 1 CL Shool Building | 1 | 739269 | 520926 | 218343 | 468833.4 | 2nd Tranche | 288375 | 757208.4 | 468833.4 | 288375 | 100% | 100% | 132.1% | 102.4% | 100% | 2008-04-24 | 2008-05-14 | 2008-09-16 | 2008-12-15 | 2008-12-17 | 90 | 100 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Lumpunid | 097318016 | Const of Brgy Lumponid Road | 1 | 2114480 | 1428790 | 685690 | 1371638.4 | 3rd Tranche | 600159 | 1971797.4 | 1371638.4 | 600159 | 100% | 100% | 87.53% | 93.25% | 100% | 2006-05-30 | 2006-06-27 | 2006-08-30 | 2007-06-30 | 2007-07-11 | 304 | 140 |  | 1
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Lumpunid | 097318016 | Construction of Warehouse w/ 1 unit Solar dryer | 1 | 1295750 | 949767 | 345983 | 854790.3 | 2nd Tranche | 418093.98 | 1272884.28 | 854790.3 | 418093.98 | 100% | 100% | 120.8% | 98.24% | 100% | 2008-04-24 | 2008-05-14 | 2008-09-16 | 2008-12-15 | 2009-04-30 | 90 | 296 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Matalang | 097318017 | Rehab of Brgy Matalang Road | 1 | 3129124 | 1719281 | 1409843 | 1719281 | 3rd Tranche | 857780.13 | 2577061.13 | 1719281 | 857780.13 | 100% | 100% | 60.84% | 82.36% | 100% | 2006-05-30 | 2006-06-27 | 2006-09-29 | 2007-05-30 | 2007-07-05 | 243 | 140 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Matalang | 097318017 | Const. of Multi-Purpose Building | 1 | 1854693 | 1347847 | 506846 | 1347847 | 3rd Tranche | 486434.05 | 1834281.05 | 1347847 | 486434.05 | 100% | 100% | 95.97% | 98.9% | 100% | 2007-05-30 | 2007-06-20 | 2007-12-03 | 2008-07-26 | 2008-07-31 | 236 | 161 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | New Katipunan | 097318018 | Rehab of Brgy New Katipunan Road | 1 | 2969185.7 | 2048631.7 | 920554 | 2048631.7 | 3rd Tranche | 438127 | 2486758.7 | 2048631.7 | 438127 | 100% | 100% | 47.59% | 83.75% | 100% | 2006-05-30 | 2006-06-27 | 2006-10-05 | 2008-05-31 | 2008-12-21 | 604 | 125 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | New Unidos | 097318019 | Construction of Rice and Corn Mill | 1 | 1492674 | 1046979 | 445695 | 1046978.8 | 3rd Tranche | 405206 | 1452184.8 | 1046978.8 | 405206 | 100% | 100% | 90.92% | 97.29% | 100% | 2008-04-24 | 2008-05-14 | 2008-09-11 | 2009-01-15 | 2009-02-18 | 126 | 83 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Palili | 097318020 | Brgy. Road Improvement | 1 | 2489620 | 1625120 | 864500 | 1517959.83 | 3rd Tranche | 1018668.5 | 2536628.33 | 1517959.83 | 1018668.5 | 100% | 100% | 117.8% | 101.9% | 100% | 2007-05-30 | 2007-06-20 | 2008-04-15 | 2008-03-31 | 2009-04-30 | -15 | 160 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Pawan | 097318039 | Training on Appropriate Farming Tech | 1 | 240500 | 121000 | 119500 | 108900 | 2nd Tranche | 91500 | 200400 | 108900 | 91500 | 100% | 100% | 76.57% | 83.33% | 100% | 2006-05-30 | 2006-06-27 | 2006-03-01 | 2007-07-31 | 2007-08-14 | 517 | 80 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Pili | 097318042 | Construction of 1 Unit 1 CL Shool Building | 1 | 664174 | 460413.5 | 203760.5 | 460413.5 | 3rd Tranche | 217390 | 677803.5 | 460413.5 | 217390 | 100% | 100% | 106.7% | 102.1% | 100% | 2008-04-24 | 2008-05-14 | 2008-09-12 | 2008-11-30 | 2009-03-05 | 79 | 70 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Pisompongan | 097318029 | Const. of School Building | 1 | 1076105 | 752478 | 323627 | 752478 | 3rd Tranche | 323627 | 1076105 | 752478 | 323627 | 100% | 100% | 100% | 100% | 100% | 2007-05-30 | 2007-06-20 | 2007-11-08 | 2008-02-21 | 2008-03-28 | 105 | 148 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Piwan | 097318021 | Construction of Day Care Center | 1 | 707633 | 687633 | 20000 | 618869.7 | 2nd Tranche | 20000 | 638869.7 | 618869.7 | 20000 | 100% | 100% | 100% | 90.28% | 100% | 2008-04-24 | 2008-05-14 | 2008-12-03 | 2009-01-15 | 2009-03-04 | 43 | 35 | Additional brgy pls see refer to MDC resolution | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Poblacion B | 097318023 | Const. of Water System Level II | 1 | 2962662.43 | 2254843.43 | 707819 | 2254843.43 | 3rd Tranche | 428421.13 | 2683264.56 | 2254843.43 | 428421.13 | 100% | 100% | 60.53% | 90.57% | 100% | 2007-05-30 | 2007-06-20 | 2008-06-18 | 2008-11-30 | 2009-01-05 | 165 | 389 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Sigapod | 097318024 | Rehab of Brgy Sigapod Road | 1 | 3968456 | 2527493 | 1440963 | 2527493 | 3rd Tranche | 1014740.5 | 3542233.5 | 2527493 | 1014740.5 | 100% | 100% | 70.42% | 89.26% | 100% | 2006-05-30 | 2006-06-27 | 2006-09-28 | 2007-06-30 | 2007-08-03 | 275 | 150 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Sigapod | 097318024 | Construction of 1 Unit 2 CL Shool Building | 1 | 988005 | 689448 | 298557 | 620503.2 | 2nd Tranche | 308880 | 929383.2 | 620503.2 | 308880 | 100% | 100% | 103.5% | 94.07% | 100% | 2008-04-24 | 2008-05-14 | 2008-07-31 | 2008-12-15 | 2009-01-05 | 137 | 48 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Timbaboy | 097318026 | Construction of Multi-Purpose Pavement | 1 | 557966 | 113565.5 | 444400.5 | 113565.5 | 3rd Tranche | 405850.5 | 519416 | 113565.5 | 405850.5 | 100% | 100% | 91.33% | 93.09% | 100% | 2008-04-24 | 2008-05-14 | 2008-08-29 | 2008-10-15 | 2008-10-30 | 47 | 236 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Tulbong | 097318027 | Construction of 1 Unit 1 CL School Building | 1 | 719735 | 508585 | 211150 | 457726.5 | 2nd Tranche | 180025 | 637751.5 | 457726.5 | 180025 | 100% | 100% | 85.26% | 88.61% | 100% | 2008-04-24 | 2008-05-14 | 2008-08-29 | 2008-12-15 | 2009-01-07 | 108 | 98 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | Midsalip | 097318 | Tuluan | 097318028 | Livelihood Training & Application on Rubber Production | 1 | 307460 | 204250 | 103210 | 163400 | 1st Tranche | 70110 | 233510 | 163400 | 70110 | 100% | 100% | 67.93% | 75.95% | 100% | 2008-04-24 | 2008-05-14 | 2008-08-18 | 2008-10-13 | 2008-12-17 | 56 | 51 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Bag- ong Misamis | 097325001 | Construction of Barangay Health Station | 1 | 623991 | 436772 | 187219 | 436772 | 3rd Tranche | 193539 | 630311 | 436772 | 193539 | 100% | 100% | 103.4% | 101% | 100% | 2008-04-28 | 2008-04-29 | 2008-10-24 | 2008-12-30 | 2009-04-20 | 67 | 119 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Bubual | 097325002 | Const of Brgy Bubual Level 2 Water System (G) | 1 | 860764 | 542731 | 318033 | 542731 | 3rd Tranche | 212997.59 | 755728.59 | 542731 | 212997.59 | 100% | 100% | 66.97% | 87.8% | 100% | 2006-05-31 | 2006-07-10 | 2006-11-15 | 2007-04-15 | 2007-07-14 | 151 | 120 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Bubual | 097325002 | Construction of Day Care Center | 1 | 568375 | 397859 | 170516 | 397859 | 3rd Tranche | 172734.85 | 570593.85 | 397859 | 172734.85 | 100% | 100% | 101.3% | 100.4% | 100% | 2008-04-28 | 2008-04-29 | 2008-08-01 | 2008-12-30 | 2009-01-12 | 151 | 58 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Buton | 097325003 | Const of Brgy Buton Level 2 Water System (G) | 1 | 1151704 | 806526 | 345178 | 806526 | 3rd Tranche | 346957.08 | 1153483.08 | 806526 | 346957.08 | 100% | 100% | 100.5% | 100.2% | 100% | 2006-05-31 | 2006-07-10 | 2006-11-10 | 2007-05-30 | 2007-12-14 | 201 | 125 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Buton | 097325003 | Construction of Multi-Purpose Pavement | 1 | 515790 | 361047 | 154743 | 361047 | 3rd Tranche | 155740.7 | 516787.7 | 361047 | 155740.7 | 100% | 100% | 100.6% | 100.2% | 100% | 2008-04-28 | 2008-04-29 | 2008-10-13 | 2008-12-30 | 2009-03-14 | 78 | 50 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Culasian | 097325004 | Construction of Barangay Health Station | 1 | 603770 | 422617 | 181153 | 422617 | 3rd Tranche | 182001.85 | 604618.85 | 422617 | 182001.85 | 100% | 100% | 100.5% | 100.1% | 100% | 2008-04-28 | 2008-04-29 | 2008-09-18 | 2008-12-03 | 2009-05-15 | 76 | 231 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Daplayan | 097325005 | Const. of 2 units 2CL School Building | 1 | 2200837 | 1540415 | 660422 | 1540415 | 3rd Tranche | 656987 | 2197402 | 1540415 | 656987 | 100% | 100% | 99.48% | 99.84% | 100% | 2007-05-28 | 2007-05-30 | 2007-10-11 | 2008-03-15 | 2008-04-07 | 156 | 190 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Daplayan | 097325005 | Construction of Day Care Center | 1 | 559406 | 391593 | 167813 | 391593 | 3rd Tranche | 174204.85 | 565797.85 | 391593 | 174204.85 | 100% | 100% | 103.8% | 101.1% | 100% | 2008-04-28 | 2008-04-29 | 2008-06-29 | 2008-12-15 | 2008-12-30 | 169 | 40 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kalilangan | 097325006 | Const. of Water System Level II | 1 | 2011525 | 1408031 | 603494 | 1304661 | 3rd Tranche | 604644.4 | 1909305.4 | 1304661 | 604644.4 | 100% | 100% | 100.2% | 94.92% | 100% | 2007-05-28 | 2007-05-30 | 2008-02-22 | 2008-05-03 | 2008-06-23 | 71 | 190 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kalilangan | 097325006 | Construction of Multi-Purpose Pavement | 1 | 470645 | 290987 | 179658 | 261888.3 | 2nd Tranche | 62800 | 324688.3 | 261888.3 | 62800 | 100% | 100% | 34.96% | 68.99% | 100% | 2008-04-28 | 2008-04-29 | 2008-02-22 | 2009-03-27 | 2009-04-24 | 399 | 40 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kapamanok | 097325007 | Const of Brgy Kapamanok Level 2 Water System (P) | 1 | 1062249.85 | 743339 | 318910.85 | 743339 | 3rd Tranche | 192330.48 | 935669.48 | 743339 | 192330.48 | 100% | 100% | 60.31% | 88.08% | 100% | 2006-05-31 | 2006-07-10 | 2006-10-20 | 2007-01-30 | 2007-02-02 | 102 | 140 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kapamanok | 097325007 | Const. of Multi-Purpose Building | 1 | 1251917 | 876404 | 375513 | 876404 | 3rd Tranche | 386373 | 1262777 | 876404 | 386373 | 100% | 100% | 102.9% | 100.9% | 100% | 2007-05-28 | 2007-05-30 | 2007-12-21 | 2008-11-30 | no data | 345 | 280 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kondum | 097325008 | Const of Brgy Kondum Level 2 Water System (G) | 1 | 397390.32 | 221216 | 176174.32 | 221216 | 3rd Tranche | 191389.4 | 412605.4 | 221216 | 191389.4 | 100% | 100% | 108.6% | 103.8% | 100% | 2006-05-31 | 2006-07-10 | 2006-10-18 | 2007-01-28 | 2007-07-19 | 102 | 85 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Kondum | 097325008 | Construction of Day Care Center | 1 | 454370 | 290987 | 163383 | 261888.3 | 3rd Tranche | 62800 | 324688.3 | 261888.3 | 62800 | 100% | 100% | 38.44% | 71.46% | 100% | 2008-04-28 | 2008-04-29 | 2008-08-07 | 2008-12-15 | 2008-12-15 | 130 | 30 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Lumbayao | 097325009 | Const. of Water System Level II | 1 | 2314520 | 1505386 | 809134 | 1431324.36 | 3rd Tranche | 737709.4 | 2169033.76 | 1431324.36 | 737709.4 | 100% | 100% | 91.17% | 93.71% | 100% | 2007-05-28 | 2007-05-30 | 2008-08-10 | 2008-11-30 | no data | 112 | 137 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Mabuhay | 097325010 | Day Care Center | 1 | 545021 | 382773 | 162248 | 382773 | 3rd Tranche | 160729 | 543502 | 382773 | 160729 | 100% | 100% | 99.06% | 99.72% | 100% | 2007-05-28 | 2007-05-30 | 2008-07-25 | 2008-12-30 | 2008-12-30 | 158 | 35 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Marcos Village | 097325011 | Construction of School Building | 1 | 555598 | 388934 | 166664 | 388934 | 3rd Tranche | 169702.85 | 558636.85 | 388934 | 169702.85 | 100% | 100% | 101.8% | 100.5% | 100% | 2008-04-28 | 2008-04-29 | 2008-09-19 | 2008-12-30 | 2009-02-08 | 102 | 50 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Marcos Vllage | 097325011 | Const of Brgy Marcos Vilage Health Station | 1 | 518592 | 303365 | 215227 | 303365 | 3rd Tranche | 195675.82 | 499040.82 | 303365 | 195675.82 | 100% | 100% | 90.92% | 96.23% | 100% | 2006-05-31 | 2006-07-10 | 2006-10-26 | 2007-02-28 | 2007-04-15 | 125 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Miasin | 097325012 | Const of Brgy Miasin Level 2 Water System (P) | 1 | 1128023 | 653699 | 474324 | 653699 | 3rd Tranche | 342205.58 | 995904.58 | 653699 | 342205.58 | 100% | 100% | 72.15% | 88.29% | 100% | 2006-05-31 | 2006-07-10 | 2006-11-10 | 2007-05-15 | 2007-07-30 | 186 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Miasin | 097325012 | Improvement of Spillway | 1 | 666021 | 466186 | 199835 | 466186 | 3rd Tranche | 201635 | 667821 | 466186 | 201635 | 100% | 100% | 100.9% | 100.3% | 100% | 2008-04-28 | 2008-04-29 | 2008-09-30 | 2008-12-30 | 2009-02-12 | 91 | 191 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Molansong | 097325013 | Const of Brgy Mulansong Level 2 Water System (P) | 1 | 1026500 | 602676 | 423824 | 602676 | 3rd Tranche | 459220.96 | 1061896.96 | 602676 | 459220.96 | 100% | 100% | 108.4% | 103.4% | 100% | 2006-05-31 | 2006-07-10 | 2006-09-18 | 2007-01-28 | 2007-08-30 | 132 | 112 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Molansong | 097325013 | Construction of Multi-Purpose Pavement | 1 | 357398 | 250178 | 107220 | 241264 | 3rd Tranche | 138718.85 | 379982.85 | 241264 | 138718.85 | 100% | 100% | 129.4% | 106.3% | 100% | 2008-04-28 | 2008-04-29 | 2008-07-03 | 2008-10-15 | 2008-11-10 | 104 | 85 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pantad | 097325014 | Const of Brgy Pantad Level 2 Water System (P) | 1 | 1028684.6 | 642859 | 385825.6 | 642859 | 3rd Tranche | 216849.72 | 859708.72 | 642859 | 216849.72 | 100% | 100% | 56.2% | 83.57% | 100% | 2006-05-31 | 2006-07-10 | 2006-10-31 | 2007-01-31 | for schedule | 92 | 145 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pantad | 097325014 | Construction of Day Care Center | 1 | 430387 | 301273 | 129114 | 301273 | 3rd Tranche | 126225 | 427498 | 301273 | 126225 | 100% | 100% | 97.76% | 99.33% | 100% | 2008-04-28 | 2008-04-29 | 2008-06-13 | 2008-12-30 | 2009-01-12 | 200 | 30 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pao | 097325015 | Construction of Multi-Purpose Pavement | 1 | 546800 | 382769 | 164031 | 382768.1 | 3rd Tranche | 176389.39 | 559157.49 | 382768.1 | 176389.39 | 100% | 100% | 107.5% | 102.3% | 100% | 2008-04-28 | 2008-04-29 | 2008-09-18 | 2008-11-30 | 2008-12-16 | 73 | 125 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Payag | 097325016 | Construction of Flea Market | 1 | 438613 | 307034 | 131579 | 293266 | 3rd Tranche | 136877.39 | 430143.39 | 293266 | 136877.39 | 100% | 100% | 104% | 98.07% | 100% | 2008-04-28 | 2008-04-29 | 2008-07-26 | 2008-10-15 | 2008-11-25 | 81 | 227 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Poblacion | 097325017 | Road Improvement / Concreting | 1 | 1548670 | 1077416 | 471254 | 1077416 | 3rd Tranche | 423186.72 | 1500602.72 | 1077416 | 423186.72 | 100% | 100% | 89.8% | 96.9% | 100% | 2007-05-28 | 2007-05-30 | 2007-12-21 | 2008-01-31 | no data | 41 | 575 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Pongapong | 097325018 | Const of Brgy Pongapong Level 2 Water System (P) | 1 | 690384 | 391396 | 298988 | 391396 | 3rd Tranche | 231888.32 | 623284.32 | 391396 | 231888.32 | 100% | 100% | 77.56% | 90.28% | 100% | 2006-05-31 | 2006-07-10 | 2006-10-18 | 2007-01-30 | 2007-07-24 | 104 | 85 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Sacbulan | 097325021 | Const. of Multi-Purpose Pavement | 1 | 505350 | 350149 | 155201 | 350149 | 3rd Tranche | 153971 | 504120 | 350149 | 153971 | 100% | 100% | 99.21% | 99.76% | 100% | 2007-05-28 | 2007-05-30 | 2007-10-10 | 2008-11-30 | no data | 417 | 191 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Sagasan | 097325020 | Const of Brgy Sagasan Health Station | 1 | 474796 | 152468 | 322328 | 148704.75 | 3rd Tranche | 289559.5 | 438264.25 | 148704.75 | 289559.5 | 100% | 100% | 89.83% | 92.31% | 100% | 2006-05-31 | 2006-07-10 | 2006-08-18 | 2007-12-05 | 2007-12-20 | 474 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Sagasan | 097325020 | Road Improvement | 1 | 740094 | 515929 | 224165 | 484626.23 | 3rd Tranche | 364271 | 848897.23 | 484626.23 | 364271 | 100% | 100% | 162.5% | 114.7% | 100% | 2008-04-28 | 2008-04-29 | 2008-10-10 | 2008-11-20 | 2009-04-29 | 41 | 100 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | San Juan | 097325029 | Rehab of Brgy San Juan Road | 1 | 3593249 | 2515407 | 1077842 | 2515407 | 3rd Tranche | 900438.72 | 3415845.72 | 2515407 | 900438.72 | 100% | 100% | 83.54% | 95.06% | 100% | 2006-05-31 | 2006-07-10 | 2006-11-21 | 2007-06-03 | 2007-06-27 | 194 | 100 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Senior | 097325022 | Construction of Water System Level 2 (pump) | 1 | 2022007 | 1379405 | 642602 | 1241464.5 | 2nd Tranche | 838589.31 | 2080053.81 | 1241464.5 | 838589.31 | 100% | 100% | 130.5% | 102.9% | 100% | 2008-04-28 | 2008-04-29 | 2008-03-08 | 2009-06-30 | for schedule | 479 | 70 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Songgoy | 097325023 | Const of Day Care Center | 1 | 544645 | 381272 | 163373 | 321631.37 | 3rd Tranche | 160014 | 481645.37 | 321631.37 | 160014 | 100% | 100% | 97.94% | 88.43% | 100% | 2007-05-28 | 2007-05-30 | 2007-12-13 | 2008-03-15 | 2008-07-28 | 93 | 104 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Tandubuay | 097325024 | Const. of concrete footbridge | 1 | 1254423 | 878154 | 376269 | 878154 | 3rd Tranche | 348749 | 1226903 | 878154 | 348749 | 100% | 100% | 92.69% | 97.81% | 100% | 2007-05-28 | 2007-05-30 | 2008-01-22 | 2008-07-03 | 2008-07-19 | 163 | 30 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Teniapan | 097325026 | Construction of Barangay Health Station | 1 | 601854 | 421323 | 180531 | 421323 | 3rd Tranche | 182429.85 | 603752.85 | 421323 | 182429.85 | 100% | 100% | 101.1% | 100.3% | 100% | 2008-04-28 | 2008-04-29 | 2008-09-16 | 2009-01-16 | 2009-04-20 | 122 | 211 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Ticala Island | 097325025 | Const of Brgy Ticala Island Elem School Bldg | 1 | 1304183 | 824318 | 479865 | 824318 | 3rd Tranche | 355214.94 | 1179532.94 | 824318 | 355214.94 | 100% | 100% | 74.02% | 90.44% | 100% | 2006-05-31 | 2006-07-10 | 2006-11-28 | 2007-06-30 | 2007-07-21 | 214 | 100 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Tubo-Pait | 097325027 | Construction of Day Care Center | 1 | 555598 | 388903 | 166695 | 386193.37 | 3rd Tranche | 172373.85 | 558567.22 | 386193.37 | 172373.85 | 100% | 100% | 103.4% | 100.5% | 100% | 2008-04-28 | 2008-04-29 | 2008-10-07 | 2008-12-30 | 2009-04-24 | 84 | 30 |  | 1 | VISAYAS
IX | 09 | Zamboanga Del Sur | 0973 | San Pablo | 097325 | Vilakapa | 097325028 | Construction of 1 Unit 2 CL Shool Building | 1 | 1254273 | 878027 | 376246 | 790224.3 | 2nd Tranche | 369666 | 1159890.3 | 790224.3 | 369666 | 100% | 100% | 98.25% | 92.48% | 100% | 2008-04-28 | 2008-04-29 | 2008-10-09 | 2008-11-30 | 2009-04-23 | 52 | 80 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Alegria | 098301001 | Const. of Water System Level II (P) | 1 | 789548.35 | 552683.85 | 236864.5 | 552683.85 | 3rd Tranche | 239897.6 | 792581.45 | 552683.85 | 239897.6 | 100% | 100% | 101.3% | 100.4% | 100% | 2006-12-14 | 2007-03-27 | 2007-06-26 | 2008-03-06 | 2008-04-15 | 254 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Alegria | 098301001 | Construction of Overflow Bridge | 1 | 839495.7 | 587362.37 | 252133.33 | 543409.67 | 3rd Tranche | 301183.33 | 844593 | 543409.67 | 301183.33 | 100% | 100% | 119.5% | 100.6% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-14 | 2009-04-15 | 2009-06-22 | 32 | 136 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Bagong Buhay | 098301026 | Const. of W.S. L2 | 1 | 1008831 | 706197.67 | 302633.33 | 706051.44 | 3rd Tranche | 302633.33 | 1008684.77 | 706051.44 | 302633.33 | 100% | 100% | 100% | 99.99% | 100% | 2008-04-22 | 2008-05-23 | 2008-11-27 | 2009-02-26 | no data | 91 | 81 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Bella | 098301004 | Const. of W.S. L2 | 1 | 1032462 | 721928.67 | 310533.33 | 650655.87 | 3rd Tranche | 293033.33 | 943689.2 | 650655.87 | 293033.33 | 100% | 100% | 94.36% | 91.4% | 100% | 2008-04-22 | 2008-05-23 | 2008-10-14 | 2009-06-28 | for schedule | 257 | 90 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Calades | 098301005 | Const. of DCC | 1 | 592474 | 414342.67 | 178131.33 | 398821.65 | 3rd Tranche | 178421.33 | 577242.98 | 398821.65 | 178421.33 | 100% | 100% | 100.2% | 97.43% | 100% | 2008-04-22 | 2008-05-23 | 2008-08-14 | 2008-09-30 | 2008-10-29 | 47 | 87 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Concepcion | 098301027 | Const. of MPB | 1 | 705841 | 490407.67 | 215433.33 | 490407.67 | 3rd Tranche | 226749.93 | 717157.6 | 490407.67 | 226749.93 | 100% | 100% | 105.3% | 101.6% | 100% | 2008-04-22 | 2008-05-23 | 2008-09-22 | 2008-11-30 | 2009-03-20 | 69 | 323 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Dawa-Dawa | 098301006 | Const. of Water System Level II | 1 | 2271464.94 | 1590025.46 | 681439.48 | 1272020.36 | 1st Tranche | 744939.31 | 2016959.67 | 1272020.36 | 744939.31 | 100% | 100% | 109.3% | 88.8% | 100% | 2006-12-14 | 2007-03-27 | 2008-07-03 | 2009-02-15 | no data | 227 | 239 | MDC Reso. # 2 | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Dawa-Dawa | 098301006 | Construction of 2 units stilt drier | 1 | 1085874.47 | 731119.57 | 354754.9 | 715661.4 | 3rd Tranche | 310904.9 | 1026566.3 | 715661.4 | 310904.9 | 100% | 100% | 87.64% | 94.54% | 100% | 2008-04-22 | 2008-12-15 | 2009-04-03 | 2009-06-30 | for schedule | 88 | 457 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Gulayon | 098301007 | Construction of Water System L2 (P) | 1 | 1424421 | 920742.53 | 503678.47 | 920742.52 | 3rd Tranche | 426336.93 | 1347079.45 | 920742.52 | 426336.93 | 100% | 100% | 84.64% | 94.57% | 100% | 2008-04-22 | 2008-12-15 | 2009-04-03 | 2009-08-10 | no data | 129 | 285 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Ilisan | 098301008 | Const. of Water System Level II (P) | 1 | 740593.61 | 406358.35 | 334235.26 | 406358.35 | 3rd Tranche | 335611.22 | 741969.57 | 406358.35 | 335611.22 | 100% | 100% | 100.4% | 100.2% | 100% | 2006-12-14 | 2007-03-27 | 2007-06-25 | 2008-04-10 | 2008-09-24 | 290 | 115 | Double entry made by the RFA in LCC in-kind | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Ilisan | 098301008 | Construction of 2 CL School Building - Elem. | 1 | 1165821.93 | 816088.6 | 349733.33 | 803488.6 | 3rd Tranche | 370516.93 | 1174005.53 | 803488.6 | 370516.93 | 100% | 100% | 105.9% | 100.7% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-11 | 2009-06-20 | 2009-06-22 | 101 | 115 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Kapatagan | 098301028 | Construction of Water System L2 (G) | 1 | 903847 | 617713.67 | 286133.33 | 562897.67 | 3rd Tranche | 466398.33 | 1029296 | 562897.67 | 466398.33 | 100% | 100% | 163% | 113.9% | 100% | 2008-04-22 | 2008-12-15 | 2009-04-15 | 2009-06-24 | for schedule | 70 | 121 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Kauswagan | 098301010 | Const. of 1 unit School Building | 1 | 592885.9 | 302054.57 | 290831.33 | 302054.57 | 3rd Tranche | 303349.3 | 605403.87 | 302054.57 | 303349.3 | 100% | 100% | 104.3% | 102.1% | 100% | 2008-04-22 | 2008-05-23 | 2008-10-18 | 2009-03-07 | 2009-03-10 | 140 | 67 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Kawayan | 098301009 | Construction of Day Care Center | 1 | 594974 | 411950.67 | 183023.33 | 396857.19 | 3rd Tranche | 223034.33 | 619891.52 | 396857.19 | 223034.33 | 100% | 100% | 121.9% | 104.2% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-16 | 2009-05-15 | 2009-06-26 | 60 | 36 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lambuyogan | 098301012 | Const. of W.S. L2 | 1 | 1335975 | 930441.67 | 405533.33 | 909763.63 | 3rd Tranche | 317176.57 | 1226940.2 | 909763.63 | 317176.57 | 100% | 100% | 78.21% | 91.84% | 100% | 2008-04-22 | 2008-05-23 | 2008-09-26 | 2008-12-29 | 2009-06-30 | 94 | 169 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lapaz | 098301011 | Const. of Water System Level II (P) | 1 | 2463308.12 | 1724315.68 | 738992.44 | 1670087.25 | 3rd Tranche | 738632.44 | 2408719.69 | 1670087.25 | 738632.44 | 100% | 100% | 99.95% | 97.78% | 100% | 2006-12-14 | 2007-03-27 | 2007-06-28 | 2008-11-27 | 2009-06-24 | 518 | 209 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lapaz | 098301011 | Construction of Day Care Center | 1 | 598674 | 418590.67 | 180083.33 | 408095.67 | 3rd Tranche | 180733.33 | 588829 | 408095.67 | 180733.33 | 100% | 100% | 100.4% | 98.36% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-21 | 2009-06-18 | 2009-06-24 | 89 | 35 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lapirawan | 098301013 | Const. of DCC | 1 | 596174 | 417140.69 | 179033.31 | 398406.98 | 3rd Tranche | 179075.31 | 577482.29 | 398406.98 | 179075.31 | 100% | 100% | 100% | 96.86% | 100% | 2008-04-22 | 2008-05-23 | 2008-09-13 | 2008-12-15 | no data | 93 | 81 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Litayon | 098301014 | Const. of Stilt Dryer | 1 | 698512.34 | 484685.77 | 213826.57 | 474046.31 | 3rd Tranche | 215826.57 | 689872.88 | 474046.31 | 215826.57 | 100% | 100% | 100.9% | 98.76% | 100% | 2008-04-22 | 2008-05-23 | 2008-08-21 | 2008-10-30 | 2009-06-30 | 70 | 100 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lutiman | 098301015 | Const. of Hanging Footbridge | 1 | 885100 | 619266.67 | 265833.33 | 574181.87 | 3rd Tranche | 265826.57 | 840008.44 | 574181.87 | 265826.57 | 100% | 100% | 100% | 94.91% | 100% | 2008-04-22 | 2008-05-23 | 2008-10-09 | 2009-03-25 | 2009-06-30 | 167 | 150 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Milagrosa | 098301002 | Construction of 1 unit Warehouse | 1 | 905728 | 633694.67 | 272033.33 | 620694.67 | 3rd Tranche | 247633.33 | 868328 | 620694.67 | 247633.33 | 100% | 100% | 91.03% | 95.87% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-20 | 2009-06-18 | 2009-06-22 | 90 | 252 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Naga-Naga | 098301016 | Construction of Flea Market | 1 | 714147 | 498213.67 | 215933.33 | 485788.65 | 3rd Tranche | 227273.65 | 713062.3 | 485788.65 | 227273.65 | 100% | 100% | 105.3% | 99.85% | 100% | 2008-04-22 | 2008-12-15 | 2009-04-06 | 2009-06-30 | for schedule | 85 | 260 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Pandan-Pandan | 098301017 | Const. of Health Station | 1 | 597506.7 | 414130.37 | 183376.33 | 414130.37 | 3rd Tranche | 193780.31 | 607910.68 | 414130.37 | 193780.31 | 100% | 100% | 105.7% | 101.7% | 100% | 2008-04-22 | 2008-05-23 | 2008-08-25 | 2008-10-30 | 2009-06-23 | 66 | 80 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Payongan | 098301018 | Construction of Day Care Center | 1 | 479137.93 | 314487.56 | 164650.37 | 306977.59 | 3rd Tranche | 164651.37 | 471628.96 | 306977.59 | 164651.37 | 100% | 100% | 100% | 98.43% | 100% | 2006-12-14 | 2007-03-27 | 2008-06-01 | 2008-10-20 | 2008-11-06 | 141 | 70 | a.) Project Cost pls refer to: MDC Reso. # 3 b.) Grant fund release changes as of July 2008-reason:Wrong entry | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Payongan | 098301018 | Construction of 1 CL School Building - Elem. | 1 | 596889.04 | 417305.71 | 179583.33 | 383705.71 | 3rd Tranche | 178083.33 | 561789.04 | 383705.71 | 178083.33 | 100% | 100% | 99.16% | 94.12% | 100% | 2008-04-22 | 2008-12-15 | 2009-04-02 | 2009-06-20 | 2009-06-23 | 79 | 266 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Poblacion | 098301019 | Const. of MPB | 1 | 792433.9 | 552980.57 | 239453.33 | 552980.57 | 3rd Tranche | 418206.57 | 971187.14 | 552980.57 | 418206.57 | 100% | 100% | 174.7% | 122.6% | 100% | 2008-04-22 | 2008-05-23 | 2008-08-13 | 2008-11-30 | 2008-12-05 | 109 | 663 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Sta. Maria | 098301020 | Const. of Water System Level II (P) | 1 | 2118061.33 | 1482642.93 | 635418.4 | 1186114.35 | 1st Tranche | 558865.65 | 1744980 | 1186114.35 | 558865.65 | 100% | 100% | 87.95% | 82.39% | 100% | 2006-12-14 | 2007-03-27 | 2008-02-18 | 2008-08-15 | 2008-09-25 | 179 | 119 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Sta. Maria | 098301020 | Construction of 2 CL School Building - Elem. | 1 | 1162321.93 | 813588.6 | 348733.33 | 813588.6 | 3rd Tranche | 316403.33 | 1129991.93 | 813588.6 | 316403.33 | 100% | 100% | 90.73% | 97.22% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-12 | 2009-05-16 | 2009-06-19 | 65 | 165 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Sto. Niño | 098301021 | Const. of Water System Level II (P) | 1 | 1518907.56 | 1063235.29 | 455672.27 | 850588.23 | 1st Tranche | 286450.26 | 1137038.49 | 850588.23 | 286450.26 | 100% | 100% | 62.86% | 74.86% | 100% | 2006-12-14 | 2007-03-27 | 2007-08-25 | 2008-12-28 | no data | 491 | 229 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Sto. Niño | 098301021 | Construction of 2 CL School Building - Elem. | 1 | 1167221.93 | 817088.6 | 350133.33 | 817088.6 | 3rd Tranche | 291715.68 | 1108804.28 | 817088.6 | 291715.68 | 100% | 100% | 83.32% | 95% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-30 | 2009-06-30 | for schedule | 92 | 210 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Talaptap | 098301022 | Const. of W.S. L 2 | 1 | 1242410 | 869576.67 | 372833.33 | 869576.67 | 3rd Tranche | 430603.74 | 1300180.41 | 869576.67 | 430603.74 | 100% | 100% | 115.5% | 104.6% | 100% | 2008-04-22 | 2008-05-23 | 2008-08-30 | 2009-02-28 | no data | 182 | 213 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Tampalan | 098301023 | Const. of Water System Level II (P) | 1 | 1254651.92 | 878256.35 | 376395.57 | 878256.35 | 3rd Tranche | 409938.61 | 1288194.96 | 878256.35 | 409938.61 | 100% | 100% | 108.9% | 102.7% | 100% | 2006-12-14 | 2007-03-27 | 2007-11-22 | 2008-06-30 | no data | 221 | 150 | b.) Grant fund release changes as of July 2008-reason:Wrong entry | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Tampalan | 098301023 | Construction of Day Care Center | 1 | 598274 | 416540.67 | 181733.33 | 416518.07 | 3rd Tranche | 199333.33 | 615851.4 | 416518.07 | 199333.33 | 100% | 100% | 109.7% | 102.9% | 100% | 2008-04-22 | 2008-12-15 | 2009-03-20 | 2009-05-18 | 2009-06-17 | 59 | 135 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Tandiong Muslim | 098301024 | Const. of Shoreline Protection | 1 | 1099706 | 766795.67 | 332910.33 | 745080.43 | 3rd Tranche | 332946.57 | 1078027 | 745080.43 | 332946.57 | 100% | 100% | 100% | 98.03% | 100% | 2008-04-22 | 2008-05-23 | 2008-10-20 | 2009-03-28 | 2009-06-20 | 159 | 64 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Timgbang-Timbang | 098301025 | Const. of Health Station | 1 | 592384 | 410050.67 | 182333.33 | 410050.67 | 3rd Tranche | 188548.43 | 598599.1 | 410050.67 | 188548.43 | 100% | 100% | 103.4% | 101% | 100% | 2008-04-22 | 2008-05-23 | 2008-07-01 | 2008-09-29 | 2008-11-20 | 90 | 286 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Abunda | 098307001 | Conts. Of Water System Level ll (P) | 1 | 800072 | 544278 | 255794 | 544278 | 3rd Tranche | 266277.6 | 810555.6 | 544278 | 266277.6 | 100% | 100% | 104.1% | 101.3% | 100% | 2005-03-30 | 2005-05-27 | 2005-08-17 | 2007-01-08 | 2007-01-08 | 509 | 107 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Bagong Silang | 098307002 | Const. of Water System L 2 (P) | 1 | 1062491 | 741820 | 320671 | 741820 | 3rd Tranche | 321853.55 | 1063673.55 | 741820 | 321853.55 | 100% | 100% | 100.4% | 100.1% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-22 | 2007-06-15 | for schedule | 328 | 104 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Bangkaw-Bangkaw | 098307003 | Conts. Of Water System Level ll (P) | 1 | 902862 | 619442 | 283420 | 619442 | 3rd Tranche | 284421 | 903863 | 619442 | 284421 | 100% | 100% | 100.4% | 100.1% | 100% | 2005-03-30 | 2005-05-27 | 2005-08-05 | 2006-03-27 | 2006-05-25 | 234 | 175 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Bangkaw-Bangkaw | 098307003 | Const. of Mini-Wharf | 1 | 760888 | 520888 | 240000 | 505097.2 | 3rd Tranche | 414030.79 | 919127.99 | 505097.2 | 414030.79 | 100% | 100% | 172.5% | 120.8% | 100% | 2007-04-30 | 2007-06-26 | 2007-09-13 | 2008-02-29 | for schedule | 169 | 175 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Caliran | 098307007 | Const. of Rice Milling Facilities | 1 | 1097406 | 762477 | 334929 | 762477 | 3rd Tranche | 336033.55 | 1098510.55 | 762477 | 336033.55 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-22 | 2006-12-31 | 2007-02-17 | 162 | 228 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Catipan | 098307008 | Const. of Foot Bridge with Pathway | 1 | 623544 | 370544 | 253000 | 370544 | 3rd Tranche | 254101.55 | 624645.55 | 370544 | 254101.55 | 100% | 100% | 100.4% | 100.2% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-22 | 2007-01-13 | 2007-01-19 | 175 | 152 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Kauswagan | 098307011 | Construction of Brgy Rice Mill | 1 | 891092 | 609371 | 281721 | 609371 | 3rd Tranche | 335331 | 944702 | 609371 | 335331 | 100% | 100% | 119% | 106% | 100% | 2005-03-30 | 2005-05-27 | 2005-07-25 | 2006-01-25 | 2006-02-04 | 184 | 151 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Ligaya | 098307013 | Const. of Water System L 2 (P) | 1 | 1175875 | 790484 | 385391 | 790484 | 3rd Tranche | 386550.55 | 1177034.55 | 790484 | 386550.55 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-08 | 2007-01-13 | 2007-01-18 | 189 | 137 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Looc -Barlak | 098307014 | Conts. Of Water System Level ll (P) | 1 | 828652 | 563838 | 264814 | 563838 | 3rd Tranche | 267821 | 831659 | 563838 | 267821 | 100% | 100% | 101.1% | 100.4% | 100% | 2005-03-30 | 2005-05-27 | 2005-08-11 | 2005-12-29 | 2006-02-28 | 140 | 152 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Looc -Barlak | 098307014 | Const. of Multi-Purpose Building | 1 | 795000 | 555600 | 239400 | 555600 | 3rd Tranche | 359261.72 | 914861.72 | 555600 | 359261.72 | 100% | 100% | 150.1% | 115.1% | 100% | 2007-04-30 | 2007-06-26 | 2007-09-04 | 2009-02-03 | for schedule | 518 | 144 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Malinao | 098307015 | Const. of Mini-Wharf | 1 | 1114855 | 763960 | 350895 | 763960 | 3rd Tranche | 355016 | 1118976 | 763960 | 355016 | 100% | 100% | 101.2% | 100.4% | 100% | 2005-03-30 | 2005-05-27 | 2005-07-25 | 2005-11-29 | 2005-11-30 | 127 | 479 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Malinao | 098307015 | Const. of Mini-Wharf | 1 | 992080 | 572075 | 420005 | 572075 | 3rd Tranche | 375498.51 | 947573.51 | 572075 | 375498.51 | 100% | 100% | 89.4% | 95.51% | 100% | 2007-04-30 | 2007-06-26 | 2007-07-31 | 2008-03-30 | for schedule | 243 | 479 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Pamansaan | 098307017 | Const. of Mini-Wharf | 1 | 1183610 | 830400 | 353210 | 747360 | 2nd Tranche | 328600 | 1075960 | 747360 | 328600 | 100% | 100% | 93.03% | 90.9% | 100% | 2007-04-30 | 2007-06-26 | 2007-08-25 | 2009-07-27 | for schedule | 702 | 95 | completed as built | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Poblacion | 098307019 | Conts. Of Water System Level ll (P) | 1 | 823178 | 481204 | 341974 | 481204 | 3rd Tranche | 346621 | 827825 | 481204 | 346621 | 100% | 100% | 101.4% | 100.6% | 100% | 2005-03-30 | 2005-05-27 | 2005-07-15 | 2006-11-26 | 2007-11-28 | 499 | 350 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Poblacion | 098307019 | Const. of Flea Market | 1 | 543000 | 261459 | 281541 | 261459 | 3rd Tranche | 282547.55 | 544006.55 | 261459 | 282547.55 | 100% | 100% | 100.4% | 100.2% | 100% | 2006-04-20 | 2006-05-30 | 2006-08-15 | 2006-12-31 | 2007-01-08 | 138 | 200 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Punawan | 098307020 | Const. of Water System L 2 (P) | 1 | 1072635 | 645279 | 427356 | 645279 | 3rd Tranche | 428411.6 | 1073690.6 | 645279 | 428411.6 | 100% | 100% | 100.2% | 100.1% | 100% | 2006-04-20 | 2006-05-30 | 2006-06-02 | 2006-10-31 | 2007-02-08 | 151 | 143 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Punawan | 098307020 | Const. of Day Care Center | 1 | 645300 | 451710 | 193590 | 425445.36 | 3rd Tranche | 190300 | 615745.36 | 425445.36 | 190300 | 100% | 100% | 98.3% | 95.42% | 100% | 2007-04-30 | 2007-06-26 | 2007-09-15 | 2008-01-15 | for schedule | 122 | 135 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | San Roque (Pinalim) | 098307018 | Construction of Multi Purpose Building | 1 | 698340 | 417566 | 280774 | 417566 | 3rd Tranche | 288573.55 | 706139.55 | 417566 | 288573.55 | 100% | 100% | 102.8% | 101.1% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-31 | 2007-03-10 | 2008-02-07 | 222 | 128 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | San Roque (Pinalim) | 098307018 | Const. of Barangay Health Station | 1 | 678700 | 475090 | 203610 | 475090 | 3rd Tranche | 208772.91 | 683862.91 | 475090 | 208772.91 | 100% | 100% | 102.5% | 100.8% | 100% | 2007-04-30 | 2007-06-26 | 2007-08-20 | 2008-01-15 | for schedule | 148 | 115 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Sawa | 098307024 | Conts. Of Water System Level ll (P) | 1 | 851482 | 591457 | 260025 | 591457 | 3rd Tranche | 261346 | 852803 | 591457 | 261346 | 100% | 100% | 100.5% | 100.2% | 100% | 2005-03-30 | 2005-05-27 | 2005-08-16 | 2005-11-27 | 2006-01-29 | 103 | 263 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Sawa | 098307024 | Const. of Mini-Wharf | 1 | 1258410 | 880887 | 377523 | 864387 | 3rd Tranche | 334795.4 | 1199182.4 | 864387 | 334795.4 | 100% | 100% | 88.68% | 95.29% | 100% | 2007-04-30 | 2007-06-26 | 2007-08-27 | 2008-02-29 | for schedule | 186 | 315 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Sioton | 098307025 | Const. of Water System L 2 (P) | 1 | 1052500 | 806572 | 245928 | 806572 | 3rd Tranche | 349733.55 | 1156305.55 | 806572 | 349733.55 | 100% | 100% | 142.2% | 109.9% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-22 | 2006-11-30 | 2007-02-10 | 131 | 135 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Sto. Niño | 098307023 | Multi Purpose Building | 1 | 909790 | 603799 | 305991 | 603799 | 3rd Tranche | 307553.55 | 911352.55 | 603799 | 307553.55 | 100% | 100% | 100.5% | 100.2% | 100% | 2006-04-20 | 2006-05-30 | 2006-07-17 | 2007-02-05 | 2007-02-28 | 203 | 120 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Taguisian | 098307026 | Const. of Concrete Pathway | 1 | 1506255 | 944603 | 561652 | 944603 | 3rd Tranche | 566651 | 1511254 | 944603 | 566651 | 100% | 100% | 100.9% | 100.3% | 100% | 2005-03-30 | 2005-05-27 | 2005-08-15 | 2006-01-10 | 2006-02-28 | 148 | 484 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Taguisian | 098307026 | Water System Level II | 1 | 1590500 | 1113350 | 477150 | 1050857.29 | 3rd Tranche | 477882.51 | 1528739.8 | 1050857.29 | 477882.51 | 100% | 100% | 100.2% | 96.12% | 100% | 2007-04-30 | 2007-06-26 | 2007-11-05 | 2009-06-30 | for schedule | 603 | 320 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Mabuhay | 098307 | Tandu-comot | 098307010 | Const. of Mini-Wharf | 1 | 917167 | 281847 | 635320 | 281847 | 3rd Tranche | 642363 | 924210 | 281847 | 642363 | 100% | 100% | 101.1% | 100.8% | 100% | 2005-03-30 | 2005-05-27 | 2005-07-27 | 2006-11-26 | 2006-11-27 | 487 | 365 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Balian | 098311001 | Construction of Water System Level 2(P) | 1 | 1473574 | 841648 | 631926 | 757483.2 | 2nd Tranche | 367591 | 1125074.2 | 757483.2 | 367591 | 100% | 100% | 58.17% | 76.35% | 100% | 2006-12-14 | 2007-04-25 | 2007-06-11 | 2008-10-09 | 2008-11-15 | 486 | 112 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Balogo - C2 | 098311021 | Const. of W.S. L2 (p) | 2 | 2363875.34 | 1766329.37 | 597545.97 | 1766328.69 | 3rd Tranche | 597061.31 | 2363390 | 1766328.69 | 597061.31 | 100% | 100% | 99.92% | 99.98% | 100% | 2008-05-02 | 2008-05-16 | 2008-11-12 | 2009-06-25 | for schedule | 225 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Talaptap | 098311020 | Const. of W.S. L2 (p) | 2 | 2363875.34 | 1766329.37 | 597545.97 | 1766328.69 | 3rd Tranche | 597061.31 | 2363390 | 1766328.69 | 597061.31 | 100% | 100% | 99.92% | 99.98% | 100% | 2008-05-02 | 2008-05-16 | 2008-11-12 | 2009-06-25 | for schedule | 225 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Balungisan | 098311002 | Construction of Flea Market | 1 | 859058 | 697077 | 161981 | 697077 | 3rd Tranche | 171981 | 869058 | 697077 | 171981 | 100% | 100% | 106.2% | 101.2% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-03 | 2009-05-25 | 2009-06-12 | 52 | 214 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Binangonan | 098311022 | Constructin of 1 unit 2 CL school building | 1 | 1316721.5 | 1034422.5 | 282299 | 1030491.99 | 3rd Tranche | 266804 | 1297295.99 | 1030491.99 | 266804 | 100% | 100% | 94.51% | 98.52% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-03 | 2009-06-26 | 2009-06-30 | 84 | 46 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Bulacan | 098311003 | Construction of Water System Level 2(P) | 1 | 1454166 | 1020640 | 433526 | 977183.8 | 3rd Tranche | 433526 | 1410709.8 | 977183.8 | 433526 | 100% | 100% | 100% | 97.01% | 100% | 2006-12-14 | 2007-04-25 | 2007-06-26 | 2007-12-14 | 2008-03-03 | 171 | 120 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Bulawan | 098311004 | Const. of 1 unit 3 CL School Building | 1 | 1715953.95 | 1256009.95 | 459944 | 1235737.84 | 3rd Tranche | 343405 | 1579142.84 | 1235737.84 | 343405 | 100% | 100% | 74.66% | 92.03% | 100% | 2008-05-02 | 2008-05-16 | 2009-02-24 | 2009-05-30 | 2009-06-09 | 95 | 120 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Calape | 098311005 | Construction of Hanging Foot Bridge | 1 | 966645 | 674525 | 292120 | 674525 | 3rd Tranche | 297120 | 971645 | 674525 | 297120 | 100% | 100% | 101.7% | 100.5% | 100% | 2006-12-14 | 2007-04-25 | 2007-06-26 | 2008-11-17 | 2009-03-05 | 510 | 117 | Clerical Error by MRB/FA/RFA | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Dalama | 098311006 | Construction of Water System Level 2(P) | 1 | 1389239 | 1007233 | 382006 | 1007145 | 3rd Tranche | 340828 | 1347973 | 1007145 | 340828 | 100% | 100% | 89.22% | 97.03% | 100% | 2006-12-14 | 2007-04-25 | 2008-02-18 | 2009-05-30 | 2009-06-28 | 467 | 98 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Fatima | 098311007 | Construction of Fatima Brgy Road | 1 | 2416144 | 1626294 | 789850 | 1519694 | 3rd Tranche | 190000 | 1709694 | 1519694 | 190000 | 100% | 100% | 24.06% | 70.76% | 100% | 2006-12-14 | 2007-04-25 | 2008-11-24 | 2009-01-31 | 2009-02-13 | 68 | 70 | Over monitization of lot | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Guintolan | 098311008 | Road Improvement | 1 | 1213512.56 | 942179.56 | 271333 | 852044.55 | 3rd Tranche | 134629 | 986673.55 | 852044.55 | 134629 | 100% | 100% | 49.62% | 81.31% | 100% | 2008-05-02 | 2008-05-16 | 2008-08-30 | 2009-02-20 | 2009-05-15 | 174 | 540 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Guiwan | 098311023 | Const. of 1 unit 2 CL school Building | 1 | 1152655.88 | 852238.03 | 300417.85 | 833067.78 | 3rd Tranche | 362558.85 | 1195626.63 | 833067.78 | 362558.85 | 100% | 100% | 120.7% | 103.7% | 100% | 2008-05-02 | 2008-05-16 | 2008-10-24 | 2009-01-30 | 2009-05-29 | 98 | 230 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Katipunan | 098311009 | Const. of 1 unit 2 CL school Building | 1 | 1153256.5 | 812270.2 | 340986.3 | 812270.2 | 3rd Tranche | 206378.3 | 1018648.5 | 812270.2 | 206378.3 | 100% | 100% | 60.52% | 88.33% | 100% | 2008-05-02 | 2008-05-16 | 2008-09-29 | 2009-01-30 | 2009-01-30 | 123 | 300 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Kima | 098311010 | Construction of Drainage Canal | 1 | 1377272 | 928820 | 448452 | 923705 | 3rd Tranche | 333600 | 1257305 | 923705 | 333600 | 100% | 100% | 74.39% | 91.29% | 100% | 2008-05-02 | 2009-02-05 | 2009-03-31 | 2009-06-26 | 2009-06-30 | 87 | 98 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Kulasian | 098311011 | Construction of 1 unit 2 Cl school building | 1 | 1280593 | 1050562 | 230031 | 1040627.21 | 3rd Tranche | 182916 | 1223543.21 | 1040627.21 | 182916 | 100% | 100% | 79.52% | 95.55% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-01 | 2009-05-30 | 2009-06-16 | 59 | 48 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Kulisap | 098311024 | Construction of Water System Level 2(P) | 1 | 1418750 | 991700 | 427050 | 959601 | 3rd Tranche | 398610 | 1358211 | 959601 | 398610 | 100% | 100% | 93.34% | 95.73% | 100% | 2006-12-14 | 2007-04-25 | 2007-06-11 | 2007-12-10 | 2007-12-28 | 182 | 85 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | La Fortuna | 098311025 | Const. of W.S. L 2 (g) | 1 | 929963.58 | 642076.92 | 287886.66 | 623691.48 | 3rd Tranche | 305891.67 | 929583.15 | 623691.48 | 305891.67 | 100% | 100% | 106.3% | 99.96% | 100% | 2008-05-02 | 2008-05-16 | 2008-08-15 | 2009-01-30 | 2009-05-18 | 168 | 95 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Labatan | 098311012 | Construction of Stilt Drier | 1 | 1079370 | 776272 | 303098 | 768128.78 | 3rd Tranche | 316850 | 1084978.78 | 768128.78 | 316850 | 100% | 100% | 104.5% | 100.5% | 100% | 2006-12-14 | 2007-04-25 | 2008-05-06 | 2009-03-30 | 2009-06-28 | 328 | 160 | Clerical Error by MRB/FA/RFA | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Lower Sumilong | 098311028 | Cobnst. Of Water System L2 (P) | 1 | 1100396 | 737153 | 363243 | 724635.91 | 3rd Tranche | 341728 | 1066363.91 | 724635.91 | 341728 | 100% | 100% | 94.08% | 96.91% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-02 | 2009-05-20 | 2009-06-17 | 48 | 52 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Mayabo | 098311018 | Construction of Solar Dryer | 1 | 446436.5 | 335039.5 | 111397 | 335038.6 | 3rd Tranche | 108937 | 443975.6 | 335038.6 | 108937 | 100% | 100% | 97.79% | 99.45% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-06 | 2009-06-25 | 2009-06-30 | 80 | 99 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Minundas | 098311019 | Construction of 1 unit 2 CL School Building | 1 | 1341977 | 1111946 | 230031 | 1097454.7 | 3rd Tranche | 213696 | 1311150.7 | 1097454.7 | 213696 | 100% | 100% | 92.9% | 97.7% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-06 | 2009-05-26 | 2009-06-26 | 50 | 40 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Mt. View | 098311013 | Construction of Water System Level 2(P) | 1 | 1274815 | 897645 | 377170 | 897645 | 3rd Tranche | 377170 | 1274815 | 897645 | 377170 | 100% | 100% | 100% | 100% | 100% | 2006-12-14 | 2007-04-25 | 2007-07-09 | 2008-04-28 | 2008-05-12 | 294 | 82 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Nanan | 098311014 | Construction of Water System L 2 (P) | 1 | 1231476 | 848986 | 382490 | 840558.42 | 3rd Tranche | 299420 | 1139978.42 | 840558.42 | 299420 | 100% | 100% | 78.28% | 92.57% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-02 | 2009-06-25 | 2009-06-23 | 84 | 102 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Poblacion | 098311015 | Const. of W.S. L 2 (p) | 1 | 1527548.29 | 1123022.38 | 404525.91 | 1121997.32 | 3rd Tranche | 440002.9 | 1562000.22 | 1121997.32 | 440002.9 | 100% | 100% | 108.8% | 102.3% | 100% | 2008-05-02 | 2008-05-16 | 2009-04-20 | 2009-06-29 | 2009-06-30 | 70 | 330 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | San Isidro | 098311026 | Construction of 1 unit 2 CL School Building | 1 | 1240593 | 1006992 | 233601 | 1000464.01 | 3rd Tranche | 222306 | 1222770.01 | 1000464.01 | 222306 | 100% | 100% | 95.16% | 98.56% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-03 | 2009-05-26 | 2009-06-15 | 53 | 45 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | San Roque | 098311016 | Construction of Water System Level 2(P) | 1 | 1240121 | 864043 | 376078 | 845197 | 3rd Tranche | 313380 | 1158577 | 845197 | 313380 | 100% | 100% | 83.33% | 93.42% | 100% | 2006-12-14 | 2007-04-25 | 2008-02-17 | 2009-06-11 | 2009-06-28 | 480 | 90 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | San Vicente | 098311017 | Const. of Health Station | 1 | 656611 | 460929.5 | 195681.5 | 440082.35 | 3rd Tranche | 208847.5 | 648929.85 | 440082.35 | 208847.5 | 100% | 100% | 106.7% | 98.83% | 100% | 2008-05-02 | 2008-05-16 | 2008-09-15 | 2009-03-20 | 2009-06-28 | 186 | 101 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Silal | 098311027 | Const. of W.S, L 1 | 1 | 511666 | 356404 | 155262 | 356404 | 3rd Tranche | 146292 | 502696 | 356404 | 146292 | 100% | 100% | 94.22% | 98.25% | 100% | 2008-05-02 | 2008-05-16 | 2008-11-11 | 2009-08-30 | no data | 292 | 150 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Payao | 098311 | Upper Sumilong | 098311029 | Construction of Water System L2 (P) | 1 | 1290271 | 949002 | 341269 | 936216.7 | 3rd Tranche | 330444 | 1266660.7 | 936216.7 | 330444 | 100% | 100% | 96.83% | 98.17% | 100% | 2008-05-02 | 2009-02-05 | 2009-04-02 | 2009-05-24 | 2009-06-22 | 52 | 86 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Baluran | 098316001 | Const. of Water System Level II | 1 | 1056219.9 | 814323 | 241896.9 | 814323 | 3rd Tranche | 60000 | 874323 | 814323 | 60000 | 100% | 100% | 24.8% | 82.78% | 100% | 2006-12-14 | 2007-03-27 | 2008-04-14 | 2008-10-30 | 2009-02-13 | 199 | 153 | Revised Special MIBF Resolution | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Baluran | 098316001 | Construction of 1 unit 2 cl school building | 1 | 838229 | 606293 | 231936 | 546388.37 | 3rd Tranche | 232481 | 778869.37 | 546388.37 | 232481 | 100% | 100% | 100.2% | 92.92% | 100% | 2008-04-23 | 2008-05-07 | 2009-03-10 | 2009-03-10 | 2009-06-23 | 0 | 337 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Batungan | 098316015 | Const. of W.S. Level 2 (g) | 1 | 852793 | 585892 | 266901 | 585892 | 3rd Tranche | 257988.5 | 843880.5 | 585892 | 257988.5 | 100% | 100% | 96.66% | 98.95% | 100% | 2008-04-23 | 2008-05-02 | 2008-10-29 | 2009-03-20 | 2009-06-22 | 142 | 102 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Cayamcam | 098316002 | Const. of W.S. Level 2 (g) | 1 | 1278710 | 881575 | 397135 | 881575 | 3rd Tranche | 403130 | 1284705 | 881575 | 403130 | 100% | 100% | 101.5% | 100.5% | 100% | 2008-04-23 | 2008-05-02 | 2008-10-15 | 2009-06-29 | for schedule | 257 | 292 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Datu Tumanggong | 098316018 | Construction of Water System Level 2(P) | 1 | 1857826 | 1252017 | 605809 | 1252017 | 3rd Tranche | 724161 | 1976178 | 1252017 | 724161 | 100% | 100% | 119.5% | 106.4% | 100% | 2006-12-14 | 2007-03-27 | 2008-02-14 | 2008-10-30 | 2008-11-21 | 259 | 98 | Revised Special MIBF Resolution | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Datu Tumanggong | 098316018 | Improvement of Farm to Market Road | 1 | 1969640 | 223545 | 1746095 | 201190.5 | 2nd Tranche | 878054 | 1079244.5 | 201190.5 | 878054 | 100% | 100% | 50.29% | 54.79% | 100% | 2008-04-23 | 2008-05-07 | 2009-04-30 | 2009-09-15 | no data | 138 | 243 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Gaycon | 098316020 | Const. of W.S. L2 (P) | 1 | 928478 | 850100 | 78378 | 850100 | 3rd Tranche | 114103 | 964203 | 850100 | 114103 | 100% | 100% | 145.6% | 103.8% | 100% | 2008-04-23 | 2008-05-02 | 2008-09-25 | 2009-02-17 | 2009-02-20 | 145 | 73 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Langon | 098316004 | Const. of W.S. Level 1 (p) | 1 | 507954 | 321065 | 186889 | 321065 | 3rd Tranche | 186482.6 | 507547.6 | 321065 | 186482.6 | 100% | 100% | 99.78% | 99.92% | 100% | 2008-04-23 | 2008-05-02 | 2008-08-12 | 2009-02-15 | 2009-06-03 | 187 | 240 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Libertad | 098316005 | Construction of Water System Level 2(P) | 1 | 2045356 | 1509956 | 535400 | 1509956 | 3rd Tranche | 537395 | 2047351 | 1509956 | 537395 | 100% | 100% | 100.4% | 100.1% | 100% | 2006-12-14 | 2007-03-27 | 2008-03-27 | 2008-12-22 | 2009-06-23 | 270 | 108 | Revised Special MIBF Resolution | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Libertad | 098316005 | Construction of Solar Dryer with Bodega | 1 | 751348 | 586828 | 164520 | 586828 | 3rd Tranche | 165550 | 752378 | 586828 | 165550 | 100% | 100% | 100.6% | 100.1% | 100% | 2008-04-23 | 2008-05-07 | 2009-04-27 | 2009-06-10 | 2009-06-23 | 44 | 700 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Linguisan | 098316006 | Const. of WS. L 1 & 2 (g & ps) | 1 | 743551.5 | 483150 | 260401.5 | 483150 | 3rd Tranche | 259644 | 742794 | 483150 | 259644 | 100% | 100% | 99.71% | 99.9% | 100% | 2008-04-23 | 2008-05-02 | 2008-09-25 | 2009-03-14 | 2009-06-24 | 170 | 89 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Little Margos | 098316021 | Improvement of Brgy. Little Margos (Santan-Sepres) Road | 1 | 1981205 | 1349455 | 631750 | 1349455 | 3rd Tranche | 668341.12 | 2017796.12 | 1349455 | 668341.12 | 100% | 100% | 105.8% | 101.8% | 100% | 2006-12-14 | 2007-03-27 | 2007-06-26 | 2008-01-08 | 2008-07-04 | 196 | 79 | a.) Revised Special MIBF Resolution b.) Changes on LCC utilized is due to formula error set up | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Little Margos | 098316021 | Training on Farming | 1 | 394265 | 235091 | 159174 | 235091 | 3rd Tranche | 156735.5 | 391826.5 | 235091 | 156735.5 | 100% | 100% | 98.47% | 99.38% | 100% | 2008-04-23 | 2008-05-02 | 2008-10-07 | 2009-03-31 | 2009-06-24 | 175 | 75 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Loboc | 098316016 | Construction of Water System L2 (P) | 1 | 833218 | 643922 | 189296 | 643922 | 3rd Tranche | 191921 | 835843 | 643922 | 191921 | 100% | 100% | 101.4% | 100.3% | 100% | 2008-04-23 | 2008-05-07 | 2009-04-08 | 2009-06-18 | 2009-06-29 | 71 | 288 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Looc Labuan | 098316007 | Const. of W.S. Level 1 (ps) | 1 | 344431 | 223499 | 120932 | 223499 | 3rd Tranche | 121062.24 | 344561.24 | 223499 | 121062.24 | 100% | 100% | 100.1% | 100% | 100% | 2008-04-23 | 2008-05-02 | 2008-08-14 | 2009-04-20 | 2009-06-25 | 249 | 101 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Lower Tungawan | 098316008 | Const. of W.S. L2 (g) | 1 | 1340613 | 953774 | 386839 | 953774 | 3rd Tranche | 325029 | 1278803 | 953774 | 325029 | 100% | 100% | 84.02% | 95.39% | 100% | 2008-04-23 | 2008-05-02 | 2008-08-30 | 2009-06-16 | for schedule | 290 | 300 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Malungon | 098316009 | Construction of Water System L2 (G) | 1 | 913418 | 737078 | 176340 | 737078 | 3rd Tranche | 176710 | 913788 | 737078 | 176710 | 100% | 100% | 100.2% | 100% | 100% | 2008-04-23 | 2008-05-07 | 2009-04-07 | 2009-06-18 | 2009-06-25 | 72 | 120 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Masao | 098316025 | Const of Brgy Masao 1 Unit 2 Classroom School Bldg. | 1 | 863530 | 582624 | 280906 | 582624 | 3rd Tranche | 179286 | 761910 | 582624 | 179286 | 100% | 100% | 63.82% | 88.23% | 100% | 2006-12-14 | 2007-03-27 | 2007-06-18 | 2008-10-30 | 2009-03-20 | 500 | 212 | Revised Special MIBF Resolution | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Masao | 098316025 | Construction of Solar Dryer with Bodega | 1 | 779963 | 586828 | 193135 | 586828 | 3rd Tranche | 193345 | 780173 | 586828 | 193345 | 100% | 100% | 100.1% | 100% | 100% | 2008-04-23 | 2008-05-07 | 2009-03-20 | 2009-04-11 | 2009-06-25 | 22 | 110 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | San Isidro | 098316017 | Construction of Water System Level 2(G) | 1 | 1485919 | 911931 | 573988 | 840791.19 | 3rd Tranche | 524336 | 1365127.19 | 840791.19 | 524336 | 100% | 100% | 91.35% | 91.87% | 100% | 2006-12-14 | 2007-03-27 | 2007-11-08 | 2008-09-24 | for schedule | 321 | 270 | Revised Special MIBF Resolution | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | San Pedro | 098316010 | Const. of W.S. L2 (P) | 1 | 971165 | 678358 | 292807 | 678358 | 3rd Tranche | 326822 | 1005180 | 678358 | 326822 | 100% | 100% | 111.6% | 103.5% | 100% | 2008-04-23 | 2008-05-02 | 2008-10-13 | 2009-06-29 | for schedule | 259 | 70 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | San Vicente | 098316014 | Improvement of Farm to Market Road | 1 | 1866007 | 1298373 | 567634 | 1245123 | 3rd Tranche | 569710 | 1814833 | 1245123 | 569710 | 100% | 100% | 100.4% | 97.26% | 100% | 2008-04-23 | 2008-05-07 | 2009-05-14 | 2009-06-30 | no data | 47 | 127 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Sisay | 098316019 | Construction of Water System L2 (G) | 1 | 896917 | 696300 | 200617 | 696300 | 3rd Tranche | 201337 | 897637 | 696300 | 201337 | 100% | 100% | 100.4% | 100.1% | 100% | 2008-04-23 | 2008-05-07 | 2009-04-07 | 2009-06-16 | 2009-06-24 | 70 | 150 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Sto. Niño | 098316022 | Const. of W.S. L2 with 2 handpumps (g) | 1 | 989066 | 685837 | 303229 | 685837 | 3rd Tranche | 269804 | 955641 | 685837 | 269804 | 100% | 100% | 88.98% | 96.62% | 100% | 2008-04-23 | 2008-05-02 | 2008-09-22 | 2009-04-30 | 2009-06-03 | 220 | 80 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Taglibas | 098316023 | Improvement of Farm to Market Road | 1 | 1893116 | 1290224 | 602892 | 1252844 | 3rd Tranche | 600643.84 | 1853487.84 | 1252844 | 600643.84 | 100% | 100% | 99.63% | 97.91% | 100% | 2008-04-23 | 2008-05-07 | 2009-05-15 | 2009-09-15 | no data | 123 | 141 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigbanuang | 098316011 | Const. of DCC | 1 | 612379 | 406658 | 205721 | 406658 | 3rd Tranche | 215946 | 622604 | 406658 | 215946 | 100% | 100% | 105% | 101.7% | 100% | 2008-04-23 | 2008-05-02 | 2008-12-03 | 2009-03-20 | 2009-06-05 | 107 | 30 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigbucay | 098316012 | Const. of WS. L 1 & 2 (g) | 1 | 632498 | 445669 | 186829 | 445669 | 3rd Tranche | 187194 | 632863 | 445669 | 187194 | 100% | 100% | 100.2% | 100.1% | 100% | 2008-04-23 | 2008-05-02 | 2008-08-26 | 2009-02-14 | 2009-07-07 | 172 | 170 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigpalay | 098316024 | Const. of W.S. L2 (P) | 1 | 1070916 | 749332 | 321584 | 749332 | 3rd Tranche | 362626.5 | 1111958.5 | 749332 | 362626.5 | 100% | 100% | 112.8% | 103.8% | 100% | 2008-04-23 | 2008-05-02 | 2008-09-08 | 2009-07-30 | for schedule | 325 | 103 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Timbabauan | 098316026 | Construction of Water System L2 (P) | 1 | 1058486 | 830609 | 227877 | 807072.38 | 3rd Tranche | 263389.5 | 1070461.88 | 807072.38 | 263389.5 | 100% | 100% | 115.6% | 101.1% | 100% | 2008-04-23 | 2008-05-07 | 2009-03-20 | 2009-06-18 | 2009-06-22 | 90 | 45 |  | 1 | VISAYAS
IX | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Upper Tungawan | 098316013 | Construction of Water System Level 2(G) | 1 | 1650119 | 1079694 | 570425 | 1079694 | 3rd Tranche | 576695 | 1656389 | 1079694 | 576695 | 100% | 100% | 101.1% | 100.4% | 100% | 2006-12-14 | 2007-03-27 | 2007-07-25 | 2008-04-04 | 2008-07-17 | 254 | 188 | Eroneous entry of MRB (RFA) | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Aurora | 050505025 | Slope Protection/Grouted Riprap | 1 | 557764 | 342720 | 215044 | 342720 | 3/3 | 187667.17 | 530387.17 | 342720 | 187667.17 | 100% | 100% | 87.27% | 95.09% | 100% | 2003-12-04 | 2004-03-23 | 2004-06-08 | 2005-01-12 | 2005-01-14 | 218 | 33 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Calzada Pob (Brgy 7) | 050505008 | Construction of Drainage System Phase II | 1 | 623690 | 380260 | 243430 | 352370 | 0.33333 | 236978.5 | 589348.5 | 352370 | 236978.5 | 100% | 100% | 97.35% | 94.49% | 100% | 2006-04-03 | 2006-05-23 | 2006-09-11 | 2008-12-31 | no data | 842 | 105 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Calzada Pob (Brgy 7) | 050505008 | Construction of Drainage System | 1 | 287500 | 110661.67 | 176838.33 | 110661.67 | 3/3 | 171616.83 | 282278.5 | 110661.67 | 171616.83 | 100% | 100% | 97.05% | 98.18% | 100% | 2005-06-23 | 2005-07-15 | 2005-09-08 | 2006-01-13 | no data | 127 | 123 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Mamlad | 050505016 | Rehab./Improvement of Farm to Market Road | 1 | 1000387 | 690000 | 310387 | 690000 | 3/3 | 317908 | 1007908 | 690000 | 317908 | 100% | 100% | 102.4% | 100.8% | 100% | 2003-12-04 | 2004-03-23 | 2004-07-03 | 2005-03-09 | 2005-03-12 | 249 | 173 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Quitinday - C2 | 050505009 | Water System Level II | 2 | 2038080.64 | 840160 | 1197920.64 | 760925.46 | 0/3 | 1023924.26 | 1784849.72 | 760925.46 | 1023924.26 | 100% | 100% | 85.48% | 87.58% | 100% | 2006-04-03 | 2006-05-23 | 2008-08-11 | 2008-11-22 | no data | 103 | 116 | for implementation | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Rizal | 050505004 | Water System Level II | 2 | 2038080.64 | 840160 | 1197920.64 | 760925.46 | 0/3 | 1023924.26 | 1784849.72 | 760925.46 | 1023924.26 | 100% | 100% | 85.48% | 87.58% | 100% | 2006-04-03 | 2006-05-23 | 2008-08-11 | 2008-11-22 | no data | 103 | 116 | for implementation | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | San Vicente - C3 | 050505022 | Rehab./Improvement of Farm to Market Road | 3 | 4046574 | 3150000 | 896574 | 3150000 | 3/3 | 896470 | 4046470 | 3150000 | 896470 | 100% | 100% | 99.99% | 100% | 100% | 2003-12-04 | 2004-03-23 | 2004-06-22 | 2005-03-09 | 2005-03-17 | 260 | 314 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Bautista | 050505011 | Rehab./Improvement of Farm to Market Road | 3 | 4046574 | 3150000 | 896574 | 3150000 | 3/3 | 896470 | 4046470 | 3150000 | 896470 | 100% | 100% | 99.99% | 100% | 100% | 2003-12-04 | 2004-03-23 | 2004-06-22 | 2005-03-09 | 2005-03-17 | 260 | 314 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Bagacay | 050505003 | Rehab./Improvement of Farm to Market Road | 3 | 4046574 | 3150000 | 896574 | 3150000 | 3/3 | 896470 | 4046470 | 3150000 | 896470 | 100% | 100% | 99.99% | 100% | 100% | 2003-12-04 | 2004-03-23 | 2004-06-22 | 2005-03-09 | 2005-03-17 | 260 | 314 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Sinagaran | 050505023 | Construction of Brgy. Health Station | 1 | 665210 | 462980 | 202230 | 462975.83 | 0.33333 | 199865.17 | 662841 | 462975.83 | 199865.17 | 100% | 100% | 98.83% | 99.64% | 100% | 2006-04-03 | 2006-05-23 | 2006-09-04 | 2007-07-30 | no data | 329 | 108 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Villa Paz - C5 | 050505024 | Rehab./Improvement of Farm to Market Road | 5 | 5185000 | 3848338.33 | 1336661.67 | 3848338.33 | 3/3 | 1198782.67 | 5047121 | 3848338.33 | 1198782.67 | 100% | 100% | 89.68% | 97.34% | 100% | 2005-06-23 | 2005-07-15 | 2005-10-24 | 2006-06-30 | no data | 249 | 154 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Maogog | 050505017 | Rehab./Improvement of Farm to Market Road | 5 | 5185000 | 3848338.33 | 1336661.67 | 3848338.33 | 3/3 | 1198782.67 | 5047121 | 3848338.33 | 1198782.67 | 100% | 100% | 89.68% | 97.34% | 100% | 2005-06-23 | 2005-07-15 | 2005-10-24 | 2006-06-30 | no data | 249 | 154 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | White Deer - C4 | 050505010 | Improvement of FMR on Critical Sections | 4 | 3922600 | 2941000 | 981600 | 2941000 | 3/3 | 943310.74 | 3884310.74 | 2941000 | 943310.74 | 100% | 100% | 96.1% | 99.02% | 100% | 2005-06-24 | 2005-07-16 | 2005-10-24 | 2006-06-30 | no data | 249 | 110 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | San Isidro | 050505020 | Improvement of FMR on Critical Sections | 4 | 3922600 | 2941000 | 981600 | 2941000 | 3/3 | 943310.74 | 3884310.74 | 2941000 | 943310.74 | 100% | 100% | 96.1% | 99.02% | 100% | 2005-06-24 | 2005-07-16 | 2005-10-24 | 2006-06-30 | no data | 249 | 110 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | San Roque | 050505021 | Improvement of FMR on Critical Sections | 4 | 3922600 | 2941000 | 981600 | 2941000 | 3/3 | 943310.74 | 3884310.74 | 2941000 | 943310.74 | 100% | 100% | 96.1% | 99.02% | 100% | 2005-06-24 | 2005-07-16 | 2005-10-24 | 2006-06-30 | no data | 249 | 110 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | Del Rosario | 050505013 | Improvement of FMR on Critical Sections | 4 | 3922600 | 2941000 | 981600 | 2941000 | 3/3 | 943310.74 | 3884310.74 | 2941000 | 943310.74 | 100% | 100% | 96.1% | 99.02% | 100% | 2005-06-24 | 2005-07-16 | 2005-10-24 | 2006-06-30 | no data | 249 | 110 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Jovellar | 050505 | White Deer - C5 | 050505010 | Rehab./Improvement of Farm to Market Road | 5 | 3689609 | 2717280 | 972329 | 2717280 | 3/3 | 974391.98 | 3691671.98 | 2717280 | 974391.98 | 100% | 100% | 100.2% | 100.1% | 100% | 2003-12-04 | 2004-03-23 | 2004-07-07 | 2005-04-13 | 2005-04-14 | 280 | 874 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Apud | 050507002 | Construction of Flood Control | 1 | 943515 | 639215 | 304300 | 639215 | 3/3 | 271000 | 910215 | 639215 | 271000 | 100% | 100% | 89.06% | 96.47% | 100% | no data | 2005-06-30 | 2006-09-21 | 2007-04-30 | no data | 221 | 386 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Apud | 050507002 | Construction of Slope protection | 1 | 1407551.73 | 1137900 | 269651.73 | 1024110 | 1/3 | 357830.82 | 1381940.82 | 1024110 | 357830.82 | 100% | 100% | 132.7% | 98.18% | 100% | 2007-06-20 | not conducted | 2008-07-30 | 2008-12-30 | no data | 153 | 386 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Bariw | 050507011 | Rehab./Improvement of Farm to Market Road | 1 | 918840 | 638040 | 280800 | 638040 | 3/3 | 281200 | 919240 | 638040 | 281200 | 100% | 100% | 100.1% | 100% | 100% | no data | 2005-06-30 | 2006-02-16 | 2006-11-08 | no data | 265 | 191 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Bariw | 050507011 | Construction of Water System Level 2 | 1 | 1399817.27 | 1131000 | 268817.27 | 1057501.92 | 1/3 | 234817.28 | 1292319.2 | 1057501.92 | 234817.28 | 100% | 100% | 87.35% | 92.32% | 100% | 2007-06-20 | not conducted | 2008-11-05 | 2009-04-30 | no data | 176 | 191 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Buga | 050507013 | Construction of Fish landing | 1 | 2367878.66 | 1928300 | 439578.66 | 1828019.92 | 1/3 | 515642.91 | 2343662.83 | 1828019.92 | 515642.91 | 100% | 100% | 117.3% | 98.98% | 100% | 2007-06-20 | not conducted | 2008-09-10 | 2008-12-30 | no data | 111 | 634 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Caguscos | 050507016 | Construction of Water System Level 2 | 1 | 0 |  |  |  |  | 1485709.02 | 1485709.02 |  | 1485709.02 | #DIV/0! | 100% | #DIV/0! | #DIV/0! | 100% | 2007-06-20 | not conducted | 2008-11-25 | 2009-06-25 | no data | 212 | 144 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Mabayawas | 050507022 | Rehab./Improvement of Farm to Market Road | 1 | 774651.5 | 541720.5 | 232931 | 541720.5 | 3/3 | 211351 | 753071.5 | 541720.5 | 211351 | 100% | 100% | 90.74% | 97.21% | 100% | no data | 2005-06-30 | 2006-01-12 | 2006-11-08 | no data | 300 | 75 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Macabugcos - C2 | 050507023 | Construction of Farm to Market Road | 2 | 1584200 | 1224200 | 360000 | 1157168.59 | 1/3 | 361000 | 1518168.59 | 1157168.59 | 361000 | 100% | 100% | 100.3% | 95.83% | 100% | 2007-06-20 | not conducted | 2008-09-01 | 2009-05-25 | no data | 266 | 549 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Magallang - C2 | 050507024 | Rehab. of Water System | 2 | 2494869 | 1679717 | 815152 | 1679717 | 3/3 | 720357 | 2400074 | 1679717 | 720357 | 100% | 100% | 88.37% | 96.2% | 100% | no data | 2005-06-30 | 2006-05-09 | 2007-05-30 | no data | 386 | 69 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Bonbon | 050507012 | Rehab. of Water System | 2 | 2494869 | 1679717 | 815152 | 1679717 | 3/3 | 720357 | 2400074 | 1679717 | 720357 | 100% | 100% | 88.37% | 96.2% | 100% | no data | 2005-06-30 | 2006-05-09 | 2007-05-30 | no data | 386 | 69 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Natasan | 050507029 | Rehab./Improvement of Farm to Market Road | 1 | 1010059.7 | 716445.1 | 293614.6 | 716445.1 | 3/3 | 293247.6 | 1009692.7 | 716445.1 | 293247.6 | 100% | 100% | 99.88% | 99.96% | 100% | no data | 2005-06-30 | 2006-02-11 | 2006-11-08 | no data | 270 | 173 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Niño Jesus | 050507045 | Rehab./Improvement of Farm to Market Road | 1 | 526768.8 | 364051 | 162717.8 | 364051 | 3/3 | 142227.8 | 506278.8 | 364051 | 142227.8 | 100% | 100% | 87.41% | 96.11% | 100% | no data | 2005-06-30 | 2005-12-08 | 2006-11-08 | no data | 335 | 77 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Nogpo | 050507030 | Construction of Fish landing | 1 | 1743866.84 | 1414700 | 329166.84 | 1374321.94 | 1/3 | 389647.4 | 1763969.34 | 1374321.94 | 389647.4 | 100% | 100% | 118.4% | 101.2% | 100% | 2007-06-20 | not conducted | 2008-11-05 | 2009-06-30 | no data | 237 | 327 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Pantao | 050507031 | Construction Public Market | 1 | 4715640.37 | 2976500 | 1739140.37 | 2976500 | 3/3 | 2130700.37 | 5107200.37 | 2976500 | 2130700.37 | 100% | 100% | 122.5% | 108.3% | 100% | no data | 2005-06-30 | 2006-01-11 | 2006-11-08 | no data | 301 | 1226 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Rawis | 050507033 | Construction of Auxiliary Dam | 1 | 2061034.14 | 1675500 | 385534.14 | 1675500 | 1/3 | 464684.14 | 2140184.14 | 1675500 | 464684.14 | 100% | 100% | 120.5% | 103.8% | 100% | 2007-06-20 | not conducted | 2008-06-02 | 2008-08-02 | no data | 61 | 381 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Sagrada Familia | 050507034 | Construction of Farm to Market Road | 1 | 2023400 | 1573400 | 450000 | 1386264.72 | 1/3 | 569570.03 | 1955834.75 | 1386264.72 | 569570.03 | 100% | 100% | 126.6% | 96.66% | 100% | 2007-06-20 | not conducted | 2008-05-15 | 2008-11-30 | no data | 199 | 268 | completed as built | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Sampongan - C2 | 050507036 | Rehab./Improvement of Farm to Market Road | 2 | 2445875 | 1704375 | 741500 | 1704375 | 3/3 | 713780 | 2418155 | 1704375 | 713780 | 100% | 100% | 96.26% | 98.87% | 100% | no data | 2005-06-30 | 2006-03-20 | 2006-11-08 | no data | 233 | 79 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Malabiga | 050507025 | Rehab./Improvement of Farm to Market Road | 2 | 2445875 | 1704375 | 741500 | 1704375 | 3/3 | 713780 | 2418155 | 1704375 | 713780 | 100% | 100% | 96.26% | 98.87% | 100% | no data | 2005-06-30 | 2006-03-20 | 2006-11-08 | no data | 233 | 79 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | San Antonio | 050507038 | Construction of Farm to Market Road | 1 | 1273174.23 | 817900 | 455274.23 | 743110 | 1/3 | 456274.22 | 1199384.22 | 743110 | 456274.22 | 100% | 100% | 100.2% | 94.2% | 100% | 2007-06-20 | not conducted | 2008-03-01 | 2008-07-01 | no data | 122 | 248 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | San Pascual - C3 | 050507041 | Rehab./Improvement of Farm to Market Road | 3 | 3278321.44 | 2287188.9 | 991132.54 | 2287188.9 | 0.66667 | 968429.5 | 3255618.4 | 2287188.9 | 968429.5 | 100% | 100% | 97.71% | 99.31% | 100% | no data | 2005-06-30 | 2006-04-24 | 2007-07-20 | no data | 452 | 176 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Salvacion | 050507035 | Rehab./Improvement of Farm to Market Road | 3 | 3278321.44 | 2287188.9 | 991132.54 | 2287188.9 | 0.66667 | 968429.5 | 3255618.4 | 2287188.9 | 968429.5 | 100% | 100% | 97.71% | 99.31% | 100% | no data | 2005-06-30 | 2006-04-24 | 2007-07-20 | no data | 452 | 176 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Matara | 050507027 | Rehab./Improvement of Farm to Market Road | 3 | 3278321.44 | 2287188.9 | 991132.54 | 2287188.9 | 0.66667 | 968429.5 | 3255618.4 | 2287188.9 | 968429.5 | 100% | 100% | 97.71% | 99.31% | 100% | no data | 2005-06-30 | 2006-04-24 | 2007-07-20 | no data | 452 | 176 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | San Ramon | 050507042 | Rehab./Improvement of Farm to Market Road | 1 | 646090 | 408290 | 237800 | 408290 | 3/3 | 175770 | 584060 | 408290 | 175770 | 100% | 100% | 73.92% | 90.4% | 100% | no data | 2005-06-30 | 2006-04-24 | 2006-11-08 | no data | 198 | 137 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | San Ramon | 050507042 | Construction of Farm to Market Road | 1 | 1433554.23 | 1159300 | 274254.23 | 1098429.51 | 1/3 | 316254.24 | 1414683.75 | 1098429.51 | 316254.24 | 100% | 100% | 115.3% | 98.68% | 100% | 2007-06-20 | not conducted | 2008-08-20 | 2009-05-25 | no data | 278 | 137 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Sta. Cruz | 050507044 | Road Rehabilitation | 1 | 988275.4 | 670282 | 317993.4 | 670282 | 3/3 | 304920.05 | 975202.05 | 670282 | 304920.05 | 100% | 100% | 95.89% | 98.68% | 100% | no data | 2005-06-30 | 2006-01-17 | 2006-11-08 | no data | 295 | 202 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Talin-talin | 050507046 | Construction of Farm to Market Road | 1 | 1803518.8 | 1461900 | 341618.8 | 1365278.51 | 1/3 | 357648.8 | 1722927.31 | 1365278.51 | 357648.8 | 100% | 100% | 104.7% | 95.53% | 100% | 2007-06-20 | not conducted | 2008-06-02 | 2008-08-02 | no data | 61 | 248 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Tambo | 050507047 | Rehab, of Tambo-Palo Road Section | 1 | 859579.2 | 585980 | 273599.2 | 585980 | 3/3 | 281419.85 | 867399.85 | 585980 | 281419.85 | 100% | 100% | 102.9% | 100.9% | 100% | no data | 2005-06-30 | 2006-03-14 | 2006-11-08 | no data | 239 | 130 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Zone 5 | 050507008 | Reinforced Concrete Box Culvert | 1 | 746597.5 | 575900 | 170697.5 | 549491.11 | 3/3 | 201697.5 | 751188.61 | 549491.11 | 201697.5 | 100% | 100% | 118.2% | 100.6% | 100% | 2007-06-20 | not conducted | 2007-12-05 | 2008-01-25 | no data | 51 | 170 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Zone 6 | 050507009 | Construction of Flood Control | 1 | 456927 | 264713.75 | 192213.25 | 211771 | 3/3 | 175388.25 | 387159.25 | 211771 | 175388.25 | 100% | 100% | 91.25% | 84.73% | 100% | no data | 2005-06-30 | 2005-09-01 | 2006-11-08 | no data | 433 | 124 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Libon | 050507 | Zone 7 | 050507010 | Construction of Flood Control | 1 | 1011824.5 | 676424.5 | 335400 | 676424.5 | 3/3 | 287062.5 | 963487 | 676424.5 | 287062.5 | 100% | 100% | 85.59% | 95.22% | 100% | no data | 2005-06-30 | 2006-09-19 | 2006-12-13 | 2007-02-01 | 85 | 317 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Agol | 050513001 | Construction of 3-Classroom School Bldg. | 1 | 1135358.7 | 701313.45 | 434045.25 | 701313.45 | 3/3 | 475549.28 | 1176862.73 | 701313.45 | 475549.28 | 100% | 100% | 109.6% | 103.7% | 100% | 2005-05-05 | 2005-07-05 | 2005-11-14 | 2006-06-15 | no data | 213 | 223 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Agol | 050513001 | Construction of Water System | 1 | 991783.43 | 627366.31 | 364417.12 | 626935.87 | 1/3 | 223177.12 | 850112.99 | 626935.87 | 223177.12 | 100% | 100% | 61.24% | 85.72% | 100% | 2007-07-16 | not conducted | 2008-07-01 | 2008-12-20 | no data | 172 | 223 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Alabangpuro | 050513002 | Construction of Water System Level 2 | 1 | 680431.5 | 416704.13 | 263727.37 | 416704.13 | 3/3 | 236827.39 | 653531.52 | 416704.13 | 236827.39 | 100% | 100% | 89.8% | 96.05% | 100% | 2005-05-05 | 2005-07-05 | 2005-10-24 | 2006-08-30 | 2006-09-20 | 310 | 112 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Alabangpuro | 050513002 | Rehabilitation of Farm to Market Road | 1 | 2132446.19 | 1428957.93 | 703488.26 | 1428957.93 | 0.66667 | 834554.2 | 2263512.13 | 1428957.93 | 834554.2 | 100% | 100% | 118.6% | 106.1% | 100% | 2006-08-04 | not conducted | 2007-02-26 | 2007-05-09 | no data | 72 | 156 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Banawan | 050513005 | Construction of Irrigation Canal | 1 | 610267.5 | 413000 | 197267.5 | 350030.12 | 1/3 | 173745.75 | 523775.87 | 350030.12 | 173745.75 | 100% | 100% | 88.08% | 85.83% | 100% | 2007-07-16 | not conducted | 2008-01-01 | 2008-12-20 | no data | 354 | 574 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Barangay 1 | 050513023 | Construction of Water System Level 2 | 1 | 1067612.69 | 711489.99 | 356122.7 | 711489.99 | 3/3 | 341962.69 | 1053452.68 | 711489.99 | 341962.69 | 100% | 100% | 96.02% | 98.67% | 100% | 2005-06-08 | 2005-07-28 | 2005-10-10 | 2006-03-16 | 2006-03-15 | 157 | 638 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Barangay 1 | 050513023 | Construction of Day Care Center | 1 | 671198.85 | 308143.24 | 363055.61 | 308143.24 | 0.66667 | 455003 | 763146.24 | 308143.24 | 455003 | 100% | 100% | 125.3% | 113.7% | 100% | 2006-08-04 | not conducted | 2006-11-15 | 2007-02-23 | no data | 100 | 605 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Barangay 2 | 050513024 | Construction of Drainage System | 1 | 1134387.5 | 723658 | 410729.5 | 723186.55 | 1/3 | 376672 | 1099858.55 | 723186.55 | 376672 | 100% | 100% | 91.71% | 96.96% | 100% | 2007-07-16 | not conducted | 2008-06-01 | 2008-12-21 | no data | 203 | 294 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Barangay 4 | 050513026 | Construction of Water System Level 2 | 1 | 610169 | 417219.41 | 192949.59 | 417219.41 | 3/3 | 194375 | 611594.41 | 417219.41 | 194375 | 100% | 100% | 100.7% | 100.2% | 100% | 2005-06-08 | 2005-07-28 | 2005-09-28 | 2006-03-16 | 2006-03-15 | 169 | 378 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Barangay 4 | 050513026 | Construction of Drainage System | 1 | 1236697.5 | 901831 | 334866.5 | 901831 | 1/3 | 432427.5 | 1334258.5 | 901831 | 432427.5 | 100% | 100% | 129.1% | 107.9% | 100% | 2007-07-16 | not conducted | 2008-06-25 | 2008-12-30 | no data | 188 | 295 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Barangay 5 | 050513027 | Construction of Water System Level 2 | 1 | 754623.35 | 510869 | 243754.35 | 510869 | 3/3 | 214705.12 | 725574.12 | 510869 | 214705.12 | 100% | 100% | 88.08% | 96.15% | 100% | 2005-06-08 | 2005-07-28 | 2005-10-12 | 2006-03-16 | 2006-03-15 | 155 | 376 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Barangay 5 | 050513027 | Construction of Flood Control | 1 | 3537504.5 | 2447425 | 1090079.5 | 2447425 | 0.33333 | 1044511.5 | 3491936.5 | 2447425 | 1044511.5 | 100% | 100% | 95.82% | 98.71% | 100% | 2006-08-04 | not conducted | 2006-11-20 | 2007-11-30 | no data | 375 | 376 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Barangay 5 | 050513027 | Community Learning Center | 1 | 675826.88 | 469299 | 206527.88 | 375439.2 | 1/3 | 209132.88 | 584572.08 | 375439.2 | 209132.88 | 100% | 100% | 101.3% | 86.5% | 100% | 2007-07-16 | not conducted | 2008-04-01 | 2008-06-01 | no data | 61 | 429 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Buyo | 050513008 | Road Rehabilitation | 1 | 2955513.25 | 2233736 | 721777.25 | 1786988.8 | 1/3 | 670297.3 | 2457286.1 | 1786988.8 | 670297.3 | 100% | 100% | 92.87% | 83.14% | 100% | 2007-07-16 | not conducted | 2008-10-10 | 2009-11-30 | no data | 416 | 93 | completed as built | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Caratagan | 050513009 | Road Rehabilitation | 1 | 1330982.23 | 803741 | 527241.23 | 803741 | 1/3 | 479831.33 | 1283572.33 | 803741 | 479831.33 | 100% | 100% | 91.01% | 96.44% | 100% | 2007-07-16 | not conducted | 2008-08-01 | 2009-06-25 | no data | 328 | 648 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Flores | 050513011 | Rehab./Improvement of Farm to Market Road | 1 | 1301605.2 | 808256.36 | 493348.84 | 808256.36 | 3/3 | 451898.92 | 1260155.28 | 808256.36 | 451898.92 | 100% | 100% | 91.6% | 96.82% | 100% | 2005-05-05 | 2005-07-05 | 2006-01-09 | 2006-08-18 | 2006-09-20 | 221 | 220 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | La Medalla | 050513033 | Construction of Water System Level 2 | 1 | 595669.94 | 405425.02 | 190244.92 | 405425.02 | 3/3 | 191644.72 | 597069.74 | 405425.02 | 191644.72 | 100% | 100% | 100.7% | 100.2% | 100% | 2005-06-08 | 2005-07-28 | 2005-10-04 | 2006-07-14 | 2006-09-20 | 283 | 368 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Lawinon | 050513012 | Road Rehabilitation | 1 | 3142817 | 2485248 | 657569 | 1996198.4 | 1/3 | 699844 | 2696042.4 | 1996198.4 | 699844 | 100% | 100% | 106.4% | 85.78% | 100% | completed as built | not conducted | 2008-10-25 | 2009-11-30 | no data | 401 | 204 | completed as built | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Macasitas | 050513013 | Rehab./Improvement of Farm to Market Road | 1 | 3228273.6 | 2279593.68 | 948679.92 | 2279593.64 | 3/3 | 941364.9 | 3220958.54 | 2279593.64 | 941364.9 | 100% | 100% | 99.23% | 99.77% | 100% | 2005-05-05 | 2005-07-05 | 2005-11-04 | 2006-11-15 | 2006-09-20 | 376 | 102 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-duran | 050513 | Malidong | 050513015 | Construction of High School Building | 1 | 1538992.6 | 1071163 | 467829.6 | 1071163 | 2/3 | 396004.5 | 1467167.5 | 1071163 | 396004.5 | 100% | 100% | 84.65% | 95.33% | 100% | 2007-07-16 | not conducted | 2008-03-01 | 2008-05-01 | no data | 61 | 314 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Mamlad | 050513016 | Rehabilitation of Farm to Market Road | 1 | 2769645 | 1911562 | 858083 | 1911562 | 0.33333 | 866316.1 | 2777878.1 | 1911562 | 866316.1 | 100% | 100% | 101% | 100.3% | 100% | 2006-08-04 | not conducted | 2007-02-26 | 2007-07-01 | no data | 125 | 125 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Marigondon | 050513017 | Construction of Water System Level 2 | 1 | 855785.3 | 580505.01 | 275280.29 | 580505.01 | 3/3 | 258735.6 | 839240.61 | 580505.01 | 258735.6 | 100% | 100% | 93.99% | 98.07% | 100% | 2005-06-08 | 2005-07-28 | 2005-10-04 | 2006-03-09 | 2006-03-15 | 156 | 218 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Nablangbulod | 050513019 | Rehab./Improvement of Farm to Market Road | 1 | 1632601.25 | 1122377.88 | 510223.37 | 1122377.88 | 3/3 | 453814.34 | 1576192.22 | 1122377.88 | 453814.34 | 100% | 100% | 88.94% | 96.54% | 100% | 2005-06-08 | 2005-07-28 | 2005-10-05 | 2006-05-16 | 2006-05-16 | 223 | 119 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Nablangbulod | 050513019 | Construction of Three (3) - Classroom Elementary Building | 1 | 1355017.65 | 916596 | 438421.65 | 916596 | 0.66667 | 375781.66 | 1292377.66 | 916596 | 375781.66 | 100% | 100% | 85.71% | 95.38% | 100% | 2006-08-04 | not conducted | 2006-11-13 | 2007-02-26 | no data | 105 | 159 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Oringon | 050513020 | Rehabilitation of Farm to Market Road | 1 | 2965370.84 | 2037124.83 | 928246.01 | 2037124.83 | 0.66667 | 924048.4 | 2961173.23 | 2037124.83 | 924048.4 | 100% | 100% | 99.55% | 99.86% | 100% | 2006-08-04 | not conducted | 2006-02-26 | 2008-03-21 | no data | 754 | 97 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Rawis | 050513028 | Rehab./Improvement of Farm to Market Road | 1 | 2781511.24 | 1931229.09 | 850282.15 | 1931229.09 | 3/3 | 729252.15 | 2660481.24 | 1931229.09 | 729252.15 | 100% | 100% | 85.77% | 95.65% | 100% | 2005-06-08 | 2005-07-28 | 2005-10-10 | 2006-09-11 | 2006-09-20 | 336 | 198 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Pio-Duran | 050513 | Rawis | 050513028 | Concreting of Farm to Market Road | 1 | 1261870 | 850191 | 411679 | 850191 | 0.66667 | 381409.57 | 1231600.57 | 850191 | 381409.57 | 100% | 100% | 92.65% | 97.6% | 100% | 2006-08-04 | not conducted | 2007-03-22 | 2007-05-28 | no data | 67 | 198 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Bagaobawan | 050515003 | Concreting of Barangay Pathway | 1 | 528847 | 348261 | 180586 | 348261 | no data | 0 | 348261 | 348261 | 0 | 100% | #DIV/0! | 0% | 65.85% | 100% | 2006-07-26 | not conducted | 2006-10-18 | 2007-07-12 | no data | 267 | 112 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Bagaobawan | 050515003 | Construction of Water System Level 2 | 1 | 741300 | 508200 | 233100 | 508200 | 0.33333 | 195584.56 | 703784.56 | 508200 | 195584.56 | 100% | 100% | 83.91% | 94.94% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2008-11-25 | no data | 238 | 140 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Batan | 050515004 | Day Care Center | 1 | 825700 | 524025 | 301675 | 516416.84 | 0.33333 | 275051 | 791467.84 | 516416.84 | 275051 | 100% | 100% | 91.17% | 95.85% | 100% | 2007-07-31 | not conducted | 2008-08-01 | 2009-05-25 | no data | 297 | 216 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Bilbao | 050515005 | Construction of Three-Classroom High School Building | 1 | 1530995 | 1036072 | 494923 | 1036072 | 3/3 | 428538.28 | 1464610.28 | 1036072 | 428538.28 | 100% | 100% | 86.59% | 95.66% | 100% | 2006-07-26 | not conducted | 2006-10-09 | 2007-06-30 | no data | 264 | 172 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Buenavista | 050515008 | Construction of Day Care Center | 1 | 656051 | 431427 | 224624 | 431427 | 3/3 | 316144 | 747571 | 431427 | 316144 | 100% | 100% | 140.7% | 114% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-19 | 2006-06-26 | 2006-07-25 | 250 | 113 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Buhatan | 050515009 | Construction of Water System Level 2 | 1 | 1423789.02 | 963650.17 | 460138.85 | 963650.17 | 3/3 | 455986 | 1419636.17 | 963650.17 | 455986 | 100% | 100% | 99.1% | 99.71% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-10 | 2006-05-15 | 2006-04-02 | 217 | 146 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Buhatan | 050515009 | Concreting of Barangay Pathway | 1 | 968977 | 597301 | 371676 | 597301 | 3/3 | 333725.65 | 931026.65 | 597301 | 333725.65 | 100% | 100% | 89.79% | 96.08% | 100% | 2006-07-26 | not conducted | 2006-10-23 | 2007-04-25 | 2007-04-25 | 184 | 146 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Calanaga | 050515010 | Construction of Water System Level 2 | 1 | 1178290.52 | 741701.11 | 436589.41 | 741701.11 | 3/3 | 380284 | 1121985.11 | 741701.11 | 380284 | 100% | 100% | 87.1% | 95.22% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-05 | 2006-03-10 | 2006-04-08 | 156 | 120 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Calanaga | 050515010 | Construction of Sea Port | 1 | 1150962 | 690600 | 460362 | 690600 | 0.33333 | 478600 | 1169200 | 690600 | 478600 | 100% | 100% | 104% | 101.6% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-04-25 | no data | 389 | 160 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Caracaran | 050515011 | Rehab./Improvement of Water System Level 2 | 1 | 1380969.12 | 912230.05 | 468739.07 | 912230.05 | 3/3 | 408576 | 1320806.05 | 912230.05 | 408576 | 100% | 100% | 87.16% | 95.64% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-22 | 2006-03-25 | 2006-04-04 | 154 | 212 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Caracaran | 050515011 | Day Care Center | 1 | 679425 | 466270 | 213155 | 463564.25 | 0.33333 | 175755 | 639319.25 | 463564.25 | 175755 | 100% | 100% | 82.45% | 94.1% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-04-25 | no data | 389 | 288 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Carogcog | 050515012 | Construction of Bridge | 1 | 369801 | 237895 | 131906 | 237895 | 3/3 | 118530 | 356425 | 237895 | 118530 | 100% | 100% | 89.86% | 96.38% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-12 | 2006-03-08 | 2006-03-27 | 147 | 63 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Carogcog | 050515012 | Construction of Water System Level 2 | 1 | 548260 | 315430 | 232830 | 315430 | 0.33333 | 174453.35 | 489883.35 | 315430 | 174453.35 | 100% | 100% | 74.93% | 89.35% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2008-10-01 | no data | 183 | 74 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Dapdap | 050515013 | Concreting of Barangay Pathway | 1 | 409143.35 | 275292.33 | 133851.02 | 275292.33 | 3/3 | 139543 | 414835.33 | 275292.33 | 139543 | 100% | 100% | 104.3% | 101.4% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-13 | 2006-02-25 | 2006-04-06 | 135 | 125 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Gaba | 050515013 | Construction of 2-Classroom School Bldg. | 1 | 1005790.13 | 764129.76 | 241660.37 | 764129.76 | 3/3 | 369132 | 1133261.76 | 764129.76 | 369132 | 100% | 100% | 152.7% | 112.7% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-07 | 2006-03-15 | 2006-04-18 | 159 | 185 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Gaba | 050515014 | Construction of Water System Level 2 | 1 | 742260 | 500090 | 242170 | 400072 | 0.33333 | 190826.56 | 590898.56 | 400072 | 190826.56 | 100% | 100% | 78.8% | 79.61% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2008-12-20 | no data | 263 | 190 | completed as built | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Galicia | 050515014 | Rehabilitation/Improvement of Water System Level 2 | 1 | 879170 | 596713 | 282457 | 596713 | 3/3 | 322557.28 | 919270.28 | 596713 | 322557.28 | 100% | 100% | 114.2% | 104.6% | 100% | 2006-07-26 | not conducted | 2006-10-16 | 2007-04-24 | 2007-04-24 | 190 | 306 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Guadalupe | 050515016 | Construction of Multi-Purpose Bldg. | 1 | 797458 | 545313 | 252145 | 545313 | 3/3 | 252145 | 797458 | 545313 | 252145 | 100% | 100% | 100% | 100% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-19 | 2006-03-25 | 2006-07-18 | 157 | 60 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Hamorawon | 050515017 | Construction of 2-Classroom School Bldg. | 1 | 816052.06 | 504746.1 | 311305.96 | 504746.1 | 3/3 | 255807 | 760553.1 | 504746.1 | 255807 | 100% | 100% | 82.17% | 93.2% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-17 | 2006-02-10 | 2006-04-01 | 116 | 194 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Hamorawon | 050515017 | Construction of 2 Room School Bldg | 1 | 1026730 | 701380 | 325350 | 685994.1 | 0.33333 | 308923.1 | 994917.2 | 685994.1 | 308923.1 | 100% | 100% | 94.95% | 96.9% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2008-12-20 | no data | 263 | 103 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Lagundi | 050515018 | Construction of 2-Classroom School Bldg. | 1 | 818988.22 | 536835.42 | 282152.8 | 536835.42 | 3/3 | 261046 | 797881.42 | 536835.42 | 261046 | 100% | 100% | 92.52% | 97.42% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-10 | 2006-03-19 | 2006-04-05 | 160 | 94 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Lagundi | 050515018 | Concreting of Pathway | 1 | 624637 | 368570 | 256067 | 362570 | 0.33333 | 185202.5 | 547772.5 | 362570 | 185202.5 | 100% | 100% | 72.33% | 87.69% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2008-10-01 | no data | 183 | 110 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Liguan | 050515019 | Construction of Day Care Center | 1 | 684540 | 468720 | 215820 | 468720 | 0.33333 | 181488 | 650208 | 468720 | 181488 | 100% | 100% | 84.09% | 94.98% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-04-25 | no data | 389 | 137 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Linao | 050515020 | Construction of 2-Classroom School Bldg. | 1 | 775627.3 | 516557.3 | 259070 | 516557.3 | 3/3 | 255360 | 771917.3 | 516557.3 | 255360 | 100% | 100% | 98.57% | 99.52% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-11 | 2006-06-12 | 2006-07-27 | 244 | 60 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Linao | 050515020 | Construction of Day Care Center | 1 | 777355.6 | 545548.9 | 231806.7 | 545548.9 | no data | 172871.1 | 718420 | 545548.9 | 172871.1 | 100% | 100% | 74.58% | 92.42% | 100% | 2006-09-01 | not conducted | 2007-03-28 | 2007-11-28 | no data | 245 | 60 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Mananao | 050515022 | Construction of Bridge | 1 | 1499500 | 1018480 | 481020 | 1018480 | 0.33333 | 368424 | 1386904 | 1018480 | 368424 | 100% | 100% | 76.59% | 92.49% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-12-20 | no data | 628 | 225 |  | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Mancao | 050515023 | Construction of Barangay Health Station | 1 | 817847 | 563035 | 254812 | 563035 | no data | 237510.72 | 800545.72 | 563035 | 237510.72 | 100% | 100% | 93.21% | 97.88% | 100% | 2006-07-26 | not conducted | 2006-11-07 | 2007-03-27 | no data | 140 | 245 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Mancao | 050515023 | Construction of Sea Port | 1 | 1490337 | 1050200 | 440137 | 1044664.84 | 0.33333 | 359591.56 | 1404256.4 | 1044664.84 | 359591.56 | 100% | 100% | 81.7% | 94.22% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-05-25 | no data | 419 | 232 | completed as built | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Manila | 050515024 | Rehabilitation/Improvement of Water System Level 2 | 1 | 873403 | 605046 | 268357 | 605046 | 3/3 | 301202.92 | 906248.92 | 605046 | 301202.92 | 100% | 100% | 112.2% | 103.8% | 100% | 2006-07-26 | not conducted | 2006-09-19 | 2007-04-19 | 2007-05-04 | 212 | 107 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Manila | 050515024 | Construction of Day Care Center | 1 | 694187 | 490070 | 204117 | 489890.28 | 0.33333 | 201764.57 | 691654.85 | 489890.28 | 201764.57 | 100% | 100% | 98.85% | 99.64% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-12-20 | no data | 628 | 137 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Masaga | 050515025 | Conreting of Pathway | 1 | 979000 | 664530 | 314470 | 645615.91 | 0.33333 | 266130.25 | 911746.16 | 645615.91 | 266130.25 | 100% | 100% | 84.63% | 93.13% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-12-20 | no data | 628 | 100 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Morocborocan | 050515026 | Construction of Day Care Center | 1 | 586355 | 421585 | 164770 | 421585 | 3/3 | 146966 | 568551 | 421585 | 146966 | 100% | 100% | 89.19% | 96.96% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-19 | 2006-03-10 | 2006-04-05 | 142 | 142 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Morocborocan | 050515026 | Construction of Mini-Pier | 1 | 3149651.2 | 1916621 | 1233030.2 | 1916621 | no data | 1137090 | 3053711 | 1916621 | 1137090 | 100% | 100% | 92.22% | 96.95% | 100% | 2006-09-01 | not conducted | 2007-02-05 | 2007-10-05 | no data | 242 | 142 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Nagcalsot | 050515027 | Concreting of Barangay Pathway | 1 | 1041383 | 653646 | 387737 | 653646 | 3/3 | 275976.95 | 929622.95 | 653646 | 275976.95 | 100% | 100% | 71.18% | 89.27% | 100% | 2006-07-26 | not conducted | 2006-10-16 | 2007-04-30 | 2007-06-29 | 196 | 143 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Sagrada | 050515030 | Concreting of Barangay Pathway | 1 | 970745.82 | 532152 | 438593.82 | 532152 | 3/3 | 452497 | 984649 | 532152 | 452497 | 100% | 100% | 103.2% | 101.4% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-06 | 2006-03-22 | 2006-04-07 | 167 | 93 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Sagrada | 050515030 | Concreting of Pathway | 1 | 1158000 | 795200 | 362800 | 783898.83 | 0.33333 | 302445 | 1086343.83 | 783898.83 | 302445 | 100% | 100% | 83.36% | 93.81% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2008-10-01 | no data | 183 | 121 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | San Ramon | 050515031 | Construction of One Classroom Elementary School Building | 1 | 654663 | 451185.4 | 203477.6 | 451185.4 | no data | 223692.6 | 674878 | 451185.4 | 223692.6 | 100% | 100% | 109.9% | 103.1% | 100% | 2006-09-01 | not conducted | 2007-01-22 | 2007-07-14 | no data | 173 | 267 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Sta. Barbara | 050515032 | Const. of Day Care Center | 1 | 662000 | 470000 | 192000 | 470000 | 0.33333 | 128531 | 598531 | 470000 | 128531 | 100% | 100% | 66.94% | 90.41% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-06-25 | no data | 450 | 35 | On-going | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Tinocawan | 050515033 | Rehab./Improvement of Water System Level 2 | 1 | 1179553.28 | 760721.22 | 418832.06 | 760721.22 | 3/3 | 357778 | 1118499.22 | 760721.22 | 357778 | 100% | 100% | 85.42% | 94.82% | 100% | 2005-06-01 | 2005-07-21 | 2005-10-12 | 2006-03-17 | 2006-04-03 | 156 | 115 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Tinopan | 050515034 | Construction of Water System Level 2 | 1 | 784809.3 | 528277.4 | 256531.9 | 528277.4 | no data | 255821.9 | 784099.3 | 528277.4 | 255821.9 | 100% | 100% | 99.72% | 99.91% | 100% | 2006-09-01 | not conducted | 2006-11-20 | 2007-07-15 | no data | 237 | 96 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Viga | 050515035 | Concreting of Pathway | 1 | 3049914 | 2024110 | 1025804 | 2024110 | 3/3 | 996764 | 3020874 | 2024110 | 996764 | 100% | 100% | 97.17% | 99.05% | 100% | 2005-06-01 | 2005-07-21 | 2005-09-28 | 2006-04-22 | 2006-07-26 | 206 | 81 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Viga | 050515035 | Construction of Day Care Center | 1 | 758401.74 | 528781.2 | 229620.54 | 528781.2 | no data | 252350.34 | 781131.54 | 528781.2 | 252350.34 | 100% | 100% | 109.9% | 103% | 100% | 2006-09-01 | not conducted | 2006-12-04 | 2007-07-13 | no data | 221 | 81 | Completed | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Villahermosa | 050515036 | Extension of Seaport | 1 | 2845376 | 1599926 | 1245450 | 1599926 | 3/3 | 1210865.58 | 2810791.58 | 1599926 | 1210865.58 | 100% | 100% | 97.22% | 98.78% | 100% | 2006-07-26 | not conducted | 2006-10-23 | 2007-04-30 | 2007-06-29 | 189 | 458 | Inaugurated | 1 | VISAYAS
V | 05 | Albay | 0505 | Rapu-rapu | 050515 | Villahermosa | 050515036 | Construction of Public Market | 1 | 1322267 | 920860 | 401407 | 920860 | 0.33333 | 337983.52 | 1258843.52 | 920860 | 337983.52 | 100% | 100% | 84.2% | 95.2% | 100% | 2007-07-31 | not conducted | 2008-04-01 | 2009-04-25 | no data | 389 | 480 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Calabaca | 051602003 | Construction of Rip-rap (Sea Wall) | 1 | 2771794.95 | 1665035.95 | 1106759 | 1665035.95 | 0.66667 | 1106759 | 2771794.95 | 1665035.95 | 1106759 | 100% | 100% | 100% | 100% | 100% | 2006-08-15 | not conducted | 2006-12-18 | 2008-03-18 | no data | 456 | 485 | On-going | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Camagsaan | 051602004 | Const. of Footbridge | 1 | 1751590 | 1310772 | 440818 | 1310772 | 0.33333 | 397678 | 1708450 | 1310772 | 397678 | 100% | 100% | 90.21% | 97.54% | 100% | 2007-07-19 | not conducted | 2008-04-01 | 2008-12-20 | no data | 263 | 168 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Catabaguangan | 051602005 | Construction of Water System Level 2 | 1 | 1364976.3 | 931000 | 433976.3 | 931000 | 1/3 | 488884.24 | 1419884.24 | 931000 | 488884.24 | 100% | 100% | 112.7% | 104% | 100% | 2007-07-19 | not conducted | 2008-07-01 | 2009-06-25 | no data | 359 | 124 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Del Pilar | 051602007 | Construction of Water System Level 2 | 1 | 1233995.9 | 924096 | 309899.9 | 831686.4 | 0.33333 | 252119.91 | 1083806.31 | 831686.4 | 252119.91 | 100% | 100% | 81.36% | 87.83% | 100% | 2007-07-19 | not conducted | 2008-06-01 | 2008-12-20 | no data | 202 | 242 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Itok | 051602008 | Construction of Water System Level 2 | 1 | 2054928.75 | 1476250 | 578678.75 | 1328625 | 0.33333 | 525735.75 | 1854360.75 | 1328625 | 525735.75 | 100% | 100% | 90.85% | 90.24% | 100% | 2006-08-15 | not conducted | 2006-11-22 | 2007-04-22 | no data | 151 | 277 | completed as built | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Itok - C2 | 051602008 | Improvement of Farm to Market Road | 2 | 2104609.97 | 1463238 | 641371.97 | 1463238 | 2/3 | 506183.12 | 1969421.12 | 1463238 | 506183.12 | 100% | 100% | 78.92% | 93.58% | 100% | 2007-07-19 | not conducted | 2008-08-01 | 2009-06-25 | no data | 328 | 350 | On-going | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Lucbanan | 051602009 | Improvement of Farm to Market Road | 1 | 5031513 | 3096120 | 1935393 | 3096120 | 3/3 | 1856354 | 4952474 | 3096120 | 1856354 | 100% | 100% | 95.92% | 98.43% | 100% | 2005-06-08 | 2005-07-13 | 2005-09-08 | 2007-01-31 | no data | 510 | 73 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Mabini | 051602010 | Construction of Water System Level 2 | 1 | 1309255 | 1032400 | 276855 | 1032400 | 3/3 | 285110 | 1317510 | 1032400 | 285110 | 100% | 100% | 103% | 100.6% | 100% | 2005-06-08 | 2005-07-13 | 2005-09-23 | 2006-09-27 | no data | 369 | 103 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Mabini | 051602010 | Rice Mill with Solar Dryer | 1 | 736865.8 | 557072.3 | 179793.5 | 501365.05 | 0.33333 | 179743.5 | 681108.55 | 501365.05 | 179743.5 | 100% | 100% | 99.97% | 92.43% | 100% | 2006-08-15 | not conducted | 2007-05-19 | 2007-07-19 | no data | 61 | 71 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Magsaysay | 051602015 | Construction of Four-Classroom High School Building | 1 | 2210189.3 | 1673458.25 | 536731.05 | 1673458.25 | 0.33333 | 517741.05 | 2191199.3 | 1673458.25 | 517741.05 | 100% | 100% | 96.46% | 99.14% | 100% | 2006-08-15 | not conducted | 2006-11-11 | 2007-04-21 | no data | 161 | 270 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Mataque | 051602012 | Construction of Day Care Center | 1 | 458467.25 | 262624 | 195843.25 | 262624 | 0.33333 | 217543.25 | 480167.25 | 262624 | 217543.25 | 100% | 100% | 111.1% | 104.7% | 100% | 2007-07-19 | not conducted | 2008-04-01 | 2008-12-20 | no data | 263 | 202 | On-going | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | San Antonio | 051602016 | Construction of Water System Level 2 | 1 | 1119329.4 | 802463.5 | 316865.9 | 802463.5 | 0.33333 | 424845.9 | 1227309.4 | 802463.5 | 424845.9 | 100% | 100% | 134.1% | 109.6% | 100% | 2006-08-15 | not conducted | 2006-11-29 | 2007-04-30 | no data | 152 | 84 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | San Isidro | 051602017 | Construction of Water System Level 2 | 1 | 774016 | 356877 | 417139 | 356877 | 3/3 | 413474 | 770351 | 356877 | 413474 | 100% | 100% | 99.12% | 99.53% | 100% | 2005-06-08 | 2005-07-13 | 2005-09-23 | 2006-10-25 | no data | 397 | 87 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | San Isidro | 051602017 | Ricemill w/ Solar Dryer | 1 | 676823.75 | 485018 | 191805.75 | 475564.41 | 0.33333 | 136682.8 | 612247.21 | 475564.41 | 136682.8 | 100% | 100% | 71.26% | 90.46% | 100% | 2007-07-19 | not conducted | 2008-07-01 | 2009-06-25 | no data | 359 | 76 | On-going | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | San Roque | 051602018 | Construction of Water System Level 2 | 1 | 1445446 | 524394 | 921052 | 524394 | 3/3 | 866523 | 1390917 | 524394 | 866523 | 100% | 100% | 94.08% | 96.23% | 100% | 2005-06-08 | 2005-07-13 | 2005-09-15 | 2006-10-26 | no data | 406 | 142 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Tanawan | 051602019 | Construction of Water System Level 2 | 1 | 2492444 | 1590209 | 902235 | 1590209 | 3/3 | 906544.5 | 2496753.5 | 1590209 | 906544.5 | 100% | 100% | 100.5% | 100.2% | 100% | 2005-06-08 | 2005-07-13 | 2005-09-25 | 2006-10-25 | no data | 395 | 83 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Villa Belen | 051602022 | Construction of Foot Bridge | 1 | 692399.9 | 425719.9 | 266680 | 425719.9 | 0.66667 | 221389.3 | 647109.2 | 425719.9 | 221389.3 | 100% | 100% | 83.02% | 93.46% | 100% | 2006-08-15 | not conducted | 2006-11-30 | 2007-03-30 | no data | 120 | 100 | Completed | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Capalonga | 051602 | Villa Belen | 051602022 | Construction of Water System Level 2 | 1 | 916176 | 680790 | 235386 | 680790 | 0.33333 | 202496.46 | 883286.46 | 680790 | 202496.46 | 100% | 100% | 86.03% | 96.41% | 100% | 2007-07-19 | not conducted | 2008-04-01 | 2008-12-20 | no data | 263 | 100 | On-going | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Basiad | 051610001 | Construction of Sea Wall | 1 | 1772179 | 1333791 | 438388 | 1333791 | 0.33333 | 445688 | 1779479 | 1333791 | 445688 | 100% | 100% | 101.7% | 100.4% | 100% | 2008-04-30 | not conducted | 2008-09-08 | 2009-03-25 | no data | 198 | 494 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Basiad | 051610001 | Construction of I Unit 2-Classroom High School Building | 1 | 1217299 | 941409 | 275890 | 711301 |  | 249290 | 960591 | 711301 | 249290 | 100% | 100% | 90.36% | 78.91% | 100% | 2008-12-12 | not conducted | 2009-03-22 | 2009-05-25 | no data | 64 | 506 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Bulala | 051610002 | Concreting of Pathway | 1 | 231463 | 125551 | 105912 | 125551 | 0.33333 | 97958.2 | 223509.2 | 125551 | 97958.2 | 100% | 100% | 92.49% | 96.56% | 100% | 2008-04-30 | not conducted | 2008-07-17 | 2008-08-16 | no data | 30 | 295 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Bulala | 051610002 | Construction of I Unit 2-Classroom High School Building | 1 | 1217299 | 592656 | 624643 | 474124.8 |  | 392631 | 866755.8 | 474124.8 | 392631 | 100% | 100% | 62.86% | 71.2% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 295 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Bulala | 051610002 | 1 Unit 2 Classroom High School Building | 1 | 1077336 | 700200 | 377136 | 700200 | 3/3 | 381986 | 1082186 | 700200 | 381986 | 100% | 100% | 101.3% | 100.5% | 100% | 2007-07-17 | not conducted | 2007-12-11 | 2008-06-25 | no data | 197 | 295 | On-going | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Don Tomas | 051610011 | Improvement of Farm to Market Road | 1 | 554570 | 395408 | 159162 | 355867.2 | 0.33333 | 140605 | 496472.2 | 355867.2 | 140605 | 100% | 100% | 88.34% | 89.52% | 100% | 2008-04-30 | not conducted | 2008-09-24 | 2008-11-28 | no data | 65 | 428 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Don Tomas | 051610011 | Improvement of Farm to Market Road | 1 | 798564 | 582267 | 216297 | 465813.6 |  | 198733 | 664546.6 | 465813.6 | 198733 | 100% | 100% | 91.88% | 83.22% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 428 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Guitol | 051610012 | Construction of Spillway | 1 | 562546 | 385206 | 177340 | 385206 | 0.33333 | 225228 | 610434 | 385206 | 225228 | 100% | 100% | 127% | 108.5% | 100% | 2008-04-30 | not conducted | 2008-07-25 | 2009-03-25 | no data | 243 | 128 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Guitol | 051610012 | Improvement of Farm to Market Road | 1 | 1374835 | 1090059 | 284776 | 782635 |  | 39912 | 822547 | 782635 | 39912 | 100% | 100% | 14.02% | 59.83% | 100% | 2008-12-12 | not conducted | 2009-03-22 | 2009-06-25 | no data | 95 | 128 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Kabuluan | 051610013 | Improvement of Farm to Market Road | 1 | 3272866 | 2413300 | 859566 | 2413300 | 0.33333 | 743336 | 3156636 | 2413300 | 743336 | 100% | 100% | 86.48% | 96.45% | 100% | 2007-07-17 | not conducted | 2008-03-26 | 2008-11-25 | no data | 244 | 390 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Kabuluan | 051610013 | Construction of Day Care Center | 1 | 624853 | 462022 | 162831 | 417681.08 |  | 147431 | 565112.08 | 417681.08 | 147431 | 100% | 100% | 90.54% | 90.44% | 100% | 2008-12-12 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 390 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Kagtalaba | 051610014 | Construction of Spillway | 1 | 570526.35 | 394063 | 176463.35 | 363924.45 | 0.33333 | 179738.35 | 543662.8 | 363924.45 | 179738.35 | 100% | 100% | 101.9% | 95.29% | 100% | 2008-04-30 | not conducted | 2008-08-26 | 2008-10-25 | no data | 60 | 226 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Kagtalaba | 051610014 | Provision of Farm Machineries | 1 | 144900 | 104988 | 39912 | 102788 |  | 39912 | 142700 | 102788 | 39912 | 100% | 100% | 100% | 98.48% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 226 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Maulawin | 051610015 | Improvement of Farm to Market Road | 1 | 1128152 | 866487 | 261665 | 779838.3 | 0.33333 | 182465 | 962303.3 | 779838.3 | 182465 | 100% | 100% | 69.73% | 85.3% | 100% | 2008-04-30 | not conducted | 2008-08-20 | 2008-11-28 | no data | 100 | 412 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Patag Ibaba | 051610016 | Improvement of Farm to Market Road | 1 | 524617 | 346355 | 178262 | 327088 | 0.33333 | 143542 | 470630 | 327088 | 143542 | 100% | 100% | 80.52% | 89.71% | 100% | 2008-04-30 | not conducted | 2008-09-22 | 2008-10-22 | no data | 30 | 122 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Patag Ibaba | 051610016 | Construction of Water System Level 1 | 1 | 73352 | 40741 | 32611 | 32592.8 |  | 20000 | 52592.8 | 32592.8 | 20000 | 100% | 100% | 61.33% | 71.7% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-09-30 | no data | 182 | 122 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Patag Iraya | 051610017 | Construction of Barangay Health Station | 1 | 710999.7 | 483678 | 227321.7 | 455916.56 | 0.33333 | 169021.7 | 624938.26 | 455916.56 | 169021.7 | 100% | 100% | 74.35% | 87.9% | 100% | 2008-04-30 | not conducted | 2008-11-05 | 2009-01-25 | no data | 81 | 126 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Plaridel | 051610018 | Provision of Electrification | 1 | 1237702 | 841500 | 396202 | 784142.69 | 2/3 | 377508.5 | 1161651.19 | 784142.69 | 377508.5 | 100% | 100% | 95.28% | 93.86% | 100% | 2007-07-17 | not conducted | 2008-04-01 | 2008-05-21 | no data | 50 | 297 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Plaridel | 051610018 | Improvement of Farm to Market Road | 1 | 598386 | 455506 | 142880 | 364404.8 |  | 142880 | 507284.8 | 364404.8 | 142880 | 100% | 100% | 100% | 84.78% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 297 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Santa Elena (Pob.) | 051610009 | Construction of I Unit 2-Classroom Elementary School Building | 1 | 1217299 | 908249 | 309050 | 641936.76 |  | 198734 | 840670.76 | 641936.76 | 198734 | 100% | 100% | 64.3% | 69.06% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 1837 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Pulongguitguit | 051610003 | Construction of Farm to Market Road | 1 | 299766 | 191680 | 108086 | 191680 | 0.33333 | 96030 | 287710 | 191680 | 96030 | 100% | 100% | 88.85% | 95.98% | 100% | 2008-04-30 | not conducted | 2008-09-15 | 2008-11-25 | no data | 71 | 329 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | San Lorenzo | 051610006 | Improvement of Farm to Market Road | 1 | 2423906 | 1745000 | 678906 | 1733633.03 | 2/3 | 567426 | 2301059.03 | 1733633.03 | 567426 | 100% | 100% | 83.58% | 94.93% | 100% | 2007-07-17 | not conducted | 2008-04-24 | 2008-11-01 | no data | 191 | 1092 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | San Vicente | 051610008 | Construction of Warehouse with Post-Harvest Facilities | 1 | 516048 | 363823 | 152225 | 345090 | 0.33333 | 151644 | 496734 | 345090 | 151644 | 100% | 100% | 99.62% | 96.26% | 100% | 2008-04-30 | not conducted | 2008-09-12 | 2008-12-25 | no data | 104 | 208 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | San Vicente | 051610008 | Construction of 1 Classroom Elementary School Building | 1 | 693735 | 522103 | 171632 | 346802.27 |  | 160506 | 507308.27 | 346802.27 | 160506 | 100% | 100% | 93.52% | 73.13% | 100% | 2008-12-12 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 208 |  | 1 | VISAYAS
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Tabugon | 051610019 | Construction of 2-Classroom High School Building | 1 | 1133931 | 813958 | 319973 | 813958 | 0.33333 | 159610 | 973568 | 813958 | 159610 | 100% | 100% | 49.88% | 85.86% | 100% | 2008-04-30 | not conducted | 2008-09-29 | 2009-03-25 | no data | 177 | 377 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Cabanbanan | 051702002 | Construction of Water system Level 2 | 1 | 1453000 | 1075850 | 377150 | 1075850 | 1/3 | 380097.08 | 1455947.08 | 1075850 | 380097.08 | 100% | 100% | 100.8% | 100.2% | 100% | 2008-05-27 | not conducted | 2008-10-05 | 2009-04-30 | no data | 207 | 255 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Cabungan | 051702003 | Construction of Ricemill | 1 | 774000 | 551400 | 222600 | 496260 | 0.66667 | 134150 | 630410 | 496260 | 134150 | 100% | 100% | 60.27% | 81.45% | 100% | 2007-07-16 | not conducted | 2008-03-10 | 2008-07-25 | no data | 137 | 152 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Camangahan | 051702004 | Construction of Day Care Center | 1 | 625000 | 528250 | 96750 | 510061 |  | 102150 | 612211 | 510061 | 102150 | 100% | 100% | 105.6% | 97.95% | 100% | 2008-12-12 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 81 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Cayogcog | 051702006 | Construction of Farm to Market Road | 1 | 3508000 | 2734300 | 773700 | 2734300 | 2/3 | 803910 | 3538210 | 2734300 | 803910 | 100% | 100% | 103.9% | 100.9% | 100% | 2007-07-16 | not conducted | 2008-05-12 | 2009-08-30 | no data | 475 | 81 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Coguit | 051702007 | Construction of Day Care Center | 1 | 595000 | 491500 | 103500 | 491500 |  | 92300 | 583800 | 491500 | 92300 | 100% | 100% | 89.18% | 98.12% | 100% | 2008-12-12 | not conducted | 2009-04-13 | 2009-06-20 | no data | 68 | 295 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Luluasan | 051702010 | Construction of One Classroom School Building | 1 | 603500 | 467750 | 135750 | 467750 |  | 106850 | 574600 | 467750 | 106850 | 100% | 100% | 78.71% | 95.21% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 440 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Montenegro | 051702011 | Construction of Water System Level 2 | 1 | 593412.5 | 527600 | 65812.5 | 519600 | 0.33333 | 66137.5 | 585737.5 | 519600 | 66137.5 | 100% | 100% | 100.5% | 98.71% | 100% | 2007-07-16 | not conducted | 2008-03-29 | 2008-07-25 | no data | 118 | 67 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Montenegro | 051702011 | Construction of One Classroom School Building | 1 | 603500 | 495250 | 108250 | 495250 |  | 107175 | 602425 | 495250 | 107175 | 100% | 100% | 99.01% | 99.82% | 100% | 2008-12-12 | not conducted | 2009-04-21 | 2009-06-20 | no data | 60 | 81 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Pararao | 051702012 | Construction of Community Learning Center | 1 | 590000 | 482350 | 107650 | 482350 |  | 721600 | 1203950 | 482350 | 721600 | 100% | 100% | 670.3% | 204.1% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 440 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Pulangdaga | 051702014 | Construction of One Classroom School Building | 1 | 635000 | 505850 | 129150 | 505850 |  | 97150 | 603000 | 505850 | 97150 | 100% | 100% | 75.22% | 94.96% | 100% | 2008-12-12 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 126 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Sagrada | 051702015 | Construction of Water System Level 2 | 1 | 830000 | 701700 | 128300 | 670200 |  | 123400 | 793600 | 670200 | 123400 | 100% | 100% | 96.18% | 95.61% | 100% | 2008-12-12 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 130 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | San Francisco | 051702016 | Construction of Water System Level 2 | 1 | 1596000 | 1286700 | 309300 | 1269684 | 2/3 | 217212 | 1486896 | 1269684 | 217212 | 100% | 100% | 70.23% | 93.16% | 100% | 2007-07-16 | not conducted | 2008-05-19 | 2008-12-25 | no data | 220 | 271 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Santiago | 051702017 | Improvement of Farm to Market Road | 1 | 1683000 | 972550 | 710450 | 875295 |  | 699250 | 1574545 | 875295 | 699250 | 100% | 100% | 98.42% | 93.56% | 100% | 2008-12-12 | not conducted | 2009-05-01 | 2009-07-30 | no data | 90 | 73 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Siramag | 051702013 | Construction of Day Care Center | 1 | 595000 | 454800 | 140200 | 454800 |  | 129890 | 584690 | 454800 | 129890 | 100% | 100% | 92.65% | 98.27% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 885 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Tapayas | 051702018 | Construction of Brgy Public Market | 1 | 1490000 | 1147500 | 342500 | 1147500 | 1/3 | 382745.77 | 1530245.77 | 1147500 | 382745.77 | 100% | 100% | 111.8% | 102.7% | 100% | 2008-05-27 | not conducted | 2008-10-15 | 2009-04-30 | no data | 197 | 335 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Tomatarayo | 051702019 | Construction of Farm to Market Road | 1 | 3634703 | 2876650 | 758053 | 2588985 | 1/3 | 70100 | 2659085 | 2588985 | 70100 | 100% | 100% | 9.247% | 73.16% | 100% | 2008-05-27 | not conducted | 2008-12-01 | 2009-03-01 | no data | 90 | 85 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Bagong Silang | 051712001 | Construction of Footbridge | 1 | 2277109.13 | 1784444.95 | 492664.18 | 1716252.7 |  | 417163.38 | 2133416.08 | 1716252.7 | 417163.38 | 100% | 100% | 84.67% | 93.69% | 100% | 2008-05-16 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 186 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Bucal | 051712002 | Construction of Farm to Market Road | 1 | 3056341.7 | 2437549 | 618792.7 | 2193794.1 | 1st Tranche | 557484.8 | 2751278.9 | 2193794.1 | 557484.8 | 100% | 100% | 90.09% | 90.02% | 100% | 2008-12-11 | not conducted | 2009-04-19 | 2009-06-30 | no data | 72 | 47 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Cabasag | 051712003 | Construction of Water System Level 2 | 1 | 741979.7 | 517260.89 | 224718.81 | 517260 | 0.33333 | 192652.44 | 709912.44 | 517260 | 192652.44 | 100% | 100% | 85.73% | 95.68% | 100% | 2008-05-16 | not conducted | 2008-07-29 | 2009-05-25 | no data | 300 | 123 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Comadaycaday | 051712004 | Construction of Water System Level 1 | 1 | 475473.9 | 329143 | 146330.9 | 263314.4 | 1st Tranche | 116987.1 | 380301.5 | 263314.4 | 116987.1 | 100% | 100% | 79.95% | 79.98% | 100% | 2008-12-11 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 137 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Magais 2 | 051712010 | Construction of Water System Level 1 | 1 | 249247.95 | 161201 | 88046.95 | 161201 | 1st Tranche | 25000 | 186201 | 161201 | 25000 | 100% | 100% | 28.39% | 74.71% | 100% | 2008-12-11 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 77 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Mansalaya | 051712011 | Construction of Footbridge | 1 | 2932768.78 | 2331395 | 601373.78 | 2282219.65 | 1st Tranche | 532995.34 | 2815214.99 | 2282219.65 | 532995.34 | 100% | 100% | 88.63% | 95.99% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 206 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Nagkalit | 051712012 | Improvement of Farm to Market Road | 1 | 2408356.18 | 1786858.62 | 621497.56 | 1772997.86 | 0.33333 | 602103.28 | 2375101.14 | 1772997.86 | 602103.28 | 100% | 100% | 96.88% | 98.62% | 100% | 2008-05-16 | not conducted | 2008-08-15 | 2009-03-25 | no data | 222 | 104 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Palaspas | 051712013 | Construction of Water System Level 1 | 1 | 437024.1 | 284568 | 152456.1 | 266978.73 | 1st Tranche | 88051.3 | 355030.03 | 266978.73 | 88051.3 | 100% | 100% | 57.76% | 81.24% | 100% | 2008-12-11 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 103 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Pasay | 051712015 | Provision of Fishing Equipment | 1 | 498650 | 352483 | 146167 | 332334.34 |  | 141280.77 | 473615.11 | 332334.34 | 141280.77 | 100% | 100% | 96.66% | 94.98% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 182 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Peñafrancia |  | Construction of Water System Level 1 | 1 | 399454.35 | 266459 | 132995.35 | 239813.1 |  | 104420.35 | 344233.45 | 239813.1 | 104420.35 | 100% | 100% | 78.51% | 86.18% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 117 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Salvacion | 051712022 | Construction of 1-Classroom Elementary School Building | 1 | 714105.64 | 500041.89 | 214063.75 | 500041.89 | 0.33333 | 184047.08 | 684088.97 | 500041.89 | 184047.08 | 100% | 100% | 85.98% | 95.8% | 100% | 2008-05-16 | not conducted | 2008-07-07 | 2009-02-25 | no data | 233 | 101 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Salvacion | 051712022 | Construction of Farm to Market Road | 1 | 1853995.79 | 1453022 | 400973.79 | 1353624.22 |  | 69394.65 | 1423018.87 | 1353624.22 | 69394.65 | 100% | 100% | 17.31% | 76.75% | 100% | 2008-12-11 | not conducted | 2009-04-06 | 2009-11-30 | no data | 238 | 101 | completed as built | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | San Juan | 051712023 | Improvement of Farm to Market Road | 1 | 2507132.8 | 1964150 | 542982.8 | 1925926.81 | 0.33333 | 522777.76 | 2448704.57 | 1925926.81 | 522777.76 | 100% | 100% | 96.28% | 97.67% | 100% | 2008-05-16 | not conducted | 2008-08-15 | 2009-03-25 | no data | 222 | 146 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | San Juan | 051712023 | Construction of Water System Level I | 1 | 405792.15 | 292173 | 113619.15 | 275936.77 | 1st Tranche | 69328.83 | 345265.6 | 275936.77 | 69328.83 | 100% | 100% | 61.02% | 85.08% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 146 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | San Pablo | 051712024 | Improvement of Barangay Road | 1 | 3492818.58 | 2617510.1 | 875308.48 | 2615688.16 | 0.33333 | 709311.83 | 3324999.99 | 2615688.16 | 709311.83 | 100% | 100% | 81.04% | 95.2% | 100% | 2008-05-16 | not conducted | 2008-09-20 | 2009-05-25 | no data | 247 | 73 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | San Pablo | 051712024 | Construction of Water System Level 1 | 1 | 339799.65 | 222941 | 116858.65 | 209700.95 | 1st Tranche | 48018.79 | 257719.74 | 209700.95 | 48018.79 | 100% | 100% | 41.09% | 75.84% | 100% | 2008-12-11 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 73 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Tabion | 051712031 | Construction of Farm to Market Road | 1 | 1934235.16 | 1492164 | 442071.16 | 1454325.1 |  | 402831.52 | 1857156.62 | 1454325.1 | 402831.52 | 100% | 100% | 91.12% | 96.02% | 100% | 2008-12-11 | not conducted | 2009-04-19 | 2009-06-30 | no data | 72 | 100 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Ason | 051714001 | Construction of Water System Level 2 | 1 | 590000 | 413000 | 177000 | 413000 | 3/3 | 174235 | 587235 | 413000 | 174235 | 100% | 100% | 98.44% | 99.53% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-22 | 2006-05-13 | 2006-05-25 | 172 | 99 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Bahi | 051714002 | Construction of Three (3) - Classroom Elementary Building | 1 | 1590000 | 1113000 | 477000 | 1113000 | no data | 434300 | 1547300 | 1113000 | 434300 | 100% | 100% | 91.05% | 97.31% | 100% | 2006-06-20 | not conducted | 2006-09-06 | 2007-03-25 | no data | 200 | 252 | Completed | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Binagasbasan | 051714003 | Construction of Multi-Purpose Bldg. | 1 | 625000 | 437500 | 187500 | 437500 | 3/3 | 188500 | 626000 | 437500 | 188500 | 100% | 100% | 100.5% | 100.2% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-09 | 2006-03-31 | 2006-04-25 | 142 | 242 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Binagasbasan | 051714003 | Construction of Training Center | 1 | 1350000 | 937000 | 413000 | 937000 | 1/3 | 398049 | 1335049 | 937000 | 398049 | 100% | 100% | 96.38% | 98.89% | 100% | 2007-07-20 | not conducted | 2007-09-26 | 2008-10-25 | no data | 395 | 213 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Brgy 1 | 051714014 | Construction of Concrete Pathway | 1 | 822640 | 528640 | 294000 | 528640 | 0.33333 | 248850 | 777490 | 528640 | 248850 | 100% | 100% | 84.64% | 94.51% | 100% | 2007-07-20 | not conducted | 2007-09-11 | 2009-05-25 | no data | 622 | 230 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Brgy 2 | 051714015 | Provision of Fishing Equipments | 1 | 700000 | 490000 | 210000 | 490000 | 1/3 | 210000 | 700000 | 490000 | 210000 | 100% | 100% | 100% | 100% | 100% | 2007-07-20 | not conducted | 2007-09-11 | 2008-10-25 | no data | 410 | 184 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Brgy 3 | 051714016 | Provision of Fishing Equipments | 1 | 700000 | 490000 | 210000 | 490000 | 3/3 | 190000 | 680000 | 490000 | 190000 | 100% | 100% | 90.48% | 97.14% | 100% | 2007-07-20 | not conducted | 2007-09-11 | 2008-10-25 | no data | 410 | 105 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Brgy 4 | 051714017 | Construction of Concrete Pathway | 1 | 1200000 | 840000 | 360000 | 786660.61 | 0.33333 | 330000 | 1116660.61 | 786660.61 | 330000 | 100% | 100% | 91.67% | 93.06% | 100% | 2007-07-20 | not conducted | 2007-10-19 | 2009-05-25 | no data | 584 | 412 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Burabod | 051714004 | Construction of Multi-Purpose Bldg. | 1 | 549500 | 346060 | 203440 | 346060 | 3/3 | 198099.72 | 544159.72 | 346060 | 198099.72 | 100% | 100% | 97.38% | 99.03% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-14 | 2006-03-30 | 2006-06-02 | 136 | 103 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Burabod - C2 | 051714004 | Construction of Concrete Pathway | 2 | 1390000 | 932900 | 457100 | 898620 | 0.33333 | 418000 | 1316620 | 898620 | 418000 | 100% | 100% | 91.45% | 94.72% | 100% | 2007-07-20 | not conducted | 2007-10-10 | 2008-10-25 | no data | 381 | 229 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Cagamutan | 051714005 | Construction of Multi-Purpose Bldg. | 1 | 607000 | 382410 | 224590 | 382410 | 3/3 | 213590 | 596000 | 382410 | 213590 | 100% | 100% | 95.1% | 98.19% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-15 | 2006-03-31 | 2006-05-25 | 136 | 95 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Cagnipa | 051714006 | Construction of 3-Classroom School Bldg. | 1 | 1300000 | 910000 | 390000 | 910000 | 3/3 | 320000 | 1230000 | 910000 | 320000 | 100% | 100% | 82.05% | 94.62% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-22 | 2006-03-30 | 2006-04-26 | 128 | 132 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Dangla | 051714008 | Construction of Multi-Purpose Bldg. | 1 | 595000 | 383500 | 211500 | 383500 | 3/3 | 194402 | 577902 | 383500 | 194402 | 100% | 100% | 91.92% | 97.13% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-16 | 2006-04-29 | 2006-05-24 | 164 | 87 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Dangla | 051714008 | Provision of Fishing Equipments | 1 | 700000 | 490000 | 210000 | 490000 | 0.33333 | 210000 | 700000 | 490000 | 210000 | 100% | 100% | 100% | 100% | 100% | 2007-07-20 | not conducted | 2007-09-24 | 2008-10-25 | no data | 397 | 109 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Denrica | 051714010 | Construction of Water System Level 2 | 1 | 870000 | 609000 | 261000 | 609000 | 3/3 | 279700 | 888700 | 609000 | 279700 | 100% | 100% | 107.2% | 102.1% | 100% | 2005-05-15 | 2005-06-15 | 2005-10-26 | 2006-03-31 | 2006-04-23 | 156 | 240 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Denrica | 051714010 | Construction of Seawall | 1 | 1350000 | 917250 | 432750 | 917250 | 1/3 | 405328 | 1322578 | 917250 | 405328 | 100% | 100% | 93.66% | 97.97% | 100% | 2007-07-20 | not conducted | 2007-09-10 | 2009-05-25 | no data | 623 | 256 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Harrison | 051714011 | Construction of Concrete Pathway | 1 | 1701000 | 1274210 | 426790 | 1274210 | 1/3 | 433040 | 1707250 | 1274210 | 433040 | 100% | 100% | 101.5% | 100.4% | 100% | 2007-07-20 | not conducted | 2007-09-25 | 2009-05-25 | no data | 608 | 258 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Mansangat | 051714012 | Construction of Multi-Purpose Bldg. | 1 | 590000 | 375000 | 215000 | 375000 | 3/3 | 185505 | 560505 | 375000 | 185505 | 100% | 100% | 86.28% | 95% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-15 | 2006-04-26 | 2006-04-25 | 162 | 102 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Pambuhan | 051714013 | Rehabilitation/Improvement of Farm to Market Road | 1 | 1500000 | 1050000 | 450000 | 1050000 | 3/3 | 408000 | 1458000 | 1050000 | 408000 | 100% | 100% | 90.67% | 97.2% | 100% | 2006-06-20 | not conducted | 2006-09-20 | 2007-04-03 | no data | 195 | 162 | Completed | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Sagrada | 051714018 | Construction of Multi-Purpose Bldg. | 1 | 900000 | 630000 | 270000 | 630000 | 3/3 | 271000 | 901000 | 630000 | 271000 | 100% | 100% | 100.4% | 100.1% | 100% | 2005-05-15 | 2005-06-15 | 2005-10-13 | 2006-04-29 | 2006-05-17 | 198 | 105 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Salvacion | 051714019 | Construction of Farm to Market Road | 1 | 4300000 | 3134000 | 1166000 | 2507200 | 1/3 | 948300 | 3455500 | 2507200 | 948300 | 100% | 100% | 81.33% | 80.36% | 100% | 2006-06-20 | not conducted | 2007-07-23 | 2008-03-23 | no data | 244 | 95 | completed as built | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | San Vicente | 051714020 | Concreting of Farm to Market Road | 1 | 967500 | 677250 | 290250 | 677250 | 3/3 | 286056.25 | 963306.25 | 677250 | 286056.25 | 100% | 100% | 98.56% | 99.57% | 100% | 2005-05-15 | 2005-06-15 | 2005-10-13 | 2006-04-29 | 2006-04-18 | 198 | 184 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Sumaoy | 051714021 | Construction of 3-Classroom School Bldg. | 1 | 1270000 | 889000 | 381000 | 889000 | 3/3 | 382000 | 1271000 | 889000 | 382000 | 100% | 100% | 100.3% | 100.1% | 100% | 2005-05-15 | 2005-06-15 | 2005-10-28 | 2006-03-31 | 2006-05-18 | 154 | 289 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Sumaoy | 051714021 | Construction of Water System Level 2 | 1 | 600000 | 490000 | 110000 | 490000 | 3/3 | 111000 | 601000 | 490000 | 111000 | 100% | 100% | 100.9% | 100.2% | 100% | 2006-06-20 | not conducted | 2006-08-17 | 2007-02-03 | no data | 170 | 289 | Completed | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Tamiawon | 051714022 | Construction of Multi-Purpose Bldg. | 1 | 636000 | 419760 | 216240 | 419760 | 3/3 | 218240 | 638000 | 419760 | 218240 | 100% | 100% | 100.9% | 100.3% | 100% | 2005-05-15 | 2005-06-15 | 2005-11-15 | 2006-03-30 | 2006-05-26 | 135 | 142 | Inaugurated | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Toytoy | 051714023 | Construction of Three (3) - Classroom Elementary Building | 1 | 1590000 | 1113000 | 477000 | 1113000 | 3/3 | 478000 | 1591000 | 1113000 | 478000 | 100% | 100% | 100.2% | 100.1% | 100% | 2006-06-20 | not conducted | 2006-09-03 | 2007-05-20 | no data | 259 | 181 | Completed | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Antipolo | 051722001 | Construction.of 1 Classroom School Bldg. | 1 | 600000 | 330936 | 269064 | 330936 | 3/3 | 278400 | 609336 | 330936 | 278400 | 100% | 100% | 103.5% | 101.6% | 100% | 2007-07-16 | not conducted | 2008-03-24 | 2008-09-25 | no data | 185 | 865 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Antipolo | 051722001 | Construction of Footbridge | 1 | 426483 | 298538.2 | 127944.8 | 238830.56 |  | 457407.63 | 696238.19 | 238830.56 | 457407.63 | 100% | 100% | 357.5% | 163.3% | 100% | 2008-12-12 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 285 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Bagolatao | 051722002 | Construction of Barangay Health Station | 1 | 770424.54 | 539297.18 | 231127.36 | 485367.45 | 1/3 | 231227.36 | 716594.81 | 485367.45 | 231227.36 | 100% | 100% | 100% | 93.01% | 100% | 2008-06-24 | not conducted | 2008-10-02 | 2008-12-30 | no data | 89 | 271 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Bagongbong | 051722003 | Construction of 1-Room Elem. School Building | 1 | 787311.27 | 551117.89 | 236193.38 | 496006.1 | 1/3 | 244893.39 | 740899.49 | 496006.1 | 244893.39 | 100% | 100% | 103.7% | 94.11% | 100% | 2008-06-24 | not conducted | 2008-10-01 | 2008-12-25 | no data | 85 | 154 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Bagongbong | 051722003 | Construction of Solar Dryer | 1 | 805681 | 563796.99 | 241884.01 | 507579.28 |  | 241704.42 | 749283.7 | 507579.28 | 241704.42 | 100% | 100% | 99.93% | 93% | 100% | 2008-12-12 | not conducted | 2009-03-30 | 2009-05-25 | no data | 56 | 154 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Nuevo | 051722004 | Construction of 1 Unit Solar Drier | 1 | 379531.13 | 241559.47 | 137971.66 | 193247.58 | 1/3 | 147370.98 | 340618.56 | 193247.58 | 147370.98 | 100% | 100% | 106.8% | 89.75% | 100% | 2008-06-24 | not conducted | 2008-09-01 | 2008-10-25 | no data | 54 | 302 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Nuevo | 051722004 | Construction of Barangay Health Station | 1 | 403986 | 282790.43 | 121195.57 | 254511.39 |  | 242896.64 | 483107.06 | 254511.39 | 228595.67 | 100% | 94.11% | 200.4% | 119.6% | 100% | 2008-12-12 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 413 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Viejo | 051722005 | Improvement of Farm to Market Road | 1 | 535300 | 374710 | 160590 | 299760 | 0.33333 | 116065 | 415825 | 299760 | 116065 | 100% | 100% | 72.27% | 77.68% | 100% | 2007-07-16 | not conducted | 2008-01-14 | 2008-05-08 | no data | 115 | 476 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Viejo | 051722005 | Construction of Drainage System | 1 | 1550295.71 | 1085206.99 | 465088.72 | 976686.29 | 1/3 | 465088.72 | 1441775.01 | 976686.29 | 465088.72 | 100% | 100% | 100% | 93% | 100% | 2008-06-24 | not conducted | 2008-10-01 | 2008-12-25 | no data | 85 | 476 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Viejo | 051722005 | Construction of Barangay Health Station | 1 | 1004383 | 705868.28 | 298514.72 | 635281.64 |  | 241704.42 | 876986.06 | 635281.64 | 241704.42 | 100% | 100% | 80.97% | 87.32% | 100% | 2008-12-12 | not conducted | 2009-03-23 | 2009-05-25 | no data | 63 | 476 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Catanusan | 051722006 | Construction of Barangay Health Station | 1 | 479250 | 335475 | 143775 | 335475 | 0.33333 | 144800 | 480275 | 335475 | 144800 | 100% | 100% | 100.7% | 100.2% | 100% | 2007-07-16 | not conducted | 2007-12-08 | 2008-07-01 | no data | 206 | 202 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Catanusan | 051722006 | Construction of Reinforced Concrete Box Culvert | 1 | 984215.66 | 688950.96 | 295264.7 | 645460.77 | 1/3 | 381903.72 | 1027364.49 | 645460.77 | 381903.72 | 100% | 100% | 129.3% | 104.4% | 100% | 2008-06-24 | not conducted | 2008-11-02 | 2009-02-25 | no data | 115 | 202 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Catanusan | 051722006 | Construction of Pathway | 1 | 805977.58 | 564184.3 | 241793.28 | 534203.63 |  | 298514.98 | 832718.61 | 534203.63 | 298514.98 | 100% | 100% | 123.5% | 103.3% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 202 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Del Carmen-Del Rosario | 051722007 | Construction of Concrete Drainage Lined Canal | 1 | 494400 | 346080 | 148320 | 341864 | 0.33333 | 149320 | 491184 | 341864 | 149320 | 100% | 100% | 100.7% | 99.35% | 100% | 2007-07-16 | not conducted | 2007-11-20 | 2008-08-01 | no data | 255 | 369 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Del Carmen-Del Rosario | 051722007 | Construction of Drainage System | 1 | 1807429.96 | 1265200.98 | 542228.98 | 1265200.98 | 1/3 | 151663.2 | 1416864.18 | 1265200.98 | 151663.2 | 100% | 100% | 27.97% | 78.39% | 100% | 2008-06-24 | not conducted | 2008-11-02 | 2009-06-25 | no data | 235 | 369 | completed as built | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Del Socorro | 051722008 | Construction of Water System Level 2 | 1 | 320282.22 | 224197.56 | 96084.66 | 224197.56 | 1/3 | 98142.33 | 322339.89 | 224197.56 | 98142.33 | 100% | 100% | 102.1% | 100.6% | 100% | 2008-06-24 | not conducted | 2008-10-01 | 2008-12-25 | no data | 85 | 218 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Hamoraon | 051722009 | Construction of Water System Level 2 | 1 | 1210200 | 847140 | 363060 | 790995.64 | 0.33333 | 636684.25 | 1427679.89 | 790995.64 | 636684.25 | 100% | 100% | 175.4% | 118% | 100% | 2007-07-16 | not conducted | 2008-05-30 | 2008-12-25 | no data | 209 | 281 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Hobo | 051722010 | Construction of 2-Units Solar Dryer | 1 | 362500 | 253750 | 108750 | 253700 | 2/3 | 109800 | 363500 | 253700 | 109800 | 100% | 100% | 101% | 100.3% | 100% | 2007-07-16 | not conducted | 2007-12-19 | 2008-09-26 | no data | 282 | 695 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Hobo | 051722010 | Construction of Day Care Center | 1 | 787340.9 | 551138.63 | 236202.27 | 440910.91 |  | 271386.54 | 712297.45 | 440910.91 | 271386.54 | 100% | 100% | 114.9% | 90.47% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 614 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Magadap | 051722012 | Construction of Barangay Health Station | 1 | 784830.54 | 549381.38 | 235449.16 | 542414.15 | 1/3 | 231824.58 | 774238.73 | 542414.15 | 231824.58 | 100% | 100% | 98.46% | 98.65% | 100% | 2008-06-24 | not conducted | 2008-10-05 | 2008-12-25 | no data | 81 | 195 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Magadap | 051722012 | Construction of Solar Dryer | 1 | 378073 | 264651.37 | 113421.63 | 238186.23 |  | 113421 | 351607.23 | 238186.23 | 113421 | 100% | 100% | 100% | 93% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 195 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Manapao | 051722014 | Construction of Drainage Lined Canal | 1 | 500000 | 300000 | 200000 | 270000 |  | 155830.75 | 388411.89 | 240000 | 148411.89 | 88.89% | 95.24% | 77.92% | 77.68% | 100% | 2008-12-12 | not conducted | 2009-03-26 | 2009-05-25 | no data | 60 | 282 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Mataoroc | 051722015 | Improvement of Farm to Market Road | 1 | 486100 | 340270 | 145830 | 272216 | 0.33333 | 146800 | 419016 | 272216 | 146800 | 100% | 100% | 100.7% | 86.2% | 100% | 2007-07-16 | not conducted | 2007-12-19 | 2008-12-04 | no data | 351 | 417 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Mataoroc | 051722015 | Construction of Drainage System | 1 | 578739.4 | 405117.58 | 173621.82 | 392430.19 | 1/3 | 173621.77 | 566051.96 | 392430.19 | 173621.77 | 100% | 100% | 100% | 97.81% | 100% | 2008-06-24 | not conducted | 2008-10-01 | 2008-12-25 | no data | 85 | 417 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Mataoroc | 051722015 | Construction of Farm to Market Road | 1 | 1138209 | 796745.95 | 341463.05 | 717071.36 |  | 320731.28 | 1037802.64 | 717071.36 | 320731.28 | 100% | 100% | 93.93% | 91.18% | 100% | 2008-12-12 | not conducted | 2009-03-23 | 2009-06-25 | no data | 94 | 417 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Sagrada Familia | 051722016 | Construction of Day Care Center | 1 | 806484.51 | 564539.15 | 241945.36 | 508085.23 | 1/3 | 241945.36 | 750030.59 | 508085.23 | 241945.36 | 100% | 100% | 100% | 93% | 100% | 2008-06-24 | not conducted | 2008-10-01 | 2008-12-25 | no data | 85 | 411 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Sagrada Familia | 051722016 | Improvement of Farm to Market Road | 1 | 443300 | 310310 | 132990 | 248240 | 0.33333 | 134000 | 382240 | 248240 | 134000 | 100% | 100% | 100.8% | 86.23% | 100% | 2007-07-16 | not conducted | 2007-12-20 | 2008-05-22 | no data | 154 | 411 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Sagrada Familia | 051722016 | Construction of Farm to Market Road | 1 | 1224878 | 855314.43 | 369563.57 | 851744.43 |  | 369563.32 | 1221307.75 | 851744.43 | 369563.32 | 100% | 100% | 100% | 99.71% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 411 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Salingogon | 051722017 | Construction of Water System Level 2 | 1 | 1600000 | 1120000 | 480000 | 1079002 | 0.33333 | 1155183.5 | 2234185.5 | 1079002 | 1155183.5 | 100% | 100% | 240.7% | 139.6% | 100% | 2007-07-16 | not conducted | 2008-09-20 | 2009-04-25 | no data | 217 | 413 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Antonio | 051722018 | Construction of Seawall | 1 | 1726420 | 1208620 | 517800 | 1208620 | 3/3 | 517983.41 | 1726603.41 | 1208620 | 517983.41 | 100% | 100% | 100% | 100% | 100% | 2007-07-16 | not conducted | 2008-05-14 | 2008-10-01 | no data | 140 | 179 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Antonio | 051722018 | Construction of Drainage Lined Canal | 1 | 1516051 | 1061235.63 | 454815.37 | 955112.06 |  | 457407.63 | 1412519.69 | 955112.06 | 457407.63 | 100% | 100% | 100.6% | 93.17% | 100% | 2008-12-12 | not conducted | 2009-03-23 | 2009-05-25 | no data | 63 | 369 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Felipe Santiago | 051722019 | Construction of Concrete Drainage Lined Canal | 1 | 537000 | 375900 | 161100 | 375900 | 2/3 | 162100 | 538000 | 375900 | 162100 | 100% | 100% | 100.6% | 100.2% | 100% | 2007-07-16 | not conducted | 2007-12-20 | 2008-08-01 | no data | 225 | 115 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Felipe Santiago | 051722019 | Construction of Drainage Lined Canal | 1 | 543099 | 380169.11 | 162929.89 | 380169.11 |  | 81464.81 | 461633.92 | 380169.11 | 81464.81 | 100% | 100% | 50% | 85% | 100% | 2008-12-12 | not conducted | 2009-03-23 | 2009-05-25 | no data | 63 | 111 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Francisco | 051722020 | Construction of Concrete Drainage Lined Canal | 1 | 451570 | 316099 | 135471 | 308128 | 0.33333 | 136630 | 444758 | 308128 | 136630 | 100% | 100% | 100.9% | 98.49% | 100% | 2007-07-16 | not conducted | 2008-02-04 | 2008-07-01 | no data | 148 | 107 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Jose | 051722021 | Day Care Center | 1 | 1681242.53 | 1176869.77 | 504372.76 | 1059182.8 | 1/3 | 504972.76 | 1564155.56 | 1059182.8 | 504972.76 | 100% | 100% | 100.1% | 93.04% | 100% | 2008-06-24 | not conducted | 2008-11-02 | 2009-02-25 | no data | 115 | 257 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Jose | 051722021 | Concreting of Pathway | 1 | 764648 | 535253.91 | 229394.09 | 499255.26 |  | 229394.54 | 728649.8 | 499255.26 | 229394.54 | 100% | 100% | 100% | 95.29% | 100% | 2008-12-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 257 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Juan San Lorenzo | 051722022 | Construction of Drainage Lined Canal | 1 | 1395047 | 976532.71 | 418514.29 | 974006.98 |  | 418257.01 | 1392263.99 | 974006.98 | 418257.01 | 100% | 100% | 99.94% | 99.8% | 100% | 2008-12-12 | not conducted | 2009-03-28 | 2009-05-31 | no data | 64 | 261 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Juan San Lorenzo | 051722022 | Concreting of Pathway | 1 | 930030.13 | 651021.09 | 279009.04 | 651021.09 | 2/3 | 279109.04 | 930130.13 | 651021.09 | 279109.04 | 100% | 100% | 100% | 100% | 100% | 2008-06-24 | not conducted | 2008-09-01 | 2008-12-25 | no data | 115 | 261 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Taban | 051722023 | Construction of Barangay Health Station | 1 | 472500 | 330750 | 141750 | 330750 | 2/3 | 142800 | 473550 | 330750 | 142800 | 100% | 100% | 100.7% | 100.2% | 100% | 2007-07-16 | not conducted | 2007-12-07 | 2008-12-26 | no data | 385 | 171 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Timbang | 051722025 | Construction of 4-Barrel Reinforced Concrete Box Culvert | 1 | 1115200 | 780640 | 334560 | 780600 | 0.33333 | 348256.38 | 1128856.38 | 780600 | 348256.38 | 100% | 100% | 104.1% | 101.2% | 100% | 2007-07-16 | not conducted | 2008-01-17 | 2008-09-04 | no data | 231 | 228 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Antipolo | 051727001 | Construction of Water System Level 2 | 1 | 524516.03 | 413300 | 111216.03 | 386040.07 | 2/3 | 99506.03 | 485546.1 | 386040.07 | 99506.03 | 100% | 100% | 89.47% | 92.57% | 100% | 2007-07-17 | not conducted | 2008-05-26 | 2008-08-30 | no data | 96 | 160 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Antipolo | 051727001 | Construction of Footbridge | 1 | 278750 | 235300 | 43450 | 211770 | 1/3 | 83550 | 295320 | 211770 | 83550 | 100% | 100% | 192.3% | 105.9% | 100% | 2008-05-28 | not conducted | 2008-12-01 | 2009-05-25 | no data | 175 | 160 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Bagong Silang | 051727002 | Construction of Barangay Health Station | 1 | 621269 | 524500 | 96769 | 524500 | 1/3 | 156869 | 681369 | 524500 | 156869 | 100% | 100% | 162.1% | 109.7% | 100% | 2008-05-28 | not conducted | 2008-12-01 | 2009-04-25 | no data | 145 | 120 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Bagong Sirang | 051727002 | Construction of Water System Level 2 | 1 | 482026.12 | 403900 | 78126.12 | 323120 | 1/3 | 97576.12 | 420696.12 | 323120 | 97576.12 | 100% | 100% | 124.9% | 87.28% | 100% | 2007-07-17 | not conducted | 2008-05-26 | 2008-08-30 | no data | 96 | 120 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Bahay | 051727003 | Construction of Drainage Canal | 1 | 926464 | 667044.3 | 259419.7 | 617911.7 | 0.66667 | 281314.7 | 899226.4 | 617911.7 | 281314.7 | 100% | 100% | 108.4% | 97.06% | 100% | 2007-07-17 | not conducted | 2007-11-25 | 2008-02-25 | no data | 92 | 298 | Completed | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Bahay | 051727003 | Construction of Water System Level 2 | 1 | 795674 | 581000 | 214674 | 581000 |  | 213684 | 794684 | 581000 | 213684 | 100% | 100% | 99.54% | 99.88% | 100% | 2009-02-05 | no data | 2009-04-01 | 2009-05-25 | no data | 54 | 353 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Balogo | 051727004 | Construction of Water System Level 2 | 1 | 891834 | 376846 | 514988 | 376846 | 1/3 | 465257 | 842103 | 376846 | 465257 | 100% | 100% | 90.34% | 94.42% | 100% | 2008-05-28 | not conducted | 2008-09-29 | 2009-03-30 | no data | 182 | 620 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Caranan | 051727005 | Construction of School Building | 1 | 1311139 | 968000 | 343139 | 774400 |  | 346489 | 1120889 | 774400 | 346489 | 100% | 100% | 101% | 85.49% | 100% | 2009-02-05 | no data | 2009-02-20 | 2009-05-25 | no data | 94 | 1178 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Cuco | 051727006 | Construction of Water System Level 2 | 1 | 441452.24 | 322156.7 | 119295.54 | 322154.36 | 1/3 | 142379.8 | 464534.16 | 322154.36 | 142379.8 | 100% | 100% | 119.4% | 105.2% | 100% | 2007-07-17 | not conducted | 2008-05-15 | 2008-09-30 | no data | 138 | 264 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Cuco | 051727006 | School Building | 1 | 980167 | 764100 | 216067 | 687690 |  | 198992.44 | 886682.44 | 687690 | 198992.44 | 100% | 100% | 92.1% | 90.46% | 100% | 2008-05-28 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 195 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Dalupaon | 051727007 | Construction of Water System Level 2 | 1 | 513671.4 | 369200 | 144471.4 | 359994.5 | 1/3 | 138411.4 | 498405.9 | 359994.5 | 138411.4 | 100% | 100% | 95.81% | 97.03% | 100% | 2007-07-17 | not conducted | 2008-05-19 | 2008-12-25 | no data | 220 | 850 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Dalupaon | 051727007 | Construction of Day Care Center | 1 | 669938 | 485800 | 184138 | 485800 | 1/3 | 176948 | 662748 | 485800 | 176948 | 100% | 100% | 96.1% | 98.93% | 100% | 2008-05-28 | not conducted | 2008-12-01 | 2009-01-25 | no data | 55 | 850 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Dalupaon | 051727007 | Construction of Drainage System | 1 | 1423619 | 1061000 | 362619 | 954900 |  | 337979 | 1292879 | 954900 | 337979 | 100% | 100% | 93.2% | 90.82% | 100% | 2009-02-05 | no data | 2009-02-20 | 2009-05-25 | no data | 94 | 842 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Itulan | 051727010 | Construction of Water System Level 2 | 1 | 360433.43 | 241500 | 118933.43 | 225133.14 | 2/3 | 114917.43 | 340050.57 | 225133.14 | 114917.43 | 100% | 100% | 96.62% | 94.34% | 100% | 2007-07-17 | not conducted | 2008-05-15 | 2008-09-30 | no data | 138 | 172 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Itulan | 051727010 | Construction of Barangay Health Station | 1 | 619950 | 432200 | 187750 | 432182.66 | 1/3 | 191110 | 623292.66 | 432182.66 | 191110 | 100% | 100% | 101.8% | 100.5% | 100% | 2008-05-28 | not conducted | 2008-12-01 | 2009-03-25 | no data | 114 | 172 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Itulan | 051727010 | Construction of School Building | 1 | 1178594 | 874000 | 304594 | 699200 |  | 313267.75 | 1012467.75 | 699200 | 313267.75 | 100% | 100% | 102.8% | 85.9% | 100% | 2009-02-05 | no data | 2009-02-20 | 2009-05-25 | no data | 94 | 167 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Macad | 051727008 | Construction of Water System Level 2 | 1 | 583240.02 | 453200 | 130040.02 | 419806.98 | 2/3 | 137843.77 | 557650.75 | 419806.98 | 137843.77 | 100% | 100% | 106% | 95.61% | 100% | 2007-07-17 | not conducted | 2008-05-19 | 2008-08-30 | no data | 103 | 347 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Macad | 051727008 | Slope Protection | 1 | 671665 | 567000 | 104665 | 567000 | 1/3 | 256380 | 823380 | 567000 | 256380 | 100% | 100% | 245% | 122.6% | 100% | 2008-05-28 | not conducted | 2008-09-22 | 2009-01-25 | 2009-04-30 | 125 | 347 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Macad | 051727008 | Construction of Footbridge | 1 | 354185 | 243000 | 111185 | 218700 |  | 112180 | 330880 | 218700 | 112180 | 100% | 100% | 100.9% | 93.42% | 100% | 2009-02-05 | no data | 2009-02-20 | 2009-04-25 | 2009-04-30 | 64 | 383 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Odicon | 051727011 | Construction of Water System Level 2 | 1 | 449725.72 | 321900 | 127825.72 | 321900 | 3/3 | 124185.72 | 446085.72 | 321900 | 124185.72 | 100% | 100% | 97.15% | 99.19% | 100% | 2007-07-17 | not conducted | 2008-05-19 | 2008-09-30 | no data | 134 | 464 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Odicon | 051727011 | Construction of Day Care Center | 1 | 491818 | 412200 | 79618 | 412200 | 1/3 | 180603 | 592803 | 412200 | 180603 | 100% | 100% | 226.8% | 120.5% | 100% | 2008-05-28 | not conducted | 2008-09-22 | 2008-12-25 | no data | 94 | 464 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Quitang | 051727012 | Construction of Water System Level 2 | 1 | 237466.05 | 182300 | 55166.05 | 182300 | 1/3 | 50816.05 | 233116.05 | 182300 | 50816.05 | 100% | 100% | 92.11% | 98.17% | 100% | 2007-07-17 | not conducted | 2008-05-19 | 2009-03-25 | no data | 310 | 461 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Quitang | 051727012 | Day Care Center | 1 | 671334 | 502100 | 169234 | 451890 |  | 142754 | 594644 | 451890 | 142754 | 100% | 100% | 84.35% | 88.58% | 100% | 2008-05-28 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 368 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Salvacion | 051727013 | Construction of Water System Level 2 | 1 | 607161.3 | 497000 | 110161.3 | 472000 | 1/3 | 95511.3 | 567511.3 | 472000 | 95511.3 | 100% | 100% | 86.7% | 93.47% | 100% | 2007-07-17 | not conducted | 2008-07-06 | 2009-05-25 | no data | 323 | 209 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Salvacion | 051727013 | Construction of Footbridge | 1 | 329685 | 224300 | 105385 | 179440 | 1/3 | 91475 | 270915 | 179440 | 91475 | 100% | 100% | 86.8% | 82.17% | 100% | 2008-05-28 | not conducted | 2008-12-26 | 2009-01-25 | no data | 30 | 209 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Salvacion | 051727013 | Construction of Drainage System | 1 | 645616 | 487000 | 158616 | 389600 |  | 140036 | 529636 | 389600 | 140036 | 100% | 100% | 88.29% | 82.04% | 100% | 2009-02-05 | no data | 2009-04-01 | 2009-06-25 | no data | 85 | 190 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | San Cirilo | 051727015 | Construction of Drainage Canal | 1 | 944641.9 | 680099 | 264542.9 | 656007.35 | 3/3 | 277217.9 | 933225.25 | 656007.35 | 277217.9 | 100% | 100% | 104.8% | 98.79% | 100% | 2007-07-17 | not conducted | 2007-11-25 | 2008-05-15 | no data | 172 | 1057 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | San Cirilo | 051727015 | Construction of Day Care Center | 1 | 686270 | 515000 | 171270 | 463500 |  | 150000 | 613500 | 463500 | 150000 | 100% | 100% | 87.58% | 89.4% | 100% | 2009-02-05 | no data | 2009-02-20 | 2009-04-25 | no data | 64 | 1057 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Sta. Rosa del Sur | 051727017 | Construction of Water System Level 2 | 1 | 321781 | 243200 | 78581 | 243160 | 3/3 | 79441 | 322601 | 243160 | 79441 | 100% | 100% | 101.1% | 100.3% | 100% | 2007-07-17 | not conducted | 2008-05-26 | 2008-08-30 | no data | 96 | 485 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Sta.Rosa del Norte | 051727016 | Slope Protection | 1 | 475480 | 334900 | 140580 | 301410 | 1/3 | 112080 | 413490 | 301410 | 112080 | 100% | 100% | 79.73% | 86.96% | 100% | 2008-05-28 | not conducted | 2008-09-22 | 2009-01-25 | no data | 125 | 542 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Tilnac | 051727019 | Construction of Footbridge | 1 | 452579.53 | 373400 | 79179.53 | 362760 | 2/3 | 104000.74 | 466760.74 | 362760 | 104000.74 | 100% | 100% | 131.3% | 103.1% | 100% | 2007-07-17 | not conducted | 2008-05-16 | 2008-09-30 | no data | 137 | 161 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Tilnac | 051727019 | Construction of 2-Classroom School Bldg | 1 | 1108521 | 808300 | 300221 | 801640 | 1/3 | 291757 | 1093397 | 801640 | 291757 | 100% | 100% | 97.18% | 98.64% | 100% | 2008-05-28 | not conducted | 2008-12-01 | 2009-04-25 | no data | 145 | 161 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Tilnac | 051727019 | Construction of Slope Protection | 1 | 887200 | 638000 | 249200 | 574200 |  | 256590 | 830790 | 574200 | 256590 | 100% | 100% | 103% | 93.64% | 100% | 2009-02-05 | no data | 2009-04-01 | 2009-05-25 | no data | 54 | 120 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Tinalmud | 051727020 | Construction of Water System Level 2 | 1 | 625930.74 | 531800 | 94130.74 | 478620 | 1/3 | 94970.74 | 573590.74 | 478620 | 94970.74 | 100% | 100% | 100.9% | 91.64% | 100% | 2007-07-17 | not conducted | 2008-06-26 | 2009-06-25 | no data | 364 | 434 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Ayugao | 051729001 | Construction of Water System Level 2 | 1 | 661000 | 490045 | 170955 | 392036 |  | 238910 | 630946 | 392036 | 238910 | 100% | 100% | 139.8% | 95.45% | 100% | 2009-01-14 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 38 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Bagong Sirang | 051729002 | Deep Sea Fishing Ulitizing Fish Aggregating Device (TABAW) | 1 | 105300 | 73000 | 32300 | 65700 | 2/3 | 21840 | 87540 | 65700 | 21840 | 100% | 100% | 67.62% | 83.13% | 100% | 2007-07-24 | not conducted | 2008-04-08 | 2008-06-08 | no data | 61 | 115 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Bagong-sirang | 051729002 | Construction of Pathway | 1 | 625000 | 435890 | 189110 | 408525 |  | 277500 | 686025 | 408525 | 277500 | 100% | 100% | 146.7% | 109.8% | 100% | 2009-01-14 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 115 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Baliguian | 051729003 | Construction of Water System Level 2 | 1 | 493800 | 319200 | 174600 | 255360 | 1/3 | 140335 | 395695 | 255360 | 140335 | 100% | 100% | 80.38% | 80.13% | 100% | 2007-07-24 | not conducted | 2008-01-28 | 2008-11-30 | no data | 307 | 202 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Bicalen | 051729005 | Construction of Water System Level 2 | 1 | 1011900 | 708451 | 303449 | 389368 | 0.33333 | 279474 | 668842 | 389368 | 279474 | 100% | 100% | 92.1% | 66.1% | 100% | 2007-07-24 | not conducted | 2008-06-24 | 2009-03-25 | no data | 274 | 84 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Bitaogan | 051729006 | Construction of School Building | 1 | 1132100 | 871500 | 260600 | 871500 | 0.33333 | 277866.19 | 1149366.19 | 871500 | 277866.19 | 100% | 100% | 106.6% | 101.5% | 100% | 2008-06-17 | not conducted | 2008-09-04 | 2009-04-25 | no data | 233 | 230 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Buenavista | 051729007 | Construction of Water System Level 2 | 1 | 1463900 | 1129930 | 333970 | 1016937 | 0 | 328546 | 1345483 | 1016937 | 328546 | 100% | 100% | 98.38% | 91.91% | 100% | 2008-06-17 | not conducted | 2008-10-12 | 2009-04-25 | no data | 195 | 182 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Bulalacao | 051729008 | Construction of Seawall | 1 | 2027600 | 1506124 | 521476 | 1355512 |  | 531112.53 | 1886624.53 | 1355512 | 531112.53 | 100% | 100% | 101.8% | 93.05% | 100% | 2009-01-14 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 210 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Cagnipa | 051729009 | Construction of Spillway | 1 | 949694 | 656839 | 292855 | 591155.1 | 0.33333 | 210151 | 801306.1 | 591155.1 | 210151 | 100% | 100% | 71.76% | 84.38% | 100% | 2008-06-17 | not conducted | 2008-09-17 | 2009-01-25 | no data | 130 | 202 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Cagnipa | 051729009 | Construction of Flood Control | 1 | 657300 | 462585 | 194715 | 416326.5 |  | 255190 | 671516.5 | 416326.5 | 255190 | 100% | 100% | 131.1% | 102.2% | 100% | 2009-01-14 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 202 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Lagha | 051729010 | Construction of Water System Level 2 | 1 | 617009 | 443244 | 173765 | 398919.6 | 0.33333 | 193581.38 | 592500.98 | 398919.6 | 193581.38 | 100% | 100% | 111.4% | 96.03% | 100% | 2008-06-17 | not conducted | 2008-09-12 | 2008-12-25 | no data | 104 | 156 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Lidong | 051729011 | Construction of Farm to Market Road | 1 | 2849400 | 2036500 | 812900 | 1213170 | 0.33333 | 189675 | 1402845 | 1213170 | 189675 | 100% | 100% | 23.33% | 49.23% | 100% | 2007-07-24 | not conducted | 2008-10-09 | 2009-08-30 | no data | 325 | 138 | completed as built | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Maangas | 051729013 | Sloping Agricultural Land Technology: Fruits & Vegetable Production | 1 | 244500 | 170045 | 74455 | 170045 | 0.33333 | 46099 | 216144 | 170045 | 46099 | 100% | 100% | 61.92% | 88.4% | 100% | 2007-07-24 | not conducted | 2008-06-02 | 2008-11-02 | no data | 153 | 677 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Maangas | 051729013 | Construction of Seawall | 1 | 1387500 | 873400 | 514100 | 853088.15 |  | 644824 | 1497912.15 | 853088.15 | 644824 | 100% | 100% | 125.4% | 108% | 100% | 2009-01-14 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 677 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Pagsangaan | 051729014 | Improvement of Farm to Market Road | 1 | 2588800 | 1863800 | 725000 | 1322685 | 1/3 | 261581.68 | 1584266.68 | 1322685 | 261581.68 | 100% | 100% | 36.08% | 61.2% | 100% | 2007-07-24 | not conducted | 2008-10-09 | 2009-08-25 | no data | 320 | 114 | completed as built | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Patrocinio | 051729016 | Construction of Water System Level 2 | 1 | 324600 | 221310 | 103290 | 221310 | 0.33333 | 74690 | 296000 | 221310 | 74690 | 100% | 100% | 72.31% | 91.19% | 100% | 2007-07-24 | not conducted | 2008-01-28 | 2008-11-25 | no data | 302 | 75 | On-going | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Pili | 051729017 | Construction of Resource Center | 1 | 819700 | 597509 | 222191 | 584820.91 | 0 | 150421 | 735241.91 | 584820.91 | 150421 | 100% | 100% | 67.7% | 89.7% | 100% | 2008-06-17 | not conducted | 2008-10-30 | 2009-06-25 | no data | 238 | 137 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Sta. Maria | 051729018 | Construction of Seawall | 1 | 2523643 | 1854156 | 669487 | 1746155.32 |  | 970504 | 2716659.32 | 1746155.32 | 970504 | 100% | 100% | 145% | 107.6% | 100% | 2009-01-14 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 920 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Aniog | 051731001 | Construction of Cable-Stayed Pedestrian Bridge | 1 | 922000 | 702000 | 220000 | 702000 | 0.33333 | 74250 | 776250 | 702000 | 74250 | 100% | 100% | 33.75% | 84.19% | 100% | 2007-07-13 | not conducted | 2008-04-21 | 2009-08-30 | no data | 496 | 153 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Atulayan | 051731002 | Construction of Lined Canal | 1 | 452134.85 | 422134.85 | 30000 | 379921.37 |  | 30100 | 410021.37 | 379921.37 | 30100 | 100% | 100% | 100.3% | 90.69% | 100% | 2008-12-11 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 167 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Bognalon | 051731003 | Sea Weeds Farming Production | 1 | 496000 | 377675 | 118325 | 359040 | 2/3 | 117925 | 476965 | 359040 | 117925 | 100% | 100% | 99.66% | 96.16% | 100% | 2007-07-13 | not conducted | 2008-04-02 | 2008-05-25 | no data | 53 | 249 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Buracan | 051731004 | Construction of Farm to market Road | 1 | 2322226.65 | 1639994.28 | 682232.37 | 1267411.62 | 0 | 312000 | 1579411.62 | 1267411.62 | 312000 | 100% | 100% | 45.73% | 68.01% | 100% | 2008-07-24 | not conducted | 2009-06-01 | 2009-07-25 | no data | 54 | 560 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Catalotoan | 051731005 | Construction of Water System Level 2 | 1 | 1660000 | 1434300 | 225700 | 1360835.97 | 0.33333 | 243420 | 1604255.97 | 1360835.97 | 243420 | 100% | 100% | 107.9% | 96.64% | 100% | 2007-07-13 | not conducted | 2008-06-28 | 2009-08-30 | no data | 428 | 261 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Del Carmen | 051731006 | Provision of Farm Machineries | 1 | 169715 | 159715 | 10000 | 127772 | 0 | 6000 | 133772 | 127772 | 6000 | 100% | 100% | 60% | 78.82% | 100% | 2008-07-24 | not conducted | 2009-02-01 | 2009-07-25 | no data | 174 | 280 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Kilantaao | 051731007 | Construction of Farm to market Road | 1 | 2037718.74 | 1368168.37 | 669550.37 | 1231351.5 | 0 | 630550.37 | 1861901.87 | 1231351.5 | 630550.37 | 100% | 100% | 94.18% | 91.37% | 100% | 2008-07-24 | not conducted | 2009-05-01 | 2009-08-30 | no data | 121 | 259 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Kilomaon | 051731008 | Construction of Water System Level 2 | 1 | 1165000 | 953500 | 211500 | 858150 | 0.33333 | 135720 | 993870 | 858150 | 135720 | 100% | 100% | 64.17% | 85.31% | 100% | 2007-07-13 | not conducted | 2008-05-25 | 2009-04-30 | no data | 340 | 271 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Mabca | 051731010 | Construction of Farm to market Road | 1 | 862300.1 | 483450.1 | 378850 | 385920 | 0 | 31000 | 416920 | 385920 | 31000 | 100% | 100% | 8.183% | 48.35% | 100% | 2008-07-24 | not conducted | 2009-02-01 | 2009-08-30 | no data | 210 | 356 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Minadongjol | 051731011 | Construction of Farm to market Road | 1 | 1872449.35 | 1333243.95 | 539205.4 | 1194764.93 | 0 | 148225 | 1342989.93 | 1194764.93 | 148225 | 100% | 100% | 27.49% | 71.72% | 100% | 2008-07-24 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 337 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Nato | 051731012 | Extension of Sea Wall | 1 | 1196053.12 | 1078783.12 | 117270 | 1033026.5 |  | 66000 | 1099026.5 | 1033026.5 | 66000 | 100% | 100% | 56.28% | 91.89% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 599 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Patitinan | 051731014 | Construction of Water System Level II | 1 | 1375461.55 | 1275461.55 | 100000 | 1020369.24 |  | 51000 | 1071369.24 | 1020369.24 | 51000 | 100% | 100% | 51% | 77.89% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 462 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | San Antonio | 051731015 | Provision of Farm Machineries | 1 | 248465 | 238465 | 10000 | 134300 | 0 | 10100 | 144400 | 134300 | 10100 | 100% | 100% | 101% | 58.12% | 100% | 2008-07-24 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 207 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | San Isidro | 051731017 | Provision of Farm Machineries | 1 | 250122 | 219122 | 31000 | 204422.95 | 0.33333 | 20100 | 224522.95 | 204422.95 | 20100 | 100% | 100% | 64.84% | 89.77% | 100% | 2007-07-13 | not conducted | 2008-04-02 | 2008-12-20 | no data | 262 | 279 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Sibaguan | 051731020 | Construction of Water System Level II | 1 | 2350244.26 | 2090244.26 | 260000 | 1672195.36 |  | 41000 | 1713195.36 | 1672195.36 | 41000 | 100% | 100% | 15.77% | 72.89% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-07-25 | no data | 85 | 439 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Sto. Niño | 051731019 | Construction of Diversion Dam | 1 | 1375000 | 1132000 | 243000 | 905600 | 0.33333 | 160120 | 1065720 | 905600 | 160120 | 100% | 100% | 65.89% | 77.51% | 100% | 2007-07-13 | not conducted | 2008-04-02 | 2008-08-25 | no data | 145 | 195 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Tinorongan | 051731022 | Construction of Cable-Stayed Pedestrian Bridge | 1 | 983000 | 837300 | 145700 | 837300 | 2/3 | 383734.65 | 1221034.65 | 837300 | 383734.65 | 100% | 100% | 263.4% | 124.2% | 100% | 2007-07-13 | not conducted | 2008-04-20 | 2009-07-25 | no data | 461 | 470 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Sagñay | 051731 | Turague | 051731023 | Construction of Farm to Market Road | 1 | 1838623.98 | 1304903.08 | 533720.9 | 1043922.46 |  | 60000 | 1103922.46 | 1043922.46 | 60000 | 100% | 100% | 11.24% | 60.04% | 100% | 2008-12-11 | not conducted | 2009-05-01 | 2009-06-25 | no data | 55 | 437 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Bagong Sirang | 051735001 | Construction of Water System Level 2 | 1 | 946000 | 648840 | 297160 | 648840 |  | 279170 | 928010 | 648840 | 279170 | 100% | 100% | 93.95% | 98.1% | 100% | 2008-08-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 80 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Boboan | 051735003 | Construction of Barangay Health Station | 1 | 651100 | 545180 | 105920 | 544921 | 3/3 | 109470 | 654391 | 544921 | 109470 | 100% | 100% | 103.4% | 100.5% | 100% | 2007-07-16 | not conducted | 2008-03-05 | 2008-06-25 | no data | 112 | 247 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Boboan | 051735003 | Construction of Day Care Center | 1 | 794000 | 584435 | 209565 | 525991.5 |  | 176740 | 702731.5 | 525991.5 | 176740 | 100% | 100% | 84.34% | 88.51% | 100% | 2008-08-12 | not conducted | 2008-12-09 | 2009-04-25 | no data | 137 | 247 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Butawanan | 051735004 | Construction of Day Care Center | 1 | 822500 | 589275 | 233225 | 589275 |  | 222725 | 812000 | 589275 | 222725 | 100% | 100% | 95.5% | 98.72% | 100% | 2008-08-12 | not conducted | 2008-12-07 | 2009-04-25 | no data | 139 | 345 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Fundado | 051735006 | Const. of 1 unit 2 Barrel Box Culvert | 1 | 589800 | 488500 | 101300 | 488500 | 1/3 | 87300 | 575800 | 488500 | 87300 | 100% | 100% | 86.18% | 97.63% | 100% | 2007-07-16 | not conducted | 2008-08-01 | 2009-04-25 | no data | 267 | 257 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Mabuhay | 051735010 | Const. of 2 units 1 Barrel Box Culvert | 1 | 840900 | 644575 | 196325 | 643664.43 | 2/3 | 187600 | 831264.43 | 643664.43 | 187600 | 100% | 100% | 95.56% | 98.85% | 100% | 2007-07-16 | not conducted | 2008-04-28 | 2008-11-25 | no data | 211 | 89 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Mabuhay | 051735010 | Construction of 1 Unit Two-Classroom School Building | 1 | 1398000 | 1042950 | 355050 | 969133.51 |  | 350580 | 1319713.51 | 969133.51 | 350580 | 100% | 100% | 98.74% | 94.4% | 100% | 2008-08-12 | not conducted | 2008-12-22 | 2009-06-25 | no data | 185 | 89 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Malaconini | 051735011 | Const. of 1 unit 2 Barrel Box Culvert | 1 | 581700 | 445025 | 136675 | 445025 | 2/3 | 66600 | 511625 | 445025 | 66600 | 100% | 100% | 48.73% | 87.95% | 100% | 2007-07-16 | not conducted | 2008-04-21 | 2008-12-15 | no data | 238 | 69 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Matandang Siruma | 051735013 | Construction oF Water System Level 2 | 1 | 974453 | 765103 | 209350 | 738883.02 |  | 209350 | 948233.02 | 738883.02 | 209350 | 100% | 100% | 100% | 97.31% | 100% | 2007-07-16 | not conducted | 2008-09-15 | 2009-04-30 | no data | 227 | 72 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Salvacion | 051735017 | Concreting /Improvement bgy. Road | 1 | 1336900 | 1087575 | 249325 | 1087575 | 0.33333 | 164100 | 1251675 | 1087575 | 164100 | 100% | 100% | 65.82% | 93.63% | 100% | 2007-07-18 | not conducted | 2008-07-05 | 2008-09-05 | no data | 62 | 221 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Salvacion | 051735017 | Construction of 1 Unit Three-Classroom School Building | 1 | 1830750 | 1451925 | 378825 | 1451925 |  | 415310.86 | 1867235.86 | 1451925 | 415310.86 | 100% | 100% | 109.6% | 102% | 100% | 2008-08-12 | not conducted | 2009-02-01 | 2009-06-25 | no data | 144 | 221 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | San Andres | 051735018 | Construction of 2 CL Elem. School Building | 1 | 955300 | 830050 | 125250 | 830050 | 0.33333 | 209785 | 1039835 | 830050 | 209785 | 100% | 100% | 167.5% | 108.8% | 100% | 2007-07-16 | not conducted | 2008-02-01 | 2008-12-20 | no data | 323 | 57 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | San Ramon | 051735019 | Construction of 1 Unit Two-Classroom School Building | 1 | 1402000 | 1037030 | 364970 | 1031054.67 |  | 370078.25 | 1401132.92 | 1031054.67 | 370078.25 | 100% | 100% | 101.4% | 99.94% | 100% | 2008-08-12 | not conducted | 2008-12-04 | 2009-05-25 | no data | 172 | 141 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Sulpa | 051735020 | Construction of Water System Level 2 | 1 | 759900 | 653900 | 106000 | 653890.8 |  | 101043 | 754933.8 | 653890.8 | 101043 | 100% | 100% | 95.32% | 99.35% | 100% | 2007-07-16 | not conducted | 2008-09-01 | 2009-05-25 | no data | 266 | 160 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Sulpa | 051735020 | Construction of Day Care Center | 1 | 787000 | 583510 | 203490 | 583510 |  | 201118.5 | 784628.5 | 583510 | 201118.5 | 100% | 100% | 98.83% | 99.7% | 100% | 2008-08-12 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 160 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Tandoc - C3 | 051735021 | Construction of Water System Level 2 | 3 | 1426900 | 1140092 | 286808 | 1140092 |  | 204400 | 1344492 | 1140092 | 204400 | 100% | 100% | 71.27% | 94.22% | 100% | 2007-07-16 | not conducted | 2009-01-20 | 2009-10-15 | no data | 268 | 299 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Homestead | 051735008 | Construction of Water System Level 2 | 3 | 1426900 | 1140092 | 286808 | 1140092 |  | 204400 | 1344492 | 1140092 | 204400 | 100% | 100% | 71.27% | 94.22% | 100% | 2007-07-16 | not conducted | 2009-01-20 | 2009-10-15 | no data | 268 | 299 |  | 1 | VISAYAS
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Tonggo-Bantigue | 051735022 | Road Rehabilitation | 1 | 628000 | 471120 | 156880 | 424008 |  | 156880 | 580888 | 424008 | 156880 | 100% | 100% | 100% | 92.5% | 100% | 2008-08-12 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 67 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Antipolo - C8 | 052001001 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Bacak - C8 | 052001002 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Bagatabao - C8 | 052001003 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Bugao | 052001004 | Construction of Seawall | 1 | 4111817.35 | 2636991.9 | 1474825.45 | 2109598.52 | 0.33333 | 1505448.58 | 3615047.1 | 2109598.52 | 1505448.58 | 100% | 100% | 102.1% | 87.92% | 100% | 2008-06-20 | not conducted | 2008-11-20 | 2009-10-28 | no data | 342 | 52 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Cahan | 052001005 | Construction of Water System Level 2 | 1 | 1025000 | 629561.7 | 395438.3 | 503649.36 |  | 253637.5 | 757286.86 | 503649.36 | 253637.5 | 100% | 100% | 64.14% | 73.88% | 100% | 2009-01-23 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 52 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Hinipaan | 052001006 | Construction of Water System Level 2 | 1 | 1020000 | 635869.07 | 384130.93 | 508695.26 | 0.33333 | 425159.07 | 933854.33 | 508695.26 | 425159.07 | 100% | 100% | 110.7% | 91.55% | 100% | 2008-06-20 | not conducted | 2008-08-01 | 2009-03-25 | no data | 236 | 87 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Hinipaan | 052001006 | Construction of Flood Control | 1 | 2675000 | 1686962.48 | 988037.52 | 1349568.98 |  | 560332.06 | 1909901.04 | 1349568.98 | 560332.06 | 100% | 100% | 56.71% | 71.4% | 100% | 2009-01-23 | not conducted | 2009-04-20 | 2009-05-31 | no data | 41 | 87 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Magsaysay | 052001007 | Construction of Drainage Canal | 1 | 1500000 | 927977.85 | 572022.15 | 835180.07 |  | 426510.75 | 1261690.82 | 835180.07 | 426510.75 | 100% | 100% | 74.56% | 84.11% | 100% | 2009-01-23 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 159 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Poblacion - C8 | 052001008 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Quezon - C8 | 052001011 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Quiragay | 052001010 | Construction of Water System Level 2 | 1 | 900000 | 564739.1 | 335260.9 | 564739.1 | 0.33333 | 338535.7 | 903274.8 | 564739.1 | 338535.7 | 100% | 100% | 101% | 100.4% | 100% | 2008-06-20 | not conducted | 2008-10-15 | 2008-12-30 | no data | 76 | 75 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Sagrada | 052001012 | Construction of Water System Level 2 | 1 | 1135000 | 660397.03 | 474602.97 | 660397.03 | 0.33333 | 425823.97 | 1086221 | 660397.03 | 425823.97 | 100% | 100% | 89.72% | 95.7% | 100% | 2008-06-20 | not conducted | 2008-08-01 | 2009-06-25 | no data | 328 | 145 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Salvacion | 052001013 | Construction of Water System Level 2 | 1 | 1490000 | 941941.91 | 548058.09 | 847747.72 |  | 445354.69 | 1293102.41 | 847747.72 | 445354.69 | 100% | 100% | 81.26% | 86.79% | 100% | 2009-01-23 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 325 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | San Isidro | 052001014 | Construction of Water System Level 2 | 1 | 2200000 | 1359892.8 | 840107.2 | 1223903.52 |  | 687165 | 1911068.52 | 1223903.52 | 687165 | 100% | 100% | 81.79% | 86.87% | 100% | 2009-01-23 | not conducted | 2009-04-01 | 2009-06-25 | no data | 85 | 673 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | San Rafael - C8 | 052001015 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | San Vicente | 052001016 | Construction of Drainage System | 1 | 1435000 | 882839.97 | 552160.03 | 706271.97 | 1/3 | 549029.12 | 1255301.09 | 706271.97 | 549029.12 | 100% | 100% | 99.43% | 87.48% | 100% | 2008-06-20 | not conducted | 2008-10-01 | 2008-12-25 | no data | 85 | 836 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Sta. Mesa - C8 | 052001017 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Sta. Teresa - C8 | 052001018 | Construction of Water System Level 2 | 8 | 8650000 | 5191133.09 | 3458866.91 | 5191133.09 | 0.33333 | 3420065.9 | 8611198.99 | 5191133.09 | 3420065.9 | 100% | 100% | 98.88% | 99.55% | 100% | 2007-06-07 | not conducted | 2008-04-03 | 2009-05-25 | no data | 417 | 1017 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Suchan | 052001019 | Construction of Water System Level 2 | 1 | 400733.82 | 208866.91 | 191866.91 | 208866.91 | 3/3 | 192053.09 | 400920 | 208866.91 | 192053.09 | 100% | 100% | 100.1% | 100% | 100% | 2007-06-07 | not conducted | 2008-01-23 | 2008-07-01 | no data | 160 | 135 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Baybay - C4 | 052004001 | Construction of Water System Level 2 | 4 | 2000000 | 1177290 | 822710 | 1177290 | 3/3 | 782860 | 1960150 | 1177290 | 782860 | 100% | 100% | 95.16% | 98.01% | 100% | 2006-07-15 | not conducted | 2006-12-05 | 2007-06-30 | 2007-10-06 | 207 | 139 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Toytoy | 052004025 | Construction of Water System Level 2 | 4 | 2000000 | 1177290 | 822710 | 1177290 | 3/3 | 782860 | 1960150 | 1177290 | 782860 | 100% | 100% | 95.16% | 98.01% | 100% | 2006-07-15 | not conducted | 2006-12-05 | 2007-06-30 | 2007-10-06 | 207 | 139 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Bothoan | 052004003 | Construction of Water System Level 2 | 4 | 2000000 | 1177290 | 822710 | 1177290 | 3/3 | 782860 | 1960150 | 1177290 | 782860 | 100% | 100% | 95.16% | 98.01% | 100% | 2006-07-15 | not conducted | 2006-12-05 | 2007-06-30 | 2007-10-06 | 207 | 139 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Bocon | 052004002 | Construction of Sea Wall | 1 | 1755738 | 947621 | 808117 | 947621 | 3/3 | 763297 | 1710918 | 947621 | 763297 | 100% | 100% | 94.45% | 97.45% | 100% | 2006-07-15 | not conducted | 2006-10-03 | 2007-12-16 | 2007-03-08 | 439 | 41 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Buenavista | 052004004 | Construction of Water System Level 2 | 1 | 455548 | 267258.6 | 188289.4 | 267258.6 | 3/3 | 178629.4 | 445888 | 267258.6 | 178629.4 | 100% | 100% | 94.87% | 97.88% | 100% | 2005-05-20 | 2005-06-20 | 2005-10-05 | 2006-02-28 | no data | 146 | 80 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Buenavista | 052004004 | Concreting of Barangay Road | 1 | 653432.32 | 429208 | 224224.32 | 343366.4 | 1/3 | 213829.32 | 557195.72 | 343366.4 | 213829.32 | 100% | 100% | 95.36% | 85.27% | 100% | 2007-08-10 | not conducted | 2005-10-05 | 2006-05-31 | no data | 238 | 95 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Bulalacao | 052004005 | Construction of Water System Level 2 | 1 | 470495.5 | 301346.5 | 169149 | 301346.5 | 3/3 | 169428 | 470774.5 | 301346.5 | 169428 | 100% | 100% | 100.2% | 100.1% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-24 | 2006-02-01 | 2006-03-07 | 130 | 97 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Camburo | 052004006 | Improvement of Farm to Market Road | 1 | 786452 | 371725.9 | 414726.1 | 371725.9 | 3/3 | 493011.9 | 864737.8 | 371725.9 | 493011.9 | 100% | 100% | 118.9% | 110% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-26 | 2005-12-22 | no data | 87 | 99 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Camburo | 052004006 | Construction of Water System Level 2 | 1 | 420000 | 148374 | 271626 | 148374 | 3/3 | 273359 | 421733 | 148374 | 273359 | 100% | 100% | 100.6% | 100.4% | 100% | 2006-07-15 | not conducted | 2006-09-11 | 2006-11-26 | 2007-03-06 | 76 | 99 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Dariao | 052004007 | Construction of Farm to Market Road | 1 | 1340000 | 763048 | 576952 | 763048 | 3/3 | 557647 | 1320695 | 763048 | 557647 | 100% | 100% | 96.65% | 98.56% | 100% | 2006-07-15 | not conducted | 2006-09-11 | 2006-12-22 | 2007-10-18 | 102 | 286 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Dariao | 052004007 | Construction of Water System Level 2 | 1 | 759523.68 | 519159 | 240364.68 | 519159 | 3/3 | 225234.68 | 744393.68 | 519159 | 225234.68 | 100% | 100% | 93.71% | 98.01% | 100% | 2007-08-10 | not conducted | 2008-03-15 | 2008-06-15 | 2008-07-30 | 92 | 384 | On-going | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Datag East - C2 | 052004008 | Rehab./Improvement of Water System Level 2 | 2 | 2377641.38 | 1484515.47 | 893125.91 | 1484515.47 | 3/3 | 893980.91 | 2378496.38 | 1484515.47 | 893980.91 | 100% | 100% | 100.1% | 100% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-27 | 2006-02-01 | 2006-03-08 | 127 | 187 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Supang | 052004024 | Rehab./Improvement of Water System Level 2 | 2 | 2377641.38 | 1484515.47 | 893125.91 | 1484515.47 | 3/3 | 893980.91 | 2378496.38 | 1484515.47 | 893980.91 | 100% | 100% | 100.1% | 100% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-27 | 2006-02-01 | 2006-03-08 | 127 | 187 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Guiamlong | 052004010 | Construction of Flood Control | 1 | 1226038 | 640879.1 | 585158.9 | 640879.1 | 3/3 | 585561.9 | 1226441 | 640879.1 | 585561.9 | 100% | 100% | 100.1% | 100% | 100% | 2005-05-20 | 2005-06-20 | 2005-10-01 | 2005-12-01 | 2006-03-08 | 61 | 495 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Guiamlong | 052004010 | Extension of Flood Control | 1 | 1372933.36 | 957522 | 415411.36 | 931702.79 | 3/3 | 374877.41 | 1306580.2 | 931702.79 | 374877.41 | 100% | 100% | 90.24% | 95.17% | 100% | 2007-08-10 | not conducted | 2007-12-07 | 2008-06-29 | 2008-07-26 | 205 | 91 | On-going | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Hitoma | 052004011 | Construction of Flood Control | 1 | 2242220 | 1233927.93 | 1008292.07 | 1233927.93 | 3/3 | 664320.07 | 1898248 | 1233927.93 | 664320.07 | 100% | 100% | 65.89% | 84.66% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-30 | 2006-01-01 | 2006-03-07 | 93 | 95 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Icanbato | 052004012 | Improvement of Water System | 1 | 140556.51 | 82466 | 58090.51 | 82466 | 1/3 | 43090.51 | 125556.51 | 82466 | 43090.51 | 100% | 100% | 74.18% | 89.33% | 100% | 2007-08-10 | not conducted | 2008-03-25 | 2009-04-30 | no data | 401 | 158 |  | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Inalmasinan | 052004013 | Construction of Flood Control | 1 | 2059719 | 880310 | 1179409 | 880310 | 3/3 | 1125409 | 2005719 | 880310 | 1125409 | 100% | 100% | 95.42% | 97.38% | 100% | 2006-07-15 | not conducted | 2006-11-17 | 2007-12-18 | 2007-03-05 | 396 | 134 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Iyao | 052004014 | Construction of Flood Control | 1 | 1514440 | 839783 | 674657 | 839783 | 3/3 | 493512.5 | 1333295.5 | 839783 | 493512.5 | 100% | 100% | 73.15% | 88.04% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-26 | 2005-12-01 | 2006-03-07 | 66 | 120 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Mabini | 052004015 | Construction of Water System Level 2 | 1 | 730999.5 | 403014.5 | 327985 | 403014.5 | 3/3 | 326641 | 729655.5 | 403014.5 | 326641 | 100% | 100% | 99.59% | 99.82% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-27 | 2006-03-01 | 2006-03-07 | 155 | 87 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Maui | 052004017 | Construction of Two-Classroom Elem. School Building | 1 | 1315000 | 762707 | 552293 | 762707 | 3/3 | 552293 | 1315000 | 762707 | 552293 | 100% | 100% | 100% | 100% | 100% | 2006-07-15 | not conducted | 2006-10-16 | 2007-07-11 | no data | 268 | 48 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Maysuram | 052004018 | Construction of Water System Level 2 | 1 | 445189.1 | 207370.1 | 237819 | 207370 | 3/3 | 286892.52 | 494262.52 | 207370 | 286892.52 | 100% | 100% | 120.6% | 111% | 100% | 2005-05-20 | 2005-06-20 | 2005-10-03 | 2006-02-28 | 2006-03-08 | 148 | 274 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Maysuram | 052004018 | Construction of Flood Control | 1 | 1694388.51 | 1114991 | 579397.51 | 1114991 | 3/3 | 596462.51 | 1711453.51 | 1114991 | 596462.51 | 100% | 100% | 102.9% | 101% | 100% | 2007-08-10 | not conducted | 2008-01-05 | 2008-12-30 | 2009-01-24 | 360 | 150 | On-going | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Milaviga | 052004019 | Construction of Sea Wall | 1 | 1760629 | 905413 | 855216 | 905413 | 3/3 | 825961.1 | 1731374.1 | 905413 | 825961.1 | 100% | 100% | 96.58% | 98.34% | 100% | 2006-07-15 | not conducted | 2006-07-20 | 2007-12-16 | 2007-03-08 | 514 | 246 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Obi | 052004028 | Construction of Water System Level 2 | 1 | 870628 | 567439.6 | 303188.4 | 567439.6 | 3/3 | 290268.4 | 857708 | 567439.6 | 290268.4 | 100% | 100% | 95.74% | 98.52% | 100% | 2005-05-20 | 2005-06-20 | 2005-09-26 | 2006-02-01 | no data | 128 | 123 | Completed | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Panique | 052004020 | Construction of Water System Level 2 | 1 | 457130 | 275870 | 181260 | 275870 | 3/3 | 165141.67 | 441011.67 | 275870 | 165141.67 | 100% | 100% | 91.11% | 96.47% | 100% | 2005-05-20 | 2005-06-20 | 2005-10-03 | 2005-12-01 | 2006-03-07 | 59 | 180 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Panique | 052004020 | Construction of Flood Control | 1 | 671890.96 | 450696 | 221194.96 | 450696 | 3/3 | 216464.96 | 667160.96 | 450696 | 216464.96 | 100% | 100% | 97.86% | 99.3% | 100% | 2007-08-10 | not conducted | 2008-01-03 | 2008-12-30 | 2009-01-15 | 362 | 202 | On-going | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Sabangan | 052004021 | Construction of Water System Level 2 | 1 | 806322 | 436325.4 | 369996.6 | 436325.4 | 3/3 | 383165 | 819490.4 | 436325.4 | 383165 | 100% | 100% | 103.6% | 101.6% | 100% | 2005-05-20 | 2005-06-20 | 2005-10-04 | 2005-12-01 | 2006-03-08 | 58 | 201 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Sabangan | 052004021 | Construction of Flood Control | 1 | 1912474.58 | 1388652 | 523822.58 | 1388651.6 | 1/3 | 530303.83 | 1918955.43 | 1388651.6 | 530303.83 | 100% | 100% | 101.2% | 100.3% | 100% | 2007-08-10 | not conducted | 2007-12-07 | 2009-04-30 | 2009-06-07 | 510 | 216 | On-going | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Sabloyon | 052004022 | Construction of Flood Control | 1 | 1895574 | 994804 | 900770 | 994804 | 3/3 | 877123 | 1871927 | 994804 | 877123 | 100% | 100% | 97.37% | 98.75% | 100% | 2006-07-15 | not conducted | 2006-10-02 | 2006-12-22 | 2007-03-08 | 81 | 122 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Sabloyon | 052004022 | Extension of Flood Control | 1 | 3566857.58 | 2542584 | 1024273.58 | 2542584 | 3/3 | 793867.83 | 3336451.83 | 2542584 | 793867.83 | 100% | 100% | 77.51% | 93.54% | 100% | 2007-08-10 | not conducted | 2007-12-05 | 2008-07-05 | 2008-11-04 | 213 | 151 | On-going | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Salvacion | 052004023 | Construction of Flood Control | 1 | 1579260 | 811199 | 768061 | 811199 | 3/3 | 751711 | 1562910 | 811199 | 751711 | 100% | 100% | 97.87% | 98.96% | 100% | 2006-07-15 | not conducted | 2006-10-01 | 2007-01-06 | 2007-03-05 | 97 | 95 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Tubli | 052004026 | Construction of Water System Level 2 | 1 | 1170000 | 709234 | 460766 | 709234 | 3/3 | 462766 | 1172000 | 709234 | 462766 | 100% | 100% | 100.4% | 100.2% | 100% | 2006-07-15 | not conducted | 2006-10-16 | 2006-12-15 | 2007-03-07 | 60 | 409 | Inaugurated | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Tubli | 052004026 | Extension of Sea Wall | 1 | 2298043.05 | 614722 | 1683321.05 | 368833.2 | 1/3 | 1710701.25 | 2079534.45 | 368833.2 | 1710701.25 | 100% | 100% | 101.6% | 90.49% | 100% | 2007-08-10 | not conducted | 2007-12-05 | 2009-04-30 | no data | 512 | 473 | completed as built | 1 | VISAYAS
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Tucao | 052004027 | Construction of Flood Control | 1 | 1910352 | 1070563.9 | 839788.1 | 1070563.9 | 3/3 | 860653.1 | 1931217 | 1070563.9 | 860653.1 | 100% | 100% | 102.5% | 101.1% | 100% | 2005-05-20 | 2005-06-20 | 2005-10-05 | 2006-02-28 | no data | 146 | 88 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Ambolong | 054101001 | Const.of 1 unit Productivity Enhancement Center | 1 | 917300 | 705900 | 211400 | 705900 | 3/3 | 246697 | 952597 | 705900 | 246697 | 100% | 100% | 116.7% | 103.8% | 100% | 2006-06-13 | 2006-06-14 | 2006-08-10 | 2006-12-11 | no data | 123 | 545 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Ambolong | 054101001 | Construction of Drainage Lined Canal | 1 | 956591.4 | 896455.15 | 60136.25 | 870792.05 | 1/3 | 97824.25 | 968616.3 | 870792.05 | 97824.25 | 100% | 100% | 162.7% | 101.3% | 100% | 2009-02-18 | no data | 2009-03-25 | 2009-07-25 | no data | 122 | 550 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Amoroy | 054101002 | Construction of Brgy. Health Station | 1 | 305953.96 | 197007.19 | 108946.77 | 197007.19 | 3/3 | 113742.91 | 310750.1 | 197007.19 | 113742.91 | 100% | 100% | 104.4% | 101.6% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-10-15 | 2004-10-20 | 144 | 116 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Amoroy | 054101002 | Construction of Water System Level 2 | 1 | 846789 | 565209 | 281580 | 565209 | 3/3 | 309990 | 875199 | 565209 | 309990 | 100% | 100% | 110.1% | 103.4% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-26 | 2006-01-24 | no data | 120 | 90 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Amotag | 054101003 | Construction of Water System Level 2 | 1 | 982581.29 | 648756.49 | 333824.8 | 648756.39 | 3/3 | 279491.8 | 928248.19 | 648756.39 | 279491.8 | 100% | 100% | 83.72% | 94.47% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-17 | 2006-01-24 | 2006-02-02 | 99 | 261 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Amotag | 054101003 | Construction of Two - Classroom Elementary School Building | 1 | 1436607.12 | 1050380 | 386227.12 | 1050380 | 3/3 | 386227 | 1436607 | 1050380 | 386227 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-23 | 2007-02-01 | no data | 131 | 261 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Amotag | 054101003 | Construction of Barangay Health Station | 1 | 735756.47 | 649516.47 | 86240 | 649516.47 | 1/3 | 86290 | 735806.47 | 649516.47 | 86290 | 100% | 100% | 100.1% | 100% | 100% | 2009-02-18 | no data | 2009-04-13 | 2009-06-15 | no data | 63 | 315 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Baga-uma | 054101004 | Construction of 2-Classroom School Bldg. | 1 | 968190 | 707580 | 260610 | 707580 | 3/3 | 272776 | 980356 | 707580 | 272776 | 100% | 100% | 104.7% | 101.3% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-26 | 2006-01-30 | no data | 126 | 424 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Baga-uma | 054101004 | Construction of Pathway | 1 | 577839.6 | 528754.6 | 49085 | 528754.6 | 1/3 | 55731 | 584485.6 | 528754.6 | 55731 | 100% | 100% | 113.5% | 101.2% | 100% | 2009-02-18 | no data | 2009-03-30 | 2009-04-25 | 2009-07-05 | 26 | 430 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Balawing | 054101005 | Construction of Day Care Center | 1 | 539534.25 | 393750 | 145784.25 | 393750 | 3/3 | 132589.19 | 526339.19 | 393750 | 132589.19 | 100% | 100% | 90.95% | 97.55% | 100% | 2003-11-20 | 2004-02-10 | 2005-08-15 | 2005-12-14 | 2005-12-14 | 121 | 125 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Balawing | 054101005 | Construction of 1-Classroom School Building | 1 | 729304.44 | 661249.44 | 68055 | 661249.44 | 1/3 | 45205 | 706454.44 | 661249.44 | 45205 | 100% | 100% | 66.42% | 96.87% | 100% | 2009-02-18 | no data | 2009-04-27 | 2009-06-20 | no data | 54 | 125 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Balete | 054101006 | Regravelling of Farm to Market Road | 1 | 1050304 | 734163 | 316141 | 734163 | 3/3 | 310646.37 | 1044809.37 | 734163 | 310646.37 | 100% | 100% | 98.26% | 99.48% | 100% | 2003-11-20 | 2004-02-10 | 2004-08-01 | 2005-01-20 | 2005-01-21 | 172 | 113 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Balete | 054101006 | Construction of Barangay Health Station | 1 | 705490.4 | 640990.4 | 64500 | 640990.4 | 1/3 | 51500 | 692490.4 | 640990.4 | 51500 | 100% | 100% | 79.84% | 98.16% | 100% | 2009-02-18 | no data | 2009-04-01 | 2009-05-31 | no data | 60 | 170 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Bangon | 054101007 | Construction of Day Care Center | 1 | 308842.7 | 198072.04 | 110770.66 | 198072.04 | 3/3 | 93964.65 | 292036.69 | 198072.04 | 93964.65 | 100% | 100% | 84.83% | 94.56% | 100% | 2003-11-20 | 2004-02-10 | 2004-10-01 | 2005-01-25 | 2005-01-26 | 116 | 299 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Cabangcalan | 054101008 | Construction of Water System Level 2 | 1 | 319977 | 223109 | 96868 | 223109 | 3/3 | 165802.4 | 388911.4 | 223109 | 165802.4 | 100% | 100% | 171.2% | 121.5% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-02 | 2004-12-03 | 2004-12-10 | 184 | 166 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Cabangcalan | 054101008 | Construction of Access Road | 1 | 502539 | 350000 | 152539 | 350000 | 3/3 | 171661 | 521661 | 350000 | 171661 | 100% | 100% | 112.5% | 103.8% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-12 | 2006-01-09 | 2006-01-19 | 89 | 168 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Cabangcalan | 054101008 | Construction of Manpower Enhancement Center | 1 | 726574.22 | 661488.22 | 65086 | 661488.22 | 1/3 | 72990 | 734478.22 | 661488.22 | 72990 | 100% | 100% | 112.1% | 101.1% | 100% | 2009-02-18 | no data | 2009-03-30 | 2009-06-21 | 2009-07-05 | 83 | 168 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Cabas-an | 054101009 | Regravelling of Farm to Market Road | 1 | 901012 | 630000 | 271012 | 630000 | 3/3 | 272011.91 | 902011.91 | 630000 | 272011.91 | 100% | 100% | 100.4% | 100.1% | 100% | 2003-11-20 | 2004-02-10 | 2004-04-20 | 2004-10-01 | 2004-10-20 | 164 | 241 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Cabas-an | 054101009 | Construction of Water System Level 2 | 1 | 493998.8 | 344147.56 | 149851.24 | 344147.56 | 3/3 | 158164.3 | 502311.86 | 344147.56 | 158164.3 | 100% | 100% | 105.5% | 101.7% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-01 | 2006-01-16 | 2006-01-17 | 107 | 215 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Cabas-an | 054101009 | Construction of Barangay Health Station | 1 | 782885.26 | 709085.26 | 73800 | 709085.26 | 1/3 | 101234.58 | 810319.84 | 709085.26 | 101234.58 | 100% | 100% | 137.2% | 103.5% | 100% | 2009-02-18 | no data | 2009-04-01 | 2009-05-31 | 2009-07-06 | 60 | 269 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Calanay | 054101010 | Construction of Water System Level 2 | 1 | 1014843.9 | 708297 | 306546.9 | 708297 | 3/3 | 243772.99 | 952069.99 | 708297 | 243772.99 | 100% | 100% | 79.52% | 93.81% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-25 | 2004-09-30 | 2004-10-20 | 128 | 280 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Calanay | 054101010 | Construction of Two - Classroom Elementary School Building | 1 | 1435994.8 | 1134500 | 301494.8 | 1134500 | 3/3 | 300774.8 | 1435274.8 | 1134500 | 300774.8 | 100% | 100% | 99.76% | 99.95% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-23 | 2007-02-01 | no data | 131 | 151 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Calanay | 054101010 | Construction of Barangay Health Station | 1 | 721014.15 | 593514.15 | 127500 | 593514.15 | 1/3 | 129670 | 723184.15 | 593514.15 | 129670 | 100% | 100% | 101.7% | 100.3% | 100% | 2009-02-18 | no data | 2009-03-28 | 2009-07-06 | no data | 100 | 360 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Capsay | 054101011 | Regravelling of Farm to Market Road | 1 | 1135985 | 794315 | 341670 | 794315 | 3/3 | 321091.3 | 1115406.3 | 794315 | 321091.3 | 100% | 100% | 93.98% | 98.19% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-01 | 2005-06-06 | 2005-06-15 | 370 | 236 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Capsay | 054101011 | Road Concreting | 1 | 552478.48 | 488491.2 | 63987.28 | 487494.4 | 1/3 | 63986.97 | 551481.37 | 487494.4 | 63986.97 | 100% | 100% | 100% | 99.82% | 100% | 2009-02-18 | no data | 2009-04-16 | 2009-05-19 | no data | 33 | 265 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Concepcion | 054101012 | Construction of Duplex Bldg. (DCC & BHS) | 1 | 554160 | 388080 | 166080 | 388080 | 3/3 | 203838.26 | 591918.26 | 388080 | 203838.26 | 100% | 100% | 122.7% | 106.8% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-10-18 | 2004-10-20 | 147 | 137 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Concepcion | 054101012 | Construction of Water System Level 2 | 1 | 1000000 | 700000 | 300000 | 700000 | 3/3 | 358087 | 1058087 | 700000 | 358087 | 100% | 100% | 119.4% | 105.8% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-21 | 2006-01-16 | 2006-01-19 | 117 | 110 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Concepcion | 054101012 | Road Concreting | 1 | 542911.85 | 491611.85 | 51300 | 491611.85 | 1/3 | 57000 | 548611.85 | 491611.85 | 57000 | 100% | 100% | 111.1% | 101% | 100% | 2009-02-18 | no data | 2009-03-23 | 2009-07-20 | no data | 119 | 142 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Dayhagan | 054101013 | Construction of Crab Processing Center | 1 | 730427.5 | 665821.25 | 64606.25 | 665821.25 | 1/3 | 97858.03 | 763679.28 | 665821.25 | 97858.03 | 100% | 100% | 151.5% | 104.6% | 100% | 2009-02-18 | no data | 2009-04-06 | 2009-06-25 | 2009-07-09 | 80 | 220 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Don Pablo dela Rosa | 054101014 | Rehab of Access Road | 1 | 312835.8 | 200819 | 112016.8 | 200819 | 3/3 | 100566.55 | 301385.55 | 200819 | 100566.55 | 100% | 100% | 89.78% | 96.34% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-09 | 2004-09-25 | 2004-10-20 | 108 | 216 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Don Pablo dela Rosa | 054101014 | Rehab./Improvement of Water System Level 2 | 1 | 1137523 | 762811 | 374712 | 762811 | 3/3 | 348260 | 1111071 | 762811 | 348260 | 100% | 100% | 92.94% | 97.67% | 100% | 2005-06-16 | 2005-07-19 | 2005-08-24 | 2005-11-15 | no data | 83 | 216 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Gumahang | 054101015 | Rehab./Improvement of Water System Level 2 | 1 | 435925.03 | 280599.56 | 155325.47 | 280599.56 | 3/3 | 147432.815 | 428032.375 | 280599.56 | 147432.815 | 100% | 100% | 94.92% | 98.19% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-28 | 2005-02-09 | 2005-02-11 | 226 | 195 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Gumahang | 054101015 | Construction of Water System Level 2 | 1 | 1359690.35 | 1223030.35 | 136660 | 1220736.15 | 1/3 | 169687 | 1390423.15 | 1220736.15 | 169687 | 100% | 100% | 124.2% | 102.3% | 100% | 2009-02-18 | no data | 2009-03-21 | 2009-07-19 | 2009-07-20 | 120 | 346 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Jaboyo-an | 054101016 | Construction of Day Care Center | 1 | 309842.7 | 198072.04 | 111770.66 | 198072.04 | 3/3 | 91777.85 | 289849.89 | 198072.04 | 91777.85 | 100% | 100% | 82.11% | 93.55% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-08 | 2004-12-08 | 2004-12-09 | 183 | 277 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Jaboyo-an | 054101016 | Rehab./Improvement of Access Road | 1 | 558725 | 450000 | 108725 | 450000 | 3/3 | 121932 | 571932 | 450000 | 121932 | 100% | 100% | 112.1% | 102.4% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-10 | 2006-01-22 | no data | 104 | 289 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Lanang | 054101017 | Consttruction of Irrigation Canal | 1 | 972604 | 682500 | 290104 | 682500 | 3/3 | 385934.15 | 1068434.15 | 682500 | 385934.15 | 100% | 100% | 133% | 109.9% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-23 | 2005-06-10 | 2005-06-15 | 383 | 110 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Lanang | 054101017 | Construction of Water System Level 2 | 1 | 683825.3 | 617518.3 | 66307 | 555766.22 | 1/3 | 66357 | 622123.22 | 555766.22 | 66357 | 100% | 100% | 100.1% | 90.98% | 100% | 2009-02-18 | no data | 2009-03-31 | 2009-06-30 | no data | 91 | 117 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Luy-a | 054101018 | Construction of Water System Level 2 | 1 | 815152.35 | 569165 | 245987.35 | 569165 | 3/3 | 306837.34 | 876002.34 | 569165 | 306837.34 | 100% | 100% | 124.7% | 107.5% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-10-16 | 2004-10-20 | 145 | 354 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Luy-a | 054101018 | Construction of Brgy. Public Market | 1 | 959998.8 | 668809.48 | 291189.32 | 668809.48 | 3/3 | 291189.32 | 959998.8 | 668809.48 | 291189.32 | 100% | 100% | 100% | 100% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-23 | 2006-01-17 | 2006-01-18 | 116 | 364 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Luy-a | 054101018 | Barangay Electrification | 1 | 1448150 | 1080800 | 367350 | 1080800 | 3/3 | 357850 | 1438650 | 1080800 | 357850 | 100% | 100% | 97.41% | 99.34% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-23 | 2009-02-25 | no data | 886 | 364 | completed as built | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Macabug | 054101019 | Construction of Water System Level 2 | 1 | 524948.75 | 487288.75 | 37660 | 487288.75 | 1/3 | 29340 | 516628.75 | 487288.75 | 29340 | 100% | 100% | 77.91% | 98.42% | 100% | 2009-02-18 | no data | 2009-03-28 | 2009-06-16 | no data | 80 | 150 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Malubi | 054101020 | Construction of Day Care Center | 1 | 304179 | 212925 | 91254 | 212925 | 3/3 | 80229.9 | 293154.9 | 212925 | 80229.9 | 100% | 100% | 87.92% | 96.38% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-07 | 2004-11-21 | 2004-12-10 | 167 | 272 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Malubi | 054101020 | Construction of Water System Level 2 | 1 | 650003.7 | 455003.7 | 195000 | 455003.7 | 3/3 | 226932.2 | 681935.9 | 455003.7 | 226932.2 | 100% | 100% | 116.4% | 104.9% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-18 | 2006-01-19 | 2006-01-19 | 93 | 271 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Malubi | 054101020 | Construction of Barangay Health Station | 1 | 673553.27 | 622671.27 | 50882 | 622671.27 | 1/3 | 56256 | 678927.27 | 622671.27 | 56256 | 100% | 100% | 110.6% | 100.8% | 100% | 2009-02-18 | no data | 2009-03-28 | 2009-06-22 | 2009-07-18 | 86 | 271 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Managa-naga | 054101021 | Construction of Water System Level 2 | 1 | 385887.7 | 269946 | 115941.7 | 269946 | 3/3 | 136436.65 | 406382.65 | 269946 | 136436.65 | 100% | 100% | 117.7% | 105.3% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-10-14 | 2004-10-20 | 143 | 184 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Managa-naga | 054101021 | Construction of Day Care Center | 1 | 485027.44 | 339500.83 | 145526.61 | 339500.83 | 3/3 | 163668 | 503168.83 | 339500.83 | 163668 | 100% | 100% | 112.5% | 103.7% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-06 | 2005-12-22 | 2006-01-19 | 77 | 17 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Managa-naga | 054101021 | Construction of Barangay Health Station | 1 | 716204.8 | 642954.8 | 73250 | 642954.8 | 1/3 | 47900 | 690854.8 | 642954.8 | 47900 | 100% | 100% | 65.39% | 96.46% | 100% | 2009-02-18 | no data | 2009-04-20 | 2009-06-20 | 2009-06-28 | 61 | 195 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Manamoc | 054101022 | Improvement of Farm to Market Road | 1 | 1545177.55 | 906184.05 | 638993.5 | 906184.05 | 3/3 | 1239815.95 | 2146000 | 906184.05 | 1239815.95 | 100% | 100% | 194% | 138.9% | 100% | 2005-06-16 | 2005-07-19 | 2005-12-08 | 2006-06-15 | no data | 189 | 120 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Manamoc | 054101022 | Construction of Farm to Market Road | 1 | 527481.38 | 466781.38 | 60700 | 466781.38 | 1/3 | 60700 | 527481.38 | 466781.38 | 60700 | 100% | 100% | 100% | 100% | 100% | 2009-02-18 | no data | 2009-04-13 | 2009-06-25 | 2009-07-16 | 73 | 140 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Mariposa | 054101023 | Rehab of Access Road | 1 | 651291.6 | 420189 | 231102.6 | 420189 | 3/3 | 208172.83 | 628361.83 | 420189 | 208172.83 | 100% | 100% | 90.08% | 96.48% | 100% | 2003-11-20 | 2004-02-10 | 2004-09-27 | 2005-03-15 | 2005-03-31 | 169 | 162 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Mariposa | 054101023 | Construction of Water System Level 2 | 1 | 727135 | 515000 | 212135 | 515000 | 3/3 | 194426.5 | 709426.5 | 515000 | 194426.5 | 100% | 100% | 91.65% | 97.56% | 100% | 2005-06-16 | 2005-07-19 | 2005-08-29 | 2006-02-15 | no data | 170 | 182 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Mariposa | 054101023 | Const. of Duplex Type Building (DCC & BHS) | 1 | 935500 | 754200 | 181300 | 754200 | 2/3 | 276315 | 1030515 | 754200 | 276315 | 100% | 100% | 152.4% | 110.2% | 100% | 2006-06-13 | 2006-06-14 | 2006-10-23 | 2007-06-01 | no data | 221 | 182 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Mariposa | 054101023 | Construction of 1-Classroom School Building | 1 | 704143.42 | 636070.42 | 68073 | 636070.42 | 1/3 | 68073 | 704143.42 | 636070.42 | 68073 | 100% | 100% | 100% | 100% | 100% | 2009-02-18 | no data | 2009-03-25 | 2009-07-11 | no data | 108 | 280 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Mataba | 054101024 | Construction of 2-units Footbridge | 1 | 708833 | 525407 | 183426 | 525407 | 3/3 | 173108 | 698515 | 525407 | 173108 | 100% | 100% | 94.37% | 98.54% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-03 | 2006-01-23 | no data | 112 | 307 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Matalang-talang | 054101025 | Rehab./Improvement of Water System Level 2 | 1 | 491120.04 | 316374.1 | 174745.94 | 316374.1 | 3/3 | 160533.04 | 476907.14 | 316374.1 | 160533.04 | 100% | 100% | 91.87% | 97.11% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-10-16 | 2004-10-20 | 145 | 228 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Matalang-talang | 054101025 | Rehab./Improvement of Brgy. Port | 1 | 764000 | 607100 | 156900 | 607100 | 3/3 | 206750 | 813850 | 607100 | 206750 | 100% | 100% | 131.8% | 106.5% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-11 | 2007-02-01 | no data | 143 | 321 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Matalang-talang | 054101025 | Construction of 1-Classroom School Building | 1 | 674873.95 | 624658.95 | 50215 | 624658.95 | 1/3 | 52555 | 677213.95 | 624658.95 | 52555 | 100% | 100% | 104.7% | 100.3% | 100% | 2009-02-18 | no data | 2009-04-07 | 2009-07-20 | no data | 104 | 312 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Matongog | 054101026 | Construction of Water System Level 2 | 1 | 1247655.56 | 805424.9 | 442230.66 | 805424.9 | 3/3 | 351290.04 | 1156714.94 | 805424.9 | 351290.04 | 100% | 100% | 79.44% | 92.71% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-10-16 | 2004-10-20 | 145 | 287 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Matongog | 054101026 | Construction of 2-Classroom School Bldg. | 1 | 901667 | 732151 | 169516 | 732151 | 3/3 | 186061.5 | 918212.5 | 732151 | 186061.5 | 100% | 100% | 109.8% | 101.8% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-13 | 2006-02-21 | no data | 161 | 142 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Matongog | 054101026 | Construction of Pathway | 1 | 412161.4 | 377521.4 | 34640 | 377521.4 | 1/3 | 47540 | 425061.4 | 377521.4 | 47540 | 100% | 100% | 137.2% | 103.1% | 100% | 2009-02-18 | no data | 2009-03-22 | 2009-06-16 | no data | 86 | 239 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Nabongsoran | 054101027 | Construction of Water System Level II | 1 | 1011958 | 817800 | 194158 | 817800 | 3/3 | 225691.5 | 1043491.5 | 817800 | 225691.5 | 100% | 100% | 116.2% | 103.1% | 100% | 2006-06-13 | 2006-06-14 | 2006-08-21 | 2006-11-28 | no data | 99 | 154 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Nabongsoran | 054101027 | Construction of Barangay Health Station | 1 | 728632.3 | 646612.3 | 82020 | 646612.3 | 1/3 | 82980 | 729592.3 | 646612.3 | 82980 | 100% | 100% | 101.2% | 100.1% | 100% | 2009-02-18 | no data | 2009-03-27 | 2009-06-15 | 2009-07-15 | 80 | 168 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Pangle | 054101028 | Construction of Water System Level 2 | 1 | 472509.29 | 328673.06 | 143836.23 | 328673.06 | 3/3 | 202506.1 | 531179.16 | 328673.06 | 202506.1 | 100% | 100% | 140.8% | 112.4% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-26 | 2006-01-23 | 2006-01-24 | 119 | 97 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Panique | 054101029 | Construction of Brgy. Health Station | 1 | 539534.25 | 393750 | 145784.25 | 393750 | 3/3 | 150053.19 | 543803.19 | 393750 | 150053.19 | 100% | 100% | 102.9% | 100.8% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-30 | 2005-12-13 | 2005-12-18 | 531 | 689 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Pinanaan | 054101030 | Provision of Electrification Facilities | 1 | 344040 | 271050 | 72990 | 271050 | 3/3 | 67822 | 338872 | 271050 | 67822 | 100% | 100% | 92.92% | 98.5% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-02 | 2006-12-05 | no data | 459 | 610 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Pinanaan | 054101030 | Const. of Duplex Type Building (DCC & BHS) | 1 | 886600 | 818800 | 67800 | 818800 | 3/3 | 119830 | 938630 | 818800 | 119830 | 100% | 100% | 176.7% | 105.9% | 100% | 2006-06-13 | 2006-06-14 | 2006-08-21 | 2006-11-29 | no data | 100 | 167 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Pinanaan | 054101030 | Road Concreting | 1 | 540823.6 | 492084.85 | 48738.75 | 468547.92 | 1/3 | 49413.75 | 517961.67 | 468547.92 | 49413.75 | 100% | 100% | 101.4% | 95.77% | 100% | 2009-02-18 | no data | 2009-04-01 | 2009-04-17 | 2009-07-17 | 16 | 245 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Pinanaan - C2 | 054101030 | Rehab. of Farm to Market Road | 2 | 2683264.3 | 1726190 | 957074.3 | 1726190 | 3/3 | 707298.7045 | 2433488.7045 | 1726190 | 707298.7045 | 100% | 100% | 73.9% | 90.69% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-12-12 | 2004-12-09 | 202 | 542 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Poblacion | 054101031 | Construction of Duplex Bldg. (DCC & BHS) | 1 | 757045 | 558515 | 198530 | 558515 | 3/3 | 224235 | 782750 | 558515 | 224235 | 100% | 100% | 112.9% | 103.4% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-12 | 2005-12-18 | no data | 97 | 610 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Poblacion | 054101031 | Construction of Footbridge | 1 | 1013723.49 | 890276.74 | 123446.75 | 890276.74 | 1/3 | 123446.75 | 1013723.49 | 890276.74 | 123446.75 | 100% | 100% | 100% | 100% | 100% | 2009-02-18 | no data | 2009-04-14 | 2009-06-15 | 2009-07-27 | 62 | 367 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Puro | 054101032 | Construction of Water System Level 2 | 1 | 1049847.76 | 673975.4 | 375872.36 | 673975.4 | 3/3 | 375658.55 | 1049633.95 | 673975.4 | 375658.55 | 100% | 100% | 99.94% | 99.98% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-08-30 | 2004-10-20 | 98 | 1561 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Puro | 054101032 | Construction of Duplex Bldg. (DCC & BHS) | 1 | 759521 | 570651 | 188870 | 570651 | 3/3 | 179522.5 | 750173.5 | 570651 | 179522.5 | 100% | 100% | 95.05% | 98.77% | 100% | 2005-06-16 | 2005-07-19 | 2005-09-23 | 2005-11-30 | no data | 68 | 926 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Puro | 054101032 | Construction of Training Center | 1 | 702581.63 | 649542.63 | 53039 | 649542.63 | 1/3 | 27500 | 677042.63 | 649542.63 | 27500 | 100% | 100% | 51.85% | 96.36% | 100% | 2009-02-18 | no data | 2009-04-01 | 2009-06-30 | 2009-07-15 | 90 | 876 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | San Agustin | 054101033 | Construction of Day Care Center | 1 | 327842.7 | 198072.04 | 129770.66 | 198072.04 | 3/3 | 91913.2 | 289985.24 | 198072.04 | 91913.2 | 100% | 100% | 70.83% | 88.45% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-15 | 2005-02-09 | 2005-02-11 | 239 | 108 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | San Agustin | 054101033 | Construction of Water System Level 2 | 1 | 553054.5 | 521939.5 | 31115 | 521654 | 1/3 | 49280 | 570934 | 521654 | 49280 | 100% | 100% | 158.4% | 103.2% | 100% | 2009-02-18 | no data | 2009-04-26 | 2009-06-11 | no data | 46 | 354 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | San Isidro | 054101034 | Construction of Water System Level 3 | 1 | 551501.44 | 384260.77 | 167240.67 | 384260.77 | 3/3 | 177879.1 | 562139.87 | 384260.77 | 177879.1 | 100% | 100% | 106.4% | 101.9% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-17 | 2006-01-17 | 2006-01-18 | 92 | 68 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | San Isidro | 054101034 | Construction of Pathway | 1 | 1219470 | 886061 | 333409 | 886061 | 3/3 | 350804 | 1236865 | 886061 | 350804 | 100% | 100% | 105.2% | 101.4% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-21 | 2006-11-30 | no data | 70 | 189 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | San Isidro | 054101034 | Construction of Pathway with Footbridge | 1 | 479152.28 | 424972.28 | 54180 | 424972.28 | 1/3 | 55230 | 480202.28 | 424972.28 | 55230 | 100% | 100% | 101.9% | 100.2% | 100% | 2009-02-18 | no data | 2009-04-02 | 2009-05-31 | no data | 59 | 198 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Sawang | 054101035 | Construction of Day Care Center | 1 | 328842.7 | 198072.04 | 130770.66 | 198072.04 | 3/3 | 101890.2 | 299962.24 | 198072.04 | 101890.2 | 100% | 100% | 77.92% | 91.22% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-28 | 2005-03-30 | 2005-03-31 | 275 | 238 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Sawang | 054101035 | Const.of One(1) unit-Two(2) Classroom School Building | 1 | 1178300 | 919700 | 258600 | 919700 | 3/3 | 301140 | 1220840 | 919700 | 301140 | 100% | 100% | 116.5% | 103.6% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-06 | 2007-02-01 | no data | 148 | 238 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Sawang | 054101035 | Construction of Water System Level 2 | 1 | 671028.5 | 631928.5 | 39100 | 631928.5 | 1/3 | 23710 | 655638.5 | 631928.5 | 23710 | 100% | 100% | 60.64% | 97.71% | 100% | 2009-02-18 | no data | 2009-03-21 | 2009-06-16 | no data | 87 | 281 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Syndicate | 054101036 | Construction of Daycare Center | 1 | 653122.59 | 593522.59 | 59600 | 593522.59 | 1/3 | 26830 | 620352.59 | 593522.59 | 26830 | 100% | 100% | 45.02% | 94.98% | 100% | 2009-02-18 | no data | 2009-03-23 | 2009-05-31 | 2009-07-23 | 69 | 325 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Syndicate - C2 | 054101036 | Rehab. of Farm to Market Road | 2 | 2683264.3 | 1726190 | 957074.3 | 1726190 | 3/3 | 707298.7045 | 2433488.7045 | 1726190 | 707298.7045 | 100% | 100% | 73.9% | 90.69% | 100% | 2003-11-20 | 2004-02-10 | 2004-05-24 | 2004-12-12 | 2004-12-09 | 202 | 542 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Talabaan | 054101037 | Construction of Pathway | 1 | 515581.65 | 473721.65 | 41860 | 473554.53 | 1/3 | 45425 | 518979.53 | 473554.53 | 45425 | 100% | 100% | 108.5% | 100.7% | 100% | 2009-02-18 | no data | 2009-03-13 | 2009-06-30 | no data | 109 | 129 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Talib | 054101038 | Construction of Water System Level 2 | 1 | 739066.61 | 469240.39 | 269826.22 | 469240.39 | 3/3 | 266508.57 | 735748.96 | 469240.39 | 266508.57 | 100% | 100% | 98.77% | 99.55% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-28 | 2004-10-08 | 2004-10-09 | 102 | 274 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Talib | 054101038 | Const.of 1 unit-Two(2) Classroom School Building | 1 | 1142700 | 935300 | 207400 | 935300 | 3/3 | 290000 | 1225300 | 935300 | 290000 | 100% | 100% | 139.8% | 107.2% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-05 | 2006-12-14 | no data | 100 | 192 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Talib | 054101038 | Construction of Livelihood and Productivity Center | 1 | 704421.3 | 614571.3 | 89850 | 614571.3 | 1/3 | 108580 | 723151.3 | 614571.3 | 108580 | 100% | 100% | 120.8% | 102.7% | 100% | 2009-02-18 | no data | 2009-04-01 | 2009-06-23 | 2009-07-02 | 83 | 274 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tigbao | 054101039 | Construction of Water System Level 2 | 1 | 505028.12 | 324092.3 | 180935.82 | 324092.3 | 3/3 | 166265.82 | 490358.12 | 324092.3 | 166265.82 | 100% | 100% | 91.89% | 97.1% | 100% | 2003-11-20 | 2004-02-10 | 2004-06-09 | 2004-10-15 | 2004-10-20 | 128 | 355 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tigbao | 054101039 | Const. of Duplex Type Building (DCC & BHS) | 1 | 968200 | 777200 | 191000 | 757200 | 3/3 | 224678 | 981878 | 757200 | 224678 | 100% | 100% | 117.6% | 101.4% | 100% | 2006-06-13 | 2006-06-14 | 2006-10-16 | 2007-02-01 | no data | 108 | 392 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tigbao | 054101039 | Construction of 1-Classroom School Building | 1 | 717125.1 | 614917.1 | 102208 | 613927.31 | 1/3 | 125358 | 739285.31 | 613927.31 | 125358 | 100% | 100% | 122.6% | 103.1% | 100% | 2009-02-18 | no data | 2009-04-14 | 2009-06-15 | no data | 62 | 445 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tinago | 054101040 | Rehab./Improvement of Water System Level 2 | 1 | 859016 | 641626 | 217390 | 641626 | 3/3 | 217240 | 858866 | 641626 | 217240 | 100% | 100% | 99.93% | 99.98% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-03 | 2006-01-24 | no data | 113 | 172 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tinago | 054101040 | Const. of Duplex Type Building (DCC & BHS) | 1 | 967500 | 781800 | 185700 | 781800 | 3/3 | 195325 | 977125 | 781800 | 195325 | 100% | 100% | 105.2% | 101% | 100% | 2006-06-13 | 2006-06-14 | 2006-08-16 | 2006-12-06 | no data | 112 | 172 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tinago | 054101040 | Construction of Training Center | 1 | 702581.42 | 641158.03 | 61423.39 | 641158.03 | 1/3 | 61451.3 | 702609.33 | 641158.03 | 61451.3 | 100% | 100% | 100% | 100% | 100% | 2009-02-18 | no data | 2009-04-01 | 2009-07-15 | 2009-07-05 | 105 | 443 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tinigban | 054101041 | Construction of Water System Level 2 | 1 | 1250014.36 | 874664.36 | 375350 | 874664.36 | 3/3 | 392761.67 | 1267426.03 | 874664.36 | 392761.67 | 100% | 100% | 104.6% | 101.4% | 100% | 2005-06-16 | 2005-07-19 | 2005-10-02 | 2006-01-31 | no data | 121 | 421 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tinigban | 054101041 | Conc./Improvement of FMR (with exception) | 1 | 1401190.4 | 1030459 | 370731.4 | 1030459 | 3/3 | 370704 | 1401163 | 1030459 | 370704 | 100% | 100% | 99.99% | 100% | 100% | 2006-06-13 | 2006-06-14 | 2006-09-21 | 2007-02-01 | no data | 133 | 418 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Aroroy | 054101 | Tinigban | 054101041 | Construction of Livelihood and Productivity Center | 1 | 727501.3 | 611482.8 | 116018.5 | 611482.8 | 1/3 | 50175 | 661657.8 | 611482.8 | 50175 | 100% | 100% | 43.25% | 90.95% | 100% | 2009-02-18 | no data | 2009-04-07 | 2009-06-16 | 2009-07-06 | 70 | 421 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Burgos | 054104001 | Construction of Water System Level 2 | 1 | 1428946.6 | 1000000 | 428946.6 | 900000 | 0.66667 | 239989.5 | 1139989.5 | 900000 | 239989.5 | 100% | 100% | 55.95% | 79.78% | 100% | 2003-05-21 | 2003-06-18 | 2003-09-12 | 2004-06-01 | 2004-07-06 | 263 | 291 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Burgos | 054104001 | Upgrading/Improvement of Drainage System | 1 | 1038680 | 675600 | 363080 | 675600 | 3/3 | 356725 | 1032325 | 675600 | 356725 | 100% | 100% | 98.25% | 99.39% | 100% | no data | 2005-12-10 | 2006-03-13 | 2006-10-31 | 2006-11-05 | 232 | 291 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Cañares | 054104002 | Rehab./Improvement of Farm to Market Road | 1 | 1282245 | 840000 | 442245 | 840000 | 3/3 | 564254 | 1404254 | 840000 | 564254 | 100% | 100% | 127.6% | 109.5% | 100% | 2003-05-21 | 2003-06-18 | 2003-08-27 | 2004-07-03 | 2004-07-06 | 311 | 231 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Cañares | 054104002 | Construction of Duplex Bldg. (DCC & BHS) | 1 | 768067 | 542327 | 225740 | 542327 | 3/3 | 250690 | 793017 | 542327 | 250690 | 100% | 100% | 111.1% | 103.2% | 100% | no data | 2005-12-10 | 2006-03-14 | 2006-07-31 | 2006-09-20 | 139 | 231 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Canvañez | 054104003 | Rehab./Improvement of Farm to Market Road | 1 | 243850 | 163500 | 80350 | 163500 | 3/3 | 47750 | 211250 | 163500 | 47750 | 100% | 100% | 59.43% | 86.63% | 100% | 2003-05-21 | 2003-06-18 | 2003-08-28 | 2004-05-01 | 2004-07-06 | 247 | 65 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Costa Rica | 054104004 | Construction of Water System Level 2 | 1 | 735818 | 424468 | 311350 | 424468 | 3/3 | 348975 | 773443 | 424468 | 348975 | 100% | 100% | 112.1% | 105.1% | 100% | no data | 2005-12-10 | 2006-04-11 | 2006-10-31 | 2006-09-20 | 203 | 161 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Danao | 054104005 | Construction of Water System Level 2 | 1 | 687045 | 484695 | 202350 | 484695 | 3/3 | 275457 | 760152 | 484695 | 275457 | 100% | 100% | 136.1% | 110.6% | 100% | no data | 2005-02-18 | 2005-04-05 | 2005-08-25 | 2005-09-30 | 142 | 127 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Gibraltar | 054104006 | Construction of Water System Level 2 | 1 | 828295 | 603065 | 225230 | 603065 | 3/3 | 255587.4 | 858652.4 | 603065 | 255587.4 | 100% | 100% | 113.5% | 103.7% | 100% | no data | 2005-02-18 | 2005-04-05 | 2005-08-25 | 2005-09-20 | 142 | 270 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Mabuhay | 054104007 | Upgrading/Improvement of FMR w/ exemption | 1 | 2420786 | 2127766 | 293020 | 2127766 | 3/3 | 282886.9 | 2410652.9 | 2127766 | 282886.9 | 100% | 100% | 96.54% | 99.58% | 100% | no data | 2005-12-10 | 2006-04-11 | 2006-12-31 | 2006-09-20 | 264 | 55 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Matabao | 054104008 | Construction of Water System Level 2 | 1 | 977939 | 768519 | 209420 | 768519 | 3/3 | 286123 | 1054642 | 768519 | 286123 | 100% | 100% | 136.6% | 107.8% | 100% | no data | 2005-02-18 | 2005-04-05 | 2005-08-25 | 2005-09-21 | 142 | 78 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Panisihan | 054104010 | Construction of Water System Level 2 | 1 | 1229592 | 758712 | 470880 | 758712 | 3/3 | 354275.2 | 1112987.2 | 758712 | 354275.2 | 100% | 100% | 75.24% | 90.52% | 100% | no data | 2005-02-18 | 2005-04-05 | 2005-08-25 | 2005-09-29 | 142 | 197 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Poblacion | 054104011 | Upgrading/Improvement of Drainage System | 1 | 1870349 | 1585009 | 285340 | 1585009 | 3/3 | 309670 | 1894679 | 1585009 | 309670 | 100% | 100% | 108.5% | 101.3% | 100% | no data | 2005-02-18 | 2005-04-05 | 2005-08-25 | 2005-09-15 | 142 | 505 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Rizal | 054104013 | Rehab./Improvement of Farm to Market Road | 1 | 1786637.35 | 1050000 | 736637.35 | 1050000 | 3/3 | 863410 | 1913410 | 1050000 | 863410 | 100% | 100% | 117.2% | 107.1% | 100% | 2003-05-21 | 2003-06-18 | 2003-09-12 | 2004-05-01 | 2004-07-06 | 232 | 168 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Royroy | 054104014 | Construction of Water System Level 2 | 1 | 1180937.2 | 800000 | 380937.2 | 800000 | 3/3 | 323871.08 | 1123871.08 | 800000 | 323871.08 | 100% | 100% | 85.02% | 95.17% | 100% | 2003-05-21 | 2003-06-18 | 2003-09-29 | 2004-06-01 | 2004-07-06 | 246 | 180 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Royroy | 054104014 | Construction of Multi-Purpose bldg. | 1 | 643049 | 429839 | 213210 | 429839 | 3/3 | 211123 | 640962 | 429839 | 211123 | 100% | 100% | 99.02% | 99.68% | 100% | no data | 2005-12-10 | 2006-03-13 | 2006-10-31 | 2006-09-20 | 232 | 180 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Batuan | 054104 | Sawang | 054104015 | Construction of 1-Classroom School Bldg. | 1 | 497225.55 | 346500 | 150725.55 | 346500 | 3/3 | 153370.8 | 499870.8 | 346500 | 153370.8 | 100% | 100% | 101.8% | 100.5% | 100% | 2003-05-21 | 2003-06-18 | 2003-09-13 | 2004-06-01 | 2004-07-07 | 262 | 103 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Albasan | 054107001 | Rehab./Concreting of Brgy. Road | 1 | 2853354 | 1876000 | 977354 | 1876000 | 3/3 | 998528.5 | 2874528.5 | 1876000 | 998528.5 | 100% | 100% | 102.2% | 100.7% | 100% | 2003-11-27 | 2004-02-27 | 2004-06-28 | 2005-04-29 | 2005-04-29 | 305 | 214 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Boca-Engaño | 054107002 | Construction of Water System Level 2 | 1 | 314000 | 201000 | 113000 | 201000 | 3/3 | 95480 | 296480 | 201000 | 95480 | 100% | 100% | 84.5% | 94.42% | 100% | 2003-11-27 | 2004-02-27 | 2004-06-22 | 2005-04-13 | 2005-04-13 | 295 | 238 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Boca-Engaño | 054107002 | Improvement of Barangay Road | 1 | 2654367 | 1959000 | 695367 | 1762400 | 2/3 | 592800 | 2302850.67 | 1710050.67 | 592800 | 97.03% | 100% | 85.25% | 86.76% | 100% | 2008-12-15 | no data | 2009-05-10 | 2009-11-30 | no data | 204 | 320 | completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Buyo | 054107003 | Road Construction | 1 | 2774937.24 | 2066942 | 707995.24 | 2066942 | 3/3 | 707995.24 | 2774937.24 | 2066942 | 707995.24 | 100% | 100% | 100% | 100% | 100% | 2006-06-27 | 2006-07-11 | 2006-10-24 | 2008-03-30 | no data | 523 | 432 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Calpi | 054107004 | Construction of Water System Level 2 | 1 | 1832360 | 1173000 | 659360 | 1173000 | 3/3 | 639822.5 | 1812822.5 | 1173000 | 639822.5 | 100% | 100% | 97.04% | 98.93% | 100% | 2003-11-27 | 2004-02-27 | 2004-06-07 | 2005-04-13 | 2005-04-13 | 310 | 239 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Canomay | 054107005 | Rehab./Concreting of Brgy. Road | 1 | 1015702 | 670000 | 345702 | 670000 | 3/3 | 255587.4 | 925587.4 | 670000 | 255587.4 | 100% | 100% | 73.93% | 91.13% | 100% | 2003-11-27 | 2004-02-27 | 2004-04-26 | 2005-03-13 | 2005-04-13 | 321 | 202 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Cawayan | 054107006 | Construction of Water System Level 2 | 1 | 1350000 | 945000 | 405000 | 945000 | 3/3 | 438100 | 1383100 | 945000 | 438100 | 100% | 100% | 108.2% | 102.5% | 100% | 2005-07-07 | 2005-08-05 | 2005-10-24 | 2006-05-30 | 2006-06-02 | 218 | 352 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Imelda | 054107022 | Road Gravelling | 1 | 1001249.97 | 782298 | 218951.97 | 704068.2 | 2/3 | 225234.35 | 929302.55 | 704068.2 | 225234.35 | 100% | 100% | 102.9% | 92.81% | 100% | 2006-06-27 | 2006-07-11 | 2007-02-07 | 2008-06-30 | no data | 509 | 360 | On-going | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Mababang Baybay | 054107009 | Road Construction | 1 | 2453243.37 | 1856408 | 596835.37 | 1856408 | 3/3 | 598835.35 | 2455243.35 | 1856408 | 598835.35 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-06-27 | 2006-07-11 | 2006-11-20 | 2008-03-30 | no data | 496 | 282 | On-going | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Mabiton | 054107010 | Rehab./Improvement of Farm to Market Road | 1 | 1401026 | 971300 | 429726 | 971300 | 3/3 | 401750 | 1373050 | 971300 | 401750 | 100% | 100% | 93.49% | 98% | 100% | 2005-07-07 | 2005-08-05 | 2005-11-21 | 2006-05-25 | 2006-05-26 | 185 | 420 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Mabiton | 054107010 | Rehabilitation of Barangay Road | 1 | 2906567 | 2153000 | 753567 | 1937700 | 2/3 | 632800 | 2528224.93 | 1895424.93 | 632800 | 97.82% | 100% | 83.97% | 86.98% | 100% | 2008-12-15 | no data | 2009-05-01 | 2009-08-25 | no data | 116 | 419 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Manapao | 054107011 | Improvement of Barangay Road | 1 | 2512667 | 1850000 | 662667 | 1480000 | 1/3 | 555000 | 1575725 | 1020725 | 555000 | 68.97% | 100% | 83.75% | 62.71% | 100% | 2008-12-15 | no data | 2009-05-20 | 2009-11-30 | no data | 194 | 179 | completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Nabasagan | 054107012 | Improvement of Barangay Road | 1 | 2707667 | 2000000 | 707667 | 1800000 | 2/3 | 615460 | 2333968.67 | 1718508.67 | 615460 | 95.47% | 100% | 86.97% | 86.2% | 100% | 2008-12-15 | no data | 2009-05-10 | 2009-10-30 | no data | 173 | 290 | completed as built | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Nonoc | 054107013 | Rehab./Improvement of Farm to Market Road | 1 | 1800000 | 1260000 | 540000 | 1260000 | 3/3 | 479376.24 | 1739376.24 | 1260000 | 479376.24 | 100% | 100% | 88.77% | 96.63% | 100% | 2005-07-07 | 2005-08-05 | 2005-10-24 | 2006-10-30 | 2006-11-29 | 371 | 370 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Osmeña | 054107014 | Upgarading of Water System | 1 | 711000 | 497700 | 213300 | 497700 | 3/3 | 188245.5 | 685945.5 | 497700 | 188245.5 | 100% | 100% | 88.25% | 96.48% | 100% | 2005-07-07 | 2005-08-05 | 2005-11-17 | 2006-04-30 | 2006-05-25 | 164 | 300 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Osmeña | 054107014 | Construction of 2-Classroom High School Building | 1 | 976923.85 | 686060 | 290863.85 | 617454 | 3/3 | 470825.85 | 1088279.85 | 617454 | 470825.85 | 100% | 100% | 161.9% | 111.4% | 100% | 2006-06-27 | 2006-07-11 | 2006-10-23 | 2008-03-30 | no data | 524 | 497 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Pasig | 054107015 | Rehab./Concreting of Brgy. Road | 1 | 2055336 | 1340000 | 715336 | 1340000 | 3/3 | 554275.2 | 1894275.2 | 1340000 | 554275.2 | 100% | 100% | 77.48% | 92.16% | 100% | 2003-11-27 | 2004-02-27 | 2004-06-17 | 2005-01-30 | 2005-03-03 | 227 | 784 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Pasig | 054107015 | Road Concreting | 1 | 1618948.92 | 1208292 | 410656.92 | 1208292 | 3/3 | 407656.92 | 1615948.92 | 1208292 | 407656.92 | 100% | 100% | 99.27% | 99.81% | 100% | 2006-06-27 | 2006-07-11 | 2006-09-11 | 2007-04-30 | no data | 231 | 740 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Poblacion 2 | 054107008 | Improvement of Barangay Road | 1 | 1353967 | 958000 | 395967 | 862200 | 2/3 | 287400 | 1101819.67 | 814419.67 | 287400 | 94.46% | 100% | 72.58% | 81.38% | 100% | 2008-12-15 | no data | 2009-05-01 | 2009-08-25 | no data | 116 | 711 |  | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | San Isidro | 054107018 | Improvement of Barangay Road | 1 | 2811717 | 2080000 | 731717 | 1872000 | 2/3 | 612800 | 2294394.08 | 1681594.08 | 612800 | 89.83% | 100% | 83.75% | 81.6% | 100% | 2008-12-15 | no data | 2009-05-05 | 2009-11-30 | no data | 209 | 274 | completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | San Ramon | 054107019 | Rehab./Concreting of Brgy. Road | 1 | 2002740 | 1340000 | 662740 | 1340000 | 3/3 | 666816 | 2006816 | 1340000 | 666816 | 100% | 100% | 100.6% | 100.2% | 100% | 2003-11-27 | 2004-02-27 | 2004-06-22 | 2005-01-31 | 2005-03-03 | 223 | 484 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | San Ramon | 054107019 | Rehab./Improvement of Farm to Market Road | 1 | 2880000 | 2016000 | 864000 | 2016000 | 3/3 | 703286 | 2719286 | 2016000 | 703286 | 100% | 100% | 81.4% | 94.42% | 100% | 2005-07-07 | 2005-08-05 | 2005-10-10 | 2006-08-30 | 2006-11-29 | 324 | 484 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Claveria | 054107 | Taguilid | 054107021 | Rehab./Improvement of Farm to Market Road | 1 | 1313203 | 910000 | 403203 | 910000 | 3/3 | 379858.25 | 1289858.25 | 910000 | 379858.25 | 100% | 100% | 94.21% | 98.22% | 100% | 2005-07-07 | 2005-08-05 | 2005-10-25 | 2006-04-30 | 2006-05-26 | 187 | 317 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Cantorna | 054114001 | Construction of Duplex Bldg. (DCC & BHS) | 1 | 788401 | 548179 | 240222 | 548179 | 3/3 | 280935 | 829114 | 548179 | 280935 | 100% | 100% | 116.9% | 105.2% | 100% | no data | 2005-07-14 | 2005-09-05 | 2005-12-02 | no data | 88 | 242 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Famosa | 054114002 | Construction of 2-Classroom School Bldg. | 1 | 571414.85 | 374861.5 | 196553.35 | 374861.5 | 3/3 | 238091.5 | 612953 | 374861.5 | 238091.5 | 100% | 100% | 121.1% | 107.3% | 100% | no data | 2004-01-30 | 2004-05-12 | 2004-07-26 | no data | 75 | 137 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Guinhadap | 054114007 | Construction of Water System Level 2 | 1 | 557329.59 | 340582.7 | 216746.89 | 340582.7 | 3/3 | 231796.89 | 572379.59 | 340582.7 | 231796.89 | 100% | 100% | 106.9% | 102.7% | 100% | no data | 2004-01-30 | 2004-04-19 | 2004-11-21 | 2004-11-23 | 216 | 141 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Guinhadap | 054114007 | Establishment of Marine Sanctuary and Eco-Park | 1 | 887733 | 510733 | 377000 | 459659.7 | 0.33333 | 60500 | 520159.7 | 459659.7 | 60500 | 100% | 100% | 16.05% | 58.59% | 100% | 2006-04-27 | not conducted | 2007-03-01 | 2008-09-25 | not yet inaugurated | 574 | 359 | On-going | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Mac Arthur | 054114003 | Construction of Water System Level 2 | 1 | 691849 | 468894 | 222955 | 468894 | 3/3 | 262435 | 731329 | 468894 | 262435 | 100% | 100% | 117.7% | 105.7% | 100% | no data | 2005-07-14 | 2005-09-13 | 2005-11-30 | no data | 78 | 477 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Maglambong | 054114004 | Construction of Water System Level 2 | 1 | 1069547.68 | 732540.7 | 337006.98 | 732540.7 | 3/3 | 417897.3 | 1150438 | 732540.7 | 417897.3 | 100% | 100% | 124% | 107.6% | 100% | no data | 2004-01-30 | 2004-04-20 | 2004-07-01 | no data | 72 | 220 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Maglambong | 054114004 | Construction of Duplex Bldg. (DCC & BHS) | 1 | 779831 | 542485 | 237346 | 542485 | 3/3 | 265050 | 807535 | 542485 | 265050 | 100% | 100% | 111.7% | 103.6% | 100% | no data | 2005-07-14 | 2005-09-01 | 2006-02-28 | no data | 180 | 196 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Morocborocan | 054114005 | Construction of Brgy. Health Station | 1 | 323773.02 | 204533.6 | 119239.42 | 204533.6 | 3/3 | 121365.92 | 325899.52 | 204533.6 | 121365.92 | 100% | 100% | 101.8% | 100.7% | 100% | no data | 2004-01-30 | 2004-04-27 | 2004-08-27 | 2004-11-23 | 122 | 246 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Poblacion | 054114006 | Construction of Drainage System | 1 | 403559.39 | 186593.9 | 216965.49 | 186593.9 | 3/3 | 179047.74 | 365641.64 | 186593.9 | 179047.74 | 100% | 100% | 82.52% | 90.6% | 100% | no data | 2004-01-30 | 2004-04-29 | 2004-11-21 | 2004-11-23 | 206 | 200 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Poblacion | 054114006 | Construction of 2-units Day Care Center | 1 | 814360 | 577014 | 237346 | 577014 | 3/3 | 267451 | 844465 | 577014 | 267451 | 100% | 100% | 112.7% | 103.7% | 100% | no data | 2005-07-14 | 2005-09-06 | 2006-01-31 | no data | 147 | 477 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Poblacion | 054114006 | Construction of Pathway and Line Canal | 1 | 554812 | 333152 | 221660 | 323770 | 0.33333 | 234095 | 557865 | 323770 | 234095 | 100% | 100% | 105.6% | 100.6% | 100% | 2006-04-27 | not conducted | 2006-09-01 | 2007-04-30 | no data | 241 | 826 | Completed | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Real | 054114008 | Construction of Water System Level 2 | 1 | 995647.58 | 678740.15 | 316907.43 | 678740.15 | 3/3 | 334245.93 | 1012986.08 | 678740.15 | 334245.93 | 100% | 100% | 105.5% | 101.7% | 100% | no data | 2004-01-30 | 2004-04-13 | 2004-11-05 | 2004-11-23 | 206 | 304 | Inaugurated | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Rizal | 054114009 | Construction of Brgy. Health Station | 1 | 314708.04 | 204533.6 | 110174.44 | 204533.6 | 3/3 | 128344.44 | 332878.04 | 204533.6 | 128344.44 | 100% | 100% | 116.5% | 105.8% | 100% | no data | 2004-01-30 | 2004-04-14 | 2004-08-04 | 2004-11-23 | 112 | 346 | Inaugurated | 1
V | 05 | Masbate | 0541 | Monreal | 054114 | Rizal | 054114009 | Construction of Farm to Market Road | 1 | 2728520 | 1886937 | 841583 | 1698242.5 | 2/3 | 583996 | 2282238.5 | 1698242.5 | 583996 | 100% | 100% | 69.39% | 83.64% | 100% | 2006-04-27 | not conducted | 2006-06-14 | 2007-10-30 | not yet inaugurated | 503 | 334 | On-going | 1 | VISAYAS
V | 05 | Masbate | 0541 | Monreal | 054114 | Sto. Niño | 054120001 | Construction of Health Station & DCC | 1 | 558249.76 | 367231.5 | 191018.26 | 367231.5 | 3/3 | 228429.5 | 595661 | 367231.5 | 228429.5 | 100% | 100% | 119.6% | 106.7% | 100% | no data | 2004-01-30 | 2004-04-25 | 2004-11-05 | 2004-11-23 | 194 | 207 | Inaugurated | 1
V | 05 | Masbate | 0541 | Monreal | 054114 | Sto. Niño | 054114010 | Construction of Boulder Dike | 1 | 700439 | 484446 | 215993 | 484446 | 3/3 | 242203 | 726649 | 484446 | 242203 | 100% | 100% | 112.1% | 103.7% | 100% | no data | 2005-07-14 | 2005-08-24 | 2005-11-30 | no data | 98 | 405 | Inaugurated | 1
V | 05 | Masbate | 0541 | Monreal | 054114 | Togoron | 054114011 | Construction of Day Care Center | 1 | 378846.1 | 210382.25 | 168463.85 | 210382.25 | 3/3 | 155886.32 | 366268.57 | 210382.25 | 155886.32 | 100% | 100% | 92.53% | 96.68% | 100% | no data | 2004-01-30 | 2004-04-22 | 2004-06-18 | no data | 57 | 310 | Completed | 1
V | 05 | Masbate | 0541 | Monreal | 054114 | Togoron | 054114011 | Construction of Seawall | 1 | 979974 | 678982 | 300992 | 678982 | 3/3 | 314947 | 993929 | 678982 | 314947 | 100% | 100% | 104.6% | 101.4% | 100% | no data | 2005-07-14 | 2005-09-28 | 2005-12-22 | no data | 85 | 330 | Inaugurated | 1
V | 05 | Masbate | 0541 | Monreal | 054114 | Togoron | 054114011 | Construction of Sea Wall | 1 | 867875 | 569178 | 298697 | 569178 | 3/3 | 296793.5 | 865971.5 | 569178 | 296793.5 | 100% | 100% | 99.36% | 99.78% | 100% | 2006-04-27 | not conducted | 2007-03-20 | 2007-06-20 | no data | 92 | 310 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Boca-Chica | 054120001 | Construction of Community Learning Center | 1 | 708041.43 | 610564.87 | 97476.56 | 589373.47 | 1/3 | 105556.56 | 694930.03 | 589373.47 | 105556.56 | 100% | 100% | 108.3% | 98.15% | 100% | 2009-02-24 | no data | 2009-04-13 | 2009-05-31 | no data | 48 | 433 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Bolod | 054120002 | Construction of Day Care Center | 1 | 648652.49 | 557775.49 | 90877 | 544839.03 | 1/3 | 90377 | 635216.03 | 544839.03 | 90377 | 100% | 100% | 99.45% | 97.93% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-05-31 | no data | 55 | 575 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Busing | 054120003 | Construction of One-Classroom Elem. School Building | 1 | 515533.85 | 316157.08 | 199376.77 | 316157.08 | 3/3 | 190051.77 | 506208.85 | 316157.08 | 190051.77 | 100% | 100% | 95.32% | 98.19% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-26 | 2008-03-26 | no data | 517 | 388 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Cueva | 054120024 | Construction of Brgy. Health Center | 1 | 312000 | 184080 | 127920 | 184080 | 3/3 | 130395 | 314475 | 184080 | 130395 | 100% | 100% | 101.9% | 100.8% | 100% | no data | 2004-03-05 | 2004-04-19 | 2004-09-01 | no data | 135 | 557 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Cueva | 054120024 | Construction of Day Care Center | 1 | 480000 | 288000 | 192000 | 288000 | 3/3 | 165800 | 453800 | 288000 | 165800 | 100% | 100% | 86.35% | 94.54% | 100% | no data | 2005-08-05 | 2005-11-15 | 2006-02-28 | no data | 105 | 59 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Cueva | 054120024 | Contruction of Breakwater/Seawall | 1 | 752202 | 616052 | 136150 | 596342.29 | 3/3 | 130890 | 727232.29 | 596342.29 | 130890 | 100% | 100% | 96.14% | 96.68% | 100% | 2009-02-24 | no data | 2009-04-07 | 2009-06-13 | no data | 67 | 551 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Dangcalan | 054120004 | Construction of Drainage System | 1 | 835250 | 491992 | 343258 | 491992 | 3/3 | 346961.6 | 838953.6 | 491992 | 346961.6 | 100% | 100% | 101.1% | 100.4% | 100% | no data | 2004-03-05 | 2004-04-19 | 2004-09-09 | 2004-10-15 | 143 | 190 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Dangcalan | 054120004 | Construction of Brgy. Health Station | 1 | 480000 | 283200 | 196800 | 283200 | 3/3 | 172050 | 455250 | 283200 | 172050 | 100% | 100% | 87.42% | 94.84% | 100% | no data | 2005-08-05 | 2005-11-14 | 2006-02-28 | no data | 106 | 66 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Dangcalan | 054120004 | Construction of Water System Level 2 | 1 | 711039.62 | 578714.62 | 132325 | 560226.62 | 1/3 | 523375 | 1083601.62 | 560226.62 | 523375 | 100% | 100% | 395.5% | 152.4% | 100% | 2009-02-24 | no data | 2009-04-20 | 2009-07-10 | no data | 81 | 336 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Halabangbaybay | 054120005 | Construction of Drainage Lined Canal | 1 | 529968 | 448598 | 81370 | 434543 | 1/3 | 82140 | 516683 | 434543 | 82140 | 100% | 100% | 100.9% | 97.49% | 100% | 2009-02-24 | no data | 2009-04-27 | 2009-05-31 | no data | 34 | 220 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Halabang-Baybay | 054120005 | Construction of Water System Level 2 | 1 | 650000 | 403000 | 247000 | 362700 | 3/3 | 236460 | 599160 | 362700 | 236460 | 100% | 100% | 95.73% | 92.18% | 100% | no data | 2004-03-05 | 2004-07-20 | 2004-09-30 | no data | 72 | 142 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Halabang-Baybay | 054120005 | Construction of 2-Classroom School Bldg. | 1 | 1260000 | 743400 | 516600 | 743400 | 3/3 | 392760 | 1136160 | 743400 | 392760 | 100% | 100% | 76.03% | 90.17% | 100% | no data | 2005-08-05 | 2005-11-16 | 2006-03-31 | no data | 135 | 80 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Iniwaran | 054120006 | Construction of Rain Water Collector | 1 | 1041647.7 | 728458.16 | 313189.54 | 727736.53 | 3/3 | 306449.54 | 1034186.07 | 727736.53 | 306449.54 | 100% | 100% | 97.85% | 99.28% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-04 | 2008-06-30 | no data | 635 | 410 | On-going | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Iniwaran | 054120006 | Construction of Community Learning Center | 1 | 708041.43 | 610564.87 | 97476.56 | 589373.46 | 1/3 | 101296.56 | 690670.02 | 589373.46 | 101296.56 | 100% | 100% | 103.9% | 97.55% | 100% | 2009-02-24 | no data | 2009-04-20 | 2009-06-13 | no data | 54 | 439 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Ki-Buaya | 054120007 | Construction of Water System Level 2 | 1 | 1300000 | 910000 | 390000 | 546000 | 3/3 | 372900 | 918900 | 546000 | 372900 | 100% | 100% | 95.62% | 70.68% | 100% | no data | 2005-08-05 | 2005-09-26 | 2006-03-31 | no data | 186 | 196 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Ki-Buaya | 054120007 | Construction of Two-Classroom Elem. School Building | 1 | 1268036.9 | 798538.73 | 469498.17 | 798538.73 | 0.33333 | 446023.2615 | 1244561.9915 | 798538.73 | 446023.2615 | 100% | 100% | 95% | 98.15% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-14 | 2007-06-30 | no data | 259 | 196 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Ki-Buaya | 054120007 | Construction of Barangay Port | 1 | 742807 | 597837 | 144970 | 569371.86 | 1/3 | 115550 | 684921.86 | 569371.86 | 115550 | 100% | 100% | 79.71% | 92.21% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-05-31 | no data | 55 | 218 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Ki-Romero | 054120008 | Construction of Two-Classroom Elem. School Building | 1 | 1157911 | 710989 | 446922 | 710989 | 3/3 | 433487 | 1144476 | 710989 | 433487 | 100% | 100% | 96.99% | 98.84% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-23 | 2007-06-30 | no data | 250 | 335 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Ki-Romero | 054120008 | Concreting of Pathway | 1 | 573107 | 493093 | 80014 | 469654.3 | 1/3 | 104154 | 573808.3 | 469654.3 | 104154 | 100% | 100% | 130.2% | 100.1% | 100% | 2009-02-24 | no data | 2009-04-27 | 2009-05-31 | no data | 34 | 350 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Laurente | 054120009 | Construction of Water System Level 2 | 1 | 1160936 | 812655 | 348281 | 812655 | 3/3 | 330697 | 1143352 | 812655 | 330697 | 100% | 100% | 94.95% | 98.49% | 100% | no data | 2005-08-05 | 2005-11-08 | 2006-06-30 | no data | 234 | 330 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Laurente | 054120009 | Improvement of Farm to Market Road | 1 | 605467 | 507907 | 97560 | 507906.4 | 1/3 | 116610 | 624516.4 | 507906.4 | 116610 | 100% | 100% | 119.5% | 103.1% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-07-10 | no data | 95 | 393 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabini | 054120010 | Rehab./Concreting of Farm to Market Road | 1 | 2000000 | 1280000 | 720000 | 1280000 | 3/3 | 668720 | 1948720 | 1280000 | 668720 | 100% | 100% | 92.88% | 97.44% | 100% | no data | 2004-03-05 | 2004-04-21 | 2004-10-30 | no data | 192 | 554 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabini | 054120010 | Improvement of Farm to Market Road | 1 | 1800000 | 1111000 | 689000 | 1111000 | 3/3 | 684804 | 1795804 | 1111000 | 684804 | 100% | 100% | 99.39% | 99.77% | 100% | no data | 2005-08-05 | 2005-09-26 | 2006-06-30 | no data | 277 | 163 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabini | 054120010 | Construction of Water System Level II | 1 | 1500000 | 909350 | 590650 | 909350 | 3/3 | 554327 | 1463677 | 909350 | 554327 | 100% | 100% | 93.85% | 97.58% | 100% | 2006-04-02 | 2006-10-04 | 2006-11-14 | 2007-03-31 | no data | 137 | 308 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabini | 054120010 | Improvement of Farm to Market Road | 1 | 837714 | 688666 | 149048 | 666168 | 1/3 | 142476 | 808644 | 666168 | 142476 | 100% | 100% | 95.59% | 96.53% | 100% | 2009-02-24 | no data | 2009-04-20 | 2009-07-10 | no data | 81 | 389 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabuhay | 054120011 | Rehab./Concreting of Farm to Market Road | 1 | 1000000 | 670000 | 330000 | 670000 | 3/3 | 402668.5 | 1072668.5 | 670000 | 402668.5 | 100% | 100% | 122% | 107.3% | 100% | no data | 2004-03-05 | 2004-05-24 | 2004-10-30 | no data | 159 | 345 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabuhay | 054120011 | Construction of Day Care Center | 1 | 535352.6 | 328370.08 | 206982.52 | 328370.06 | 3/3 | 213308.52 | 541678.58 | 328370.06 | 213308.52 | 100% | 100% | 103.1% | 101.2% | 100% | 2006-04-02 | 2006-10-04 | 2006-11-25 | 2008-06-01 | no data | 554 | 305 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mabuhay | 054120011 | Improvement of Farm to Market Road | 1 | 644230 | 518865 | 125365 | 504328.35 | 1/3 | 84315 | 588643.35 | 504328.35 | 84315 | 100% | 100% | 67.26% | 91.37% | 100% | 2009-02-24 | no data | 2009-04-13 | 2009-07-10 | no data | 88 | 310 | completed as built | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Malaking-Ilog | 054120025 | Construction of 2-Classroom High School Bldg. | 1 | 693000 | 476400 | 216600 | 476400 | 3/3 | 199921.5 | 676321.5 | 476400 | 199921.5 | 100% | 100% | 92.3% | 97.59% | 100% | no data | 2004-03-05 | 2004-07-06 | 2004-09-30 | no data | 86 | 397 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Malaking-Ilog | 054120025 | Construction of Community Learning Center | 1 | 734979.95 | 652064.95 | 82915 | 634747.86 | 1/3 | 63915 | 698662.86 | 634747.86 | 63915 | 100% | 100% | 77.08% | 95.06% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-07-10 | no data | 95 | 364 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mapanique | 054120013 | Construction of Farm to Market Road | 1 | 200000 | 133000 | 67000 | 133000 | 3/3 | 59600 | 192600 | 133000 | 59600 | 100% | 100% | 88.96% | 96.3% | 100% | no data | 2004-03-05 | 2004-04-20 | 2004-10-30 | no data | 193 | 223 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mapanique | 054120013 | Construction of Barangay Health Station | 1 | 505260.62 | 334208.52 | 171052.1 | 334208.52 | 3/3 | 180492.13 | 514700.65 | 334208.52 | 180492.13 | 100% | 100% | 105.5% | 101.9% | 100% | 2006-04-02 | 2006-10-04 | 2006-08-30 | 2006-12-31 | no data | 123 | 309 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Mapanique | 054120013 | Construction of Fish Landing | 1 | 410044 | 352900 | 57144 | 342185 | 1/3 | 58144 | 400329 | 342185 | 58144 | 100% | 100% | 101.7% | 97.63% | 100% | 2009-02-24 | no data | 2009-04-02 | 2009-05-31 | no data | 59 | 405 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Nazareno | 054120014 | Rehab./Concreting of Farm to Market Road | 1 | 1000000 | 679000 | 321000 | 679000 | 3/3 | 317786 | 996786 | 679000 | 317786 | 100% | 100% | 99% | 99.68% | 100% | no data | 2004-03-05 | 2004-04-20 | 2004-10-30 | no data | 193 | 230 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Nazareno | 054120014 | Construction of Water System Level 2 | 1 | 419392.3 | 363130.78 | 56261.52 | 363130.78 | 1/3 | 56261.52 | 419392.3 | 363130.78 | 56261.52 | 100% | 100% | 100% | 100% | 100% | 2009-02-24 | no data | 2009-04-13 | 2009-07-10 | no data | 88 | 296 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Pinamasingan | 054120015 | Construction of Water System Level 2 | 1 | 500000 | 310000 | 190000 | 310000 | 3/3 | 204675 | 514675 | 310000 | 204675 | 100% | 100% | 107.7% | 102.9% | 100% | no data | 2004-03-05 | 2004-05-24 | 2004-11-05 | no data | 165 | 112 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Pinamasingan | 054120015 | Construction of Barangay Port | 1 | 1500000 | 1050000 | 450000 | 1050000 | 3/3 | 440445.75 | 1490445.75 | 1050000 | 440445.75 | 100% | 100% | 97.88% | 99.36% | 100% | no data | 2005-08-05 | 2005-09-12 | 2006-02-28 | no data | 169 | 150 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Pinamasingan | 054120015 | Construction of Two-Classroom Elem. School Building | 1 | 1226010.9 | 840716.27 | 385294.63 | 840716.27 | 3/3 | 381049.63 | 1221765.9 | 840716.27 | 381049.63 | 100% | 100% | 98.9% | 99.65% | 100% | 2006-04-02 | 2006-10-04 | 2006-11-15 | 2007-06-30 | no data | 227 | 291 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Pinamasingan | 054120015 | Improvement of Farm to Market Road | 1 | 646843 | 164999.08 | 481843.92 | 164999.08 | 3/3 | 462543.92 | 627543 | 164999.08 | 462543.92 | 100% | 100% | 95.99% | 97.02% | 100% | 2009-02-24 | no data | 2009-04-20 | 2009-05-31 | no data | 41 | 355 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Quintina | 054120016 | Construction of Water System Level II | 1 | 1005221.7 | 644981.76 | 360239.94 | 515985.41 | 3/3 | 353930.94 | 869916.35 | 515985.41 | 353930.94 | 100% | 100% | 98.25% | 86.54% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-23 | 2007-03-30 | no data | 158 | 254 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Quintina | 054120016 | Concreting of Pathway | 1 | 480301 | 412842 | 67459 | 391694.15 | 1/3 | 62515 | 454209.15 | 391694.15 | 62515 | 100% | 100% | 92.67% | 94.57% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-07-10 | no data | 95 | 449 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Jose | 054120019 | Construction of Water System Level 2 | 1 | 1888000 | 1208620 | 679380 | 1208620 | 3/3 | 521696 | 1730316 | 1208620 | 521696 | 100% | 100% | 76.79% | 91.65% | 100% | no data | 2004-03-05 | 2004-06-29 | 2004-10-30 | no data | 123 | 405 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Jose | 054120019 | Construction of 2-Classroom School Bldg. | 1 | 1261012 | 852012 | 409000 | 852012 | 3/3 | 418200 | 1270212 | 852012 | 418200 | 100% | 100% | 102.2% | 100.7% | 100% | no data | 2005-08-05 | 2005-09-28 | 2006-03-31 | no data | 184 | 126 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Jose | 054120019 | Construction of Duplex Multi-Purpose Building | 1 | 1097076 | 684362.8 | 412713.2 | 684013.41 | 3/3 | 395851.2 | 1079864.61 | 684013.41 | 395851.2 | 100% | 100% | 95.91% | 98.43% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-04 | 2007-07-15 | no data | 284 | 377 | On-going | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Jose | 054120019 | Construction of Day Care Center | 1 | 677497.95 | 601148.58 | 76349.37 | 600817.09 | 1/3 | 51349.37 | 652166.46 | 600817.09 | 51349.37 | 100% | 100% | 67.26% | 96.26% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-07-10 | no data | 95 | 319 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Pedro | 054120020 | Construction of 1-Classroom High School Bldg. | 1 | 346500 | 174908 | 171592 | 174908 | 3/3 | 173640.75 | 348548.75 | 174908 | 173640.75 | 100% | 100% | 101.2% | 100.6% | 100% | no data | 2004-03-05 | 2004-05-27 | 2004-09-30 | no data | 126 | 312 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Pedro | 054120020 | Construction of Health Center | 1 | 740124.28 | 627795.76 | 112328.52 | 603471.63 | 3/3 | 70000 | 673471.63 | 603471.63 | 70000 | 100% | 100% | 62.32% | 90.99% | 100% | 2009-02-24 | no data | 2009-04-20 | 2009-05-31 | no data | 41 | 602 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Rafael | 054120021 | Rehab./Concreting of Farm to Market Road | 1 | 1000000 | 589000 | 411000 | 589000 | 3/3 | 411250 | 1000250 | 589000 | 411250 | 100% | 100% | 100.1% | 100% | 100% | no data | 2004-03-05 | 2004-06-22 | 2004-10-01 | no data | 101 | 779 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | San Rafael | 054120021 | Construction of Drainage Lined Canal | 1 | 702609 | 589797 | 112812 | 582018.93 | 1/3 | 115000 | 697018.93 | 582018.93 | 115000 | 100% | 100% | 101.9% | 99.2% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-07-10 | no data | 95 | 593 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Sta. Cruz | 054120022 | Construction of Day Care Center | 1 | 535352.6 | 303867.6 | 231485 | 303867.6 | 0.33333 | 208336.5 | 512204.1 | 303867.6 | 208336.5 | 100% | 100% | 90% | 95.68% | 100% | 2006-04-02 | 2006-10-04 | 2006-10-27 | 2007-03-25 | no data | 149 | 303 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Sta. Cruz | 054120022 | Conncreting of Pathway | 1 | 576954 | 499729 | 77225 | 489785.68 | 1/3 | 74225 | 564010.68 | 489785.68 | 74225 | 100% | 100% | 96.12% | 97.76% | 100% | 2009-02-24 | no data | 2009-04-13 | 2009-07-10 | no data | 88 | 378 |  | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Terraplin | 054120023 | Construction of Water System Level 2 | 1 | 1166482 | 549733 | 616749 | 549733 | 3/3 | 611923.75 | 1161656.75 | 549733 | 611923.75 | 100% | 100% | 99.22% | 99.59% | 100% | no data | 2005-08-05 | 2005-12-12 | 2006-06-30 | no data | 200 | 242 | Completed | 1
V | 05 | Masbate | 0541 | San Pascual | 054120 | Terraplin | 054120023 | Contruction of Breakwater/Seawall | 1 | 593692 | 506955 | 86737 | 493533.75 | 1/3 | 101737 | 595270.75 | 493533.75 | 101737 | 100% | 100% | 117.3% | 100.3% | 100% | 2009-02-24 | no data | 2009-04-06 | 2009-06-01 | no data | 56 | 254 |  | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Awai | 056207002 | Construction of Drainage System | 1 | 1122506.4 | 646408.63 | 476097.77 | 646408.63 | 3/3 | 511576.32 | 1157984.95 | 646408.63 | 511576.32 | 100% | 100% | 107.5% | 103.2% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-22 | 2006-11-08 | no data | 351 | 107 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Banban | 056207003 | Rehab./Improvement of Farm to Market Road | 1 | 2345323 | 1475741.4 | 869581.6 | 1475741.4 | 3/3 | 607866.58 | 2083607.98 | 1475741.4 | 607866.58 | 100% | 100% | 69.9% | 88.84% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-29 | 2007-04-25 | no data | 512 | 142 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Baras | 056207006 | Construction of Water System Level 2 | 1 | 768331.65 | 471511.32 | 296820.33 | 471511.32 | 3/3 | 250261.33 | 721772.65 | 471511.32 | 250261.33 | 100% | 100% | 84.31% | 93.94% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-28 | 2006-06-16 | no data | 200 | 60 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Girawan | 056207015 | Construction of 3-Classroom School Bldg. | 1 | 1437140 | 997344 | 439796 | 997344 | 3/3 | 383934.4 | 1381278.4 | 997344 | 383934.4 | 100% | 100% | 87.3% | 96.11% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-21 | 2006-04-11 | no data | 141 | 60 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Lourdes | 056207019 | Rehab./Improvement of Farm to Market Road | 1 | 4207727.7 | 2230400 | 1977327.7 | 2230400 | 0.33333 | 136110 | 2366510 | 2230400 | 136110 | 100% | 100% | 6.884% | 56.24% | 100% | 2005-07-01 | 2005-10-05 | 2006-10-23 | 2007-12-30 | no data | 433 | 57 | completed as built | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Malinao | 056207022 | Rehab./Improvement of Farm to Market Road | 1 | 2691240 | 1367794.2 | 1323445.8 | 1367793.68 | 0.66667 | 487092 | 1854885.68 | 1367793.68 | 487092 | 100% | 100% | 36.8% | 68.92% | 100% | 2005-07-01 | 2005-10-05 | 2006-10-17 | 2007-07-30 | no data | 286 | 50 | completed as built | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | San Antonio | 056207035 | Construction of Water System Level 2 | 1 | 939000 | 537227.6 | 401772.4 | 537227.6 | 3/3 | 293860 | 831087.6 | 537227.6 | 293860 | 100% | 100% | 73.14% | 88.51% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-15 | 2006-01-30 | no data | 76 | 132 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | San Jose | 056207037 | Construction of Water System Level 2 | 1 | 654034.5 | 406870.5 | 247164 | 406870.5 | 3/3 | 176170 | 583040.5 | 406870.5 | 176170 | 100% | 100% | 71.28% | 89.15% | 100% | 2005-07-01 | 2005-10-05 | 2005-12-05 | 2006-04-06 | no data | 122 | 78 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | San Rafael | 056207038 | Construction of Water System Level 2 | 1 | 979724.65 | 574134.65 | 405590 | 574134.65 | 3/3 | 368807.5 | 942942.15 | 574134.65 | 368807.5 | 100% | 100% | 90.93% | 96.25% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-25 | 2006-05-31 | no data | 187 | 193 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Tagbac | 056207045 | Rehab./Improvement of Farm to Market Road | 1 | 3758327 | 2323498 | 1434829 | 2323498 | 3/3 | 49910 | 2373408 | 2323498 | 49910 | 100% | 100% | 3.478% | 63.15% | 100% | 2005-07-01 | 2005-10-05 | 2006-07-07 | 2006-11-16 | no data | 132 | 37 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Tinanogan | 056207046 | Construction of Water System Level 2 | 1 | 781838.5 | 511717 | 270121.5 | 511717 | 3/3 | 262649 | 774366 | 511717 | 262649 | 100% | 100% | 97.23% | 99.04% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-21 | 2006-06-15 | no data | 206 | 295 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Tres Marias | 056207048 | Construction of Drainage System | 1 | 3076167 | 2134477.6 | 941689.4 | 2134477.6 | 3/3 | 890030.65 | 3024508.25 | 2134477.6 | 890030.65 | 100% | 100% | 94.51% | 98.32% | 100% | 2005-07-01 | 2005-10-05 | 2005-11-21 | 2006-04-11 | no data | 141 | 264 | Completed | 1
V | 05 | Sorsogon | 0562 | Donsol | 056207 | Tuba | 056207049 | Rehab./Improvement of Farm to Market Road | 1 | 3126398.7 | 1622875.1 | 1503523.6 | 1460587.59 | 0.33333 | 205692.8 | 1666280.39 | 1460587.59 | 205692.8 | 100% | 100% | 13.68% | 53.3% | 100% | 2005-07-01 | 2005-10-05 | 2006-11-08 | 2007-05-30 | no data | 203 | 138 | completed as built | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Anog | 056210001 | Construction of Day Care Center | 1 | 657474 | 486531 | 170943 | 486531 | 2/3 | 161555.5 | 648086.5 | 486531 | 161555.5 | 100% | 100% | 94.51% | 98.57% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2009-03-25 | no data | 175 | 305 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Aroroy | 056210002 | Construction of Water System Level 2 | 1 | 1416974 | 1048561 | 368413 | 1048561 | 1/3 | 363874.6 | 1412435.6 | 1048561 | 363874.6 | 100% | 100% | 98.77% | 99.68% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2009-04-25 | no data | 206 | 186 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Binanuahan | 056210004 | Construction of 2-Classroom Elementary School Building | 1 | 1170808 | 866398 | 304410 | 813646 |  | 270719.16 | 1084365.16 | 813646 | 270719.16 | 100% | 100% | 88.93% | 92.62% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 216 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Biriran | 056210005 | Construction of Brgy. Road | 1 | 1170414 | 866106 | 304308 | 866106 | 3/3 | 313788 | 1179894 | 866106 | 313788 | 100% | 100% | 103.1% | 100.8% | 100% | 2007-07-07 | not conducted | 2007-10-03 | 2008-04-15 | 2008-06-05 | 195 | 416 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Biriran | 056210005 | Concreting of Pathway Biriran Road Section | 1 | 1735880 | 1284551 | 451329 | 1284551 |  | 285856 | 1570407 | 1284551 | 285856 | 100% | 100% | 63.34% | 90.47% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 416 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Buraburan | 056210006 | Construction of Water System Level 2 | 1 | 1880870 | 1391844 | 489026 | 1389321.56 | 3/3 | 545386 | 1934707.56 | 1389321.56 | 545386 | 100% | 100% | 111.5% | 102.9% | 100% | 2007-07-07 | not conducted | 2007-11-19 | 2008-06-30 | 2008-07-07 | 224 | 367 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Calmayon | 056210008 | Construction of Day Care Center | 1 | 722580 | 534709 | 187871 | 481238 |  | 135207 | 616445 | 481238 | 135207 | 100% | 100% | 71.97% | 85.31% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 86 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Carohayon | 056210009 | Concreting of Pathway, Caruhayon Road Section | 1 | 1303831 | 964835 | 338996 | 964835 | 1/3 | 257643 | 1222478 | 964835 | 257643 | 100% | 100% | 76% | 93.76% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2009-03-25 | no data | 175 | 149 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Carohayon | 056210009 | Construction of Day Care Center | 1 | 691251 | 511526 | 179725 | 484418.5 |  | 121351 | 605769.5 | 484418.5 | 121351 | 100% | 100% | 67.52% | 87.63% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 149 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Catanagan | 056210010 | Concreting of Pathway Catanagan Road Section | 1 | 1033680 | 764923 | 268757 | 764523 |  | 175825.25 | 940348.25 | 764523 | 175825.25 | 100% | 100% | 65.42% | 90.97% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 196 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Catanusan | 056210010 | Construction of Pathway | 1 | 1497542 | 1108181 | 389361 | 1076884.5 | 3/3 | 352671 | 1429555.5 | 1076884.5 | 352671 | 100% | 100% | 90.58% | 95.46% | 100% | 2007-07-07 | not conducted | 2007-11-26 | 2008-09-30 | 2008-10-01 | 309 | 181 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Cogon | 056210012 | Construction of 3 Classroom School Bldg | 1 | 1334611 | 987612 | 346999 | 925929 | 3/3 | 377566 | 1303495 | 925929 | 377566 | 100% | 100% | 108.8% | 97.67% | 100% | 2007-07-07 | not conducted | 2007-11-07 | 2008-05-31 | 2008-06-06 | 206 | 342 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Cogon | 056210012 | Construction of Day Care Center | 1 | 657474 | 537031 | 120443 | 537031 | 1/3 | 127205.5 | 664236.5 | 537031 | 127205.5 | 100% | 100% | 105.6% | 101% | 100% | no data | not conducted | 2008-10-01 | 2009-03-25 | no data | 175 | 342 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Embarcadero | 056210013 | Construction of Barangay Health Station | 1 | 604220 | 447123 | 157097 | 447123 | 3/3 | 156745.3 | 603868.3 | 447123 | 156745.3 | 100% | 100% | 99.78% | 99.94% | 100% | 2007-07-07 | not conducted | 2007-11-19 | 2008-05-31 | 2008-06-06 | 194 | 216 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Guruyan | 056210014 | Construction of Water System Level 2 | 1 | 1152821 | 853088 | 299733 | 853088 | 3/3 | 487051.1 | 1340139.1 | 853088 | 487051.1 | 100% | 100% | 162.5% | 116.2% | 100% | 2007-07-07 | not conducted | 2008-02-26 | 2008-09-30 | 2008-10-20 | 217 | 517 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Guruyan | 056210014 | Construction of 2-Classroom Elementary School Building | 1 | 1155069 | 854751 | 300318 | 854751 |  | 185361.75 | 1040112.75 | 854751 | 185361.75 | 100% | 100% | 61.72% | 90.05% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 517 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | North Poblacion | 056210019 | Construction of 2-Classroom Elementary School Building | 1 | 1155069 | 854751 | 300318 | 802748 |  | 192786.03 | 995534.03 | 802748 | 192786.03 | 100% | 100% | 64.19% | 86.19% | 100% | 2008-11-10 | not conducted | 2009-02-01 | 2009-05-25 | no data | 113 | 153 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Sablayan | 056210023 | Construction of Covered Stairs & Pathway | 1 | 1112093 | 822949 | 289144 | 822949 | 3/3 | 292054 | 1115003 | 822949 | 292054 | 100% | 100% | 101% | 100.3% | 100% | 2007-07-07 | not conducted | 2007-12-03 | 2008-10-13 | 2008-10-14 | 315 | 154 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Sablayan | 056210023 | Construction of 2-Classroom Elementary School Building | 1 | 1279815 | 947063 | 332752 | 947063 |  | 317938 | 1265001 | 947063 | 317938 | 100% | 100% | 95.55% | 98.84% | 100% | 2008-11-10 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 154 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Sipaya - C2 | 056210024 | Construction of Water System Level 2 | 2 | 1945442 | 1439627 | 505815 | 1439627 | 1/3 | 518525 | 1958152 | 1439627 | 518525 | 100% | 100% | 102.5% | 100.7% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2009-03-25 | no data | 175 | 196 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Calateo | 056210007 | Construction of Barangay Health Station | 2 | 728668 | 539214 | 189454 | 539214 |  | 115419 | 654633 | 539214 | 115419 | 100% | 100% | 60.92% | 89.84% | 100% | 2008-11-10 | not conducted | 2009-04-01 | 2009-05-25 | no data | 54 | 196 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | South Poblacion | 056210020 | Improvement of Drainage System | 1 | 630830 | 466814 | 164016 | 466814 | 3/3 | 168398 | 635212 | 466814 | 168398 | 100% | 100% | 102.7% | 100.7% | 100% | 2007-07-07 | not conducted | 2007-11-15 | 2008-07-30 | 2008-07-31 | 258 | 249 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | South Poblacion | 056210020 | Construction of Day Care Center | 1 | 672610 | 497731 | 174879 | 497731 |  | 169404 | 667135 | 497731 | 169404 | 100% | 100% | 96.87% | 99.19% | 100% | 2008-11-10 | not conducted | 2009-01-01 | 2009-04-25 | no data | 114 | 249 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Taboc | 056210025 | Improvement of Irrigation Canal | 1 | 535899 | 396565 | 139334 | 396565 | 3/3 | 158122.75 | 554687.75 | 396565 | 158122.75 | 100% | 100% | 113.5% | 103.5% | 100% | 2007-07-07 | not conducted | 2007-10-01 | 2008-04-21 | 2008-06-05 | 203 | 146 | On-going | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Taboc | 056210025 | Construction of Barangay Road | 1 | 1436359 | 1062906 | 373453 | 1062906 | 2/3 | 359579.67 | 1422485.67 | 1062906 | 359579.67 | 100% | 100% | 96.29% | 99.03% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2008-11-25 | no data | 55 | 146 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Tinago | 056210026 | Construction of Barangay Road | 1 | 1991862 | 1473978 | 517884 | 1473978 | 1/3 | 472441 | 1946419 | 1473978 | 472441 | 100% | 100% | 91.23% | 97.72% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2009-04-25 | no data | 206 | 117 |  | 1
V | 05 | Sorsogon | 0562 | Juban | 056210 | Tughan | 056210027 | Construction of Day Care Center | 1 | 771662 | 486531 | 285131 | 486531 | 2/3 | 162036.75 | 648567.75 | 486531 | 162036.75 | 100% | 100% | 56.83% | 84.05% | 100% | 2008-05-15 | not conducted | 2008-10-01 | 2008-11-25 | no data | 55 | 288 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Abucay | 056213002 | Construction of Water System Level 2 | 1 | 1480633 | 971800 | 508833 | 916136 |  | 137335.2 | 1053471.2 | 916136 | 137335.2 | 100% | 100% | 26.99% | 71.15% | 100% | 2008-07-11 | not conducted | 2009-01-26 | 2009-06-01 | no data | 126 | 152 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Banuyo | 056213004 | Construction of Drainage System | 1 | 1534928 | 1464600 | 70328 | 1464600 |  | 52000 | 1516600 | 1464600 | 52000 | 100% | 100% | 73.94% | 98.81% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 320 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Binanuahan | 056213007 | Construction of Learning and Training Center | 1 | 941292 | 807200 | 134092 | 807200 |  | 51000 | 858200 | 807200 | 51000 | 100% | 100% | 38.03% | 91.17% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 50 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Cabiguan | 056213009 | Concreting of Pathway | 1 | 1256779 | 1181900 | 74879 | 1181900 |  | 77726 | 1259626 | 1181900 | 77726 | 100% | 100% | 103.8% | 100.2% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 303 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Calongay | 056213011 | Construction of Irrigation | 1 | 3128400 | 1946200 | 1182200 | 1946200 | 2/3 | 665058.71 | 2611258.71 | 1946200 | 665058.71 | 100% | 100% | 56.26% | 83.47% | 100% | 2007-08-23 | not conducted | 2008-04-08 | 2009-03-25 | no data | 351 | 277 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Catamlangan | 056213013 | Concreting of Pathway | 1 | 867810 | 800700 | 67110 | 793560 |  | 40000 | 833560 | 793560 | 40000 | 100% | 100% | 59.6% | 96.05% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 114 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Comapo-capo | 056213014 | Construction of Water System Level 2 | 1 | 977561 | 829400 | 148161 | 829400 | 0.33333 | 156525.71 | 985925.71 | 829400 | 156525.71 | 100% | 100% | 105.6% | 100.9% | 100% | 2007-08-23 | not conducted | 2008-04-12 | 2009-05-25 | no data | 408 | 144 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Danlog | 056213015 | Construction of Water System Level 2 | 1 | 1028215 | 860600 | 167615 | 860600 | 2/3 | 162960.5 | 1023560.5 | 860600 | 162960.5 | 100% | 100% | 97.22% | 99.55% | 100% | 2007-08-23 | not conducted | 2008-04-14 | 2008-12-15 | no data | 245 | 157 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Danlog | 056213015 | Construction of Duplex Type Building | 1 | 1189580 | 1137000 | 52580 | 1083800 |  | 41000 | 1124800 | 1083800 | 41000 | 100% | 100% | 77.98% | 94.55% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 144 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Del Rosario | 056213018 | Construction of Water System Level 2 | 1 | 1886533 | 1390600 | 495933 | 1251540 | 1/3 | 91024 | 1342564 | 1251540 | 91024 | 100% | 100% | 18.35% | 71.17% | 100% | 2008-07-11 | not conducted | 2008-11-20 | 2009-04-30 | no data | 161 | 276 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Esmerada | 056213019 | Construction of Water System Level 2 | 1 | 948640 | 796400 | 152240 | 796400 | 2/3 | 79260 | 875660 | 796400 | 79260 | 100% | 100% | 52.06% | 92.31% | 100% | 2007-08-23 | not conducted | 2008-04-08 | 2008-12-15 | no data | 251 | 79 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Esmerada | 056213019 | Construction of Day Care Center | 1 | 789257 | 722900 | 66357 | 722900 |  | 45000 | 767900 | 722900 | 45000 | 100% | 100% | 67.82% | 97.29% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 429 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Esperanza | 056213019 | Construction of Water System Level 2 | 1 | 1205270 | 1035660 | 169610 | 932094 | 2/3 | 208620 | 1140714 | 932094 | 208620 | 100% | 100% | 123% | 94.64% | 100% | 2007-08-23 | not conducted | 2008-03-03 | 2008-12-15 | no data | 287 | 247 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Esperanza | 056213019 | Rehab/Improvement of Farm to Market Road | 1 | 1475959 | 1060600 | 415359 | 1043804.65 | 1/3 | 76374.5 | 1120179.15 | 1043804.65 | 76374.5 | 100% | 100% | 18.39% | 75.9% | 100% | 2008-07-11 | not conducted | 2008-10-20 | 2009-04-30 | no data | 192 | 79 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Ginablan | 056213022 | Rehab/Improvement of Farm to Market Road | 1 | 3661100 | 2733700 | 927400 | 2733700 | 2/3 | 62500 | 2796200 | 2733700 | 62500 | 100% | 100% | 6.739% | 76.38% | 100% | 2007-08-23 | not conducted | 2008-02-15 | 2009-05-25 | no data | 465 | 330 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Ginablan | 056213022 | Construction of Day Care Center | 1 | 770078 | 685400 | 84678 | 685400 |  | 77000 | 762400 | 685400 | 77000 | 100% | 100% | 90.93% | 99% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 247 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Guiron | 056213021 | Construction of Health Center | 1 | 752481 | 686246 | 66235 | 686246 |  | 51000 | 737246 | 686246 | 51000 | 100% | 100% | 77% | 97.98% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 330 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Inang | 056213023 | Construction of Health Center | 1 | 754616 | 687746 | 66870 | 687746 |  | 52000 | 739746 | 687746 | 52000 | 100% | 100% | 77.76% | 98.03% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 126 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Inapugan | 056213024 | Construction of Water System Level 2 | 1 | 1655596 | 1310700 | 344896 | 1310610 |  | 168881 | 1479491 | 1310610 | 168881 | 100% | 100% | 48.97% | 89.36% | 100% | 2008-07-11 | not conducted | 2008-11-15 | 2009-04-30 | no data | 166 | 338 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Lipason | 056213027 | Rehab/Improvement of Farm to Market Road | 1 | 2925096 | 2193900 | 731196 | 2193900 |  | 60435 | 2254335 | 2193900 | 60435 | 100% | 100% | 8.265% | 77.07% | 100% | 2008-07-11 | not conducted | 2008-11-15 | 2009-04-30 | no data | 166 | 53 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Lipason | 056213027 | Construction of Health Center | 1 | 788671 | 719600 | 69071 | 719600 |  | 62979.5 | 782579.5 | 719600 | 62979.5 | 100% | 100% | 91.18% | 99.23% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 53 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Lubiano | 056213025 | Construction of Water System Level 2 | 1 | 1432081 |  | 1432081 | 0 |  | 10000 | 5000 | 0 | 5000 | #DIV/0! | 50% | 0.6983% | 0.3491% | 100% | 2008-12-20 | 2009-01-28 | 2009-05-18 | 2009-11-30 | no data | 196 | 125 | completed | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Lumbang | 056213030 | Rehab/Improvement of Farm to Market Road | 1 | 2576560 | 1924700 | 651860 | 1924700 | 1/3 | 74543.5 | 1999243.5 | 1924700 | 74543.5 | 100% | 100% | 11.44% | 77.59% | 100% | 2008-07-11 | not conducted | 2008-11-15 | 2009-04-30 | no data | 166 | 143 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Lungib | 056213029 | Construction of Water System Level 2 | 1 | 1268112 | 1091624 | 176488 | 1083991.6 | 2/3 | 195855.5 | 1279847.1 | 1083991.6 | 195855.5 | 100% | 100% | 111% | 100.9% | 100% | 2007-08-23 | not conducted | 2008-06-02 | 2009-03-25 | no data | 296 | 350 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Malbog | 056213032 | Construction of Irrigation | 1 | 1254872 | 1153500 | 101372 | 1153500 |  | 64000 | 1217500 | 1153500 | 64000 | 100% | 100% | 63.13% | 97.02% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 324 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Marifosque | 056213033 | Construction of Resource Learning Center | 1 | 875820 | 742700 | 133120 | 742700 | 2/3 | 164957.5 | 907657.5 | 742700 | 164957.5 | 100% | 100% | 123.9% | 103.6% | 100% | 2007-08-23 | not conducted | 2008-05-15 | 2009-03-25 | no data | 314 | 353 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Mercedes | 056213034 | Improvement of Farm to Market Road | 1 | 1516589 | 1243516 | 273073 | 1235516.2 | 0.33333 | 313481.5 | 1548997.7 | 1235516.2 | 313481.5 | 100% | 100% | 114.8% | 102.1% | 100% | 2007-08-23 | not conducted | 2008-04-26 | 2008-12-15 | no data | 233 | 139 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Mercedes | 056213034 | Construction of Health Center | 1 | 786671 | 719600 | 67071 | 719600 |  | 35000 | 754600 | 719600 | 35000 | 100% | 100% | 52.18% | 95.92% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 353 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Migabod | 056213035 | Construction of Water System Level 2 | 1 | 842303 | 775300 | 67003 | 775300 |  | 51000 | 826300 | 775300 | 51000 | 100% | 100% | 76.12% | 98.1% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 139 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Palanas | 056213037 | Construction of Water System Level 2 | 1 | 852250 | 700000 | 152250 | 630000 | 2/3 | 178420.71 | 808420.71 | 630000 | 178420.71 | 100% | 100% | 117.2% | 94.86% | 100% | 2007-08-23 | not conducted | 2008-05-15 | 2009-03-25 | no data | 314 | 200 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Pangpang | 056213038 | Construction of Water System Level 2 | 1 | 1615391 | 1539700 | 75691 | 1539700 |  | 69257 | 1608957 | 1539700 | 69257 | 100% | 100% | 91.5% | 99.6% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 124 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Pineda | 056213040 | Improvement of Farm to Market Road | 1 | 3064608 | 1986900 | 1077708 | 1976900 | 2/3 | 90480 | 2067380 | 1976900 | 90480 | 100% | 100% | 8.396% | 67.46% | 100% | 2007-08-23 | not conducted | 2008-04-14 | 2009-08-30 | no data | 503 | 167 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Poctol | 056213042 | Construction of Water System Level 2 | 1 | 882743 | 733300 | 149443 | 733300 | 0.33333 | 179022.66 | 912322.66 | 733300 | 179022.66 | 100% | 100% | 119.8% | 103.4% | 100% | 2007-08-23 | not conducted | 2008-04-03 | 2008-12-15 | no data | 256 | 62 | On-going | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Pudo | 056213043 | Construction of Water System Level 2 | 1 | 1827914 | 1321800 | 506114 | 1321800 |  | 52070 | 1373870 | 1321800 | 52070 | 100% | 100% | 10.29% | 75.16% | 100% | 2008-07-11 | not conducted | 2008-12-05 | 2009-02-05 | no data | 62 | 167 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Pudo | 056213043 | Construction of Day Care Center | 1 | 789245 | 724400 | 64845 | 698212 |  | 51000 | 749212 | 698212 | 51000 | 100% | 100% | 78.65% | 94.93% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-06-25 | no data | 91 | 167 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Putiao | 056213044 | Construction of Resource Center | 1 | 773470 | 530000 | 243470 | 530000 | 1/3 | 215266 | 745266 | 530000 | 215266 | 100% | 100% | 88.42% | 96.35% | 100% | 2008-07-11 | not conducted | 2008-11-20 | 2009-01-20 | no data | 61 | 62 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Sacnangan | 056213045 | Rehab/Improvement of Farm to Market Road | 1 | 1192445 | 877800 | 314645 | 874383.01 | 1/3 | 46000 | 920383.01 | 874383.01 | 46000 | 100% | 100% | 14.62% | 77.18% | 100% | 2008-07-11 | not conducted | 2008-10-15 | 2009-04-30 | no data | 197 | 394 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Salvacion | 056213046 | Construction of Water System Level 2 | 1 | 1522602 | 1082800 | 439802 | 1082800 |  | 45000 | 1127800 | 1082800 | 45000 | 100% | 100% | 10.23% | 74.07% | 100% | 2008-07-11 | not conducted | 2009-01-26 | 2009-09-30 | no data | 247 | 154 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | Salvacion | 056213046 | Construction of Rice and Corn Mill | 1 | 1056901 | 980600 | 76301 | 980600 |  | 53884 | 1034484 | 980600 | 53884 | 100% | 100% | 70.62% | 97.88% | 100% | 2008-12-20 | 2009-01-28 | 2009-03-26 | 2009-05-25 | no data | 60 | 154 |  | 1
V | 05 | Sorsogon | 0562 | Pilar | 056213 | San Rafael | 056213050 | Rehab/Improvement of Farm to Market Road | 1 | 2696570 | 2035300 | 661270 | 1424710 |  | 118220 | 1542930 | 1424710 | 118220 | 100% | 100% | 17.88% | 57.22% | 100% | 2008-07-11 | not conducted | 2009-01-07 | 2009-11-30 | no data | 327 | 212 | completed | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Agbatuan | 061904001 | Road Upgrading with Spot Concreting | 1 | 1065028.25 | 881847.25 | 183181 | 881847.25 | Last Tranche | 194697 | 1076544.25 | 881847.25 | 194697 | 100% | 100% | 106.3% | 101.1% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-20 | 2007-06-07 | no data | 199 | 129 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Aglalana | 061904002 | Water System Level II | 1 | 1678014.91 | 1399689.78 | 278325.13 | 1399689.78 | Last Tranche | 298856.8 | 1698546.58 | 1399689.78 | 298856.8 | 100% | 100% | 107.4% | 101.2% | 100% | 2005-04-25 | 2005-06-08 | 2005-08-18 | 2006-03-15 | 2006-05-29 | 209 | 95 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Aglanot | 061904003 | Day Care Center | 1 | 923231 | 728729 | 194502 | 486011.9 | 1st Tranche | 175986.78 | 661998.68 | 486011.9 | 175986.78 | 100% | 100% | 90.48% | 71.7% | 100% | 2007-08-15 | no data | 2008-09-02 | 2009-04-30 | n/a | 240 | 129 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Agsirab | 061904006 | Road Upgrading with Spot Concreting | 1 | 1719247.25 | 1519133.25 | 200114 | 1367219.93 | 1st Tranche | 137690 | 1504909.93 | 1367219.93 | 137690 | 100% | 100% | 68.81% | 87.53% | 100% | 2006-07-04 | 2006-08-15 | 2006-12-04 | 2009-09-30 | n/a | 1031 | 209 | completed as built | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Alipaciawan | 061904007 | 2 Classroom Elementary School Building | 1 | 1107176 | 899490 | 207686 | 899490 | Last Tranche | 203040 | 1102530 | 899490 | 203040 | 100% | 100% | 97.76% | 99.58% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-27 | 2007-07-01 | no data | 216 | 108 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Bayog | 061904009 | Health Station | 1 | 624244.31 | 564876.51 | 59367.8 | 564876.51 | Last Tranche | 77087 | 641963.51 | 564876.51 | 77087 | 100% | 100% | 129.8% | 102.8% | 100% | 2005-04-25 | 2005-06-08 | 2005-07-30 | 2006-04-01 | 2006-07-03 | 245 | 44 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Calapawan | 061904011 | Road Upgrading | 1 | 1756691.5 | 1569677.25 | 187014.25 | 1501837.25 | Last Tranche | 156513.5 | 1658350.75 | 1501837.25 | 156513.5 | 100% | 100% | 83.69% | 94.4% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-20 | 2007-10-01 | no data | 315 | 152 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Codingle | 061904016 | Health Station | 1 | 718682.08 | 502802.08 | 215880 | 502802.08 | Last Tranche | 255219.67 | 758021.75 | 502802.08 | 255219.67 | 100% | 100% | 118.2% | 105.5% | 100% | 2005-04-25 | 2005-06-08 | 2005-08-15 | 2006-02-28 | 2006-06-22 | 197 | 257 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Codingle | 061904016 | 3 CL School Building | 1 | 1761000 | 1205648.81 | 555351.19 | 1085083.93 | 1st Tranche | 568628.58 | 1653712.51 | 1085083.93 | 568628.58 | 100% | 100% | 102.4% | 93.91% | 100% | 2007-08-15 | no data | 2007-12-17 | 2009-02-28 | n/a | 439 | 262 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Cubi | 061904012 | Road Upgrading | 1 | 1109258.25 | 973798.25 | 135460 | 973798.25 | Last Tranche | 126826.6 | 1100624.85 | 973798.25 | 126826.6 | 100% | 100% | 93.63% | 99.22% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-13 | 2007-04-14 | no data | 152 | 125 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Gibato | 061904015 | Electrification | 1 | 1885385.25 | 1468467.25 | 416918 | 1468467.25 | Last Tranche | 401247.94 | 1869715.19 | 1468467.25 | 401247.94 | 100% | 100% | 96.24% | 99.17% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-23 | 2007-02-28 | no data | 97 | 424 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Guinotos | 061904017 | Health Station | 1 | 598351.42 | 489436.22 | 108915.2 | 489436.22 | Last Tranche | 130400 | 619836.22 | 489436.22 | 130400 | 100% | 100% | 119.7% | 103.6% | 100% | 2005-04-25 | 2005-06-08 | 2005-09-23 | 2006-03-10 | 2006-03-24 | 168 | 147 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Guinotos | 061904017 | Hanging Bridge | 1 | 2314600 | 1961634.81 | 352965.19 | 1961634.81 | 1st Tranche | 300084.19 | 2261719 | 1961634.81 | 300084.19 | 100% | 100% | 85.02% | 97.72% | 100% | 2007-08-15 | no data | 2008-04-07 | 2009-09-30 | n/a | 541 | 153 | completed as built | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Jambad | 061904018 | Road Upgrading | 1 | 1541851.25 | 1379742.25 | 162109 | 1379742.25 | Last Tranche | 162372 | 1542114.25 | 1379742.25 | 162372 | 100% | 100% | 100.2% | 100% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-20 | 2007-05-25 | no data | 186 | 121 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Jambad | 061904018 | Road Improvement | 1 | 825000 | 701946.62 | 123053.38 | 631751.96 | 1st Tranche | 211551 | 654036.3015 | 631751.96 | 22284.3415 | 100% | 10.53% | 171.9% | 79.28% | 100% | 2007-08-15 | no data | 2008-05-27 | 2009-08-30 | no data | 460 | 125 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Janguslob | 061904019 | Hanging Foot Bridge | 1 | 2095854.78 | 1996082.78 | 99772 | 1996082.78 | Last Tranche | 124106.75 | 2120189.53 | 1996082.78 | 124106.75 | 100% | 100% | 124.4% | 101.2% | 100% | 2005-04-25 | 2005-06-08 | 2005-09-12 | 2006-05-08 | 2006-05-08 | 238 | 182 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Lawaan | 061904021 | Hanging Bridge | 1 | 2316853 | 2047821.09 | 269031.91 | 1934403.97 | 1st Tranche | 164506.4343 | 339820.2771 | 257567.06 | 82253.2171 | 13.32% | 50% | 61.15% | 14.67% | 100% | 2007-08-15 | no data | 2008-07-15 | 2009-09-30 | n/a | 442 | 339 | completed as built | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Nagsulang | 061904024 | Road Upgrading | 1 | 1134276.25 | 976217.25 | 158059 | 976217.25 | Last Tranche | 224885.34 | 1126809.92 | 976217.25 | 150592.67 | 100% | 66.96% | 142.3% | 99.34% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-15 | 2007-06-01 | no data | 198 | 226 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Ongol Ilawod | 061904026 | Hanging Foot Bridge | 1 | 1995067.17 | 1893715.17 | 101352 | 1893715.17 | Last Tranche | 142182.09 | 2035897.26 | 1893715.17 | 142182.09 | 100% | 100% | 140.3% | 102% | 100% | 2005-04-25 | 2005-06-08 | 2005-09-15 | 2006-04-30 | 2006-05-05 | 227 | 120 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Sibariwan | 061904033 | Road Improvement | 1 | 2032492 | 1639698 | 392794 | 1311758.4 | 1st Tranche | 153629.1162 | 1388572.9581 | 1311758.4 | 76814.5581 | 100% | 50% | 39.11% | 68.32% | 100% | 2007-08-15 | no data | 2008-07-02 | 2009-08-30 | no data | 424 | 279 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Tamulalod | 061904034 | Water System Level II | 1 | 1349442.5 | 1210052.54 | 139389.96 | 1210052.53 | Last Tranche | 147713.71 | 1357766.24 | 1210052.53 | 147713.71 | 100% | 100% | 106% | 100.6% | 100% | 2005-04-25 | 2005-06-08 | 2005-08-15 | 2006-02-28 | 2006-03-16 | 197 | 142 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Taslan | 061904035 | Road Upgrading | 1 | 1075335.08 | 1011166.08 | 64169 | 1011166.08 | Last Tranche | 67816.75 | 1078982.83 | 1011166.08 | 67816.75 | 100% | 100% | 105.7% | 100.3% | 100% | 2005-04-25 | 2005-06-08 | 2005-09-05 | 2006-03-10 | 2006-06-09 | 186 | 146 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Taslan | 061904035 | 2 CL School Building | 1 | 1256100 | 1043092.45 | 213007.55 | 938783.21 | 1st Tranche | 378833.26 | 1317616.47 | 938783.21 | 378833.26 | 100% | 100% | 177.8% | 104.9% | 100% | 2007-08-15 | no data | 2008-05-27 | 2009-02-28 | n/a | 277 | 146 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Tina | 061904036 | Solar Dryer with Shed House | 1 | 736431.75 | 639174.78 | 97256.97 | 639174.78 | Last Tranche | 95746.49 | 734921.27 | 639174.78 | 95746.49 | 100% | 100% | 98.45% | 99.79% | 100% | 2005-04-25 | 2005-06-08 | 2005-08-22 | 2006-02-28 | 2006-03-10 | 190 | 285 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Tinaytayan | 061904037 | Travelling Rice Mill | 1 | 639534.61 | 193004.06 | 446530.55 | 193004.06 | Last Tranche | 450170.02 | 643174.08 | 193004.06 | 450170.02 | 100% | 100% | 100.8% | 100.6% | 100% | 2005-04-25 | 2005-06-08 | 2005-10-02 | 2006-02-28 | 2006-04-18 | 149 | 262 |  | 1
VI | 06 | Capiz | 0619 | Dumarao | 061904 | Traciano | 061904038 | Road Upgrading | 1 | 1554353.75 | 231627.25 | 1322726.5 | 185301.8 | 1st Tranche | 92351 | 277652.8 | 185301.8 | 92351 | 100% | 100% | 6.982% | 17.86% | 100% | 2006-07-04 | 2006-08-15 | 2006-11-27 | 2009-09-30 | n/a | 1038 | 197 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agambolong | 061906001 | Slope Protection w/ Road Concreting | 1 | 700000 | 609153 | 90847 | 548237.7 |  | 105514.43 | 653752.13 | 548237.7 | 105514.43 | 100% | 100% | 116.1% | 93.39% | 100% | 2009-02-05 | no data | 2009-04-20 | 2009-06-30 | no data | 71 | 2282 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agambulong | 061906001 | Road Rehabilitation | 1 | 595636 | 156903.39 | 438732.61 | 156903.39 | 3rd Tranche | 449249.65 | 606153.04 | 156903.39 | 449249.65 | 100% | 100% | 102.4% | 101.8% | 100% | 2004-01-17 | 2004-02-24 | 2004-06-01 | 2005-01-25 | 2005-01-30 | 238 | 448 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agambulong | 061906001 | Road Construction | 1 | 951971.7 | 225737.34 | 726234.36 | 180589.87 | 1st Tranche | 500000 | 430589.87 | 180589.87 | 250000 | 100% | 50% | 68.85% | 45.23% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-03-01 | no data | 472 | 331 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agbun-od | 061906002 | Road Concreting | 1 | 611400 | 523896.5 | 87503.5 | 471506.85 | 1st | 104103.2 | 575610.05 | 471506.85 | 104103.2 | 100% | 100% | 119% | 94.15% | 100% | 2009-02-05 | no data | 2009-04-20 | 2009-06-30 | no data | 71 | 158 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agcagay | 061906003 | Road Upgrading | 1 | 1063292.81 | 774723.03 | 288569.78 | 724473.03 | 2nd Tranche | 260532.91 | 866949.56 | 724473.03 | 142476.53 | 100% | 54.69% | 90.28% | 81.53% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-03-05 | 2008-03-10 | 476 | 267 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agcagay | 061906003 | Road Improvement w/ spot concreting | 1 | 451000 | 381218.5 | 69781.5 | 304974.8 | 1st | 58962.97 | 363937.77 | 304974.8 | 58962.97 | 100% | 100% | 84.5% | 80.7% | 100% | 2009-02-05 | no data | 2009-05-16 | 2009-08-31 | no data | 107 | 268 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Aglibacao | 061906004 | Road Regravelling | 1 | 310217 | 152297 | 157920 | 152297 | 3rd Tranche | 177533.5 | 329830.5 | 152297 | 177533.5 | 100% | 100% | 112.4% | 106.3% | 100% | 2004-01-17 | 2004-02-24 | 2004-04-26 | 2005-01-25 | 2005-04-30 | 274 | 106 |  | 1
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Aglibacao | 061906004 | Communal Irrigation | 1 | 688527.71 | 498048.06 | 190479.65 | 498048.05 | 2nd Tranche | 188097.42 | 677261.97 | 498048.05 | 179213.92 | 100% | 95.28% | 98.75% | 98.36% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-02-25 | 2008-02-27 | 467 | 106 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Aglibacao | 061906004 | Const. of Day Care Center | 1 | 605700 | 514086.5 | 91613.5 | 462677.85 | 1st | 89976.7 | 552654.55 | 462677.85 | 89976.7 | 100% | 100% | 98.21% | 91.24% | 100% | 2009-02-05 | no data | 2009-05-08 | 2009-06-30 | no data | 53 | 118 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agloloway | 061906005 | Road Upgrading/Concreting | 1 | 2279198.48 | 2050013.58 | 229184.9 | 2050013.58 | 3rd Tranche | 247880.53 | 2297894.11 | 2050013.58 | 247880.53 | 100% | 100% | 108.2% | 100.8% | 100% | 2005-07-05 | 2005-08-16 | 2005-11-23 | 2008-05-01 | no data | 890 | 119 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Agloloway | 061906005 | Const. of 1-CL School Building | 1 | 650000 | 559153 | 90847 | 503237.7 |  | 109202.9 | 612440.6 | 503237.7 | 109202.9 | 100% | 100% | 120.2% | 94.22% | 100% | 2009-02-05 | no data | 2009-05-04 | 2009-06-30 | no data | 57 | 138 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Bayebaye | 061906006 | Road Regravelling | 1 | 425140.5 | 319380.5 | 105760 | 319380.5 | 3rd Tranche | 133604.5 | 452985 | 319380.5 | 133604.5 | 100% | 100% | 126.3% | 106.5% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-24 | 2004-12-30 | 2005-01-30 | 220 | 311 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Baye-baye | 061906006 | Road Improvement w/ Intermittent Const. of PCPP | 1 | 590000 | 503172.5 | 86827.5 | 452855.25 | 1st | 101616.3 | 554471.55 | 452855.25 | 101616.3 | 100% | 100% | 117% | 93.98% | 100% | 2009-02-05 | no data | 2009-04-18 | 2009-06-30 | no data | 73 | 1654 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Caridad | 061906007 | Road Rehabilitation | 1 | 1025922 | 722674 | 303248 | 722674 | 3rd Tranche | 337367 | 1060041 | 722674 | 337367 | 100% | 100% | 111.3% | 103.3% | 100% | 2004-01-17 | 2004-02-24 | 2004-06-25 | 2005-06-30 | 2005-10-12 | 370 | 127 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Caridad | 061906007 | Communal Irrigation System | 1 | 1418152.02 | 1118049.94 | 300102.08 | 1118049.94 | 3rd Tranche | 339675.03 | 1559510.49 | 1118049.94 | 441460.55 | 100% | 130% | 113.2% | 110% | 100% | 2005-07-05 | 2005-08-16 | 2005-10-31 | 2006-06-30 | 2006-10-30 | 242 | 127 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Caridad | 061906007 | Road Concreting | 1 | 566400 | 481490.5 | 84909.5 | 481490.5 | 1st | 84255.5 | 565746 | 481490.5 | 84255.5 | 100% | 100% | 99.23% | 99.88% | 100% | 2009-02-05 | no data | 2009-05-04 | 2009-06-30 | no data | 57 | 171 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Esperanza | 061906008 | Post Harvest Facilities | 1 | 2889506.92 | 1999200.89 | 890306.03 | 1999200.89 | 2nd Tranche | 251000 | 2250200.89 | 1999200.89 | 251000 | 100% | 100% | 28.19% | 77.87% | 100% | 2006-07-06 | 2006-07-14 | 2006-10-30 | 2008-05-01 | no data | 549 | 161 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Esperanza | 061906008 | Const. of Day Care Center | 1 | 605700 | 513486.5 | 92213.5 | 460078.1 | 1st | 109118.1 | 569196.2 | 460078.1 | 109118.1 | 100% | 100% | 118.3% | 93.97% | 100% | 2009-02-05 | no data | 2009-04-27 | 2009-06-30 | no data | 64 | 172 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Fe | 061906009 | Road Rehabilitation | 1 | 835680 | 339642.2 | 496037.8 | 339642.2 | 3rd Tranche | 500904.9 | 840547.1 | 339642.2 | 500904.9 | 100% | 100% | 101% | 100.6% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-28 | 2004-11-30 | 2005-01-15 | 186 | 98 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Fe | 061906009 | Communal Irrigation | 1 | 740648.46 | 562257.54 | 178390.92 | 562257.54 | 2nd Tranche | 36625 | 598882.54 | 562257.54 | 36625 | 100% | 100% | 20.53% | 80.86% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-02-29 | 2008-03-03 | 471 | 108 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Fe | 061906009 | Rehab. Of pump driven Comm. Irrigation | 1 | 578000 | 494732.5 | 83267.5 | 443920.75 |  | 133482.38 | 577403.13 | 443920.75 | 133482.38 | 100% | 100% | 160.3% | 99.9% | 100% | 2009-02-05 | no data | 2009-05-04 | 2009-07-31 | no data | 88 | 150 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Ganzon | 061906010 | Road Rehabilitation | 1 | 3131476.89 | 2914576.3 | 216900.59 | 2914576.3 | 3rd Tranche | 235490 | 3150066.3 | 2914576.3 | 235490 | 100% | 100% | 108.6% | 100.6% | 100% | 2004-01-17 | 2004-02-24 | 2004-06-29 | 2006-06-30 | 2006-08-23 | 731 | 116 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Guintas | 061906011 | Road Regravelling | 1 | 875093.03 | 710937.63 | 164155.4 | 710937.63 | 3rd Tranche | 207347.18 | 918284.81 | 710937.63 | 207347.18 | 100% | 100% | 126.3% | 104.9% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-03 | 2005-01-20 | 2005-01-25 | 262 | 230 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Guintas - C2 | 061906011 | Road Improvement w/ Intermittent Const. of PCCP | 2 | 1155000 | 1018076.5 | 136923.5 | 712653.55 |  | 135232.65 | 847886.2 | 712653.55 | 135232.65 | 100% | 100% | 98.77% | 73.41% | 100% | 2009-02-05 | no data | 2009-04-15 | 2009-08-31 | no data | 138 | 310 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Igang | 061906012 | Road Upgrading | 1 | 1135467.95 | 874147.66 | 261320.29 | 699318.13 | 1st Tranche | 65450 | 764768.13 | 699318.13 | 65450 | 100% | 100% | 25.05% | 67.35% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-03-01 | no data | 472 | 106 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Igang | 061906012 | Road Improvement w/ spot concreting | 1 | 670000 | 590264.5 | 79735.5 | 472211.6 | 1st | 106251.1 | 578462.7 | 472211.6 | 106251.1 | 100% | 100% | 133.3% | 86.34% | 100% | 2009-02-05 | no data | 2009-04-07 | 2009-08-31 | no data | 146 | 503 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Jaena Norte | 061906013 | Road Upgrading with Spot Concreting | 1 | 741670.8 | 524594.49 | 217076.31 | 419675.59 | 1st Tranche | 123363.63 | 543039.22 | 419675.59 | 123363.63 | 100% | 100% | 56.83% | 73.22% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2006-12-31 | 2006-12-31 | 46 | 402 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Jaena Sur | 061906014 | Road Upgrading | 1 | 935371.95 | 681629.93 | 253742.02 | 681629.93 | 1st Tranche | 52713.4 | 734343.33 | 681629.93 | 52713.4 | 100% | 100% | 20.77% | 78.51% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-02-29 | 2008-03-14 | 471 | 180 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Jaena Sur - C2 | 061906014 | Road Improvement w/ Spot concreting | 2 | 1050000 | 914968.5 | 135031.5 | 731974.8 |  | 149181.05 | 881155.85 | 731974.8 | 149181.05 | 100% | 100% | 110.5% | 83.92% | 100% | 2009-02-05 | no data | 2009-04-15 | 2009-08-31 | no data | 138 | 836 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Jagnaya | 061906015 | Road Rehabilitation | 1 | 525670 | 350554 | 175116 | 350554 | 3rd Tranche | 196981 | 547535 | 350554 | 196981 | 100% | 100% | 112.5% | 104.2% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-19 | 2005-01-25 | 2005-02-10 | 251 | 242 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Jagnaya | 061906015 | Const. of Drainage Canal | 1 | 590000 | 498396.5 | 91603.5 | 448556.85 | 1st | 90207.18 | 538764.03 | 448556.85 | 90207.18 | 100% | 100% | 98.48% | 91.32% | 100% | 2009-02-05 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 1175 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | La Paz | 061906016 | Road Concreting of FMR | 1 | 565600 | 481108.5 | 84491.5 | 432997.6 | 1st | 92165.33 | 525162.93 | 432997.6 | 92165.33 | 100% | 100% | 109.1% | 92.85% | 100% | 2009-02-05 | no data | 2009-03-30 | 2009-06-30 | no data | 92 | 1226 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Lapaz | 061906016 | Road Construction | 1 | 925319.75 | 674106.79 | 251212.96 | 673806.79 | 1st Tranche | 162957.96 | 738560.38 | 673806.79 | 64753.59 | 100% | 39.74% | 64.87% | 79.82% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2007-06-01 | no data | 198 | 224 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Linambasan | 061906017 | Road Regravelling | 1 | 388081.5 | 296771.5 | 91310 | 296771.5 | 3rd Tranche | 108590 | 405361.5 | 296771.5 | 108590 | 100% | 100% | 118.9% | 104.5% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-01 | 2004-12-30 | 2005-01-27 | 243 | 254 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Linambasan | 061906017 | Const. of Brgy. Health Station | 1 | 620000 | 104401.5 | 515598.5 | 93961.35 | 1st | 206807.95 | 300769.3 | 93961.35 | 206807.95 | 100% | 100% | 40.11% | 48.51% | 100% | 2009-02-05 | no data | 2009-04-06 | 2009-06-30 | no data | 85 | 306 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Lucero | 061906018 | Road Improvement | 1 | 597250 | 527920.5 | 69329.5 | 512013 | 1st | 72425.62 | 584438.62 | 512013 | 72425.62 | 100% | 100% | 104.5% | 97.85% | 100% | 2009-02-05 | no data | 2009-05-19 | 2009-08-31 | no data | 104 | 552 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Lucero - C2 | 061906018 | Road Upgrading/Concreting | 2 | 1955518.77 | 1611599.48 | 343919.29 | 1610454.01 | 1st Tranche | 362919.29 | 1951425.51 | 1610454.01 | 340971.5 | 100% | 93.95% | 105.5% | 99.79% | 100% | 2005-07-05 | 2005-08-16 | 2005-11-16 | 2007-05-01 | no data | 531 | 413 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Maantol | 061906019 | Road Regravelling | 1 | 804249 | 675231 | 129018 | 675231 | 3rd Tranche | 171516 | 846747 | 675231 | 171516 | 100% | 100% | 132.9% | 105.3% | 100% | 2004-01-17 | 2004-02-24 | 2004-06-07 | 2005-03-15 | 2005-04-30 | 281 | 186 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Maantol | 061906019 | Health Station | 1 | 672647.19 | 455040.29 | 217606.9 | 455040.29 | 3rd Tranche | 235812.9 | 690853.19 | 455040.29 | 235812.9 | 100% | 100% | 108.4% | 102.7% | 100% | 2005-07-05 | 2005-08-16 | 2005-11-07 | 2006-05-12 | 2006-05-13 | 186 | 186 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Masgrau | 061906020 | Hanging Bridge | 1 | 787388.4 | 660748.4 | 126640 | 660748.4 | 3rd Tranche | 132385.5 | 793133.9 | 660748.4 | 132385.5 | 100% | 100% | 104.5% | 100.7% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-12 | 2005-01-25 | 2005-01-29 | 258 | 47 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Masgrau | 061906020 | Road Construction of Farm to Market Road | 1 | 550000 | 496764.5 | 53235.5 | 397411.6 |  | 30532.83 | 427944.43 | 397411.6 | 30532.83 | 100% | 100% | 57.35% | 77.81% | 100% | 2009-02-05 | no data | 2009-05-04 | 2009-08-31 | no data | 119 | 53 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Milan | 061906021 | Road Improvement of FMR w/ 1 unit RCPC | 1 | 820000 | 750860.5 | 69139.5 | 600688.4 | 1st | 64780.75 | 665469.15 | 600688.4 | 64780.75 | 100% | 100% | 93.7% | 81.15% | 100% | 2009-02-05 | no data | 2009-04-07 | 2009-08-31 | no data | 146 | 310 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Molet | 061906022 | Road Rehabilitation | 1 | 755200.5 | 631400.5 | 123800 | 631400.5 | 3rd Tranche | 171658.5 | 803059 | 631400.5 | 171658.5 | 100% | 100% | 138.7% | 106.3% | 100% | 2004-01-17 | 2004-02-24 | 2004-05-01 | 2005-01-25 | 2005-02-05 | 269 | 74 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Molet | 061906022 | Pre & Post Harvest Facilities | 1 | 461040.84 | 342209.56 | 118831.28 | 342209.56 | 100% Tranche | 28000 | 370209.56 | 342209.56 | 28000 | 100% | 100% | 23.56% | 80.3% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2006-12-31 | no data | 46 | 75 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Molet | 061906022 | Const. of Brgy. Health Station | 1 | 620000 | 552262.5 | 67737.5 | 497036.25 | 1st | 66097.95 | 563134.2 | 497036.25 | 66097.95 | 100% | 100% | 97.58% | 90.83% | 100% | 2009-02-05 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 89 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabat | 061906023 | Health Station | 1 | 442997.27 | 293058.3 | 149938.97 | 293058.3 | 3rd Tranche | 158978 | 452036.3 | 293058.3 | 158978 | 100% | 100% | 106% | 102% | 100% | 2004-01-17 | 2004-02-24 | 2004-04-28 | 2005-01-30 | 2005-01-31 | 277 | 302 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabat | 061906023 | Communal Irrigation | 1 | 1139452.3 | 802348.62 | 337103.68 | 764492.19 | 1st Tranche | 69132 | 833624.19 | 764492.19 | 69132 | 100% | 100% | 20.51% | 73.16% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2008-02-01 | 2008-03-06 | 443 | 319 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabuan | 061906024 | Health Station | 1 | 434219.03 | 286344.03 | 147875 | 286344.03 | 3rd Tranche | 203216.97 | 489561 | 286344.03 | 203216.97 | 100% | 100% | 137.4% | 112.7% | 100% | 2004-01-17 | 2004-02-24 | 2004-04-28 | 2005-01-25 | 2005-04-26 | 272 | 270 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabuan | 061906024 | Road Upgrading | 1 | 759072.57 | 551100.26 | 207972.31 | 440880.21 | 1st Tranche | 48997.71 | 489877.92 | 440880.21 | 48997.71 | 100% | 100% | 23.56% | 64.54% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2007-06-01 | 2008-02-26 | 198 | 287 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabuan | 061906024 | Const. of Day Care Center | 1 | 605700 | 513486.5 | 92213.5 | 462137.85 | 1st | 91015.5 | 553153.35 | 462137.85 | 91015.5 | 100% | 100% | 98.7% | 91.32% | 100% | 2009-02-05 | no data | 2009-04-06 | 2009-06-30 | no data | 85 | 306 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Pasol-o | 061906025 | Road Improvement with Spot Concreting of 1.5 km FMR | 1 | 785000 | 711198.5 | 73801.5 | 568958.8 | 1st | 70287.64 | 639246.44 | 568958.8 | 70287.64 | 100% | 100% | 95.24% | 81.43% | 100% | 2009-02-05 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 160 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Poblacion | 061906026 | Water System Level II | 1 | 2645650.33 | 1912793.93 | 732856.4 | 1912793.93 | 3rd Tranche | 733856.4 | 2646650.33 | 1912793.93 | 733856.4 | 100% | 100% | 100.1% | 100% | 100% | 2005-07-05 | 2005-08-16 | 2005-11-08 | 2006-11-30 | 2006-11-23 | 387 | 317 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | San Jose | 061906027 | Road Improvement w/ 1 unit RCP culvert of 2.0 km FMR | 1 | 650000 | 575500.5 | 74499.5 | 460400.4 |  | 61758.62 | 522159.02 | 460400.4 | 61758.62 | 100% | 100% | 82.9% | 80.33% | 100% | 2009-02-05 | no data | 2009-04-06 | 2009-08-31 | no data | 147 | 220 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | San Jose | 061906027 | Road Upgrading/Concreting | 1 | 916875.28 | 761868.38 | 155006.9 | 761868.38 | 3rd Tranche | 153069.4 | 914937.78 | 761868.38 | 153069.4 | 100% | 100% | 98.75% | 99.79% | 100% | 2005-07-05 | 2005-08-16 | 2005-11-09 | 2006-06-30 | 2006-11-24 | 233 | 208 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | San Juan - C2 | 061906028 | Road Improvement w/ Spot Concreting of FMR | 2 | 2270000 | 2170914.5 | 99085.5 | 1736731.6 | 1st | 103131.68 | 1839863.28 | 1736731.6 | 103131.68 | 100% | 100% | 104.1% | 81.05% | 100% | 2009-02-05 | no data | 2009-04-28 | 2009-08-31 | no data | 125 | 200 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | San Vicente | 061906029 | Water System L II | 1 | 683081.25 | 489481.25 | 193600 | 489481.25 | 3rd Tranche | 264132 | 753613.25 | 489481.25 | 264132 | 100% | 100% | 136.4% | 110.3% | 100% | 2004-01-17 | 2004-02-24 | 2004-06-23 | 2004-11-30 | 2005-01-25 | 160 | 226 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | San Vicente | 061906029 | Health Station | 1 | 699488.3 | 489895.83 | 209592.47 | 489895.83 | Last Tranche | 53895 | 543790.83 | 489895.83 | 53895 | 100% | 100% | 25.71% | 77.74% | 100% | 2006-07-06 | 2006-07-14 | 2006-11-15 | 2006-12-31 | no data | 46 | 223 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Sto. Rosario | 061906030 | Road Upgrading/Concreting | 1 | 1322008.3 | 1090634.4 | 231373.9 | 1078549.37 | 1st Tranche | 238772.28 | 1253002.77 | 1078549.37 | 174453.4 | 100% | 73.06% | 103.2% | 94.78% | 100% | 2005-07-05 | 2005-08-16 | 2005-11-09 | 2007-05-01 | no data | 538 | 216 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Jamindan | 061906 | Sto. Rosario | 061906030 | Const. of Day Care Center | 1 | 605700 | 513486.5 | 92213.5 | 462137.85 |  | 93665.95 | 555803.8 | 462137.85 | 93665.95 | 100% | 100% | 101.6% | 91.76% | 100% | 2009-02-05 | no data | 2009-03-30 | 2009-06-30 | no data | 92 | 99 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Alasaging | 061907002 | .68 km. Road Improvrmrnt with overflow | 1 | 753600 | 641700 | 111900 | 577530 | 1st Tranche | 136869.04 | 699930 | 577530 | 122400 | 100% | 89.43% | 122.3% | 92.88% | 100% | 2007-08-01 | no data | 2008-04-07 | 2009-04-30 | n/a | 388 | 133 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Alayunan | 061907003 | Road Upgrading | 1 | 1416267.93 | 489746.04 | 926521.89 | 454771.43 | 2nd Tranche | 936232.81 | 1372314.24 | 454771.43 | 917542.81 | 100% | 98% | 101% | 96.9% | 100% | 2006-07-04 | 2006-08-18 | 2006-11-20 | 2008-06-30 | no data | 588 | 96 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Batabat | 061907005 | 4 unit 4" Portable Water Pump | 1 | 656200 | 560200 | 96000 | 533502 | 1st Tranche | 110596 | 628902 | 533502 | 95400 | 100% | 86.26% | 115.2% | 95.84% | 100% | 2007-08-01 | no data | 2008-08-05 | 2009-04-30 | n/a | 268 | 244 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Bongbongan | 061907006 | Road Upgrading | 1 | 3027195.31 | 2228519.65 | 798675.66 | 2005667.7 | 2nd Tranche | 819931.74 | 2825599.44 | 2005667.7 | 819931.74 | 100% | 100% | 102.7% | 93.34% | 100% | 2005-04-27 | 2005-06-20 | 2005-10-10 | 2006-05-10 | 2006-03-16 | 212 | 208 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Cabungahan | 061907007 | Road Upgrading | 1 | 1197986.82 | 989677.93 | 208308.89 | 989677.93 | Last Tranche | 197966.14 | 1187644.07 | 989677.93 | 197966.14 | 100% | 100% | 95.03% | 99.14% | 100% | 2006-07-04 | 2006-08-18 | 2007-03-16 | 2007-11-30 | no data | 259 | 268 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Duluan | 061907010 | .80 km Road Improvement w/ spot concreting | 1 | 870000 | 755600 | 114400 | 680040 | 1st Tranche | 121205 | 798385 | 680040 | 118345 | 100% | 97.64% | 105.9% | 91.77% | 100% | 2007-08-01 | no data | 2008-04-02 | 2009-04-30 | n/a | 393 | 96 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Guinbi-alan | 061907013 | Road Upgrading | 1 | 1553586.63 | 1274722.36 | 278864.27 | 1239151.91 | 1st Tranche | 284447.9 | 1516591.77 | 1239151.91 | 277439.86 | 100% | 97.54% | 102% | 97.62% | 100% | 2006-07-04 | 2006-08-18 | 2007-02-28 | 2008-06-30 | no data | 488 | 149 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Indayagan | 061907014 | 1.40km Road Improvement | 1 | 766700 | 653200 | 113500 | 522560 | 1st Tranche | 110200 | 592185.19 | 522560 | 69625.19 | 100% | 63.18% | 97.09% | 77.24% | 100% | 2007-08-01 | no data | 2008-03-05 | 2008-10-30 | no data | 239 | 261 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Jebaca | 061907015 | Hanging Foot Bridge | 1 | 1565725.3 | 1435699.18 | 130026.12 | 1292129.26 | 2nd Tranche | 174956.12 | 1467085.38 | 1292129.26 | 174956.12 | 100% | 100% | 134.6% | 93.7% | 100% | 2005-04-27 | 2005-06-20 | 2005-09-05 | 2006-04-26 | 2006-04-27 | 233 | 163 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Maalan | 061907016 | .600km Road Conc. With conc. Side Ditch Canal | 1 | 1410500 | 1224700 | 185800 | 1176195.17 |  | 234439.7 | 1344325.11 | 1176195.17 | 168129.94 | 100% | 71.72% | 126.2% | 95.31% | 100% | 2007-08-01 | no data | 2008-05-02 | 2009-07-30 | no data | 454 | 153 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Manayupit | 061907017 | 3 Classroon School Building | 1 | 1514744.8 | 1346801.96 | 167942.84 | 1297211.45 | 2nd Tranche | 131928.7 | 1424565.56 | 1297211.45 | 127354.11 | 100% | 96.53% | 78.56% | 94.05% | 100% | 2006-07-04 | 2006-08-18 | 2006-11-27 | 2008-02-28 | no data | 458 | 163 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | New Guia | 061907018 | Day Care Center | 1 | 644900 | 447000 | 197900 | 402300 |  | 183891 | 586191 | 402300 | 183891 | 100% | 100% | 92.92% | 90.9% | 100% | 2007-08-01 | no data | 2008-08-05 | 2009-04-30 | n/a | 268 | 22 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Old Guia | 061907020 | Hanging Foot Bridge | 1 | 1965985.58 | 1806255.58 | 159730 | 1625630.02 | 2nd Tranche | 265450.22 | 1891080.24 | 1625630.02 | 265450.22 | 100% | 100% | 166.2% | 96.19% | 100% | 2005-04-27 | 2005-06-20 | 2005-09-08 | 2006-05-10 | 2006-05-11 | 244 | 153 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Parallan | 061907022 | 1.09km Road Improvement | 1 | 962300 | 835200 | 127100 | 794994.88 | 1st Tranche | 174463.4 | 921579.88 | 794994.88 | 126585 | 100% | 72.56% | 137.3% | 95.77% | 100% | 2007-08-01 | no data | 2008-03-29 | 2009-06-30 | no data | 458 | 86 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Piña | 061907023 | Road Upgrading | 1 | 968827.09 | 847008.63 | 121818.46 | 847008.63 | Last Tranche | 114757.1 | 961765.73 | 847008.63 | 114757.1 | 100% | 100% | 94.2% | 99.27% | 100% | 2006-07-04 | 2006-08-18 | 2007-03-19 | 2008-06-30 | no data | 469 | 184 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Pob. Ilawod | 061907024 | Water System Level II | 1 | 1428500 | 1186700 | 241800 | 1068030 |  | 204693.5 | 1193848.5 | 1068030 | 125818.5 | 100% | 61.47% | 84.65% | 83.57% | 100% | 2007-08-01 | no data | 2008-08-05 | 2009-04-30 | n/a | 268 | 271 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Poblacion Ilaya | 061907025 | Water System Level II | 1 | 1997986.18 | 1750120.97 | 247865.21 | 1750120.97 | Last Tranche | 224612.68 | 1974733.65 | 1750120.97 | 224612.68 | 100% | 100% | 90.62% | 98.84% | 100% | 2006-07-04 | 2006-08-18 | 2007-03-07 | 2008-06-30 | no data | 481 | 366 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Poblacion Tabuc | 061907026 | Water System Level II | 1 | 1347728.82 | 1170450.16 | 177278.66 | 1137367.1 | 1st Tranche | 198306.05 | 1295673.15 | 1137367.1 | 158306.05 | 100% | 79.83% | 111.9% | 96.14% | 100% | 2006-07-04 | 2006-08-18 | 2006-11-27 | 2008-08-30 | no data | 642 | 296 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Quevedo | 061907019 | Water System Level II | 1 | 1554382.92 | 1418120.3 | 136262.62 | 1418120.3 | Last Tranche | 213456.74 | 1630777.04 | 1418120.3 | 212656.74 | 100% | 99.63% | 156.7% | 104.9% | 100% | 2005-04-27 | 2005-06-20 | 2005-10-03 | 2006-09-18 | 2006-09-21 | 350 | 179 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Quinabonglan | 061907028 | 2 CL Classroom Building | 1 | 1202500 | 1042500 | 160000 | 1010580.64 | 1st Tranche | 150330 | 1133820.64 | 1010580.64 | 123240 | 100% | 81.98% | 93.96% | 94.29% | 100% | 2007-08-01 | no data | 2008-05-01 | 2009-02-28 | n/a | 303 | 186 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Quinat-uyan | 061907029 | Day Care Center | 1 | 647600 | 526400 | 121200 | 473760 | 3rd Tranche | 125898 | 476393.25 | 473760 | 2633.25 | 100% | 2.092% | 103.9% | 73.56% | 100% | 2007-08-01 | no data | 2008-03-31 | 2009-04-30 | n/a | 395 | 238 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Salgan | 061907030 | 2 Unit Overflow | 1 | 1970213.77 | 1731471.95 | 238741.82 | 1731471.95 | Last Tranche | 280522.5 | 2008209.69 | 1731471.95 | 276737.74 | 100% | 98.65% | 117.5% | 101.9% | 100% | 2006-07-04 | 2006-08-18 | 2007-03-10 | 2007-10-30 | 2007-11-01 | 234 | 203 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Tapulang | 061907031 | Water System Level I & II | 1 | 1244400 | 1079400 | 165000 | 1022298.12 | 1st Tranche | 159492.88 | 1154246 | 1022298.12 | 131947.88 | 100% | 82.73% | 96.66% | 92.76% | 100% | 2007-08-01 | no data | 2008-08-06 | 2009-07-30 | no data | 358 | 248 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | Tuburan | 061907032 | 40-unit Level I Water System | 1 | 756700 | 647400 | 109300 | 582660 | 1st Tranche | 124080 | 706740 | 582660 | 124080 | 100% | 100% | 113.5% | 93.4% | 100% | 2007-08-01 | no data | 2008-03-05 | 2009-04-30 | n/a | 421 | 371 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Maayon | 061907 | West Villaflores | 061907034 | Road Upgrading | 1 | 2900405.29 | 2711405.29 | 189000 | 2574254.76 | 3rd Tranche | 223879.85 | 2791694.76 | 2574254.76 | 217440 | 100% | 97.12% | 118.5% | 96.25% | 100% | 2005-04-27 | 2005-06-20 | 2005-10-10 | 2006-06-30 | 2007-02-01 | 263 | 261 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Abangay | 061917001 | 2 Classroom School Building (Elementary) | 1 | 1048141.63 | 520350.02 | 527791.61 | 475886.99 | 2nd Tranche | 836438.51 | 1312325.5 | 475886.99 | 836438.51 | 100% | 100% | 158.5% | 125.2% | 100% | 2006-09-12 | 2006-10-26 | 2007-03-12 | 2008-04-01 | 2008-05-20 | 386 | 99 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Acuña | 061917002 | 1 Unit 2 Classroom School Building | 1 | 1095724.87 | 805710.91 | 290013.96 | 725139.82 | 1st Tranche | 247272.34 | 972412.16 | 725139.82 | 247272.34 | 100% | 100% | 85.26% | 88.75% | 100% | 2007-11-21 | no data | 2009-01-01 | 2009-08-31 | no data | 242 | 111 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Agcococ | 061917003 | Health Station | 1 | 655200.01 | 427589.91 | 227610.1 | 427589.9 | 1st Tranche | 215008.82 | 642598.72 | 427589.9 | 215008.82 | 100% | 100% | 94.46% | 98.08% | 100% | 2007-11-21 | no data | 2008-06-04 | 2009-04-30 | n/a | 330 | 130 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Aglinab | 061917004 | Road Upgrading | 1 | 3477172.46 | 2704635.89 | 772536.57 | 2434172.3 | 1st Tranche | 837104.18 | 3271276.48 | 2434172.3 | 837104.18 | 100% | 100% | 108.4% | 94.08% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-29 | 2009-07-30 | no data | 762 | 125 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Aglupacan | 061917005 | Post Harvest Facilities | 1 | 603662.51 | 495451.24 | 108211.27 | 458079.05 | 1st Tranche | 132104.95 | 590184 | 458079.05 | 132104.95 | 100% | 100% | 122.1% | 97.77% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-27 | 2008-12-01 | no data | 523 | 19 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Apero | 061917007 | Road Improvement & Construction of 2.10 kms. | 1 | 1569500 | 855871.87 | 713628.13 | 684697.5 | 1st Tranche | 532761.05 | 1217458.55 | 684697.5 | 532761.05 | 100% | 100% | 74.66% | 77.57% | 100% | 2007-11-21 | no data | 2009-04-08 | 2009-08-31 | no data | 145 | 276 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Artuz | 061917008 | 1 Unit 2 Classroom School Building | 1 | 1428400 | 1149445.98 | 278954.02 | 1034501.39 |  | 280454.0233 | 1268600.4091 | 1034501.39 | 234099.0191 | 100% | 83.47% | 100.5% | 88.81% | 100% | 2008-07-16 | no data | 2008-12-04 | 2009-06-30 | no data | 208 | 214 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Bag-Ong Barrio | 061917009 | Solar Dryer with Warehouse | 1 | 1091800 | 755818.08 | 335981.92 | 680236.27 |  | 299327.53 | 838569.6033 | 680236.27 | 158333.3333 | 100% | 52.9% | 89.09% | 76.81% | 100% | 2008-07-16 | no data | 2009-01-01 | 2009-08-31 | no data | 242 | 147 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Bato-Bato | 061917010 | Heallth Station | 1 | 597949.1 | 383286.94 | 214662.16 | 344958.24 | 1st Tranche | 261062.99 | 606021.23 | 344958.24 | 261062.99 | 100% | 100% | 121.6% | 101.3% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-11 | 2008-05-01 | 2008-04-23 | 325 | 47 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Camburanan | 061917012 | Mini Market | 1 | 993800 | 792373.77 | 201426.23 | 713136.39 |  | 157333.33 | 870469.72 | 713136.39 | 157333.33 | 100% | 100% | 78.11% | 87.59% | 100% | 2008-07-16 | no data | 2009-01-01 | 2009-06-30 | no data | 180 | 157 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Candelaria | 061917013 | Road Upgrading | 1 | 3757923.9 | 3100391.46 | 657532.44 | 2790352.32 | 1st Tranche | 670070.91 | 3434169.75 | 2764098.84 | 670070.91 | 99.06% | 100% | 101.9% | 91.38% | 100% | 2006-09-12 | 2006-10-26 | 2007-11-24 | 2009-04-30 | n/a | 523 | 403 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Carida | 061917014 | Day Care Center | 1 | 725600 | 517060.7 | 208539.3 | 465354.63 |  | 219437.63 | 603576.33 | 465354.63 | 138221.7 | 100% | 62.99% | 105.2% | 83.18% | 100% | 2008-07-16 | no data | 2008-11-27 | 2009-04-30 | n/a | 154 | 132 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Cristina | 061917015 | Road Improvement of 3.16kms | 1 | 2635300 | 2101303.44 | 533996.56 | 1891173.09 |  | 467341.46 | 2100572.15 | 1891173.09 | 209399.06 | 100% | 44.81% | 87.52% | 79.71% | 100% | 2008-07-16 | no data | 2008-11-27 | 2009-08-31 | no data | 277 | 165 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Da-an Banwa | 061917016 | 1 Unit 2 Classroom School Building | 1 | 985484.39 | 748573.97 | 236910.42 | 673716.58 | 1st Tranche | 201708.82 | 875425.4 | 673716.58 | 201708.82 | 100% | 100% | 85.14% | 88.83% | 100% | 2007-11-21 | no data | 2008-09-01 | 2009-06-30 | no data | 302 | 116 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Da-an Norte | 061917017 | Health Station | 1 | 611699.75 | 392960.83 | 218738.92 | 353664.74 | 2nd Tranche | 272310.61 | 625975.35 | 353664.74 | 272310.61 | 100% | 100% | 124.5% | 102.3% | 100% | 2006-09-12 | 2006-10-26 | 2007-03-26 | 2008-04-01 | 2008-03-24 | 372 | 109 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Daan Sur | 061917018 | Health Station | 1 | 611619.49 | 389934.6 | 221684.89 | 350941.14 | 1st Tranche | 255930.45 | 606871.59 | 350941.14 | 255930.45 | 100% | 100% | 115.4% | 99.22% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-26 | 2009-01-01 | n/a | 555 | 130 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Garcia | 061917019 | Day Care Center | 1 | 604128.77 | 273224.24 | 330904.53 | 245901.92 | 1st Tranche | 614722.76 | 860624.68 | 245901.92 | 614722.76 | 100% | 100% | 185.8% | 142.5% | 100% | 2006-09-12 | 2006-10-26 | 2007-04-02 | 2008-06-01 | no data | 426 | 134 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Gebio-an | 061917020 | 2 Classroom School Building (Elementary) | 1 | 975367.14 | 786389.24 | 188977.9 | 707750.31 | 1st Tranche | 281262.44 | 989012.75 | 707750.31 | 281262.44 | 100% | 100% | 148.8% | 101.4% | 100% | 2006-09-12 | 2006-10-26 | 2007-05-07 | 2008-05-01 | no data | 360 | 111 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Initan | 061917022 | Improvement of 0.96 kms. w/ 60.0 m. Spot Concreting FTMR | 1 | 767303 | 531040.43 | 236262.57 | 477936.34 | 1st Tranche | 153312.82 | 631249.16 | 477936.34 | 153312.82 | 100% | 100% | 64.89% | 82.27% | 100% | 2007-11-21 | no data | 2008-06-16 | 2009-07-30 | no data | 409 | 126 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Katipunan | 061917023 | Potable Water System Level II (Pump Driven) | 1 | 704001.32 | 520988.59 | 183012.73 | 416790.87 | 1st Tranche | 261024.72 | 677815.59 | 416790.87 | 261024.72 | 100% | 100% | 142.6% | 96.28% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-11 | 2008-04-01 | 2008-04-15 | 295 | 120 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Katipunan | 061917023 | Mini Market | 1 | 973400 | 646480.61 | 326919.39 | 581832.55 |  | 330719.39 | 816165.88 | 581832.55 | 234333.33 | 100% | 70.86% | 101.2% | 83.85% | 100% | 2008-07-16 | no data | 2008-12-12 | 2009-07-31 | no data | 231 | 145 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Lagdungan | 061917024 | Day Care Center | 1 | 586638.66 | 361319.57 | 225319.09 | 361319.57 | 1st Tranche | 197915.82 | 559235.39 | 361319.57 | 197915.82 | 100% | 100% | 87.84% | 95.33% | 100% | 2007-11-21 | no data | 2008-06-11 | 2009-05-30 | no data | 353 | 138 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Libertad | 061917026 | Health Station | 1 | 622432.18 | 487511.22 | 134920.96 | 462046.71 | 2nd Tranche | 219044.5 | 681091.21 | 462046.71 | 219044.5 | 100% | 100% | 162.4% | 109.4% | 100% | 2006-09-12 | 2006-10-26 | 2007-03-02 | 2008-04-01 | 2008-04-28 | 396 | 131 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Libertad | 061917026 | 1 Unit 2 Classroom School Building | 1 | 1323400 | 1024923.96 | 298476.04 | 922431.57 |  | 306446.04 | 1056764.9 | 922431.57 | 134333.33 | 100% | 43.84% | 102.7% | 79.85% | 100% | 2008-07-16 | no data | 2009-01-01 | 2009-06-30 | no data | 180 | 82 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Mabini | 061917027 | Health Station | 1 | 605746.31 | 402169.74 | 203576.57 | 361952.76 | 1st Tranche | 251560.98 | 613513.74 | 361952.76 | 251560.98 | 100% | 100% | 123.6% | 101.3% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-06 | 2008-06-01 | no data | 361 | 42 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Maliao | 061917028 | Health Station | 1 | 599819.84 | 388139.87 | 211679.97 | 349325.88 | 2nd Tranche | 257974.5 | 607300.38 | 349325.88 | 257974.5 | 100% | 100% | 121.9% | 101.2% | 100% | 2006-09-12 | 2006-10-26 | 2007-04-24 | 2008-05-01 | 2008-03-31 | 373 | 108 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Malitbog | 061917029 | Health Station | 1 | 614625.69 | 442282.33 | 172343.36 | 442282.33 | 2nd Tranche | 285242.62 | 727524.95 | 442282.33 | 285242.62 | 100% | 100% | 165.5% | 118.4% | 100% | 2006-09-12 | 2006-10-26 | 2007-03-07 | 2008-04-01 | 2008-04-29 | 391 | 218 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Minan | 061917030 | Post Harvest Facilities | 1 | 602807.25 | 495142.21 | 107665.04 | 445627.99 | 1st Tranche | 169739.33 | 615367.32 | 445627.99 | 169739.33 | 100% | 100% | 157.7% | 102.1% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-27 | 2008-06-01 | no data | 340 | 73 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Poblacion | 061917032 | 1 Unit 2 Classroom School Building | 1 | 1220900 | 1119142.5 | 101757.5 | 1007228.25 |  | 81705.2615 | 1048080.8808 | 1007228.25 | 40852.6308 | 100% | 50% | 80.29% | 85.84% | 100% | 2008-07-16 | no data | 2008-12-02 | 2009-06-30 | no data | 210 | 335 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Rizal Sur | 061917034 | Health Station | 1 | 602515.92 | 384670.75 | 217845.17 | 346203.67 | 1st Tranche | 270546.99 | 616750.66 | 346203.67 | 270546.99 | 100% | 100% | 124.2% | 102.4% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-11 | 2008-08-01 | no data | 417 | 41 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Roosevelt | 061917035 | Improvement of 1.50 kms. FTMR | 1 | 1752449.09 | 1481381.45 | 271067.64 | 1333243.31 | 1st Tranche | 156058.82 | 1489302.13 | 1333243.31 | 156058.82 | 100% | 100% | 57.57% | 84.98% | 100% | 2007-11-21 | no data | 2008-07-27 | 2009-08-31 | no data | 400 | 93 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Roxas | 061917036 | Health Station | 1 | 666861.24 | 450740.2 | 216121.04 | 444369.18 | 1st Tranche | 214656.82 | 659026 | 444369.18 | 214656.82 | 100% | 100% | 99.32% | 98.83% | 100% | 2007-11-21 | no data | 2008-06-16 | 2009-04-30 | n/a | 318 | 150 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Antonio | 061917038 | Improvement of 2.46 kms. FTMR | 1 | 1671900 | 1242086.18 | 429813.82 | 1117877.56 |  | 390498.82 | 1333896.38 | 1117877.56 | 216018.82 | 100% | 55.32% | 90.85% | 79.78% | 100% | 2007-11-21 | no data | 2008-09-01 | 2009-08-31 | no data | 364 | 130 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Francisco | 061917039 | Post Harvest Facilities | 1 | 746808.56 | 588233.51 | 158575.05 | 549634.89 | 1st Tranche | 136347.84 | 685982.73 | 549634.89 | 136347.84 | 100% | 100% | 85.98% | 91.86% | 100% | 2006-09-12 | 2006-10-26 | 2007-09-06 | 2009-06-30 | no data | 663 | 24 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Julian | 061917042 | Health Station | 1 | 780300 | 563993.65 | 216306.35 | 507594.29 |  | 217326.68 | 671927.62 | 507594.29 | 164333.33 | 100% | 75.62% | 100.5% | 86.11% | 100% | 2008-07-16 | no data | 2008-12-01 | 2009-04-30 | n/a | 150 | 160 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Miguel Ilaya | 061917044 | Improvement of 1.70kms FTMR | 1 | 1007881.33 | 839434 | 168447.33 | 755490.6 |  | 55340 | 810830.6 | 755490.6 | 55340 | 100% | 100% | 32.85% | 80.45% | 100% | 2007-11-21 | no data | 2008-09-01 | 2009-08-31 | no data | 364 | 151 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Nicolas | 061917045 | Improvement & Construction of 3.12 kms. FTMR | 1 | 1914500 | 1667462.47 | 247037.53 | 1500716.23 | 1st Tranche | 203037.53 | 702689.54 | 499652.01 | 203037.53 | 33.29% | 100% | 82.19% | 36.7% | 100% | 2007-11-21 | no data | 2009-04-08 | 2009-08-31 | no data | 145 | 353 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Pedro | 061917046 | Day Care Center | 1 | 583500 | 373892.93 | 209607.07 | 373892.92 | 1st Tranche | 210951.42 | 584844.34 | 373892.92 | 210951.42 | 100% | 100% | 100.6% | 100.2% | 100% | 2007-11-21 | no data | 2008-07-24 | 2009-06-30 | no data | 341 | 53 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | San Vicente | 061917048 | Improvement of 1.14 kms. FTMR | 1 | 1606989.2 | 1267259.72 | 339729.48 | 1140533.78 |  | 169558.82 | 1310092.6 | 1140533.78 | 169558.82 | 100% | 100% | 49.91% | 81.52% | 100% | 2007-11-21 | no data | 2008-09-01 | 2009-03-30 | n/a | 210 | 44 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Senunod | 061917051 | Health Station | 1 | 1355898.65 | 355024.4 | 1000874.25 | 319521.96 | 1st Tranche | 815554.48 | 274706.16 | 0 | 274706.16 | 0% | 33.68% | 81.48% | 20.26% | 100% | 2006-09-12 | 2006-10-26 | 2007-06-11 | 2008-05-01 | 2008-04-24 | 325 | 22 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Sta. Ana | 061917049 | Improvement & Construction of 2.24 kms. FTMR | 1 | 1680300 | 1235249.83 | 445050.17 | 1111724.85 |  | 228058.82 | 1339783.67 | 1111724.85 | 228058.82 | 100% | 100% | 51.24% | 79.73% | 100% | 2007-11-21 | no data | 2009-04-08 | 2009-08-31 | no data | 145 | 158 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Sta. Petronila | 061917050 | Hanging Foot Bridge | 1 | 4111000 | 3168749.12 | 942250.88 | 2851874.21 |  | 991726.21 | 3238385.69 | 2500052.36 | 738333.33 | 87.66% | 74.45% | 105.3% | 78.77% | 100% | 2008-07-16 | no data | 2009-02-23 | 2009-08-31 | no data | 189 | 71 | completed as built | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Tacayan | 061917055 | 1 Unit 2 Classroom School Building | 1 | 1233400 | 912386.56 | 321013.44 | 821147.92 | 1st Tranche | 278320.82 | 1099468.74 | 821147.92 | 278320.82 | 100% | 100% | 86.7% | 89.14% | 100% | 2007-11-21 | no data | 2008-07-30 | 2009-06-30 | no data | 335 | 75 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Taft | 061917056 | 1 Unit 2 Classroom School Building | 1 | 1297300 | 1002339.39 | 294960.61 | 902105.45 |  | 296458.11 | 1045438.78 | 902105.45 | 143333.33 | 100% | 48.35% | 100.5% | 80.59% | 100% | 2008-07-16 | no data | 2008-12-08 | 2009-06-30 | no data | 204 | 183 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Taslan | 061917058 | Road Upgrading | 1 | 1954431.52 | 1418200.76 | 536230.76 | 1134560.6 | 1st Tranche | 1859933.75 | 455992.84 | 0 | 455992.84 | 0% | 24.52% | 346.9% | 23.33% | 100% | 2006-09-12 | 2006-10-26 | 2007-04-04 | 2008-05-01 | no data | 393 | 162 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Taslan | 061917058 | 1 Unit 2 Classroom School Building | 1 | 1381800 | 1102496.58 | 279303.42 | 992246.92 |  | 296248.4233 | 1170580.2533 | 992246.92 | 178333.3333 | 100% | 60.2% | 106.1% | 84.71% | 100% | 2008-07-16 | no data | 2008-12-11 | 2009-06-30 | no data | 201 | 112 |  | 1 | VISAYAS
VI | 06 | Capiz | 0619 | Tapaz | 061917 | Wright | 061917059 | Road Upgrading | 1 | 3086378.78 | 2871012.16 | 215366.62 | 2583910.94 | 1st Tranche | 862058.07 | 1135076.44 | 319521.96 | 815554.48 | 12.37% | 94.61% | 400.3% | 36.78% | 100% | 2006-09-12 | 2006-10-26 | 2007-03-23 | 2009-08-31 | no data | 892 | 188 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Adcadarao | 063001001 | Health Station | 1 | 597629.68 | 475517.46 | 122112.22 | 475517.46 | 3rd Tranche | 167688.52 | 643205.98 | 475517.46 | 167688.52 | 100% | 100% | 137.3% | 107.6% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-14 | 2004-11-18 | 2005-01-20 | 157 | 99 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Adcadarao | 063001001 | Road Upgrading | 1 | 594650 | 504570 | 90080 | 500675.75 |  | 101118.24 | 601793.99 | 500675.75 | 101118.24 | 100% | 100% | 112.3% | 101.2% | 100% | 2009-01-31 | no data | 2009-05-11 | 2009-07-24 | no data | 74 | 112 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Agbobolo | 063001002 | Post harvest Facilities | 1 | 1158731.01 | 609393.64 | 549337.37 | 609393.64 | 3rd Tranche | 569688.87 | 1179082.51 | 609393.64 | 569688.87 | 100% | 100% | 103.7% | 101.8% | 100% | 2004-02-03 | 2004-04-23 | 2004-06-10 | 2005-01-13 | 2005-03-22 | 217 | 63 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Agbobolo | 063001002 | Cooperative Building | 1 | 338420 | 301840 | 36580 | 284504 | 2nd Tranche | 28150 | 312654 | 284504 | 28150 | 100% | 100% | 76.95% | 92.39% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-02 | 2008-03-28 | no data | 512 | 125 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Agbobolo | 063001002 | Road Upgrading | 1 | 1620720 | 1552260 | 68460 | 1474335.88 |  | 88620 | 1562955.88 | 1474335.88 | 88620 | 100% | 100% | 129.4% | 96.44% | 100% | 2009-01-31 | no data | 2009-04-27 | 2009-06-27 | no data | 61 | 77 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Badiangan | 063001003 | Health Station | 1 | 600549.18 | 419994.76 | 180554.42 | 419994.76 | 3rd Tranche | 232560.53 | 652555.29 | 419994.76 | 232560.53 | 100% | 100% | 128.8% | 108.7% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-10 | 2004-11-17 | 2005-03-01 | 160 | 192 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Badiangan | 063001003 | School Building 2 Classroom | 1 | 1038343.02 | 873186 | 165157.02 | 873186 | 3rd Tranche | 165637.02 | 1038823.02 | 873186 | 165637.02 | 100% | 100% | 100.3% | 100% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-24 | 2006-10-31 | no data | 372 | 192 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Badiangan | 063001003 | Overflow | 1 | 263455 | 195110 | 68345 | 195110 |  | 65740 | 260850 | 195110 | 65740 | 100% | 100% | 96.19% | 99.01% | 100% | 2009-01-31 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 218 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Barrido | 063001004 | Artificial Coral Reef | 1 | 257518.2 | 194748.25 | 62769.95 | 194748.25 | 3rd Tranche | 101184.95 | 295933.2 | 194748.25 | 101184.95 | 100% | 100% | 161.2% | 114.9% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-16 | 2005-01-09 | 2005-02-03 | 207 | 279 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Bay-ang | 063001006 | Road Upgrading | 1 | 2055430 | 555845.99 | 1499584.01 | 555845.99 | 1st Tranche | 1475174.01 | 2028142.75 | 555845.99 | 1472296.76 | 100% | 99.8% | 98.37% | 98.67% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-02 | 2008-03-01 | no data | 485 | 444 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Bucana Bunglas | 063001007 | Water Supply System | 1 | 1629508.1 | 1436055.61 | 193452.49 | 1436055.61 | 3rd Tranche | 280666.4 | 1716722.01 | 1436055.61 | 280666.4 | 100% | 100% | 145.1% | 105.4% | 100% | 2004-02-03 | 2005-04-23 | 2004-05-25 | 2005-02-28 | 2005-06-08 | 279 | 74 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Lanjagan | 063001010 | Road Concreting | 1 | 931807.92 | 380697.7 | 551110.22 | 380697.7 | 3rd Tranche | 602224.9 | 982922.6 | 380697.7 | 602224.9 | 100% | 100% | 109.3% | 105.5% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-08 | 2004-12-31 | 2005-02-23 | 206 | 240 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Lanjagan | 063001010 | Road Upgrading | 1 | 1392035.68 | 1033805.68 | 358230 | 1033805.68 | 3rd Tranche | 383970.32 | 1417776 | 1033805.68 | 383970.32 | 100% | 100% | 107.2% | 101.8% | 100% | 2005-08-03 | 2005-08-23 | 2005-11-05 | 2006-06-30 | no data | 237 | 240 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Lanjagan | 063001010 | 3 Classroom School Building | 1 | 1507857 | 1385912 | 121945 | 1385912 | 2nd Tranche | 82645.48 | 1465847 | 1385912 | 79935 | 100% | 96.72% | 67.77% | 97.21% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-20 | 2008-03-19 | no data | 485 | 240 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Luca | 063001011 | Water System Level II | 1 | 2324708 | 1710200 | 614508 | 1710200 | 1st | 607348 | 2317548 | 1710200 | 607348 | 100% | 100% | 98.83% | 99.69% | 100% | 2009-01-31 | no data | 2009-05-11 | 2009-07-13 | no data | 63 | 584 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Malayu-an | 063001012 | Day Care Center | 1 | 499150 | 357180 | 141970 | 335137.39 | 2nd Tranche | 150477 | 483890.61 | 335137.39 | 148753.22 | 100% | 98.85% | 106% | 96.94% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-02 | 2007-06-17 | no data | 227 | 532 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Malayu-an | 063001012 | Coinstruction of 2-CL School Building | 1 | 1233503.33 | 878090 | 355413.33 | 878090 | 1st | 349095 | 1227185 | 878090 | 349095 | 100% | 100% | 98.22% | 99.49% | 100% | 2009-01-31 | no data | 2009-04-16 | 2009-06-21 | no data | 66 | 550 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Mangorocoro | 063001013 | Seawall | 1 | 2566360 | 2317210 | 249150 | 2317210 | Last Tranche | 187681 | 2504891 | 2317210 | 187681 | 100% | 100% | 75.33% | 97.6% | 100% | 2005-08-03 | 2005-08-23 | 2006-01-11 | 2007-03-30 | no data | 443 | 256 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Mangorocoro | 063001013 | Seawall Upgrading | 1 | 1191121.67 | 944680 | 246441.67 | 879242 |  | 264860 | 1144102 | 879242 | 264860 | 100% | 100% | 107.5% | 96.05% | 100% | 2009-01-31 | no data | 2009-05-24 | 2009-06-22 | no data | 29 | 278 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Nasidman | 063001014 | Health Station | 1 | 570167.49 | 357029.5 | 213137.99 | 357029.5 | 3rd Tranche | 267677.99 | 624707.49 | 357029.5 | 267677.99 | 100% | 100% | 125.6% | 109.6% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-08 | 2004-11-16 | 2005-02-25 | 161 | 87 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Nasidman | 063001014 | Artificial Coral Reef | 1 | 647653.1 | 588710 | 58943.1 | 588710 | 3rd Tranche | 61038.1 | 649748.1 | 588710 | 61038.1 | 100% | 100% | 103.6% | 100.3% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-24 | 2006-06-30 | no data | 249 | 87 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Nasidman | 063001014 | Installation of Electricity Generating Systems | 1 | 777196 | 592040 | 185156 | 553876 | 1st | 188220 | 742096 | 553876 | 188220 | 100% | 100% | 101.7% | 95.48% | 100% | 2009-01-31 | no data | 2009-03-18 | 2009-04-17 | 2009-07-14 | 30 | 98 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pantalan Navarro | 063001016 | Barangay Road Rehabilitation | 1 | 1503167.7 | 1223599.16 | 279568.54 | 1223599.16 | 3rd Tranche | 485139.7 | 1708738.86 | 1223599.16 | 485139.7 | 100% | 100% | 173.5% | 113.7% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-18 | 2005-07-31 | no data | 408 | 76 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pantalan Navarro | 063001016 | River Dredging | 1 | 592129 | 518545 | 73584 | 489275 | 1st Tranche | 103672 | 590205.5 | 489275 | 100930.5 | 100% | 97.36% | 140.9% | 99.68% | 100% | 2006-07-12 | 2006-08-08 | 2008-01-14 | 2008-03-30 | no data | 76 | 82 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pantalan Navarro | 063001016 | Road Upgrading | 1 | 1158615 | 910700 | 247915 | 894331 |  | 315745.76 | 1210076.76 | 894331 | 315745.76 | 100% | 100% | 127.4% | 104.4% | 100% | 2009-01-31 | no data | 2009-04-17 | 2009-05-25 | no data | 38 | 84 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pedada | 063001017 | Construction of Health Station | 1 | 695840 | 528710 | 167130 | 494222.75 | 1st | 176397 | 670619.75 | 494222.75 | 176397 | 100% | 100% | 105.5% | 96.38% | 100% | 2009-01-31 | no data | 2009-04-27 | 2009-07-27 | no data | 91 | 260 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pinantan Diel | 063001019 | Health Station | 1 | 652502.65 | 443188.18 | 209314.47 | 443188.18 | 3rd Tranche | 194143.81 | 637331.99 | 443188.18 | 194143.81 | 100% | 100% | 92.75% | 97.68% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-14 | 2004-09-04 | 2004-12-28 | 82 | 100 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pinantan Elizalde | 063001020 | Health Station | 1 | 600639.18 | 456394.76 | 144244.42 | 456394.76 | 3rd Tranche | 274784.74 | 731179.5 | 456394.76 | 274784.74 | 100% | 100% | 190.5% | 121.7% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-10 | 2004-08-28 | 2004-12-17 | 79 | 109 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pinantan Elizalde | 063001020 | Road Upgrading | 1 | 1313958.49 | 1293398.49 | 20560 | 1293398.49 | 3rd Tranche | 62414 | 1355812.49 | 1293398.49 | 62414 | 100% | 100% | 303.6% | 103.2% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-24 | 2006-10-31 | no data | 372 | 109 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pinantan Elizalde | 063001020 | Const. of 3-Barrel Box Culvert | 1 | 1033800 | 731520 | 302280 | 685522 |  | 312023 | 997545 | 685522 | 312023 | 100% | 100% | 103.2% | 96.49% | 100% | 2009-01-31 | no data | 2009-05-11 | 2009-06-28 | no data | 48 | 114 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pinay Espinosa | 063001021 | Health Station | 1 | 602677.18 | 372092.76 | 230584.42 | 372092.76 | 3rd Tranche | 268475.91 | 640568.67 | 372092.76 | 268475.91 | 100% | 100% | 116.4% | 106.3% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-02 | 2004-11-16 | 2005-02-28 | 167 | 227 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Pinay Espinosa | 063001021 | Day Care Center | 1 | 505317 | 449436 | 55881 | 429055.4 | 2nd Tranche | 63029.5 | 490056 | 429055.4 | 61000.6 | 100% | 96.78% | 112.8% | 96.98% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-02 | 2008-03-14 | no data | 498 | 230 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Poblacion | 063001022 | Technology and Livelihood Development Center | 1 | 1110298 | 898437 | 211861 | 898437 | 2nd Tranche | 161013 | 1059450 | 898437 | 161013 | 100% | 100% | 76% | 95.42% | 100% | 2006-07-12 | 2006-08-08 | 2007-05-31 | 2008-03-28 | no data | 302 | 704 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Progreso | 063001023 | Health Station | 1 | 656236.55 | 525207.8 | 131028.75 | 525207.8 | 3rd Tranche | 132553.75 | 657761.55 | 525207.8 | 132553.75 | 100% | 100% | 101.2% | 100.2% | 100% | 2005-08-03 | 2005-08-23 | 2005-11-09 | 2006-06-30 | no data | 233 | 310 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Progreso | 063001023 | 2 Barrel Box Culvert | 1 | 1407070 | 878110 | 528960 | 876621.5 | 1st | 544563 | 1421184.5 | 876621.5 | 544563 | 100% | 100% | 102.9% | 101% | 100% | 2009-01-31 | no data | 2009-04-30 | 2009-07-05 | no data | 66 | 331 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Puente Bunglas | 063001024 | Health Station | 1 | 630716.34 | 601410.89 | 29305.45 | 601410.89 | 3rd Tranche | 51600.45 | 653011.34 | 601410.89 | 51600.45 | 100% | 100% | 176.1% | 103.5% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-25 | 2006-06-30 | no data | 248 | 257 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Puente Bunglas | 063001024 | Water System Level II | 1 | 1520948 | 1192810 | 328138 | 1156620 | 1st | 322085.77 | 1478705.77 | 1156620 | 322085.77 | 100% | 100% | 98.16% | 97.22% | 100% | 2009-01-31 | no data | 2009-05-13 | 2009-08-13 | no data | 92 | 270 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Punta Buri | 063001025 | RC Pipe Culvert | 1 | 379716.48 | 246899.64 | 132816.84 | 246899.64 | 3rd Tranche | 198853.21 | 445752.85 | 246899.64 | 198853.21 | 100% | 100% | 149.7% | 117.4% | 100% | 2004-02-03 | 2005-04-23 | 2004-07-07 | 2004-12-15 | 2005-02-03 | 161 | 267 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Punta Buri | 063001025 | Artificial Coral Reef | 1 | 1429548 | 1266899 | 162649 | 1266899 | 1st Tranche | 174577 | 1441476 | 1266899 | 174577 | 100% | 100% | 107.3% | 100.8% | 100% | 2006-07-12 | 2006-08-08 | 2007-02-28 | 2008-03-31 | no data | 397 | 247 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Punta Buri | 063001025 | 1-CL High School Building | 1 | 889800 | 768300 | 121500 | 737475.8 |  | 135753 | 873228.8 | 737475.8 | 135753 | 100% | 100% | 111.7% | 98.14% | 100% | 2009-01-31 | no data | 2009-05-15 | 2009-08-27 | 2009-07-14 | 104 | 246 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Rojas | 063001026 | Construction of Line Ditch Canal | 1 | 783075 | 637790 | 145285 | 617790 | 1st | 146727 | 764517 | 617790 | 146727 | 100% | 100% | 101% | 97.63% | 100% | 2009-01-31 | no data | 2009-04-16 | 2009-06-16 | no data | 61 | 93 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | San Antonio | 063001027 | Health Station | 1 | 624364.41 | 495686.2 | 128678.21 | 495686.2 | 3rd Tranche | 139228.21 | 634914.41 | 495686.2 | 139228.21 | 100% | 100% | 108.2% | 101.7% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-27 | 2006-06-30 | no data | 246 | 368 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | San Antonio | 063001027 | 3 Classroom School Building | 1 | 1205520 | 1047100 | 158420 | 1047100 | 2nd Tranche | 119130 | 1166230 | 1047100 | 119130 | 100% | 100% | 75.2% | 96.74% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-13 | 2007-12-30 | no data | 412 | 390 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | San Antonio | 063001027 | Construction of 1 Unit 4-CL High School Building | 1 | 2325740 | 1782400 | 543340 | 1782400 | 1st | 517430 | 2299830 | 1782400 | 517430 | 100% | 100% | 95.23% | 98.89% | 100% | 2009-01-31 | no data | 2009-04-26 | 2009-07-17 | no data | 82 | 403 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Silagon | 063001028 | Barangay Road Rehabilitation | 1 | 3357118.7 | 422663.12 | 2934455.58 | 422663.12 | 3rd Tranche | 2553772.07 | 2976435.19 | 422663.12 | 2553772.07 | 100% | 100% | 87.03% | 88.66% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-18 | 2005-07-30 | 2006-02-03 | 407 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Silagon | 063001028 | Health Station | 1 | 653109.54 | 593795.89 | 59313.65 | 593795.89 | 3rd Tranche | 67493.77 | 661289.66 | 593795.89 | 67493.77 | 100% | 100% | 113.8% | 101.3% | 100% | 2005-08-03 | 2005-08-23 | 2005-11-03 | 2006-05-31 | no data | 209 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Silagon | 063001028 | Construction of Reinforced Pipe Culverts & Slope Protection | 1 | 621755 | 486240 | 135515 | 484574.5 |  | 155832.25 | 640406.75 | 484574.5 | 155832.25 | 100% | 100% | 115% | 103% | 100% | 2009-01-31 | no data | 2009-04-16 | 2009-05-18 | no data | 32 | 108 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Sto. Rosario | 063001029 | Health Station | 1 | 627279.12 | 459934.7 | 167344.42 | 459934.7 | 3rd Tranche | 226001.39 | 685936.09 | 459934.7 | 226001.39 | 100% | 100% | 135.1% | 109.4% | 100% | 2004-02-03 | 2005-04-23 | 2004-05-31 | 2004-09-12 | 2005-02-28 | 104 | 215 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Sto. Rosario | 063001029 | Electrification | 1 | 2188810 | 1461700 | 727110 | 1461700 | 1st Tranche | 745909.96 | 2184854.96 | 1461700 | 723154.96 | 100% | 96.95% | 102.6% | 99.82% | 100% | 2006-07-12 | 2006-08-08 | 2007-06-30 | 2008-08-01 | no data | 398 | 303 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tagubanhan | 063001030 | Break Water | 1 | 581714.8 | 262377.45 | 319337.35 | 262377.45 | 3rd Tranche | 391299.89 | 653677.34 | 262377.45 | 391299.89 | 100% | 100% | 122.5% | 112.4% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-09 | 2004-11-30 | 2005-12-29 | 174 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tagubanhan | 063001030 | Artificial Coral Reef | 1 | 643936.45 | 207414.84 | 436521.61 | 207414.84 | 3rd Tranche | 443779.11 | 651193.95 | 207414.84 | 443779.11 | 100% | 100% | 101.7% | 101.1% | 100% | 2005-08-03 | 2005-08-23 | 2005-12-06 | 2006-06-30 | no data | 206 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tagubanhan | 063001030 | 1 Classroom School Building | 1 | 566650 | 495430 | 71220 | 495416.2 | 1st Tranche | 64955 | 558406.4 | 495416.2 | 62990.2 | 100% | 96.98% | 91.2% | 98.55% | 100% | 2006-07-12 | 2006-08-08 | 2007-06-30 | 2008-03-01 | no data | 245 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tagubanhan | 063001030 | Installation of Electricity Generating Systems | 1 | 840405 | 707980 | 132425 | 674383 |  | 122573 | 796956 | 674383 | 122573 | 100% | 100% | 92.56% | 94.83% | 100% | 2009-01-31 | no data | 2009-05-08 | 2009-06-30 | 2009-07-14 | 53 | 172 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Taguhangin | 063001031 | Water Supply System | 1 | 1537799.45 | 1298762.27 | 239037.18 | 1298762.27 | 3rd Tranche | 289272.18 | 1588034.45 | 1298762.27 | 289272.18 | 100% | 100% | 121% | 103.3% | 100% | 2004-02-03 | 2005-04-23 | 2004-05-31 | 2005-02-28 | 2005-06-08 | 273 | 171 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Taguhangin | 063001031 | Day Care Center | 1 | 541508.11 | 496380.43 | 45127.68 | 496380.43 | 3rd Tranche | 70787.68 | 567168.11 | 496380.43 | 70787.68 | 100% | 100% | 156.9% | 104.7% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-20 | 2006-05-31 | no data | 223 | 171 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Taguhangin | 063001031 | 2 Classroom School Building | 1 | 966892 | 868783.01 | 98108.99 | 868783.01 | 2nd Tranche | 118915.75 | 971559.99 | 868783.01 | 102776.98 | 100% | 86.43% | 121.2% | 100.5% | 100% | 2006-07-12 | 2006-08-08 | 2006-11-07 | 2008-03-01 | no data | 480 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Taguhangin | 063001031 | Construction of Health Station | 1 | 772100 | 573190 | 198910 | 541690 | 1st | 203045 | 744735 | 541690 | 203045 | 100% | 100% | 102.1% | 96.46% | 100% | 2009-01-31 | no data | 2009-04-20 | 2009-07-20 | no data | 91 | 176 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tanduyan | 063001032 | Health Station | 1 | 577239.18 | 449569.76 | 127669.42 | 449569.76 | 3rd Tranche | 160208.76 | 609778.52 | 449569.76 | 160208.76 | 100% | 100% | 125.5% | 105.6% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-08 | 2004-11-13 | 2005-01-19 | 158 | 140 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tanduyan | 063001032 | Road Upgrading | 1 | 894711 | 592892 | 301819 | 474313.6 | 1st Tranche | 324515.45 | 775641.11 | 474313.6 | 301327.51 | 100% | 92.85% | 107.5% | 86.69% | 100% | 2006-07-12 | 2006-08-08 | 2007-06-30 | 2007-06-30 | no data | 0 | 141 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tipacla | 063001033 | Day Care Center | 1 | 465618.66 | 330746.03 | 134872.63 | 330746.03 | 3rd Tranche | 170636.63 | 501382.66 | 330746.03 | 170636.63 | 100% | 100% | 126.5% | 107.7% | 100% | 2004-02-03 | 2005-04-23 | 2004-06-06 | 2004-08-21 | 2005-03-08 | 76 | 282 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tipacla | 063001033 | Health Station | 1 | 625331.54 | 585567.89 | 39763.65 | 585567.89 | 3rd Tranche | 60373.65 | 645941.54 | 585567.89 | 60373.65 | 100% | 100% | 151.8% | 103.3% | 100% | 2005-08-03 | 2005-08-23 | 2005-11-17 | 2006-05-31 | no data | 195 | 282 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tipacla | 063001033 | Road Upgrading with Spot Concreting | 1 | 1069610 | 856360 | 213250 | 809113.5 |  | 185318.75 | 994432.25 | 809113.5 | 185318.75 | 100% | 100% | 86.9% | 92.97% | 100% | 2009-01-31 | no data | 2009-05-06 | 2009-07-03 | no data | 58 | 275 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tubogan | 063001034 | Barangay Road Rehabilitation | 1 | 423605.4 | 360335.25 | 63270.15 | 360335.25 | 3rd Tranche | 129489.4 | 489824.65 | 360335.25 | 129489.4 | 100% | 100% | 204.7% | 115.6% | 100% | 2004-02-03 | 2005-04-23 | 2004-07-15 | 2004-12-31 | 2005-01-31 | 169 | 110 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tubogan | 063001034 | Health Station | 1 | 661856.34 | 588225.89 | 73630.45 | 588225.89 | 3rd Tranche | 96851.8 | 685077.69 | 588225.89 | 96851.8 | 100% | 100% | 131.5% | 103.5% | 100% | 2005-08-03 | 2005-08-23 | 2005-10-20 | 2006-04-30 | no data | 192 | 110 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Ajuy | 063001 | Tubogan | 063001034 | Construction of Day Care Center | 1 | 680495 | 568940 | 111555 | 536047 | 1st | 105316 | 641363 | 536047 | 105316 | 100% | 100% | 94.41% | 94.25% | 100% | 2009-01-31 | no data | 2009-04-06 | 2009-07-06 | no data | 91 | 134 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Bugnay | 063008002 | Barangay Road Rehabilitation | 1 | 593622.2 | 223591.7 | 370030.5 | 223591.7 | 3rd Tranche | 626522.5 | 850114.2 | 223591.7 | 626522.5 | 100% | 100% | 169.3% | 143.2% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-31 | 2005-05-23 | 2005-11-30 | 357 | 96 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | California | 063008004 | Warehouse | 1 | 440842.34 | 301350.34 | 139492 | 301350.34 | 3rd Tranche | 278345 | 579695.34 | 301350.34 | 278345 | 100% | 100% | 199.5% | 131.5% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-27 | 2005-03-22 | 2005-04-21 | 299 | 149 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | California - C4 | 063008004 | Improvement of FMR | 4 | 9882600 | 4517467 | 5365133 | 4517467 | 1st | 5114233 | 9631700 | 4517467 | 5114233 | 100% | 100% | 95.32% | 97.46% | 100% | 2009-02-19 | no data | 2009-04-20 | 2009-08-31 | no data | 133 | 745 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Del Pilar | 063008005 | Baby Cono | 1 | 703759.28 | 286939.28 | 416820 | 286939.28 | 3rd Tranche | 147472.75 | 434412.03 | 286939.28 | 147472.75 | 100% | 100% | 35.38% | 61.73% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-21 | 2004-10-05 | 2005-03-23 | 137 | 116 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Del Pilar | 063008005 | Health Station | 1 | 843019.83 | 719217.41 | 123802.42 | 719217.41 | 3rd Tranche | 125426.15 | 844643.56 | 719217.41 | 125426.15 | 100% | 100% | 101.3% | 100.2% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-03 | 2006-06-14 | 2006-06-15 | 254 | 116 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Del Pilar - C2 | 063008005 | Const. of Box Culvert | 2 | 1607172 | 1287353 | 319819 | 1287353 | 1st | 270176.85 | 1557529.85 | 1287353 | 270176.85 | 100% | 100% | 84.48% | 96.91% | 100% | 2009-02-19 | no data | 2009-04-15 | 2009-08-31 | no data | 138 | 399 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Dela Peña | 063008006 | Barangay Road Rehabilitation | 1 | 478711.18 | 334369.18 | 144342 | 334369.18 | 3rd Tranche | 571732.5 | 906101.68 | 334369.18 | 571732.5 | 100% | 100% | 396.1% | 189.3% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-15 | 2004-10-22 | 2005-03-16 | 160 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Dela Peña | 063008006 | Health Station | 1 | 748565.51 | 594828.01 | 153737.5 | 594828.01 | Last Tranche | 159077.5 | 753905.51 | 594828.01 | 159077.5 | 100% | 100% | 103.5% | 100.7% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-03 | 2006-03-31 | 2006-06-17 | 179 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Dela Pena - C5 | 063008006 | Water System Level II | 5 | 12184077.8 | 7001560 | 5182517.8 | 7001560 | 1st Tranche | 3417620 | 10419180 | 7001560 | 3417620 | 100% | 100% | 65.95% | 85.51% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-27 | 2008-03-01 | no data | 430 | 785 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | General Luna | 063008007 | Level II Water System | 1 | 906632 | 451125 | 455507 | 451125 | 3rd Tranche | 460685.14 | 911810.14 | 451125 | 460685.14 | 100% | 100% | 101.1% | 100.6% | 100% | 2003-12-16 | 2004-03-09 | 2004-06-11 | 2005-01-20 | 2005-03-23 | 223 | 242 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | General Luna | 063008007 | Science Laboratory room w/ facilities | 1 | 1061742.5 | 783395 | 278347.5 | 783395 | 3rd Tranche | 280272.46 | 1063667.46 | 783395 | 280272.46 | 100% | 100% | 100.7% | 100.2% | 100% | 2005-07-12 | 2005-08-18 | 2005-09-26 | 2006-06-14 | 2006-06-15 | 261 | 242 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | La Fortuna | 063008009 | Baby Cono | 1 | 629211.18 | 339541.18 | 289670 | 339541.18 | 3rd Tranche | 368155 | 707696.18 | 339541.18 | 368155 | 100% | 100% | 127.1% | 112.5% | 100% | 2003-12-16 | 2004-03-09 | 2004-06-09 | 2005-04-01 | 2005-04-21 | 296 | 235 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | La Fortuna | 063008009 | 2 Sets Farm Equipment & Storage Structure | 1 | 863609.35 | 747500 | 116109.35 | 747500 | Last Tranche | 117698 | 865198 | 747500 | 117698 | 100% | 100% | 101.4% | 100.2% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-19 | 2006-06-18 | 2006-06-20 | 242 | 235 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Lipata | 063008010 | Barangay Road concreting | 1 | 549054.77 | 319771.44 | 229283.33 | 319771.44 | 3rd Tranche | 276202.5 | 595973.94 | 319771.44 | 276202.5 | 100% | 100% | 120.5% | 108.5% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-21 | 2004-12-19 | 2005-03-16 | 212 | 409 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Lipata | 063008010 | Health Station | 1 | 765225.51 | 559888.01 | 205337.5 | 559888.01 | Last Tranche | 201825 | 761713.01 | 559888.01 | 201825 | 100% | 100% | 98.29% | 99.54% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-10 | 2006-04-14 | 2006-06-17 | 186 | 409 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Lipata - C5 | 063008010 | Water System Level II | 5 | 12184077.8 | 7001560 | 5182517.8 | 7001560 | 1st Tranche | 3417620 | 10419180 | 7001560 | 3417620 | 100% | 100% | 65.95% | 85.51% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-27 | 2008-03-01 | no data | 430 | 785 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Natividad | 063008011 | Day Care Center | 1 | 443706.94 | 318894.94 | 124812 | 318894.94 | 3rd Tranche | 129942 | 448836.94 | 318894.94 | 129942 | 100% | 100% | 104.1% | 101.2% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-13 | 2004-11-27 | 2005-03-22 | 198 | 364 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Nueva Sevilla | 063008013 | Level II Water System | 1 | 481544.32 | 336727.82 | 144816.5 | 336727.82 | 3rd Tranche | 500192.96 | 836920.78 | 336727.82 | 500192.96 | 100% | 100% | 345.4% | 173.8% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-04 | 2005-01-31 | 2005-03-17 | 272 | 369 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Nueva Sevilla | 063008013 | Road Concreting | 1 | 1049714.61 | 269174.48 | 780540.13 | 269174.48 | 3rd Tranche | 495326.69 | 764501.17 | 269174.48 | 495326.69 | 100% | 100% | 63.46% | 72.83% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-29 | 2007-05-16 | no data | 564 | 369 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Nueva Sevilla | 063008013 | Artificial Reef | 1 | 860095.1 | 612130 | 247965.1 | 612130 | 1st | 220110.05 | 832240.05 | 612130 | 220110.05 | 100% | 100% | 88.77% | 96.76% | 100% | 2009-02-19 | no data | 2009-05-22 | 2009-08-31 | no data | 101 | 1985 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Poblacion | 063008014 | Drainage System | 1 | 1033204.4 | 458468.85 | 574735.55 | 458468.85 | 3rd Tranche | 611824.33 | 1070293.18 | 458468.85 | 611824.33 | 100% | 100% | 106.5% | 103.6% | 100% | 2003-12-16 | 2004-03-09 | 2004-04-26 | 2005-02-18 | 2005-03-17 | 298 | 950 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Poblacion | 063008014 | Improvement of Drainage System (1 Line 2-Barrel RCPC) | 1 | 237869.4 | 185790 | 52079.4 | 185790 | 1st | 47892.2 | 233682.2 | 185790 | 47892.2 | 100% | 100% | 91.96% | 98.24% | 100% | 2009-02-19 | no data | 2009-04-25 | 2009-08-31 | no data | 128 | 1195 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Puerto Princesa | 063008016 | Health Station | 1 | 455278.84 | 348888.84 | 106390 | 348888.84 | 3rd Tranche | 375954.75 | 724843.59 | 348888.84 | 375954.75 | 100% | 100% | 353.4% | 159.2% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-05 | 2004-10-18 | 2005-03-22 | 166 | 153 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Puerto Princesa | 063008016 | Water System Level II | 1 | 1583059.84 | 1166400 | 416659.84 | 1166400 | Last Tranche | 417936.65 | 1584336.65 | 1166400 | 417936.65 | 100% | 100% | 100.3% | 100.1% | 100% | 2005-07-12 | 2005-08-18 | 2005-09-05 | 2006-06-18 | 2006-06-26 | 286 | 153 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Puerto Princesa | 063008016 | Road Upgrading with Head Wall and RCPC | 1 | 482127.76 | 401240 | 80887.76 | 370290 | 1st Tranche | 708209.26 | 1078499.26 | 370290 | 708209.26 | 100% | 100% | 875.5% | 223.7% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-15 | 2007-03-07 | no data | 82 | 150 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Puerto Princesa - C2 | 063008016 | Improvement of FMR | 2 | 6348419.5 | 3939032 | 2409387.5 | 3939032 | 1st | 2119156.25 | 6058188.25 | 3939032 | 2119156.25 | 100% | 100% | 87.95% | 95.43% | 100% | 2009-02-19 | no data | 2009-04-20 | 2009-08-31 | no data | 133 | 345 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Rizal | 063008017 | Farm Equipment & Storage | 1 | 392880.51 | 302448.18 | 90432.33 | 302448.18 | 3rd Tranche | 105941 | 408389.18 | 302448.18 | 105941 | 100% | 100% | 117.1% | 103.9% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-11 | 2004-09-05 | 2005-03-16 | 117 | 193 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Rizal | 063008017 | Day Care Center | 1 | 710555.57 | 521129.07 | 189426.5 | 521129.07 | Last Tranche | 182191.75 | 703320.82 | 521129.07 | 182191.75 | 100% | 100% | 96.18% | 98.98% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-05 | 2006-06-14 | 2006-06-15 | 252 | 193 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Rizal | 063008017 | Improvement of FMR | 1 | 951827 | 570972 | 380855 | 570972 |  | 360580 | 931552 | 570972 | 360580 | 100% | 100% | 94.68% | 97.87% | 100% | 2009-02-19 | no data | 2009-05-22 | 2009-08-31 | no data | 101 | 189 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Rizal - C5 | 063008017 | Water System Level II | 5 | 12184077.8 | 7001560 | 5182517.8 | 7001560 | 1st Tranche | 3417620 | 10419180 | 7001560 | 3417620 | 100% | 100% | 65.95% | 85.51% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-27 | 2008-03-01 | no data | 430 | 785 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Antonio | 063008019 | Health Station | 1 | 470878.84 | 324864.84 | 146014 | 324864.84 | 3rd Tranche | 199274 | 524138.84 | 324864.84 | 199274 | 100% | 100% | 136.5% | 111.3% | 100% | 2003-12-16 | 2004-03-09 | 2004-06-01 | 2005-02-26 | 2005-03-21 | 270 | 397 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Fernando | 063008021 | Health Station | 1 | 455278.84 | 363789.84 | 91489 | 363789.84 | 3rd Tranche | 95870 | 459659.84 | 363789.84 | 95870 | 100% | 100% | 104.8% | 101% | 100% | 2003-12-16 | 2004-03-09 | 2004-06-15 | 2005-04-26 | 2005-05-21 | 315 | 221 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Francisco | 063008023 | Health Station | 1 | 455278.84 | 332109.84 | 123169 | 332109.84 | 3rd Tranche | 157602.93 | 489712.77 | 332109.84 | 157602.93 | 100% | 100% | 128% | 107.6% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-31 | 2004-11-15 | 2005-03-22 | 168 | 163 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Geronimo | 063008024 | Post Harvest Facility | 1 | 658878.19 | 385695.69 | 273182.5 | 385695.69 | 3rd Tranche | 251200.5 | 636896.19 | 385695.69 | 251200.5 | 100% | 100% | 91.95% | 96.66% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-11 | 2004-12-20 | 2005-03-16 | 223 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Geronimo | 063008024 | Health Station | 1 | 773360.51 | 523323.01 | 250037.5 | 523323.01 | Last Tranche | 258162.5 | 781485.51 | 523323.01 | 258162.5 | 100% | 100% | 103.2% | 101.1% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-05 | 2006-06-13 | 2006-06-15 | 251 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Geronimo - C5 | 063008024 | Water System Level II | 5 | 12184077.8 | 7001560 | 5182517.8 | 7001560 | 1st Tranche | 3417620 | 10419180 | 7001560 | 3417620 | 100% | 100% | 65.95% | 85.51% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-27 | 2008-03-01 | no data | 430 | 785 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Lucas | 063008026 | Mechanical Drier & Baby Cono | 1 | 897508.3 | 270386.94 | 627121.36 | 270386.94 | 3rd Tranche | 773726.61 | 1044113.55 | 270386.94 | 773726.61 | 100% | 100% | 123.4% | 116.3% | 100% | 2003-12-16 | 2004-03-09 | 2004-06-04 | 2005-04-18 | 2005-09-12 | 318 | 750 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Lucas | 063008026 | Health Station | 1 | 830681.52 | 683500 | 147181.52 | 683500 | Last Tranche | 151288.1 | 834788.1 | 683500 | 151288.1 | 100% | 100% | 102.8% | 100.5% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-12 | 2006-06-18 | 2006-06-20 | 249 | 750 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Miguel | 063008027 | Barangay Road Rehabilitation | 1 | 826961.96 | 266407.96 | 560554 | 266407.96 | 3rd Tranche | 614734.04 | 881142 | 266407.96 | 614734.04 | 100% | 100% | 109.7% | 106.6% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-25 | 2005-03-30 | 2005-11-30 | 309 | 293 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Miguel | 063008027 | Health Station | 1 | 746360.51 | 593323.01 | 153037.5 | 593323.01 | 3rd Tranche | 163277.5 | 756600.51 | 593323.01 | 163277.5 | 100% | 100% | 106.7% | 101.4% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-29 | 2006-06-11 | 2006-06-26 | 225 | 293 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Miguel - C5 | 063008027 | Water System Level II | 5 | 12184077.8 | 7001560 | 5182517.8 | 7001560 | 1st Tranche | 3417620 | 10419180 | 7001560 | 3417620 | 100% | 100% | 65.95% | 85.51% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-27 | 2008-03-01 | no data | 430 | 785 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | San Roque | 063008029 | Health Station | 1 | 476878.84 | 277290.84 | 199588 | 277290.83 | 3rd Tranche | 274685.26 | 551976.09 | 277290.83 | 274685.26 | 100% | 100% | 137.6% | 115.7% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-07 | 2004-12-16 | 2005-02-27 | 223 | 235 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Santiago | 063008030 | 2 Classroom High School Building | 1 | 1047590.78 | 472232.78 | 575358 | 472232.78 | 3rd Tranche | 612679.25 | 1084912.03 | 472232.78 | 612679.25 | 100% | 100% | 106.5% | 103.6% | 100% | 2003-12-16 | 2004-03-09 | 2004-04-27 | 2005-02-12 | 2005-04-17 | 291 | 221 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Santiago | 063008030 | Construction of Mini-market | 1 | 488023.97 | 340739.5 | 147284.47 | 340739.5 | 1st | 126584.74 | 467324.24 | 340739.5 | 126584.74 | 100% | 100% | 85.95% | 95.76% | 100% | 2009-02-19 | no data | 2009-04-16 | 2009-08-31 | no data | 137 | 447 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Santo Domingo | 063008031 | Concreting of FMR | 1 | 1205186.6 | 977560 | 227626.6 | 977560 |  | 176256 | 1153816 | 977560 | 176256 | 100% | 100% | 77.43% | 95.74% | 100% | 2009-02-19 | no data | 2009-05-28 | 2009-08-31 | no data | 95 | 223 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Sto. Domingo | 063008031 | Health Station | 1 | 439878.84 | 278217.84 | 161661 | 278217.84 | 3rd Tranche | 162980 | 441197.84 | 278217.84 | 162980 | 100% | 100% | 100.8% | 100.3% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-26 | 2005-01-28 | 2005-02-20 | 247 | 197 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Sto. Domingo | 063008031 | Road Upgrading with Head Wall | 1 | 1113201.44 | 397200 | 716001.44 | 397200 | Last Tranche | 572427.38 | 969627.38 | 397200 | 572427.38 | 100% | 100% | 79.95% | 87.1% | 100% | 2006-07-10 | 2006-08-25 | 2006-12-04 | 2007-09-30 | no data | 300 | 186 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Sto. Tomas | 063008032 | Barangay Road Rehabilitation | 1 | 1738130.9 | 213770.9 | 1524360 | 213770.9 | 3rd Tranche | 1516355 | 1730125.9 | 213770.9 | 1516355 | 100% | 100% | 99.47% | 99.54% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-04 | 2004-12-16 | 2005-03-23 | 226 | 231 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Ugasan | 063008033 | Health Station | 1 | 468878.84 | 349238.84 | 119640 | 349238.84 | 3rd Tranche | 117145 | 466383.84 | 349238.84 | 117145 | 100% | 100% | 97.91% | 99.47% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-26 | 2005-02-22 | 2005-03-21 | 272 | 212 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Ugasan | 063008033 | Day Care Center | 1 | 801705.5 | 638322 | 163383.5 | 638322 | 3rd Tranche | 164591.35 | 802913.35 | 638322 | 164591.35 | 100% | 100% | 100.7% | 100.2% | 100% | 2005-07-12 | 2005-08-18 | 2005-10-12 | 2006-09-02 | 2006-09-05 | 325 | 212 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Vista Alegre | 063008034 | Day Care Center | 1 | 425706.94 | 243876.94 | 181830 | 243876.94 | 3rd Tranche | 202734.8 | 446611.74 | 243876.94 | 202734.8 | 100% | 100% | 111.5% | 104.9% | 100% | 2003-12-16 | 2004-03-09 | 2004-05-03 | 2004-10-19 | 2005-02-26 | 169 | 407 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Barotac Viejo | 063007 | Vista Alegre | 063008034 | Health Center | 1 | 704104.7 | 528178 | 175926.7 | 528178 | 1st | 157180.85 | 685358.85 | 528178 | 157180.85 | 100% | 100% | 89.34% | 97.34% | 100% | 2009-02-19 | no data | 2009-04-15 | 2009-08-31 | no data | 138 | 410 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Agba-o | 063010001 | Acquisition of 1 unit travelling rice mill with 37.5 sq.m garage | 1 | 827000 | 547090 | 279910 | 437672 |  | 277090 | 714762 | 437672 | 277090 | 100% | 100% | 98.99% | 86.43% | 100% | 2008-09-09 | no data | 2009-04-13 | 2009-07-31 | no data | 109 | 95 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Alabidhan | 063010002 | Road Improvement - 1,713 ln.m Farm to Market Road | 1 | 763000 | 480600 | 282400 | 432540 |  | 280000 | 712540 | 432540 | 280000 | 100% | 100% | 99.15% | 93.39% | 100% | 2008-09-09 | no data | 2009-04-13 | 2009-08-31 | no data | 140 | 211 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Bulabog | 063010003 | Road Improvement of 2,030 ln.m Farm to Market road | 1 | 919000 | 646600 | 272400 | 581880 |  | 278340 | 860220 | 581880 | 278340 | 100% | 100% | 102.2% | 93.6% | 100% | 2008-09-09 | no data | 2009-04-13 | 2009-08-31 | no data | 140 | 156 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Cairohan | 063010004 | Water System Level I & II | 1 | 842242 | 785677 | 56565 | 707109.3 | 1st Tranche | 68833.32 | 775942.62 | 707109.3 | 68833.32 | 100% | 100% | 121.7% | 92.13% | 100% | 2008-02-13 | no data | 2008-07-15 | 2009-08-30 | no data | 411 | 91 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Guinhulacan | 063010005 | Health Station | 1 | 665378 | 583953 | 81425 | 525557.7 | 1st Tranche | 85042 | 610599.7 | 525557.7 | 85042 | 100% | 100% | 104.4% | 91.77% | 100% | 2008-02-13 | no data | 2008-07-02 | 2009-08-30 | no data | 424 | 125 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Inamyungan | 063010006 | Road Upgrading | 1 | 834741 | 783981 | 50760 | 705582.9 | 1st Tranche | 35000 | 740582.9 | 705582.9 | 35000 | 100% | 100% | 68.95% | 88.72% | 100% | 2008-02-13 | no data | 2008-07-25 | 2009-06-30 | no data | 340 | 101 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Malitbog Ilawod | 063010007 | Road Upgrading & New Construction | 1 | 844562 | 784412 | 60150 | 705970.8 | 1st Tranche | 44630 | 750600.8 | 705970.8 | 44630 | 100% | 100% | 74.2% | 88.87% | 100% | 2008-02-13 | no data | 2008-07-25 | 2009-08-31 | no data | 402 | 110 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Malitbog Ilaya | 063010008 | Road Upgrading | 1 | 545293 | 491613 | 53680 | 442451.7 |  | 52272 | 494723.7 | 442451.7 | 52272 | 100% | 100% | 97.38% | 90.73% | 100% | 2008-02-13 | no data | 2008-07-28 | 2009-04-01 | n/a | 247 | 132 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Ngingi-an | 063010009 | Constrcution of Water System Level II with rectangular well ground tank, main and distribution line and tapstand | 1 | 1089000 | 777005.34 | 311994.66 | 699304.8 |  | 311386.16 | 1010690.96 | 699304.8 | 311386.16 | 100% | 100% | 99.8% | 92.81% | 100% | 2008-09-09 | no data | 2009-04-13 | 2009-08-31 | no data | 140 | 112 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Poblacion | 063010010 | Road improvement of 1,990 ln.m Farm to Market road | 1 | 854100 | 551600 | 302500 | 496440 |  | 310340 | 806780 | 496440 | 310340 | 100% | 100% | 102.6% | 94.46% | 100% | 2008-09-09 | no data | 2009-04-13 | 2009-08-31 | no data | 140 | 477 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Quinar-upan | 063010012 | Road Improvement - 1,740 ln.m Farm to market road with 260 ln.m spot concreting | 1 | 1657004.68 | 1197104.68 | 459900 | 1077394.21 |  | 437625 | 1515019.21 | 1077394.21 | 437625 | 100% | 100% | 95.16% | 91.43% | 100% | 2008-09-09 | no data | 2009-03-21 | 2009-08-31 | no data | 163 | 294 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Tapacon | 063010013 | Road Upgrading | 1 | 575146 | 529246 | 45900 | 476321.4 | 1st Tranche | 43612 | 519933.4 | 476321.4 | 43612 | 100% | 100% | 95.02% | 90.4% | 100% | 2008-02-13 | no data | 2008-07-27 | 2009-03-01 | n/a | 217 | 100 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Bingawan | 063010 | Tubod | 063010014 | Road Upgrading | 1 | 1013886 | 241118 | 772768 | 217006.2 |  | 768893 | 974274.2 | 217006.2 | 757268 | 100% | 98.49% | 99.5% | 96.09% | 100% | 2008-02-13 | no data | 2008-12-08 | 2009-08-31 | no data | 266 | 80 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Agcalaga | 063013002 | 1 Classroom School Building | 1 | 707000 | 539886.93 | 167113.07 | 485898.23 | 2nd Tranche | 167233.07 | 653131.3 | 485898.23 | 167233.07 | 100% | 100% | 100.1% | 92.38% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-07 | 2008-03-28 | 2008-07-04 | 507 | 186 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Aglonok | 063013004 | Hanging Bridge | 1 | 2026548 | 1876398.94 | 150149.06 | 1688759.05 | 2nd Tranche | 93795 | 1782554.05 | 1688759.05 | 93795 | 100% | 100% | 62.47% | 87.96% | 100% | 2005-08-09 | 2005-08-31 | 2006-02-27 | 2006-07-27 | 2006-08-21 | 150 | 140 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Alibunan | 063013006 | Day Care Center | 1 | 625100 | 495495.08 | 129604.92 | 477915.57 | 2nd Tranche | 129604.92 | 607520.49 | 477915.57 | 129604.92 | 100% | 100% | 100% | 97.19% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-13 | 2009-02-25 | n/a | 835 | 460 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badlan Grande | 063013007 | Post Harvest Facilities | 1 | 630598.55 | 317146.57 | 313451.98 | 317146.57 | 3rd Tranche | 304305.34 | 621451.91 | 317146.57 | 304305.34 | 100% | 100% | 97.08% | 98.55% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-31 | 2005-01-11 | 2005-01-11 | 225 | 202 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badlan Grande | 063013007 | Pre & Post Harvest Facilities | 1 | 543535.16 | 498866.77 | 44668.39 | 498866.77 | 3rd Tranche | 50168.29 | 549035.06 | 498866.77 | 50168.29 | 100% | 100% | 112.3% | 101% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-13 | 2005-11-17 | 2006-01-07 | 35 | 84 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badlan Grande | 063013007 | Solar Dryer | 1 | 611000 | 459554.87 | 151445.13 | 413599.38 | 2nd Tranche | 151545.13 | 565144.51 | 413599.38 | 151545.13 | 100% | 100% | 100.1% | 92.5% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-05 | 2009-05-30 | no data | 968 | 202 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badu | 063013009 | School Building 2 Classroom | 1 | 672552.82 | 575060.6 | 97492.22 | 575060.6 | 3rd Tranche | 99826.57 | 674887.17 | 575060.6 | 99826.57 | 100% | 100% | 102.4% | 100.3% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-14 | 2006-05-11 | 2006-05-16 | 178 | 289 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Badu | 063013009 | Pre & Post Harvest Facilities | 1 | 574000 | 432361.18 | 141638.82 | 432361.18 | 100% Tranche | 141638.82 | 532195 | 432361.18 | 99833.82 | 100% | 70.48% | 100% | 92.72% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-03 | 2007-02-25 | 2008-07-04 | 114 | 260 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Baje San Julian | 063013062 | School Building 1 Classroom | 1 | 660678.58 | 597455.58 | 63223 | 597455.58 | 3rd Tranche | 65991.7 | 663447.28 | 597455.58 | 65991.7 | 100% | 100% | 104.4% | 100.4% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-22 | 2006-05-18 | 2006-06-23 | 208 | 106 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Baje San Julian | 063013062 | Pre & Post Harvest Facilities | 1 | 380100 | 306990.5 | 73109.5 | 306990.5 | 100% Tranche | 73209.5 | 380200 | 306990.5 | 73209.5 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-13 | 2007-02-25 | 2008-07-04 | 104 | 102 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Balaticon | 063013011 | Post Harvest Facilities | 1 | 387434.62 | 366896.62 | 20538 | 366896.62 | 3rd Tranche | 23173 | 390069.62 | 366896.62 | 23173 | 100% | 100% | 112.8% | 100.7% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-07 | 2004-12-01 | 2005-01-23 | 177 | 92 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Banban Grande | 063013012 | Health Station | 1 | 634457.17 | 412508.31 | 221948.86 | 412508.31 | 3rd Tranche | 206779.3 | 619287.61 | 412508.31 | 206779.3 | 100% | 100% | 93.17% | 97.61% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-13 | 2005-01-08 | 2005-01-08 | 240 | 140 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Banban Grande | 063013012 | Pre & Post Harvest Facilities | 1 | 601000 | 510168.73 | 90831.27 | 510168.73 | 100% Tranche | 557410 | 1067578.73 | 510168.73 | 557410 | 100% | 100% | 613.7% | 177.6% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-18 | 2007-02-13 | 2008-07-04 | 118 | 140 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Banban Pequeño | 063013013 | School Building 1 Classroom | 1 | 683784.5 | 583769.75 | 100014.75 | 583769.75 | 3rd Tranche | 101524.75 | 685294.5 | 583769.75 | 101524.75 | 100% | 100% | 101.5% | 100.2% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-17 | 2006-05-04 | 2006-05-30 | 199 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Banban Pequeño | 063013013 | Pre & Post Harvest Facilities | 1 | 671000 | 558537.48 | 112462.52 | 558537.48 | 100% Tranche | 112562.53 | 671100.01 | 558537.48 | 112562.53 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2007-02-23 | 2008-07-04 | 95 | 164 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Barrio Calinog | 063013022 | Post Harvest Facilities | 1 | 352798.97 | 327334.97 | 25464 | 327334.97 | 3rd Tranche | 31564 | 358898.97 | 327334.97 | 31564 | 100% | 100% | 124% | 101.7% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-21 | 2005-01-10 | 2005-01-20 | 234 | 114 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Cabagiao | 063013017 | Health Station | 1 | 404991.63 | 322687.02 | 82304.61 | 322687.02 | 3rd Tranche | 114717.84 | 437404.86 | 322687.02 | 114717.84 | 100% | 100% | 139.4% | 108% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-03 | 2004-12-25 | 2005-01-20 | 205 | 189 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Cabugao | 063013017 | Day Care Center | 1 | 578901.12 | 340487.28 | 238413.84 | 340487.28 | 3rd Tranche | 222767.55 | 563254.83 | 340487.28 | 222767.55 | 100% | 100% | 93.44% | 97.3% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-07 | 2005-03-01 | 2005-03-05 | 267 | 80 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Cahigon - C4 | 063013020 | Barangay Road Rehabilitation | 4 | 10606163.62 | 5340751.22 | 5265412.4 | 5340751.22 | 3rd Tranche | 1718523.04 | 7059274.26 | 5340751.22 | 1718523.04 | 100% | 100% | 32.64% | 66.56% | 100% | 2004-02-12 | 2004-04-13 | 2004-09-06 | 2009-08-31 | no data | 1820 | 820 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Binolosan Pequeno | 063013016 | Barangay Road Rehabilitation | 4 | 10606163.62 | 5340751.22 | 5265412.4 | 5340751.22 | 3rd Tranche | 1718523.04 | 7059274.26 | 5340751.22 | 1718523.04 | 100% | 100% | 32.64% | 66.56% | 100% | 2004-02-12 | 2004-04-13 | 2004-09-06 | 2009-08-31 | no data | 1820 | 820 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Supanga | 063013074 | Barangay Road Rehabilitation | 4 | 10606163.62 | 5340751.22 | 5265412.4 | 5340751.22 | 3rd Tranche | 1718523.04 | 7059274.26 | 5340751.22 | 1718523.04 | 100% | 100% | 32.64% | 66.56% | 100% | 2004-02-12 | 2004-04-13 | 2004-09-06 | 2009-08-31 | no data | 1820 | 820 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Caratagan | 063013025 | Barangay Road Rehabilitation | 4 | 10606163.62 | 5340751.22 | 5265412.4 | 5340751.22 | 3rd Tranche | 1718523.04 | 7059274.26 | 5340751.22 | 1718523.04 | 100% | 100% | 32.64% | 66.56% | 100% | 2004-02-12 | 2004-04-13 | 2004-09-06 | 2009-08-31 | no data | 1820 | 820 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Camalongo | 063013023 | Health Station | 1 | 723145.51 | 647823.1 | 75322.41 | 647823.1 | 3rd Tranche | 71617.46 | 719440.56 | 647823.1 | 71617.46 | 100% | 100% | 95.08% | 99.49% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-28 | 2006-05-04 | 2006-05-11 | 188 | 155 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Camalongo | 063013023 | 2 Classroom School Building | 1 | 1126500 | 862131.18 | 264368.82 | 775918.07 | 2nd Tranche | 264468.82 | 1040386.89 | 775918.07 | 264468.82 | 100% | 100% | 100% | 92.36% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-13 | 2008-03-28 | 2008-07-04 | 501 | 148 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Canabajan | 063013024 | Health Station | 1 | 641450.18 | 443923.26 | 197526.92 | 443923.26 | 3rd Tranche | 178241.3 | 622164.56 | 443923.26 | 178241.3 | 100% | 100% | 90.24% | 96.99% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-20 | 2004-11-18 | 2005-12-23 | 182 | 240 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Canabajan | 063013024 | Pre & Post Harvest Facilities | 1 | 930000 | 769803.75 | 160196.25 | 717410.71 | 2nd Tranche | 160296.25 | 877706.96 | 717410.71 | 160296.25 | 100% | 100% | 100.1% | 94.38% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-08 | 2008-11-01 | no data | 755 | 230 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Dalid | 063013027 | 1 Classroom School Building | 1 | 720000 | 562332.38 | 157667.62 | 506099.14 | 2nd Tranche | 157667.62 | 663766.76 | 506099.14 | 157667.62 | 100% | 100% | 100% | 92.19% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-16 | 2008-08-01 | no data | 624 | 236 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Datagan | 063013028 | Health Station | 1 | 766171.63 | 574374.24 | 191797.39 | 574374.24 | 3rd Tranche | 230572.4 | 804946.64 | 574374.24 | 230572.4 | 100% | 100% | 120.2% | 105.1% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-24 | 2006-04-27 | 2006-07-22 | 185 | 172 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Datagan | 063013028 | 1 Classroom School Building | 1 | 795000 | 573093.99 | 221906.01 | 515784.59 | 2nd Tranche | 222006.01 | 737790.6 | 515784.59 | 222006.01 | 100% | 100% | 100% | 92.8% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2008-04-30 | no data | 527 | 158 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Gama Grande | 063013030 | Hanging Bridge | 1 | 1625565.53 | 760298.99 | 865266.54 | 760298.99 | 3rd Tranche | 862097.33 | 1622396.32 | 760298.99 | 862097.33 | 100% | 100% | 99.63% | 99.81% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-18 | 2005-06-28 | 2006-07-19 | 406 | 143 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Gama Grande | 063013030 | Level II Potable Water System | 1 | 821500 | 664406.65 | 157093.35 | 597965.99 | 2nd Tranche | 157193.35 | 755159.34 | 597965.99 | 157193.35 | 100% | 100% | 100.1% | 91.92% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2008-04-30 | no data | 527 | 143 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Gama Pequeño | 063013031 | Barangay Road Rehabilitation | 1 | 1066575.6 | 528862.32 | 537713.28 | 528862.32 | 3rd Tranche | 598657.14 | 1127519.46 | 528862.32 | 598657.14 | 100% | 100% | 111.3% | 105.7% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-11 | 2005-04-26 | 2005-07-04 | 319 | 78 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Gama Pequeño | 063013031 | Water System Level II | 1 | 1042189.23 | 941903.86 | 100285.37 | 941903.86 | 3rd Tranche | 87754.37 | 1029658.23 | 941903.86 | 87754.37 | 100% | 100% | 87.5% | 98.8% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-06 | 2006-06-29 | 2006-06-30 | 235 | 84 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Gama Pequeño | 063013031 | Pre & Post Harvest Facilities | 1 | 605400 | 510568.76 | 94831.24 | 510568.76 | 100% Tranche | 94931.24 | 605500 | 510568.76 | 94931.24 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-27 | 2007-02-13 | 2008-07-04 | 109 | 78 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Garangan | 063013032 | Level II Water System | 1 | 644340.01 | 513060.39 | 131279.62 | 513060.39 | 3rd Tranche | 141592.15 | 654652.54 | 513060.39 | 141592.15 | 100% | 100% | 107.9% | 101.6% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-25 | 2004-12-01 | no data | 190 | 147 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Garangan | 063013032 | 1 Classroom School Building | 1 | 707000 | 550470.94 | 156529.06 | 495423.85 | 2nd Tranche | 156629.06 | 652052.91 | 495423.85 | 156629.06 | 100% | 100% | 100.1% | 92.23% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-29 | 2009-05-30 | no data | 944 | 147 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Guinbonyugan | 063013034 | 1 Classroom School Building | 1 | 754300 | 559117.55 | 195182.45 | 553992.1 | 2nd Tranche | 199075.94 | 753068.04 | 553992.1 | 199075.94 | 100% | 100% | 102% | 99.84% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-27 | 2008-03-28 | no data | 518 | 116 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Guiso | 063013036 | Level II Water System | 1 | 811821.2 | 594960.47 | 216860.73 | 594960.47 | 3rd Tranche | 200294.18 | 795254.65 | 594960.47 | 200294.18 | 100% | 100% | 92.36% | 97.96% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-06 | 2004-12-01 | 2005-01-27 | 209 | 106 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Guiso | 063013036 | Day Care Center | 1 | 582200 | 490390.75 | 91809.25 | 441351.67 | 2nd Tranche | 91909.25 | 533260.92 | 441351.67 | 91909.25 | 100% | 100% | 100.1% | 91.59% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-03 | 2008-03-28 | 2008-07-04 | 511 | 106 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Hilwan | 063013037 | Road Construction | 1 | 4474947.88 | 2332174.28 | 2142773.6 | 2332174.28 | 3rd Tranche | 131234.5 | 2463408.78 | 2332174.28 | 131234.5 | 100% | 100% | 6.125% | 55.05% | 100% | 2004-02-12 | 2004-04-13 | 2004-10-01 | 2009-08-31 | n/a | 1795 | 110 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Impalidan | 063013038 | Electrification | 1 | 545774.48 | 508500.8 | 37273.68 | 508500.8 | 3rd Tranche | 39273.63 | 547774.43 | 508500.8 | 39273.63 | 100% | 100% | 105.4% | 100.4% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-07 | 2006-06-05 | 2006-03-30 | 210 | 100 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Impalidan | 063013038 | Travelling Rice Mill | 1 | 794000 | 645898.55 | 148101.45 | 581308.7 | Last Tranche | 148201.45 | 729510.15 | 581308.7 | 148201.45 | 100% | 100% | 100.1% | 91.88% | 100% | 2006-07-03 | 2006-08-08 | 2007-02-05 | 2008-06-01 | 2008-07-04 | 482 | 92 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Ipil | 063013040 | Road Construction | 1 | 2793767.79 | 2475485.57 | 318282.22 | 2227937.02 | 2nd Tranche | 160393.41 | 2388330.43 | 2227937.02 | 160393.41 | 100% | 100% | 50.39% | 85.49% | 100% | 2005-08-09 | 2005-08-31 | 2005-12-26 | 2006-08-31 | no data | 248 | 178 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Jamin-ay | 063013041 | Day Care Center | 1 | 696100 | 505313.03 | 190786.97 | 454781.72 | 2nd Tranche | 190786.98 | 645568.7 | 454781.72 | 190786.98 | 100% | 100% | 100% | 92.74% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-18 | 2008-02-28 | 2008-07-04 | 498 | 141 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Lampaya | 063013042 | Health Station | 1 | 454965.6 | 346411.72 | 108553.88 | 346411.72 | 3rd Tranche | 130257.23 | 476668.95 | 346411.72 | 130257.23 | 100% | 100% | 120% | 104.8% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-28 | 2005-01-07 | 2005-02-13 | 224 | 161 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Lampaya | 063013042 | Water System Level II | 1 | 1050419.21 | 907746.91 | 142672.3 | 907746.91 | 3rd Tranche | 157523.55 | 1065270.46 | 907746.91 | 157523.55 | 100% | 100% | 110.4% | 101.4% | 100% | 2005-08-09 | 2005-08-31 | 2006-01-23 | 2006-08-31 | 2006-11-18 | 220 | 161 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Libot | 063013043 | Health Station | 1 | 643221.54 | 441031.01 | 202190.53 | 441031.01 | 3rd Tranche | 186222.21 | 627253.22 | 441031.01 | 186222.21 | 100% | 100% | 92.1% | 97.52% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-24 | 2004-11-30 | 2005-01-15 | 190 | 201 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Libot | 063013043 | Road Upgrading with Spot Concreting | 1 | 1156000 | 949571.5 | 206428.5 | 854614.35 | 1st Tranche | 211828.5 | 1066442.85 | 854614.35 | 211828.5 | 100% | 100% | 102.6% | 92.25% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-07 | 2009-01-01 | n/a | 786 | 201 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Malag-it | 063013073 | Road Upgrading | 1 | 1016382.42 | 932188.67 | 84193.75 | 932188.67 | 3rd Tranche | 106890 | 1039078.67 | 932188.67 | 106890 | 100% | 100% | 127% | 102.2% | 100% | 2005-08-09 | 2005-08-31 | 2006-01-02 | 2006-05-11 | 2006-06-23 | 129 | 86 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Malaguinabot | 063013045 | Day Care Center | 1 | 582093.75 | 419742.26 | 162351.49 | 419742.26 | 3rd Tranche | 192636.58 | 612378.84 | 419742.26 | 192636.58 | 100% | 100% | 118.7% | 105.2% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-02 | 2004-11-30 | 2005-12-23 | 181 | 76 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Malaguinabot | 063013045 | Pre & Post Harvest Facilities | 1 | 653200 | 528006.49 | 125193.51 | 528006.49 | 100% Tranche | 125293.51 | 653300 | 528006.49 | 125293.51 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-26 | 2007-12-31 | 2008-07-04 | 431 | 76 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Malapawe | 063013046 | Level II Water System | 1 | 448092.85 | 391196.29 | 56896.56 | 391196.29 | 3rd Tranche | 71508.66 | 462704.95 | 391196.29 | 71508.66 | 100% | 100% | 125.7% | 103.3% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-02 | 2004-10-15 | 2005-04-14 | 135 | 86 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Malapawe | 063013046 | Pre & Post Harvest Facilities | 1 | 703439.4 | 642608.63 | 60830.77 | 578347.76 | 2nd Tranche | 62237.47 | 640585.23 | 578347.76 | 62237.47 | 100% | 100% | 102.3% | 91.06% | 100% | 2005-08-09 | 2005-08-31 | 2005-12-12 | 2006-03-23 | 2006-06-07 | 101 | 80 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Mambiranan | 063013049 | Health Station | 1 | 698156.11 | 630729.31 | 67426.8 | 630729.31 | 3rd Tranche | 61323.5 | 692052.81 | 630729.31 | 61323.5 | 100% | 100% | 90.95% | 99.13% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-23 | 2006-04-13 | 2006-05-29 | 172 | 140 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Mambiranan | 063013049 | Day Care Center | 1 | 622750 | 512036.9 | 110713.1 | 460833.21 | 2nd Tranche | 110713.1 | 571546.31 | 460833.21 | 110713.1 | 100% | 100% | 100% | 91.78% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-07 | 2008-03-28 | no data | 507 | 145 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Manaripay | 063013050 | Day Care Center | 1 | 742000 | 527847.58 | 214152.42 | 475062.82 | 2nd Tranche | 214252.42 | 689315.24 | 475062.82 | 214252.42 | 100% | 100% | 100% | 92.9% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2008-03-28 | 2008-07-04 | 494 | 128 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Marandig | 063013051 | 1 Classroom School Building | 1 | 745600 | 553102.99 | 192497.01 | 497792.69 | 1st Tranche | 192597.01 | 690389.7 | 497792.69 | 192597.01 | 100% | 100% | 100.1% | 92.6% | 100% | 2006-07-03 | 2006-08-08 | 2006-10-20 | 2009-05-30 | no data | 953 | 208 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Masaroy | 063013052 | 1 Classroom School Building | 1 | 733000 | 548143.82 | 184856.18 | 493329.44 | 2nd Tranche | 184956.18 | 678285.62 | 493329.44 | 184956.18 | 100% | 100% | 100.1% | 92.54% | 100% | 2006-07-03 | 2006-08-08 | 2006-09-25 | 2008-03-29 | 2008-07-04 | 551 | 64 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Maspasan | 063013053 | School Building 1 Classroom | 1 | 656675.23 | 567641.7 | 89033.53 | 567641.7 | 3rd Tranche | 79855 | 647496.7 | 567641.7 | 79855 | 100% | 100% | 89.69% | 98.6% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-28 | 2006-04-13 | 2006-06-14 | 167 | 140 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Maspasan | 063013053 | Pre & Post Harvest Facilities | 1 | 425500 | 356285.57 | 69214.43 | 356285.57 | 100% Tranche | 69314.43 | 425600 | 356285.57 | 69314.43 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-13 | 2007-03-19 | 2008-07-04 | 126 | 139 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Nalbugan | 063013054 | Box Culvert | 1 | 375000 | 312331.77 | 62668.23 | 281098.6 | 2nd Tranche | 62768.23 | 343866.83 | 281098.6 | 62768.23 | 100% | 100% | 100.2% | 91.7% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-02 | 2008-08-01 | no data | 638 | 119 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Poblacion Delgado | 063013058 | Drainage System | 1 | 938307.98 | 792935.92 | 145372.06 | 792935.92 | 3rd Tranche | 140050.58 | 932986.5 | 792935.92 | 140050.58 | 100% | 100% | 96.34% | 99.43% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-28 | 2006-06-17 | no data | 201 | 255 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Poblacion Ilaya | 063013060 | Drainage System | 1 | 531263.49 | 368072.41 | 163191.08 | 368072.41 | 3rd Tranche | 128700.04 | 496772.45 | 368072.41 | 128700.04 | 100% | 100% | 78.86% | 93.51% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-07 | 2005-02-25 | 2006-10-28 | 263 | 311 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | San Nicolas | 063013063 | 2 Classroom School Building | 1 | 965274.57 | 702757.46 | 262517.11 | 702757.46 | 3rd Tranche | 248879.16 | 951636.62 | 702757.46 | 248879.16 | 100% | 100% | 94.8% | 98.59% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-03 | 2005-04-12 | no data | 313 | 121 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | San Nicolas | 063013063 | Pre & Post Harvest Facilities | 1 | 597661.98 | 556091.25 | 41570.73 | 556091.25 | 3rd Tranche | 44850.77 | 600942.02 | 556091.25 | 44850.77 | 100% | 100% | 107.9% | 100.5% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-08 | 2006-04-20 | no data | 163 | 123 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Simsiman | 063013064 | Day Care Center | 1 | 578901.13 | 376862.25 | 202038.88 | 376862.25 | 3rd Tranche | 189330.55 | 566192.8 | 376862.25 | 189330.55 | 100% | 100% | 93.71% | 97.8% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-02 | 2004-12-01 | 2005-12-18 | 182 | 218 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Simsiman | 063013064 | Water System Level II | 1 | 1116279.01 | 858836.2 | 257442.81 | 858836.2 | 3rd Tranche | 273322.68 | 1132158.88 | 858836.2 | 273322.68 | 100% | 100% | 106.2% | 101.4% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-12 | 2006-06-15 | 2006-06-14 | 246 | 241 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Simsiman | 063013064 | 2 Classroom School Building | 1 | 1090400 | 815934.86 | 274465.14 | 734340.03 | 2nd Tranche | 274466.63 | 1008805.17 | 734340.03 | 274465.14 | 100% | 100% | 100% | 92.52% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2007-03-19 | no data | 119 | 218 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tabucan | 063013065 | Level II Water System | 1 | 847533.17 | 722548.27 | 124984.9 | 722548.27 | 3rd Tranche | 93748.15 | 816296.42 | 722548.27 | 93748.15 | 100% | 100% | 75.01% | 96.31% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-28 | 2005-04-20 | 2005-04-25 | 327 | 224 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tabucan | 063013065 | Road Concreting | 1 | 1144000 | 975066.24 | 168933.76 | 877559.61 | 1st Tranche | 169033.76 | 1046593.37 | 877559.61 | 169033.76 | 100% | 100% | 100.1% | 91.49% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-02 | 2009-02-25 | n/a | 846 | 224 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tahing | 063013066 | Health Station | 1 | 715259.7 | 639486.65 | 75773.05 | 639486.65 | 3rd Tranche | 91047.5 | 730534.15 | 639486.65 | 91047.5 | 100% | 100% | 120.2% | 102.1% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-03 | 2006-05-04 | 2006-05-16 | 182 | 67 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tahing | 063013066 | Road Upgrading | 1 | 780000 | 566805.77 | 213194.23 | 510125.19 | 1st Tranche | 213194.23 | 602230.83 | 510125.19 | 92105.64 | 100% | 43.2% | 100% | 77.21% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2009-01-01 | n/a | 773 | 62 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tibiao | 063013068 | 1 Classroom School Building | 1 | 590876.06 | 407910.26 | 182965.8 | 407910.26 | 3rd Tranche | 170296.48 | 578206.74 | 407910.26 | 170296.48 | 100% | 100% | 93.08% | 97.86% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-26 | 2004-11-30 | 2005-01-22 | 188 | 75 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tibiao | 063013068 | Health Station | 1 | 725622.4 | 654954.54 | 70667.86 | 654954.54 | 3rd Tranche | 68217.5 | 723172.04 | 654954.54 | 68217.5 | 100% | 100% | 96.53% | 99.66% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-24 | 2006-04-20 | 2006-05-06 | 178 | 74 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tibiao | 063013068 | Pre & Post Harvest Facilities | 1 | 591800 | 512541.75 | 79258.25 | 512541.75 | 100% Tranche | 79358.25 | 591900 | 512541.75 | 79358.25 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-20 | 2007-03-22 | 2008-07-04 | 122 | 75 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Tigbayog | 063013069 | Health Station | 1 | 682659.86 | 514014.11 | 168645.75 | 514014.11 | 3rd Tranche | 176436.8 | 690450.91 | 514014.11 | 176436.8 | 100% | 100% | 104.6% | 101.1% | 100% | 2004-02-12 | 2004-04-13 | 2004-06-21 | 2005-05-03 | 2005-05-03 | 316 | 129 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Toyungan | 063013071 | Health Station | 1 | 730351.55 | 593729.2 | 136622.35 | 593729.2 | 3rd Tranche | 130615.39 | 724344.59 | 593729.2 | 130615.39 | 100% | 100% | 95.6% | 99.18% | 100% | 2005-08-09 | 2005-08-31 | 2005-10-26 | 2006-06-22 | 2006-03-24 | 239 | 432 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Ulayan | 063013072 | Day Care Center | 1 | 582093.75 | 408362.26 | 173731.49 | 408362.26 | 3rd Tranche | 185531.22 | 593893.48 | 408362.26 | 185531.22 | 100% | 100% | 106.8% | 102% | 100% | 2004-02-12 | 2004-04-13 | 2004-05-31 | 2004-12-01 | 2005-03-17 | 184 | 69 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Ulayan | 063013072 | Water System Level II | 1 | 712947.46 | 643411.82 | 69535.64 | 643411.82 | 3rd Tranche | 73478.12 | 716889.94 | 643411.82 | 73478.12 | 100% | 100% | 105.7% | 100.6% | 100% | 2005-08-09 | 2005-08-31 | 2005-11-14 | 2006-05-18 | no data | 185 | 63 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Calinog | 063013 | Ulayan | 063013072 | 1 Classroom School Building | 1 | 712000 | 545802.46 | 166197.54 | 545802.46 | Last Tranche | 166297.54 | 712100 | 545802.46 | 166297.54 | 100% | 100% | 100.1% | 100% | 100% | 2006-07-03 | 2006-08-08 | 2006-11-02 | 2007-03-22 | no data | 140 | 102 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Abong | 063014001 | Ricemill with Warehouse & Collecting Tank | 1 | 1658729.38 | 1345000 | 313729.38 | 1345000 | 3rd Tranche | 388352.38 | 1733352.38 | 1345000 | 388352.38 | 100% | 100% | 123.8% | 104.5% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-21 | 2006-06-29 | 2006-06-30 | 220 | 380 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Abong | 063014001 | Delivery Vehicle with Garage | 1 | 840516 | 778016 | 62500 | 699541.6 |  | 51253.75 | 750795.35 | 699541.6 | 51253.75 | 100% | 100% | 82.01% | 89.33% | 100% | 2009-02-12 | no data | 2009-06-15 | 2009-08-04 | no data | 50 | 370 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Asluman | 063014003 | Health Station | 1 | 545978.72 | 475703 | 70275.72 | 475703 | 3rd Tranche | 73257.72 | 548960.72 | 475703 | 73257.72 | 100% | 100% | 104.2% | 100.5% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-17 | 2004-12-22 | 2005-03-03 | 219 | 465 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Asluman | 063014003 | 2 Classroom School Building | 1 | 1023750 | 824300 | 199450 | 824300 | 1st Tranche | 193037.5 | 1017337.5 | 824300 | 193037.5 | 100% | 100% | 96.78% | 99.37% | 100% | 2006-07-04 | 2006-07-31 | 2007-02-07 | 2008-06-01 | no data | 480 | 381 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Asluman | 063014003 | 1 Classroom School Building | 1 | 774541 | 713287.25 | 61253.75 | 639097.9 |  | 44375 | 683472.9 | 639097.9 | 44375 | 100% | 100% | 72.44% | 88.24% | 100% | 2009-02-12 | no data | 2009-05-28 | 2009-08-11 | no data | 75 | 563 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bancal | 063014004 | 2 Classroom School Building | 1 | 784400.4 | 656100.4 | 128300 | 656100.4 | 3rd Tranche | 132685 | 788785.4 | 656100.4 | 132685 | 100% | 100% | 103.4% | 100.6% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-18 | 2004-11-25 | 2005-02-25 | 191 | 856 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bancal | 063014004 | 1 Classroom School Building | 1 | 666235.75 | 604982 | 61253.75 | 541047.8 |  | 35375 | 576422.8 | 541047.8 | 35375 | 100% | 100% | 57.75% | 86.52% | 100% | 2009-02-12 | no data | 2009-05-20 | 2009-07-31 | no data | 72 | 965 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Barosbos | 063014006 | 1 Classroom School Building | 1 | 598060 | 503300 | 94760 | 463800 | 2nd Tranche | 100370 | 564170 | 463800 | 100370 | 100% | 100% | 105.9% | 94.33% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-06 | 2008-06-01 | no data | 573 | 496 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Barosbos | 063014006 | Delivery Vehicle with Garage | 1 | 840516 | 778016 | 62500 | 699541.6 |  | 51253.75 | 750795.35 | 699541.6 | 51253.75 | 100% | 100% | 82.01% | 89.33% | 100% | 2009-02-12 | no data | 2009-06-11 | 2009-08-02 | no data | 52 | 518 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Binuluangan | 063014009 | 1 Classroom School Building | 1 | 604040 | 431600 | 172440 | 402524.5 | 1st Tranche | 168659 | 571183.5 | 402524.5 | 168659 | 100% | 100% | 97.81% | 94.56% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-15 | 2007-08-01 | no data | 259 | 262 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Binuluangan | 063014009 | Health Station | 1 | 823266.5 | 755766.5 | 67500 | 675821.6 |  | 57375 | 733196.6 | 675821.6 | 57375 | 100% | 100% | 85% | 89.06% | 100% | 2009-02-12 | no data | 2009-05-27 | 2009-08-15 | no data | 80 | 309 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bito-on | 063014010 | 2 Classroom School Building | 1 | 1036392.5 | 384040 | 652352.5 | 345636 | 1st Tranche | 77076 | 422712 | 345636 | 77076 | 100% | 100% | 11.82% | 40.79% | 100% | 2006-07-04 | 2006-07-31 | 2007-04-01 | 2008-09-01 | no data | 519 | 292 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bito-on | 063014010 | 1 Classroom School Building | 1 | 744291 | 683037.25 | 61253.75 | 614733.53 |  | 44375 | 659108.53 | 614733.53 | 44375 | 100% | 100% | 72.44% | 88.56% | 100% | 2009-02-12 | no data | 2009-05-20 | 2009-08-08 | no data | 80 | 50 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bolo | 063014011 | 2 Classroom School Building | 1 | 946320 | 826300 | 120020 | 743670 | 2nd Tranche | 125875 | 869545 | 743670 | 125875 | 100% | 100% | 104.9% | 91.89% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-21 | 2006-04-27 | 2006-04-27 | 157 | 220 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bolo | 063014011 | Health Station | 1 | 753690 | 581600 | 172090 | 581600 | 2nd Tranche | 135090 | 716690 | 581600 | 135090 | 100% | 100% | 78.5% | 95.09% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-16 | 2008-06-01 | no data | 563 | 217 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Bolo | 063014011 | Travelling Rice Mill with Garage | 1 | 871516 | 809516 | 62000 | 724146.6 |  | 50853.75 | 775000.35 | 724146.6 | 50853.75 | 100% | 100% | 82.02% | 88.93% | 100% | 2009-02-12 | no data | 2009-06-17 | 2009-07-28 | no data | 41 | 232 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Buaya | 063014012 | Fishing Boat with Arong | 1 | 1982500 | 1575370 | 407130 | 1575370 | 3rd Tranche | 438020 | 2013390 | 1575370 | 438020 | 100% | 100% | 107.6% | 101.6% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-23 | 2006-05-19 | 2006-08-11 | 177 | 333 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Buenavista | 06301401 | 1 Classroom School Building | 1 | 744291 | 683037.25 | 61253.75 | 614733.53 |  | 44375 | 659108.53 | 614733.53 | 44375 | 100% | 100% | 72.44% | 88.56% | 100% | 2009-02-12 | no data | 2009-05-11 | 2009-08-11 | no data | 92 | 319 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabilao Grande | 063014016 | 1 Classroom School Building | 1 | 597405 | 509400 | 88005 | 509400 | 3rd Tranche | 106363.55 | 615763.55 | 509400 | 106363.55 | 100% | 100% | 120.9% | 103.1% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-18 | 2006-05-15 | 2006-07-10 | 178 | 262 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabilao Grande | 063014016 | Delivery Vehicle with Garage | 1 | 840516 | 778016 | 62500 | 699541.6 |  | 51253.75 | 750795.35 | 699541.6 | 51253.75 | 100% | 100% | 82.01% | 89.33% | 100% | 2009-02-12 | no data | 2009-06-09 | 2009-08-05 | no data | 57 | 310 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabilao Pequeno | 063014017 | Delivery Vehicle with Garage | 1 | 840516 | 778016 | 62500 | 699541.6 |  | 51253.75 | 750795.35 | 699541.6 | 51253.75 | 100% | 100% | 82.01% | 89.33% | 100% | 2009-02-12 | no data | 2009-06-15 | 2009-08-04 | no data | 50 | 282 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabilao Pequeño | 063014017 | Mini Market | 1 | 328757.12 | 266269.04 | 62488.08 | 266269.04 | 3rd Tranche | 74359.36 | 340628.4 | 266269.04 | 74359.36 | 100% | 100% | 119% | 103.6% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-19 | 2004-12-09 | 2005-02-25 | 204 | 243 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabilao Pequeño | 063014017 | 3 Classroom School Building | 1 | 1446800 | 1196100 | 250700 | 1160700.98 | 2nd Tranche | 232360 | 1393060.98 | 1160700.98 | 232360 | 100% | 100% | 92.68% | 96.29% | 100% | 2006-07-04 | 2006-07-31 | 2007-04-01 | 2007-11-01 | no data | 214 | 244 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabuguana | 063014018 | Feeder Road Rehabilitation | 1 | 810740 | 662840 | 147900 | 643866.75 | 1st Tranche | 124890 | 768756.75 | 643866.75 | 124890 | 100% | 100% | 84.44% | 94.82% | 100% | 2006-07-04 | 2006-07-31 | 2007-06-04 | 2008-10-01 | no data | 485 | 244 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cabuguana | 063014018 | Delivery Vehicle with Garage | 1 | 840516 | 778016 | 62500 | 699541.6 |  | 60253.75 | 759795.35 | 699541.6 | 60253.75 | 100% | 100% | 96.41% | 90.4% | 100% | 2009-02-12 | no data | 2009-05-20 | 2009-08-02 | no data | 74 | 250 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cawayan | 063014019 | Bagsakan Center | 1 | 990125 | 702480 | 287645 | 702480 | 3rd Tranche | 330775 | 1033255 | 702480 | 330775 | 100% | 100% | 115% | 104.4% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-21 | 2006-06-28 | 2006-06-29 | 219 | 525 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cawayan | 063014019 | 1 Classroom School Building | 1 | 577650 | 465300 | 112350 | 437952 | 2nd Tranche | 107070 | 545022 | 437952 | 107070 | 100% | 100% | 95.3% | 94.35% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-07 | 2008-06-01 | no data | 572 | 399 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Cawayan | 063014019 | Road Improvement | 1 | 904290 | 840790 | 63500 | 750826 |  | 25375 | 776201 | 750826 | 25375 | 100% | 100% | 39.96% | 85.84% | 100% | 2009-02-12 | no data | 2009-06-23 | 2009-08-05 | no data | 43 | 540 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Dayhagan | 063014020 | Water Supply System | 1 | 1764316.25 | 1469326.25 | 294990 | 1469326.25 | 3rd Tranche | 379042.18 | 1848368.43 | 1469326.25 | 379042.18 | 100% | 100% | 128.5% | 104.8% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-15 | 2005-01-25 | 2005-02-25 | 255 | 194 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Dayhagan | 063014020 | Health Station | 1 | 760210 | 620650 | 139560 | 620650 | 3rd Tranche | 156612.5 | 777262.5 | 620650 | 156612.5 | 100% | 100% | 112.2% | 102.2% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-17 | 2006-05-22 | 2006-06-17 | 186 | 194 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Dayhagan | 063014020 | Small Market | 1 | 928580 | 801325 | 127255 | 740128.96 | 1st Tranche | 117265 | 857393.96 | 740128.96 | 117265 | 100% | 100% | 92.15% | 92.33% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-13 | 2008-06-01 | no data | 566 | 196 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Gabi | 063014021 | 1 Classroom Building w/ facilities | 1 | 475587.53 | 419038.81 | 56548.72 | 419038.81 | 3rd Tranche | 60323.08 | 479361.89 | 419038.81 | 60323.08 | 100% | 100% | 106.7% | 100.8% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-25 | 2004-12-30 | 2005-03-03 | 219 | 456 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Gabi | 063014021 | Feeder Road Upgrading with Concreting | 1 | 2138146.5 | 1963000 | 175146.5 | 1963000 | 3rd Tranche | 207301.5 | 2170301.5 | 1963000 | 207301.5 | 100% | 100% | 118.4% | 101.5% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-23 | 2006-08-30 | 2006-09-05 | 280 | 456 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Gabi | 063014021 | 1 Classroom School Building | 1 | 774541 | 535696.75 | 238844.25 | 478036.7 |  | 95875 | 573911.7 | 478036.7 | 95875 | 100% | 100% | 40.14% | 74.1% | 100% | 2009-02-12 | no data | 2009-05-29 | 2009-08-06 | no data | 69 | 510 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Granada | 063014022 | Road Concreting w/ side ditches | 1 | 1381945.75 | 988445.75 | 393500 | 988445.75 | 3rd Tranche | 398390 | 1386835.75 | 988445.75 | 398390 | 100% | 100% | 101.2% | 100.4% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-28 | 2005-02-20 | 2005-03-03 | 268 | 518 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Granada | 063014022 | Brgy. Trail | 1 | 1063817 | 861500 | 202317 | 775350 | 1st Tranche | 199547 | 974897 | 775350 | 199547 | 100% | 100% | 98.63% | 91.64% | 100% | 2006-07-04 | 2006-07-31 | 2007-06-01 | 2008-06-01 | no data | 366 | 463 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Granada | 063014022 | 1 Classroom School Building | 1 | 774541 | 713287.25 | 61253.75 | 639097.9 |  | 44375 | 683472.9 | 639097.9 | 44375 | 100% | 100% | 72.44% | 88.24% | 100% | 2009-02-12 | no data | 2009-05-28 | 2009-08-11 | no data | 75 | 588 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Guinticgan | 063014023 | Delivery Vehicle with Garage | 1 | 840516 | 778016 | 62500 | 699541.6 |  | 50253.75 | 749795.35 | 699541.6 | 50253.75 | 100% | 100% | 80.41% | 89.21% | 100% | 2009-02-12 | no data | 2009-06-16 | 2009-08-02 | no data | 47 | 482 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Isla De Caña | 063014014 | 1 Classroom School Building | 1 | 497581.93 | 443313.61 | 54268.32 | 443313.61 | 3rd Tranche | 62185.32 | 505498.93 | 443313.61 | 62185.32 | 100% | 100% | 114.6% | 101.6% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-14 | 2004-12-16 | 2005-03-02 | 216 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Isla De Caña | 063014014 | Rain Catchment with Collecting Tank | 1 | 1218356.49 | 1120800 | 97556.49 | 1008720 | 2nd Tranche | 103842.48 | 1112562.48 | 1008720 | 103842.48 | 100% | 100% | 106.4% | 91.32% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-23 | 2006-05-24 | 2006-06-02 | 182 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Isla de Caña | 063014014 | 3 Sets Solar Charging Station | 1 | 708740 | 622600 | 86140 | 622600 | 1st Tranche | 82150 | 704750 | 622600 | 82150 | 100% | 100% | 95.37% | 99.44% | 100% | 2006-07-04 | 2006-07-31 | 2007-04-01 | 2008-06-01 | no data | 427 | 84 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Lantangan | 063014024 | 2 Classroom Building w/ facilities | 1 | 790511.92 | 687790.24 | 102721.68 | 687790.24 | 3rd Tranche | 121741.68 | 809531.92 | 687790.24 | 121741.68 | 100% | 100% | 118.5% | 102.4% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-18 | 2005-02-26 | 2005-03-03 | 284 | 136 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Manlot | 063014025 | Health Station | 1 | 536910.22 | 489223.5 | 47686.72 | 489223.5 | 3rd Tranche | 51186.97 | 540410.47 | 489223.5 | 51186.97 | 100% | 100% | 107.3% | 100.7% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-14 | 2004-12-29 | 2005-03-04 | 229 | 122 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Pantalan | 063014027 | 2 Classroom School Building | 1 | 787720.42 | 711795.24 | 75925.18 | 711795.24 | 3rd Tranche | 78825.18 | 790620.42 | 711795.24 | 78825.18 | 100% | 100% | 103.8% | 100.4% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-18 | 2004-12-16 | 2005-03-02 | 212 | 375 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Pantalan | 063014027 | Health Station | 1 | 823266.5 | 755766.5 | 67500 | 675821.6 |  | 48375 | 724196.6 | 675821.6 | 48375 | 100% | 100% | 71.67% | 87.97% | 100% | 2009-02-12 | no data | 2009-05-18 | 2009-08-11 | no data | 85 | 365 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Poblacion | 063014028 | Road Rehabilitation | 1 | 659595 | 515540 | 144055 | 510540 | 2nd Tranche | 146455 | 656995 | 510540 | 146455 | 100% | 100% | 101.7% | 99.61% | 100% | 2006-07-04 | 2006-07-31 | 2007-04-01 | 2008-06-01 | no data | 427 | 612 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Poblacion | 063014028 | Water Truck with Garage | 1 | 1092333.5 | 1008333.5 | 84000 | 905858.35 |  | 59000 | 964858.35 | 905858.35 | 59000 | 100% | 100% | 70.24% | 88.33% | 100% | 2009-02-12 | no data | 2009-06-16 | 2009-08-05 | no data | 50 | 612 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta (Bolocawe) | 063014029 | Road Improvement | 1 | 972290 | 906790 | 65500 | 816111 |  | 26475 | 842586 | 816111 | 26475 | 100% | 100% | 40.42% | 86.66% | 100% | 2009-02-12 | no data | 2009-06-20 | 2009-08-05 | no data | 46 | 245 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta (Carles/Bolacawe) | 063014029 | Health Station | 1 | 519871.32 | 416264.2 | 103607.12 | 416264.2 | 3rd Tranche | 106198.62 | 522462.82 | 416264.2 | 106198.62 | 100% | 100% | 102.5% | 100.5% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-15 | 2004-11-25 | 2005-02-25 | 194 | 222 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta (Carles/Bolacawe) | 063014029 | Water Truck/ Multi-Purpose Vehicle with Garage | 1 | 857810 | 769070 | 88740 | 747077 | 2nd Tranche | 83080 | 830157 | 747077 | 83080 | 100% | 100% | 93.62% | 96.78% | 100% | 2006-07-04 | 2006-07-31 | 2007-04-01 | 2008-06-01 | no data | 427 | 244 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta Batuanan | 063014007 | 2 Classroom School Building | 1 | 787720.42 | 705189.24 | 82531.18 | 705189.24 | 3rd Tranche | 85833.18 | 791022.42 | 705189.24 | 85833.18 | 100% | 100% | 104% | 100.4% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-24 | 2004-12-31 | 2005-03-02 | 221 | 185 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Carles | 063014 | Punta Batuanan | 063014007 | Day Care Center | 1 | 709060.25 | 648806.5 | 60253.75 | 572350.6 |  | 25375 | 597725.6 | 572350.6 | 25375 | 100% | 100% | 42.11% | 84.3% | 100% | 2009-02-12 | no data | 2009-05-28 | 2009-08-04 | no data | 68 | 50 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | San Fernando | 063014030 | Solar Panel with Controller & Battery | 1 | 715503.75 | 559491.75 | 156012 | 472292.58 |  | 188696.25 | 660988.83 | 472292.58 | 188696.25 | 100% | 100% | 120.9% | 92.38% | 100% | 2009-02-12 | no data | 2009-07-06 | 2009-07-12 | no data | 6 | 25 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tabugon | 063014031 | Health Station | 1 | 531679.09 | 393801.97 | 137877.12 | 393801.97 | 3rd Tranche | 144699.16 | 538501.13 | 393801.97 | 144699.16 | 100% | 100% | 104.9% | 101.3% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-25 | 2004-12-21 | 2005-03-04 | 210 | 320 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tabugon | 063014031 | Construction of 1CL school building | 1 | 774291 | 683037.25 | 91253.75 | 614497.9 |  | 58000 | 672497.9 | 614497.9 | 58000 | 100% | 100% | 63.56% | 86.85% | 100% | 2009-02-12 | no data | 2009-06-10 | 2009-08-12 | no data | 63 | 330 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Talingting | 063014032 | Passenger Flat Boat | 1 | 240360.08 | 150242.4 | 90117.68 | 150242.4 | 3rd Tranche | 105325.74 | 255568.14 | 150242.4 | 105325.74 | 100% | 100% | 116.9% | 106.3% | 100% | 2004-01-17 | 2004-03-19 | 2004-06-01 | 2005-02-17 | 2005-03-04 | 261 | 243 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tarong | 063014033 | 2 Classroom School Building | 1 | 814567.65 | 647003.85 | 167563.8 | 647003.85 | 3rd Tranche | 190628.8 | 837632.65 | 647003.85 | 190628.8 | 100% | 100% | 113.8% | 102.8% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-12 | 2004-12-29 | 2005-02-25 | 231 | 276 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tarong | 063014033 | Bagsakan Center | 1 | 715226.55 | 590400 | 124826.55 | 590400 | 3rd Tranche | 128806.55 | 719206.55 | 590400 | 128806.55 | 100% | 100% | 103.2% | 100.6% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-23 | 2006-06-30 | 2006-07-03 | 219 | 276 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tarong | 063014033 | Communal Multi-Purpose Vehicle with Garage | 1 | 735235 | 586485 | 148750 | 586485 | 2nd Tranche | 153900 | 740385 | 586485 | 153900 | 100% | 100% | 103.5% | 100.7% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-02 | 2007-07-01 | no data | 241 | 439 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tinigban | 063014034 | Pump Boat | 1 | 426251.2 | 362831.6 | 63419.6 | 362831.6 | 3rd Tranche | 69837.6 | 432669.2 | 362831.6 | 69837.6 | 100% | 100% | 110.1% | 101.5% | 100% | 2004-01-17 | 2004-03-19 | 2004-06-26 | 2005-02-17 | 2005-03-02 | 236 | 219 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tupaz | 063014035 | 2 Classroom School Building | 1 | 784400.4 | 617660.9 | 166739.5 | 617660.9 | 3rd Tranche | 180634.5 | 798295.4 | 617660.9 | 180634.5 | 100% | 100% | 108.3% | 101.8% | 100% | 2004-01-17 | 2004-03-19 | 2004-05-21 | 2004-12-14 | 2005-02-25 | 207 | 250 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tupaz | 063014035 | Health Station | 1 | 712400 | 646600 | 65800 | 581940 | 2nd Tranche | 76590 | 658530 | 581940 | 76590 | 100% | 100% | 116.4% | 92.44% | 100% | 2005-08-09 | 2005-10-20 | 2005-11-21 | 2006-04-18 | 2006-04-19 | 148 | 250 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tupaz | 063014035 | Rice Mill (Baby Cono) | 1 | 805090 | 694400 | 110690 | 663533 | 2nd Tranche | 119118 | 782651 | 663533 | 119118 | 100% | 100% | 107.6% | 97.21% | 100% | 2006-07-04 | 2006-07-31 | 2006-11-08 | 2008-06-01 | no data | 571 | 255 |  | 1
VI | 06 | Iloilo | 0630 | Carles | 063014 | Tupaz | 063014035 | 1 Classroom School Building | 1 | 666235.75 | 604982 | 61253.75 | 541047.8 |  | 37875 | 578922.8 | 541047.8 | 37875 | 100% | 100% | 61.83% | 86.89% | 100% | 2009-02-12 | no data | 2009-06-02 | 2009-08-11 | no data | 70 | 256 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Aglosong | 063015002 | Water System (Level-II) | 1 | 323785 | 220800 | 102985 | 220800 | 3rd Tranche | 173752.51 | 394552.51 | 220800 | 173752.51 | 100% | 100% | 168.7% | 121.9% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-06 | 2004-05-03 | 2004-06-14 | 240 | 22 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Agnaga | 063015003 | Water System (Level-II) | 1 | 685236 | 386250 | 298986 | 386250 | 3rd Tranche | 315511.01 | 701761.01 | 386250 | 315511.01 | 100% | 100% | 105.5% | 102.4% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-03 | 2004-03-02 | 2004-06-14 | 181 | 45 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Agnaga | 063015003 | 3-unit Solar Dryer, 1 unit Storage | 1 | 1603999.09 | 1138730 | 465269.09 | 1138730 | 3rd Tranche | 488493.44 | 1627223.44 | 1138730 | 488493.44 | 100% | 100% | 105% | 101.4% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-12-30 | 2006-01-31 | 291 | 157 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Agnaga | 063015003 | Rural Electrification | 1 | 958206.39 | 696260.65 | 261945.74 | 626634.58 |  | 265296.31 | 891930.89 | 626634.58 | 265296.31 | 100% | 100% | 101.3% | 93.08% | 100% | 2009-02-18 | no data | 2009-06-01 | 2009-07-31 | no data | 60 | 73 | completed as built | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bacjawan Norte | 063015004 | Water System (Level-II) | 1 | 560250 | 442840 | 117410 | 442840 | 3rd Tranche | 134416.67 | 577256.67 | 442840 | 134416.67 | 100% | 100% | 114.5% | 103% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-01 | 2004-03-09 | 2004-06-14 | 190 | 25 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bacjawan Norte | 063015004 | Day Care Center | 1 | 576996.07 | 476617.17 | 100378.9 | 476617.17 | 3rd Tranche | 113311.16 | 589928.33 | 476617.17 | 113311.16 | 100% | 100% | 112.9% | 102.2% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 30 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bacjawan Norte | 063015004 | Rural Electrification | 1 | 719051.35 | 422387 | 296664.35 | 337909.6 |  | 244532.1 | 582441.7 | 337909.6 | 244532.1 | 100% | 100% | 82.43% | 81% | 100% | 2009-02-18 | no data | 2009-03-15 | 2009-07-31 | no data | 138 | 42 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bacjawan Sur | 063015005 | Water System (Level-II) | 1 | 642000 | 322000 | 320000 | 322000 | 3rd Tranche | 329107.34 | 651107.34 | 322000 | 329107.34 | 100% | 100% | 102.8% | 101.4% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-07 | 2004-03-04 | 2004-06-14 | 179 | 35 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bacjawan Sur | 063015005 | Construction of Day Care Center | 1 | 637469.67 | 532296.45 | 105173.22 | 479066.81 |  | 102843.22 | 581910.03 | 479066.81 | 102843.22 | 100% | 100% | 97.78% | 91.28% | 100% | 2009-02-18 | no data | 2009-05-11 | 2009-06-30 | no data | 50 | 218 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bagongon | 063015006 | School Building | 1 | 726780 | 531720 | 195060 | 531720 | 3rd Tranche | 195418.35 | 727138.35 | 531720 | 195418.35 | 100% | 100% | 100.2% | 100% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-02 | 2004-01-25 | 2004-06-14 | 145 | 80 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Bagongon | 063015006 | Barangay Trail | 1 | 1070777 | 713717 | 357060 | 713717 | 3rd Tranche | 356971.93 | 1070688.93 | 713717 | 356971.93 | 100% | 100% | 99.98% | 99.99% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-09-30 | 2006-01-31 | 200 | 309 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Batiti | 063015007 | Water System (Level-II) | 1 | 527250 | 322000 | 205250 | 322000 | 3rd Tranche | 194703.34 | 516703.34 | 322000 | 194703.34 | 100% | 100% | 94.86% | 98% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-02 | 2004-03-08 | 2004-06-14 | 188 | 34 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Batiti | 063015007 | Day Care Center | 1 | 552506.21 | 465947.64 | 86558.57 | 465947.64 | 3rd Tranche | 78213.21 | 544160.85 | 465947.64 | 78213.21 | 100% | 100% | 90.36% | 98.49% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 30 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Batiti | 063015007 | Construction of Solar Dryer and Warehouse | 1 | 982349.79 | 846174.49 | 136175.3 | 761557.04 |  | 126614.17 | 888171.21 | 761557.04 | 126614.17 | 100% | 100% | 92.98% | 90.41% | 100% | 2009-02-18 | no data | 2009-05-25 | 2009-07-31 | no data | 67 | 191 | completed as built | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Botlog | 063015008 | Day Care Center | 1 | 338980 | 240410 | 98570 | 240410 | 3rd Tranche | 136285.01 | 376695.01 | 240410 | 136285.01 | 100% | 100% | 138.3% | 111.1% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-14 | 2004-03-02 | 2004-06-14 | 170 | 62 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Botlog | 063015008 | Construction of Heatlh Station | 1 | 790884.59 | 656157 | 134727.59 | 656157 | 3rd Tranche | 149711.17 | 805868.17 | 656157 | 149711.17 | 100% | 100% | 111.1% | 101.9% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 526 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Calamigan | 063015009 | Water System (Level-II) | 1 | 674274 | 403500 | 270774 | 403500 | 3rd Tranche | 345719.01 | 749219.01 | 403500 | 345719.01 | 100% | 100% | 127.7% | 111.1% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-03 | 2004-04-05 | 2004-06-14 | 215 | 45 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Calamigan | 063015009 | Consltruction of 1-CL School Building | 1 | 627377.73 | 527497.37 | 99880.36 | 474747.64 |  | 102484.14 | 577231.78 | 474747.64 | 102484.14 | 100% | 100% | 102.6% | 92.01% | 100% | 2009-02-18 | no data | 2009-05-11 | 2009-07-31 | no data | 81 | 125 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Dungon | 063015010 | Pump Boat Passenger | 1 | 346146 | 250000 | 96146 | 250000 | 3rd Tranche | 170642.01 | 420642.01 | 250000 | 170642.01 | 100% | 100% | 177.5% | 121.5% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-09 | 2004-03-14 | 2004-06-14 | 187 | 248 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Dungon | 063015010 | Construction of 1-CL School Building | 1 | 646634.67 | 522204.29 | 124430.38 | 417763.43 |  | 121123.78 | 538887.21 | 417763.43 | 121123.78 | 100% | 100% | 97.34% | 83.34% | 100% | 2009-02-18 | no data | 2009-05-14 | 2009-07-31 | no data | 78 | 66 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Igbon | 063015011 | Water System (Level-II) | 1 | 497440 | 394971 | 102469 | 394971 | 3rd Tranche | 127875.01 | 522846.01 | 394971 | 127875.01 | 100% | 100% | 124.8% | 105.1% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-05 | 2004-02-11 | 2004-06-14 | 159 | 154 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Igbon | 063015011 | Construction of Brgy Trail w/ slope | 1 | 1429094.59 | 902109 | 526985.59 | 902109 | 3rd Tranche | 513597.672 | 1415706.672 | 902109 | 513597.672 | 100% | 100% | 97.46% | 99.06% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 442 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Igbon | 063015011 | Construction of 1-CL School Building | 1 | 678177.75 | 573172.39 | 105005.36 | 458537.91 |  | 64275.36 | 522813.27 | 458537.91 | 64275.36 | 100% | 100% | 61.21% | 77.09% | 100% | 2009-02-18 | no data | 2009-05-11 | 2009-07-31 | no data | 81 | 333 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Jamul-Awon | 063015012 | Health Station | 1 | 446130 | 336000 | 110130 | 336000 | 3rd Tranche | 115590.01 | 451590.01 | 336000 | 115590.01 | 100% | 100% | 105% | 101.2% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-01 | 2004-02-03 | 2004-06-14 | 155 | 178 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Jamul-awon | 063015012 | Brgy. Road Rehab | 1 | 1597301.86 | 1398046 | 199255.86 | 1258241.4 | 1st Tranche | 161046.54 | 1419287.94 | 1258241.4 | 161046.54 | 100% | 100% | 80.82% | 88.86% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-05-01 | no data | 413 | 178 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Jamul-awon | 063015012 | Road Improvement | 1 | 3592133.85 | 2731396.65 | 860737.2 | 1535755.21 |  | 528740 | 2064495.21 | 1535755.21 | 528740 | 100% | 100% | 61.43% | 57.47% | 100% | 2009-02-18 | no data | 2009-05-26 | 2009-08-31 | no data | 97 | 210 | completed as built | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Lo-ong | 063015013 | Brgy. Road Rehab | 1 | 800455.64 | 643034 | 157421.64 | 643034 | 1st Tranche | 59587.13 | 702621.13 | 643034 | 59587.13 | 100% | 100% | 37.85% | 87.78% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 54 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Lo-ong | 063015013 | Construction of 1-CL School Building | 1 | 625457.73 | 463152.37 | 162305.36 | 402967.62 |  | 160795.36 | 563762.98 | 402967.62 | 160795.36 | 100% | 100% | 99.07% | 90.14% | 100% | 2009-02-18 | no data | 2009-05-16 | 2009-07-31 | no data | 76 | 378 | completed as built | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macalbang | 063015014 | Health Station | 1 | 418700 | 288500 | 130200 | 288500 | 3rd Tranche | 145785.01 | 434285.01 | 288500 | 145785.01 | 100% | 100% | 112% | 103.7% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-01 | 2004-02-05 | 2004-06-14 | 157 | 270 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macalbang | 063015014 | 2-units Day Care Center (2 Sitios) | 1 | 1166118.52 | 964707.89 | 201410.63 | 964707.89 | 3rd Tranche | 178467.67 | 1143175.56 | 964707.89 | 178467.67 | 100% | 100% | 88.61% | 98.03% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 270 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macalbang | 063015014 | Road Improvement | 1 | 4048417.05 | 2767867.45 | 1280549.6 | 1840859.7 |  | 1285317.5 | 3126177.2 | 1840859.7 | 1285317.5 | 100% | 100% | 100.4% | 77.22% | 100% | 2009-02-18 | no data | 2009-05-01 | 2009-08-31 | no data | 122 | 334 | completed as built | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macatunao | 063015015 | Water System (Level-II) | 1 | 437695 | 338160 | 99535 | 338160 | 3rd Tranche | 110750.01 | 448910.01 | 338160 | 110750.01 | 100% | 100% | 111.3% | 102.6% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-04 | 2004-03-15 | 2004-06-14 | 193 | 88 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macatunao | 063015015 | Day Care Center | 1 | 818876.48 | 588690 | 230186.48 | 588690 | 3rd Tranche | 226945 | 815635 | 588690 | 226945 | 100% | 100% | 98.59% | 99.6% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-12-30 | 2006-01-31 | 291 | 347 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macatunao | 063015015 | Concrete Footbridge 1 Meter | 1 | 687068.81 | 506508 | 180560.81 | 506508 | 3rd Tranche | 177882.79 | 684390.79 | 506508 | 177882.79 | 100% | 100% | 98.52% | 99.61% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 342 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Macatunao | 063015015 | Improvement of Brgy. Trail | 1 | 798330.62 | 574902.46 | 223428.16 | 517412.22 |  | 223820.16 | 741232.38 | 517412.22 | 223820.16 | 100% | 100% | 100.2% | 92.85% | 100% | 2009-02-18 | no data | 2009-05-25 | 2009-07-31 | no data | 67 | 337 | completed as built | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Malangabang | 063015016 | 1 CL School Building | 1 | 582014.38 | 444847 | 137167.38 | 444847 | 2nd Tranche | 123841.11 | 568688.11 | 444847 | 123841.11 | 100% | 100% | 90.28% | 97.71% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 395 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Maliogliog | 063015017 | Foot Bridge | 1 | 559476 | 448625 | 110851 | 448625 | 3rd Tranche | 109410.01 | 558035.01 | 448625 | 109410.01 | 100% | 100% | 98.7% | 99.74% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-05 | 2004-01-22 | 2004-06-14 | 139 | 144 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Maliogliog | 063015017 | Water System Level II | 1 | 1083961.54 | 886520 | 197441.54 | 886520 | 3rd Tranche | 201092.86 | 1087612.86 | 886520 | 201092.86 | 100% | 100% | 101.8% | 100.3% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-11-25 | 2006-01-31 | 256 | 99 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Niño | 063015018 | Day Care Center | 1 | 305510 | 222880 | 82630 | 222880 | 3rd Tranche | 113490.01 | 336370.01 | 222880 | 113490.01 | 100% | 100% | 137.3% | 110.1% | 100% | 2003-05-06 | 2003-07-28 | 2003-08-29 | 2004-03-09 | 2004-06-14 | 193 | 25 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Niño | 063015018 | Road Rehabilitation | 1 | 1682373.28 | 971650 | 710723.28 | 971650 | 3rd Tranche | 178700.72 | 1150350.72 | 971650 | 178700.72 | 100% | 100% | 25.14% | 68.38% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-10-07 | 2006-01-31 | 207 | 60 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Niño | 063015018 | Construction of Heatlh Station | 1 | 601135.63 | 535138.77 | 65996.86 | 535138.77 | 3rd Tranche | 55234.07 | 590372.84 | 535138.77 | 55234.07 | 100% | 100% | 83.69% | 98.21% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 60 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Nipa | 063015019 | Water System (Level-II) | 1 | 566487 | 381180 | 185307 | 381180 | 3rd Tranche | 273485.01 | 654665.01 | 381180 | 273485.01 | 100% | 100% | 147.6% | 115.6% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-02 | 2004-05-12 | 2004-06-14 | 253 | 60 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Nipa | 063015019 | Construction of 1-CL School Building | 1 | 628977.73 | 533702.37 | 95275.36 | 480332.14 |  | 98236.36 | 578568.5 | 480332.14 | 98236.36 | 100% | 100% | 103.1% | 91.99% | 100% | 2009-02-18 | no data | 2009-05-12 | 2009-06-30 | no data | 49 | 160 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Plandico | 063015021 | Day Care Center | 1 | 602725 | 450600 | 152125 | 450600 | 3rd Tranche | 224965.01 | 675565.01 | 450600 | 224965.01 | 100% | 100% | 147.9% | 112.1% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-22 | 2004-04-16 | 2004-06-14 | 207 | 50 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Plandico | 063015021 | Construction of WS Level I&2 | 1 | 537326.46 | 156205.53 | 381120.93 | 140584.98 | 1st Tranche | 361642.78 | 502227.76 | 140584.98 | 361642.78 | 100% | 100% | 94.89% | 93.47% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 21 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Poblacion | 063015022 | Day Care Center | 1 | 352000 | 248160 | 103840 | 248160 | 3rd Tranche | 120010.1 | 368170.1 | 248160 | 120010.1 | 100% | 100% | 115.6% | 104.6% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-22 | 2004-03-19 | 2004-06-14 | 179 | 24 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Polopiña | 063015023 | Barangay Trail | 1 | 1737381.4 | 954800 | 782581.4 | 954800 | 3rd Tranche | 823435.39 | 1778235.39 | 954800 | 823435.39 | 100% | 100% | 105.2% | 102.4% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-09-25 | 2006-01-31 | 195 | 589 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Polopiña | 063015023 | Construction of Brgy Trail | 1 | 644306.88 | 350682 | 293624.88 | 350682 | 3rd Tranche | 249525.14 | 600207.14 | 350682 | 249525.14 | 100% | 100% | 84.98% | 93.16% | 100% | 2006-01-18 | 2006-01-30 | 2006-03-14 | 2007-01-01 | no data | 293 | 632 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Salvacion | 063015024 | Health Station | 1 | 426250 | 332100 | 94150 | 332100 | 3rd Tranche | 125455.01 | 457555.01 | 332100 | 125455.01 | 100% | 100% | 133.3% | 107.3% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-04 | 2004-04-07 | 2004-06-14 | 216 | 148 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Salvacion | 063015024 | Sea Wall | 1 | 1171650 | 741053 | 430597 | 741053 | 3rd Tranche | 331107.98 | 1072160.98 | 741053 | 331107.98 | 100% | 100% | 76.9% | 91.51% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-11-25 | 2006-01-31 | 256 | 122 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Salvacion | 063015024 | Installation of Artificial Reefs | 1 | 506109.98 | 421224.68 | 84885.3 | 336979.74 |  | 94859.42 | 431839.16 | 336979.74 | 94859.42 | 100% | 100% | 111.8% | 85.33% | 100% | 2009-02-18 | no data | 2009-05-18 | 2009-06-30 | no data | 43 | 127 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Talotu-an | 063015025 | Improvement of Brgy. Trail | 1 | 552267.83 | 435029.39 | 117238.44 | 391526.45 |  | 122318.44 | 513844.89 | 391526.45 | 122318.44 | 100% | 100% | 104.3% | 93.04% | 100% | 2009-02-18 | no data | 2009-05-14 | 2009-07-31 | no data | 78 | 527 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Talotu-an | 063015025 | Water System (Level-II) | 1 | 354450 | 233300 | 121150 | 233300 | 3rd Tranche | 246545.71 | 479845.71 | 233300 | 246545.71 | 100% | 100% | 203.5% | 135.4% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-04 | 2004-03-17 | 2004-06-14 | 195 | 84 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Tambaliza | 063015026 | Day Care Center | 1 | 564118 | 445490 | 118628 | 445490 | 3rd Tranche | 119390.01 | 564880.01 | 445490 | 119390.01 | 100% | 100% | 100.6% | 100.1% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-15 | 2004-03-12 | 2004-06-14 | 179 | 42 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Tambaliza | 063015026 | Improvement of Brgy. Trail | 1 | 639545.69 | 452731.99 | 186813.7 | 359849.35 |  | 173216.85 | 533066.2 | 359849.35 | 173216.85 | 100% | 100% | 92.72% | 83.35% | 100% | 2009-02-18 | no data | 2009-05-28 | 2009-07-31 | no data | 64 | 589 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Tamis-ac | 063015027 | Water System (Level-II) | 1 | 481537 | 259700 | 221837 | 259700 | 3rd Tranche | 126975.01 | 386675.01 | 259700 | 126975.01 | 100% | 100% | 57.24% | 80.3% | 100% | 2003-05-06 | 2003-07-28 | 2003-09-06 | 2004-02-17 | 2004-06-14 | 164 | 45 |  | 1
VI | 06 | Iloilo | 0630 | Concepcion | 063015 | Tamis-ac | 063015027 | Barangay Trail | 1 | 2387315.45 | 1504840 | 882475.45 | 1504840 | 3rd Tranche | 336877.01 | 1841717.01 | 1504840 | 336877.01 | 100% | 100% | 38.17% | 77.15% | 100% | 2004-12-03 | 2005-01-19 | 2005-03-14 | 2005-10-07 | 2006-01-31 | 207 | 88 |  | 1
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Abangay | 063023001 | Health Station | 1 | 551660.64 | 435562.64 | 116098 | 435562.64 | Last Tranche | 114431 | 549993.64 | 435562.64 | 114431 | 100% | 100% | 98.56% | 99.7% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-21 | 2007-02-28 | no data | 99 | 178 |  | 1
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Abangay | 063023001 | Day Care Center | 1 | 635740.01 | 547510.01 | 88230 | 492759.01 | 1st | 88650 | 581409.01 | 492759.01 | 88650 | 100% | 100% | 100.5% | 91.45% | 100% | 2009-02-09 | no data | 2009-03-31 | 2009-07-31 | no data | 122 | 170 |  | 1
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Agcarope - C2 | 063023002 | Road Upgrading with Spot Concreting | 2 | 4979654.04 | 4590848.54 | 388805.5 | 3672678.83 | 1st Tranche | 267883.5 | 3940562.33 | 3672678.83 | 267883.5 | 100% | 100% | 68.9% | 79.13% | 100% | 2006-07-17 | 2006-08-10 | 2007-05-25 | 2009-02-25 | n/a | 642 | 451 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Canawili | 063023012 | Road Upgrading with Spot Concreting | 2 | 4979654.04 | 4590848.54 | 388805.5 | 3672678.83 | 1st Tranche | 267883.5 | 3940562.33 | 3672678.83 | 267883.5 | 100% | 100% | 68.9% | 79.13% | 100% | 2006-07-17 | 2006-08-10 | 2007-05-25 | 2009-02-25 | n/a | 642 | 451 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aglobong | 063023003 | Road Construction | 1 | 3567842.55 | 1275242.55 | 2292600 | 1275242.55 | 3rd Tranche | 141500 | 1416742.55 | 1275242.55 | 141500 | 100% | 100% | 6.172% | 39.71% | 100% | 2004-01-04 | 2004-03-04 | 2004-06-28 | 2006-05-31 | 2005-05-25 | 702 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aglobong | 063023003 | One Classroom Building | 1 | 908883.88 | 809638.88 | 99245 | 728674.99 | 1st | 99332.5 | 828007.49 | 728674.99 | 99332.5 | 100% | 100% | 100.1% | 91.1% | 100% | 2009-02-09 | no data | 2009-03-26 | 2009-06-30 | no data | 96 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aguingay | 063023004 | Level II Water System | 1 | 864285.5 | 563737.5 | 300548 | 563737.5 | 3rd Tranche | 197145.58 | 760883.08 | 563737.5 | 197145.58 | 100% | 100% | 65.6% | 88.04% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-03 | 2005-04-25 | 2005-05-05 | 357 | 59 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aguingay | 063023004 | Health Station | 1 | 821724.51 | 671233.05 | 150491.46 | 604109.74 | 2nd Tranche | 236040.73 | 840150.47 | 604109.74 | 236040.73 | 100% | 100% | 156.8% | 102.2% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-21 | 2006-05-31 | 2006-06-10 | 222 | 59 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aguingay | 063023004 | One Classroom Building | 1 | 736764.34 | 656166.34 | 80598 | 590549.71 | 1st | 75927.2 | 666476.91 | 590549.71 | 75927.2 | 100% | 100% | 94.2% | 90.46% | 100% | 2009-02-09 | no data | 2009-03-24 | 2009-06-30 | no data | 98 | 62 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Anhawan | 063023005 | Barangay Road Rehabilitation | 1 | 1259484.73 | 997108 | 262376.73 | 997108 | 3rd Tranche | 156414.23 | 1153522.23 | 997108 | 156414.23 | 100% | 100% | 59.61% | 91.59% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-24 | 2005-04-30 | 2005-05-02 | 341 | 143 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Anhawan | 063023005 | Day Care Center | 1 | 681007.58 | 600437.58 | 80570 | 540393.82 | 1st | 80725 | 621118.82 | 540393.82 | 80725 | 100% | 100% | 100.2% | 91.21% | 100% | 2009-02-09 | no data | 2009-03-30 | 2009-06-30 | 2009-07-12 | 92 | 157 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aquino Nobleza East | 063023046 | Construction of Drainage System | 1 | 1544354.05 | 754061.35 | 790292.7 | 754061.35 | 3rd Tranche | 1069606.45 | 1823667.8 | 754061.35 | 1069606.45 | 100% | 100% | 135.3% | 118.1% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-17 | 2005-01-19 | 2005-03-05 | 247 | 300 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Aquino Nobleza East | 063023046 | Day Care Center | 1 | 510012.5 | 448214.54 | 61797.96 | 448214.54 | Last Tranche | 67752.96 | 515967.5 | 448214.54 | 67752.96 | 100% | 100% | 109.6% | 101.2% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-28 | 2007-05-31 | 2007-06-23 | 184 | 240 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Atimonan | 063023006 | Road Construction | 1 | 2551281.5 | 305275 | 2246006.5 | 305275 | 3rd Tranche | 357491.5 | 662766.5 | 305275 | 357491.5 | 100% | 100% | 15.92% | 25.98% | 100% | 2004-01-04 | 2004-03-04 | 2004-09-27 | 2005-10-31 | no data | 399 | 210 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Atimonan | 063023006 | One Unit Classroom Building | 1 | 972111.08 | 875206.08 | 96905 | 787685.47 | 1st | 96932.5 | 884617.97 | 787685.47 | 96932.5 | 100% | 100% | 100% | 91% | 100% | 2009-02-09 | no data | 2009-03-28 | 2009-06-30 | no data | 94 | 228 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Balanac | 063023007 | Two Classrom School Building | 1 | 1257614.64 | 999310.22 | 258304.42 | 999310.22 | 3rd Tranche | 202489.21 | 1201799.43 | 999310.22 | 202489.21 | 100% | 100% | 78.39% | 95.56% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-24 | 2006-06-30 | 2006-08-12 | 249 | 134 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Balanac | 063023007 | One Unit Classroom Bulding | 1 | 736164.34 | 656166.34 | 79998 | 624888.01 | 1st | 80058 | 704946.01 | 624888.01 | 80058 | 100% | 100% | 100.1% | 95.76% | 100% | 2009-02-09 | no data | 2009-03-24 | 2009-06-30 | no data | 98 | 123 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Barasalon | 063023008 | Road Construction | 1 | 5316300.6 | 2104531.8 | 3211768.8 | 2104531.8 | 3rd Tranche | 266110.67 | 2370642.47 | 2104531.8 | 266110.67 | 100% | 100% | 8.285% | 44.59% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-17 | 2006-05-31 | no data | 744 | 249 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Barasalon | 063023008 | Health Station | 1 | 681784.52 | 609834.52 | 71950 | 548851.07 | 1st | 86375 | 635226.07 | 548851.07 | 86375 | 100% | 100% | 120% | 93.17% | 100% | 2009-02-09 | no data | 2009-03-28 | 2009-06-30 | no data | 94 | 309 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Bongol | 063023009 | Water System Level II | 1 | 640730.01 | 123790.7 | 516939.31 | 123790.7 | Last Tranche | 520208.56 | 643999.26 | 123790.7 | 520208.56 | 100% | 100% | 100.6% | 100.5% | 100% | 2006-07-17 | 2006-08-10 | 2006-10-16 | 2007-09-30 | no data | 349 | 77 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Bongol | 063023009 | Roap Upgrading with 40 Ln.m concreting | 1 | 889408.22 | 769718.22 | 119690 | 692746.4 | 1st | 149750.65 | 842497.05 | 692746.4 | 149750.65 | 100% | 100% | 125.1% | 94.73% | 100% | 2009-02-13 | no data | 2009-03-29 | 2009-07-31 | no data | 124 | 350 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Cabantog | 063023010 | Barangay Road Rehabilitation | 1 | 1137679.5 | 370867.5 | 766812 | 370867.5 | 3rd Tranche | 1000267.67 | 1371135.17 | 370867.5 | 1000267.67 | 100% | 100% | 130.4% | 120.5% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-07 | 2005-02-28 | 2005-03-20 | 297 | 42 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Cabantog | 063023010 | Health Station | 1 | 551378.63 | 506157.96 | 45220.67 | 504357.96 | 2nd Tranche | 41393.46 | 545751.42 | 504357.96 | 41393.46 | 100% | 100% | 91.54% | 98.98% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-03 | 2007-09-30 | 2007-11-23 | 331 | 47 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Cabantog | 063023010 | Road Upgrading with Concreting | 1 | 505003.15 | 407811.15 | 97192 | 367030.03 | 1st | 128372 | 495402.03 | 367030.03 | 128372 | 100% | 100% | 132.1% | 98.1% | 100% | 2009-02-13 | no data | 2009-05-01 | 2009-06-30 | no data | 60 | 42 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Calmay | 063023011 | Health Station | 1 | 549422.2 | 333116.2 | 216306 | 333116.2 | 3rd Tranche | 339127 | 672243.2 | 333116.2 | 339127 | 100% | 100% | 156.8% | 122.4% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-26 | 2005-02-28 | 2005-02-19 | 308 | 241 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Calmay | 063023011 | Road Upgrading with Spot Concreting | 1 | 1112583.72 | 942746.15 | 169837.57 | 925918.43 | 2nd Tranche | 162327.64 | 1088246.07 | 925918.43 | 162327.64 | 100% | 100% | 95.58% | 97.81% | 100% | 2006-07-17 | 2006-08-10 | 2006-12-06 | 2007-12-31 | no data | 390 | 347 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Calmay | 063023011 | Day Care Center | 1 | 636940.01 | 560750.01 | 76190 | 504675.01 | 1st | 76935 | 581610.01 | 504675.01 | 76935 | 100% | 100% | 101% | 91.31% | 100% | 2009-02-09 | no data | 2009-03-27 | 2009-06-30 | 2009-07-07 | 95 | 373 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Canawillian | 063023013 | One Unit Classroom Building | 1 | 962290.33 | 881270.33 | 81020 | 793143.3 | 1st | 82095 | 875238.3 | 793143.3 | 82095 | 100% | 100% | 101.3% | 90.95% | 100% | 2009-02-09 | no data | 2009-03-28 | 2009-06-30 | no data | 94 | 237 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Canawillian | 063023013 | Road Construction | 1 | 2347809 | 343387 | 2004422 | 309048.3 | 2nd Tranche | 101000 | 372396.8 | 309048.3 | 63348.5 | 100% | 62.72% | 5.039% | 15.86% | 100% | 2004-01-04 | 2004-03-04 | 2005-06-15 | 2008-03-01 | no data | 990 | 214 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caranas | 063023014 | Barangay Road Rehabilitation | 1 | 1301646.9 | 446228.2 | 855418.7 | 446228.2 | 3rd Tranche | 1160896.42 | 1607124.62 | 446228.2 | 1160896.42 | 100% | 100% | 135.7% | 123.5% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-15 | 2006-06-30 | no data | 776 | 144 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caranas | 063023014 | Irrigation System | 1 | 1804533.92 | 1635458.81 | 169075.11 | 1593245.31 | 2nd Tranche | 119706.64 | 1712951.95 | 1593245.31 | 119706.64 | 100% | 100% | 70.8% | 94.92% | 100% | 2006-07-17 | 2006-08-10 | 2007-03-26 | 2007-12-31 | no data | 280 | 130 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caranas | 063023014 | Road Opening | 1 | 2404455.28 | 2201141.28 | 203314 | 1760913.02 | 1st | 241998.38 | 2002911.4 | 1760913.02 | 241998.38 | 100% | 100% | 119% | 83.3% | 100% | 2009-02-13 | no data | 2009-06-23 | 2009-08-28 | no data | 66 | 153 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caraudan | 063023015 | Common Post Harvest Facility | 1 | 2206050.02 | 1058081.1 | 1147968.92 | 1058081.1 | 3rd Tranche | 1227293.92 | 2285375.02 | 1058081.1 | 1227293.92 | 100% | 100% | 106.9% | 103.6% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-19 | 2005-01-31 | 2005-01-14 | 287 | 158 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caraudan | 063023015 | Health Station | 1 | 966954.56 | 790177.44 | 176777.12 | 790177.44 | 3rd Tranche | 182390.12 | 972567.56 | 790177.44 | 182390.12 | 100% | 100% | 103.2% | 100.6% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-17 | 2006-06-30 | 2006-09-18 | 256 | 158 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caraudan | 063023015 | Road Upgrading | 1 | 857760.11 | 642010.71 | 215749.4 | 642010.71 | Last Tranche | 213928.34 | 855939.05 | 642010.71 | 213928.34 | 100% | 100% | 99.16% | 99.79% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-08 | 2007-06-30 | 2007-06-09 | 234 | 158 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Caraudan | 063023015 | Day Care Center | 1 | 636540.01 | 573550.01 | 62990 | 547075.25 | 1st | 60291 | 607366.25 | 547075.25 | 60291 | 100% | 100% | 95.72% | 95.42% | 100% | 2009-02-09 | no data | 2009-03-17 | 2009-04-30 | 2009-04-30 | 44 | 186 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Carigangan | 063023016 | Double-Triple Box Culvert Single Lane (RCDG Bridge) | 1 | 1604061.8 | 781372.6 | 822689.2 | 781372.6 | 3rd Tranche | 591854.1 | 1373226.7 | 781372.6 | 591854.1 | 100% | 100% | 71.94% | 85.61% | 100% | 2004-01-04 | 2004-03-04 | 2004-09-15 | 2005-11-30 | 2007-05-09 | 441 | 168 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Carigangan | 063023016 | Road Upgraing with Spot Concreting | 1 | 2752723.08 | 2324883.08 | 427840 | 2092394.77 | 1st | 428090 | 2520484.77 | 2092394.77 | 428090 | 100% | 100% | 100.1% | 91.56% | 100% | 2009-02-13 | no data | 2009-05-08 | 2009-07-31 | no data | 84 | 187 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Cunsad | 063023017 | Barangay Road Rehabilitation | 1 | 470400 | 273600 | 196800 | 273600 | 3rd Tranche | 194187.75 | 467787.75 | 273600 | 194187.75 | 100% | 100% | 98.67% | 99.44% | 100% | 2004-01-04 | 2004-03-04 | 2004-07-02 | 2005-04-30 | 2005-06-03 | 302 | 98 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Cunsad | 063023017 | Day Care Center | 1 | 698934.55 | 609485.59 | 89448.96 | 609485.59 | 3rd Tranche | 96424.48 | 705910.07 | 609485.59 | 96424.48 | 100% | 100% | 107.8% | 101% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-08 | 2006-06-30 | 2006-08-04 | 234 | 99 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Cunsad | 063023017 | Road Concreting w/ Side Ditch | 1 | 1016300.99 | 702544.99 | 313756 | 632290.49 | 1st | 314230.2 | 946520.69 | 632290.49 | 314230.2 | 100% | 100% | 100.2% | 93.13% | 100% | 2009-02-13 | no data | 2009-05-07 | 2009-08-31 | no data | 116 | 77 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | D.G. Abordo (Conception Pob.) | 063023049 | Drainage Canal | 1 | 229474.24 | 180400.39 | 49073.85 | 180400.39 | Last Tranche | 67760.3 | 248160.69 | 180400.39 | 67760.3 | 100% | 100% | 138.1% | 108.1% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-08 | 2007-06-23 | 2007-06-23 | 227 | 52 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | D.G. Abordo (Conception Pob.) - C2 | 063023049 | Drainage System Improvement | 2 | 1754350.25 | 1513520.25 | 240830 | 1319844.41 |  | 240904.94 | 1560749.35 | 1319844.41 | 240904.94 | 100% | 100% | 100% | 88.96% | 100% | 2009-02-13 | no data | 2009-04-21 | 2009-06-25 | no data | 65 | 206 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Dabong | 063023018 | Health Station | 1 | 858510.39 | 643894.65 | 214615.74 | 643894.65 | 3rd Tranche | 221546.9 | 865441.55 | 643894.65 | 221546.9 | 100% | 100% | 103.2% | 100.8% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-02 | 2006-06-30 | 2006-07-08 | 240 | 209 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Dabong | 063023018 | Road Upgrading of 1.86km FMR | 1 | 1019585.65 | 952015.65 | 67570 | 856814.09 | 1st | 68905 | 925719.09 | 856814.09 | 68905 | 100% | 100% | 102% | 90.79% | 100% | 2009-02-13 | no data | 2009-05-12 | 2009-06-30 | no data | 49 | 219 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Damires | 063023019 | Level II Water System | 1 | 1120050.55 | 662676.85 | 457373.7 | 662676.85 | 3rd Tranche | 498444.7 | 1161121.55 | 662676.85 | 498444.7 | 100% | 100% | 109% | 103.7% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-14 | 2005-04-30 | 2005-05-15 | 351 | 253 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Danao | 063023021 | Multi purpose Drainage System | 1 | 2048394.2 | 872932.2 | 1175462 | 872932.2 | 3rd Tranche | 1229901 | 2102833.2 | 872932.2 | 1229901 | 100% | 100% | 104.6% | 102.7% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-19 | 2005-09-02 | 2007-10-15 | 471 | 371 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Danao | 063023021 | Road Upgrading of 2,106 ln.m w/ 100 ln.m Concreting | 1 | 1616106.97 | 1468409.97 | 147697 | 1321568.97 | 1st | 252458.6 | 1574027.57 | 1321568.97 | 252458.6 | 100% | 100% | 170.9% | 97.4% | 100% | 2009-02-13 | no data | 2009-04-03 | 2009-06-30 | no data | 88 | 448 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Don T.L. West | 063023054 | Drainage System Improvement | 1 | 521798.29 | 399908.29 | 121890 | 383404.25 |  | 128472 | 511876.25 | 383404.25 | 128472 | 100% | 100% | 105.4% | 98.1% | 100% | 2009-02-13 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 288 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Gines | 063023022 | Water System Level II | 1 | 2123919.91 | 1740412.87 | 383507.04 | 1653392.22 | 3rd Tranche | 204299.05 | 1857691.27 | 1653392.22 | 204299.05 | 100% | 100% | 53.27% | 87.47% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-15 | 2007-06-30 | no data | 592 | 135 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Golgota - C5 | 063023050 | Bio-Disposal | 5 | 1508358.83 | 1368623 | 139735.83 | 1368623 | 1st Tranche | 118694.06 | 1487317.06 | 1368623 | 118694.06 | 100% | 100% | 84.94% | 98.6% | 100% | 2006-07-17 | 2006-08-10 | 2007-04-23 | 2007-11-30 | no data | 221 | 258 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | San Julian | 063023057 | Bio-Disposal | 5 | 1508358.83 | 1368623 | 139735.83 | 1368623 | 1st Tranche | 118694.06 | 1487317.06 | 1368623 | 118694.06 | 100% | 100% | 84.94% | 98.6% | 100% | 2006-07-17 | 2006-08-10 | 2007-04-23 | 2007-11-30 | no data | 221 | 258 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | A.N. West | 063023047 | Bio-Disposal | 5 | 1508358.83 | 1368623 | 139735.83 | 1368623 | 1st Tranche | 118694.06 | 1487317.06 | 1368623 | 118694.06 | 100% | 100% | 84.94% | 98.6% | 100% | 2006-07-17 | 2006-08-10 | 2007-04-23 | 2007-11-30 | no data | 221 | 258 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Don T.L. West | 063023054 | Bio-Disposal | 5 | 1508358.83 | 1368623 | 139735.83 | 1368623 | 1st Tranche | 118694.06 | 1487317.06 | 1368623 | 118694.06 | 100% | 100% | 84.94% | 98.6% | 100% | 2006-07-17 | 2006-08-10 | 2007-04-23 | 2007-11-30 | no data | 221 | 258 |  | 1 | VISAYAS
Locsi | 06 | Iloilo | 0630 | Janiuay | 063023 | Locsin | 063023051 | Bio-Disposal | 5 | 1508358.83 | 1368623 | 139735.83 | 1368623 | 1st Tranche | 118694.06 | 1487317.06 | 1368623 | 118694.06 | 100% | 100% | 84.94% | 98.6% | 100% | 2006-07-17 | 2006-08-10 | 2007-04-23 | 2007-11-30 | no data | 221 | 258 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Jibolo | 063023025 | Line Canal | 1 | 2225995.3 | 1873639.35 | 352355.95 | 1873639.35 | Last Tranche | 339748.95 | 2213388.3 | 1873639.35 | 339748.95 | 100% | 100% | 96.42% | 99.43% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-29 | 2007-12-31 | no data | 397 | 750 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Kuyot | 063023026 | Hanging Bridge | 1 | 633690 | 443583 | 190107 | 443583 | 3rd Tranche | 260517 | 704100 | 443583 | 260517 | 100% | 100% | 137% | 111.1% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-22 | 2005-01-31 | 2005-01-20 | 284 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Kuyot | 063023026 | Health Station | 1 | 778010.95 | 703332.97 | 74677.98 | 703332.97 | 3rd Tranche | 75930.53 | 779263.5 | 703332.97 | 75930.53 | 100% | 100% | 101.7% | 100.2% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-17 | 2006-06-30 | 2006-08-09 | 256 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Kuyot | 063023026 | Road Upgrading | 1 | 1689554.22 | 1068690.16 | 620864.06 | 1035379.44 | Last Tranche | 45244.79 | 1080624.23 | 1035379.44 | 45244.79 | 100% | 100% | 7.287% | 63.96% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-30 | 2007-09-30 | no data | 304 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Kuyot | 063023026 | One Classroom Building | 1 | 736764.34 | 656166.34 | 80598 | 624929.47 | 1st | 78143.2 | 703072.67 | 624929.47 | 78143.2 | 100% | 100% | 96.95% | 95.43% | 100% | 2009-02-09 | no data | 2009-04-01 | 2009-06-30 | no data | 90 | 179 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Locsin | 063023051 | Drainage Canal with Curb & Gutter | 1 | 737344.5 | 504032.81 | 233311.69 | 403226.25 | 1st Tranche | 223640.7 | 626866.95 | 403226.25 | 223640.7 | 100% | 100% | 95.85% | 85.02% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-17 | 2006-01-31 | 2006-03-31 | 106 | 29 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Madong | 063023027 | Irrigation Canal | 1 | 848283.1 | 340670.5 | 507612.6 | 340670.5 | 3rd Tranche | 581000.8 | 921671.3 | 340670.5 | 581000.8 | 100% | 100% | 114.5% | 108.7% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-14 | 2005-01-26 | 2005-01-30 | 287 | 374 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Madong | 063023027 | Day Care Center | 1 | 327890.06 | 286697.77 | 41192.29 | 286697.77 | 2nd Tranche | 48361.94 | 335059.71 | 286697.77 | 48361.94 | 100% | 100% | 117.4% | 102.2% | 100% | 2006-07-17 | 2006-08-10 | 2006-12-04 | 2007-11-30 | 2007-12-20 | 361 | 341 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Madong | 063023027 | Barangay Health Station | 1 | 724840.7 | 623794.7 | 101046 | 561415.23 | 1st | 99846 | 661261.23 | 561415.23 | 99846 | 100% | 100% | 98.81% | 91.23% | 100% | 2009-02-09 | no data | 2009-03-26 | 2009-06-30 | no data | 96 | 380 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Manacabac | 063023028 | Road Concreting | 1 | 1022065.05 | 742303.05 | 279762 | 661947.91 | 1st | 336308.4 | 998256.31 | 661947.91 | 336308.4 | 100% | 100% | 120.2% | 97.67% | 100% | 2009-02-13 | no data | 2009-05-12 | 2009-07-31 | no data | 80 | 158 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Mañacabac | 063023028 | Double-Triple Box Culvert Single Lane (RCDG Bridge) | 1 | 1626286.64 | 855941.6 | 770345.04 | 855941.6 | 3rd Tranche | 725117.04 | 1581058.64 | 855941.6 | 725117.04 | 100% | 100% | 94.13% | 97.22% | 100% | 2004-01-04 | 2004-03-04 | 2004-07-15 | 2005-06-19 | 2005-11-05 | 339 | 148 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Mañacabac | 063023028 | Road Upgrading with Spot Concreting | 1 | 491591.89 | 442955.95 | 48635.94 | 436048.56 | Last Tranche | 196711.84 | 632760.4 | 436048.56 | 196711.84 | 100% | 100% | 404.5% | 128.7% | 100% | 2006-07-17 | 2006-08-10 | 2006-12-13 | 2007-11-30 | no data | 352 | 148 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Mangil | 063023029 | Hanging Bridge | 1 | 767965.03 | 572048.65 | 195916.38 | 572048.65 | 3rd Tranche | 229377.28 | 801425.93 | 572048.65 | 229377.28 | 100% | 100% | 117.1% | 104.4% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-17 | 2006-06-30 | 2006-07-29 | 256 | 210 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Mangil | 063023029 | 2 Classroom School Building | 1 | 1369724.21 | 1151297.22 | 218426.99 | 1151297.22 | Last Tranche | 194973.95 | 1346271.17 | 1151297.22 | 194973.95 | 100% | 100% | 89.26% | 98.29% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-13 | 2007-05-31 | 2007-06-20 | 199 | 190 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Mangil | 063023029 | Road Opening | 1 | 2865094.35 | 2661788.35 | 203306 | 2395609.51 |  | 204329 | 2599938.51 | 2395609.51 | 204329 | 100% | 100% | 100.5% | 90.75% | 100% | 2009-02-13 | no data | 2009-05-05 | 2009-08-31 | no data | 118 | 288 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Matag-ub | 063023030 | Level II Water System | 1 | 1153306.45 | 906522.15 | 246784.3 | 906522.15 | 3rd Tranche | 367046.3 | 1273568.45 | 906522.15 | 367046.3 | 100% | 100% | 148.7% | 110.4% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-14 | 2005-04-30 | 2008-01-16 | 351 | 175 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Matag-ub | 063023030 | Health Station | 1 | 896832.78 | 752994.29 | 143838.49 | 752994.29 | Last Tranche | 123819.19 | 876813.48 | 752994.29 | 123819.19 | 100% | 100% | 86.08% | 97.77% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-28 | 2007-06-27 | 2007-06-23 | 211 | 287 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Monte Magapa | 063023031 | Road Construction | 1 | 629370 | 283350 | 346020 | 283350 | 3rd Tranche | 46520 | 323870 | 283350 | 40520 | 100% | 87.1% | 13.44% | 51.46% | 100% | 2004-01-04 | 2004-03-04 | 2004-06-24 | 2007-03-31 | no data | 1010 | 250 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pangilihan | 063023032 | Barangay Road Rehabilitation | 1 | 322560 | 220280 | 102280 | 220280 | 3rd Tranche | 109478 | 329758 | 220280 | 109478 | 100% | 100% | 107% | 102.2% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-21 | 2004-12-30 | 2005-02-20 | 253 | 166 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pangilihan | 063023032 | Day Care Center | 1 | 739328.49 | 642233.37 | 97095.12 | 642233.37 | 3rd Tranche | 88670.48 | 730903.85 | 642233.37 | 88670.48 | 100% | 100% | 91.32% | 98.86% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-07 | 2006-06-30 | 2006-08-08 | 235 | 166 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pangilihan | 063023032 | Road Upgrading with Concreting RC Pipe Culvert & Side Ditch Canal | 1 | 1611662.33 | 1257848.33 | 353814 | 1132063.5 | 1st | 365064.2 | 1497127.7 | 1132063.5 | 365064.2 | 100% | 100% | 103.2% | 92.89% | 100% | 2009-02-13 | no data | 2009-04-15 | 2009-07-31 | no data | 107 | 181 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Panuran | 063023033 | Barangay Road Rehabilitation | 1 | 1154187 | 220219 | 933968 | 220219 | 3rd Tranche | 116768 | 316317.5 | 220219 | 96098.5 | 100% | 82.3% | 12.5% | 27.41% | 100% | 2004-01-04 | 2004-03-04 | 2004-06-24 | 2008-03-29 | no data | 1374 | 167 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Panuran | 063023033 | Road Upgrading | 1 | 1324500.36 | 1086570.36 | 237930 | 977913.32 | 1st | 239095 | 1217008.32 | 977913.32 | 239095 | 100% | 100% | 100.5% | 91.88% | 100% | 2009-02-13 | no data | 2009-06-01 | 2009-07-31 | no data | 60 | 180 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pararinga | 063023034 | 1 Classroom School Building | 1 | 387219 | 301609.56 | 85609.44 | 301609.56 | 3rd Tranche | 166288.02 | 467897.58 | 301609.56 | 166288.02 | 100% | 100% | 194.2% | 120.8% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-04 | 2005-02-28 | 2005-04-06 | 300 | 95 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pararinga | 063023034 | Day Care Center | 1 | 651062.68 | 582024.58 | 69038.1 | 582024.58 | 3rd Tranche | 84046.1 | 666070.68 | 582024.58 | 84046.1 | 100% | 100% | 121.7% | 102.3% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-11 | 2006-06-30 | 2006-09-30 | 262 | 95 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pararinga | 063023034 | Road Upgrading with Spot Concreting | 1 | 552963.68 | 427347.49 | 125616.19 | 427347.49 | Last Tranche | 145610.83 | 572958.32 | 427347.49 | 145610.83 | 100% | 100% | 115.9% | 103.6% | 100% | 2006-07-17 | 2006-08-10 | 2006-10-23 | 2009-12-30 | no data | 1164 | 95 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Pararinga | 063023034 | Slope Protection | 1 | 1320464.33 | 1137176.73 | 183287.6 | 1023459.05 | 1st | 183287.6 | 1206746.65 | 1023459.05 | 183287.6 | 100% | 100% | 100% | 91.39% | 100% | 2009-02-13 | no data | 2009-04-28 | 2009-07-31 | no data | 94 | 104 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Quipot | 063023036 | Health Station | 1 | 835913.45 | 680020.95 | 155892.5 | 680020.95 | 3rd Tranche | 156722.55 | 836743.5 | 680020.95 | 156722.55 | 100% | 100% | 100.5% | 100.1% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-18 | 2006-06-30 | 2006-04-22 | 255 | 512 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Quipot | 063023036 | Hanging Foot Bridge | 1 | 446663.43 | 374549.34 | 72114.09 | 359974.5 | Last Tranche | 76062.58 | 436037.08 | 359974.5 | 76062.58 | 100% | 100% | 105.5% | 97.62% | 100% | 2006-07-17 | 2006-08-10 | 2006-11-22 | 2007-05-31 | 2007-07-12 | 190 | 512 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Quipot | 063023036 | One Classroom Building | 1 | 786872.74 | 706612.74 | 80260 | 635951.47 | 1st | 84850 | 720801.47 | 635951.47 | 84850 | 100% | 100% | 105.7% | 91.6% | 100% | 2009-02-09 | no data | 2009-03-29 | 2009-05-31 | 2009-06-18 | 63 | 551 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | S.M. Villa | 063023061 | Protection Railing | 1 | 288441.8 | 259288.76 | 29153.04 | 259288.76 | Last Tranche | 28380.86 | 287669.62 | 259288.76 | 28380.86 | 100% | 100% | 97.35% | 99.73% | 100% | 2006-07-17 | 2006-08-10 | 2006-10-08 | 2007-03-27 | 2007-03-27 | 170 | 54 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | San Julian | 063023057 | Road Widening, Gutter & Concrete Footwalk | 1 | 1612037.5 | 1011074.01 | 600963.49 | 1011074.01 | 3rd Tranche | 684514.01 | 1695588.02 | 1011074.01 | 684514.01 | 100% | 100% | 113.9% | 105.2% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-16 | 2004-10-23 | 2005-02-12 | 190 | 273 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | San Julian | 063023057 | Road Concreting with Canal | 1 | 1707604.54 | 1060220.18 | 647384.36 | 1060220.18 | 3rd Tranche | 619572.18 | 1679792.36 | 1060220.18 | 619572.18 | 100% | 100% | 95.7% | 98.37% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-11 | 2006-06-30 | 2006-07-05 | 262 | 273 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | San Pedro | 063023058 | Drainage System Improvement | 1 | 358298.76 | 209792.36 | 148506.4 | 188813.12 |  | 149481.4 | 338294.52 | 188813.12 | 149481.4 | 100% | 100% | 100.7% | 94.42% | 100% | 2009-02-13 | no data | 2009-04-13 | 2009-06-30 | 2009-07-07 | 78 | 99 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Sarawag | 063023038 | Health Station | 1 | 452702.4 | 315716.2 | 136986.2 | 315716.2 | 3rd Tranche | 138745.7 | 454461.9 | 315716.2 | 138745.7 | 100% | 100% | 101.3% | 100.4% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-29 | 2005-02-28 | 2005-02-27 | 305 | 110 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Sta. Rita | 063023059 | Multi-Purpose Drainage | 1 | 3794571.21 | 2638756.98 | 1155814.23 | 2374881.28 | 2nd Tranche | 1136356.66 | 3449444.87 | 2374881.28 | 1074563.59 | 100% | 94.56% | 98.32% | 90.9% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-25 | 2006-06-30 | 2006-09-04 | 248 | 121 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Sto. Tomas | 063023037 | Barangay Road Rehabilitation | 1 | 955975.3 | 596991.5 | 358983.8 | 596991.5 | 3rd Tranche | 580328.8 | 1177320.3 | 596991.5 | 580328.8 | 100% | 100% | 161.7% | 123.2% | 100% | 2004-01-04 | 2004-03-04 | 2004-07-17 | 2005-01-26 | 2005-02-27 | 193 | 138 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Sto. Tomas | 063023037 | Health Station | 1 | 581648.68 | 488726.23 | 92922.45 | 488726.23 | Last Tranche | 88975.45 | 577701.68 | 488726.23 | 88975.45 | 100% | 100% | 95.75% | 99.32% | 100% | 2006-07-17 | 2006-08-10 | 2006-10-31 | 2007-04-30 | 2007-05-09 | 181 | 135 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Sto. Tomas | 063023037 | Road Upgrading with spot concreting | 1 | 1190379.06 | 939099.06 | 251280 | 845189.16 | 1st | 251405 | 1096594.16 | 845189.16 | 251405 | 100% | 100% | 100% | 92.12% | 100% | 2009-02-13 | no data | 2009-04-12 | 2009-06-30 | no data | 79 | 145 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tambal | 063023039 | Day Care Center | 1 | 685426.95 | 554243.43 | 131183.52 | 554243.43 | 3rd Tranche | 119966.76 | 674210.19 | 554243.43 | 119966.76 | 100% | 100% | 91.45% | 98.36% | 100% | 2005-07-06 | 2005-08-18 | 2005-10-13 | 2006-06-30 | 2006-10-06 | 260 | 227 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tambal | 063023039 | Barangay Health Station | 1 | 725540.7 | 617601.71 | 107938.99 | 567904.82 | 1st | 113485.48 | 681390.3 | 567904.82 | 113485.48 | 100% | 100% | 105.1% | 93.91% | 100% | 2009-02-09 | no data | 2009-03-20 | 2009-06-30 | no data | 102 | 238 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tamu-an | 063023040 | 1 CL Building | 1 | 736764.34 | 647549.34 | 89215 | 582794.41 | 1st | 101477.5 | 684271.91 | 582794.41 | 101477.5 | 100% | 100% | 113.7% | 92.88% | 100% | 2009-02-09 | no data | 2009-03-30 | 2009-07-31 | no data | 123 | 177 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tamu-an | 063023040 | Road Upgrading with Concreting | 1 | 2497130.83 | 1616358.35 | 880772.48 | 1454722.52 | 2nd Tranche | 722713.08 | 2105535.6 | 1454722.52 | 650813.08 | 100% | 90.05% | 82.05% | 84.32% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-11 | 2006-06-30 | 2006-09-16 | 231 | 178 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tiringanan | 063023041 | Health Station | 1 | 552995.4 | 269116.2 | 283879.2 | 269116.2 | 3rd Tranche | 268441.7 | 537557.9 | 269116.2 | 268441.7 | 100% | 100% | 94.56% | 97.21% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-12 | 2005-07-18 | no data | 462 | 146 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tiringanan | 063023041 | 1 CL Building | 1 | 738764.34 | 649269.34 | 89495 | 584342.21 | 1st | 90045 | 674387.21 | 584342.21 | 90045 | 100% | 100% | 100.6% | 91.29% | 100% | 2009-02-09 | no data | 2009-04-07 | 2009-07-31 | no data | 115 | 42 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tuburan | 063023043 | Level II Water System | 1 | 763506.55 | 512822.55 | 250684 | 512822.55 | 3rd Tranche | 274473 | 787295.55 | 512822.55 | 274473 | 100% | 100% | 109.5% | 103.1% | 100% | 2004-01-04 | 2004-03-04 | 2004-04-26 | 2005-03-04 | 2005-04-24 | 312 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Tuburan | 063023043 | Health Station | 1 | 908056.62 | 683704.65 | 224351.97 | 683704.65 | 3rd Tranche | 180787.13 | 833118.94 | 683704.65 | 149414.29 | 100% | 82.65% | 80.58% | 91.75% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-05 | 2006-06-30 | no data | 237 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Ubian | 063023044 | Hanging Bridge | 1 | 359144.95 | 251401.45 | 107743.5 | 251401.45 | 3rd Tranche | 72822.5 | 324223.95 | 251401.45 | 72822.5 | 100% | 100% | 67.59% | 90.28% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-15 | 2005-01-14 | 2005-02-24 | 244 | 175 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Ubian | 063023044 | Health Station | 1 | 776913.45 | 227658.26 | 549255.19 | 227658.26 | 2nd Tranche | 470158 | 697816.26 | 227658.26 | 470158 | 100% | 100% | 85.6% | 89.82% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-05 | 2007-05-31 | no data | 572 | 175 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Yabon | 063023045 | Day Care Center | 1 | 636890.01 | 560750.01 | 76140 | 504675.01 | 1st | 78050 | 582725.01 | 504675.01 | 78050 | 100% | 100% | 102.5% | 91.5% | 100% | 2009-02-09 | no data | 2009-03-27 | 2009-06-30 | no data | 95 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Yabon | 063023045 | Hanging Bridge | 1 | 446635.36 | 302330.88 | 144304.48 | 302330.88 | 3rd Tranche | 111275.66 | 413606.54 | 302330.88 | 111275.66 | 100% | 100% | 77.11% | 92.6% | 100% | 2004-01-04 | 2004-03-04 | 2004-05-15 | 2005-03-19 | 2005-04-23 | 308 | 157 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Janiuay | 063023 | Yabon | 063023045 | Road Upgrading/ Concreting | 1 | 2595424.75 | 2080851 | 514573.75 | 2080851 | 3rd Tranche | 657822.14 | 2738673.14 | 2080851 | 657822.14 | 100% | 100% | 127.8% | 105.5% | 100% | 2005-07-06 | 2005-08-18 | 2005-11-11 | 2007-05-31 | 2006-07-12 | 566 | 157 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Agsirab | 063025001 | Hanging Foot Bridge | 1 | 2274715 | 1337942.65 | 936772.35 | 1070354.12 | 1st Tranche | 869110 | 1939464.12 | 1070354.12 | 869110 | 100% | 100% | 92.78% | 85.26% | 100% | 2006-06-26 | 2006-07-31 | 2007-03-05 | 2008-08-01 | no data | 515 | 257 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Alugmawa | 063025003 | Hanging Foot Bridge | 1 | 1627008.91 | 1442117.19 | 184891.72 | 1200526.68 | 1st Tranche | 255431.44 | 1455958.12 | 1200526.68 | 255431.44 | 100% | 100% | 138.2% | 89.49% | 100% | 2006-06-26 | 2006-07-31 | 2007-01-01 | 2007-12-01 | no data | 334 | 1192 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Badiangan | 063025004 | Road Upgrading | 1 | 1548222.4 | 1366127.94 | 182094.46 | 1092902.35 | 1st Tranche | 191555.9 | 1284458.25 | 1092902.35 | 191555.9 | 100% | 100% | 105.2% | 82.96% | 100% | 2006-06-26 | 2006-07-31 | 2007-03-05 | 2008-05-01 | no data | 423 | 62 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bagongbong | 063025005 | Road Construction | 1 | 4140718.62 | 1329331.04 | 2811387.58 | 1329331.04 | 3rd Tranche | 2811770.49 | 4141101.53 | 1329331.04 | 2811770.49 | 100% | 100% | 100% | 100% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-02 | 2005-07-31 | no data | 363 | 198 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Banban | 063025007 | Hanging Foot Bridge | 1 | 1752000 | 1607183.94 | 144816.06 | 1607183.94 | 1st Tranche | 139185.36 | 1746369.3 | 1607183.94 | 139185.36 | 100% | 100% | 96.11% | 99.68% | 100% | 2006-06-26 | 2006-07-31 | 2007-07-01 | 2009-01-01 | n/a | 550 | 137 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bansag | 063025008 | Day Care Center | 1 | 620000 | 498871 | 121129 | 448983.9 | 1st Tranche | 163100 | 612083.9 | 448983.9 | 163100 | 100% | 100% | 134.6% | 98.72% | 100% | 2006-06-26 | 2006-07-31 | 2006-12-08 | 2009-01-01 | n/a | 755 | 103 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bayuco | 063025009 | Road Rehabilitation & Construction | 1 | 4222218.5 | 4024818.5 | 197400 | 4024818.5 | 3rd Tranche | 397159 | 4421977.5 | 4024818.5 | 397159 | 100% | 100% | 201.2% | 104.7% | 100% | 2005-07-11 | 2005-08-10 | 2005-12-05 | 2006-07-31 | no data | 238 | 58 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Binaba-an Armada | 063025010 | Water System level II | 1 | 627500 | 469250 | 158250 | 469250 | 3rd Tranche | 161935.1 | 631185.1 | 469250 | 161935.1 | 100% | 100% | 102.3% | 100.6% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-02 | 2005-04-30 | no data | 271 | 95 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Binaba-an Labayno | 063025011 | Water Supply System level II | 1 | 637500 | 430950 | 206550 | 430950 | 3rd Tranche | 195225.5 | 626175.5 | 430950 | 195225.5 | 100% | 100% | 94.52% | 98.22% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-09 | 2005-06-30 | no data | 325 | 111 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Binaba-an Limoso | 063025012 | Water Supply System level II | 1 | 617594 | 447194 | 170400 | 447194 | 3rd Tranche | 168239 | 615433 | 447194 | 168239 | 100% | 100% | 98.73% | 99.65% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-02 | 2005-05-31 | no data | 302 | 87 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Binabaan Portigo | 063025013 | Day Care Center | 1 | 758840.05 | 682560.05 | 76280 | 682560.05 | 3rd Tranche | 77329.5 | 759889.55 | 682560.05 | 77329.5 | 100% | 100% | 101.4% | 100.1% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-07 | 2006-07-31 | no data | 266 | 101 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Binaba-an Tirador | 063025014 | Day Care Center | 1 | 517440.06 | 323966.62 | 193473.44 | 323966.62 | 3rd Tranche | 194325.14 | 518291.76 | 323966.62 | 194325.14 | 100% | 100% | 100.4% | 100.2% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-15 | 2005-03-31 | no data | 259 | 20 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Bonbon | 063025015 | Road Upgrading | 1 | 1140000 | 1029642.06 | 110357.94 | 823713.65 | 1st Tranche | 260357.94 | 1084071.59 | 823713.65 | 260357.94 | 100% | 100% | 235.9% | 95.09% | 100% | 2006-06-26 | 2006-07-31 | 2007-06-01 | 2009-04-30 | n/a | 699 | 138 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Buri | 063025017 | Road Rehabilitation & Construction | 1 | 2598558.98 | 2300958.98 | 297600 | 2179598.33 | 2nd Tranche | 368401.62 | 2547999.95 | 2179598.33 | 368401.62 | 100% | 100% | 123.8% | 98.05% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-21 | 2006-07-31 | no data | 252 | 100 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Buwang - C2 | 063025019 | Hanging Footbridge | 2 | 2050840.35 | 1921600.35 | 129240 | 1921600.35 | 3rd Tranche | 143493.4 | 2065093.75 | 1921600.35 | 143493.4 | 100% | 100% | 111% | 100.7% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-22 | 2006-07-31 | no data | 251 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Malag-it | 063025046 | Hanging Footbridge | 2 | 2050840.35 | 1921600.35 | 129240 | 1921600.35 | 3rd Tranche | 143493.4 | 2065093.75 | 1921600.35 | 143493.4 | 100% | 100% | 111% | 100.7% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-22 | 2006-07-31 | no data | 251 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cabatangan | 063025020 | 2 Classroom Elementary School Building | 1 | 1395165.18 | 1137597.42 | 257567.76 | 910077.94 | 1st Tranche | 189622.07 | 1099700.01 | 910077.94 | 189622.07 | 100% | 100% | 73.62% | 78.82% | 100% | 2006-06-26 | 2006-07-31 | 2006-12-18 | 2009-03-30 | n/a | 833 | 305 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cabugao | 063025021 | Road Improvement | 1 | 1495485 | 1137511 | 357974 | 1137511 | 3rd Tranche | 392367.25 | 1529878.25 | 1137511 | 392367.25 | 100% | 100% | 109.6% | 102.3% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-30 | 2005-04-30 | no data | 243 | 248 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cabugao | 063025021 | 2 Classroom Elementary School Building | 1 | 1007000 | 908530.35 | 98469.65 | 847583.35 | 2nd Tranche | 98469.65 | 946053 | 847583.35 | 98469.65 | 100% | 100% | 100% | 93.95% | 100% | 2006-06-26 | 2006-07-31 | 2006-11-13 | 2009-04-30 | n/a | 899 | 157 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cabunlawan | 063025022 | Travelling Ricemill | 1 | 695963.77 | 593092.71 | 102871.06 | 559590.78 | 1st Tranche | 97553.06 | 657143.84 | 559590.78 | 97553.06 | 100% | 100% | 94.83% | 94.42% | 100% | 2006-06-26 | 2006-07-31 | 2007-06-01 | 2009-04-30 | n/a | 699 | 84 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Caguisanan | 063025023 | Road Construction | 1 | 5015289.6 | 1446613.44 | 3568676.16 | 1446613.44 | 3rd Tranche | 3517905.91 | 4964519.35 | 1446613.44 | 3517905.91 | 100% | 100% | 98.58% | 98.99% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-30 | 2005-06-30 | no data | 273 | 257 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Caguisanan | 063025023 | 1 Classroom Elementary School Building | 1 | 703188.4 | 222355.84 | 480832.56 | 177884.67 | 1st Tranche | 435172.27 | 613056.94 | 177884.67 | 435172.27 | 100% | 100% | 90.5% | 87.18% | 100% | 2006-06-26 | 2006-07-31 | 2007-01-19 | 2008-03-01 | no data | 407 | 220 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Caloy-Ahan | 063025024 | Road Improvement | 1 | 1708163.33 | 1331607.33 | 376556 | 1331607.33 | 3rd Tranche | 225347.2 | 1556954.53 | 1331607.33 | 225347.2 | 100% | 100% | 59.84% | 91.15% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-30 | 2005-03-31 | no data | 213 | 138 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cayan Este | 063025027 | Water System level II | 1 | 1585382 | 1028322.14 | 557059.86 | 1028322.14 | 3rd Tranche | 558272.8 | 1586594.94 | 1028322.14 | 558272.8 | 100% | 100% | 100.2% | 100.1% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-05 | 2005-03-31 | no data | 269 | 104 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cayan Oeste | 063025028 | Water System level II | 1 | 1339015.43 | 953556.41 | 385459.02 | 953556.41 | 3rd Tranche | 437321.53 | 1390877.94 | 953556.41 | 437321.53 | 100% | 100% | 113.5% | 103.9% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-26 | 2005-06-30 | no data | 339 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Corot-on | 063025029 | Road Rehabilitation | 1 | 1969607.64 | 1464087.64 | 505520 | 1464087.64 | 3rd Tranche | 144326.25 | 1608413.89 | 1464087.64 | 144326.25 | 100% | 100% | 28.55% | 81.66% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-19 | 2005-05-31 | no data | 254 | 35 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Coto | 063025030 | Road Rehabilitation & Construction | 1 | 3593002.73 | 3228852.73 | 364150 | 2905967.46 | 2nd Tranche | 476752.08 | 3382719.54 | 2905967.46 | 476752.08 | 100% | 100% | 130.9% | 94.15% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-21 | 2007-05-01 | no data | 526 | 100 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cubay | 063025031 | Water System Level II | 1 | 995000 | 669260.45 | 325739.55 | 602334.41 | 1st Tranche | 345308.4 | 947642.81 | 602334.41 | 345308.4 | 100% | 100% | 106% | 95.24% | 100% | 2006-06-26 | 2006-07-31 | 2007-03-26 | 2009-03-30 | n/a | 735 | 135 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Cunarum | 063025032 | Day Care Center | 1 | 623941.26 | 573405.26 | 50536 | 573405.26 | 3rd Tranche | 128961 | 702366.26 | 573405.26 | 128961 | 100% | 100% | 255.2% | 112.6% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-08 | 2006-07-31 | no data | 265 | 187 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Daanbanwa | 063025033 | Health Station | 1 | 958289.16 | 841669.16 | 116620 | 841669.16 | 3rd Tranche | 111735 | 953404.16 | 841669.16 | 111735 | 100% | 100% | 95.81% | 99.49% | 100% | 2005-07-11 | 2005-08-10 | 2005-10-31 | 2006-10-31 | no data | 365 | 201 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Higpos | 063025035 | Road Construction | 1 | 1547000.01 | 1195517.13 | 351482.88 | 956413.7 | 1st Tranche | 451482.88 | 1407896.58 | 956413.7 | 451482.88 | 100% | 100% | 128.5% | 91.01% | 100% | 2006-06-26 | 2006-07-31 | 2007-03-28 | 2009-08-31 | no data | 887 | 161 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Jayubo | 063025036 | 3 Units Box Culvert | 1 | 1877264.15 | 1386678.55 | 490585.6 | 1248010.7 | 1st Tranche | 195851.68 | 1443862.38 | 1248010.7 | 195851.68 | 100% | 100% | 39.92% | 76.91% | 100% | 2006-06-26 | 2006-07-31 | 2007-06-01 | 2009-08-31 | no data | 822 | 640 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Jorog | 063025037 | Day Care Center | 1 | 642128.14 | 553688.14 | 88440 | 553688.14 | 3rd Tranche | 96155 | 649843.14 | 553688.14 | 96155 | 100% | 100% | 108.7% | 101.2% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-17 | 2006-11-30 | no data | 378 | 82 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Lanot Grande | 063025038 | Road Upgrading | 1 | 1177000.01 | 1072695.38 | 104304.63 | 858156.3 | 1st Tranche | 195804.63 | 1053960.93 | 858156.3 | 195804.63 | 100% | 100% | 187.7% | 89.55% | 100% | 2006-06-26 | 2006-07-31 | 2006-11-23 | 2009-03-30 | n/a | 858 | 80 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Lanot Pequeño | 063025039 | Road Upgrading | 1 | 3469307.54 | 3390085.04 | 79222.5 | 3390085.04 | 3rd Tranche | 204500 | 3594585.04 | 3390085.04 | 204500 | 100% | 100% | 258.1% | 103.6% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-28 | 2009-03-30 | n/a | 1218 | 51 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Legayada | 063025040 | Day Care Center | 1 | 571740.06 | 372660.06 | 199080 | 372660.06 | 3rd Tranche | 197300 | 569960.06 | 372660.06 | 197300 | 100% | 100% | 99.11% | 99.69% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-05 | 2005-03-31 | no data | 269 | 76 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Lumanay | 063025041 | Day Care Center | 1 | 630200.13 | 557890.13 | 72310 | 502101.13 | 2nd Tranche | 45930 | 548031.13 | 502101.13 | 45930 | 100% | 100% | 63.52% | 86.96% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-17 | 2006-07-31 | no data | 256 | 120 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Madarag | 063025042 | Water Supply System level II | 1 | 614218 | 372547.5 | 241670.5 | 372547.5 | 3rd Tranche | 245176.8 | 617724.3 | 372547.5 | 245176.8 | 100% | 100% | 101.5% | 100.6% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-28 | 2005-05-31 | no data | 307 | 120 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Marong | 063025049 | Road Construction | 1 | 1204413.78 | 756815.4 | 447598.38 | 605452.32 | 1st Tranche | 427817.18 | 1033269.5 | 605452.32 | 427817.18 | 100% | 100% | 95.58% | 85.79% | 100% | 2006-06-26 | 2006-07-31 | 2006-12-11 | 2008-08-01 | no data | 599 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Natividad | 063025051 | Water System level II | 1 | 663499 | 450649 | 212850 | 450649 | 3rd Tranche | 255833.5 | 706482.5 | 450649 | 255833.5 | 100% | 100% | 120.2% | 106.5% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-02 | 2005-05-31 | no data | 302 | 93 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Natividad | 063025051 | Road Construction | 1 | 2276509.11 | 1463953.68 | 812555.43 | 1171162.94 | 1st Tranche | 769867.43 | 1941030.37 | 1171162.94 | 769867.43 | 100% | 100% | 94.75% | 85.26% | 100% | 2006-06-26 | 2006-07-31 | 2006-12-15 | 2008-02-01 | no data | 413 | 88 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Pajo | 063025052 | 2 Classroom Elementary School Building | 1 | 1223775.32 | 1009848.95 | 213926.37 | 908864.05 | 2nd Tranche | 178930.69 | 1087794.74 | 908864.05 | 178930.69 | 100% | 100% | 83.64% | 88.89% | 100% | 2006-06-26 | 2006-07-31 | 2006-12-19 | 2007-12-01 | no data | 347 | 340 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Pandan | 063025053 | Road Improvement | 1 | 1563957.93 | 1255845.53 | 308112.4 | 1255845.53 | 3rd Tranche | 322477.72 | 1578323.25 | 1255845.53 | 322477.72 | 100% | 100% | 104.7% | 100.9% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-06 | 2005-05-31 | no data | 267 | 145 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Panuran | 063025054 | 2 Classroom School Building | 1 | 632472.99 | 431339.31 | 201133.68 | 431339.31 | 3rd Tranche | 102633.67 | 533972.98 | 431339.31 | 102633.67 | 100% | 100% | 51.03% | 84.43% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-05 | 2005-06-30 | no data | 360 | 235 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Pasig | 063025055 | Road Rehabilitation | 1 | 4901081.9 | 1572824.08 | 3328257.82 | 1572824.08 | 3rd Tranche | 3335720.31 | 4908544.39 | 1572824.08 | 3335720.31 | 100% | 100% | 100.2% | 100.2% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-26 | 2005-05-31 | no data | 278 | 243 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Patag | 063025056 | Road Improvement | 1 | 871737 | 663187 | 208550 | 663187 | 3rd Tranche | 216474 | 879661 | 663187 | 216474 | 100% | 100% | 103.8% | 100.9% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-07 | 2005-04-30 | no data | 235 | 71 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Poblacion Ilaya | 063025058 | Solar Dryer | 1 | 508592.28 | 435196.03 | 73396.25 | 435196.03 | 3rd Tranche | 68406.25 | 503602.28 | 435196.03 | 68406.25 | 100% | 100% | 93.2% | 99.02% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-22 | 2007-05-01 | no data | 525 | 60 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Poong | 063025059 | Road Rehabilitation | 1 | 3289860 | 1701824 | 1588036 | 1701824 | 3rd Tranche | 1383140.07 | 3084964.07 | 1701824 | 1383140.07 | 100% | 100% | 87.1% | 93.77% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-23 | 2005-05-31 | no data | 250 | 94 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Pughanan | 063025060 | Hydraulic Ram Pump Irrigation | 1 | 2084116.71 | 1015686.72 | 1068429.99 | 1015686.72 | 3rd Tranche | 415188.05 | 1430874.77 | 1015686.72 | 415188.05 | 100% | 100% | 38.86% | 68.66% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-30 | 2005-08-31 | no data | 335 | 296 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Pungsod | 063025061 | Day Care Center | 1 | 494440.06 | 306075.06 | 188365 | 306075.06 | 3rd Tranche | 129776.44 | 435851.5 | 306075.06 | 129776.44 | 100% | 100% | 68.9% | 88.15% | 100% | 2004-02-19 | 2004-04-28 | 2004-06-28 | 2005-05-31 | no data | 337 | 78 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Sagcup | 063025063 | Road Rehabilitation | 1 | 5502750 | 1061936 | 4440814 | 1061936 | 3rd Tranche | 4212239 | 5282237.92 | 1061936 | 4220301.92 | 100% | 100.2% | 94.85% | 95.99% | 100% | 2004-02-19 | 2004-04-28 | 2004-09-13 | 2005-08-31 | no data | 352 | 96 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | San Gregorio | 063025064 | Day Care Center | 1 | 610000 | 503832.5 | 106167.5 | 484654.54 | 2nd Tranche | 105660 | 590314.54 | 484654.54 | 105660 | 100% | 100% | 99.52% | 96.77% | 100% | 2006-06-26 | 2006-07-31 | 2006-10-13 | 2009-01-01 | n/a | 811 | 107 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Sibacungan | 063025065 | Water System level II | 1 | 1557517 | 1021591 | 535926 | 1021591 | 3rd Tranche | 528284.1 | 1567092.25 | 1021591 | 545501.25 | 100% | 103.3% | 98.57% | 100.6% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-12 | 2005-06-30 | no data | 353 | 212 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Sibaguan | 063025066 | Health Station | 1 | 810060.75 | 733010.75 | 77050 | 733010.75 | 3rd Tranche | 72075 | 805085.75 | 733010.75 | 72075 | 100% | 100% | 93.54% | 99.39% | 100% | 2005-07-11 | 2005-08-10 | 2005-10-31 | 2006-09-30 | no data | 334 | 73 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Simsiman | 063025067 | Water Supply System level II | 1 | 783999 | 362999 | 421000 | 362999 | 3rd Tranche | 257856 | 620855 | 362999 | 257856 | 100% | 100% | 61.25% | 79.19% | 100% | 2004-02-19 | 2004-04-28 | 2004-07-27 | 2005-05-31 | no data | 308 | 119 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Simsiman | 063025067 | 1 Classroom Elementary School Building | 1 | 627431.18 | 519747 | 107684.18 | 494779.68 | 1st Tranche | 103061.82 | 597841.5 | 494779.68 | 103061.82 | 100% | 100% | 95.71% | 95.28% | 100% | 2006-06-26 | 2006-07-31 | 2006-11-05 | 2008-04-01 | no data | 513 | 114 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Supoc | 063025068 | Road Rehabilitation | 1 | 1295446.12 | 948446.12 | 347000 | 948446.12 | 3rd Tranche | 139410.25 | 1087856.37 | 948446.12 | 139410.25 | 100% | 100% | 40.18% | 83.98% | 100% | 2004-02-19 | 2004-04-28 | 2004-08-25 | 2005-05-31 | no data | 279 | 49 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Supoc | 063025068 | Day Care Center | 1 | 636646.71 | 497390.79 | 139255.92 | 471665.94 | 1st Tranche | 125878.48 | 597544.42 | 471665.94 | 125878.48 | 100% | 100% | 90.39% | 93.86% | 100% | 2006-06-26 | 2006-07-31 | 2006-11-28 | 2008-10-01 | no data | 673 | 50 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Tubungan | 063025071 | Road Upgrading | 1 | 1399742.91 | 952189.92 | 447552.99 | 761751.93 | 1st Tranche | 455911.23 | 1217663.16 | 761751.93 | 455911.23 | 100% | 100% | 101.9% | 86.99% | 100% | 2006-06-26 | 2006-07-31 | 2007-01-01 | 2009-03-30 | n/a | 819 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Tuburan | 063025072 | Road Upgrading & New Construction | 1 | 2834562.66 | 2656264.88 | 178297.78 | 2656264.88 | 3rd Tranche | 249150 | 2905414.88 | 2656264.88 | 249150 | 100% | 100% | 139.7% | 102.5% | 100% | 2005-07-11 | 2005-08-10 | 2005-11-14 | 2008-03-01 | no data | 838 | 120 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lambunao | 063025 | Walang | 063025073 | Water System Level II | 1 | 2411795.77 | 1728609.15 | 683186.62 | 1644599.8 | 1st Tranche | 1192909.15 | 2837508.95 | 1644599.8 | 1192909.15 | 100% | 100% | 174.6% | 117.7% | 100% | 2006-06-26 | 2006-07-31 | 2007-03-26 | 2009-04-30 | n/a | 766 | 388 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Agpipili | 063027001 | Electrification | 1 | 628664.08 | 361502.28 | 267161.8 | 361502.28 | 3rd Tranche | 268481.8 | 629984.08 | 361502.28 | 268481.8 | 100% | 100% | 100.5% | 100.2% | 100% | 2004-02-05 | 2004-04-27 | 2004-09-01 | 2005-06-30 | no data | 302 | 170 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Alcantara | 063027002 | Road Upgrading | 1 | 1407200.92 | 1118100 | 289100.92 | 1118100 | 1st Tranche | 283487.92 | 1401587.92 | 1118100 | 283487.92 | 100% | 100% | 98.06% | 99.6% | 100% | 2006-08-02 | 2006-08-23 | 2007-03-01 | 2009-05-30 | no data | 821 | 171 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Almeñana | 063027003 | Health Station | 1 | 740072.86 | 623000 | 117072.86 | 623000 | 3rd Tranche | 126897.16 | 749897.16 | 623000 | 126897.16 | 100% | 100% | 108.4% | 101.3% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-16 | 2006-07-31 | no data | 257 | 230 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Almeñana | 063027003 | Water System Level II | 1 | 1657177.6 | 1402027.6 | 255150 | 1261824.84 | 1st Tranche | 113000 | 1374824.84 | 1261824.84 | 113000 | 100% | 100% | 44.29% | 82.96% | 100% | 2006-08-02 | 2006-08-23 | 2007-05-01 | 2009-04-30 | n/a | 730 | 190 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Anabo | 063027004 | Post Harvest Facilities | 1 | 680342.66 | 439929.36 | 240413.3 | 439929.36 | 3rd Tranche | 259756.18 | 699685.54 | 439929.36 | 259756.18 | 100% | 100% | 108% | 102.8% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-21 | 2006-04-30 | no data | 160 | 195 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Anabo | 063027004 | 3 Classroom School Building | 1 | 1619920 | 1205460 | 414460 | 1147608.17 | 1st Tranche | 420840 | 1568448.17 | 1147608.17 | 420840 | 100% | 100% | 101.5% | 96.82% | 100% | 2006-08-02 | 2006-08-23 | 2006-11-20 | 2009-07-30 | no data | 983 | 200 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Bankal | 063027005 | Barangay Road Rehabilitation | 1 | 1022687.5 | 942877.5 | 79810 | 942877.5 | 3rd Tranche | 130615 | 1073492.5 | 942877.5 | 130615 | 100% | 100% | 163.7% | 105% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-03 | 2005-05-31 | no data | 332 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Buenavista | 063027006 | Barangay Road Rehabilitation | 1 | 1201565.6 | 933890.6 | 267675 | 933890.6 | 3rd Tranche | 753551.8 | 1687442.4 | 933890.6 | 753551.8 | 100% | 100% | 281.5% | 140.4% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-21 | 2005-05-31 | no data | 314 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Cabantohan | 063027007 | Farm Facilities | 1 | 522200 | 392700 | 129500 | 392700 | 100% Tranche | 196750 | 589450 | 392700 | 196750 | 100% | 100% | 151.9% | 112.9% | 100% | 2006-08-02 | 2006-08-23 | 2006-10-12 | 2007-01-31 | no data | 111 | 192 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Capiñahan | 063027008 | Barangay Road Rehabilitation | 1 | 980603.5 | 923183.5 | 57420 | 923183.5 | 3rd Tranche | 386927 | 1310110.5 | 923183.5 | 386927 | 100% | 100% | 673.9% | 133.6% | 100% | 2004-02-05 | 2004-04-27 | 2004-09-08 | 2005-05-31 | 2005-10-11 | 265 | 114 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Capiñahan | 063027008 | Three Barrel Box Culvert | 1 | 1480010.77 | 1329667.91 | 150342.86 | 1329667.91 | 3rd Tranche | 151657.16 | 1481325.07 | 1329667.91 | 151657.16 | 100% | 100% | 100.9% | 100.1% | 100% | 2005-08-22 | 2005-09-20 | 2005-12-05 | 2006-06-30 | no data | 207 | 116 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Dalipe | 063027009 | Solar Dryer | 1 | 336928.03 | 269500 | 67428.03 | 269500 | 3rd Tranche | 75475.66 | 344975.66 | 269500 | 75475.66 | 100% | 100% | 111.9% | 102.4% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-08 | 2006-05-31 | no data | 204 | 65 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Dapdapan | 063027010 | Barangay Road Rehabilitation | 1 | 1376691.2 | 1221581.2 | 155110 | 1221581.2 | 3rd Tranche | 422910 | 1644491.2 | 1221581.2 | 422910 | 100% | 100% | 272.7% | 119.5% | 100% | 2004-02-05 | 2004-04-27 | 2004-09-28 | 2005-06-30 | no data | 275 | 88 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Dapdapan | 063027010 | Road Upgrading | 1 | 1083826.74 | 998733.89 | 85092.85 | 998733.89 | 3rd Tranche | 113773.36 | 1112507.25 | 998733.89 | 113773.36 | 100% | 100% | 133.7% | 102.6% | 100% | 2005-08-22 | 2005-09-20 | 2005-12-06 | 2006-06-30 | no data | 206 | 88 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Gerongan | 063027011 | Solar Drier | 1 | 644839.75 | 465852.75 | 178987 | 465852.75 | 3rd Tranche | 219175 | 685027.75 | 465852.75 | 219175 | 100% | 100% | 122.5% | 106.2% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-05 | 2005-04-30 | no data | 299 | 194 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Imbaulan | 063027012 | Electrification | 1 | 536967.52 | 371085.69 | 165881.83 | 371085.69 | 3rd Tranche | 272632.83 | 643718.52 | 371085.69 | 272632.83 | 100% | 100% | 164.4% | 119.9% | 100% | 2004-02-05 | 2004-04-27 | 2004-09-01 | 2005-06-30 | no data | 302 | 179 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Layogbato | 063027013 | Barangay Road Rehabilitation | 1 | 1592142.8 | 1184042.8 | 408100 | 1184042.6 | 3rd Tranche | 410570 | 1594612.6 | 1184042.6 | 410570 | 100% | 100% | 100.6% | 100.2% | 100% | 2004-02-05 | 2004-04-27 | 2004-09-26 | 2005-09-30 | no data | 369 | 72 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Marapal | 063027014 | Water Supply System Level II | 1 | 1239112.2 | 899500.2 | 339612 | 899500.2 | 3rd Tranche | 349532 | 1249032.2 | 899500.2 | 349532 | 100% | 100% | 102.9% | 100.8% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-12 | 2005-06-30 | no data | 353 | 167 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Marapal | 063027014 | Day Care Center | 1 | 766247.66 | 256307.09 | 509940.57 | 230676.38 | 2nd Tranche | 360548.03 | 591224.41 | 230676.38 | 360548.03 | 100% | 100% | 70.7% | 77.16% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-21 | 2007-05-01 | no data | 526 | 167 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Milan | 063027015 | Water System Level I | 1 | 532380 | 426000 | 106380 | 340800 | 1st Tranche | 61198.93 | 401998.93 | 340800 | 61198.93 | 100% | 100% | 57.53% | 75.51% | 100% | 2006-08-02 | 2006-08-23 | 2006-11-15 | 2008-10-01 | no data | 686 | 200 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Nasapahan | 063027017 | Rice Mill | 1 | 660469.55 | 585819.55 | 74650 | 585819.55 | 3rd Tranche | 65830 | 651649.55 | 585819.55 | 65830 | 100% | 100% | 88.18% | 98.66% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-05 | 2005-05-31 | no data | 330 | 74 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Nasapahan | 063027017 | 2 Unit Solar Dryer | 1 | 397910.2 | 309800 | 88110.2 | 309800 | 1st Tranche | 77710.2 | 387510.2 | 309800 | 77710.2 | 100% | 100% | 88.2% | 97.39% | 100% | 2006-08-02 | 2006-08-23 | 2006-11-04 | 2009-02-25 | n/a | 844 | 50 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Poblacion NW Zone | 063027020 | 3 Classroom School Building | 1 | 1563695 | 1161600 | 402095 | 1045440 | 1st Tranche | 277000 | 1322440 | 1045440 | 277000 | 100% | 100% | 68.89% | 84.57% | 100% | 2006-08-02 | 2006-08-23 | 2006-11-16 | 2009-02-25 | n/a | 832 | 190 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Omio | 063027018 | Health Station | 1 | 457162.39 | 190986.55 | 266175.84 | 190986.55 | 3rd Tranche | 306960.84 | 497947.39 | 190986.55 | 306960.84 | 100% | 100% | 115.3% | 108.9% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-03 | 2005-05-31 | no data | 332 | 132 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Pacuan | 063027019 | Road Concreting | 1 | 2582204.06 | 2328500 | 253704.06 | 2328500 | 3rd Tranche | 263704.06 | 2591382.65 | 2328500 | 262882.65 | 100% | 99.69% | 103.9% | 100.4% | 100% | 2005-08-22 | 2005-09-20 | 2006-01-29 | 2006-08-30 | no data | 213 | 113 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Pontoc | 063027022 | 1 CL School Building | 1 | 801864.06 | 662821.2 | 139042.86 | 662821.2 | 3rd Tranche | 166445.03 | 829266.23 | 662821.2 | 166445.03 | 100% | 100% | 119.7% | 103.4% | 100% | 2005-08-22 | 2005-09-20 | 2005-12-05 | 2006-07-31 | no data | 238 | 240 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Pontoc | 063027022 | Day Care Center | 1 | 609700 | 494500 | 115200 | 395600 | 1st Tranche | 68000 | 463600 | 395600 | 68000 | 100% | 100% | 59.03% | 76.04% | 100% | 2006-08-02 | 2006-08-23 | 2006-12-06 | 2008-12-01 | no data | 726 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | San Antonio | 063027023 | Health Station | 1 | 739225.36 | 615822.5 | 123402.86 | 615822.5 | 3rd Tranche | 424673.84 | 1040496.34 | 615822.5 | 424673.84 | 100% | 100% | 344.1% | 140.8% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-16 | 2006-07-31 | no data | 257 | 114 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | San Diego | 063027024 | Electrification | 1 | 1359234.53 | 954300 | 404934.53 | 954300 | 3rd Tranche | 406089.53 | 1363407.54 | 954300 | 409107.54 | 100% | 100.7% | 100.3% | 100.3% | 100% | 2005-08-22 | 2005-09-20 | 2005-12-26 | 2006-06-30 | no data | 186 | 130 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | San Jose Moto | 063027025 | Health Station | 1 | 457162.39 | 402822.39 | 54340 | 402822.39 | 3rd Tranche | 62660 | 465482.39 | 402822.39 | 62660 | 100% | 100% | 115.3% | 101.8% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-22 | 2005-05-31 | no data | 313 | 190 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Sincua | 063027027 | Road Upgrading | 1 | 2305157 | 2050000 | 255157 | 1640000 | 1st Tranche | 149047 | 1789047 | 1640000 | 149047 | 100% | 100% | 58.41% | 77.61% | 100% | 2006-08-02 | 2006-08-23 | 2007-12-01 | 2009-08-31 | no data | 639 | 143 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Poblacion SE Zone | 063027021 | Travelling Ricemill | 1 | 470700 | 306612.4 | 164087.6 | 306612.4 | 100% Tranche | 164087.6 | 383200 | 306612.4 | 76587.6 | 100% | 46.67% | 100% | 81.41% | 100% | 2006-08-02 | 2006-08-23 | 2006-10-27 | 2007-01-31 | no data | 96 | 523 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Tabunan | 063027028 | Two Unit Solar drier w/ bodega | 1 | 724621.99 | 587709.13 | 136912.86 | 587709.13 | 3rd Tranche | 161610.74 | 749319.87 | 587709.13 | 161610.74 | 100% | 100% | 118% | 103.4% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-17 | 2006-07-31 | no data | 256 | 150 |  | 1
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Tabunan | 063027028 | Farm Facilities | 1 | 499140 | 433200 | 65940 | 433200 | 100% Tranche | 65940 | 496200 | 433200 | 63000 | 100% | 95.54% | 100% | 99.41% | 100% | 2006-08-02 | 2006-08-23 | 2006-11-10 | 2007-01-31 | no data | 82 | 150 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Tugas | 063027029 | Solar Dryer | 1 | 341720.38 | 233708.92 | 108011.46 | 233708.92 | 3rd Tranche | 155332.92 | 389086.72 | 233708.92 | 155377.8 | 100% | 100% | 143.8% | 113.9% | 100% | 2005-08-22 | 2005-09-20 | 2005-11-08 | 2006-05-31 | no data | 204 | 129 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Velasco | 063027030 | Mechanical Drier | 1 | 542082.96 | 492482.96 | 49600 | 492482.96 | 3rd Tranche | 224031 | 716513.96 | 492482.96 | 224031 | 100% | 100% | 451.7% | 132.2% | 100% | 2004-02-05 | 2004-04-27 | 2004-07-12 | 2005-05-31 | no data | 323 | 191 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Lemery | 063027 | Yawyawan | 063027031 | Barangay Road construction | 1 | 1187369.57 | 324372.03 | 862997.54 | 324372.03 | 3rd Tranche | 1067752.96 | 1392124.99 | 324372.03 | 1067752.96 | 100% | 100% | 123.7% | 117.2% | 100% | 2004-02-05 | 2004-04-27 | 2004-08-21 | 2005-06-30 | no data | 313 | 88 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Abilay | 063029002 | Road Construction | 1 | 3712706.94 | 2261447.1 | 1451259.84 | 2261447.1 | 3rd Tranche | 1222313 | 3483760.1 | 2261447.1 | 1222313 | 100% | 100% | 84.22% | 93.83% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-07 | 2006-10-31 | 2006-12-05 | 328 | 162 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Amerang | 063029005 | Barangay Road Rehabilitation | 1 | 665229.8 | 409786.28 | 255443.52 | 409786.28 | 3rd Tranche | 304797.27 | 714583.55 | 409786.28 | 304797.27 | 100% | 100% | 119.3% | 107.4% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-13 | 2005-02-28 | 2005-06-10 | 230 | 56 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Amerang | 063029005 | Const. of 1 Unit 2 CL Sch. Bldg | 1 | 1142884.56 | 1012226 | 130658.56 | 906527.41 |  | 132017.36 | 1038544.77 | 906527.41 | 132017.36 | 100% | 100% | 101% | 90.87% | 100% | 2009-02-19 | no data | 2009-05-11 | 2009-08-31 | no data | 112 | 65 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Bagacay East | 063029006 | Drainage System | 1 | 601536 | 560233 | 41303 | 560233 | 3rd Tranche | 94591 | 654824 | 560233 | 94591 | 100% | 100% | 229% | 108.9% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-24 | 2005-01-13 | 2005-01-31 | 203 | 74 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Bagacay West | 063029007 | Drainage System | 1 | 893114 | 833948 | 59166 | 833948 | 3rd Tranche | 66461 | 900409 | 833948 | 66461 | 100% | 100% | 112.3% | 100.8% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-23 | 2005-01-13 | 2005-01-31 | 204 | 144 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Bolo | 063029009 | School Building | 1 | 680967.5 | 544279.5 | 136688 | 544279.5 | 3rd Tranche | 137038 | 681317.5 | 544279.5 | 137038 | 100% | 100% | 100.3% | 100.1% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-21 | 2005-02-28 | 2005-06-10 | 252 | 131 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Bolo | 063029009 | Road Concreting w/ Grouter Riprap and Side Ditches | 1 | 1479711 | 1405936 | 73775 | 1265342 | 1st | 48338 | 1313680 | 1265342 | 48338 | 100% | 100% | 65.52% | 88.78% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 168 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Bug-ot | 063029008 | Road Upgrading with Spot Concreting | 1 | 2340675.41 | 2217685.1 | 122990.31 | 2217685.1 | 3rd Tranche | 173203.75 | 2390888.85 | 2217685.1 | 173203.75 | 100% | 100% | 140.8% | 102.1% | 100% | 2005-07-22 | 2005-08-05 | 2005-11-28 | 2006-10-31 | 2006-11-23 | 337 | 42 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Bulay | 063029010 | Water System Level II | 1 | 1828746.46 | 1556561.85 | 272184.61 | 1556561.85 | 3rd Tranche | 276433.75 | 1832995.6 | 1556561.85 | 276433.75 | 100% | 100% | 101.6% | 100.2% | 100% | 2005-07-22 | 2005-08-05 | 2005-11-23 | 2006-10-19 | 2006-10-26 | 330 | 66 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Buntalan | 063029011 | Water Supply System | 1 | 469033.36 | 410693.76 | 58339.6 | 410693.76 | 3rd Tranche | 92019.6 | 502713.36 | 410693.76 | 92019.6 | 100% | 100% | 157.7% | 107.2% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-24 | 2005-01-13 | 2005-06-10 | 203 | 122 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Buntalan | 063029011 | Multi-Purpose Vehicle | 1 | 213550 | 179750 | 33800 | 179750 | 3rd Tranche | 35000 | 214750 | 179750 | 35000 | 100% | 100% | 103.6% | 100.6% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-12 | 2006-02-28 | 2006-04-25 | 78 | 122 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Burak | 063029012 | Barangay Road Rehabilitation | 1 | 620281 | 539501 | 80780 | 539401 | 3rd Tranche | 80775 | 620176 | 539401 | 80775 | 100% | 100% | 99.99% | 99.98% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-05 | 2005-02-23 | 2005-06-10 | 233 | 106 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cabangcalan | 063029013 | Barangay Road Rehabilitation | 1 | 480316 | 404070 | 76246 | 404070 | 3rd Tranche | 67686 | 471756 | 404070 | 67686 | 100% | 100% | 88.77% | 98.22% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-24 | 2005-02-28 | 2005-06-10 | 249 | 138 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cabangcalan | 063029013 | 2 Classroom School Building | 1 | 952193.05 | 769372.82 | 182820.23 | 727669.86 | 2nd Tranche | 80869.34 | 808539.2 | 727669.86 | 80869.34 | 100% | 100% | 44.23% | 84.91% | 100% | 2006-06-27 | 2006-07-18 | 2007-02-27 | 2008-09-01 | no data | 552 | 126 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cabatac | 063029014 | Road Upgrading | 1 | 1012398.3 | 776890.13 | 235508.17 | 774237.82 | 1st Tranche | 112496.08 | 886733.9 | 774237.82 | 112496.08 | 100% | 100% | 47.77% | 87.59% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-22 | 2008-03-01 | no data | 465 | 81 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cabatac | 063029014 | Const. of Day Care Center | 1 | 646307 | 583182 | 63125 | 524863.8 |  | 63301.15 | 588164.95 | 524863.8 | 63301.15 | 100% | 100% | 100.3% | 91% | 100% | 2009-02-19 | no data | 2009-04-28 | 2009-07-31 | no data | 94 | 148 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Caigon | 063029015 | Barangay Road Rehabilitation | 1 | 317322 | 296644 | 20678 | 296644 | 3rd Tranche | 50548.75 | 347192.75 | 296644 | 50548.75 | 100% | 100% | 244.5% | 109.4% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-05 | 2005-01-20 | 2005-06-10 | 199 | 109 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Caigon | 063029015 | Road Concreting with Grouted Riprap and Side Ditches | 1 | 1298636 | 1125611 | 173025 | 1013049.9 |  | 158692.1 | 1171742 | 1013049.9 | 158692.1 | 100% | 100% | 91.72% | 90.23% | 100% | 2009-02-19 | no data | 2009-04-29 | 2009-07-31 | no data | 93 | 107 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cananghan | 063029016 | Box Culvert | 1 | 198751.72 | 164307.52 | 34444.2 | 164307.52 | 3rd Tranche | 52903.02 | 217210.54 | 164307.52 | 52903.02 | 100% | 100% | 153.6% | 109.3% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-24 | 2005-01-29 | 2005-06-10 | 219 | 88 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cananghan | 063029016 | Road Upgrading with Spot Concreting | 1 | 1809893.64 | 1466957.09 | 342936.55 | 1400166.81 | 2nd Tranche | 97673.43 | 1497840.24 | 1400166.81 | 97673.43 | 100% | 100% | 28.48% | 82.76% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-22 | 2008-04-01 | no data | 496 | 87 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Cananghan | 063029016 | Construction of Day Care Center | 1 | 646307 | 583182 | 63125 | 524863.8 | 1st | 74022.95 | 598886.75 | 524863.8 | 74022.95 | 100% | 100% | 117.3% | 92.66% | 100% | 2009-02-19 | no data | 2009-05-11 | 2009-08-31 | no data | 112 | 70 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Canawili | 063029017 | Barangay Road Rehabilitation | 1 | 387636.9 | 183351.42 | 204285.48 | 183351.42 | 3rd Tranche | 185527.91 | 368879.33 | 183351.42 | 185527.91 | 100% | 100% | 90.82% | 95.16% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-13 | 2005-03-25 | 2005-06-10 | 255 | 46 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Dagami | 063029020 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1303444 | 1240619 | 62825 | 1116557.1 | 1st | 51987.9 | 1168545 | 1116557.1 | 51987.9 | 100% | 100% | 82.75% | 89.65% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 181 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Daja | 063029021 | Water Supply System | 1 | 1069170.7 | 984996.7 | 84174 | 984996.7 | 3rd Tranche | 137213.5 | 1122210.2 | 984996.7 | 137213.5 | 100% | 100% | 163% | 105% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-24 | 2005-03-31 | 2005-06-10 | 280 | 190 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Daja | 063029021 | Day Care Center | 1 | 675050 | 543588.33 | 131461.67 | 503870.66 | 2nd Tranche | 51529.08 | 555399.74 | 503870.66 | 51529.08 | 100% | 100% | 39.2% | 82.28% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-20 | 2007-11-01 | no data | 346 | 45 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Del-Car (Delgado-Cartagena) | 063029023 | Road Upgrading | 1 | 905670 | 807733.09 | 97936.91 | 807733.09 | Last Tranche | 56789.27 | 864522.36 | 807733.09 | 56789.27 | 100% | 100% | 57.99% | 95.46% | 100% | 2006-06-27 | 2006-07-18 | 2007-02-27 | 2007-06-09 | 2007-08-31 | 102 | 48 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Inabasan | 063029025 | Day Care Center | 1 | 664200.08 | 499164.17 | 165035.91 | 494656.88 | 2nd Tranche | 99532.53 | 594189.41 | 494656.88 | 99532.53 | 100% | 100% | 60.31% | 89.46% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-08 | 2007-11-09 | no data | 366 | 88 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Inabasan | 063029025 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1153275 | 990700 | 162575 | 891630 | 1st | 146792.6 | 1038422.6 | 891630 | 146792.6 | 100% | 100% | 90.29% | 90.04% | 100% | 2009-02-19 | no data | 2009-05-14 | 2009-08-31 | no data | 109 | 176 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Layog | 063029026 | Day Care Center | 1 | 666347.89 | 558517.92 | 107829.97 | 530426.47 | 2nd Tranche | 84092.53 | 614519 | 530426.47 | 84092.53 | 100% | 100% | 77.99% | 92.22% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-22 | 2008-04-01 | no data | 496 | 226 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Layog | 063029026 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1479711 | 1405936 | 73775 | 1265342.4 |  | 64232.5 | 1329574.9 | 1265342.4 | 64232.5 | 100% | 100% | 87.07% | 89.85% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 224 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Linab | 063029029 | Road Upgrading with Spot Concreting | 1 | 1198267.99 | 1063306.73 | 134961.26 | 1039384.36 | 1st Tranche | 87253.13 | 1126637.49 | 1039384.36 | 87253.13 | 100% | 100% | 64.65% | 94.02% | 100% | 2006-06-27 | 2006-07-18 | 2007-02-27 | 2008-09-01 | no data | 552 | 85 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Liñagan Calsada | 063029027 | Creek Wall Protection | 1 | 896393 | 818078 | 78315 | 736270.2 | 1st | 65200 | 801470.2 | 736270.2 | 65200 | 100% | 100% | 83.25% | 89.41% | 100% | 2009-02-19 | no data | 2009-05-15 | 2009-07-25 | no data | 71 | 58 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Liñagan Calsada | 063029027 | Road Upgrading with Spot Concreting | 1 | 1132577.53 | 1050486.17 | 82091.36 | 1050486.17 | 3rd Tranche | 78151.29 | 1128637.46 | 1050486.17 | 78151.29 | 100% | 100% | 95.2% | 99.65% | 100% | 2005-07-22 | 2005-08-05 | 2005-11-21 | 2006-08-31 | 2006-10-13 | 283 | 54 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Liñagan Tacas | 063029028 | Barangay Road Rehabilitation | 1 | 431798.5 | 220862.48 | 210936.02 | 220862.48 | 3rd Tranche | 217007 | 437869.48 | 220862.48 | 217007 | 100% | 100% | 102.9% | 101.4% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-25 | 2005-02-24 | 2005-06-10 | 244 | 60 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Liñagan Tacas | 063029028 | 2 Classroom School Building | 1 | 999996.78 | 804806.39 | 195190.39 | 788071.25 | 2nd Tranche | 118271 | 906342.25 | 788071.25 | 118271 | 100% | 100% | 60.59% | 90.63% | 100% | 2006-06-27 | 2006-07-18 | 2007-02-22 | 2008-04-01 | no data | 404 | 33 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Magsaysay | 063029031 | Water Supply System | 1 | 804350.92 | 742085.92 | 62265 | 742085.92 | 3rd Tranche | 99063 | 841148.92 | 742085.92 | 99063 | 100% | 100% | 159.1% | 104.6% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-02 | 2005-05-31 | 2005-06-10 | 333 | 152 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Magsaysay | 063029031 | Health Station | 1 | 663381.77 | 532888.93 | 130492.84 | 474992.54 | 1st Tranche | 86893.13 | 560386.61 | 474992.54 | 85394.07 | 100% | 98.27% | 66.59% | 84.47% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-03 | 2008-04-01 | no data | 515 | 156 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Magsaysay | 063029031 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1298636 | 1125611 | 173025 | 1013049.9 | 1st | 158485.3 | 1171535.2 | 1013049.9 | 158485.3 | 100% | 100% | 91.6% | 90.21% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 155 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Mandog | 063029032 | Solid Waste Management Facilities | 1 | 590475 | 516369.6 | 74105.4 | 516369.6 | 3rd Tranche | 77892.9 | 594262.5 | 516369.6 | 77892.9 | 100% | 100% | 105.1% | 100.6% | 100% | 2005-07-22 | 2005-08-05 | 2006-01-24 | 2006-10-31 | 2006-11-17 | 280 | 179 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Miapa | 063029033 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1298636 | 1125611 | 173025 | 1013049.9 | 1st | 161609.55 | 1174659.45 | 1013049.9 | 161609.55 | 100% | 100% | 93.4% | 90.45% | 100% | 2009-02-19 | no data | 2009-05-04 | 2009-07-31 | no data | 88 | 42 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Nagba | 063029034 | Road Upgrading | 1 | 1532675.27 | 1258000.04 | 274675.23 | 1258000.04 | 2nd Tranche | 391620.18 | 1649620.22 | 1258000.04 | 391620.18 | 100% | 100% | 142.6% | 107.6% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-06 | 2008-04-01 | no data | 512 | 200 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Nasaka | 063029035 | Barangay Road Rehabilitation | 1 | 803717.4 | 726333.4 | 77384 | 726333.4 | 3rd Tranche | 1211273.03 | 1937606.43 | 726333.4 | 1211273.03 | 100% | 100% | 1565% | 241.1% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-12 | 2005-01-28 | 2005-06-10 | 200 | 132 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Nasaka | 063029035 | Water System Level II | 1 | 1564570.34 | 1427559.15 | 137011.19 | 1427559.15 | 3rd Tranche | 199765 | 1627324.15 | 1427559.15 | 199765 | 100% | 100% | 145.8% | 104% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-12 | 2006-08-31 | 2006-09-15 | 262 | 132 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Nasaka | 063029035 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 561363 | 445238 | 116125 | 400714 | 1st | 110125 | 510839 | 400714 | 110125 | 100% | 100% | 94.83% | 91% | 100% | 2009-02-19 | no data | 2009-03-03 | 2009-08-31 | no data | 181 | 142 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Naslo-Bucao | 063029036 | River Wall Protection | 1 | 1966192 | 1017327 | 948865 | 912594.3 |  | 982041.3 | 1894635.6 | 912594.3 | 982041.3 | 100% | 100% | 103.5% | 96.36% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 320 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Nasuli | 063029037 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1439643 | 1365868 | 73775 | 1229281.2 | 1st | 63807.5 | 1293088.7 | 1229281.2 | 63807.5 | 100% | 100% | 86.49% | 89.82% | 100% | 2009-02-19 | no data | 2009-05-11 | 2009-08-31 | no data | 112 | 95 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Panalian | 063029038 | Barangay Road Rehabilitation | 1 | 795207 | 740371 | 54836 | 740371 | 3rd Tranche | 72251 | 812622 | 740371 | 72251 | 100% | 100% | 131.8% | 102.2% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-15 | 2005-03-25 | 2005-06-10 | 253 | 109 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Panalian | 063029038 | Health Station | 1 | 839708.75 | 755953.75 | 83755 | 755953.75 | 3rd Tranche | 92495 | 848448.75 | 755953.75 | 92495 | 100% | 100% | 110.4% | 101% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-07 | 2006-10-31 | 2006-11-24 | 328 | 109 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Piandaan East | 063029039 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1439643 | 1365868 | 73775 | 1229281.2 | 1st | 60470 | 1289751.2 | 1229281.2 | 60470 | 100% | 100% | 81.97% | 89.59% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 47 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Piandaan West | 063029040 | Barangay Health Station | 1 | 446142.2 | 376692.2 | 69450 | 376692.2 | 3rd Tranche | 76500 | 453192.2 | 376692.2 | 76500 | 100% | 100% | 110.2% | 101.6% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-09 | 2005-02-24 | 2005-06-10 | 230 | 68 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Piandaan West | 063029040 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1439643 | 1365868 | 73775 | 1229281.2 | 1st | 63557.5 | 1292838.7 | 1229281.2 | 63557.5 | 100% | 100% | 86.15% | 89.8% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 65 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Pispis | 063029041 | Barangay Road Rehabilitation | 1 | 279956 | 184193 | 95763 | 184193 | 3rd Tranche | 73093 | 257286 | 184193 | 73093 | 100% | 100% | 76.33% | 91.9% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-30 | 2005-05-26 | 2005-06-10 | 330 | 108 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Pispis | 063029041 | Water System Level II | 1 | 1520572.88 | 1341514.75 | 179058.13 | 1073211.8 | 1st Tranche | 70169.5 | 1120121.1 | 1073211.8 | 46909.3 | 100% | 66.85% | 39.19% | 73.66% | 100% | 2006-06-27 | 2006-07-18 | 2007-02-26 | 2007-06-15 | no data | 109 | 74 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Pispis | 063029041 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1289636 | 1125611 | 164025 | 1013049.9 | 1st | 173192.82 | 1186242.72 | 1013049.9 | 173192.82 | 100% | 100% | 105.6% | 91.98% | 100% | 2009-02-19 | no data | 2009-05-22 | 2009-07-31 | no data | 70 | 134 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Punong | 063029042 | Barangay Health Station | 1 | 460177.21 | 410317.21 | 49860 | 410317.21 | 3rd Tranche | 51060 | 461377.21 | 410317.21 | 51060 | 100% | 100% | 102.4% | 100.3% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-08 | 2005-02-24 | 2005-06-10 | 231 | 44 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Sinubsuban | 063029044 | Road Opening | 1 | 1789732.25 | 1481613.5 | 308118.75 | 1481613.5 | 3rd Tranche | 330672.5 | 1812286 | 1481613.5 | 330672.5 | 100% | 100% | 107.3% | 101.3% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-25 | 2005-02-28 | 2005-06-10 | 248 | 85 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Sinubsuban | 063029044 | Multi-Purpose Emergency Vehicle | 1 | 213550 | 202550 | 11000 | 202550 | 3rd Tranche | 13732.5 | 216282.5 | 202550 | 13732.5 | 100% | 100% | 124.8% | 101.3% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-19 | 2006-04-28 | 2006-07-28 | 130 | 85 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Siwalo | 063029045 | Water Supply System | 1 | 1309303.14 | 1197218.14 | 112085 | 1197218.14 | 3rd Tranche | 167895.64 | 1365113.78 | 1197218.14 | 167895.64 | 100% | 100% | 149.8% | 104.3% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-15 | 2005-03-31 | 2005-06-10 | 289 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Siwalo | 063029045 | Two Classrom School Building | 1 | 954853.66 | 743980.33 | 210873.33 | 743980.33 | 3rd Tranche | 237902.53 | 981882.86 | 743980.33 | 237902.53 | 100% | 100% | 112.8% | 102.8% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-07 | 2006-09-29 | 2006-11-10 | 296 | 154 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Siwalo | 063029045 | Construction of Day Care Center | 1 | 646307 | 583182 | 63125 | 524863.8 | 1st | 69183.94 | 594047.74 | 524863.8 | 69183.94 | 100% | 100% | 109.6% | 91.91% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 157 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Sta. Rita | 063029046 | Road Upgrading with Spot Concreting | 1 | 1120404.1 | 991977.63 | 128426.47 | 985028.5 | 2nd Tranche | 60197 | 1045225.5 | 985028.5 | 60197 | 100% | 100% | 46.87% | 93.29% | 100% | 2006-06-27 | 2006-07-18 | 2007-02-16 | 2008-09-01 | no data | 563 | 76 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Subog | 063029047 | Road Construction | 1 | 2983498.82 | 2421641.12 | 561857.7 | 2421641.12 | 3rd Tranche | 521333.75 | 2942974.87 | 2421641.12 | 521333.75 | 100% | 100% | 92.79% | 98.64% | 100% | 2005-07-22 | 2005-08-05 | 2005-11-28 | 2006-10-31 | 2006-11-27 | 337 | 84 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tigbauan | 063029050 | Barangay Road Rehabilitation | 1 | 1027170.8 | 972150.8 | 55020 | 972150.8 | 3rd Tranche | 55875 | 1028025.8 | 972150.8 | 55875 | 100% | 100% | 101.6% | 100.1% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-09 | 2005-02-28 | 2005-06-10 | 234 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tigbauan | 063029050 | Irrigation System | 1 | 2033734.36 | 1502397.85 | 531336.51 | 1502397.85 | 3rd Tranche | 542535 | 2044932.85 | 1502397.85 | 542535 | 100% | 100% | 102.1% | 100.6% | 100% | 2005-07-22 | 2005-08-05 | 2005-12-05 | 2006-10-31 | 2006-11-22 | 330 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tigbauan | 063029050 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1439643 | 1365868 | 73775 | 1229281.2 | 1st | 63707.5 | 1292988.7 | 1229281.2 | 63707.5 | 100% | 100% | 86.35% | 89.81% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 180 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Trangka | 063029051 | Road Opening | 1 | 3003671.81 | 1995830.17 | 1007841.64 | 1995830.17 | 3rd Tranche | 637794.65 | 2633624.82 | 1995830.17 | 637794.65 | 100% | 100% | 63.28% | 87.68% | 100% | 2004-01-26 | 2004-04-22 | 2004-07-14 | 2006-02-23 | 2007-02-28 | 589 | 128 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tubang | 063029052 | Health Station | 1 | 673530 | 517800.37 | 155729.63 | 517800.37 | Last Tranche | 114081.66 | 631882.03 | 517800.37 | 114081.66 | 100% | 100% | 73.26% | 93.82% | 100% | 2006-06-27 | 2006-07-18 | 2006-10-31 | 2007-10-01 | 2007-10-03 | 335 | 184 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tubang | 063029052 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1298636 | 1125611 | 173025 | 1013049.9 | 1st | 164007.5 | 1177057.4 | 1013049.9 | 164007.5 | 100% | 100% | 94.79% | 90.64% | 100% | 2009-02-19 | no data | 2009-05-14 | 2009-07-31 | no data | 78 | 211 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tulahong | 063029052 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1431163 | 1331388 | 99775 | 1198249.2 | 1st | 66850.7 | 1265099.9 | 1198249.2 | 66850.7 | 100% | 100% | 67% | 88.4% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-07-31 | no data | 74 | 67 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tulahong | 063029052 | Water Supply System | 1 | 703705 | 620797 | 82908 | 620797 | 3rd Tranche | 100333 | 721130 | 620797 | 100333 | 100% | 100% | 121% | 102.5% | 100% | 2004-01-26 | 2004-04-22 | 2004-06-09 | 2005-04-04 | 2005-06-10 | 299 | 71 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tulahong | 063029052 | Road Concreting | 1 | 1020200.76 | 900823.64 | 119377.12 | 900823.64 | Last Tranche | 84788.99 | 985612.63 | 900823.64 | 84788.99 | 100% | 100% | 71.03% | 96.61% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-16 | 2007-08-31 | 2007-09-12 | 288 | 73 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tuy-an East | 063029054 | Health Station | 1 | 673531.73 | 532802.1 | 140729.63 | 504810 | 2nd Tranche | 60800 | 565610 | 504810 | 60800 | 100% | 100% | 43.2% | 83.98% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-23 | 2008-04-01 | no data | 495 | 139 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tuy-an East | 063029054 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1298636 | 1125611 | 173025 | 1013049.9 | 1st | 166686.51 | 1179736.41 | 1013049.9 | 166686.51 | 100% | 100% | 96.34% | 90.84% | 100% | 2009-02-19 | no data | 2009-05-04 | 2009-08-31 | no data | 119 | 137 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tuy-an West | 063029055 | Road Construction with 2 RCBC | 1 | 1060957.27 | 872020.24 | 188937.03 | 697616.19 | 1st Tranche | 55353.86 | 752970.05 | 697616.19 | 55353.86 | 100% | 100% | 29.3% | 70.97% | 100% | 2006-06-27 | 2006-07-18 | 2007-03-16 | 2009-08-31 | n/a | 899 | 100 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Tuy-an West | 063029055 | Road Concreting w/ Grouted Riprap and Side Ditches | 1 | 1439643 | 1365868 | 73775 | 1229281 |  | 46662.55 | 1275943.55 | 1229281 | 46662.55 | 100% | 100% | 63.25% | 88.63% | 100% | 2009-02-19 | no data | 2009-05-18 | 2009-08-31 | no data | 105 | 104 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | Maasin | 063029 | Ubian | 063029056 | Road Upgrading with Spot Concreting | 1 | 868058.02 | 553178.86 | 314879.16 | 521220.4 | 1st Tranche | 269174.32 | 790394.72 | 521220.4 | 269174.32 | 100% | 100% | 85.48% | 91.05% | 100% | 2006-06-27 | 2006-07-18 | 2006-11-22 | 2008-09-01 | no data | 649 | 127 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Agdaliran | 063038001 | Road Concreting | 1 | 394172.8 | 312922.8 | 81250 | 312922.8 | 3rd Tranche | 103650 | 416572.8 | 312922.8 | 103650 | 100% | 100% | 127.6% | 105.7% | 100% | 2004-02-03 | 2004-04-26 | 2004-07-03 | 2005-01-05 | 2005-02-25 | 186 | 189 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Agdaliran | 063038001 | Day Care Center | 1 | 748610 | 624157 | 124453 | 624157 | 3rd Tranche | 140737.5 | 764894.5 | 624157 | 140737.5 | 100% | 100% | 113.1% | 102.2% | 100% | 2005-08-11 | 2005-09-05 | 2005-10-20 | 2006-06-30 | no data | 253 | 198 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Agdaliran | 063038001 | Drainage System with Box Culvert | 1 | 1262837.56 | 946900 | 315937.56 | 905856.53 | 1st Tranche | 321983.57 | 1227840.1 | 905856.53 | 321983.57 | 100% | 100% | 101.9% | 97.23% | 100% | 2006-07-31 | 2006-08-23 | 2007-06-22 | 2008-03-01 | no data | 253 | 199 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Agdaliran | 063038001 | Road Improvement of Farm to Market Road w/ Road Concreting | 1 | 893210.35 | 746410.35 | 146800 | 671769.31 | 1st | 199260 | 871029.31 | 671769.31 | 199260 | 100% | 100% | 135.7% | 97.52% | 100% | 2009-02-11 | no data | 2009-05-26 | 2009-08-18 | no data | 84 | 201 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Amayong | 063038002 | Day Care Center | 1 | 483750.03 | 433025.98 | 50724.05 | 433025.98 | 3rd Tranche | 102994.05 | 536020.03 | 433025.98 | 102994.05 | 100% | 100% | 203% | 110.8% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-23 | 2005-01-10 | 2005-02-25 | 201 | 86 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Amayong | 063038002 | Water System Level II | 1 | 595121.75 | 516249.75 | 78872 | 490463 | 2nd Tranche | 83633.8 | 574096.8 | 490463 | 83633.8 | 100% | 100% | 106% | 96.47% | 100% | 2006-07-31 | 2006-08-23 | 2007-03-27 | 2008-03-01 | no data | 340 | 110 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Amayong | 063038002 | Road Improvement of Farm to Market Road w/ Road Concreting | 1 | 721740.45 | 590430.45 | 131310 | 531387.41 | 1st | 143620 | 675007.41 | 531387.41 | 143620 | 100% | 100% | 109.4% | 93.52% | 100% | 2009-02-11 | no data | 2009-05-28 | 2009-08-15 | no data | 79 | 117 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Bagacay | 063038003 | Road Concreting | 1 | 2803495 | 2198200 | 605295 | 2198200 | 3rd Tranche | 627626.25 | 2825826.25 | 2198200 | 627626.25 | 100% | 100% | 103.7% | 100.8% | 100% | 2005-08-11 | 2005-09-05 | 2005-10-24 | 2006-06-30 | no data | 249 | 231 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Bagacay | 063038003 | 1 Unit Solar Dryer | 1 | 516329.5 | 336500 | 179829.5 | 319969.5 | 2nd Tranche | 180437.6 | 500407.1 | 319969.5 | 180437.6 | 100% | 100% | 100.3% | 96.92% | 100% | 2006-07-31 | 2006-08-23 | 2006-12-20 | 2008-03-01 | no data | 437 | 397 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Batuan | 063038004 | Post Harvest Facilities | 1 | 596010.11 | 503664.08 | 92346.03 | 503664.08 | 3rd Tranche | 145896.03 | 649560.11 | 503664.08 | 145896.03 | 100% | 100% | 158% | 109% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-07 | 2005-03-15 | 2005-06-18 | 281 | 100 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Bondulan | 063038005 | Day Care Center | 1 | 483752.032 | 443337.982 | 40414.05 | 443337.982 | 3rd Tranche | 90534.05 | 533872.03 | 443337.98 | 90534.05 | 100% | 100% | 224% | 110.4% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-10 | 2004-11-30 | 2005-02-25 | 173 | 260 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Bondulan | 063038005 | Construction of Drainage Canal | 1 | 810884.95 | 646719.95 | 164165 | 582047.95 | 1st | 154925 | 736972.95 | 582047.95 | 154925 | 100% | 100% | 94.37% | 90.89% | 100% | 2009-02-11 | no data | 2009-04-01 | 2009-06-30 | no data | 90 | 304 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Boroñgan | 063038006 | Barangay Health Station | 1 | 560055.14 | 504323.92 | 55731.22 | 504323.92 | 3rd Tranche | 96031.22 | 600355.14 | 504323.92 | 96031.22 | 100% | 100% | 172.3% | 107.2% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-20 | 2005-01-08 | 2005-02-25 | 202 | 179 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Borongon | 063038006 | Road Improvement of Farm to Market Road w/ Road Concreting | 1 | 757267.35 | 589852.35 | 167415 | 530867.11 | 1st | 180250.25 | 711117.36 | 530867.11 | 180250.25 | 100% | 100% | 107.7% | 93.91% | 100% | 2009-02-11 | no data | 2009-05-30 | 2009-08-31 | no data | 93 | 159 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Canas | 063038007 | Water Supply System level II | 1 | 426418.04 | 362205.54 | 64212.5 | 362205.536 | 3rd Tranche | 99398.5 | 461604.04 | 362205.54 | 99398.5 | 100% | 100% | 154.8% | 108.3% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-21 | 2005-01-05 | 2005-02-25 | 198 | 177 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Canas | 063038007 | Dry and Wet Market | 1 | 1404835 | 987343 | 417492 | 987343 | 3rd Tranche | 302665.15 | 1290008.15 | 987343 | 302665.15 | 100% | 100% | 72.5% | 91.83% | 100% | 2005-08-11 | 2005-09-05 | 2005-10-13 | 2006-06-30 | no data | 260 | 177 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Canas | 063038007 | Concreting of Brgy. Road | 1 | 601984.55 | 473399.55 | 128585 | 426059.59 | 1st | 133650 | 559709.59 | 426059.59 | 133650 | 100% | 100% | 103.9% | 92.98% | 100% | 2009-02-11 | no data | 2009-06-01 | 2009-08-31 | no data | 91 | 232 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Capinang | 063038008 | Post Harvest Facilities | 1 | 969366.69 | 710500 | 258866.69 | 710500 | 3rd Tranche | 261717.22 | 972217.22 | 710500 | 261717.22 | 100% | 100% | 101.1% | 100.3% | 100% | 2005-08-11 | 2005-09-05 | 2005-11-13 | 2006-06-30 | no data | 229 | 164 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Capinang | 063038008 | Construction of Day Care Center | 1 | 677653.86 | 564478.86 | 113175 | 508030.97 | 1st | 102025 | 610055.97 | 508030.97 | 102025 | 100% | 100% | 90.15% | 90.02% | 100% | 2009-02-11 | no data | 2009-04-17 | 2009-06-30 | no data | 74 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Cubay | 063038009 | Road Concreting | 1 | 606018.85 | 462000.65 | 144018.2 | 462000.65 | 3rd Tranche | 178743.2 | 640743.85 | 462000.65 | 178743.2 | 100% | 100% | 124.1% | 105.7% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-19 | 2005-01-06 | 2005-02-25 | 201 | 225 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Cubay | 063038009 | Day Care Center | 1 | 511886.66 | 362000 | 149886.66 | 325800 | 2nd Tranche | 146136.66 | 471936.66 | 325800 | 146136.66 | 100% | 100% | 97.5% | 92.2% | 100% | 2006-07-31 | 2006-08-23 | 2006-11-20 | 2008-01-01 | no data | 407 | 225 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Cubay | 063038009 | Purchase of 1 Unit Travelling Rice Mill and Construction of Garage | 1 | 834124.97 | 627534.47 | 206590.5 | 564781.03 | 1st | 213215.5 | 777996.53 | 564781.03 | 213215.5 | 100% | 100% | 103.2% | 93.27% | 100% | 2009-02-11 | no data | 2009-05-11 | 2009-06-30 | no data | 50 | 238 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Cudionan | 063038010 | 2 Units Solar Dryer | 1 | 1406488.9 | 1169138.14 | 237350.76 | 1052224.33 | 2nd Tranche | 220494.46 | 1272718.79 | 1052224.33 | 220494.46 | 100% | 100% | 92.9% | 90.49% | 100% | 2006-07-31 | 2006-08-23 | 2006-12-20 | 2008-01-01 | no data | 377 | 278 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Dugman | 063038011 | Day Care Center | 1 | 495715.03 | 439295.98 | 56419.05 | 439295.98 | 3rd Tranche | 102001.55 | 541297.53 | 439295.98 | 102001.55 | 100% | 100% | 180.8% | 109.2% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-16 | 2005-01-07 | 2005-02-05 | 205 | 209 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Dugman | 063038011 | Post Harvest Facilities | 1 | 1110305.93 | 749400 | 360905.93 | 749400 | 3rd Tranche | 370737.5 | 1120137.5 | 749400 | 370737.5 | 100% | 100% | 102.7% | 100.9% | 100% | 2005-08-11 | 2005-09-05 | 2005-10-27 | 2006-06-30 | no data | 246 | 223 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Dugman | 063038011 | 1 Classroom School Building | 1 | 551244.48 | 475600 | 75644.48 | 428040 | 2nd Tranche | 71043.5 | 499083.5 | 428040 | 71043.5 | 100% | 100% | 93.92% | 90.54% | 100% | 2006-07-31 | 2006-08-23 | 2006-11-13 | 2008-01-01 | no data | 414 | 223 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Hacienda Conchita | 063038012 | Barangay Health Station | 1 | 607905.14 | 499143.92 | 108761.22 | 499143.92 | 3rd Tranche | 150011 | 649154.92 | 499143.92 | 150011 | 100% | 100% | 137.9% | 106.8% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-07 | 2005-02-25 | 2005-02-25 | 263 | 185 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Hacienda Conchita | 063038012 | 2 Classroom School Building | 1 | 956989.44 | 811900 | 145089.44 | 811900 | 2nd Tranche | 147105 | 959005 | 811900 | 147105 | 100% | 100% | 101.4% | 100.2% | 100% | 2006-07-31 | 2006-08-23 | 2007-03-05 | 2008-03-01 | no data | 362 | 190 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Hacienda Conchita | 063038012 | Construction of 2 CL School Building | 1 | 1155216.76 | 965441.76 | 189775 | 858114.7 |  | 187700 | 1045814.7 | 858114.7 | 187700 | 100% | 100% | 98.91% | 90.53% | 100% | 2009-02-11 | no data | 2009-05-08 | 2009-08-31 | no data | 115 | 192 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Madanlog | 063038013 | Day Care Center | 1 | 487734.98 | 432148.44 | 55586.54 | 432148.44 | 3rd Tranche | 94289.4 | 526437.84 | 432148.44 | 94289.4 | 100% | 100% | 169.6% | 107.9% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-08 | 2005-01-05 | 2005-02-25 | 211 | 135 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Madanlog | 063038013 | Construction of 1 unit Solar Dryer | 1 | 589847.19 | 435897.19 | 153950 | 392307.48 | 1st | 160795 | 553102.48 | 392307.48 | 160795 | 100% | 100% | 104.4% | 93.77% | 100% | 2009-02-11 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 147 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Mandu-awak | 063038014 | Water System Level II | 1 | 535962.5 | 304212.11 | 231750.39 | 243369.68 | 1st Tranche | 210955.39 | 454325.07 | 243369.68 | 210955.39 | 100% | 100% | 91.03% | 84.77% | 100% | 2006-07-31 | 2006-08-23 | 2007-03-15 | 2008-03-01 | no data | 352 | 408 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Moto | 063038015 | Road Upgrading with Canalization | 1 | 1045650 | 696200 | 349450 | 626580 | 2nd Tranche | 332420 | 959000 | 626580 | 332420 | 100% | 100% | 95.13% | 91.71% | 100% | 2006-07-31 | 2006-08-23 | 2007-03-16 | 2008-03-01 | no data | 351 | 97 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Moto | 063038015 | Construction of Day Care Center | 1 | 677653.86 | 564478.86 | 113175 | 508030.97 | 1st | 105925 | 613955.97 | 508030.97 | 105925 | 100% | 100% | 93.59% | 90.6% | 100% | 2009-02-11 | no data | 2009-04-29 | 2009-06-30 | no data | 62 | 109 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Naborot | 063038016 | Water Supply System level II | 1 | 664463.41 | 612773.38 | 51690.03 | 612773.38 | 3rd Tranche | 123979.03 | 736752.41 | 612773.38 | 123979.03 | 100% | 100% | 239.9% | 110.9% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-15 | 2005-02-02 | 2005-02-25 | 232 | 33 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Naborot | 063038016 | Day Care Center | 1 | 691600 | 602500 | 89100 | 602500 | 3rd Tranche | 98233.75 | 700733.75 | 602500 | 98233.75 | 100% | 100% | 110.3% | 101.3% | 100% | 2005-08-11 | 2005-09-05 | 2005-10-24 | 2006-06-30 | no data | 249 | 33 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Naborot | 063038016 | Concreting of Brgy. Footpath | 1 | 688817.55 | 604242.55 | 84575 | 544638.29 |  | 90235 | 634873.29 | 544638.29 | 90235 | 100% | 100% | 106.7% | 92.17% | 100% | 2009-02-11 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 37 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Nipa | 063038017 | Road Concreting | 1 | 452834 | 431316.86 | 21517.14 | 431316.86 | 3rd Tranche | 70792.14 | 502109 | 431316.86 | 70792.14 | 100% | 100% | 329% | 110.9% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-17 | 2005-01-10 | 2005-02-25 | 207 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Nipa | 063038017 | Canal Drainage | 1 | 831925.15 | 721900 | 110025.15 | 721900 | 3rd Tranche | 131990 | 853890 | 721900 | 131990 | 100% | 100% | 120% | 102.6% | 100% | 2005-08-11 | 2005-09-05 | 2005-11-25 | 2006-06-30 | no data | 217 | 90 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Nipa | 063038017 | Road Improvement of Farm to Market Road w/ Road Concreting | 1 | 1111813.95 | 1032888.95 | 78925 | 929600.05 | 1st | 142375 | 1071975.05 | 929600.05 | 142375 | 100% | 100% | 180.4% | 96.42% | 100% | 2009-02-11 | no data | 2009-04-25 | 2009-07-31 | no data | 97 | 94 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Odiongan | 063038018 | Water Supply System level II | 1 | 768955.11 | 704956.6 | 63998.51 | 704956.6 | 3rd Tranche | 115183.5 | 820140.1 | 704956.6 | 115183.5 | 100% | 100% | 180% | 106.7% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-25 | 2005-02-23 | 2005-02-05 | 243 | 197 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Odiongan | 063038018 | Const. of Drainage Canal | 1 | 552642.7 | 382317.7 | 170325 | 344085.93 | 1st | 174050 | 518135.93 | 344085.93 | 174050 | 100% | 100% | 102.2% | 93.76% | 100% | 2009-02-11 | no data | 2009-04-20 | 2009-06-30 | no data | 71 | 208 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pangi | 063038019 | Road regravelling with concrete box culvert | 1 | 1081365.29 | 821718.95 | 259646.34 | 821718.95 | 3rd Tranche | 293369.66 | 1115088.61 | 821718.95 | 293369.66 | 100% | 100% | 113% | 103.1% | 100% | 2004-02-03 | 2004-04-26 | 2004-09-28 | 2005-06-14 | 2005-06-18 | 259 | 284 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pangi | 063038019 | Water System Level II | 1 | 726891.61 | 594400 | 132491.61 | 564960 | 2nd Tranche | 125999.98 | 690959.98 | 564960 | 125999.98 | 100% | 100% | 95.1% | 95.06% | 100% | 2006-07-31 | 2006-08-23 | 2006-11-20 | 2008-03-01 | no data | 467 | 309 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pangi | 063038019 | Road Improvement of Farm to Market Road | 1 | 830375.75 | 661960.75 | 168415 | 595765.57 |  | 191450 | 787215.57 | 595765.57 | 191450 | 100% | 100% | 113.7% | 94.8% | 100% | 2009-02-11 | no data | 2009-05-16 | 2009-08-13 | no data | 89 | 330 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pase | 063038020 | Day Care Center | 1 | 483752.032 | 443337.982 | 40414.05 | 443337.982 | 3rd Tranche | 81319.05 | 524657.03 | 443337.98 | 81319.05 | 100% | 100% | 201.2% | 108.5% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-10 | 2004-11-30 | 2005-02-25 | 173 | 179 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pase | 063038020 | Water System Level II | 1 | 1154381.94 | 955600 | 198781.94 | 860040 | 2nd Tranche | 201068.57 | 1061108.57 | 860040 | 201068.57 | 100% | 100% | 101.2% | 91.92% | 100% | 2006-07-31 | 2006-08-23 | 2006-11-23 | 2008-01-01 | no data | 404 | 166 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pase | 063038020 | Purchase of 1 Unit Travelling Mill and Construction of Garage | 1 | 834124.97 | 627534.47 | 206590.5 | 564781.03 | 1st | 138620 | 703401.03 | 564781.03 | 138620 | 100% | 100% | 67.1% | 84.33% | 100% | 2009-02-11 | no data | 2009-04-22 | 2009-06-30 | no data | 69 | 202 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | San Nicolas | 063038022 | Day Care Center | 1 | 543919.98 | 432019.98 | 111900 | 432019.98 | 3rd Tranche | 165575 | 597594.98 | 432019.98 | 165575 | 100% | 100% | 148% | 109.9% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-13 | 2005-02-25 | 2005-02-25 | 257 | 110 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | San Nicolas | 063038022 | Water System Level II | 1 | 671640 | 600200 | 71440 | 600200 | 3rd Tranche | 77678.85 | 677878.85 | 600200 | 77678.85 | 100% | 100% | 108.7% | 100.9% | 100% | 2005-08-11 | 2005-09-05 | 2005-10-19 | 2006-06-30 | no data | 254 | 110 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | San Nicolas | 063038022 | Const. of 1 Unit Solar Dryer w/ 1 unit Storage | 1 | 589847.19 | 470897.19 | 118950 | 423807.47 | 1st | 102945 | 526752.47 | 423807.47 | 102945 | 100% | 100% | 86.54% | 89.3% | 100% | 2009-02-11 | no data | 2009-04-21 | 2009-06-30 | no data | 70 | 132 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Santol | 063038024 | Post Harvest Facilities | 1 | 924170.26 | 587400 | 336770.26 | 587400 | 3rd Tranche | 343438 | 930838 | 587400 | 343438 | 100% | 100% | 102% | 100.7% | 100% | 2005-08-11 | 2005-09-05 | 2005-11-11 | 2006-06-30 | no data | 231 | 135 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Santol | 063038024 | Construction of Mini-Market | 1 | 672406.32 | 505256.32 | 167150 | 454730.69 | 1st | 163400 | 618130.69 | 454730.69 | 163400 | 100% | 100% | 97.76% | 91.93% | 100% | 2009-02-11 | no data | 2009-04-20 | 2009-06-30 | no data | 71 | 148 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Siempreviva | 063038025 | Road Improvement of Farm to Market Road w/ Road Concreting | 1 | 1026183.35 | 796408.35 | 229775 | 716767.51 | 1st | 258151.64 | 974919.15 | 716767.51 | 258151.64 | 100% | 100% | 112.3% | 95% | 100% | 2009-02-11 | no data | 2009-04-27 | 2009-07-31 | no data | 95 | 378 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Sua | 063038026 | Road Upgrading with Canalization | 1 | 413944.4 | 364200 | 49744.4 | 327780 | 2nd Tranche | 48704.5 | 376484.5 | 327780 | 48704.5 | 100% | 100% | 97.91% | 90.95% | 100% | 2006-07-31 | 2006-08-23 | 2007-03-12 | 2008-03-01 | no data | 355 | 232 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Sua | 063038026 | Road Improvement of Farm to Market Road | 1 | 463238.45 | 370488.45 | 92750 | 333439.61 | 1st | 93600 | 427039.61 | 333439.61 | 93600 | 100% | 100% | 100.9% | 92.19% | 100% | 2009-02-11 | no data | 2009-05-07 | 2009-06-30 | no data | 54 | 239 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Talo-ato | 063038027 | Day Care Center | 1 | 500400.03 | 422510.98 | 77889.05 | 422510.98 | 3rd Tranche | 133461.21 | 555972.19 | 422510.98 | 133461.21 | 100% | 100% | 171.3% | 111.1% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-22 | 2005-01-29 | 2005-02-25 | 221 | 159 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Talo-ato | 063038027 | Post Harvest Facilities | 1 | 1458224.5 | 918400 | 539824.5 | 918400 | 3rd Tranche | 515225 | 1433625 | 918400 | 515225 | 100% | 100% | 95.44% | 98.31% | 100% | 2005-08-11 | 2005-09-05 | 2005-11-05 | 2006-06-30 | no data | 237 | 159 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Talo-ato | 063038027 | Road Upgrading with Spot Concreting | 1 | 1458134.68 | 805500 | 652634.68 | 724950 | 1st Tranche | 209421.55 | 934371.55 | 724950 | 209421.55 | 100% | 100% | 32.09% | 64.08% | 100% | 2006-07-31 | 2006-08-23 | 2007-07-16 | 2008-03-01 | no data | 229 | 169 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Talo-ato | 063038027 | Concreting of Brgy. Road | 1 | 1019706.9 | 829781.9 | 189925 | 746803.71 | 1st | 198400 | 945203.71 | 746803.71 | 198400 | 100% | 100% | 104.5% | 92.69% | 100% | 2009-02-11 | no data | 2009-05-31 | 2009-08-31 | no data | 92 | 196 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tamangi | 063038028 | Day Care Center | 1 | 511973 | 361600 | 150373 | 344154.12 | 2nd Tranche | 154311 | 498465.12 | 344154.12 | 154311 | 100% | 100% | 102.6% | 97.36% | 100% | 2006-07-31 | 2006-08-23 | 2006-12-13 | 2008-01-01 | no data | 384 | 160 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tamangi | 063038028 | Road Improvement of Farm to Market Road w/ Road Concreting | 1 | 750307.5 | 595482.5 | 154825 | 535934.25 |  | 158700 | 694634.25 | 535934.25 | 158700 | 100% | 100% | 102.5% | 92.58% | 100% | 2009-02-11 | no data | 2009-05-18 | 2009-07-31 | no data | 74 | 160 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tiabas | 063038029 | Construction of Day Care Center | 1 | 677653.86 | 564478.86 | 113175 | 508030.97 | 1st | 108425 | 616455.97 | 508030.97 | 108425 | 100% | 100% | 95.8% | 90.97% | 100% | 2009-02-11 | no data | 2009-04-20 | 2009-06-30 | no data | 71 | 329 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tuble | 063038030 | Day Care Center | 1 | 495710.03 | 439295.98 | 56414.05 | 439295.98 | 3rd Tranche | 102639.05 | 541935.03 | 439295.98 | 102639.05 | 100% | 100% | 181.9% | 109.3% | 100% | 2004-02-03 | 2004-04-26 | 2004-06-12 | 2005-01-08 | 2005-02-25 | 210 | 267 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tuble | 063038030 | Road Improvement of Farm to Market Road | 1 | 1035561.5 | 808811.5 | 226750 | 714760.97 | 1st | 278098.03 | 992859 | 714760.97 | 278098.03 | 100% | 100% | 122.6% | 95.88% | 100% | 2009-02-11 | no data | 2009-05-27 | 2009-07-31 | no data | 65 | 295 | completed as built | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Aripdip | 063042001 | Day Care Center | 1 | 401941.69 | 299781.69 | 102160 | 299781.69 | 3rd Tranche | 121683.35 | 421465.04 | 299781.69 | 121683.35 | 100% | 100% | 119.1% | 104.9% | 100% | 2003-12-15 | 2004-02-05 | 2004-04-28 | 2004-12-31 | 2005-02-05 | 247 | 139 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Aripdip | 063042001 | Health Station | 1 | 766476.51 | 570887.01 | 195589.5 | 570887.01 | 3rd Tranche | 209594.5 | 780481.51 | 570887.01 | 209594.5 | 100% | 100% | 107.2% | 101.8% | 100% | 2005-06-16 | 2005-07-12 | 2005-08-24 | 2006-02-24 | no data | 184 | 139 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Bagacay | 063042002 | Health Station | 1 | 475482.77 | 363171.74 | 112311.03 | 363171.74 | 3rd Tranche | 124525 | 487696.74 | 363171.74 | 124525 | 100% | 100% | 110.9% | 102.6% | 100% | 2003-12-15 | 2004-02-05 | 2004-05-03 | 2004-12-31 | 2005-03-05 | 242 | 231 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Bagacay | 063042002 | Day Care Center | 1 | 710790 | 476001 | 234789 | 428400.9 | 2nd Tranche | 160769.9 | 589170.8 | 428400.9 | 160769.9 | 100% | 100% | 68.47% | 82.89% | 100% | 2006-06-27 | 2006-08-10 | 2006-10-28 | 2007-10-01 | no data | 338 | 239 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Calaigang | 063042003 | 1 Unit Ambulance | 1 | 1121982.12 | 868422.12 | 253560 | 868422.12 | 100% Tranche | 256885 | 1125307.12 | 868422.12 | 256885 | 100% | 100% | 101.3% | 100.3% | 100% | 2005-06-16 | 2005-07-12 | 2005-09-22 | 2005-12-30 | no data | 99 | 248 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Ilongbukid | 063042004 | Road Rehabilitation & RCBC | 1 | 765867.08 | 539419.61 | 226447.47 | 539419.61 | 3rd Tranche | 423983 | 963402.61 | 539419.61 | 423983 | 100% | 100% | 187.2% | 125.8% | 100% | 2003-12-15 | 2004-02-05 | 2004-05-03 | 2005-01-31 | 2005-02-05 | 273 | 285 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Ilongbukid | 063042004 | Health Station | 1 | 738453.01 | 541160.51 | 197292.5 | 541160.51 | 3rd Tranche | 194227.5 | 735388.01 | 541160.51 | 194227.5 | 100% | 100% | 98.45% | 99.58% | 100% | 2005-06-16 | 2005-07-12 | 2005-08-26 | 2006-02-24 | no data | 182 | 285 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Ilongbukid | 063042004 | 1 Classroom School Building | 1 | 712167 | 543000 | 169167 | 488700 | 2nd Tranche | 127786 | 603318.71 | 488700 | 114618.71 | 100% | 89.7% | 75.54% | 84.72% | 100% | 2006-06-27 | 2006-08-10 | 2006-10-04 | 2007-05-01 | no data | 209 | 293 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | Poblacion | 063042010 | Day Care Center | 1 | 400789.33 | 295390.89 | 105398.44 | 295390.89 | 3rd Tranche | 114998.35 | 410389.24 | 295390.89 | 114998.35 | 100% | 100% | 109.1% | 102.4% | 100% | 2003-12-15 | 2004-02-05 | 2004-05-03 | 2004-12-31 | 2005-03-05 | 242 | 743 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | San Andres | 063042007 | Health Station | 1 | 738736 | 529764 | 208972 | 476787.6 | 2nd Tranche | 155651.67 | 620580.41 | 476787.6 | 143792.81 | 100% | 92.38% | 74.48% | 84.01% | 100% | 2006-06-27 | 2006-08-10 | 2006-10-25 | 2007-05-01 | no data | 188 | 380 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | San Dionisio | 063042008 | Road Rehabilitation & RCBC | 1 | 1045106.33 | 622093 | 423013.33 | 622093 | 3rd Tranche | 485404.75 | 1107497.75 | 622093 | 485404.75 | 100% | 100% | 114.7% | 106% | 100% | 2003-12-15 | 2004-02-05 | 2004-05-03 | 2005-02-28 | 2005-03-05 | 301 | 227 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | San Dionisio | 063042008 | Health Station | 1 | 740475.76 | 556163.26 | 184312.5 | 556163.26 | 3rd Tranche | 208180 | 764343.26 | 556163.26 | 208180 | 100% | 100% | 112.9% | 103.2% | 100% | 2005-06-16 | 2005-07-12 | 2005-08-31 | 2006-02-24 | no data | 177 | 227 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | San Dionisio | 063042008 | 1 Classroom School Building | 1 | 671625 | 530668 | 140957 | 477601.2 | 2nd Tranche | 282425 | 558122.77 | 477601.2 | 80521.57 | 100% | 28.51% | 200.4% | 83.1% | 100% | 2006-06-27 | 2006-08-10 | 2006-10-28 | 2007-05-01 | no data | 185 | 228 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | San Florentino | 063042009 | Road concreting | 1 | 837841.4 | 580143.07 | 257698.33 | 580143.07 | 3rd Tranche | 174507 | 754650.07 | 580143.07 | 174507 | 100% | 100% | 67.72% | 90.07% | 100% | 2003-12-15 | 2004-02-05 | 2004-04-28 | 2004-12-31 | 2005-03-05 | 247 | 285 |  | 1 | VISAYAS
VI | 06 | Iloilo | 0630 | San Rafael | 063042 | San Florentino | 063042009 | Health Station | 1 | 738736 | 525739 | 212997 | 473165.1 | 2nd Tranche | 156766.67 | 616280.1 | 473165.1 | 143115 | 100% | 91.29% | 73.6% | 83.42% | 100% | 2006-06-27 | 2006-08-10 | 2006-10-27 | 2007-05-01 | no data | 186 | 300 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Abaca | 064507001 | Road Improvement | 1 | 4630000 | 2823500 | 1806500 | 2823500 | Last Tranche | 3941231.36 | 6658731.36 | 2823500 | 3835231.36 | 100% | 97.31% | 218.2% | 143.8% | 100% | 2005-05-30 | 2005-07-20 | 2005-10-17 | 2008-02-18 | no data | 854 | 250 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Baclao | 064507002 | Road Improvement | 1 | 2782900 | 1567200 | 1215700 | 1567200 | Last Tranche | 2006636.93 | 3573836.93 | 1567200 | 2006636.93 | 100% | 100% | 165.1% | 128.4% | 100% | 2005-05-30 | 2005-07-20 | 2005-10-17 | 2007-03-31 | 2007-07-11 | 530 | 178 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Basak | 064507007 | Overflow w/ RCPC Pipe Culverts | 1 | 908000 | 575197.5 | 332802.5 | 517677.75 |  | 110396.25 | 557677.75 | 517677.75 | 40000 | 100% | 36.23% | 33.17% | 61.42% | 100% | 2007-08-22 | no data | 2008-08-01 | completed as built | n/a | #VALUE! | 626 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Bulata | 064507008 | Construction of Day Care Center | 1 | 589900 | 473437.5 | 116462.5 | 426093.76 | 1st Tranche | 78793.7 | 504887.46 | 426093.76 | 78793.7 | 100% | 100% | 67.66% | 85.59% | 100% | 2007-08-22 | no data | 2008-10-01 | 2009-07-30 | no data | 302 | 75 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Caliling | 064507009 | Construction of 2 CL School Building | 1 | 1046800 | 851435.44 | 195364.56 | 766291.9 |  | 210997.06 | 977288.96 | 766291.9 | 210997.06 | 100% | 100% | 108% | 93.36% | 100% | 2007-08-22 | no data | 2008-10-01 | 2009-07-30 | no data | 302 | 80 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Camindangan | 064507012 | Road Upgrading | 1 | 2334000 | 1006188 | 1327812 | 920201 | 1st Tranche | 100700 | 983282.47 | 920201 | 63081.47 | 100% | 62.64% | 7.584% | 42.13% | 100% | 2006-09-26 | 2006-10-18 | 2007-03-06 | 2009-08-31 | no data | 909 | 290 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Elihan | 064507013 | RCPC w/ headwell and line ditch | 1 | 386400 | 295127.5 | 91272.5 | 265614.75 |  | 65610 | 305614.75 | 265614.75 | 40000 | 100% | 60.97% | 71.88% | 79.09% | 100% | 2007-08-22 | no data | 2009-02-16 | 2009-10-30 | n/a | 256 | 902 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Guiljungan | 064507014 | Road Upgrading | 1 | 1635000 | 666282.67 | 968717.33 | 599654.41 | 1st Tranche | 1710820 | 2296765.57 | 599654.41 | 1697111.16 | 100% | 99.2% | 176.6% | 140.5% | 100% | 2006-09-26 | 2006-10-18 | 2007-01-04 | completed as built | n/a | #VALUE! | 2145 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Isio | 064507016 | Water System Level II | 1 | 5501000 | 2023400 | 3477600 | 2023400 | 2nd Tranche | 610613.34 | 2634013.34 | 2023400 | 610613.34 | 100% | 100% | 17.56% | 47.88% | 100% | 2005-05-30 | 2005-07-20 | 2005-10-17 | completed as built | n/a | #VALUE! | 1111 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Linaon | 064507017 | Construction of 2 CL School Building | 1 | 1051500 | 843503.96 | 207996.04 | 759153.56 |  | 194700.13 | 953853.69 | 759153.56 | 194700.13 | 100% | 100% | 93.61% | 90.71% | 100% | 2007-08-22 | no data | 2008-10-01 | 2009-07-30 | no data | 302 | 66 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Lumbia | 064507018 | Road Improvement | 1 | 1722600 | 1085900 | 636700 | 1085900 | Last Tranche | 1375620 | 2461520 | 1085900 | 1375620 | 100% | 100% | 216.1% | 142.9% | 100% | 2005-05-30 | 2005-07-20 | 2005-10-17 | 2007-05-30 | 2007-07-29 | 590 | 248 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Mambugsay | 064507020 | Construction of Day Care Center | 1 | 589900 | 516862.5 | 73037.5 | 465176.24 |  | 69398.05 | 534574.29 | 465176.24 | 69398.05 | 100% | 100% | 95.02% | 90.62% | 100% | 2007-08-22 | no data | 2008-10-01 | 2009-08-31 | no data | 334 | 84 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Man-Uling | 064507021 | Artificial Coral Reef | 1 | 489000 | 379552 | 109448 | 341596.8 | 1st Tranche | 69900 | 411496.8 | 341596.8 | 69900 | 100% | 100% | 63.87% | 84.15% | 100% | 2006-09-26 | 2006-10-18 | 2007-02-05 | 2008-09-01 | n/a | 574 | 533 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Molobolo | 064507023 | Construction of 2 CL School Building | 1 | 1052400 | 892857.5 | 159542.5 | 803571.75 |  | 152325 | 952871.75 | 803571.75 | 149300 | 100% | 98.01% | 95.48% | 90.54% | 100% | 2007-08-22 | no data | 2008-12-01 | 2009-07-30 | no data | 241 | 46 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Poblacion | 064507004 | Pre-Post Harvest Facilities | 1 | 789800 | 696067.5 | 93732.5 | 626460.75 |  | 126725 | 753185.75 | 626460.75 | 126725 | 100% | 100% | 135.2% | 95.36% | 100% | 2007-08-22 | no data | 2008-12-01 | 2009-08-30 | no data | 272 | 151 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Tambad | 064507028 | Road Upgrading and Construction | 1 | 2460000 | 1051549 | 1408451 | 946394.1 | 1st Tranche | 155275 | 1101669.1 | 946394.1 | 155275 | 100% | 100% | 11.02% | 44.78% | 100% | 2006-09-26 | 2006-10-18 | 2007-09-26 | completed as built | n/a | #VALUE! | 187 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Tiling | 064507029 | Road Upgrading | 1 | 3265000 | 1666002.67 | 1598997.33 | 1499402.41 | 1st Tranche | 1780785 | 3280187.41 | 1499402.41 | 1780785 | 100% | 100% | 111.4% | 100.5% | 100% | 2006-09-26 | 2006-10-18 | 2007-05-24 | completed as built | n/a | #VALUE! | 611 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Tomina - C2 | 064507030 | Road Upgrading | 2 | 5390000 | 2424909.33 | 2965090.67 | 2182418.39 | 1st Tranche | 136500 | 2051549.88 | 1915049.88 | 136500 | 87.75% | 100% | 4.604% | 38.06% | 100% | 2006-09-26 | 2006-10-18 | 2007-10-10 | completed as built | n/a | #VALUE! | 273 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Sura | 064507025 | Road Upgrading | 2 | 5390000 | 2424909.33 | 2965090.67 | 2182418.39 | 1st Tranche | 136500 | 2051549.88 | 1915049.88 | 136500 | 87.75% | 100% | 4.604% | 38.06% | 100% | 2006-09-26 | 2006-10-18 | 2007-10-10 | completed as built | n/a | #VALUE! | 273 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Cauayan | 064507 | Tuyom | 064507031 | Artificial Coral Reef | 1 | 537872 | 305516.33 | 232355.67 | 274964.69 | 1st Tranche | 198150 | 466928.78 | 274964.69 | 191964.09 | 100% | 96.88% | 85.28% | 86.81% | 100% | 2006-09-26 | 2006-10-18 | 2007-03-27 | 2008-12-30 | no data | 644 | 1047 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Bago (Lalung) | 064532001 | Post Harvest Facilities | 1 | 1429000 | 1301000 | 128000 | 1170900 | 1st Tranche | 105290.63 | 1276190.63 | 1170900 | 105290.63 | 100% | 100% | 82.26% | 89.31% | 100% | 2007-06-26 | no data | 2008-03-11 | 2008-12-01 | no data | 265 | 353 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Bagong Silang | 064532002 | Construction of Solar Dryer | 1 | 911700 | 799000 | 112700 | 734298.25 | 2nd Tranche | 107308.63 | 841606.88 | 734298.25 | 107308.63 | 100% | 100% | 95.22% | 92.31% | 100% | 2007-06-26 | no data | 2007-10-26 | 2008-04-11 | no data | 168 | 253 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Bagong Silang | 064532002 | Construction of Vermi Composting Production Center | 1 | 880708.01 | 614728.01 | 265980 | 580752.5 |  | 250026 | 830778.5 | 580752.5 | 250026 | 100% | 100% | 94% | 94.33% | 100% | 2008-10-21 | no data | 2009-02-02 | 2009-06-30 | no data | 148 | 487 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Bunga | 064532003 | Construction of Post Harvest Facilities | 1 | 2636470.93 | 1743280.14 | 893190.79 | 1568952.13 |  | 869440.79 | 2438392.92 | 1568952.13 | 869440.79 | 100% | 100% | 97.34% | 92.49% | 100% | 2008-10-21 | no data | 2009-02-19 | 2009-06-30 | no data | 131 | 820 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Igmaya-an | 064532004 | Pre & Post Harvest Facilities | 1 | 1333000 | 620850 | 712150 | 557643.6 |  | 705873.38 | 1263516.98 | 557643.6 | 705873.38 | 100% | 100% | 99.12% | 94.79% | 100% | 2008-02-25 | no data | 2008-07-29 | 2009-01-30 | no data | 185 | 748 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Salvador Benedicto | 064532 | Pandanon | 064532006 | Construction of Pre & Post Harvest Facilities | 1 | 1639300 | 1479150 | 160150 | 1435516.35 |  | 140875.5 | 1576391.85 | 1435516.35 | 140875.5 | 100% | 100% | 87.96% | 96.16% | 100% | 2008-02-27 | no data | 2008-08-01 | 2009-03-20 | n/a | 231 | 400 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Alim | 064512001 | Improvement of exisiting sea wall | 1 | 1430000 | 990000 | 440000 | 891000 |  | 220000 | 1001000 | 891000 | 110000 | 100% | 50% | 50% | 70% | 100% | 2008-11-24 | no data | 2009-04-13 | 2009-06-30 | no data | 78 | 371 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Asia | 064512002 | Road Improvement of Existing Earth Road | 1 | 1734400 | 1008000 | 726400 | 907200 | 1st Tranche | 733563.76 | 1640663.76 | 907200 | 733463.76 | 100% | 99.99% | 101% | 94.6% | 100% | 2007-08-01 | no data | 2008-02-25 | 2008-04-24 | no data | 59 | 627 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Bacuyangan | 064512003 | Construction of Flood Control and sea wall | 1 | 1300000 | 870000 | 430000 | 783000 |  | 129000 | 891415 | 783000 | 108415 | 100% | 84.04% | 30% | 68.57% | 100% | 2008-11-24 | no data | 2009-03-27 | 2009-06-25 | no data | 90 | 224 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Brgy. 1 | 064512004 | Construction of Retaining Wall / Flood Control | 1 | 1697000 | 1340000 | 357000 | 1206000 | 1st Tranche | 246644.04 | 1391837.86 | 1206000 | 185837.86 | 100% | 75.35% | 69.09% | 82.02% | 100% | 2008-03-13 | no data | 2008-08-23 | 2009-06-02 | no data | 283 | 717 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Brgy. 2 | 064512005 | Road Construction | 1 | 1530000 | 1050000 | 480000 | 840000 | 1st Tranche | 501044.09 | 1292012.27 | 840000 | 452012.27 | 100% | 90.21% | 104.4% | 84.45% | 100% | 2008-03-13 | no data | 2008-09-11 | 2009-02-02 | n/a | 144 | 526 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Bulwangan | 064512006 | Construction of Flood Control with Dredging | 1 | 1725000 | 1310000 | 415000 | 1179000 |  | 299443.57 | 1478443.57 | 1179000 | 299443.57 | 100% | 100% | 72.16% | 85.71% | 100% | 2008-11-24 | no data | 2009-03-27 | 2009-06-25 | no data | 90 | 189 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Culipapa | 064512007 | Construction of Flood Control with Dredging | 1 | 1585000 | 706800 | 878200 | 636120 |  | 612545 | 1248665 | 636120 | 612545 | 100% | 100% | 69.75% | 78.78% | 100% | 2008-11-24 | no data | 2009-04-16 | 2009-06-25 | no data | 70 | 1030 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Damutan | 064512008 | Pre and Post Harvest Facilities | 1 | 1349900 | 1033000 | 316900 | 991181.75 | 1st Tranche | 347130.8 | 1323707.03 | 991181.75 | 332525.28 | 100% | 95.79% | 109.5% | 98.06% | 100% | 2007-08-01 | no data | 2008-02-29 | 2009-05-02 | n/a | 428 | 173 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Daug | 064512009 | Provision of Pre & Post Harvest Facilities w/ garage | 1 | 816178.5 | 476000 | 340178.5 | 428400 |  | 343519.16 | 771919.16 | 428400 | 343519.16 | 100% | 100% | 101% | 94.58% | 100% | 2008-11-24 | no data | 2009-02-16 | 2009-06-25 | no data | 129 | 348 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Po-ok | 064512010 | Road Improvement | 1 | 868000 | 710000 | 158000 | 568000 |  | 153537.32 | 711462.98 | 568000 | 143462.98 | 100% | 93.44% | 97.18% | 81.97% | 100% | 2008-03-13 | no data | 2008-08-25 | 2008-10-14 | no data | 50 | 412 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | San Rafael | 064512011 | Hanging Bridge | 1 | 1607100 | 1262700 | 344400 | 1255612 | 1st Tranche | 342862.16 | 1598474.16 | 1255612 | 342862.16 | 100% | 100% | 99.55% | 99.46% | 100% | 2007-08-01 | no data | 2007-12-14 | 2009-04-09 | n/a | 482 | 788 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Sangke | 064512012 | Pre and Post Harvest Facilities | 1 | 777400 | 596300 | 181100 | 572244 | 1st Tranche | 194950.82 | 764463.82 | 572244 | 192219.82 | 100% | 98.6% | 107.6% | 98.34% | 100% | 2007-08-01 | no data | 2008-02-27 | 2009-05-21 | n/a | 449 | 382 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Hinoba-an | 064512 | Talacagay | 064512013 | Construction of Hanging Foot Bridge | 1 | 1030000 | 800000 | 230000 | 764495.71 |  | 517246.25 | 1281741.96 | 764495.71 | 517246.25 | 100% | 100% | 224.9% | 124.4% | 100% | 2008-03-13 | no data | 2009-02-02 | 2009-06-18 | no data | 136 | 526 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 1 - C8 | 064519002 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 2 - C8 | 064519003 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 3 - C8 | 064519004 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 4- C8 | 064519005 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 5 - C8 | 064519006 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 6 - C8 | 064519007 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Barangay 7 - C8 | 064519008 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Crossing Magallon | 064519009 | Production Center | 8 | 2109000 | 1877740 | 231260 | 1689966 |  | 230421.05 | 1920387.05 | 1689966 | 230421.05 | 100% | 100% | 99.64% | 91.06% | 100% | 2008-11-25 | no data | 2009-03-03 | 2009-06-30 | no data | 119 | 1699 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Guinpana-an - C2 | 064519010 | Water System Level II | 2 | 6566999.9981 | 3824095 | 2742904.9981 | 3441685.5 |  | 2625956.68 | 3468685.5 | 3441685.5 | 27000 | 100% | 1.028% | 95.74% | 52.82% | 100% | 2008-02-27 | no data | 2009-01-22 | 2009-06-30 | no data | 159 | 759 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Magallon Cadre | 064519013 | Water System Level II | 2 | 6566999.9981 | 3824095 | 2742904.9981 | 3441685.5 |  | 2625956.68 | 3468685.5 | 3441685.5 | 27000 | 100% | 1.028% | 95.74% | 52.82% | 100% | 2008-02-27 | no data | 2009-01-22 | 2009-06-30 | no data | 159 | 759 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Inolingan | 064519011 | Health Station | 1 | 751000 | 675905 | 75095 | 657729 | 1st Tranche | 77673.8 | 725417.8 | 657729 | 67688.8 | 100% | 87.14% | 103.4% | 96.59% | 100% | 2008-02-27 | no data | 2008-08-18 | 2009-03-31 | n/a | 225 | 940 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Macagahay | 064519012 | Construction of 2-units,3 Barrels RCBC wd 3.0m x67.0m Spillway | 1 | 2551455 | 1632779 | 918676 | 1632779 | 1st Tranche | 847843.99 | 2781739.99 | 1632779 | 1148960.99 | 100% | 135.5% | 92.29% | 109% | 100% | 2007-07-06 | no data | 2008-02-27 | 2009-03-25 | n/a | 392 | 335 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Montilla | 064519014 | Overflow | 1 | 3653720.4 | 2551074.84 | 1102645.56 | 2295967 |  | 174099.28 | 2470066.28 | 2295967 | 174099.28 | 100% | 100% | 15.79% | 67.6% | 100% | 2008-11-25 | no data | 2009-04-06 | 2009-08-31 | no data | 147 | 350 | completed as built | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Odiong | 064519015 | Health Station | 1 | 689000 | 599410 | 89590 | 584820.5 | 1st Tranche | 88790 | 688850.19 | 584820.5 | 104029.69 | 100% | 117.2% | 99.11% | 99.98% | 100% | 2007-07-06 | no data | 2008-01-08 | 2009-02-25 | n/a | 414 | 788 |  | 1 | VISAYAS
VI | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Quintin Remo | 064519016 | Hanging Bridge | 1 | 3650800 | 2267811 | 1382989 | 2267811 | 1st Tranche | 1380791.5 | 4059296.08 | 2267811 | 1791485.08 | 100% | 129.7% | 99.84% | 111.2% | 100% | 2007-07-06 | no data | 2008-03-04 | 2009-03-25 | n/a | 386 | 1126 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Bilangbilangan Dako (West) | 071248001 | Concrete Paving of Barangay Pathways | 1 | 543259 | 337929 | 205330 | 337375.51 |  | 182350 | 519725.51 | 337375.51 | 182350 | 100% | 100% | 88.81% | 95.67% | 100% | 2007-02-21 | n/a | 2007-12-14 | 2008-08-30 | no data | 260 | 319 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Bilangbilangan East (Diot) | 071248002 | Multi Purpose Building With Rain Collector | 1 | 975000 | 869250.38 | 105749.62 | 869250.38 | 3rd Tranche | 75639.62 | 944890 | 869250.38 | 75639.62 | 100% | 100% | 71.53% | 96.91% | 100% | 2005-07-01 | 2005-08-24 | 2005-11-25 | 2006-02-01 | 2006-02-01 | 68 | 115 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Hingotanan East | 071248003 | Construction of Seawall | 1 | 724886 | 472176 | 252710 | 459300.53 |  | 215880 | 675180.53 | 459300.53 | 215880 | 100% | 100% | 85.43% | 93.14% | 100% | 2007-02-21 | n/a | 2007-07-13 | 2007-08-31 | no data | 49 | 311 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Hingotanan West | 071248004 | Concrete Paving of Barangay Pathways | 1 | 703777 | 491907 | 211870 | 477872.25 |  | 190850 | 668722.71 | 477872.25 | 190850.46 | 100% | 100% | 90.08% | 95.02% | 100% | 2007-02-21 | n/a | 2007-09-24 | 2007-12-12 | no data | 79 | 243 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Liberty | 071248005 | Surfacing of Farm-to-Market Road | 1 | 1081112 | 974302 | 106810 | 974302 |  | 104910 | 1079212 | 974302 | 104910 | 100% | 100% | 98.22% | 99.82% | 100% | 2006-05-17 | n/a | 2006-09-20 | 2006-12-18 | 2007-01-09 | 89 | 155 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Liberty | 071248005 | Construction of health Center | 1 | 741251 | 517576 | 223675 | 503778.46 |  | 128615 | 632393.46 | 503778.46 | 128615 | 100% | 100% | 57.5% | 85.31% | 100% | 2007-02-21 | n/a | 2007-07-20 | 2007-09-24 | no data | 66 | 156 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Malingin | 071248006 | Construction of Mini-Port | 1 | 961210 | 816080 | 145130 | 816080 |  | 144780 | 960860 | 816080 | 144780 | 100% | 100% | 99.76% | 99.96% | 100% | 2006-05-17 | n/a | 2006-10-18 | 2007-02-22 | 2007-02-28 | 127 | 288 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Mandawa | 071248007 | Surfacing and Concreting of Mandawa 3.5 km Farm to Market Road | 1 | 3070472 | 2909258.1 | 161213.9 | 2909258.1 | 3rd Tranche | 113723.9 | 3022982 | 2909258.1 | 113723.9 | 100% | 100% | 70.54% | 98.45% | 100% | 2005-07-01 | 2005-08-24 | 2005-10-28 | 2006-02-01 | 2006-02-01 | 96 | 359 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Mandawa | 071248007 | Single Phase Extension to Sitio Bikal and Purok 2 (Electrification) | 1 | 1003039 | 182938 | 820101 | 182938 |  | 140166.96 | 323104.96 | 182938 | 140166.96 | 100% | 100% | 17.09% | 32.21% | 100% | 2007-02-21 | n/a | 2008-01-12 | 2008-07-18 | no data | 188 | 359 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Maomawan | 071248008 | Construction of Multi-Purpose Building w/ Rain Water Collector | 1 | 950075 | 769735 | 180340 | 769735 |  | 176912.58 | 946647.58 | 769735 | 176912.58 | 100% | 100% | 98.1% | 99.64% | 100% | 2006-05-17 | n/a | 2006-09-22 | 2006-11-06 | 2006-11-24 | 45 | 383 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Nueva Esperanza | 071248009 | Surfacing of Farm-to-Market Road | 1 | 1244756 | 1127606 | 117150 | 1014845.4 |  | 115060 | 1129905.4 | 1014845.4 | 115060 | 100% | 100% | 98.22% | 90.77% | 100% | 2006-05-17 | n/a | 2006-10-30 | 2007-04-15 | no data | 167 | 436 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Nueva Estrella | 071248010 | Day Care Center | 1 | 771142 | 639392.63 | 131749.37 | 639392.63 | 3rd Tranche | 103108.87 | 742501.5 | 639392.63 | 103108.87 | 100% | 100% | 78.26% | 96.29% | 100% | 2005-07-01 | 2005-08-24 | 2005-10-19 | 2005-11-30 | 2005-11-30 | 42 | 258 |  | 1
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Nueva Estrella | 071248010 | Surfacing of Nueva Estrella barangay Farm to Market Road | 1 | 398844 | 266731 | 132113 | 248028.22 |  | 118093 | 366121.22 | 248028.22 | 118093 | 100% | 100% | 89.39% | 91.8% | 100% | 2007-02-21 | n/a | 2007-08-23 | 2007-10-20 | no data | 58 | 258 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Pinamgo | 071248011 | Concreting of .25Km Pathways | 1 | 608124 | 202524 | 405600 | 202524 |  | 398701 | 601225 | 202524 | 398701 | 100% | 100% | 98.3% | 98.87% | 100% | 2006-05-17 | n/a | 2006-10-05 | 2007-01-31 | 2007-01-19 | 118 | 387 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Pinamgo | 071248011 | Concrete Paving of Barangay Pathways (Broken Section) | 1 | 548145 | 381885 | 166260 | 368286.29 |  | 116850 | 485136.29 | 368286.29 | 116850 | 100% | 100% | 70.28% | 88.51% | 100% | 2007-02-21 | n/a | 2007-09-28 | 2008-05-15 | no data | 230 | 387 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Poblacion | 071248012 | Construction of Day Care Center | 1 | 708636 | 464836 | 243800 | 448375.1 |  | 222240 | 670615.1 | 448375.1 | 222240 | 100% | 100% | 91.16% | 94.63% | 100% | 2007-02-21 | n/a | 2007-07-20 | 2007-09-14 | no data | 56 | 549 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Puerto San Pedro | 071248013 | Asphalt Paving of .04Km Farm-to-Market Road | 1 | 797714 | 609753 | 187961 | 609753 |  | 174640 | 784393 | 609753 | 174640 | 100% | 100% | 92.91% | 98.33% | 100% | 2006-05-17 | n/a | 2006-09-21 | 2007-01-31 | 2007-01-26 | 132 | 185 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Puerto San Pedro | 071248013 | Surfacing of Puerto San Pedro Barangay Farm to Market Road | 1 | 494433 | 321283 | 173150 | 302847.93 |  | 142550 | 445397.93 | 302847.93 | 142550 | 100% | 100% | 82.33% | 90.08% | 100% | 2007-02-21 | n/a | 2007-10-29 | 2008-02-22 | no data | 116 | 165 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Sagasa | 071248014 | Electrification (Generator Set) | 1 | 1075079 | 495263 | 579816 | 495167.94 |  | 178100 | 673267.94 | 495167.94 | 178100 | 100% | 100% | 30.72% | 62.62% | 100% | 2007-02-21 | n/a | 2008-01-12 | 2008-07-19 | no data | 189 | 224 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Bien Unido | 071248 | Tuboran | 071248015 | Surfacing of Tuboran Barangay Farm to Market Road | 1 | 811326 | 567476 | 243850 | 549473.88 |  | 215300 | 764773.88 | 549473.88 | 215300 | 100% | 100% | 88.29% | 94.26% | 100% | 2007-02-21 | n/a | 2007-09-28 | 2008-02-23 | no data | 148 | 161 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Anonang | 071209001 | Construction of Bailey Bridge | 1 | 1394884.78 | 735679.77 | 659205.01 | 735679.77 |  | 1056410 | 1792089.77 | 735679.77 | 1056410 | 100% | 100% | 160.3% | 128.5% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2007-10-30 | no data | 393 | 65 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Asinan | 071209002 | Construction of 2 Classroom Elemnetary School Building | 1 | 1414387 | 1152546.53 | 261840.47 | 1150476.42 |  | 293055.51 | 1443531.93 | 1150476.42 | 293055.51 | 100% | 100% | 111.9% | 102.1% | 100% | 2007-02-23 | n/a | 2007-07-07 | 2008-04-30 | no data | 298 | 151 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bago | 071209003 | Water System Level II | 1 | 1678108.08 | 1074180.14 | 603927.94 | 1074180.14 | 2nd Tranche | 615127.94 | 1689308.08 | 1074180.14 | 615127.94 | 100% | 100% | 101.9% | 100.7% | 100% | 2005-06-08 | 2005-08-16 | 2006-05-09 | 2007-06-27 | 2007-07-04 | 414 | 100 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Baluarte | 071209004 | Regravelling of Farm-to-Market Road | 1 | 973008 | 846607.46 | 126400.54 | 846607.46 |  | 133200 | 979807.46 | 846607.46 | 133200 | 100% | 100% | 105.4% | 100.7% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2007-03-26 | 2007-04-12 | 175 | 65 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bantuan | 071209005 | Installation of Level II WWS | 1 | 1032879 | 658456.92 | 374422.08 | 658456.92 |  | 374422.08 | 1032879 | 658456.92 | 374422.08 | 100% | 100% | 100% | 100% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2008-11-20 | no data | 780 | 97 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bato | 071209006 | Farm to Market Road | 1 | 573969 | 480638.69 | 93330.31 | 469944.22 |  | 93330.31 | 563274.53 | 469944.22 | 93330.31 | 100% | 100% | 100% | 98.14% | 100% | 2007-02-23 | n/a | 2007-06-09 | 2007-12-05 | no data | 179 | 136 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bonotbonot | 071209007 | Construction of 2 Classroom Elemnetary School Building | 1 | 1034797 | 894901.21 | 139895.79 | 861718.86 |  | 149289.32 | 1011008.18 | 861718.86 | 149289.32 | 100% | 100% | 106.7% | 97.7% | 100% | 2007-02-23 | n/a | 2007-12-19 | 2008-07-21 | no data | 215 | 128 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bugaong | 071209008 | Rehabilitation of & Improvement of Farm-to-Market Road | 1 | 1119707 | 795476.51 | 324230.49 | 795476.51 |  | 482648 | 1278124.51 | 795476.51 | 482648 | 100% | 100% | 148.9% | 114.1% | 100% | 2006-06-30 | n/a | 2006-10-05 | 2007-02-10 | 2007-02-22 | 128 | 86 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Western Cabul-an | 071209021 | Construction of Cause Way | 2 | 1851676 | 1666713.85 | 184962.15 | 1666662.53 |  | 201487.15 | 1868149.68 | 1666662.53 | 201487.15 | 100% | 100% | 108.9% | 100.9% | 100% | 2006-06-30 | n/a | 2006-12-04 | 2008-01-25 | no data | 417 | 584 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Western Cabul-an | 071209040 | Construction of Cause Way | 2 | 1851676 | 1666713.85 | 184962.15 | 1666662.53 |  | 201487.15 | 1868149.68 | 1666662.53 | 201487.15 | 100% | 100% | 108.9% | 100.9% | 100% | 2006-06-30 | n/a | 2006-12-04 | 2008-01-25 | no data | 417 | 584 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Eastern Cabul-an | 071209021 | Construction of Cause Way | 2 | 1851676 | 1666713.85 | 184962.15 | 1666662.53 |  | 201487.15 | 1868149.68 | 1666662.53 | 201487.15 | 100% | 100% | 108.9% | 100.9% | 100% | 2006-06-30 | n/a | 2006-12-04 | 2008-01-25 | no data | 417 | 584 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cambuhat | 071209011 | Farm to Market Road | 1 | 1149683 | 1026353.09 | 123329.91 | 1011740.34 |  | 123529.91 | 1135270.25 | 1011740.34 | 123529.91 | 100% | 100% | 100.2% | 98.75% | 100% | 2007-02-23 | n/a | 2008-01-07 | 2008-06-20 | no data | 165 | 210 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cambus-oc | 071209012 | Construction of Day Care Center | 1 | 628549 | 522648.98 | 105900.02 | 522648.98 |  | 94750 | 617398.98 | 522648.98 | 94750 | 100% | 100% | 89.47% | 98.23% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2007-03-26 | 2007-02-07 | 175 | 118 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cangawa | 071209013 | Installation of Level II WWS | 1 | 982874 | 749747.32 | 233126.68 | 742481.71 |  | 242626.13 | 985107.84 | 742481.71 | 242626.13 | 100% | 100% | 104.1% | 100.2% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2007-06-30 | no data | 271 | 145 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cantomugcad | 071209014 | Water System Level II | 1 | 1511915.65 | 1379579.59 | 132336.06 | 1379579.59 | 3rd Tranche | 155790.06 | 1535369.65 | 1379579.59 | 155790.06 | 100% | 100% | 117.7% | 101.6% | 100% | 2005-06-08 | 2005-08-16 | 2006-03-30 | 2006-09-27 | 2006-09-27 | 181 | 69 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cantores | 071209015 | Road Opening of Farm-to-Market Road | 1 | 1002074 | 896435 | 105639 | 896435 |  | 144550.63 | 1040985.63 | 896435 | 144550.63 | 100% | 100% | 136.8% | 103.9% | 100% | 2006-06-30 | n/a | 2006-10-05 | 2007-01-31 | 2007-02-02 | 118 | 92 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cantuba | 071209016 | Installation of Level II WWS | 1 | 892706 | 750343.19 | 142362.81 | 694568.82 |  | 118703.55 | 813272.37 | 694568.82 | 118703.55 | 100% | 100% | 83.38% | 91.1% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2008-04-11 | no data | 557 | 70 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Catigbian | 071209017 | Water System Level II | 1 | 1876900.25 | 1546655.34 | 330244.91 | 1546655.34 | 2nd Tranche | 361324.91 | 1907980.25 | 1546655.34 | 361324.91 | 100% | 100% | 109.4% | 101.7% | 100% | 2005-06-08 | 2005-08-16 | 2006-08-25 | 2006-12-20 | 2006-12-29 | 117 | 108 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cawag | 071209018 | Water System Level II | 1 | 1241540.42 | 914755.5 | 326784.92 | 914755.5 | 3rd Tranche | 326784.92 | 1241540.42 | 914755.5 | 326784.92 | 100% | 100% | 100% | 100% | 100% | 2005-06-08 | 2005-08-16 | 2006-03-30 | 2006-12-04 | 2006-12-06 | 249 | 106 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cruz | 071209019 | Construction of 2 Classroom Elemnetary School Building | 1 | 1047405 | 923204.41 | 124200.59 | 914208.28 |  | 133300.58 | 1047508.86 | 914208.28 | 133300.58 | 100% | 100% | 107.3% | 100% | 100% | 2007-02-23 | n/a | 2007-07-07 | 2008-04-30 | no data | 298 | 167 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Dait | 071209020 | Farm to Market Road | 1 | 996371 | 896081.5 | 100289.5 | 880492.9 |  | 100289.5 | 980782.4 | 880492.9 | 100289.5 | 100% | 100% | 100% | 98.44% | 100% | 2007-02-23 | n/a | 2007-05-25 | 2007-12-15 | no data | 204 | 167 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Hunan | 071209022 | Construction of Mother & Child Learning Center | 1 | 617330 | 507072.14 | 110257.86 | 507072.14 |  | 120658.84 | 627730.98 | 507072.14 | 120658.84 | 100% | 100% | 109.4% | 101.7% | 100% | 2006-06-30 | n/a | 2006-10-03 | 2007-03-06 | 2006-12-27 | 154 | 140 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lapacan Norte | 071209025 | Water Works System L2 | 1 | 1044405 | 829770 | 214635 | 791202.69 |  | 215635 | 1006837.69 | 791202.69 | 215635 | 100% | 100% | 100.5% | 96.4% | 100% | 2007-02-23 | n/a | 2007-05-25 | 2008-06-20 | no data | 392 | 72 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lapacan Sur | 071209026 | Water Works System L2 | 1 | 1095729 | 857403.7 | 238325.3 | 842142.34 |  | 238325.3 | 1080467.64 | 842142.34 | 238325.3 | 100% | 100% | 100% | 98.61% | 100% | 2007-02-23 | n/a | 2007-06-08 | 2008-09-15 | no data | 465 | 80 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lubang | 071209028 | Water System Level II | 1 | 1943606.71 | 1722561.59 | 221045.12 | 1722561.59 | 1st Tranche | 256221.12 | 1978782.71 | 1722561.59 | 256221.12 | 100% | 100% | 115.9% | 101.8% | 100% | 2005-06-08 | 2005-08-16 | 2006-03-30 | 2007-12-05 | 2007-12-31 | 615 | 145 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lusong | 071209029 | Rehabilitation of Farm to Market Road | 1 | 1382500.69 | 1247932.69 | 134568 | 1231010.94 |  | 177426.62 | 1408437.56 | 1231010.94 | 177426.62 | 100% | 100% | 131.8% | 101.9% | 100% | 2007-02-23 | n/a | 2007-06-07 | 2007-12-05 | no data | 181 | 88 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Magkaya | 071209030 | 2 Unit multi purpose spillways and resurfacing of FMR | 1 | 924449.5 | 788466.71 | 135982.79 | 788466.71 |  | 149800 | 938266.71 | 788466.71 | 149800 | 100% | 100% | 110.2% | 101.5% | 100% | 2006-06-30 | n/a | 2006-10-05 | 2007-04-12 | no data | 189 | 137 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Merryland | 071209031 | Water Works System L2 | 1 | 1003330.13 | 566020.67 | 437309.46 | 540809.72 |  | 437409.46 | 978219.18 | 540809.72 | 437409.46 | 100% | 100% | 100% | 97.5% | 100% | 2007-02-23 | n/a | 2007-05-21 | 2008-04-10 | no data | 325 | 46 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Nueva Granada | 071209032 | Gravelling of Farm-to-Market Road | 1 | 890480 | 637352.15 | 253127.85 | 637352.15 |  | 263519.97 | 900872.12 | 637352.15 | 263519.97 | 100% | 100% | 104.1% | 101.2% | 100% | 2006-06-30 | n/a | 2006-10-02 | 2007-01-15 | 2007-02-02 | 105 | 78 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Nueva Montaña | 071209033 | Day Care Center | 1 | 698636.51 | 583597.45 | 115039.06 | 583597.45 | 3rd Tranche | 88398 | 671995.45 | 583597.45 | 88398 | 100% | 100% | 76.84% | 96.19% | 100% | 2005-06-08 | 2005-08-16 | 2006-04-04 | 2006-07-13 | 2006-07-13 | 100 | 84 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Overland | 071209034 | Construction of heatlh Center | 1 | 910667 | 788134.87 | 122532.13 | 582003.43 |  | 105872.13 | 687876.56 | 582003.43 | 105873.13 | 100% | 100% | 86.4% | 75.54% | 100% | 2007-02-23 | n/a | 2008-06-23 | 2009-01-28 | no data | 219 | 145 |  | 1
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Panghagban | 071209035 | Water System Level II | 1 | 2206555.96 | 1801297.25 | 405258.71 | 1801297.25 | 3rd Tranche | 233450 | 2034747.25 | 1801297.25 | 233450 | 100% | 100% | 57.61% | 92.21% | 100% | 2005-06-08 | 2005-08-16 | 2006-05-09 | 2007-01-12 | 2007-01-18 | 248 | 180 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Poblacion | 071209036 | Construction of Skills Training Center | 1 | 1200580 | 945000 | 255580 | 945000 |  | 384980 | 1329980 | 945000 | 384980 | 100% | 100% | 150.6% | 110.8% | 100% | 2006-06-30 | n/a | 2006-10-03 | 2006-12-29 | 2007-01-18 | 87 | 101 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Puting-Bato | 071209037 | Farm to Market Road | 1 | 999575 | 837012.04 | 162562.96 | 835410.01 |  | 162562.96 | 997972.97 | 835410.01 | 162562.96 | 100% | 100% | 100% | 99.84% | 100% | 2007-02-23 | n/a | 2007-05-30 | 2008-07-30 | no data | 427 | 91 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Rufo Hill | 071209038 | Water System Level II | 1 | 1207193.26 | 911623.26 | 295570 | 911623.26 | 3rd Tranche | 182726 | 1094349.26 | 911623.26 | 182726 | 100% | 100% | 61.82% | 90.65% | 100% | 2005-06-08 | 2005-08-16 | 2006-03-16 | 2006-11-30 | 2006-12-06 | 259 | 145 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Sweetland | 071209039 | Day Care Center | 1 | 680901.87 | 565749.88 | 115151.99 | 565749.88 | 3rd Tranche | 63200 | 628949.88 | 565749.88 | 63200 | 100% | 100% | 54.88% | 92.37% | 100% | 2005-06-08 | 2005-08-16 | 2006-04-04 | 2006-07-13 | 2006-07-13 | 100 | 113 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Aguining | 071235001 | Concrete Paving & Resurfacing of Farm-to-Market Road | 1 | 5230837 | 2849946.82 | 2380890.18 | 2770469.4 |  | 477370 | 3247839.4 | 2770469.4 | 477370 | 100% | 100% | 20.05% | 62.09% | 100% | 2006-04-26 | n/a | 2006-11-14 | 2008-06-25 | no data | 589 | 444 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Basiao | 071235003 | Construction of Barangay Health Center | 1 | 815800 | 520450 | 295350 | 488920.03 |  | 150700 | 639620.032 | 488920.03 | 150700.002 | 100% | 100% | 51.02% | 78.4% | 100% | 2007-02-28 | n/a | 2008-05-19 | 2008-10-25 | no data | 159 | 155 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Baud | 071235004 | Construction of Concrete Path | 1 | 786340 | 456205 | 330135 | 426695.68 |  | 198500 | 625195.68 | 426695.68 | 198500 | 100% | 100% | 60.13% | 79.51% | 100% | 2007-02-28 | n/a | 2007-12-15 | 2008-07-30 | no data | 228 | 132 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Bayog | 071235005 | Construction of Concrete Path | 1 | 813325 | 508585 | 304740 | 486020 |  | 171883.13 | 657903.13 | 486020 | 171883.13 | 100% | 100% | 56.4% | 80.89% | 100% | 2007-02-28 | n/a | 2008-05-22 | 2008-06-28 | no data | 37 | 51 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Bogo | 071235006 | Construction of Concrete Path | 1 | 1079990 | 726110 | 353880 | 714915 |  | 301947.89 | 1016862.89 | 714915 | 301947.89 | 100% | 100% | 85.32% | 94.15% | 100% | 2007-02-28 | n/a | 2007-12-20 | 2008-10-25 | no data | 310 | 201 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Bonbonon | 071235007 | Construction of Concrete Path | 1 | 815950 | 530145 | 285805 | 512454 |  | 234700 | 747154 | 512454 | 234700 | 100% | 100% | 82.12% | 91.57% | 100% | 2007-02-28 | n/a | 2007-12-20 | 2008-07-30 | no data | 223 | 290 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Butan | 071235023 | Rehabilitation of Existing Power Supply System (GenSet & Solar) cum installation of Lighting Facilities | 1 | 374510 | 139508.43 | 235001.57 | 111606.74 |  | 172842.5 | 284449.24 | 111606.74 | 172842.5 | 100% | 100% | 73.55% | 75.95% | 100% | 2006-04-26 | n/a | 2006-12-15 | 2008-01-30 | no data | 411 | 102 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Butan | 071235023 | Electirification project of Butan Island | 1 | 392160 | 323360 | 68800 | 323360 |  | 150700 | 474060 | 323360 | 150700 | 100% | 100% | 219% | 120.9% | 100% | 2007-02-28 | n/a | 2008-05-19 | 2008-05-23 | no data | 4 | 102 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Campamanog | 071235009 | Construction of Concrete Path | 1 | 1163175 | 720410 | 442765 | 644839 |  | 485000 | 1129839 | 644839 | 485000 | 100% | 100% | 109.5% | 97.13% | 100% | 2007-02-28 | n/a | 2008-05-05 | 2008-07-30 | no data | 86 | 204 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Canmangao | 071235008 | Construction of 2 Classroom School Building | 1 | 1476401 | 1249517.97 | 226883.03 | 1249517.97 | 3rd Tranche | 224088.57 | 1473606.54 | 1249517.97 | 224088.57 | 100% | 100% | 98.77% | 99.81% | 100% | 2005-07-29 | 2005-10-14 | 2006-01-16 | 2006-05-30 | 2006-07-12 | 134 | 166 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Gaus | 071235010 | Electrification | 1 | 2492804 | 1371866.73 | 1120937.27 | 1371866.73 | 3rd Tranche | 213040 | 1584906.73 | 1371866.73 | 213040 | 100% | 100% | 19.01% | 63.58% | 100% | 2005-07-29 | 2005-10-14 | 2006-01-11 | 2006-08-31 | 2006-11-29 | 232 | 191 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Lapinig | 071235012 | Electrification Project of Lapinig Island | 1 | 1029230 | 620546 | 408684 | 620546 |  | 511800 | 1132346.002 | 620546 | 511800.002 | 100% | 100% | 125.2% | 110% | 100% | 2007-02-28 | n/a | 2008-09-11 | 2009-03-25 | n/a | 195 | 190 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Lipata | 071235013 | Construction of Day Care Center | 1 | 630941 | 470550 | 160391 | 465118.67 |  | 140000 | 605118.67 | 465118.67 | 140000 | 100% | 100% | 87.29% | 95.91% | 100% | 2007-02-28 | n/a | 2008-05-15 | 2008-10-22 | no data | 160 | 140 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Eastern Cabul-an | 071209040 | Construction of Cause Way | 2 | 1851676 | 1666713.85 | 184962.15 | 1666662.53 |  | 201487.15 | 1868149.68 | 1666662.53 | 201487.15 | 100% | 100% | 108.9% | 100.9% | 100% | 2006-06-30 | n/a | 2006-12-04 | 2008-01-25 | no data | 417 | 584 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Carlos P. Garcia (Pitogo) | 071235 | Concrete Paving of .210Km Farm-to-Market Road | 1 | 1153932 | 858416.85 | 295515.15 | 858416.85 |  | 161360 | 1019776.85 | 858416.85 | 161360 | 100% | 100% | 54.6% | 88.37% | 100% | 2006-04-26 | n/a | 2006-11-14 | 2007-07-16 | no data | 244 | 473 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Popoo | 071235015 | Concrete Pavement of 300m and Resurfacing of 500m Farm-to-Market Road | 1 | 1647207 | 1332221.85 | 314985.15 | 1332221.85 | 1st Tranche | 345744.17 | 1677966.02 | 1332221.85 | 345744.17 | 100% | 100% | 109.8% | 101.9% | 100% | 2005-07-29 | 2005-10-14 | 2006-01-06 | 2006-11-15 | 2006-12-18 | 313 | 213 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Saguise | 071235016 | Electrification | 1 | 1353770 | 906625 | 447145 | 867336.8 |  | 128120 | 995456.8 | 867336.8 | 128120 | 100% | 100% | 28.65% | 73.53% | 100% | 2006-04-26 | n/a | 2006-11-10 | 2007-10-15 | no data | 339 | 50 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | San Jose | 071235017 | Construction of Concrete Path | 1 | 645356 | 430205 | 215151 | 430143.68 |  | 157000 | 587143.68 | 430143.68 | 157000 | 100% | 100% | 72.97% | 90.98% | 100% | 2007-02-28 | n/a | 2007-12-15 | 2008-06-30 | no data | 198 | 204 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | San Vicente | 071235024 | Construction of Concrete Path | 1 | 807781 | 480640 | 327141 | 475970.12 |  | 307000 | 782970.12 | 475970.12 | 307000 | 100% | 100% | 93.84% | 96.93% | 100% | 2007-02-28 | n/a | 2007-12-15 | 2008-06-30 | no data | 198 | 90 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Sto. Rosario - C2 | 071235018 | Concrete Paving & Resurfacing of Farm-to-Market Road cum Box Culvert | 2 | 2641776.21 | 2145502.9 | 496273.31 | 2126125.32 |  | 360030 | 2486155.32 | 2126125.32 | 360030 | 100% | 100% | 72.55% | 94.11% | 100% | 2006-04-26 | n/a | 2006-12-10 | 2007-10-15 | no data | 309 | 147 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Kabangkalan | 071235011 | Concrete Paving & Resurfacing of Farm-to-Market Road cum Box Culvert | 2 | 2641776.21 | 2145502.9 | 496273.31 | 2126125.32 |  | 360030 | 2486155.32 | 2126125.32 | 360030 | 100% | 100% | 72.55% | 94.11% | 100% | 2006-04-26 | n/a | 2006-12-10 | 2007-10-15 | no data | 309 | 147 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Tilmobo | 071235019 | Construction of Sea Wall | 1 | 675120 | 510630 | 164490 | 510630 |  | 120800 | 631430 | 510630 | 120800 | 100% | 100% | 73.44% | 93.53% | 100% | 2007-02-28 | n/a | 2008-06-01 | 2009-03-26 | n/a | 298 | 52 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Tugas | 071235020 | Construction of Sea Wall | 1 | 1227428 | 1018199.55 | 209228.45 | 1018199.55 | 3rd Tranche | 252056.29 | 1270255.84 | 1018199.55 | 252056.29 | 100% | 100% | 120.5% | 103.5% | 100% | 2005-07-29 | 2005-10-14 | 2006-01-03 | 2006-07-30 | 2006-08-24 | 208 | 154 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Tugnao | 071235021 | Construction of Concrete Path | 1 | 862185 | 602164 | 260021 | 575494 |  | 265359 | 840853 | 575494 | 265359 | 100% | 100% | 102.1% | 97.53% | 100% | 2007-02-28 | n/a | 2008-04-25 | 2008-06-28 | no data | 64 | 203 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Villa Milagrosa | 071235022 | Construction of 3 Classroom School Building | 1 | 2162224 | 1928193.9 | 234030.1 | 1928193.9 | 3rd Tranche | 219530 | 2147723.9 | 1928193.9 | 219530 | 100% | 100% | 93.8% | 99.33% | 100% | 2005-07-29 | 2005-10-14 | 2006-01-06 | 2006-04-06 | 2006-07-12 | 90 | 233 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Alegria | 071212001 | Rehabilitation/Improvement of Road with Sectional Conctreting | 1 | 2067651 | 1573431 | 494220 | 1572911.72 |  | 476073 | 2048984.72 | 1572911.72 | 476073 | 100% | 100% | 96.33% | 99.1% | 100% | 2007-03-20 | n/a | 2008-02-04 | 2008-07-30 | no data | 177 | 215 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Bicao | 071212002 | Improvement of Farm to Market Road | 1 | 1200135 | 882935 | 317200 | 771011 |  | 319220 | 1085296 | 771011 | 314285 | 100% | 98.45% | 100.6% | 90.43% | 100% | 2008-05-15 | n/a | 2008-09-04 | 2009-02-12 | n/a | 161 | 426 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Buenavista | 071212003 | Construction of Home Economics Building | 1 | 1081060 | 800570 | 280490 | 796946 |  | 274933.08 | 1071879.08 | 796946 | 274933.08 | 100% | 100% | 98.02% | 99.15% | 100% | 2008-05-15 | n/a | 2008-08-19 | 2008-11-30 | no data | 103 | 445 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Buenos Aires | 071212004 | Construction of Level II Wateworks System | 1 | 1483870 | 1021373 | 462497 | 919235.7 |  | 444934.55 | 1364170.25 | 919235.7 | 444934.55 | 100% | 100% | 96.2% | 91.93% | 100% | 2006-06-21 | n/a | 2006-10-06 | 2008-01-03 | no data | 454 | 140 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Calatrava | 071212005 | Construction of Water System Level II | 1 | 1195295 | 926220 | 269075 | 833598 |  | 247402.5 | 1081000.5 | 833598 | 247402.5 | 100% | 100% | 91.95% | 90.44% | 100% | 2008-05-15 | n/a | 2008-11-26 | 2009-08-28 | n/a | 275 | 110 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | El Progreso | 071212006 | Rehabilitaion / Improvement of Farm-to-Market Road | 1 | 2122471 | 1484982 | 637489 | 1336483.8 |  | 657484 | 1993967.8 | 1336483.8 | 657484 | 100% | 100% | 103.1% | 93.95% | 100% | 2006-06-21 | n/a | 2006-12-06 | 2008-04-26 | no data | 507 | 177 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | El Salvador | 071212007 | Concreting of Farm-to-Market Road | 1 | 1140679 | 699483 | 441196 | 699483 |  | 494727.25 | 1194210.25 | 699483 | 494727.25 | 100% | 100% | 112.1% | 104.7% | 100% | 2006-06-21 | n/a | 2006-09-26 | 2007-06-20 | no data | 267 | 120 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Guadalupe | 071212008 | Construction of Level II Wateworks System | 1 | 1575921 | 1091657 | 484264 | 1091657 |  | 490396.48 | 1582053.48 | 1091657 | 490396.48 | 100% | 100% | 101.3% | 100.4% | 100% | 2006-06-21 | n/a | 2006-10-02 | 2007-02-21 | 2007-02-22 | 142 | 155 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Guadalupe | 071212008 | Contruction of Barangay Health Station | 1 | 677279 | 266700.49 | 410578.51 | 240030.43 |  | 410734.77 | 684893.75 | 240030.43 | 444863.32 | 100% | 108.3% | 100% | 101.1% | 100% | 2007-03-20 | n/a | 2007-07-06 | 2008-12-12 | no data | 525 | 330 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Katipunan | 071212009 | Construction of 2 CL School Building | 1 | 1274308 | 980088 | 294220 | 882079.2 |  | 318320 | 1200399.2 | 882079.2 | 318320 | 100% | 100% | 108.2% | 94.2% | 100% | 2008-05-15 | n/a | 2008-08-04 | 2008-11-12 | no data | 100 | 470 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Libertad | 071212010 | Rehabilitaion / Improvement of Farm-to-Market Road | 1 | 1604335 | 1111550 | 492785 | 1104231.89 |  | 479627.5 | 1583859.39 | 1104231.89 | 479627.5 | 100% | 100% | 97.33% | 98.72% | 100% | 2006-06-21 | n/a | 2006-11-22 | 2008-06-28 | no data | 584 | 125 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Paz | 071212011 | Improvement of Farm to Market Road | 1 | 1156674 | 859117 | 297557 | 856406.31 |  | 309588.01 | 1165994.32 | 856406.31 | 309588.01 | 100% | 100% | 104% | 100.8% | 100% | 2008-05-15 | n/a | 2008-08-20 | 2008-12-20 | n/a | 122 | 276 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Salvacion | 071212012 | Construction of Level II Wateworks System | 1 | 1227500 | 842415 | 385085 | 842415 |  | 371779.5 | 1214194.5 | 842415 | 371779.5 | 100% | 100% | 96.54% | 98.92% | 100% | 2006-06-21 | n/a | 2006-10-02 | 2007-03-21 | 2007-04-28 | 170 | 89 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Salvacion | 071212012 | Improvement of Farm to Market Road | 1 | 1241631 | 975821 | 265810 | 889948.38 |  | 258050 | 1147871.18 | 889948.38 | 257922.8 | 100% | 99.95% | 97.08% | 92.45% | 100% | 2008-05-15 | n/a | 2008-09-10 | 2009-06-11 | n/a | 274 | 205 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Victoria | 071212013 | Construction of roadside protection of FMR | 1 | 446933 | 308592.1 | 138340.9 | 308592.1 |  | 145560 | 454152.1 | 308592.1 | 145560 | 100% | 100% | 105.2% | 101.6% | 100% | 2008-05-15 | n/a | 2009-03-23 | 2009-08-29 | n/a | 159 | 174 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Matin-ao | 071212014 | Construction of Water System Level II | 1 | 1204060 | 943715 | 260345 | 922824 |  | 243575 | 1166399 | 922824 | 243575 | 100% | 100% | 93.56% | 96.87% | 100% | 2008-05-15 | n/a | 2008-11-12 | 2009-06-11 | n/a | 211 | 159 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montehermoso | 071212015 | Improvement of Farm to Market Road | 1 | 1284813 | 860923 | 423890 | 855923 |  | 406261 | 1262184 | 855923 | 406261 | 100% | 100% | 95.84% | 98.24% | 100% | 2007-03-20 | n/a | 2007-06-24 | 2008-06-28 | no data | 370 | 176 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montesuerte | 071212016 | Construction of 2 CL School Building | 1 | 1274308 | 822508.1 | 451799.9 | 740257.29 |  | 438676.9 | 1178934.19 | 740257.29 | 438676.9 | 100% | 100% | 97.1% | 92.52% | 100% | 2008-05-15 | n/a | 2008-08-06 | 2008-11-10 | no data | 96 | 512 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montesunting | 071212017 | Rehabilitation/Improvement of Road with Sectional Conctreting | 1 | 2338155 | 1467455 | 870700 | 1403715.18 |  | 784474.25 | 2187649.43 | 1403715.18 | 783934.25 | 100% | 99.93% | 90.1% | 93.56% | 100% | 2007-03-20 | n/a | 2008-05-12 | 2009-04-30 | n/a | 353 | 162 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montevideo | 071212018 | Construction of Water System Level II | 1 | 1046989 | 627273 | 419716 | 618517.88 |  | 422846 | 1041363.88 | 618517.88 | 422846 | 100% | 100% | 100.7% | 99.46% | 100% | 2007-03-20 | n/a | 2007-07-01 | 2008-03-25 | no data | 268 | 229 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Nueva Fuerza | 071212019 | Construction of Water System Level II | 1 | 1234016 | 954136 | 279880 | 943715 |  | 243150 | 1186865 | 943715 | 243150 | 100% | 100% | 86.88% | 96.18% | 100% | 2008-05-15 | n/a | 2008-12-12 | 2009-04-30 | n/a | 139 | 140 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Nueva Vida Este | 071212020 | Construction of 2 CL High School Building | 1 | 1196744 | 730949 | 465795 | 657854.1 |  | 468985.53 | 1126839.63 | 657854.1 | 468985.53 | 100% | 100% | 100.7% | 94.16% | 100% | 2007-03-20 | n/a | 2007-07-03 | 2008-04-30 | no data | 302 | 193 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Nueva Vida Norte | 071212022 | Construction of 2 CL Elementary School Building | 1 | 1178738 | 682659 | 496079 | 614393.1 |  | 321881.02 | 936274.12 | 614393.1 | 321881.02 | 100% | 100% | 64.89% | 79.43% | 100% | 2007-03-20 | n/a | 2007-07-01 | 2008-06-28 | no data | 363 | 190 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Nueva Vida Sur | 071212021 | Construction of Birthing Center | 1 | 689776 | 321295 | 368481 | 289165.5 |  | 341120.38 | 630285.88 | 289165.5 | 341120.38 | 100% | 100% | 92.57% | 91.38% | 100% | 2007-03-20 | n/a | 2007-07-06 | 2008-06-28 | no data | 358 | 180 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Poblacion Norte | 071212023 | Improvement w/ Concreting of Box Culvert Approaches | 1 | 720256 | 319606 | 400650 | 319161 |  | 387533.75 | 706694.75 | 319161 | 387533.75 | 100% | 100% | 96.73% | 98.12% | 100% | 2007-03-20 | n/a | 2008-06-10 | 2009-04-29 | n/a | 323 | 521 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Poblacion Sur | 071212024 | Construction of 2 CL School Building | 1 | 1274308 | 554889.9 | 719418.1 | 443911.92 |  | 718438.1 | 1162350.02 | 443911.92 | 718438.1 | 100% | 100% | 99.86% | 91.21% | 100% | 2008-05-15 | n/a | 2008-07-23 | 2008-10-21 | no data | 90 | 513 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Tambo-an | 071212025 | Construction of Level II Wateworks System | 1 | 1387025 | 939441 | 447584 | 845496.9 |  | 553741 | 1399237.9 | 845496.9 | 553741 | 100% | 100% | 123.7% | 100.9% | 100% | 2006-06-21 | n/a | 2006-09-27 | 2007-03-21 | no data | 175 | 166 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Vallehermoso | 071212026 | Construction of Water System Level II | 1 | 1332293 | 856072.51 | 476220.49 | 770465.26 |  | 476260.75 | 1246726.01 | 770465.26 | 476260.75 | 100% | 100% | 100% | 93.58% | 100% | 2007-03-20 | n/a | 2007-06-27 | 2008-05-30 | no data | 338 | 348 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Villaflor | 071212027 | Construction of Water System Level II | 1 | 1154666 | 686519 | 468147 | 635133.46 |  | 415510.38 | 1050643.84 | 635133.46 | 415510.38 | 100% | 100% | 88.76% | 90.99% | 100% | 2007-03-20 | n/a | 2007-07-01 | 2008-05-30 | no data | 334 | 154 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Villafuerte | 071212028 | Improvement of Farm-to-Market Road | 1 | 2166635 | 1509099 | 657536 | 1509099 |  | 668386 | 2177485 | 1509099 | 668386 | 100% | 100% | 101.7% | 100.5% | 100% | 2006-06-21 | n/a | 2006-12-11 | 2007-03-20 | 2007-06-26 | 99 | 160 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Villafuerte | 071212028 | Contruction of Barangay Health Station | 1 | 697629 | 307117 | 390512 | 294992.15 |  | 400128.25 | 695120.4 | 294992.15 | 400128.25 | 100% | 100% | 102.5% | 99.64% | 100% | 2007-03-20 | n/a | 2007-05-24 | 2008-09-01 | no data | 466 | 200 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Carmen | 071212 | Villarcayo | 071212029 | Rehab./improvement with sectional concreting of farm to market road | 1 | 491193 | 308592.1 | 182600.9 | 277732.89 |  | 160370 | 438102.89 | 277732.89 | 160370 | 100% | 100% | 87.83% | 89.19% | 100% | 2008-05-15 | n/a | 2009-03-04 | 2009-06-30 | n/a | 118 | 359 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Cabatuan | 071218001 | Single Phase Line @ Sitio Rowena Heights, Cabatuan | 1 | 777723 | 550255 | 227468 | 495229.5 | 1st | 173790 | 669019.5 | 495229.5 | 173790 | 100% | 100% | 76.4% | 86.02% | 100% | 2009-02-06 | no data | 2009-05-27 | 2009-08-31 | n/a | 96 | 23 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Cantubod | 071218002 | Construction of Road Concreting cum Solar Drier | 1 | 730225 | 580815 | 149410 | 580815 |  | 64910 | 645725 | 580815 | 64910 | 100% | 100% | 43.44% | 88.43% | 100% | 2006-06-18 | n/a | 2006-10-02 | 2006-11-23 | 2006-11-22 | 52 | 175 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Cantubod | 071218002 | Purchase and Installation of Flat Bed Dryer | 1 | 576884 | 539444 | 37440 | 539444 | 1st | 38380 | 577824 | 539444 | 38380 | 100% | 100% | 102.5% | 100.2% | 100% | 2009-02-06 | no data | 2009-05-06 | 2009-06-23 | n/a | 48 | 109 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Carbon | 071218003 | Sustainability Agriculture Capability Building | 1 | 848372 | 341484.15 | 506887.85 | 273187.32 | 1st Tranche | 187280 | 460467.32 | 273187.32 | 187280 | 100% | 100% | 36.95% | 54.28% | 100% | 2005-07-07 | 2005-08-30 | 2004-11-25 | 2006-06-22 | 2006-06-22 | 574 | 102 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Carbon | 071218003 | Construction of Barangay Pathways | 1 | 543892 | 468642 | 75250 | 374913.6 | 1st | 59800 | 434713.6 | 374913.6 | 59800 | 100% | 100% | 79.47% | 79.93% | 100% | 2009-02-06 | no data | 2009-05-25 | 2009-07-07 | n/a | 43 | 105 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Concepcion | 071218004 | 2 Classroom School Building | 1 | 925000 | 671350 | 253650 | 671350 | 3rd Tranche | 293154 | 964504 | 671350 | 293154 | 100% | 100% | 115.6% | 104.3% | 100% | 2003-11-18 | 2004-02-03 | 2004-03-04 | 2004-06-18 | 2004-06-18 | 106 | 267 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Concepcion | 071218004 | Construction of Spillway (Rehabilitation & Extension) | 1 | 529789 | 446039 | 83750 | 356831.2 | 1st | 77164.2 | 433995.4 | 356831.2 | 77164.2 | 100% | 100% | 92.14% | 81.92% | 100% | 2009-02-06 | no data | 2009-04-28 | 2009-06-20 | n/a | 53 | 267 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Dagohoy | 071218005 | Construction of Dagohoy Water System | 1 | 2461000 | 1778946.25 | 682053.75 | 1601051.62 | 2nd Tranche | 465175.25 | 2066226.87 | 1601051.62 | 465175.25 | 100% | 100% | 68.2% | 83.96% | 100% | 2003-11-18 | 2004-02-03 | 2004-04-14 | 2005-01-26 | 2005-01-26 | 287 | 111 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Dagohoy | 071218005 | Construction of Day Care Center | 1 | 638275 | 568085 | 70190 | 511276.5 | 1st | 44298.5 | 555575 | 511276.5 | 44298.5 | 100% | 100% | 63.11% | 87.04% | 100% | 2009-02-06 | no data | 2009-04-29 | 2009-06-29 | n/a | 61 | 54 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Hibale | 071218006 | Construction of 2Classroom School Building | 1 | 1352867 | 991551.16 | 361315.84 | 991551.16 |  | 105560.84 | 1097112 | 991551.16 | 105560.84 | 100% | 100% | 29.22% | 81.1% | 100% | 2006-06-18 | n/a | 2006-09-15 | 2006-12-05 | 2006-12-05 | 81 | 159 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Hibale | 071218006 | Concreting of Hibale Farm-to-Market Road | 1 | 509914 | 432824 | 77090 | 389541.6 | 1st | 63930 | 453471.6 | 389541.6 | 63930 | 100% | 100% | 82.93% | 88.93% | 100% | 2009-02-06 | no data | 2009-05-22 | 2009-07-07 | n/a | 46 | 168 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Magtangtang | 071218007 | Capability Training | 1 | 355482 | 245680.35 | 109801.65 | 221112.32 |  | 81000 | 302112.32 | 221112.32 | 81000 | 100% | 100% | 73.77% | 84.99% | 100% | 2006-06-18 | n/a | 2006-10-19 | 2006-12-07 | 2006-11-22 | 49 | 102 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Magtangtang - C2 | 071218007 | Single Phase Line @ Sitio Hagimit, Pulang Yuta Magtangtang, San Jose Tabok, Danao | 2 | 1754665 | 1354886 | 399779 | 1336948.11 | 1st | 254144.09 | 1591092.2 | 1336948.11 | 254144.09 | 100% | 100% | 63.57% | 90.68% | 100% | 2009-02-06 | no data | 2009-05-30 | 2009-08-12 | n/a | 74 | 40 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Tabok | 071218015 | Single Phase Line @ Sitio Hagimit, Pulang Yuta Magtangtang, San Jose Tabok, Danao | 2 | 1754665 | 1354886 | 399779 | 1336948.11 | 1st | 254144.09 | 1591092.2 | 1336948.11 | 254144.09 | 100% | 100% | 63.57% | 90.68% | 100% | 2009-02-06 | no data | 2009-05-30 | 2009-08-12 | n/a | 74 | 40 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Nahud | 071218008 | Construction of Day Car Center | 1 | 771200 | 562195.01 | 209004.99 | 562195.01 |  | 175110.57 | 737305.58 | 562195.01 | 175110.57 | 100% | 100% | 83.78% | 95.6% | 100% | 2006-06-18 | n/a | 2006-09-05 | 2006-10-31 | 2006-11-03 | 56 | 127 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Nahud | 071218008 | Upgrading and Expansion of Nahud Level II Water System Project | 1 | 752641 | 657706 | 94935 | 656985.5 | 1st | 151375.26 | 808360.76 | 656985.5 | 151375.26 | 100% | 100% | 159.5% | 107.4% | 100% | 2009-02-06 | no data | 2009-05-08 | 2009-06-18 | n/a | 41 | 132 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Poblacion | 071218009 | Purchase of Multi-purpose Car | 1 | 510000 | 360000 | 150000 | 360000 |  | 151900 | 511900 | 360000 | 151900 | 100% | 100% | 101.3% | 100.4% | 100% | 2006-06-18 | n/a | 2007-02-08 | 2007-02-08 | no data | 0 | 512 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Poblacion | 071218009 | Purchase and Installation of Flat Bed Dryer | 1 | 573884 | 538414 | 35470 | 538414 | 1st | 53500 | 591914 | 538414 | 53500 | 100% | 100% | 150.8% | 103.1% | 100% | 2009-02-06 | no data | 2009-05-06 | 2009-06-21 | n/a | 46 | 523 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Remedios | 071218010 | Construction of 1 CL School Building | 1 | 635456 | 422193.38 | 213262.62 | 422193.38 | 3rd Tranche | 190833.5 | 613026.88 | 422193.38 | 190833.5 | 100% | 100% | 89.48% | 96.47% | 100% | 2005-07-07 | 2005-08-30 | 2005-10-15 | 2006-03-17 | 2006-03-17 | 153 | 182 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Remedios | 071218010 | Construction of Solar Drier | 1 | 200204 | 156684 | 43520 | 156016.45 | 1st | 49012.35 | 205028.8 | 156016.45 | 49012.35 | 100% | 100% | 112.6% | 102.4% | 100% | 2009-02-06 | no data | 2009-04-27 | 2009-06-17 | n/a | 51 | 215 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | San Carlos | 071218011 | Construction of Level II Waterworks System | 1 | 1347703 | 840228.15 | 507474.85 | 756205.34 |  | 441924.25 | 1198129.59 | 756205.34 | 441924.25 | 100% | 100% | 87.08% | 88.9% | 100% | 2006-06-18 | n/a | 2006-09-20 | 2006-12-07 | 2006-11-07 | 78 | 212 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | San Carlos | 071218011 | Construction of Spillway | 1 | 549824 | 459324 | 90500 | 413391.6 |  | 115570 | 528961.6 | 413391.6 | 115570 | 100% | 100% | 127.7% | 96.21% | 100% | 2009-02-06 | no data | 2009-05-25 | 2009-07-03 | n/a | 39 | 78 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | San Miguel | 071218012 | Construction of Health Station | 1 | 767765 | 532313.34 | 235451.66 | 479082 |  | 113901.3 | 592983.3 | 479082 | 113901.3 | 100% | 100% | 48.38% | 77.24% | 100% | 2006-06-18 | n/a | 2006-09-20 | 2006-11-23 | 2006-11-23 | 64 | 87 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | San Miguel | 071218012 | Construction of Spillway (Rehabilitation & Extension) | 1 | 501516 | 424046 | 77470 | 381641.4 | 1st | 73652.85 | 455294.25 | 381641.4 | 73652.85 | 100% | 100% | 95.07% | 90.78% | 100% | 2009-02-06 | no data | 2009-05-01 | 2009-06-27 | n/a | 57 | 78 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Sta. Fe | 071218013 | Construction of 1 CL School Building | 1 | 644075 | 459545.43 | 184529.57 | 459545.43 | 3rd Tranche | 183125 | 642670.43 | 459545.43 | 183125 | 100% | 100% | 99.24% | 99.78% | 100% | 2005-07-07 | 2005-08-30 | 2005-10-15 | 2006-02-03 | 2006-02-03 | 111 | 88 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Sta. Fe | 071218013 | Construction of Day care Center | 1 | 638275 | 568085 | 70190 | 511276.5 | 1st | 43330 | 554606.5 | 511276.5 | 43330 | 100% | 100% | 61.73% | 86.89% | 100% | 2009-02-06 | no data | 2009-05-18 | 2009-06-29 | n/a | 42 | 38 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Sto. Nino | 071218014 | Construction of Solar Drier | 1 | 320451 | 276931 | 43520 | 267511.55 | 1st | 56938.03 | 324449.58 | 267511.55 | 56938.03 | 100% | 100% | 130.8% | 101.2% | 100% | 2009-02-06 | no data | 2009-04-27 | 2009-06-18 | n/a | 52 | 176 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Sto. Niño | 071218014 | Construction Communal Irrigation | 1 | 1358007 | 987217 | 370790 | 888495.3 |  | 231700 | 1120195.3 | 888495.3 | 231700 | 100% | 100% | 62.49% | 82.49% | 100% | 2006-06-18 | n/a | 2006-10-19 | 2008-07-02 | no data | 622 | 144 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Tabok | 071218015 | Construction of 1 CL School Building | 1 | 669975 | 528445.43 | 141529.57 | 528445.43 | 3rd Tranche | 114190 | 642635.43 | 528445.43 | 114190 | 100% | 100% | 80.68% | 95.92% | 100% | 2005-07-07 | 2005-08-30 | 2005-10-15 | 2006-02-03 | 2006-02-03 | 111 | 152 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Tabok - C3 | 071218015 | Construction of Water System | 3 | 3555545 | 2649703.75 | 905841.25 | 2649703.75 | 3rd Tranche | 1016602.5 | 3666306.25 | 2649703.75 | 1016602.5 | 100% | 100% | 112.2% | 103.1% | 100% | 2003-11-18 | 2004-02-03 | 2004-04-12 | 2005-03-31 | 2005-03-31 | 353 | 531 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Cantubod | 071218002 | Construction of Water System | 3 | 3555545 | 2649703.75 | 905841.25 | 2649703.75 | 3rd Tranche | 1016602.5 | 3666306.25 | 2649703.75 | 1016602.5 | 100% | 100% | 112.2% | 103.1% | 100% | 2003-11-18 | 2004-02-03 | 2004-04-12 | 2005-03-31 | 2005-03-31 | 353 | 531 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Remedios | 071218010 | Construction of Water System | 3 | 3555545 | 2649703.75 | 905841.25 | 2649703.75 | 3rd Tranche | 1016602.5 | 3666306.25 | 2649703.75 | 1016602.5 | 100% | 100% | 112.2% | 103.1% | 100% | 2003-11-18 | 2004-02-03 | 2004-04-12 | 2005-03-31 | 2005-03-31 | 353 | 531 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Taming | 071218016 | Taming Level II Water System | 1 | 2328488 | 1401491.73 | 926996.27 | 1401491.73 | 3rd Tranche | 429306.95 | 1830798.68 | 1401491.73 | 429306.95 | 100% | 100% | 46.31% | 78.63% | 100% | 2005-07-07 | 2005-08-30 | 2005-10-15 | 2006-11-30 | 2006-11-30 | 411 | 148 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Taming | 071218016 | Construction of Barangay Health Station | 1 | 704235 | 629745 | 74490 | 566770.5 | 1st | 29795.16 | 596565.66 | 566770.5 | 29795.16 | 100% | 100% | 40% | 84.71% | 100% | 2009-02-06 | no data | 2009-04-28 | 2009-07-07 | n/a | 70 | 52 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Villa Anunciado | 071218017 | Improvements & Opening of 1.85KM Farm to Market Road | 1 | 2228734 | 1946839.88 | 281894.12 | 1946839.88 | 1st Tranche | 133750 | 2080589.88 | 1946839.88 | 133750 | 100% | 100% | 47.45% | 93.35% | 100% | 2005-07-07 | 2005-08-30 | 2005-11-15 | 2006-11-30 | 2006-12-06 | 380 | 33 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Danao | 071218 | Villa Anunciado | 071218017 | Construction of Barangay Pathways | 1 | 494820 | 428890 | 65930 | 386001 | 1st | 57697.05 | 443698.05 | 386001 | 57697.05 | 100% | 100% | 87.51% | 89.67% | 100% | 2009-02-06 | no data | 2009-05-04 | 2009-06-26 | n/a | 53 | 32 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Alumar | 071226001 | Concreting of Pathway | 1 | 1031144 | 668464 | 362680 | 645069.44 |  | 315130 | 960199.44 | 645069.44 | 315130 | 100% | 100% | 86.89% | 93.12% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2007-12-05 | no data | 187 | 138 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Banacon Island | 071226002 | Electrification of Banacon Island (Generator Set) | 1 | 3809995 | 2357303.65 | 1452691.35 | 2357303.65 | 1st Tranche | 962480.35 | 3319784 | 2357303.65 | 962480.35 | 100% | 100% | 66.25% | 87.13% | 100% | 2005-07-16 | 2005-09-09 | 2006-03-01 | 2006-10-31 | 2006-11-28 | 244 | 279 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Buyog | 071226003 | Installation of Buyog Level II Waterworks System | 1 | 1026913 | 697662 | 329251 | 697662 |  | 316530 | 1014192 | 697662 | 316530 | 100% | 100% | 96.14% | 98.76% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2008-05-16 | no data | 350 | 129 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Cabasakan | 071226004 | Electrification Expansion Project | 1 | 2163309 | 1050239 | 1113070 | 1050239 |  | 752281 | 1802520 | 1050239 | 752281 | 100% | 100% | 67.59% | 83.32% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2009-02-18 | n/a | 628 | 218 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Campao Occidental | 071226006 | Concreting and Regraveling of Campao Occidental FMR | 1 | 1510548 | 1138568.04 | 371979.96 | 1138568.04 | 3rd Tranche | 516059.81 | 1654627.85 | 1138568.04 | 516059.81 | 100% | 100% | 138.7% | 109.5% | 100% | 2005-07-16 | 2005-09-09 | 2006-03-02 | 2006-11-30 | 2007-02-09 | 273 | 75 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Campao Oriental | 071226007 | Installation of Campao Oriental Level II Waterworks System | 1 | 2105887 | 1838910.3 | 266976.7 | 1838910.3 | 3rd Tranche | 278379.86 | 2117290.16 | 1838910.3 | 278379.86 | 100% | 100% | 104.3% | 100.5% | 100% | 2005-07-16 | 2005-09-09 | 2006-03-01 | 2006-11-30 | 2006-11-30 | 274 | 165 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Cangmundo | 071226008 | Upgrading and Expansion of Level II Waterworks System | 1 | 1313092 | 916912 | 396180 | 916912 |  | 399156.79 | 1316068.79 | 916912 | 399156.79 | 100% | 100% | 100.8% | 100.2% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2008-04-25 | no data | 329 | 173 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Carlos P. Garcia | 071226009 | Installation of Level I Waterworks System | 1 | 1083074 | 780994 | 302080 | 780994 |  | 293242.49 | 1074236.49 | 780994 | 293242.49 | 100% | 100% | 97.07% | 99.18% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2007-10-12 | 2007-10-19 | 375 | 111 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Corte Baud | 071226010 | Construction of Fish Port | 1 | 441557 | 227897 | 213660 | 227897 |  | 296503.28 | 524400.28 | 227897 | 296503.28 | 100% | 100% | 138.8% | 118.8% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2007-01-31 | 2007-02-08 | 121 | 132 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Corte Baud | 071226010 | Extension of Fish Landing | 1 | 618577 | 370417 | 248160 | 370417 |  | 242310 | 612727 | 370417 | 242310 | 100% | 100% | 97.64% | 99.05% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2007-12-22 | no data | 204 | 128 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Handumon | 071226011 | Upgrading and Expansion of Level II Waterworks System | 1 | 1439424 | 995119 | 444305 | 995119 |  | 238538.81 | 1233657.81 | 995119 | 238538.81 | 100% | 100% | 53.69% | 85.7% | 100% | 2006-06-19 | n/a | 2007-03-23 | 2009-08-26 | n/a | 887 | 138 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Jagoliao | 071226012 | Construction of Fish Port | 1 | 1233483 | 768223 | 465260 | 768223 |  | 563960.8 | 1332183.8 | 768223 | 563960.8 | 100% | 100% | 121.2% | 108% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2007-02-02 | 2007-02-08 | 123 | 255 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Jandayan Norte | 071226013 | Electrification (Generator Set) | 1 | 1941766 | 1239166 | 702600 | 1239166 |  | 176850 | 1416016 | 1239166 | 176850 | 100% | 100% | 25.17% | 72.92% | 100% | 2006-06-19 | n/a | 2007-03-23 | 2008-09-20 | no data | 547 | 140 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Jandayan Sur | 071226013 | Electrification (Genset 35KVA) | 1 | 1656352 | 991522 | 664830 | 991522 |  | 529280 | 1520802 | 991522 | 529280 | 100% | 100% | 79.61% | 91.82% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2008-09-20 | no data | 477 | 272 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Mahanay Island | 071226015 | Installation of Mahanay Level I Waterworks | 1 | 693721 | 541961 | 151760 | 541961 | 1st Tranche | 204760 | 746721 | 541961 | 204760 | 100% | 100% | 134.9% | 107.6% | 100% | 2005-07-16 | 2005-09-09 | 2006-05-15 | 2006-11-28 | 2006-11-30 | 197 | 73 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Nasingin | 071226016 | Construction of Daycare Center | 1 | 985189 | 670329 | 314860 | 670329 |  | 283960 | 954289 | 670329 | 283960 | 100% | 100% | 90.19% | 96.86% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2007-09-30 | 2007-10-19 | 121 | 340 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Pandanon | 071226017 | Fabrication of MALTABANA Rainwater Collector | 1 | 1146074 | 635714.95 | 510359.05 | 635714.95 | 3rd Tranche | 510617.5 | 1146332.45 | 635714.95 | 510617.5 | 100% | 100% | 100.1% | 100% | 100% | 2005-07-16 | 2005-09-09 | 2006-03-06 | 2006-10-16 | 2006-11-28 | 224 | 369 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Poblacion | 071226018 | Construction of Poblacion Training Center | 1 | 875003 | 687542.06 | 187460.94 | 687542.06 | 3rd Tranche | 189673.29 | 877215.35 | 687542.06 | 189673.29 | 100% | 100% | 101.2% | 100.3% | 100% | 2005-07-16 | 2005-09-09 | 2006-06-19 | 2006-10-11 | 2006-10-11 | 114 | 421 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Saguise | 071226019 | Construction of 1-Classroom School Building | 1 | 763476 | 521890 | 241586 | 521890 |  | 306082.07 | 827972.07 | 521890 | 306082.07 | 100% | 100% | 126.7% | 108.4% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2006-11-30 | 2006-12-07 | 59 | 287 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Salog | 071226020 | Installation of Level II Waterworks System | 1 | 1683560 | 1173380 | 510180 | 1173380 |  | 475388.52 | 1648768.52 | 1173380 | 475388.52 | 100% | 100% | 93.18% | 97.93% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2008-06-25 | no data | 390 | 185 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | San Jose | 071226021 | Installation of Level I Waterworks System | 1 | 1106547 | 779468 | 327079 | 779468 |  | 344529.74 | 1123997.74 | 779468 | 344529.74 | 100% | 100% | 105.3% | 101.6% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2007-11-30 | no data | 424 | 111 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Sto. Niño | 071226022 | Installation of Level I Waterworks System | 1 | 1100326 | 777246 | 323080 | 777246 |  | 260530 | 1037776 | 777246 | 260530 | 100% | 100% | 80.64% | 94.32% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2007-09-30 | 2007-10-18 | 363 | 111 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Taytay | 071226023 | Construction of 1-Classroom School Building | 1 | 769591 | 520547 | 249044 | 520547 |  | 268248.17 | 788795.17 | 520547 | 268248.17 | 100% | 100% | 107.7% | 102.5% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2006-11-30 | 2006-12-07 | 59 | 229 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Tugas | 071226024 | Upgrading and Expansion of Level II Waterworks System | 1 | 1102934 | 661075 | 441859 | 661075 |  | 375659 | 1036734 | 661075 | 375659 | 100% | 100% | 85.02% | 94% | 100% | 2007-02-26 | n/a | 2007-06-01 | 2007-10-30 | no data | 151 | 155 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Getafe | 071226 | Tulang | 071226025 | Construction of Health Station | 1 | 923810 | 589450 | 334360 | 589450 |  | 523222.77 | 1112672.77 | 589450 | 523222.77 | 100% | 100% | 156.5% | 120.4% | 100% | 2006-06-19 | n/a | 2006-10-02 | 2007-02-05 | 2007-02-09 | 126 | 284 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Abaca | 071231001 | Construction of Single Box Culvert | 1 | 1353900 | 1010460 | 343440 | 997725 |  | 340890.72 | 1338615.72 | 997725 | 340890.72 | 100% | 100% | 99.26% | 98.87% | 100% | 2007-02-17 | n/a | 2007-07-23 | 2008-03-15 | no data | 236 | 442 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Abad Santos | 071231002 | Rehabilitation of Farm to Market Road | 1 | 896200 | 586785 | 309415 | 586785 |  | 286537.65 | 873322.65 | 586785 | 286537.65 | 100% | 100% | 92.61% | 97.45% | 100% | 2007-02-17 | n/a | 2008-06-01 | 2008-12-19 | no data | 201 | 120 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Aguipo - C3 | 071231003 | Water Works System L2 (cluster with San Roque and San Isidro) | 3 | 5200428 | 3005679 | 2194749 | 3005679 |  | 2135309.06 | 5140988.06 | 3005679 | 2135309.06 | 100% | 100% | 97.29% | 98.86% | 100% | 2008-05-16 | n/a | 2008-07-16 | 2009-06-10 | n/a | 329 | 980 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Isidro | 071231017 | Water Works System L2 (cluster with San Roque and San Isidro) | 3 | 5200428 | 3005679 | 2194749 | 3005679 |  | 2135309.06 | 5140988.06 | 3005679 | 2135309.06 | 100% | 100% | 97.29% | 98.86% | 100% | 2008-05-16 | n/a | 2008-07-16 | 2009-06-10 | n/a | 329 | 980 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Roque (Cabulao) | 071231020 | Water Works System L2 (cluster with San Roque and San Isidro) | 3 | 5200428 | 3005679 | 2194749 | 3005679 |  | 2135309.06 | 5140988.06 | 3005679 | 2135309.06 | 100% | 100% | 97.29% | 98.86% | 100% | 2008-05-16 | n/a | 2008-07-16 | 2009-06-10 | n/a | 329 | 980 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Baybayon | 071231005 | Upgrading and Expansion of Level II Waterworks System | 1 | 1366617 | 1059506.14 | 307110.86 | 953555.53 |  | 331945.82 | 1285501.35 | 953555.53 | 331945.82 | 100% | 100% | 108.1% | 94.06% | 100% | 2006-07-15 | n/a | 2006-10-25 | 2008-05-09 | no data | 562 | 280 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Bulawan | 071231006 | Asphalting of Farm-to-Market Road | 1 | 1215369 | 940600.48 | 274768.52 | 912596.63 |  | 283591.56 | 1196188.19 | 912596.63 | 283591.56 | 100% | 100% | 103.2% | 98.42% | 100% | 2006-07-15 | n/a | 2006-11-08 | 2008-02-20 | no data | 469 | 119 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Cabidian | 071231007 | Asphalting of Farm-to-Market Road | 1 | 1189251 | 940071.93 | 249179.07 | 846064.73 |  | 236999.11 | 1083063.84 | 846064.73 | 236999.11 | 100% | 100% | 95.11% | 91.07% | 100% | 2006-07-15 | n/a | 2006-11-07 | 2008-06-30 | no data | 601 | 225 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Cawayanan | 071231009 | Water Works System L2 | 1 | 1183077 | 810657 | 372420 | 729591.3 |  | 359920 | 1089511.3 | 729591.3 | 359920 | 100% | 100% | 96.64% | 92.09% | 100% | 2007-02-17 | n/a | 2007-09-05 | 2008-03-15 | no data | 192 | 314 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Concepcion | 071231004 | Upgrading and Expansion of Level II Waterworks System | 1 | 1192332 | 801582.37 | 390749.63 | 767751.1 |  | 395142.63 | 1162893.73 | 767751.1 | 395142.63 | 100% | 100% | 101.1% | 97.53% | 100% | 2006-07-15 | n/a | 2006-10-25 | 2007-07-21 | no data | 269 | 189 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Del Mar | 071231010 | Upgrading and Expansion of Level II Waterworks System | 1 | 1400284.99 | 1016350.98 | 383934.01 | 986350.97 |  | 410899.81 | 1397250.78 | 986350.97 | 410899.81 | 100% | 100% | 107% | 99.78% | 100% | 2006-07-15 | n/a | 2006-10-23 | 2008-06-30 | no data | 616 | 138 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Lungsoda-an | 071231011 | Concrete Paving of Farm to Market Road | 1 | 1014219 | 689219 | 325000 | 689219 |  | 228600 | 917819 | 689219 | 228600 | 100% | 100% | 70.34% | 90.5% | 100% | 2008-05-16 | n/a | 2008-08-01 | 2008-09-26 | no data | 56 | 201 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Marcelo | 071231012 | Asphalting of Farm-to-Market Road | 1 | 1256653 | 940004.38 | 316648.62 | 912067.38 |  | 328695.06 | 1240762.44 | 912067.38 | 328695.06 | 100% | 100% | 103.8% | 98.74% | 100% | 2006-07-15 | n/a | 2006-11-07 | 2008-11-25 | no data | 749 | 164 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Minol | 071231013 | Construction of Single Barrel Box Culvert | 1 | 917679 | 638024 | 279655 | 638024 |  | 411971.34 | 1049995.34 | 638024 | 411971.34 | 100% | 100% | 147.3% | 114.4% | 100% | 2008-05-16 | n/a | 2008-08-18 | 2008-11-24 | no data | 98 | 442 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Paraiso | 071231014 | Water Works System L2 | 1 | 1319969 | 826744 | 493225 | 807204 |  | 493228.4 | 1300432.4 | 807204 | 493228.4 | 100% | 100% | 100% | 98.52% | 100% | 2007-02-17 | n/a | 2007-06-23 | 2008-02-15 | no data | 237 | 145 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Poblacion I | 071231015 | Mini Fish Port | 1 | 1460122 | 1110122 | 350000 | 1110122 |  | 332714 | 1442836 | 1110122 | 332714 | 100% | 100% | 95.06% | 98.82% | 100% | 2008-05-16 | n/a | 2008-07-28 | 2008-11-24 | no data | 119 | 264 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Poblacion II | 071231016 | Asphaliting of Farm to Market Road | 1 | 1496956 | 1156956 | 340000 | 1156956 |  | 312360.2 | 1469316.2 | 1156956 | 312360.2 | 100% | 100% | 91.87% | 98.15% | 100% | 2008-05-16 | n/a | 2008-07-25 | 2009-01-28 | no data | 187 | 244 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Poblacion II | 071231016 | Construction of Birthing Center | 1 | 943380 | 575100.5 | 368279.5 | 560966.37 |  | 354589.5 | 915555.87 | 560966.37 | 354589.5 | 100% | 100% | 96.28% | 97.05% | 100% | 2008-05-16 | n/a | 2008-11-03 | 2009-04-28 | n/a | 176 | 244 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Jose | 071231018 | Water Works System L2 | 1 | 1278071 | 992000 | 286071 | 992000 |  | 274162 | 1266162 | 992000 | 274162 | 100% | 100% | 95.84% | 99.07% | 100% | 2007-02-17 | n/a | 2007-10-19 | 2008-09-26 | no data | 343 | 194 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Rafael | 071231019 | Upgrading and Expansion of Level II Waterworks System | 1 | 1176933.99 | 901883.72 | 275050.27 | 811695.35 |  | 301942.39 | 1113637.74 | 811695.35 | 301942.39 | 100% | 100% | 109.8% | 94.62% | 100% | 2006-07-15 | n/a | 2006-10-25 | 2007-02-20 | 2007-08-07 | 118 | 132 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Tambo | 071231021 | Rehabilitation of Farm to Market Road | 1 | 1545169 | 1033544 | 511625 | 1033544 |  | 448328.5 | 1481872.5 | 1033544 | 448328.5 | 100% | 100% | 87.63% | 95.9% | 100% | 2007-02-17 | n/a | 2008-06-01 | 2008-12-19 | no data | 201 | 168 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Tangkigan | 071231022 | Water Works System L2 | 1 | 1095209 | 764355 | 330854 | 687919.5 |  | 339604 | 1027523.5 | 687919.5 | 339604 | 100% | 100% | 102.6% | 93.82% | 100% | 2007-02-17 | n/a | 2007-08-27 | 2008-03-15 | no data | 201 | 303 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Mabini | 071231 | Valaga | 071231023 | Water Works System L2 | 1 | 835087 | 575455 | 259632 | 572125 |  | 296972.2 | 869097.2 | 572125 | 296972.2 | 100% | 100% | 114.4% | 104.1% | 100% | 2007-02-17 | n/a | 2007-06-22 | 2007-09-20 | no data | 90 | 145 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Aurora | 071234001 | Improvement of 1 km Farm to Market Road | 1 | 1026839 | 390738.95 | 636100.05 | 375811.36 |  | 644615.5 | 1020426.86 | 375811.36 | 644615.5 | 100% | 100% | 101.3% | 99.38% | 100% | 2007-02-16 | n/a | 2007-05-11 | 2008-06-25 | no data | 411 | 72 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Bagacay | 071234002 | Construction of Level II Water System | 1 | 1274115 | 734274.26 | 539840.74 | 660846.84 |  | 552930.38 | 1213777.22 | 660846.84 | 552930.38 | 100% | 100% | 102.4% | 95.26% | 100% | 2007-02-16 | n/a | 2007-06-25 | 2007-10-05 | 2007-10-09 | 102 | 204 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Bagumbayan | 071234003 | Improvement of 1.3 Km Farm to Market Road | 1 | 1436502 | 663387.42 | 773114.58 | 650637.42 |  | 829108.99 | 1479746.41 | 650637.42 | 829108.99 | 100% | 100% | 107.2% | 103% | 100% | 2007-02-16 | n/a | 2007-06-08 | 2008-06-25 | no data | 383 | 254 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Bayong | 071234004 | Farm-to-Market Road | 1 | 937392 | 450931.62 | 486460.38 | 450931.62 | 1st Tranche | 472330 | 923261.62 | 450931.62 | 472330 | 100% | 100% | 97.1% | 98.49% | 100% | 2006-06-09 | n/a | 2006-10-13 | 2007-03-23 | 2007-03-29 | 161 | 280 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Buenasuerte | 071234005 | Improvement of 1.3 Km Farm to Market Road | 1 | 928929 | 404728.43 | 524200.57 | 323782.74 |  | 1086635 | 1410417.74 | 323782.74 | 1086635 | 100% | 100% | 207.3% | 151.8% | 100% | 2007-02-16 | n/a | 2007-06-08 | 2008-06-28 | no data | 386 | 149 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Cagawasan | 071234006 | Construction of 2 CL School Building | 1 | 1244216 | 636851.85 | 607364.15 | 573166.66 |  | 587472.15 | 1160638.81 | 573166.66 | 587472.15 | 100% | 100% | 96.72% | 93.28% | 100% | 2007-02-16 | n/a | 2007-04-12 | 2007-09-30 | no data | 171 | 153 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Cagawasan | 071234006 | Barangay Health Station | 1 | 775631 | 406690.35 | 368940.65 | 366021.31 |  | 356760 | 722781.31 | 366021.31 | 356760 | 100% | 100% | 96.7% | 93.19% | 100% | 2008-05-28 | n/a | 2008-08-19 | 2008-12-22 | no data | 125 | 184 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Cansungay | 071234007 | Improvement of 1 Km Farm-to-Market Road | 1 | 1414471 | 789410.08 | 625060.92 | 710469.07 |  | 606749.33 | 1317218.4 | 710469.07 | 606749.33 | 100% | 100% | 97.07% | 93.12% | 100% | 2006-06-09 | n/a | 2006-10-13 | 2007-03-27 | 2007-03-29 | 165 | 155 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Cansungay | 071234007 | Hat-Mat Weaving | 1 | 929022 | 530002 | 399020 | 477001.8 |  | 377560 | 854561.8 | 477001.8 | 377560 | 100% | 100% | 94.62% | 91.99% | 100% | 2008-05-28 | n/a | 2008-08-19 | 2008-12-20 | no data | 123 | 150 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Catagda-an | 071234008 | Improvement of 950 M Farm-to-Market Road | 1 | 978412 | 532351.58 | 446060.42 | 532351.58 | 1st Tranche | 559990 | 1092341.58 | 532351.58 | 559990 | 100% | 100% | 125.5% | 111.6% | 100% | 2006-06-09 | n/a | 2006-10-13 | 2007-03-23 | 2007-03-29 | 161 | 271 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Del Pilar | 071234009 | Construction of Box Culvert | 1 | 1253650 | 747189.03 | 506460.97 | 747189.03 | 1st Tranche | 660960 | 1408149.03 | 747189.03 | 660960 | 100% | 100% | 130.5% | 112.3% | 100% | 2006-06-09 | n/a | 2006-10-13 | 2007-02-08 | 2007-02-09 | 118 | 151 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Del Pilar | 071234009 | Construction of HE Building | 1 | 975873 | 567028 | 408845 | 567028 |  | 406792 | 973820 | 567028 | 406792 | 100% | 100% | 99.5% | 99.79% | 100% | 2008-05-28 | n/a | 2008-09-15 | 2008-12-22 | no data | 98 | 163 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Estaca | 071234010 | Construction of 3-Classroom School Building | 1 | 1606628 | 1065907.69 | 540720.31 | 1065907.69 | 1st Tranche | 515995 | 1581902.69 | 1065907.69 | 515995 | 100% | 100% | 95.43% | 98.46% | 100% | 2006-06-09 | n/a | 2006-10-17 | 2006-12-27 | 2006-12-27 | 71 | 484 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Estaca | 071234010 | Construction of Solar Drier | 1 | 688569 | 406288.18 | 282280.82 | 406288.18 |  | 285040 | 691328.18 | 406288.18 | 285040 | 100% | 100% | 101% | 100.4% | 100% | 2008-05-28 | n/a | 2008-11-05 | 2008-12-20 | no data | 45 | 525 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Ilaud | 071234011 | Construction of Level II Water System | 1 | 1290635 | 600032.54 | 690602.46 | 597330.19 |  | 635252 | 1232582.19 | 597330.19 | 635252 | 100% | 100% | 91.99% | 95.5% | 100% | 2007-02-16 | n/a | 2007-06-15 | 2008-10-31 | no data | 504 | 176 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Inaghuban | 071234012 | Improvement of Barangay Market | 1 | 1162403 | 521065.22 | 641337.78 | 416852.18 |  | 646154.66 | 1063006.84 | 416852.18 | 646154.66 | 100% | 100% | 100.8% | 91.45% | 100% | 2007-02-16 | n/a | 2007-06-04 | 2008-06-28 | no data | 390 | 194 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | La Suerte | 071234013 | Construction of Level II Water System | 1 | 789213 | 232012.95 | 557200.05 | 208811.65 |  | 559569.55 | 768381.2 | 208811.65 | 559569.55 | 100% | 100% | 100.4% | 97.36% | 100% | 2007-02-16 | n/a | 2007-06-15 | 2008-02-15 | no data | 245 | 125 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | La Suerte | 071234013 | Construction of 2 CL School Building | 1 | 1287049 | 753297.33 | 533751.67 | 753297.33 |  | 528677.65 | 1281974.98 | 753297.33 | 528677.65 | 100% | 100% | 99.05% | 99.61% | 100% | 2008-05-28 | n/a | 2008-09-15 | 2009-02-15 | n/a | 153 | 142 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Lumbay | 071234014 | Improvement of 750 m Farm to Road | 1 | 1388655 | 546166.76 | 842488.24 | 526484.58 |  | 805550.72 | 1332035.3 | 526484.58 | 805550.72 | 100% | 100% | 95.62% | 95.92% | 100% | 2007-02-16 | n/a | 2007-05-17 | 2008-06-24 | no data | 404 | 195 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Lumbay | 071234014 | Organic Fertilizer Production | 1 | 624150 | 317809.4 | 306340.6 | 286028.46 |  | 326060 | 612088.46 | 286028.46 | 326060 | 100% | 100% | 106.4% | 98.07% | 100% | 2008-05-28 | n/a | 2008-11-08 | 2009-03-17 | n/a | 129 | 189 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Lundag | 071234015 | Improvement of 1 km Farm to Market Road | 1 | 1287400 | 537199.55 | 750200.45 | 518758.4 |  | 748341.85 | 1267100.25 | 518758.4 | 748341.85 | 100% | 100% | 99.75% | 98.42% | 100% | 2007-02-16 | n/a | 2007-06-15 | 2008-06-25 | no data | 376 | 172 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Pamacsalan | 071234016 | Installation of Level II Waterworks System | 1 | 1472435 | 965414.14 | 507020.86 | 965414.14 | 1st Tranche | 542700 | 1508114.14 | 965414.14 | 542700 | 100% | 100% | 107% | 102.4% | 100% | 2006-06-09 | n/a | 2006-10-17 | 2006-12-28 | 2006-12-28 | 72 | 122 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Poblacion | 071234017 | Construction of Support Facility Building | 1 | 1203861 | 622010.09 | 581850.91 | 559809.08 |  | 553813.42 | 1113622.5 | 559809.08 | 553813.42 | 100% | 100% | 95.18% | 92.5% | 100% | 2007-02-16 | n/a | 2007-04-27 | 2007-10-22 | 2007-10-25 | 178 | 446 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Poblacion | 071234017 | Eco-tourism: Ride for Life | 1 | 4654963 | 2537213 | 2117750 | 2283491.7 |  | 2337652 | 2630312.45 | 1879164.45 | 751148 | 82.29% | 32.13% | 110.4% | 56.51% | 100% | 2008-05-28 | n/a | 2009-04-06 | 2010-05-31 | n/a | 420 | 520 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | Rizal | 071234018 | Farm-to-Market Road | 1 | 1976414 | 1149991.02 | 826422.98 | 1149991.02 |  | 1126162.81 | 2276153.83 | 1149991.02 | 1126162.81 | 100% | 100% | 136.3% | 115.2% | 100% | 2006-06-09 | n/a | 2007-01-29 | 2007-07-18 | 2007-07-20 | 170 | 267 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Carlos | 071234019 | Construction of Health Station | 1 | 822832 | 411531.98 | 411300.02 | 329225.58 |  | 352930.62 | 682156.2 | 329225.58 | 352930.62 | 100% | 100% | 85.81% | 82.9% | 100% | 2007-02-16 | n/a | 2007-04-12 | 2007-10-05 | no data | 176 | 165 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Isidro | 071234020 | Acquisition of 1-unit Ambulance with Accessories | 1 | 910878 | 446878 | 464000 | 357502.4 |  | 487754 | 845256.4 | 357502.4 | 487754 | 100% | 100% | 105.1% | 92.8% | 100% | 2006-06-09 | n/a | 2007-10-17 | 2007-10-17 | no data | 0 | 423 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Isidro | 071234020 | Organic Fertilizer Production | 1 | 918294 | 474073.32 | 444220.68 | 426665.99 |  | 453850.42 | 880516.41 | 426665.99 | 453850.42 | 100% | 100% | 102.2% | 95.89% | 100% | 2008-05-28 | n/a | 2008-08-19 | 2009-06-09 | n/a | 294 | 520 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Vicente | 071234021 | Construction of Health Station | 1 | 618147 | 151926.84 | 466220.16 | 151926.84 |  | 462785.6 | 614712.44 | 151926.84 | 462785.6 | 100% | 100% | 99.26% | 99.44% | 100% | 2006-06-09 | n/a | 2006-11-08 | 2007-01-18 | 2007-01-26 | 71 | 147 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Vicente | 071234021 | Eco-tourism: Spring Development | 1 | 2565076 | 1031696 | 1533380 | 928526.4 |  | 1462600 | 2391126.4 | 928526.4 | 1462600 | 100% | 100% | 95.38% | 93.22% | 100% | 2008-05-28 | n/a | 2009-02-28 | 2009-08-28 | n/a | 181 | 147 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Bayongan | 071238001 | Electrification Project | 1 | 1254630 | 873974.7 | 380655.3 | 819458.28 |  | 384029.8 | 1203488.08 | 819458.28 | 384029.8 | 100% | 100% | 100.9% | 95.92% | 100% | 2008-05-19 | n/a | 2008-08-15 | 2008-10-21 | no data | 67 | 35 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Bugang | 071238003 | Farm to Market road wqith Spillway (.109 km) | 1 | 1050370 | 664750.01 | 385619.99 | 664750 | 1st Tranche | 385620 | 1050370 | 664750 | 385620 | 100% | 100% | 100% | 100% | 100% | 2006-06-22 | n/a | 2006-09-30 | 2007-03-23 | 2007-03-23 | 174 | 187 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Bugang | 071238003 | Concrete Pavement Solar Drier | 1 | 654578 | 458068 | 196510 | 453068 |  | 200670 | 653738 | 453068 | 200670 | 100% | 100% | 102.1% | 99.87% | 100% | 2007-03-22 | n/a | 2007-07-09 | 2007-09-17 | 2007-10-19 | 70 | 170 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Bugang | 071238003 | Construction of 2 CL School Building w/ Electrical & CR | 1 | 544344 | 278921.2 | 265422.8 | 278921.2 |  | 263067.8 | 541989 | 278921.2 | 263067.8 | 100% | 100% | 99.11% | 99.57% | 100% | 2008-05-19 | n/a | 2008-08-11 | 2008-12-17 | no data | 128 | 170 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Cabangahan | 071238004 | Improvement of .0816 Km Farm-to-Market Road | 1 | 925960 | 693640 | 232320 | 693640 | 1st Tranche | 232320 | 925960 | 693640 | 232320 | 100% | 100% | 100% | 100% | 100% | 2006-06-22 | n/a | 2006-10-05 | 2007-03-16 | 2007-03-15 | 162 | 124 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Cabangahan | 071238004 | Concreting of Cabangahan FMR with Spillway & Riprap | 1 | 670502 | 450596.67 | 219905.33 | 449225.56 |  | 225232 | 674457.56 | 449225.56 | 225232 | 100% | 100% | 102.4% | 100.6% | 100% | 2007-03-22 | n/a | 2007-06-28 | 2007-09-20 | 2007-09-21 | 84 | 120 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Calausan | 071238012 | Concreting of 0.10 Km Farm-to-Market Road | 1 | 492048 | 235828.01 | 256219.99 | 235828.01 | 1st Tranche | 256220 | 492048.01 | 235828.01 | 256220 | 100% | 100% | 100% | 100% | 100% | 2006-06-22 | n/a | 2006-10-05 | 2007-03-16 | 2007-03-15 | 162 | 104 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Calausan | 071238012 | Concreting of Caluasan Farm to Market Road | 1 | 545658 | 374418.2 | 171239.8 | 336976.38 |  | 182239.8 | 519216.18 | 336976.38 | 182239.8 | 100% | 100% | 106.4% | 95.15% | 100% | 2007-03-22 | n/a | 2007-11-15 | 2008-04-25 | no data | 162 | 263 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Camanaga | 071238006 | Construction of Barangay Health Station (BHS) | 1 | 733543 | 510238.7 | 223304.3 | 508635 |  | 228168.7 | 736803.7 | 508635 | 228168.7 | 100% | 100% | 102.2% | 100.4% | 100% | 2008-05-19 | n/a | 2008-07-29 | 2008-12-04 | no data | 128 | 308 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Cambangay Norte | 071238007 | Construction of 2-CL School Building with CR & Electrical | 1 | 1019396 | 595051.09 | 424344.91 | 595051.09 | 1st Tranche | 443047.51 | 1038098.6 | 595051.09 | 443047.51 | 100% | 100% | 104.4% | 101.8% | 100% | 2006-06-22 | n/a | 2006-10-09 | 2006-12-15 | 2006-12-18 | 67 | 275 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Cambangay Norte | 071238007 | Construction of Barangay Health Station (BHS) | 1 | 682160 | 475940.3 | 206219.7 | 473729 |  | 251044.2 | 724773.2 | 473729 | 251044.2 | 100% | 100% | 121.7% | 106.2% | 100% | 2008-05-19 | n/a | 2008-08-04 | 2008-11-17 | no data | 105 | 264 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Capayas | 071238008 | Improvement of Capayas Farm to Market Road | 1 | 710477 | 494917.25 | 215559.75 | 494917.25 |  | 225888.18 | 720805.43 | 494917.25 | 225888.18 | 100% | 100% | 104.8% | 101.5% | 100% | 2008-05-19 | n/a | 2008-09-10 | 2009-06-16 | n/a | 279 | 213 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Corazon | 071238009 | Concrete Paving of 720 sq.m Solar Drier | 1 | 549353 | 270020 | 279333 | 270020 | 1st Tranche | 280333 | 550353 | 270020 | 280333 | 100% | 100% | 100.4% | 100.2% | 100% | 2006-06-22 | n/a | 2006-10-05 | 2006-11-10 | 2006-11-12 | 36 | 273 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Corazon | 071238009 | Electrification Project | 1 | 400024 | 219806.88 | 180217.12 | 197826.19 |  | 184879.62 | 382705.81 | 197826.19 | 184879.62 | 100% | 100% | 102.6% | 95.67% | 100% | 2008-05-19 | n/a | 2008-11-17 | 2009-02-10 | n/a | 85 | 15 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Garcia | 071238010 | Electrification Project | 1 | 1020988 | 684657.85 | 336330.15 | 616192.07 |  | 336330.15 | 952522.22 | 616192.07 | 336330.15 | 100% | 100% | 100% | 93.29% | 100% | 2008-05-19 | n/a | 2008-08-18 | 2008-11-17 | no data | 91 | 30 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Hagbuyo | 071238011 | Water Impounding System | 1 | 681532 | 413288 | 268244 | 413288 | 1st Tranche | 268244 | 681532 | 413288 | 268244 | 100% | 100% | 100% | 100% | 100% | 2006-06-22 | n/a | 2006-10-01 | 2006-11-19 | 2006-11-21 | 49 | 195 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Hagbuyo | 071238011 | 1 CL School Building with CR and Electrical | 1 | 500119 | 327416.71 | 172702.29 | 325951.85 |  | 179344.91 | 505296.76 | 325951.85 | 179344.91 | 100% | 100% | 103.8% | 101% | 100% | 2007-03-22 | n/a | 2007-07-05 | 2007-10-19 | no data | 106 | 190 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Kagawasan | 071238005 | Construction of 2 Annex Classroom Sch. Bldg. with CR & Electrical | 1 | 1058809 | 604329.41 | 454479.59 | 604329.41 | 1st Tranche | 512679.6 | 1117009.01 | 604329.41 | 512679.6 | 100% | 100% | 112.8% | 105.5% | 100% | 2006-06-22 | n/a | 2006-10-05 | 2007-03-16 | 2007-04-03 | 162 | 258 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Kagawasan | 071238005 | Concreting of Kagawasan Farm to Market Road | 1 | 688565 | 481944.4 | 206620.6 | 478845.68 |  | 225773 | 704618.68 | 478845.68 | 225773 | 100% | 100% | 109.3% | 102.3% | 100% | 2007-03-22 | n/a | 2007-07-02 | 2008-03-15 | no data | 257 | 86 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Mahayag | 071238013 | 2 CL School Building with CR and Electrical | 1 | 1018719 | 653081.4 | 365637.6 | 607759.53 |  | 389604 | 997363.53 | 607759.53 | 389604 | 100% | 100% | 106.6% | 97.9% | 100% | 2007-03-22 | n/a | 2007-10-01 | 2008-02-29 | no data | 151 | 389 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Mahayag | 071238013 | Improvement of Mahayag Farm to Market Road | 1 | 427143 | 295983 | 131160 | 266384.7 |  | 131160 | 397544.7 | 266384.7 | 131160 | 100% | 100% | 100% | 93.07% | 100% | 2008-05-19 | n/a | 2008-09-10 | 2008-12-29 | no data | 110 | 389 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Poblacion | 071238014 | 2 CL School Building with CR and Electrical | 1 | 1048824 | 725489.8 | 323334.2 | 723742.26 |  | 325121.74 | 1048864 | 723742.26 | 325121.74 | 100% | 100% | 100.6% | 100% | 100% | 2007-03-22 | n/a | 2007-06-26 | 2007-08-31 | no data | 66 | 347 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Poblacion | 071238014 | Concrete Pavement Solar Drier | 1 | 387981 | 269498.25 | 118482.75 | 269498.25 |  | 118482.75 | 387981 | 269498.25 | 118482.75 | 100% | 100% | 100% | 100% | 100% | 2008-05-19 | n/a | 2008-08-08 | 2008-09-27 | no data | 50 | 347 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Poblacion | 071238014 | Construction of Municipal Library & Information Center | 1 | 797750 | 300000 | 497750 | 300000 |  | 485410 | 785410 | 300000 | 485410 | 100% | 100% | 97.52% | 98.45% | 100% | n/a | n/a | 2009-05-02 | 2009-07-16 | n/a | 75 | 347 | incentive funds | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Isidro | 071238015 | Concreting of San Isidro Farm-to-Market Road w/ Spillway & Riprap | 1 | 942103 | 652783 | 289320 | 650337.5 |  | 321760.5 | 972098 | 650337.5 | 321760.5 | 100% | 100% | 111.2% | 103.2% | 100% | 2008-05-19 | n/a | 2008-09-08 | 2009-02-18 | n/a | 163 | 245 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Jose | 071238016 | Improvement of 1.12 Km Farm-to-Market Road | 1 | 1119994 | 835994 | 284000 | 835994 | 1st Tranche | 284000 | 1119994 | 835994 | 284000 | 100% | 100% | 100% | 100% | 100% | 2006-06-22 | n/a | 2006-10-05 | 2007-02-28 | 2007-02-28 | 146 | 122 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Jose | 071238016 | Improvement of san Jose Farm to market Road | 1 | 827728 | 642107.81 | 185620.19 | 577897.03 |  | 233759.86 | 811656.89 | 577897.03 | 233759.86 | 100% | 100% | 125.9% | 98.06% | 100% | 2007-03-22 | n/a | 2007-11-20 | 2008-06-20 | no data | 213 | 113 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Jose | 071238016 | Concrete Pavement Solar Drier | 1 | 309184 | 209644 | 99540 | 205550 |  | 99540 | 305090 | 205550 | 99540 | 100% | 100% | 100% | 98.68% | 100% | 2008-05-19 | n/a | 2008-08-15 | 2008-09-27 | no data | 43 | 113 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Vicente | 071238017 | Improvement of 1.0 Km Farm-to-Market Road | 1 | 1190539 | 934019.2 | 256519.8 | 934019.2 | 1st Tranche | 385720 | 1319739.2 | 934019.2 | 385720 | 100% | 100% | 150.4% | 110.9% | 100% | 2006-06-22 | n/a | 2006-09-29 | 2007-02-13 | 2007-02-14 | 137 | 80 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Vicente | 071238017 | Concrete Pavement Solar Drier | 1 | 522692 | 360232 | 162460 | 348871.86 |  | 163120 | 511991.86 | 348871.86 | 163120 | 100% | 100% | 100.4% | 97.95% | 100% | 2007-03-22 | n/a | 2007-06-30 | 2007-09-15 | 2007-10-18 | 77 | 147 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Vicente | 071238017 | Construction of San Vicente Footbridge | 1 | 444849 | 301489 | 143360 | 299377.8 |  | 143360 | 442737.8 | 299377.8 | 143360 | 100% | 100% | 100% | 99.53% | 100% | 2008-05-19 | n/a | 2008-09-10 | 2008-11-08 | no data | 59 | 170 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Sto. Niño | 071238018 | Electrification | 1 | 662112.93 | 153080.28 | 509032.65 | 153080.28 |  | 420580.72 | 573661 | 153080.28 | 420580.72 | 100% | 100% | 82.62% | 86.64% | 100% | 2006-06-22 | n/a | 2006-12-18 | 2006-12-29 | 2007-02-14 | 11 | 42 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Sto. Niño | 071238018 | Improvement of Sto Niño Farm to Market Road | 1 | 631022 | 441202 | 189820 | 397081.8 |  | 197820 | 594901.8 | 397081.8 | 197820 | 100% | 100% | 104.2% | 94.28% | 100% | 2007-03-22 | n/a | 2007-09-24 | 2007-12-10 | no data | 77 | 125 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Tomoc | 071238019 | Concreting of Tomoc Farm to Market Road with Spillway & Riprap | 1 | 717763 | 485443.01 | 232319.99 | 480773.17 |  | 243120 | 723893.17 | 480773.17 | 243120 | 100% | 100% | 104.6% | 100.9% | 100% | 2007-03-22 | n/a | 2007-07-09 | 2007-09-30 | 2007-10-18 | 83 | 179 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Tomoc | 071238019 | Improvement of Tomoc Farm to Market Road | 1 | 503613 | 351952.75 | 151660.25 | 351952.75 |  | 151660.25 | 503613 | 351952.75 | 151660.25 | 100% | 100% | 100% | 100% | 100% | 2008-05-19 | n/a | 2008-08-15 | 2009-03-31 | n/a | 228 | 179 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Bagacay | 071243001 | Concreting & Regravelling of Farm to Market Road | 1 | 1551955 | 1141838.79 | 410116.21 | 1141378.99 |  | 423965.8 | 1582039.79 | 1141378.99 | 440660.8 | 100% | 103.9% | 103.4% | 101.9% | 100% | 2007-03-14 | n/a | 2008-01-14 | 2008-10-10 | no data | 270 | 508 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Balintawak | 071243002 | Construction of Skills Training Center cum Training Center | 1 | 1764749.01 | 1256595.35 | 508153.66 | 1256595.35 |  | 560210.48 | 1816805.83 | 1256595.35 | 560210.48 | 100% | 100% | 110.2% | 102.9% | 100% | 2006-06-18 | n/a | 2006-10-19 | 2007-06-02 | no data | 226 | 246 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Burgos | 071243006 | Concreting of Farm to Market Road | 1 | 1152772 | 797352 | 355420 | 793956.84 |  | 455620 | 1260511.83 | 793956.84 | 466554.99 | 100% | 102.4% | 128.2% | 109.3% | 100% | 2007-03-14 | n/a | 2007-07-02 | 2008-01-11 | no data | 193 | 140 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Busalian | 071243007 | Construction of Rainwater Harvester | 1 | 958594.01 | 678199.66 | 280394.35 | 678199.66 |  | 380394.35 | 1058594.01 | 678199.66 | 380394.35 | 100% | 100% | 135.7% | 110.4% | 100% | 2006-06-18 | n/a | 2006-10-16 | 2007-05-18 | 2007-05-18 | 214 | 459 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Calituban | 071243008 | Construction of 2 classroom High School Building | 1 | 1227487.97 | 748899.97 | 478588 | 740619.69 |  | 763188.55 | 1516207.5 | 740619.69 | 775587.81 | 100% | 101.6% | 159.5% | 123.5% | 100% | 2007-03-14 | n/a | 2007-10-05 | 2008-06-20 | no data | 259 | 656 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Cataban | 071243009 | Electrification (Generator Set) | 1 | 2067659 | 1180000 | 887659 | 1180000 |  | 830658.99 | 2027353.99 | 1180000 | 847353.99 | 100% | 102% | 93.58% | 98.05% | 100% | 2006-06-18 | n/a | 2006-10-16 | 2007-05-28 | 2007-05-31 | 224 | 224 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Guindacpan | 071243010 | Water System Level II | 1 | 779586 | 457545.87 | 322040.13 | 457545.87 | 3rd Tranche | 343040.13 | 800586 | 457545.87 | 343040.13 | 100% | 100% | 106.5% | 102.7% | 100% | 2005-06-26 | 2005-08-24 | 2005-10-27 | 2006-02-02 | 2006-02-02 | 98 | 381 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Magsaysay | 071243013 | Asphalt Paving of Magsaysay 1.4 km Farm to Market Road | 1 | 1681870 | 1191202.81 | 490667.19 | 1125984.45 | 1st Tranche | 490672 | 1616656.45 | 1125984.45 | 490672 | 100% | 100% | 100% | 96.12% | 100% | 2005-06-26 | 2005-08-24 | 2005-11-12 | 2008-07-10 | no data | 971 | 231 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Mahanay | 071243014 | Concreting of Footwalk | 1 | 1307567.99 | 820000 | 487567.99 | 820000 |  | 486343.13 | 1306343.13 | 820000 | 486343.13 | 100% | 100% | 99.75% | 99.91% | 100% | 2006-06-18 | n/a | 2006-10-16 | 2007-05-28 | 2007-05-31 | 224 | 231 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Nocnocan | 071243017 | Rain Water Harvesting | 1 | 943059 | 720838.35 | 222220.65 | 720838.35 | 3rd Tranche | 264836.5 | 985674.85 | 720838.35 | 264836.5 | 100% | 100% | 119.2% | 104.5% | 100% | 2005-06-26 | 2005-08-24 | 2005-10-24 | 2006-05-18 | 2006-05-18 | 206 | 281 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Poblacion | 071243021 | Construction of 2 CL Elementary School Building | 1 | 1272428 | 937763.91 | 334664.09 | 845987.52 |  | 334745.59 | 1180733.11 | 845987.52 | 334745.59 | 100% | 100% | 100% | 92.79% | 100% | 2007-03-14 | n/a | 2007-12-12 | 2008-04-30 | no data | 140 | 788 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Rizal | 071243023 | Acquisition of 1 unit 6-wheeler Dump Truck | 1 | 758750 | 548750 | 210000 | 510125 |  | 160100 | 670225 | 510125 | 160100 | 100% | 100% | 76.24% | 88.33% | 100% | 2007-03-14 | n/a | 2008-03-29 | 2008-03-29 | no data | 0 | 230 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Sag | 071243024 | Acquisition of Pump Boat and Accessories | 1 | 430625 | 300625 | 130000 | 293375 |  | 154600 | 447975 | 293375 | 154600 | 100% | 100% | 118.9% | 104% | 100% | 2007-03-14 | n/a | 2007-12-17 | 2007-12-21 | 2007-12-21 | 4 | 126 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Agustin | 071243026 | Water System Level II | 1 | 2540014 | 2214944.71 | 325069.29 | 2214944.71 | 3rd Tranche | 344981.99 | 2576371.7 | 2214944.71 | 361426.99 | 100% | 104.8% | 106.1% | 101.4% | 100% | 2005-06-26 | 2005-08-24 | 2005-10-21 | 2008-08-28 | no data | 1042 | 737 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Carlos | 071243027 | Installation of Water System Level II | 1 | 1444311.3 | 1160546.3 | 283765 | 1153566.5 |  | 191965 | 1345531.5 | 1153566.5 | 191965 | 100% | 100% | 67.65% | 93.16% | 100% | 2007-03-14 | n/a | 2007-12-17 | 2009-07-31 | n/a | 592 | 310 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Francisco | 071243028 | Construction of 1.8Km Farm-to-Market Road | 1 | 1122605.01 | 697019.5 | 425585.51 | 697019.5 |  | 573572.47 | 1270591.97 | 697019.5 | 573572.47 | 100% | 100% | 134.8% | 113.2% | 100% | 2006-06-18 | n/a | 2006-11-03 | 2007-06-13 | 2007-07-13 | 222 | 890 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Isidro | 071243029 | Construction of 1.4Km Farm-to-Market Road | 1 | 1199414 | 695514 | 503900 | 695514 |  | 507216.07 | 1202730.07 | 695514 | 507216.07 | 100% | 100% | 100.7% | 100.3% | 100% | 2006-06-18 | n/a | 2006-11-03 | 2007-07-06 | 2007-08-16 | 245 | 590 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Jose | 071243030 | Construction of Organic Fertilizer Manufacturing Building | 1 | 1406765.99 | 965005.63 | 441760.36 | 868505.07 |  | 442000.37 | 1310505.83 | 868505.07 | 442000.76 | 100% | 100% | 100.1% | 93.16% | 100% | 2006-06-18 | n/a | 2006-11-03 | 2007-05-28 | 2007-05-30 | 206 | 910 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Pedro | 071243031 | Single Barrel Box Culvert | 1 | 829504.51 | 639144.47 | 190360.04 | 639144.47 | 3rd Tranche | 198440.04 | 846679.51 | 639144.47 | 207535.04 | 100% | 104.6% | 104.2% | 102.1% | 100% | 2005-06-26 | 2005-08-24 | 2005-11-12 | 2006-02-02 | 2006-02-02 | 82 | 234 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Roque | 071243032 | Acquisition of 1-unit 6 Wheeler Dumptruck | 1 | 627666 | 407666 | 220000 | 407666 |  | 230870 | 649081 | 407666 | 241415 | 100% | 104.6% | 104.9% | 103.4% | 100% | 2006-06-18 | n/a | 2007-02-21 | 2007-02-21 | 2007-03-28 | 0 | 435 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Sikatuna | 071243034 | Spillway | 1 | 681710.96 | 485245.16 | 196465.8 | 485245.16 | 3rd Tranche | 201455.8 | 689450.96 | 485245.16 | 204205.8 | 100% | 101.4% | 102.5% | 101.1% | 100% | 2005-06-26 | 2005-08-24 | 2005-10-27 | 2006-02-02 | 2006-02-02 | 98 | 300 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Sto. Niño | 071243033 | Construction of 2 CL Elementary School Building | 1 | 1240746.83 | 868566.83 | 372180 | 826210.9 |  | 513280 | 1339490.9 | 826210.9 | 513280 | 100% | 100% | 137.9% | 108% | 100% | 2007-03-14 | n/a | 2007-12-05 | 2008-08-28 | no data | 267 | 578 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Suba | 071243035 | School Building 4 CL | 1 | 2510278 | 1791078.64 | 719199.36 | 1791078.64 | 3rd Tranche | 726409.16 | 2534082.8 | 1791078.64 | 743004.16 | 100% | 102.3% | 101% | 100.9% | 100% | 2005-06-26 | 2005-08-24 | 2005-12-05 | 2006-05-18 | 2006-05-18 | 164 | 328 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Tanghaligue | 071243036 | Concreting of Farm to Market Road | 1 | 1495432 | 995657.2 | 499774.8 | 995657.2 |  | 420254.8 | 1429232.1 | 995657.2 | 433574.9 | 100% | 103.2% | 84.09% | 95.57% | 100% | 2007-03-14 | n/a | 2008-06-01 | 2008-12-05 | no data | 187 | 327 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Talibon | 071243 | Zamora | 071243038 | Installation of Level II Waterworks System | 1 | 1368957 | 799999.86 | 568957.14 | 788911.71 |  | 568937.14 | 1357848.85 | 788911.71 | 568937.14 | 100% | 100% | 100% | 99.19% | 100% | 2006-06-18 | n/a | 2006-10-11 | 2009-05-20 | n/a | 952 | 289 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Banlasan | 071244001 | Road Opening of 360m farm to market Road and construction of box culvert | 1 | 1779551 | 1382670.52 | 396880.48 | 1370340.51 |  | 413170 | 1783510.51 | 1370340.51 | 413170 | 100% | 100% | 104.1% | 100.2% | 100% | 2007-03-14 | n/a | 2007-07-30 | 2009-06-13 | n/a | 684 | 202 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Bongbong | 071244002 | Road Improvement of 1060m Farm to Market Road | 1 | 785718 | 555422.85 | 230295.15 | 539148.69 |  | 224524.3 | 763672.99 | 539148.69 | 224524.3 | 100% | 100% | 97.49% | 97.19% | 100% | 2007-03-14 | n/a | 2007-07-19 | 2008-06-28 | no data | 345 | 182 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Catoogan | 071244003 | Road Rehabilitation of 2.23 km Farm-to-Market Road | 1 | 1247388 | 903493.53 | 343894.47 | 813144.18 | 1st Tranche | 281180.47 | 1094324.65 | 813144.18 | 281180.47 | 100% | 100% | 81.76% | 87.73% | 100% | 2006-06-23 | n/a | 2006-10-27 | 2007-07-16 | 2007-09-07 | 262 | 166 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Catoogan | 071244003 | Construction of Barangay Health Station | 1 | 723586 | 252356.36 | 471229.64 | 244456 |  | 459049.64 | 703505.64 | 244456 | 459049.64 | 100% | 100% | 97.42% | 97.22% | 100% | 2008-05-21 | n/a | 2008-11-27 | 2009-06-17 | n/a | 202 | 152 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Guinobatan | 071244004 | Road Improvement (Concreting of 80m) of Farm to Market Road | 1 | 418778 | 225150.75 | 193627.25 | 225150.75 |  | 198000 | 423150.75 | 225150.75 | 198000 | 100% | 100% | 102.3% | 101% | 100% | 2007-03-14 | n/a | 2007-08-08 | 2008-05-31 | no data | 297 | 319 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Hinlayagan Ilaud | 071244005 | Concreting of 0.25km Farm-to-Market Road | 1 | 1394326 | 1083041 | 311285 | 1083041 |  | 290265 | 1373306 | 1083041 | 290265 | 100% | 100% | 93.25% | 98.49% | 100% | 2006-06-23 | n/a | 2006-10-27 | 2007-07-15 | 2007-09-07 | 261 | 298 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Hinlayagan Ilaud | 071244005 | Solar Drier | 1 | 408930 | 285994.75 | 122935.25 | 285994.75 |  | 120615.25 | 406610 | 285994.75 | 120615.25 | 100% | 100% | 98.11% | 99.43% | 100% | 2008-05-21 | n/a | 2008-08-11 | 2008-11-29 | no data | 110 | 180 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Hinlayagan Ilaya | 071244006 | Construction of 2-Classroom School Building | 1 | 1046141 | 745262.19 | 300878.81 | 745262.19 | 1st Tranche | 300878.81 | 1046141 | 745262.19 | 300878.81 | 100% | 100% | 100% | 100% | 100% | 2006-06-23 | n/a | 2006-10-05 | 2006-12-13 | 2006-12-18 | 69 | 450 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Hinlayagan Ilaya | 071244006 | Construction of Footbridge | 1 | 666357 | 451236.2 | 215120.8 | 451236.2 |  | 36960 | 488196.2 | 451236.2 | 36960 | 100% | 100% | 17.18% | 73.26% | 100% | 2008-05-21 | n/a | 2008-08-01 | 2009-05-10 | n/a | 282 | 296 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Kauswagan | 071244007 | Electrification | 1 | 2264608 | 1502753.28 | 761854.72 | 1368267.06 |  | 704958.33 | 2073225.39 | 1368267.06 | 704958.33 | 100% | 100% | 92.53% | 91.55% | 100% | 2006-06-23 | n/a | 2007-07-18 | 2007-10-11 | no data | 85 | 116 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Kauswagan | 071244007 | Construction of 1 CL School Building | 1 | 621410 | 447849.75 | 173560.25 | 403064.78 |  | 107575 | 510639.78 | 403064.78 | 107575 | 100% | 100% | 61.98% | 82.17% | 100% | 2008-05-21 | n/a | 2008-08-12 | 2009-01-05 | no data | 146 | 384 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Kinan-onan | 071244008 | 1 CL School Building | 1 | 510347 | 398460.42 | 111886.58 | 396463.38 |  | 121279 | 517742.38 | 396463.38 | 121279 | 100% | 100% | 108.4% | 101.4% | 100% | 2007-03-14 | n/a | 2008-02-18 | 2008-06-14 | no data | 117 | 227 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | La Victoria | 071244010 | Road Improvement of 451m Farm to Market Road | 1 | 421742 | 262381.8 | 159360.2 | 235232.83 |  | 160360.2 | 395593.03 | 235232.83 | 160360.2 | 100% | 100% | 100.6% | 93.8% | 100% | 2007-03-14 | n/a | 2007-08-01 | 2008-01-10 | no data | 162 | 246 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Mahagbu | 071244013 | Construction of 2 CL School Building | 1 | 882742 | 641309.4 | 241432.6 | 624500.35 |  | 241619.7 | 866120.05 | 624500.35 | 241619.7 | 100% | 100% | 100.1% | 98.12% | 100% | 2007-03-14 | n/a | 2007-07-02 | 2007-08-28 | no data | 57 | 159 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Manuel M. Roxas | 071244014 | Rehabilitation of 0.37km & Concreting of 0.5 km Barangay Farm-to-Market Road | 1 | 1350047 | 981870.01 | 368176.99 | 919230.37 | 1st Tranche | 205705 | 1124935.37 | 919230.37 | 205705 | 100% | 100% | 55.87% | 83.33% | 100% | 2006-06-23 | n/a | 2006-12-10 | 2007-07-14 | 2007-09-07 | 216 | 168 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Manuel M. Roxas | 071244014 | Construction of 1 CL School Building | 1 | 566166 | 240274.84 | 325891.16 | 240273.84 |  | 109220.05 | 349493.89 | 240273.84 | 109220.05 | 100% | 100% | 33.51% | 61.73% | 100% | 2008-05-21 | n/a | 2008-08-20 | 2009-06-17 | n/a | 301 | 184 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Poblacion | 071244015 | Poblacion Multi Purpose Transport Facility | 1 | 411250 | 287875 | 123375 | 287875 |  | 176375 | 464250 | 287875 | 176375 | 100% | 100% | 143% | 112.9% | 100% | 2007-03-14 | n/a | 2008-03-01 | 2008-06-04 | no data | 95 | 529 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Poblacion | 071244015 | Day Care Center | 1 | 669154 | 464913.15 | 204240.85 | 464913.15 |  | 61120 | 527559 | 464913.15 | 62645.85 | 100% | 102.5% | 29.93% | 78.84% | 100% | 2008-05-21 | n/a | 2008-08-20 | 2009-06-13 | n/a | 297 | 529 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | San Isidro | 071244016 | Construction of Day Care Center | 1 | 699707 | 489878.28 | 209828.72 | 475375.01 |  | 210297.36 | 685672.37 | 475375.01 | 210297.36 | 100% | 100% | 100.2% | 97.99% | 100% | 2007-03-14 | n/a | 2007-07-09 | 2007-08-22 | no data | 44 | 88 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | San Isidro | 071244016 | Farm-to-Market Road | 1 | 2251407 | 1478186.55 | 773220.45 | 1478186.55 |  | 83100 | 1561286.55 | 1478186.55 | 83100 | 100% | 100% | 10.75% | 69.35% | 100% | 2008-05-21 | n/a | 2008-09-02 | 2009-08-19 | n/a | 351 | 88 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | San Vicente | 071244017 | Farm-to-Market Road | 1 | 1390278 | 973052.1 | 417225.9 | 973052.1 |  | 156145 | 1129197.1 | 973052.1 | 156145 | 100% | 100% | 37.42% | 81.22% | 100% | 2008-05-21 | n/a | 2008-08-16 | 2009-01-05 | no data | 142 | 232 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Santo Tomas | 071244018 | Farm-to-Market Road | 1 | 1787989 | 1144768.16 | 643220.84 | 1144768.16 |  | 92270 | 1237038.16 | 1144768.16 | 92270 | 100% | 100% | 14.34% | 69.19% | 100% | 2008-05-21 | n/a | 2008-09-09 | 2009-07-15 | n/a | 309 | 147 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Soom | 071244019 | Construction of Day Care Center | 1 | 682716 | 396961.06 | 285754.94 | 386706.27 |  | 281040.82 | 667747.09 | 386706.27 | 281040.82 | 100% | 100% | 98.35% | 97.81% | 100% | 2007-03-14 | n/a | 2007-07-16 | 2007-08-24 | no data | 39 | 265 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Soom | 071244019 | Barangay Health Station | 1 | 723576 | 513725.5 | 209850.5 | 462352.95 |  | 186240 | 648592.95 | 462352.95 | 186240 | 100% | 100% | 88.75% | 89.64% | 100% | 2008-05-21 | n/a | 2008-08-19 | 2009-02-20 | n/a | 185 | 265 | completed as built | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Sto. Tomas | 071244018 | Electrification | 1 | 1404700 | 783579.99 | 621120.01 | 783579.99 |  | 548120 | 1331699.99 | 783579.99 | 548120 | 100% | 100% | 88.25% | 94.8% | 100% | 2006-06-23 | n/a | 2007-06-13 | 2007-07-17 | no data | 34 | 75 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Tagum Norte | 071244020 | Road Improvement of 1.5 km Farm to Market Road | 1 | 979871 | 729370.92 | 250500.08 | 656433.83 |  | 238250 | 894683.83 | 656433.83 | 238250 | 100% | 100% | 95.11% | 91.31% | 100% | 2007-03-14 | n/a | 2007-10-05 | 2008-06-28 | no data | 267 | 242 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Tagum Sur | 071244021 | Road Improvement of 1.5 km Farm to Market Road | 1 | 930619 | 630519 | 300100 | 603020 |  | 300100 | 903120 | 603020 | 300100 | 100% | 100% | 100% | 97.05% | 100% | 2007-03-14 | n/a | 2007-07-16 | 2008-01-15 | no data | 183 | 192 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Tagum Sur | 071244021 | Construction of 3 unit water impounding system | 1 | 510991 | 234872.25 | 276118.75 | 187897.8 |  | 259898.75 | 447796.55 | 187897.8 | 259898.75 | 100% | 100% | 94.13% | 87.63% | 100% | 2008-05-21 | n/a | 2008-12-08 | 2009-03-26 | n/a | 108 | 192 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Achila | 071246001 | Farm to Market Road | 1 | 737593 | 513543 | 224050 | 462188.7 |  | 225410 | 687598.7 | 462188.7 | 225410 | 100% | 100% | 100.6% | 93.22% | 100% | 2008-04-29 | n/a | 2008-06-03 | 2008-09-16 | no data | 105 | 253 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Bay-ang | 071246002 | Construction of Processing Center cum Attached Decaying Basin | 1 | 1109583 | 770033 | 339550 | 770033 |  | 353733.8 | 1123766.8 | 770033 | 353733.8 | 100% | 100% | 104.2% | 101.3% | 100% | 2006-07-15 | n/a | 2006-11-06 | 2007-05-10 | 2007-05-25 | 185 | 300 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Benliw | 071246005 | Construction of Health Center | 1 | 830931 | 565611 | 265320 | 509049.9 |  | 267940 | 776989.9 | 509049.9 | 267940 | 100% | 100% | 101% | 93.51% | 100% | 2007-03-18 | n/a | 2007-06-28 | 2007-10-09 | 2007-10-23 | 103 | 397 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Biabas | 071246004 | Farm to Market Road | 1 | 873418 | 597998 | 275420 | 597998 |  | 278940 | 876938 | 597998 | 278940 | 100% | 100% | 101.3% | 100.4% | 100% | 2008-04-29 | n/a | 2008-07-21 | 2008-12-29 | no data | 161 | 476 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Bongbong | 071246007 | Improvement of Farm to Market Road | 1 | 1365133 | 953453 | 411680 | 876977.05 |  | 414800 | 1291777.05 | 876977.05 | 414800 | 100% | 100% | 100.8% | 94.63% | 100% | 2008-04-29 | n/a | 2008-08-18 | 2008-12-23 | no data | 127 | 174 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Bood | 071246008 | Construction of 2 CL School Building | 1 | 1257900 | 873610 | 384290 | 819412.9 |  | 395456.5 | 1214869.4 | 819412.9 | 395456.5 | 100% | 100% | 102.9% | 96.58% | 100% | 2008-04-29 | n/a | 2008-07-31 | 2008-12-05 | no data | 127 | 395 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Buenavista | 071246009 | Asphalt Paving of Farm-to-Market Road | 1 | 1578677 | 1101592 | 477085 | 991432.8 | 1st Tranche | 479685 | 1471117.8 | 991432.8 | 479685 | 100% | 100% | 100.5% | 93.19% | 100% | 2006-07-15 | n/a | 2006-11-03 | 2007-05-15 | 2007-05-24 | 193 | 128 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Bulilis | 071246055 | Solar Drier with Storage Building | 1 | 1648107 | 1016777 | 631330 | 1016777 |  | 678400 | 1695177 | 1016777 | 678400 | 100% | 100% | 107.5% | 102.9% | 100% | 2007-03-18 | n/a | 2007-12-10 | 2008-06-28 | no data | 201 | 296 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Cagting | 071246011 | Construction & Installation of Level II Waterworks System | 1 | 2461181 | 1687298 | 773883 | 1349838.4 | 1st Tranche | 775703 | 2125541.4 | 1349838.4 | 775703 | 100% | 100% | 100.2% | 86.36% | 100% | 2006-07-15 | n/a | 2006-11-16 | 2007-07-18 | no data | 244 | 159 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Calanggaman | 071246027 | Construction of 2-Classroom School Building | 1 | 1168222 | 785478 | 382744 | 785478 | 1st Tranche | 384955.75 | 1170433.75 | 785478 | 384955.75 | 100% | 100% | 100.6% | 100.2% | 100% | 2006-07-15 | n/a | 2006-10-17 | 2007-01-31 | 2007-02-06 | 106 | 291 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | California | 071246056 | Improvement of Farm-to-Market Road | 1 | 1696361 | 1135231 | 561130 | 1135231 | 1st Tranche | 561130 | 1696361 | 1135231 | 561130 | 100% | 100% | 100% | 100% | 100% | 2006-07-15 | n/a | 2006-11-30 | 2007-07-20 | 2007-08-16 | 232 | 174 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Camambugan | 071246013 | Farm to Market Road | 1 | 1179070 | 820370 | 358700 | 820370 |  | 360580 | 1180950 | 820370 | 360580 | 100% | 100% | 100.5% | 100.2% | 100% | 2008-04-29 | n/a | 2008-07-25 | 2008-10-27 | no data | 94 | 433 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Camali-an | 071246012 | Concrete Paving of Camalian Solar Drier | 1 | 507261 | 303648 | 203613 | 242918.4 |  | 241964.25 | 484882.65 | 242918.4 | 241964.25 | 100% | 100% | 118.8% | 95.59% | 100% | 2007-03-18 | n/a | 2008-01-10 | 2008-04-17 | 2008-04-17 | 98 | 115 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Casate | 071246015 | Farm to Market Road | 1 | 741322 | 480502 | 260820 | 442823 |  | 212475 | 655298 | 442823 | 212475 | 100% | 100% | 81.46% | 88.4% | 100% | 2008-04-29 | n/a | 2008-08-01 | 2008-11-29 | no data | 120 | 330 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Cuya | 071246017 | Improvement of Brgy Cuya Farm to Market Road | 1 | 1352381 | 939381 | 413000 | 919381 |  | 412380 | 1331761 | 919381 | 412380 | 100% | 100% | 99.85% | 98.48% | 100% | 2007-03-18 | n/a | 2007-08-08 | 2008-03-29 | 2008-03-29 | 234 | 96 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Fatima | 071246018 | Barangay Health Station | 1 | 777140 | 543220 | 233920 | 543220 |  | 228980 | 772200 | 543220 | 228980 | 100% | 100% | 97.89% | 99.36% | 100% | 2008-04-29 | n/a | 2008-08-01 | 2008-12-12 | no data | 133 | 568 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Gabi | 071246019 | Construction of 2 CL School Building | 1 | 1337034 | 933389 | 403645 | 868910.25 |  | 406835 | 1275745.25 | 868910.25 | 406835 | 100% | 100% | 100.8% | 95.42% | 100% | 2008-04-29 | n/a | 2008-07-16 | 2008-10-31 | no data | 107 | 176 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Gov. Boyles | 071246020 | Improvement of Brgy. Gov. Boyles Farm-to-Market Road | 1 | 1927500 | 1348840 | 578660 | 1348840 | 1st Tranche | 638480 | 1987320 | 1348840 | 638480 | 100% | 100% | 110.3% | 103.1% | 100% | 2006-07-15 | n/a | 2006-10-22 | 2007-06-20 | 2007-06-27 | 241 | 193 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Guintabo-an | 071246021 | Rehabilitation of Barangay Farm-to-Market Road | 1 | 726092 | 415292 | 310800 | 415292 | 1st Tranche | 354761.53 | 770053.53 | 415292 | 354761.53 | 100% | 100% | 114.1% | 106.1% | 100% | 2006-07-15 | n/a | 2006-11-16 | 2007-04-12 | 2007-04-19 | 147 | 118 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Hambabauran | 071246022 | FMR with Box Culvert | 1 | 1662709 | 1158249 | 504460 | 1158249 |  | 592900 | 1751149 | 1158249 | 592900 | 100% | 100% | 117.5% | 105.3% | 100% | 2008-04-29 | n/a | 2008-07-28 | 2009-03-20 | n/a | 235 | 200 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Humay-humay | 071246023 | Rehabilitation of Barangay Farm-to-Market Road | 1 | 1457923 | 949298 | 508625 | 854188.2 | 1st Tranche | 512355 | 1366543.2 | 854188.2 | 512355 | 100% | 100% | 100.7% | 93.73% | 100% | 2006-07-15 | n/a | 2006-10-28 | 2007-04-15 | 2007-04-30 | 169 | 303 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Ilihan | 071246024 | Construction of 2 CL School Building | 1 | 1256705 | 877505 | 379200 | 781671 |  | 457865 | 1239536 | 781671 | 457865 | 100% | 100% | 120.7% | 98.63% | 100% | 2007-03-18 | n/a | 2007-07-27 | 2008-01-28 | 2008-01-28 | 185 | 165 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Ilihan | 071246024 | Day Care Center | 1 | 702502 | 491582 | 210920 | 459854 |  | 327700 | 787554 | 459854 | 327700 | 100% | 100% | 155.4% | 112.1% | 100% | 2008-04-29 | n/a | 2008-08-01 | 2008-10-20 | no data | 80 | 166 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Imelda | 071246025 | Farm to Market Road | 1 | 823746 | 511066 | 312680 | 511066 |  | 312680 | 823746 | 511066 | 312680 | 100% | 100% | 100% | 100% | 100% | 2008-04-29 | n/a | 2008-07-24 | 2008-11-28 | no data | 127 | 394 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Juagdan | 071246026 | Construction & Installation of Piped Water System Level II & IV | 1 | 1332554 | 920314 | 412240 | 828282.6 | 1st Tranche | 447290 | 1275572.6 | 828282.6 | 447290 | 100% | 100% | 108.5% | 95.72% | 100% | 2006-07-15 | n/a | 2006-12-15 | 2007-08-07 | no data | 235 | 75 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Juagdan | 071246026 | Improvement Of Brgy. Farm to Market Road | 1 | 1071494 | 696474 | 375020 | 696474 |  | 375020 | 1071494 | 696474 | 375020 | 100% | 100% | 100% | 100% | 100% | 2008-04-29 | n/a | 2008-10-01 | 2008-12-29 | no data | 89 | 220 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Katarungan | 071246016 | Improvement of Farm-to-Market Road | 1 | 1514612 | 1006012 | 508600 | 1006012 | 1st Tranche | 549290.004 | 1555302 | 1006012 | 549290 | 100% | 100% | 108% | 102.7% | 100% | 2006-07-15 | n/a | 2006-11-03 | 2007-02-15 | 2007-02-15 | 104 | 275 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Lomangog | 071246031 | Construction of 3 CL Elementary Schoool Building | 1 | 1560903 | 1089960 | 470943 | 980964 |  | 476768 | 1457732 | 980964 | 476768 | 100% | 100% | 101.2% | 93.39% | 100% | 2007-03-18 | n/a | 2007-12-17 | 2008-04-14 | 2008-04-14 | 119 | 384 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Los Angeles | 071246030 | Installation of Level II Waterworks System | 1 | 1654200 | 1151020 | 503180 | 1151020 | 1st Tranche | 503180.0034 | 1654200 | 1151020 | 503180 | 100% | 100% | 100% | 100% | 100% | 2006-07-15 | n/a | 2006-10-28 | 2007-03-25 | 2007-02-06 | 148 | 110 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Pag-asa | 071246032 | Installation of Brgy Pag-asa Elactrification of Purok | 1 | 793107 | 355832 | 437275 | 284665.6 |  | 438175 | 722840.6 | 284665.6 | 438175 | 100% | 100% | 100.2% | 91.14% | 100% | 2007-03-18 | n/a | 2007-10-08 | 2008-05-31 | 2008-05-31 | 236 | 176 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Pangpang | 071246033 | Construction of 2 CL School Building | 1 | 1246621 | 866021 | 380600 | 692816.8 |  | 394505 | 1087321.8 | 692816.8 | 394505 | 100% | 100% | 103.7% | 87.22% | 100% | 2007-03-18 | n/a | 2007-06-28 | 2007-08-17 | 2007-10-16 | 50 | 202 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Pangpang | 071246033 | Communal Latrines | 1 | 149653 | 102543 | 47110 | 97641.25 |  | 48490 | 146131.25 | 97641.25 | 48490 | 100% | 100% | 102.9% | 97.65% | 100% | 2008-04-29 | n/a | 2008-08-19 | 2008-11-29 | no data | 102 | 202 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Poblacion | 071246034 | Brgy Poblacion Multipurpose Site Development cum Farmers Trading Area | 1 | 1692428 | 934148 | 758280 | 932750 |  | 757820 | 1690570 | 932750 | 757820 | 100% | 100% | 99.94% | 99.89% | 100% | 2007-03-18 | n/a | 2007-07-23 | 2007-11-05 | 2007-11-05 | 105 | 669 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | San Francisco | 071246037 | Installation of Brgy San Francisco Electrification | 1 | 2652562 | 1550572 | 1101990 | 1406854.5 |  | 1111100 | 2517954.5 | 1406854.5 | 1111100 | 100% | 100% | 100.8% | 94.93% | 100% | 2007-03-18 | n/a | 2007-09-10 | 2008-05-15 | 2008-05-15 | 248 | 296 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | San Isidro | 071246038 | Improvement of Farm-to-Market Road | 1 | 1490106 | 954906 | 535200 | 954906 | 1st Tranche | 555000 | 1509906 | 954906 | 555000 | 100% | 100% | 103.7% | 101.3% | 100% | 2006-07-15 | n/a | 2006-11-07 | 2007-03-15 | 2007-03-29 | 128 | 110 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | San Pascual | 071246040 | Upgrading and Expansion of Water System | 1 | 4538091 | 2905931 | 1632160 | 2905931 |  | 1624000 | 4529931 | 2905931 | 1624000 | 100% | 100% | 99.5% | 99.82% | 100% | 2007-03-18 | n/a | 2007-10-08 | 2008-10-10 | no data | 368 | 616 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | San Vicente | 071246041 | Construction & Installation of Piped Water System Level I & II | 1 | 1197549 | 822195 | 375354 | 771602.78 |  | 382154 | 1153756.78 | 771602.78 | 382154 | 100% | 100% | 101.8% | 96.34% | 100% | 2007-03-18 | n/a | 2007-06-28 | 2008-02-05 | 2008-02-05 | 222 | 219 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Sentinila | 071246043 | Improvement of Farm to Market Road | 1 | 1231600 | 860500 | 371100 | 860500 |  | 370020 | 1230520 | 860500 | 370020 | 100% | 100% | 99.71% | 99.91% | 100% | 2008-04-29 | n/a | 2008-07-23 | 2008-10-28 | no data | 97 | 201 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Sinandigan | 071246044 | Farm to Market Road | 1 | 1394989 | 975749 | 419240 | 975749 |  | 425320 | 1401069 | 975749 | 425320 | 100% | 100% | 101.5% | 100.4% | 100% | 2008-04-29 | n/a | 2008-07-24 | 2008-12-04 | no data | 133 | 335 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tapal | 071246045 | Improvement of Farm to Market Road | 1 | 1149967 | 797447 | 352520 | 797447 |  | 352520 | 1149967 | 797447 | 352520 | 100% | 100% | 100% | 100% | 100% | 2008-04-29 | n/a | 2008-07-23 | 2008-10-28 | no data | 97 | 281 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tapon | 071246046 | Communal Latrines (7 units) | 1 | 1107216 | 773851 | 333365 | 737815.75 |  | 346825 | 1084640.75 | 737815.75 | 346825 | 100% | 100% | 104% | 97.96% | 100% | 2008-04-29 | n/a | 2008-07-25 | 2008-10-31 | no data | 98 | 481 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tintinan | 071246047 | Construction of Multi-Purpose Building Rainwater Collector | 1 | 904450 | 568330 | 336120 | 454664 | 1st Tranche | 431753.5 | 886417.5 | 454664 | 431753.5 | 100% | 100% | 128.5% | 98.01% | 100% | 2006-07-15 | n/a | 2006-10-26 | 2007-11-16 | no data | 386 | 119 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tipolo | 071246048 | Construction of Two Classroom Sch.Bldg. | 1 | 1766591 | 874786 | 891805 | 874786 |  | 516785 | 1391571 | 874786 | 516785 | 100% | 100% | 57.95% | 78.77% | 100% | 2008-04-29 | n/a | 2008-10-01 | 2008-12-29 | no data | 89 | 486 | from the excess funds of previous cycles | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tubog | 071246049 | Construction of 1 CL School Building | 1 | 725328 | 505793 | 219535 | 492156.1 |  | 224824.5 | 716980.6 | 492156.1 | 224824.5 | 100% | 100% | 102.4% | 98.85% | 100% | 2008-04-29 | n/a | 2008-08-04 | 2008-10-18 | no data | 75 | 175 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tuboran | 071246050 | Construction of Health Center | 1 | 738116 | 406356 | 331760 | 365720.4 | 1st Tranche | 334290 | 700010.4 | 365720.4 | 334290 | 100% | 100% | 100.8% | 94.84% | 100% | 2006-07-15 | n/a | 2006-10-30 | 2007-04-15 | 2007-04-10 | 167 | 235 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Tuboran | 071246050 | Farm to Market Road | 1 | 701491 | 487641 | 213850 | 485073.46 |  | 216895 | 701968.46 | 485073.46 | 216895 | 100% | 100% | 101.4% | 100.1% | 100% | 2008-04-29 | n/a | 2008-06-02 | 2008-11-21 | no data | 172 | 235 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Union | 071246052 | Improvement of Farm to Market Road | 1 | 1189034 | 819494 | 369540 | 819494 |  | 330900 | 1150394 | 819494 | 330900 | 100% | 100% | 89.54% | 96.75% | 100% | 2008-04-29 | n/a | 2008-07-24 | 2008-12-13 | no data | 142 | 465 |  | 1 | VISAYAS
VII | 07 | Bohol | 0712 | Ubay | 071246 | Villa Teresita | 071246054 | Improvement of Brgy Teresita Farm to Market Road | 1 | 1400959 | 972419 | 428540 | 972419 |  | 485559.9999 | 1457979 | 972419 | 485560 | 100% | 100% | 113.3% | 104.1% | 100% | 2007-03-18 | n/a | 2007-07-25 | 2008-06-20 | 2008-06-20 | 331 | 303 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Balolong | 076101001 | Asphalting of Balolong Farm-to-Market Road | 1 | 1017064 | 947255 | 69809 | 947255 | 3rd Tranche | 51242 | 998497 | 947255 | 51242 | 100% | 100% | 73.4% | 98.17% | 100% | 2005-01-22 | 2005-03-30 | 2005-05-15 | 2005-07-13 | 2005-07-30 | 59 | 87 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Balolong | 076101001 | Electrification | 1 | 472298 | 282725 | 189573 | 270012 | 1st | 189573 | 459585 | 270012 | 189573 | 100% | 100% | 100% | 97.31% | 100% | 2009-02-09 | no data | 2009-04-04 | 2009-05-18 | n/a | 44 | 16 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bino-ongan | 076101002 | Construction of Day Care Center | 1 | 703782 | 509309 | 194473 | 458378.1 | 1st | 196323.8 | 654701.9 | 458378.1 | 196323.8 | 100% | 100% | 101% | 93.03% | 100% | 2009-02-09 | no data | 2009-04-02 | 2009-06-16 | n/a | 75 | 114 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bino-ongan | 076101002 | Construction of Waterworks System | 1 | 1152665 | 1097835 | 54830 | 1097835 | 3rd Tranche | 54830 | 1152665 | 1097835 | 54830 | 100% | 100% | 100% | 100% | 100% | 2005-11-21 | 2005-12-16 | 2006-03-01 | 2006-07-09 | 2006-07-12 | 130 | 106 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bitaug | 076101003 | Const. of 1 Unit Production Well | 1 | 618237 | 486836.1 | 131400.9 | 486836.1 | 1st | 130700.9 | 630435.2 | 486836.1 | 143599.1 | 100% | 109.9% | 99.47% | 102% | 100% | 2009-02-09 | no data | 2009-04-13 | 2009-06-25 | n/a | 73 | 188 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bolot | 076101004 | Bolot Electrification Project | 1 | 1646359.5 | 1324462 | 321897.5 | 1324462 | 3rd Tranche | 90220 | 1414682 | 1324462 | 90220 | 100% | 100% | 28.03% | 85.93% | 100% | 2005-01-22 | 2005-03-30 | 2005-05-15 | 2005-07-13 | 2005-07-30 | 59 | 59 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bolot | 076101004 | Construction of Day Care Center | 1 | 701184 | 471309 | 229875 | 424178.1 | 1st | 231675 | 655853.1 | 424178.1 | 231675 | 100% | 100% | 100.8% | 93.54% | 100% | 2009-02-09 | no data | 2009-03-30 | 2009-06-16 | n/a | 78 | 31 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Camogao | 076101005 | Construction of Seawall | 1 | 799204 | 514460 | 284744 | 508352.5 | 1st | 309702.37 | 818054.87 | 508352.5 | 309702.37 | 100% | 100% | 108.8% | 102.4% | 100% | 2009-02-09 | no data | 2009-04-03 | 2009-07-07 | n/a | 95 | 51 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Cangmangki | 076101006 | Construction of Day Care Center | 1 | 738646 | 644100 | 94546 | 644100 | 3rd Tranche | 94546 | 738646 | 644100 | 94546 | 100% | 100% | 100% | 100% | 100% | 2005-11-21 | 2005-12-16 | 2006-03-01 | 2006-04-30 | 2006-03-31 | 60 | 56 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Cangmangki | 076101006 | Construction of Box Culvert and Concrete Pavement Approach | 1 | 697567 | 560060 | 137507 | 448048 | 1st | 139586.3 | 587634.3 | 448048 | 139586.3 | 100% | 100% | 101.5% | 84.24% | 100% | 2009-02-09 | no data | 2009-04-04 | 2009-06-11 | n/a | 68 | 97 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Cangmangki - C5 | 076101006 | Upgrading and Expansion of CAPABILICA Water Works System | 5 | 2905477.0025 | 2132146.5125 | 773330.49 | 2132146.5125 | 3rd Tranche | 540523.13 | 2672669.6425 | 2132146.5125 | 540523.13 | 100% | 100% | 69.9% | 91.99% | 100% | 2003-04-24 | 2003-05-30 | 2003-12-15 | 2005-09-15 | 2005-02-18 | 640 | 475 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Parian | 076101012 | Upgrading and Expansion of CAPABILICA Water Works System | 5 | 2905477.0025 | 2132146.5125 | 773330.49 | 2132146.5125 | 3rd Tranche | 540523.13 | 2672669.6425 | 2132146.5125 | 540523.13 | 100% | 100% | 69.9% | 91.99% | 100% | 2003-04-24 | 2003-05-30 | 2003-12-15 | 2005-09-15 | 2005-02-18 | 640 | 475 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bino-ongan | 076101002 | Upgrading and Expansion of CAPABILICA Water Works System | 5 | 2905477.0025 | 2132146.5125 | 773330.49 | 2132146.5125 | 3rd Tranche | 540523.13 | 2672669.6425 | 2132146.5125 | 540523.13 | 100% | 100% | 69.9% | 91.99% | 100% | 2003-04-24 | 2003-05-30 | 2003-12-15 | 2005-09-15 | 2005-02-18 | 640 | 475 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Libo | 076101007 | Upgrading and Expansion of CAPABILICA Water Works System | 5 | 2905477.0025 | 2132146.5125 | 773330.49 | 2132146.5125 | 3rd Tranche | 540523.13 | 2672669.6425 | 2132146.5125 | 540523.13 | 100% | 100% | 69.9% | 91.99% | 100% | 2003-04-24 | 2003-05-30 | 2003-12-15 | 2005-09-15 | 2005-02-18 | 640 | 475 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Camogao | 076101005 | Upgrading and Expansion of CAPABILICA Water Works System | 5 | 2905477.0025 | 2132146.5125 | 773330.49 | 2132146.5125 | 3rd Tranche | 540523.13 | 2672669.6425 | 2132146.5125 | 540523.13 | 100% | 100% | 69.9% | 91.99% | 100% | 2003-04-24 | 2003-05-30 | 2003-12-15 | 2005-09-15 | 2005-02-18 | 640 | 475 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Libo | 076101007 | Construction of New Home Economics Bldg. with Facilities | 1 | 920369 | 760470 | 159899 | 760470 | 3rd Tranche | 184899 | 945369 | 760470 | 184899 | 100% | 100% | 115.6% | 102.7% | 100% | 2005-11-21 | 2005-12-16 | 2006-03-01 | 2006-05-10 | 2006-06-01 | 70 | 131 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Libo | 076101007 | Excavation of Libo River Bed | 1 | 867306 | 646406.01 | 220899.99 | 640300.16 | 1st | 220899.99 | 861200.15 | 640300.16 | 220899.99 | 100% | 100% | 100% | 99.3% | 100% | 2009-02-09 | no data | 2009-04-06 | 2009-05-25 | n/a | 49 | 138 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Lomangcapan | 076101008 | Construction of Day Care Center | 1 | 702584 | 539604 | 162980 | 485643.6 | 1st | 162980 | 648623.6 | 485643.6 | 162980 | 100% | 100% | 100% | 92.32% | 100% | 2009-02-09 | no data | 2009-03-30 | 2009-06-05 | n/a | 67 | 153 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Lotloton | 076101009 | Construction of FMR | 1 | 1095021 | 674948.89 | 420072.11 | 670267.2 | 1st | 420757.97 | 1091025.17 | 670267.2 | 420757.97 | 100% | 100% | 100.2% | 99.64% | 100% | 2009-02-09 | no data | 2009-04-06 | 2009-06-16 | n/a | 71 | 111 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Manan-ao | 076101010 | re-surfacing of 680m Farm to Market Road | 1 | 248777 | 235385 | 13392 | 235385 | 3rd Tranche | 13392 | 248777 | 235385 | 13392 | 100% | 100% | 100% | 100% | 100% | 2005-11-21 | 2005-12-16 | 2006-03-01 | 2006-03-27 | 2006-03-31 | 26 | 115 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Manan-ao | 076101010 | Construction of Day Care Center | 1 | 706884 | 524909 | 181975 | 472418.1 | 1st | 181975 | 654393.1 | 472418.1 | 181975 | 100% | 100% | 100% | 92.57% | 100% | 2009-02-09 | no data | 2009-03-30 | 2009-06-23 | n/a | 85 | 30 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Olave | 076101011 | Olave Electrification Project | 1 | 1097000 | 620611.05 | 476388.95 | 620611.05 | 3rd Tranche | 476388.95 | 1097000 | 620611.05 | 476388.95 | 100% | 100% | 100% | 100% | 100% | 2003-04-24 | 2003-05-30 | 2003-08-04 | 2003-10-14 | 2003-10-14 | 71 | 51 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Olave | 076101011 | Asphalting of Lower Libo-Lower Olave Farm-to-Market Road | 1 | 1444528 | 1353000 | 91528 | 1353000 | 3rd Tranche | 71821.05 | 1424821.05 | 1353000 | 71821.05 | 100% | 100% | 78.47% | 98.64% | 100% | 2005-01-22 | 2005-03-30 | 2005-05-15 | 2005-07-13 | 2005-07-30 | 59 | 143 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Olave | 076101011 | Opening and Asphalt Paving of Olave Farm to Market Road | 1 | 1750515 | 551444 | 1199071 | 544962 | 1st | 1195071.16 | 1740033.16 | 544962 | 1195071.16 | 100% | 100% | 99.67% | 99.4% | 100% | 2009-02-09 | no data | 2009-04-03 | 2009-06-07 | n/a | 65 | 62 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Parian | 076101012 | Improvement/Repair/Rehabilitation of 500m Farm to Market Road | 1 | 979756 | 897370 | 82386 | 897370 | 3rd Tranche | 82386 | 979756 | 897370 | 82386 | 100% | 100% | 100% | 100% | 100% | 2005-11-21 | 2005-12-16 | 2006-03-01 | 2006-05-29 | 2006-06-01 | 89 | 205 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Parian | 076101012 | Construction of Day Care Center | 1 | 701684 | 509309 | 192375 | 461487.76 | 1st | 192375 | 653862.76 | 461487.76 | 192375 | 100% | 100% | 100% | 93.18% | 100% | 2009-02-09 | no data | 2009-04-06 | 2009-06-16 | n/a | 71 | 45 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Poblacion | 076101013 | Construction of Day Care Center | 1 | 641085 | 564840 | 76245 | 564840 | 3rd Tranche | 76245 | 641085 | 564840 | 76245 | 100% | 100% | 100% | 100% | 100% | 2005-11-21 | 2005-12-16 | 2006-03-01 | 2006-05-10 | 2006-03-31 | 70 | 49 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Poblacion | 076101013 | Installation of Poblacion Level I Waterworks System | 1 | 538695 | 365890 | 172805 | 361882 | 1st | 172805 | 534687 | 361882 | 172805 | 100% | 100% | 100% | 99.26% | 100% | 2009-02-09 | no data | 2009-05-04 | 2009-07-04 | n/a | 61 | 108 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Poblacion - C3 | 076101013 | Upgrading and Expansion of PMT Water Works System | 3 | 2044400 | 1382323.96 | 662076.04 | 1382323.958 | 3rd Tranche | 605105.75 | 1987429.708 | 1382323.958 | 605105.75 | 100% | 100% | 91.4% | 97.21% | 100% | 2003-04-24 | 2003-05-30 | 2003-11-03 | 2004-08-31 | 2004-08-31 | 302 | 325 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Manan-ao | 076101010 | Upgrading and Expansion of PMT Water Works System | 3 | 2044400 | 1382323.96 | 662076.04 | 1382323.958 | 3rd Tranche | 605105.75 | 1987429.708 | 1382323.958 | 605105.75 | 100% | 100% | 91.4% | 97.21% | 100% | 2003-04-24 | 2003-05-30 | 2003-11-03 | 2004-08-31 | 2004-08-31 | 302 | 325 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Tulapos | 076101014 | Upgrading and Expansion of PMT Water Works System | 3 | 2044400 | 1382323.96 | 662076.04 | 1382323.958 | 3rd Tranche | 605105.75 | 1987429.708 | 1382323.958 | 605105.75 | 100% | 100% | 91.4% | 97.21% | 100% | 2003-04-24 | 2003-05-30 | 2003-11-03 | 2004-08-31 | 2004-08-31 | 302 | 325 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Tulapos | 076101014 | Construction of Tulapos Daycare Center | 1 | 680700 | 567135 | 113565 | 567135 | 3rd Tranche | 73524.06 | 640659.06 | 567135 | 73524.06 | 100% | 100% | 64.74% | 94.12% | 100% | 2005-01-22 | 2005-03-30 | 2005-05-17 | 2005-06-30 | 2005-07-30 | 44 | 11 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Enrique Villanueva | 076101 | Tulapos | 076101014 | Electrification | 1 | 724140 | 362790 | 361350 | 362790 | 1st | 361350 | 724140 | 362790 | 361350 | 100% | 100% | 100% | 100% | 100% | 2009-02-09 | no data | 2009-04-06 | 2009-08-28 | n/a | 144 | 55 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Banban | 076106001 | Construction of Footwalk | 1 | 659817 | 434512 | 225305 | 432913 | 1st | 229425.5 | 662338.5 | 432913 | 229425.5 | 100% | 100% | 101.8% | 100.4% | 100% | 2009-02-02 | no data | 2009-03-30 | 2009-06-05 | n/a | 67 | 150 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Bolos | 076106002 | Opening of Farm to Market Road | 1 | 627740 | 514624 | 113116 | 490520.59 | 1st | 113116 | 603636.59 | 490520.59 | 113116 | 100% | 100% | 100% | 96.16% | 100% | 2009-02-02 | no data | 2009-04-21 | 2009-06-10 | n/a | 50 | 64 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caipilan | 076106003 | Asphalting of Farm to Market Road | 1 | 624120 | 526704 | 97416 | 524479.25 | 1st | 97416 | 621895.25 | 524479.25 | 97416 | 100% | 100% | 100% | 99.64% | 100% | 2009-02-02 | no data | 2009-04-02 | 2009-05-30 | n/a | 58 | 234 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caipilan - C8 | 076106003 | Construction of Water System | 8 | 6374152 | 3534652.5 | 2839499.5 | 3534652.5 | 3rd Tranche | 3109461.3 | 6644113.8 | 3534652.5 | 3109461.3 | 100% | 100% | 109.5% | 104.2% | 100% | 2003-11-08 | 2003-11-18 | 2004-07-20 | 2005-09-03 | 2005-09-03 | 410 | 1000 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caitican | 076106004 | Asphalting of Farm to Market Road | 1 | 630409 | 467992.96 | 162416.04 | 445524.23 | 1st | 162416.04 | 607940.27 | 445524.23 | 162416.04 | 100% | 100% | 100% | 96.44% | 100% | 2009-02-02 | no data | 2009-04-17 | 2009-06-15 | n/a | 59 | 92 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Calalinan | 076106005 | Day Care Center | 1 | 593326 | 195996.5 | 397329.5 | 195996.5 | 3rd Tranche | 417295.3 | 613291.8 | 195996.5 | 417295.3 | 100% | 100% | 105% | 103.4% | 100% | 2003-11-08 | 2003-11-18 | 2004-01-19 | 2004-08-31 | 2004-08-31 | 225 | 112 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Calalinan | 076106005 | Asphalting of Farm to Market Road | 1 | 622082 | 426859.45 | 195222.55 | 401933.93 | 1st | 195222.55 | 597156.48 | 401933.93 | 195222.55 | 100% | 100% | 100% | 95.99% | 100% | 2009-02-02 | no data | 2009-04-05 | 2009-06-15 | n/a | 71 | 134 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Canal | 076106007 | Rehab / Asphalt Paving of FMR | 1 | 627916 | 473000 | 154916 | 449083.41 | 1st | 154916 | 603999.41 | 449083.41 | 154916 | 100% | 100% | 100% | 96.19% | 100% | 2009-02-02 | no data | 2009-03-30 | 2009-06-15 | n/a | 77 | 78 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Candanay Norte | 076106008 | Rehabilitation/Asphalt Paving of FMR | 1 | 630987 | 523929.2 | 107057.8 | 513255.89 | 1st | 107057.8 | 620313.69 | 513255.89 | 107057.8 | 100% | 100% | 100% | 98.31% | 100% | 2009-02-02 | no data | 2009-03-27 | 2009-06-30 | n/a | 95 | 185 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Candanay Sur | 076106009 | Acquisition of 1 Unit Vehicle | 1 | 524371 | 415000 | 109371 | 415000 | 1st | 187976.35 | 602976.35 | 415000 | 187976.35 | 100% | 100% | 171.9% | 115% | 100% | 2009-02-02 | no data | 2009-06-08 | 2009-06-15 | n/a | 7 | 174 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-adieng | 076106010 | Construction of Cornmill Building with Equipment and Solar Dryer Pavement | 1 | 671926 | 504837.22 | 167088.78 | 490075.22 | 1st | 174930.03 | 665005.25 | 490075.22 | 174930.03 | 100% | 100% | 104.7% | 98.97% | 100% | 2009-02-02 | no data | 2009-03-27 | 2009-05-22 | n/a | 56 | 61 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-agong | 076106011 | Road Opening/Asphalt Paving of FMR | 1 | 631822 | 544999.9 | 86822.1 | 544361.69 | 1st | 86822.1 | 631183.79 | 544361.69 | 86822.1 | 100% | 100% | 100% | 99.9% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-06-20 | n/a | 80 | 190 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-agong - C3 | 076106011 | Construction of Water System | 3 | 3071614 | 1276822.35 | 1794791.65 | 1276822.35 | 3rd Tranche | 1600824.17 | 2877646.52 | 1276822.35 | 1600824.17 | 100% | 100% | 89.19% | 93.69% | 100% | 2003-11-08 | 2003-11-18 | 2004-06-07 | 2005-09-25 | 2005-09-25 | 475 | 374 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Sabang | 076106034 | Construction of Water System | 3 | 3071614 | 1276822.35 | 1794791.65 | 1276822.35 | 3rd Tranche | 1600824.17 | 2877646.52 | 1276822.35 | 1600824.17 | 100% | 100% | 89.19% | 93.69% | 100% | 2003-11-08 | 2003-11-18 | 2004-06-07 | 2005-09-25 | 2005-09-25 | 475 | 374 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Luyang | 076106024 | Construction of Water System | 3 | 3071614 | 1276822.35 | 1794791.65 | 1276822.35 | 3rd Tranche | 1600824.17 | 2877646.52 | 1276822.35 | 1600824.17 | 100% | 100% | 89.19% | 93.69% | 100% | 2003-11-08 | 2003-11-18 | 2004-06-07 | 2005-09-25 | 2005-09-25 | 475 | 374 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-alwang | 076106012 | Opening of Farm-to-Market Road | 1 | 2571127 | 1485099.97 | 1086027.03 | 1483621.27 |  | 109620.31 | 1593241.58 | 1483621.27 | 109620.31 | 100% | 100% | 10.09% | 61.97% | 100% | 2006-07-18 | n/a | 2006-10-30 | 2007-06-25 | no data | 238 | 160 | completed as built | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-alwang | 076106012 | Construction of Day Care Center | 1 | 667237 | 411375 | 255862 | 406279.25 | 1st | 250265.5 | 656544.75 | 406279.25 | 250265.5 | 100% | 100% | 97.81% | 98.4% | 100% | 2009-02-02 | no data | 2009-03-23 | 2009-05-24 | n/a | 62 | 162 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-asa | 076106013 | Construction of Level II Waterworks System | 1 | 925712 | 602130.2 | 323581.8 | 602130.2 |  | 50857.8 | 652988 | 602130.2 | 50857.8 | 100% | 100% | 15.72% | 70.54% | 100% | 2006-07-18 | n/a | 2006-10-03 | 2007-06-25 | no data | 265 | 197 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-asa | 076106013 | Acquisition of 1 Unit Vehicle | 1 | 650025 | 442500.1 | 207524.9 | 441523.1 | 1st | 212124.9 | 653648 | 441523.1 | 212124.9 | 100% | 100% | 102.2% | 100.6% | 100% | 2009-02-02 | no data | 2009-06-01 | 2009-06-20 | n/a | 19 | 202 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-atuyom | 076106006 | Construction of Solar Dryer Pavement | 1 | 631730 | 497660 | 134070 | 497660 | 1st | 134070 | 631730 | 497660 | 134070 | 100% | 100% | 100% | 100% | 100% | 2009-02-02 | no data | 2009-03-24 | 2009-05-23 | n/a | 60 | 72 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Canghunoghunog | 076106016 | Acqisition of 1 Unit Vehicle with Garage | 1 | 656071 | 568043 | 88028 | 528311.2 | 1st | 87708 | 616019.2 | 528311.2 | 87708 | 100% | 100% | 99.64% | 93.9% | 100% | 2009-02-02 | no data | 2009-06-01 | 2009-06-15 | n/a | 14 | 72 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Canghunog-hunog | 076106016 | Electrification | 1 | 780517 | 572531.54 | 207985.46 | 572531.54 | 3rd Tranche | 209985.46 | 782517 | 572531.54 | 209985.46 | 100% | 100% | 101% | 100.3% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-19 | 2006-02-10 | 2006-02-10 | 114 | 41 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Canghunog-hunog | 076106016 | Construction of Day Care Center | 1 | 646564 | 541168.71 | 105395.29 | 541168.71 |  | 41018.42 | 582187.13 | 541168.71 | 41018.42 | 100% | 100% | 38.92% | 90.04% | 100% | 2006-07-18 | n/a | 2006-10-03 | 2006-12-27 | 2006-12-27 | 85 | 46 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-inte | 076106014 | Farm to Market Road | 1 | 2547909 | 2459288.26 | 88620.74 | 2459288.26 | 3rd Tranche | 51499.24 | 2510787.5 | 2459288.26 | 51499.24 | 100% | 100% | 58.11% | 98.54% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-24 | 2006-02-24 | 2006-10-06 | 123 | 41 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-inte | 076106014 | Cang-inte Electrification Project | 1 | 748321 | 489026 | 259295 | 460427.5 | 1st | 229399.5 | 689827 | 460427.5 | 229399.5 | 100% | 100% | 88.47% | 92.18% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-05-27 | n/a | 56 | 25 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-isad | 076106015 | Farm to Market Road | 1 | 2753900 | 2634574.2 | 119325.8 | 2634574.2 | 3rd Tranche | 38737.8 | 2673312 | 2634574.2 | 38737.8 | 100% | 100% | 32.46% | 97.07% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-24 | 2006-01-15 | 2006-01-15 | 83 | 32 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-isad | 076106015 | Cang-isad Electrification | 1 | 702164 | 525799 | 176365 | 520260.35 | 1st | 166702.5 | 686962.85 | 520260.35 | 166702.5 | 100% | 100% | 94.52% | 97.84% | 100% | 2009-02-02 | no data | 2009-04-12 | 2009-05-25 | n/a | 43 | 13 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cangmatnog | 076106017 | Electrification | 1 | 746200 | 237092.55 | 509107.45 | 213383.295 | 2nd Tranche | 312943.91 | 526327.205 | 213383.295 | 312943.91 | 100% | 100% | 61.47% | 70.53% | 100% | 2003-11-08 | 2003-11-18 | 2004-01-09 | 2004-09-25 | 2004-09-25 | 260 | 38 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cangmatnog | 076106017 | Construction of Cornmill Bldg with Equipment and Pathwalk Pavement | 1 | 668269 | 544835.66 | 123433.34 | 543711.16 | 1st | 122203.34 | 665914.5 | 543711.16 | 122203.34 | 100% | 100% | 99% | 99.65% | 100% | 2009-02-02 | no data | 2009-04-07 | 2009-06-07 | n/a | 61 | 40 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cangmohao | 076106018 | Asphalting of Farm to Market Road | 1 | 624533 | 558923.55 | 65609.45 | 538332.14 | 1st | 65609.45 | 603941.59 | 538332.14 | 65609.45 | 100% | 100% | 100% | 96.7% | 100% | 2009-02-02 | no data | 2009-04-14 | 2009-06-12 | n/a | 59 | 49 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cantabon - C2 | 076106019 | Construction of Water System | 2 | 2852198 | 2027462 | 824736 | 2027462 | 3rd Tranche | 906910.1 | 2934372.1 | 2027462 | 906910.1 | 100% | 100% | 110% | 102.9% | 100% | 2003-11-08 | 2003-11-18 | 2004-10-12 | 2005-09-08 | 2005-09-08 | 331 | 142 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tebjong | 076106040 | Construction of Water System | 2 | 2852198 | 2027462 | 824736 | 2027462 | 3rd Tranche | 906910.1 | 2934372.1 | 2027462 | 906910.1 | 100% | 100% | 110% | 102.9% | 100% | 2003-11-08 | 2003-11-18 | 2004-10-12 | 2005-09-08 | 2005-09-08 | 331 | 142 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cantabon | 076106019 | Construction of Day Care Center | 1 | 671229 | 533421.5 | 137807.5 | 506168.88 | 1st | 141928 | 648096.88 | 506168.88 | 141928 | 100% | 100% | 103% | 96.55% | 100% | 2009-02-02 | no data | 2009-03-24 | 2009-06-10 | n/a | 78 | 97 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caticugan | 076106020 | Construction of Cornmill with Equipement | 1 | 648493 | 440448.5 | 208044.5 | 396403.65 | 1st | 205590.16 | 601993.81 | 396403.65 | 205590.16 | 100% | 100% | 98.82% | 92.83% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-05-26 | n/a | 55 | 172 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Dumanhog | 076106021 | Farm to Market Road | 1 | 2057091.6 | 1935571.6 | 121520 | 1935571.6 | 3rd Tranche | 107520.4 | 2043092 | 1935571.6 | 107520.4 | 100% | 100% | 88.48% | 99.32% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-19 | 2006-02-28 | 2006-02-28 | 132 | 94 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Dumanhog | 076106021 | Rehab / Asphalt Paving of FMR | 1 | 631232 | 483200 | 148032 | 455354.05 | 1st | 148032 | 603386.05 | 455354.05 | 148032 | 100% | 100% | 100% | 95.59% | 100% | 2009-02-02 | no data | 2009-03-24 | 2009-05-14 | n/a | 51 | 111 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Ibabao | 076106022 | Upgrading and And Asphalt Paving of Farm-to-Market Road | 1 | 2339159 | 1401895.3 | 937263.7 | 1384950.91 |  | 99636.65 | 1484587.56 | 1384950.91 | 99636.65 | 100% | 100% | 10.63% | 63.47% | 100% | 2006-07-18 | n/a | 2006-10-30 | 2007-06-25 | no data | 238 | 65 | completed as built | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Ibabao | 076106022 | Construction of Solar Dryer Pavement | 1 | 631793 | 507546.5 | 124246.5 | 493617.73 | 1st | 126798.75 | 620416.48 | 493617.73 | 126798.75 | 100% | 100% | 102.1% | 98.2% | 100% | 2009-02-02 | no data | 2009-04-16 | 2009-06-22 | n/a | 67 | 63 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Lambojon | 076106023 | Asphalting of Farm to Market Road | 1 | 631239 | 495000 | 136239 | 492872.92 | 1st | 136239 | 629111.92 | 492872.92 | 136239 | 100% | 100% | 100% | 99.66% | 100% | 2009-02-02 | no data | 2009-03-29 | 2009-06-22 | n/a | 85 | 67 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Luyang | 076106024 | Construction of Barangay Health Station | 1 | 660105 | 491720.43 | 168384.57 | 488776.15 | 1st | 162480.57 | 651256.72 | 488776.15 | 162480.57 | 100% | 100% | 96.49% | 98.66% | 100% | 2009-02-02 | no data | 2009-03-25 | 2009-06-05 | n/a | 72 | 143 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Luzong | 076106025 | Farm To Market Road | 1 | 1900880 | 1015496.36 | 885383.64 | 1015496.36 | 3rd Tranche | 1069151.81 | 2084648.17 | 1015496.36 | 1069151.81 | 100% | 100% | 120.8% | 109.7% | 100% | 2003-11-08 | 2003-11-18 | 2004-02-16 | 2005-01-27 | 2005-01-27 | 346 | 109 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Luzong | 076106025 | Construction of Day Care Center | 1 | 683789 | 492273.99 | 191515.01 | 472250.81 | 1st | 178846.01 | 651096.82 | 472250.81 | 178846.01 | 100% | 100% | 93.38% | 95.22% | 100% | 2009-02-02 | no data | 2009-04-17 | 2009-06-17 | n/a | 61 | 110 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Olo | 076106026 | Farm to Market Road | 1 | 1141360 | 1056673.99 | 84686.01 | 1056673.99 | 3rd Tranche | 44030.51 | 1100704.5 | 1056673.99 | 44030.51 | 100% | 100% | 51.99% | 96.44% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-21 | 2005-12-15 | 2005-12-15 | 55 | 125 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Olo | 076106026 | Upgrading and And Asphalt Paving of Farm-to-Market Road | 1 | 1121679 | 554209.12 | 567469.88 | 546815.46 |  | 47677.23 | 594492.69 | 546815.46 | 47677.23 | 100% | 100% | 8.402% | 53% | 100% | 2006-07-18 | n/a | 2006-09-28 | 2007-06-25 | no data | 270 | 104 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Olo | 076106026 | Rehab / Asphalt Paving of FMR | 1 | 632354 | 505000 | 127354 | 483799.63 | 1st | 127354 | 611153.63 | 483799.63 | 127354 | 100% | 100% | 100% | 96.65% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-05-25 | n/a | 54 | 123 | completed as built | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pangi | 076106027 | Construction of Day Care Center | 1 | 675281 | 588625 | 86656 | 570937.17 | 1st | 83089 | 654026.17 | 570937.17 | 83089 | 100% | 100% | 95.88% | 96.85% | 100% | 2009-02-02 | no data | 2009-03-31 | 2009-06-22 | n/a | 83 | 228 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Panlautan | 076106028 | Farm to Market Road | 1 | 2103939 | 1995630.86 | 108308.14 | 1995630.86 | 3rd Tranche | 46473.64 | 2042104.5 | 1995630.86 | 46473.64 | 100% | 100% | 42.91% | 97.06% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-21 | 2006-03-31 | 2006-03-31 | 161 | 44 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Panlautan | 076106028 | Construction of Level II Waterworks System | 1 | 1670368 | 1301468.88 | 368899.12 | 1292695.05 |  | 134075.21 | 1426770.26 | 1292695.05 | 134075.21 | 100% | 100% | 36.34% | 85.42% | 100% | 2006-07-18 | n/a | 2006-10-04 | 2007-06-25 | no data | 264 | 42 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Panlautan | 076106028 | Construction of Day Care Center | 1 | 677281 | 485399 | 191882 | 482680.99 | 1st | 183794.75 | 666475.74 | 482680.99 | 183794.75 | 100% | 100% | 95.79% | 98.4% | 100% | 2009-02-02 | no data | 2009-03-31 | 2009-06-25 | n/a | 86 | 43 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pasihagon | 076106029 | Construction of Water System | 1 | 2869653 | 1711473.69 | 1158179.31 | 1711473.69 | 3rd Tranche | 1218718.25 | 2930191.94 | 1711473.69 | 1218718.25 | 100% | 100% | 105.2% | 102.1% | 100% | 2003-11-08 | 2003-11-18 | 2004-05-17 | 2005-01-27 | 2005-01-27 | 255 | 235 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pasihagon | 076106029 | Improvement of Water Works System Level II | 1 | 666308 | 482687 | 183621 | 476097.2 | 1st | 189244.5 | 665341.7 | 476097.2 | 189244.5 | 100% | 100% | 103.1% | 99.85% | 100% | 2009-02-02 | no data | 2009-03-26 | 2009-06-30 | n/a | 96 | 233 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pili | 076106030 | Asphalting of Farm to Market Road | 1 | 622645 | 446729 | 175916 | 445398.51 | 1st | 175916 | 621314.51 | 445398.51 | 175916 | 100% | 100% | 100% | 99.79% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-05-15 | n/a | 44 | 77 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pili - C2 | 076106030 | Construction of Water System | 2 | 2932366 | 1846378.4 | 1085987.6 | 1846378.4 | 3rd Tranche | 1155434.4 | 3001812.8 | 1846378.4 | 1155434.4 | 100% | 100% | 106.4% | 102.4% | 100% | 2003-11-08 | 2003-11-18 | 2004-07-07 | 2006-01-14 | 2006-01-14 | 556 | 204 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Banban | 076106001 | Construction of Water System | 2 | 2932366 | 1846378.4 | 1085987.6 | 1846378.4 | 3rd Tranche | 1155434.4 | 3001812.8 | 1846378.4 | 1155434.4 | 100% | 100% | 106.4% | 102.4% | 100% | 2003-11-08 | 2003-11-18 | 2004-07-07 | 2006-01-14 | 2006-01-14 | 556 | 204 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Poblacion | 076106031 | Drainage Canal | 1 | 1309523 | 1214725.94 | 94797.06 | 1214725.94 | 3rd Tranche | 94797.06 | 1309523 | 1214725.94 | 94797.06 | 100% | 100% | 100% | 100% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-19 | 2006-02-09 | 2006-02-09 | 113 | 245 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Poblacion | 076106031 | Construction of Drainage Canal | 1 | 520168 | 426237.17 | 93930.83 | 426237.17 |  | 35081.89 | 461319.06 | 426237.17 | 35081.89 | 100% | 100% | 37.35% | 88.69% | 100% | 2006-07-18 | n/a | 2006-09-28 | 2006-11-22 | no data | 55 | 239 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Poblacion | 076106031 | Construction of Reinforced Concrete Canal | 1 | 673485 | 548350 | 125135 | 524026.5 | 1st | 124766 | 648792.5 | 524026.5 | 124766 | 100% | 100% | 99.71% | 96.33% | 100% | 2009-02-02 | no data | 2009-03-17 | 2009-06-28 | n/a | 103 | 263 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Ponong | 076106033 | Construction of Level II Waterworks System | 1 | 1369107 | 1051990.23 | 317116.77 | 1027690.72 |  | 80944.77 | 1108635.49 | 1027690.72 | 80944.77 | 100% | 100% | 25.53% | 80.98% | 100% | 2006-07-18 | n/a | 2006-10-03 | 2007-06-25 | no data | 265 | 175 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Ponong | 076106033 | Construction of Corn Mill Building with Equipment | 1 | 670639 | 518214.22 | 152424.78 | 505237.22 | 1st | 154731.03 | 659968.25 | 505237.22 | 154731.03 | 100% | 100% | 101.5% | 98.41% | 100% | 2009-02-02 | no data | 2009-04-13 | 2009-06-13 | n/a | 61 | 169 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pulangyuta | 076106032 | Rehabilitation of Water System Level II | 1 | 802451 | 548982.5 | 253468.5 | 548982.5 | 1st | 232849.5 | 781832 | 548982.5 | 232849.5 | 100% | 100% | 91.87% | 97.43% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-11-30 | n/a | 243 | 34 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Sabang | 076106034 | Asphalting of Farm to Market Road | 1 | 622579 | 476663 | 145916 | 428996.7 | 1st | 146016 | 575012.7 | 428996.7 | 146016 | 100% | 100% | 100.1% | 92.36% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-05-30 | n/a | 59 | 56 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | San Antonio | 076106035 | Construction of Trading Post | 1 | 902536 | 326572.36 | 575963.64 | 326572.36 |  | 15686.31 | 342258.67 | 326572.36 | 15686.31 | 100% | 100% | 2.723% | 37.92% | 100% | 2006-07-18 | n/a | 2006-10-23 | 2008-03-28 | no data | 522 | 136 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | San Antonio | 076106035 | Construction of Barangay Health Station | 1 | 652303 | 560000 | 92303 | 556634.5 | 1st | 99621.5 | 656256 | 556634.5 | 99621.5 | 100% | 100% | 107.9% | 100.6% | 100% | 2009-02-02 | no data | 2009-04-01 | 2009-06-25 | n/a | 85 | 179 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Songculan | 076106036 | Road Opening of 884.4m Songculan Farm-to-Market Road | 1 | 2615531 | 754596.5 | 1860934.5 | 754596.5 | 3rd Tranche | 1155376.5 | 1909973 | 754596.5 | 1155376.5 | 100% | 100% | 62.09% | 73.02% | 100% | 2003-11-08 | 2003-11-18 | 2004-07-13 | 2005-09-08 | 2005-09-08 | 422 | 53 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Songculan | 076106036 | Rehab / Asphalt Paving of FMR | 1 | 631357 | 565000 | 66357 | 548674.3 | 1st | 66357 | 615031.3 | 548674.3 | 66357 | 100% | 100% | 100% | 97.41% | 100% | 2009-02-02 | no data | 2009-04-03 | 2009-06-28 | n/a | 86 | 50 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tacdog | 076106037 | Solar Drier | 1 | 824499 | 731003.61 | 93495.39 | 731003.61 | 3rd Tranche | 93495.36 | 824498.97 | 731003.61 | 93495.36 | 100% | 100% | 100% | 100% | 100% | 2005-07-15 | 2005-09-09 | 2005-10-19 | 2006-02-09 | 2006-02-09 | 113 | 82 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tacdog | 076106037 | Upgrading and And Asphalt Paving of Farm-to-Market Road | 1 | 1848337 | 1117592.4 | 730744.6 | 1106074 |  | 127766.43 | 1233840.43 | 1106074 | 127766.43 | 100% | 100% | 17.48% | 66.75% | 100% | 2006-07-18 | n/a | 2006-10-04 | 2007-06-25 | no data | 264 | 85 | completed as built | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tacdog | 076106037 | Construction of Reinforced Concrete Canal | 1 | 672843 | 526857.5 | 145985.5 | 496624.75 | 1st | 145599 | 642223.75 | 496624.75 | 145599 | 100% | 100% | 99.74% | 95.45% | 100% | 2009-02-02 | no data | 2009-03-20 | 2009-06-10 | n/a | 82 | 98 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tacloban | 076106038 | Road Opening of FMR | 1 | 631232 | 435000 | 196232 | 433349.95 | 1st | 196232 | 629581.95 | 433349.95 | 196232 | 100% | 100% | 100% | 99.74% | 100% | 2009-02-02 | no data | 2009-03-31 | 2009-06-06 | n/a | 67 | 139 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tambisan | 076106039 | Construction of Level II Waterworks System | 1 | 1743688 | 1348612.44 | 395075.56 | 1310772.64 |  | 100817.56 | 1411590.2 | 1310772.64 | 100817.56 | 100% | 100% | 25.52% | 80.95% | 100% | 2006-07-18 | n/a | 2006-10-04 | 2007-06-25 | no data | 264 | 148 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tambisan | 076106039 | Construction of Day Care Center | 1 | 679141 | 492114.75 | 187026.25 | 469340.75 | 1st | 184166.5 | 653507.25 | 469340.75 | 184166.5 | 100% | 100% | 98.47% | 96.23% | 100% | 2009-02-02 | no data | 2009-03-25 | 2009-05-28 | n/a | 64 | 150 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tebjong | 076106040 | Upgrading and And Asphalt Paving of Farm-to-Market Road | 1 | 2533348 | 1575282.15 | 958065.85 | 1556808.36 |  | 124300.6 | 1681108.96 | 1556808.36 | 124300.6 | 100% | 100% | 12.97% | 66.36% | 100% | 2006-07-18 | n/a | 2006-10-30 | 2007-06-25 | no data | 238 | 49 | completed as built | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tebjong | 076106040 | Asphalting of Farm to Market Road | 1 | 630507 | 451650 | 178857 | 427232.17 | 1st | 179057 | 606289.17 | 427232.17 | 179057 | 100% | 100% | 100.1% | 96.16% | 100% | 2009-02-02 | no data | 2009-04-02 | 2009-06-30 | n/a | 89 | 48 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tinago | 076106041 | Construction of Day Care Center | 1 | 646564 | 541168.71 | 105395.29 | 541168.71 |  | 54248.92 | 595417.63 | 541168.71 | 54248.92 | 100% | 100% | 51.47% | 92.09% | 100% | 2006-07-18 | n/a | 2006-10-03 | 2006-12-14 | no data | 72 | 160 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tinago | 076106041 | Construction of Bgy Health Station | 1 | 659227 | 522093 | 137134 | 503660.66 | 1st | 130584.25 | 634244.91 | 503660.66 | 130584.25 | 100% | 100% | 95.22% | 96.21% | 100% | 2009-02-02 | no data | 2009-04-07 | 2009-06-14 | n/a | 68 | 146 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tongo | 076106042 | Construction of Day Care Center | 1 | 586232 | 326572.36 | 259659.64 | 261257.89 |  | 37201.76 | 298459.65 | 261257.89 | 37201.76 | 100% | 100% | 14.33% | 50.91% | 100% | 2006-07-18 | n/a | 2006-10-23 | 2006-12-23 | no data | 61 | 118 |  | 1 | VISAYAS
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tongo | 076106042 | Construction of Barangay Health Station | 1 | 656227 | 532403.07 | 123823.93 | 516763.32 | 1st | 116720.68 | 633484 | 516763.32 | 116720.68 | 100% | 100% | 94.26% | 96.53% | 100% | 2009-02-02 | no data | 2009-04-13 | 2009-06-13 | n/a | 61 | 138 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Balaquid | 087803001 | Seawall | 1 | 578414 | 404889.8 | 173524.2 | 361036.92 | 2nd Tranche | 160106.2 | 521143.12 | 361036.92 | 160106.2 | 100% | 100% | 92.27% | 90.1% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-25 | 2007-12-16 | no data | 144 | 139 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Balaquid | 087803001 | Installation of Streetlights | 1 | 612000 | 452880 | 159120 | 407592 | 1st Tranche | 83000 | 490592 | 407592 | 83000 | 100% | 100% | 52.16% | 80.16% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-27 | 2009-08-28 | n/a | 123 | 139 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Baso | 087803002 | Brgy. Road | 1 | 420000 | 294000 | 126000 | 260583.62 | 2nd Tranche | 122845.85 | 383429.47 | 260583.62 | 122845.85 | 100% | 100% | 97.5% | 91.29% | 100% | 2007-03-01 | 2007-04-16 | 2007-08-10 | 2008-01-05 | no data | 148 | 144 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Baso | 087803002 | Construction of Sea Wall | 1 | 1063600 | 744520 | 319080 | 670068 | 2nd Tranche | 343452 | 1013520 | 670068 | 343452 | 100% | 100% | 107.6% | 95.29% | 100% | no data | no data | 2008-10-21 | 2008-12-31 | n/a | 71 | 144 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Baso | 087803002 | Installation of Streetlights | 1 | 356000 | 263440 | 92560 | 210752 | 1st Tranche | 64272.3 | 275024.3 | 210752 | 64272.3 | 100% | 100% | 69.44% | 77.25% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-28 | 2009-07-31 | no data | 94 | 144 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Bunga | 087803003 | Brgy. Road | 1 | 509300 | 254880.2 | 254419.8 | 226300.24 | 2nd Tranche | 202188 | 428488.24 | 226300.24 | 202188 | 100% | 100% | 79.47% | 84.13% | 100% | 2007-03-01 | 2007-04-16 | 2007-09-03 | 2008-04-14 | n/a | 224 | 254 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Bunga | 087803003 | Construction of Day Care Center | 1 | 600000 | 420000 | 180000 | 419065.96 | 3rd Tranche | 190338 | 609403.96 | 419065.96 | 190338 | 100% | 100% | 105.7% | 101.6% | 100% | no data | no data | 2008-08-16 | 2008-12-31 | n/a | 137 | 254 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Bunga | 087803003 | Installation of Streetlights | 1 | 728000 | 537300 | 190700 | 483570 | 1st Tranche | 92894.9 | 576464.9 | 483570 | 92894.9 | 100% | 100% | 48.71% | 79.18% | 100% | 2009-01-27 | 2009-02-25 | 2009-05-04 | 2009-08-28 | n/a | 116 | 254 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Caanibongan | 087803004 | Road Widening | 1 | 258300 | 179410 | 78890 | 159254.73 | 2nd Tranche | 77500 | 236754.73 | 159254.73 | 77500 | 100% | 100% | 98.24% | 91.66% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-10 | 2007-12-14 | no data | 157 | 140 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Caanibongan | 087803004 | Construction of Guard Rails | 1 | 435400 | 301980 | 133420 | 271782 | 2nd Tranche | 134574.73 | 406356.73 | 271782 | 134574.73 | 100% | 100% | 100.9% | 93.33% | 100% | no data | no data | 2008-08-09 | 2008-12-31 | n/a | 144 | 140 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Caanibongan | 087803004 | Improvement of Water Supply System | 1 | 282000 | 208680 | 73320 | 187812 | 1st Tranche | 74931.13 | 262743.13 | 187812 | 74931.13 | 100% | 100% | 102.2% | 93.17% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-20 | 2009-07-31 | no data | 102 | 140 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Casiawan | 087803005 | Brgy. Road | 1 | 244300 | 171010 | 73290 | 171010 | 3rd Tranche | 91012.5 | 262022.5 | 171010 | 91012.5 | 100% | 100% | 124.2% | 107.3% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-16 | 2008-04-30 | n/a | 289 | 108 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Casiawan | 087803005 | Construction of Lined Ditch Canal | 1 | 428100 | 299670 | 128430 | 299670 | 3rd Tranche | 135891 | 435561 | 299670 | 135891 | 100% | 100% | 105.8% | 101.7% | 100% | no data | no data | 2008-07-28 | 2008-11-28 | n/a | 123 | 108 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Casiawan | 087803005 | Construction of Barangay Health Station | 1 | 706000 | 522440 | 183560 | 470196 | 1st Tranche | 133932.5 | 604128.5 | 470196 | 133932.5 | 100% | 100% | 72.96% | 85.57% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-11 | 2009-08-28 | n/a | 139 | 108 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Esperanza | 087803007 | Drainage System | 1 | 421600 | 295120 | 126480 | 265608 | 2nd Tranche | 128771.4 | 394379.4 | 265608 | 128771.4 | 100% | 100% | 101.8% | 93.54% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-16 | 2008-06-30 | n/a | 350 | 216 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Esperanza | 087803007 | Construction of Canal with Box Culvert | 1 | 265000 | 196100 | 68900 | 156880 | 1st Tranche | 63000 | 219880 | 156880 | 63000 | 100% | 100% | 91.44% | 82.97% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-27 | 2009-06-30 | no data | 64 | 216 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Langgao | 087803008 | Health Station | 1 | 539400 | 377580 | 161820 | 376129.23 | 3rd Tranche | 169545.49 | 545674.72 | 376129.23 | 169545.49 | 100% | 100% | 104.8% | 101.2% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-15 | 2008-08-31 | no data | 413 | 167 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Langgao | 087803008 | Construction of Drainage System | 1 | 533870 | 333970 | 199900 | 333803.2 | 3rd Tranche | 143130 | 476933.2 | 333803.2 | 143130 | 100% | 100% | 71.6% | 89.34% | 100% | no data | no data | 2008-07-25 | 2008-11-29 | n/a | 127 | 167 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Langgao | 087803008 | Construction of Barangay Road | 1 | 315000 | 233100 | 81900 | 209790 | 1st Tranche | 63332.55 | 273122.55 | 209790 | 63332.55 | 100% | 100% | 77.33% | 86.71% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-06 | 2009-06-30 | no data | 85 | 167 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Libertad | 087803009 | Brgy. Road | 1 | 269400 | 188580 | 80820 | 188580 | 2nd Tranche | 75047.4 | 263627.4 | 188580 | 75047.4 | 100% | 100% | 92.86% | 97.86% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-16 | 2007-11-29 | no data | 136 | 264 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Libertad | 087803009 | Construction of Sea Wall | 1 | 514200 | 359940 | 154260 | 323946 | 2nd Tranche | 154260 | 478206 | 323946 | 154260 | 100% | 100% | 100% | 93% | 100% | no data | no data | 2008-10-01 | 2008-12-31 | n/a | 91 | 264 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Libertad | 087803009 | Construction of Drainage System | 1 | 328000 | 242720 | 85280 | 218448 | 1st Tranche | 70444.28 | 288892.28 | 218448 | 70444.28 | 100% | 100% | 82.6% | 88.08% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-20 | 405236 | no data | 365313 | 264 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Looc | 087803010 | Water System | 1 | 313700 | 219590 | 94110 | 219531.53 | 3rd Tranche | 109682 | 329213.53 | 219531.53 | 109682 | 100% | 100% | 116.5% | 104.9% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-17 | 2008-11-22 | n/a | 494 | 473 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Looc | 087803010 | Installation of Streetlights | 1 | 495000 | 366300 | 128700 | 329670 | 1st Tranche | 253054.85 | 582724.85 | 329670 | 253054.85 | 100% | 100% | 196.6% | 117.7% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-15 | 2009-07-31 | no data | 107 | 473 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Magbangon | 087803011 | Brgy. Road | 1 | 563200 | 394240 | 168960 | 394240 | 3rd Tranche | 173787.45 | 568027.45 | 394240 | 173787.45 | 100% | 100% | 102.9% | 100.9% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-10 | 2008-10-31 | n/a | 479 | 301 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Magbangon | 087803011 | Construction of CHB Lined Canal | 1 | 654000 | 457800 | 196200 | 451520 | 3rd Tranche | 230990 | 682510 | 451520 | 230990 | 100% | 100% | 117.7% | 104.4% | 100% | no data | no data | 2008-09-19 | 2008-11-27 | n/a | 69 | 301 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Magbangon | 087803011 | Construction of Seawall | 1 | 668000 | 494320 | 173680 | 444888 | 1st Tranche | 91442.9 | 536330.9 | 444888 | 91442.9 | 100% | 100% | 52.65% | 80.29% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-27 | 2009-07-31 | no data | 95 | 301 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Pawikan | 087803012 | Seawall | 1 | 540200 | 378140 | 162060 | 378140 | 3rd Tranche | 164538.65 | 542678.65 | 378140 | 164538.65 | 100% | 100% | 101.5% | 100.5% | 100% | 2007-03-01 | 2007-04-16 | 2007-08-06 | 2008-06-30 | n/a | 329 | 284 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Pawikan | 087803012 | Improvement of Water System | 1 | 278000 | 205720 | 72280 | 164576 | 1st Tranche | 166168.25 | 330744.25 | 164576 | 166168.25 | 100% | 100% | 229.9% | 119% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-20 | 2009-06-30 | no data | 71 | 284 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Salawad | 087803013 | Drainage System | 1 | 405600 | 283920 | 121680 | 252570.15 | 2nd Tranche | 101975 | 354545.15 | 252570.15 | 101975 | 100% | 100% | 83.81% | 87.41% | 100% | 2007-03-01 | 2007-04-16 | 2007-07-09 | 2007-12-06 | no data | 150 | 96 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Salawad | 087803013 | Construction of Health Station | 1 | 602880 | 476000 | 126880 | 476000 | 3rd Tranche | 217324 | 693324 | 476000 | 217324 | 100% | 100% | 171.3% | 115% | 100% | no data | no data | 2008-09-25 | 2008-12-31 | n/a | 97 | 96 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Salawad | 087803013 | Installation of Streetlights | 1 | 345000 | 255300 | 89700 | 229770 | 1st Tranche | 187619.74 | 417389.74 | 229770 | 187619.74 | 100% | 100% | 209.2% | 121% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-27 | 2009-06-30 | no data | 64 | 96 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Talibong | 087803014 | Improvement of Brgy. Road | 1 | 655200 | 458640 | 196560 | 408657 | 2nd Tranche | 179498.65 | 588155.65 | 408657 | 179498.65 | 100% | 100% | 91.32% | 89.77% | 100% | 2007-03-01 | 2007-04-16 | 2007-09-03 | 2008-02-26 | no data | 176 | 146 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Talibong | 087803014 | Construction of Health Station | 1 | 680000 | 476000 | 204000 | 476000 | 3rd Tranche | 218998 | 694998 | 476000 | 218998 | 100% | 100% | 107.4% | 102.2% | 100% | no data | no data | 2008-10-01 | 2008-12-11 | n/a | 71 | 146 |  | 1
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Talibong | 087803014 | Construction of Drainage System | 1 | 445000 | 329300 | 115700 | 296370 | 1st Tranche | 76821.49 | 373191.49 | 296370 | 76821.49 | 100% | 100% | 66.4% | 83.86% | 100% | 2009-01-27 | 2009-02-25 | 2009-04-21 | 2009-08-28 | n/a | 129 | 146 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Alegria | 087804001 | Sea Wall | 1 | 692229 | 463052 | 229177 | 463052 | 3rd Tranche | 210517.5 | 673569.5 | 463052 | 210517.5 | 100% | 100% | 91.86% | 97.3% | 100% | 2005-04-12 | 2005-06-10 | 2006-02-06 | 2006-06-15 | no data | 129 | 137 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Asug | 087804002 | Flood Control | 1 | 596306 | 421806 | 174500 | 421806 | 3rd Tranche | 144500 | 566306 | 421806 | 144500 | 100% | 100% | 82.81% | 94.97% | 100% | 2005-04-12 | 2005-06-10 | 2005-09-26 | 2006-04-23 | 2006-06-20 | 209 | 122 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Binohangan | 087804004 | Construction of Water System | 1 | 1415732 | 1057946 | 357786 | 1057946 | 3rd Tranche | 183550 | 1241496 | 1057946 | 183550 | 100% | 100% | 51.3% | 87.69% | 100% | 2005-04-12 | 2005-06-10 | 2005-11-14 | 2006-09-28 | no data | 318 | 211 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Cabibihan | 087804005 | Improvement of Water System | 1 | 400620 | 282140 | 118480 | 282140 | 3rd Tranche | 60612.5 | 342752.5 | 282140 | 60612.5 | 100% | 100% | 51.16% | 85.56% | 100% | 2005-04-12 | 2005-06-10 | 2005-10-24 | 2006-06-30 | no data | 249 | 260 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Caulangohan | 087804010 | Construction of Day Care Center | 1 | 510758 | 353258 | 157500 | 353258 | 3rd Tranche | 134584.98 | 487842.98 | 353258 | 134584.98 | 100% | 100% | 85.45% | 95.51% | 100% | 2005-04-12 | 2005-06-10 | 2005-09-27 | 2006-06-15 | 2006-06-23 | 261 | 86 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Kawayanon | 087804006 | Improvement of Water System | 1 | 917891 | 644601 | 273290 | 644601 | 3rd Tranche | 132578.17 | 777179.17 | 644601 | 132578.17 | 100% | 100% | 48.51% | 84.67% | 100% | 2005-04-12 | 2005-06-10 | 2005-11-07 | 2006-07-15 | no data | 250 | 100 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Looc | 087804007 | Brgy Health Station | 1 | 540782 | 373642 | 167140 | 373642 | 3rd Tranche | 193949 | 567591 | 373642 | 193949 | 100% | 100% | 116% | 105% | 100% | 2005-04-12 | 2005-06-10 | 2005-10-17 | 2006-06-15 | no data | 241 | 145 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Manlabang | 087804009 | Construction of Water System | 1 | 1098120 | 768620 | 329500 | 768620 | 3rd Tranche | 234450.12 | 1003070.12 | 768620 | 234450.12 | 100% | 100% | 71.15% | 91.34% | 100% | 2005-04-12 | 2005-06-10 | 2005-11-09 | 2006-07-15 | no data | 248 | 305 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Tomalistis | 087804014 | Solar Dryer | 1 | 576013 | 341153 | 234860 | 341153 | 3rd Tranche | 273592 | 614745 | 341153 | 273592 | 100% | 100% | 116.5% | 106.7% | 100% | 2005-04-12 | 2005-06-10 | 2005-09-23 | 2006-03-31 | 2006-06-20 | 189 | 161 |  | 1
VIII | 08 | Biliran | 0878 | Caibiran | 087804 | Union | 087804015 | Brgy Health Station | 1 | 571552 | 393782 | 177770 | 393782 | 3rd Tranche | 96046.72 | 489828.72 | 393782 | 96046.72 | 100% | 100% | 54.03% | 85.7% | 100% | 2005-04-12 | 2005-06-10 | 2005-11-07 | 2006-09-28 | no data | 325 | 174 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Anislagan | 087808002 | Water System Improvement (L2) | 1 | 661802 | 457509 | 204293 | 411758.1 | 2nd Tranche | 216889 | 628647.1 | 411758.1 | 216889 | 100% | 100% | 106.2% | 94.99% | 100% | 2007-04-27 | 2007-08-24 | 2007-12-17 | 2008-08-11 | n/a | 238 | 115 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Borac | 087808021 | Water System Improvement (L2) | 1 | 1155705 | 808993 | 346712 | 808993 | 3rd Tranche | 358283.5 | 1167276.5 | 808993 | 358283.5 | 100% | 100% | 103.3% | 101% | 100% | 2007-04-27 | 2007-08-24 | 2007-12-26 | 2008-06-24 | No data | 181 | 119 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Cabungan | 087808022 | Water System Improvement (L2) | 1 | 606110 | 423921 | 182189 | 421522.19 | 3rd Tranche | 196231 | 617753.19 | 421522.19 | 196231 | 100% | 100% | 107.7% | 101.9% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-14 | 2008-10-18 | n/a | 278 | 170 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Calumpang | 087808004 | Barangay Road | 1 | 226186 | 158330 | 67856 | 142497 | 2nd Tranche | 67873 | 210370 | 142497 | 67873 | 100% | 100% | 100% | 93.01% | 100% | 2007-04-27 | 2007-08-24 | 2007-12-28 | 2008-05-09 | No data | 133 | 888 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Caraycaray | 087808006 | Drainage System | 1 | 713144 | 499201 | 213943 | 449280.9 | 2nd Tranche | 226891 | 676171.9 | 449280.9 | 226891 | 100% | 100% | 106.1% | 94.82% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-09 | 2008-05-19 | No data | 131 | 634 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Haguikhikan | 087808008 | Water System Improvement (L2) | 1 | 934738 | 606826 | 327912 | 546143.4 | 2nd Tranche | 334020.5 | 880163.9 | 546143.4 | 334020.5 | 100% | 100% | 101.9% | 94.16% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-09 | 2008-07-11 | No data | 184 | 244 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Imelda | 087808023 | Farm to Market Road | 1 | 990906 | 646424 | 344482 | 634204.73 | 3rd Tranche | 331425 | 965629.73 | 634204.73 | 331425 | 100% | 100% | 96.21% | 97.45% | 100% | 2007-04-27 | 2007-08-24 | 2008-02-01 | 2008-08-02 | No data | 183 | 306 |  | 1
VIII | 08 | Biliran | 0878 | Naval | 087808 | Libtong | 087808025 | Farm to Market Road | 1 | 1535690 | 1064266 | 471424 | 1064266 | 3rd Tranche | 486718.25 | 1550984.25 | 1064266 | 486718.25 | 100% | 100% | 103.2% | 101% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-28 | 2008-09-27 | n/a | 243 | 164 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Mabini | 087808014 | Brgy Health Station Improvement | 1 | 403646 | 267506 | 136140 | 240755.4 | 2nd Tranche | 142177 | 382932.4 | 240755.4 | 142177 | 100% | 100% | 104.4% | 94.87% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-17 | 2008-06-27 | No data | 162 | 254 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Padre Sergio Eamiguel | 087808026 | Water System Improvement (L2) | 1 | 414878 | 252945 | 161933 | 252875.97 | 3rd Tranche | 171329 | 424204.97 | 252875.97 | 171329 | 100% | 100% | 105.8% | 102.2% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-05 | 2008-04-30 | n/a | 116 | 203 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Sabang | 087808027 | Water System Improvement (L2) | 1 | 1150010 | 760064 | 389946 | 759998.18 | 3rd Tranche | 372686 | 1132684.18 | 759998.18 | 372686 | 100% | 100% | 95.57% | 98.49% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-29 | 2008-11-30 | n/a | 306 | 80 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Sto Nino | 087808016 | Barangay Road | 1 | 767931 | 527051 | 240880 | 474345.9 | 2nd Tranche | 248095.6 | 722441.5 | 474345.9 | 248095.6 | 100% | 100% | 103% | 94.08% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-25 | 2008-04-30 | n/a | 96 | 432 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Talustusan | 087808018 | Water System Improvement (L2) | 1 | 583666 | 386264 | 197402 | 386018.98 | 3rd Tranche | 211117 | 597135.98 | 386018.98 | 211117 | 100% | 100% | 106.9% | 102.3% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-09 | 2008-08-25 | no data | 229 | 230 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Villa Caneja | 087808019 | Brgy Health Station | 1 | 696262 | 482686 | 213576 | 434551.7 | 2nd Tranche | 218764 | 653315.7 | 434551.7 | 218764 | 100% | 100% | 102.4% | 93.83% | 100% | 2007-04-27 | 2007-08-24 | 2008-04-01 | 2008-10-06 | n/a | 188 | 131 |  | 1 | VISAYAS
VIII | 08 | Biliran | 0878 | Naval | 087808 | Villa Consuelo | 087808020 | Water System Improvement (L2) | 1 | 625175 | 374089 | 251086 | 373826.55 | 3rd Tranche | 266875 | 640701.55 | 373826.55 | 266875 | 100% | 100% | 106.3% | 102.5% | 100% | 2007-04-27 | 2007-08-24 | 2008-01-14 | 2008-08-25 | no data | 224 | 292 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Bacjao | 082602001 | School Building | 1 | 567191.94 | 414286.5 | 152905.44 | 414286.5 | 3rd Tranche | 253570 | 667856.5 | 414286.5 | 253570 | 100% | 100% | 165.8% | 117.7% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-15 | 2005-02-04 | 2005-01-12 | 326 | 96 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Bacjao | 082602001 | Day Care Center | 1 | 678297 | 371918 | 306379 | 371918 | 3rd Tranche | 140843.5 | 512761.5 | 371918 | 140843.5 | 100% | 100% | 45.97% | 75.6% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-15 | 2006-05-31 | 2006-06-22 | 289 | 110 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Bacjao | 082602001 | Drainage | 1 | 658177 | 442918 | 215259 | 442918 | 1st Tranche | 172929 | 615847 | 442918 | 172929 | 100% | 100% | 80.34% | 93.57% | 100% | 2008-12-02 | 2008-12-18 | 2009-03-31 | 2009-08-28 | n/a | 150 | 300 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cag-olango | 082602002 | Water System Level II | 1 | 447317 | 127035 | 320282 | 127035 | 3rd Tranche | 324692 | 451727 | 127035 | 324692 | 100% | 100% | 101.4% | 101% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-15 | 2006-05-05 | 2006-07-27 | 263 | 68 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cag-olango | 082602002 | Construction of Drainage Canal | 1 | 502762 | 371362 | 131400 | 371362 | 3rd Tranche | 211115 | 582477 | 371362 | 211115 | 100% | 100% | 160.7% | 115.9% | 100% | 2006-05-23 | 2006-05-23 | 2006-10-25 | 2007-03-25 | No data | 151 | 68 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cag-olango | 082602002 | Sanitary Toilet | 1 | 616630 | 335810 | 280820 | 302229 | 1st Tranche | 186460 | 488689 | 302229 | 186460 | 100% | 100% | 66.4% | 79.25% | 100% | 2008-12-02 | 2008-12-18 | 2009-03-26 | 2009-06-30 | n/a | 96 | 60 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cansumangkay | 082602003 | Construction of Drainage Canal | 1 | 1052016 | 744527 | 307489 | 744527 | 3rd Tranche | 284651.75 | 1029178.75 | 744527 | 284651.75 | 100% | 100% | 92.57% | 97.83% | 100% | 2006-05-23 | 2006-05-23 | 2006-11-06 | 2007-02-28 | No data | 114 | 190 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Cansumangkay | 082602003 | Construction of Day Care Center | 1 | 641933 | 429293 | 212640 | 386316 | 1st Tranche | 194590 | 580906 | 386316 | 194590 | 100% | 100% | 91.51% | 90.49% | 100% | 2008-12-02 | 2008-12-18 | 2009-04-02 | 2009-09-30 | n/a | 181 | 190 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Guinmaayohan | 082602004 | River Flood Control | 1 | 805311.2 | 172930.36 | 632380.84 | 172930.36 | 3rd Tranche | 402590.25 | 575520.61 | 172930.36 | 402590.25 | 100% | 100% | 63.66% | 71.47% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-22 | 2005-01-22 | 2005-02-01 | 306 | 189 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Guinmaayohan | 082602004 | Construction of Drainage Canal | 1 | 419136 | 280659 | 138477 | 280659 | 3rd Tranche | 173776 | 454435 | 280659 | 173776 | 100% | 100% | 125.5% | 108.4% | 100% | 2006-05-23 | 2006-05-23 | 2006-11-08 | 2007-02-28 | No data | 112 | 189 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Guinmaayohan | 082602004 | Sanitary Toilets | 1 | 1536985 | 634603 | 902382 | 553261.1 | 1st Tranche | 289472 | 842733.1 | 553261.1 | 289472 | 100% | 100% | 32.08% | 54.83% | 100% | 2008-12-02 | 2008-12-18 | 2009-04-01 | 2009-09-30 | n/a | 182 | 189 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Maybunga | 082602013 | Electrification | 1 | 273480.18 | 210673 | 62807.18 | 210673 | 3rd Tranche | 69717.18 | 280390.18 | 210673 | 69717.18 | 100% | 100% | 111% | 102.5% | 100% | 2003-12-17 | 2004-01-27 | 2004-04-17 | 2004-12-08 | 2004-12-16 | 235 | 33 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Maybunga | 082602013 | Water and Sanitation | 1 | 381361 | 272816 | 108545 | 272816 | 3rd Tranche | 101120 | 373936 | 272816 | 101120 | 100% | 100% | 93.16% | 98.05% | 100% | 2006-05-23 | 2006-05-23 | 2006-11-13 | 2007-03-28 | No data | 135 | 22 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Maybunga | 082602013 | Construction of Drainage Canal and Culvert | 1 | 581833.75 | 335561 | 246272.75 | 301984.9 | 1st Tranche | 194486.5 | 496471.4 | 301984.9 | 194486.5 | 100% | 100% | 78.97% | 85.33% | 100% | 2008-12-02 | 2008-12-18 | 2009-04-23 | 2009-09-30 | n/a | 160 | 22 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 1 | 082602005 | Road Concreting | 1 | 849451.26 | 567846.5 | 281604.76 | 567846.5 | 3rd Tranche | 250054.74 | 817901.24 | 567846.5 | 250054.74 | 100% | 100% | 88.8% | 96.29% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-15 | 2005-01-15 | 2004-09-27 | 306 | 272 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 1 | 082602005 | Brgy Street Concreting | 1 | 1631165 | 1122428 | 508737 | 1122428 | 3rd Tranche | 489090.75 | 1611518.75 | 1122428 | 489090.75 | 100% | 100% | 96.14% | 98.8% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-18 | 2006-05-27 | 2006-06-22 | 282 | 337 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 1 | 082602005 | Construction of Day Care Center | 1 | 537685 | 404501 | 133184 | 404501 | 3rd Tranche | 114881.75 | 519382.75 | 404501 | 114881.75 | 100% | 100% | 86.26% | 96.6% | 100% | 2006-05-23 | 2006-05-23 | 2006-11-13 | 2007-06-22 | No data | 221 | 337 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 1 | 082602005 | Construction of Drainage Canal | 1 | 861283 | 588500 | 272783 | 529650 | 1st Tranche | 255013 | 784663 | 529650 | 255013 | 100% | 100% | 93.49% | 91.1% | 100% | 2008-12-02 | 2008-12-18 | 2009-03-24 | 2009-08-31 | n/a | 160 | 337 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 2 | 082602006 | Drainage System | 1 | 705090.37 | 494203.9 | 210886.47 | 494203.9 | 3rd Tranche | 211133.47 | 705337.37 | 494203.9 | 211133.47 | 100% | 100% | 100.1% | 100% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-22 | 2005-02-13 | 2004-09-27 | 328 | 119 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 2 | 082602006 | Street Concreting-Drainage | 1 | 853306 | 601472 | 251834 | 601472 | 3rd Tranche | 259164 | 860636 | 601472 | 259164 | 100% | 100% | 102.9% | 100.9% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-16 | 2006-03-02 | 2006-06-22 | 198 | 138 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 2 | 082602006 | Construction of Drainage Canal | 1 | 329200 | 245414 | 83786 | 245414 | 3rd Tranche | 90528 | 335942 | 245414 | 90528 | 100% | 100% | 108% | 102% | 100% | 2006-05-23 | 2006-05-23 | 2006-10-16 | 2006-12-15 | No data | 60 | 138 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 2 | 082602006 | Construction of Day Care Center | 1 | 641933 | 429293 | 212640 | 386363.3 | 1st Tranche | 196955 | 583318.3 | 386363.3 | 196955 | 100% | 100% | 92.62% | 90.87% | 100% | 2008-12-02 | 2008-12-18 | 2009-04-07 | 2009-09-30 | n/a | 176 | 138 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 3 | 082602007 | Barangay Road | 1 | 444065.32 | 264386 | 179679.32 | 264386 | 3rd Tranche | 189516.3 | 453902.3 | 264386 | 189516.3 | 100% | 100% | 105.5% | 102.2% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-08 | 2004-09-26 | 2004-09-27 | 202 | 120 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 3 | 082602007 | Construction of Drainage Canal | 1 | 403546 | 291696 | 111850 | 291696 | 3rd Tranche | 118870 | 410566 | 291696 | 118870 | 100% | 100% | 106.3% | 101.7% | 100% | 2006-05-23 | 2006-05-23 | 2006-10-17 | 2006-12-09 | No data | 53 | 116 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 3 | 082602007 | Drainage | 1 | 669774 | 454114 | 215660 | 408703.2 | 1st Tranche | 192165 | 600868.2 | 408703.2 | 192165 | 100% | 100% | 89.11% | 89.71% | 100% | 2008-12-02 | 2008-12-18 | 2009-03-23 | 2009-08-28 | n/a | 158 | 90 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 4 | 082602008 | Drainage System | 1 | 779057 | 639486 | 139571 | 639486 | 3rd Tranche | 291944 | 931430 | 639486 | 291944 | 100% | 100% | 209.2% | 119.6% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-16 | 2006-03-30 | 2006-06-02 | 226 | 116 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 4 | 082602008 | Construction of Drainage Canal with Cover | 1 | 479655 | 294110 | 185545 | 264699 | 1st Tranche | 173405 | 438104 | 264699 | 173405 | 100% | 100% | 93.46% | 91.34% | 100% | 2008-12-02 | 2008-12-18 | 2009-03-30 | 2009-08-28 | n/a | 151 | 80 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 5 | 082602009 | Drainage System | 1 | 745535.33 | 470815.1 | 274720.23 | 470815.1 | 3rd Tranche | 246055.23 | 716870.33 | 470815.1 | 246055.23 | 100% | 100% | 89.57% | 96.16% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-22 | 2004-10-16 | 2005-01-28 | 208 | 168 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 5 | 082602009 | Drainage System | 1 | 382976 | 247936 | 135040 | 247936 | 3rd Tranche | 127840 | 375776 | 247936 | 127840 | 100% | 100% | 94.67% | 98.12% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-15 | 2006-02-03 | 2006-02-07 | 172 | 168 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 5 | 082602009 | Construction of Drainage Canal | 1 | 488859 | 361016 | 127843 | 361016 | 3rd Tranche | 126252.5 | 487268.5 | 361016 | 126252.5 | 100% | 100% | 98.76% | 99.67% | 100% | 2006-05-23 | 2006-05-23 | 2006-11-02 | 2007-01-11 | No data | 70 | 168 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 5 | 082602009 | Drainage | 1 | 298125 | 204245 | 93880 | 183820.5 | 1st Tranche | 92595 | 276415.5 | 183820.5 | 92595 | 100% | 100% | 98.63% | 92.72% | 100% | 2008-12-02 | 2008-12-18 | 2009-03-25 | 2009-09-30 | n/a | 189 | 168 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 6 | 082602010 | Road Concreting | 1 | 1313410.44 | 1040982.24 | 272428.2 | 1040982.24 | 3rd Tranche | 282655.2 | 1323637.44 | 1040982.24 | 282655.2 | 100% | 100% | 103.8% | 100.8% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-15 | 2004-11-17 | 2004-09-27 | 247 | 318 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 6 | 082602010 | Brgy Street Concreting | 1 | 1066467 | 789725 | 276742 | 789725 | 3rd Tranche | 272169.5 | 1061894.5 | 789725 | 272169.5 | 100% | 100% | 98.35% | 99.57% | 100% | 2005-05-10 | 2005-06-09 | 2005-08-15 | 2006-03-31 | 2006-06-22 | 228 | 330 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 6 | 082602010 | Construction of Drainage Canal | 1 | 603504 | 454111 | 149393 | 454111 | 3rd Tranche | 140700 | 594811 | 454111 | 140700 | 100% | 100% | 94.18% | 98.56% | 100% | 2006-05-23 | 2006-05-23 | 2006-10-23 | 2007-02-28 | No data | 128 | 330 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Poblacion 6 | 082602010 | Road Opening | 1 | 3375241 | 1356553 | 2018688 | 1245356 | 1st Tranche | 1688360.5 | 2773602.5 | 1085242 | 1688360.5 | 87.14% | 100% | 83.64% | 82.17% | 100% | 2008-12-02 | 2008-12-18 | 2009-05-27 | 2009-08-31 | n/a | 96 | 330 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | San Miguel | 082602011 | Day Care Center | 1 | 361864.12 | 263876.4 | 97987.72 | 263876.4 | 3rd Tranche | 91412.42 | 355288.82 | 263876.4 | 91412.42 | 100% | 100% | 93.29% | 98.18% | 100% | 2003-12-17 | 2004-01-27 | 2004-03-29 | 2005-02-24 | 2005-02-24 | 332 | 229 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | San Miguel | 082602011 | Construction of Drainage Canal | 1 | 622753 | 473898 | 148855 | 473898 | 3rd Tranche | 150226.65 | 624124.65 | 473898 | 150226.65 | 100% | 100% | 100.9% | 100.2% | 100% | 2006-05-23 | 2006-05-23 | 2006-10-24 | 2006-12-20 | No data | 57 | 294 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | San Miguel | 082602011 | Road Opening | 1 | 418045 | 261000 | 157045 | 208800 | 1st Tranche | 118555 | 327355 | 208800 | 118555 | 100% | 100% | 75.49% | 78.31% | 100% | 2008-12-02 | 2008-12-18 | 2009-04-29 | 2009-10-31 | n/a | 185 | 294 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Balangiga | 082602 | Sta. Rosa | 082602012 | Water System | 1 | 1414104 | 734000 | 680104 | 587200 | 1st Tranche | 497934.5 | 1085134.5 | 587200 | 497934.5 | 100% | 100% | 73.21% | 76.74% | 100% | 2008-12-02 | 2008-12-18 | 2009-08-17 | 2009-10-24 | n/a | 68 | 272 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Balagon | 082605001 | Water System Level II | 1 | 285000 | 197105 | 87895 | 197105 | 3rd Tranche | 73685 | 270790 | 197105 | 73685 | 100% | 100% | 83.83% | 95.01% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-27 | 2006-09-15 | 2006-09-30 | 141 | 60 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Baruk | 082605002 | Water System Level II | 1 | 494323.63 | 342167 | 152156.63 | 342167 | 3rd Tranche | 81652.31 | 423819.31 | 342167 | 81652.31 | 100% | 100% | 53.66% | 85.74% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-19 | 2006-11-10 | 2006-11-17 | 205 | 116 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Boco | 082605003 | Corn Mill with structure | 1 | 808436.44 | 540605.51 | 267830.93 | 540605.51 | 3rd Tranche | 50413.47 | 591018.98 | 540605.51 | 50413.47 | 100% | 100% | 18.82% | 73.11% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-05 | 2005-02-01 | 2005-07-04 | 241 | 72 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Boco | 082605003 | School Building | 1 | 820836.66 | 645395 | 175441.66 | 645395 | 3rd Tranche | 110172.49 | 755567.49 | 645395 | 110172.49 | 100% | 100% | 62.8% | 92.05% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-21 | 2006-06-30 | 2006-06-21 | 70 | 61 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Caghalong | 082605004 | Rural Electrification | 1 | 348739.06 | 228030.38 | 120708.68 | 228030.38 | 3rd Tranche | 61546.18 | 289576.56 | 228030.38 | 61546.18 | 100% | 100% | 50.99% | 83.04% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-30 | 2005-04-30 | 2005-05-27 | 304 | 54 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Caghalong | 082605004 | Water System Level II | 1 | 370410.36 | 235124 | 135286.36 | 235124 | 3rd Tranche | 53181.97 | 288305.97 | 235124 | 53181.97 | 100% | 100% | 39.31% | 77.83% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-17 | 2006-06-30 | 2006-07-04 | 74 | 57 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Camantang | 082605005 | Post Harvest Facilities | 1 | 815278.48 | 547794.76 | 267483.72 | 493015.28 | 3rd Tranche | 41521.04 | 534536.32 | 493015.28 | 41521.04 | 100% | 100% | 15.52% | 65.56% | 100% | 2003-11-11 | 2004-01-28 | 2004-07-12 | 2005-04-15 | 2005-07-04 | 277 | 220 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Camantang | 082605005 | Water System Level II | 1 | 460744.38 | 322433 | 138311.38 | 322433 | 3rd Tranche | 123524 | 445957 | 322433 | 123524 | 100% | 100% | 89.31% | 96.79% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-10 | 2006-11-07 | 2006-11-29 | 211 | 223 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Can-ilay | 082605007 | Post Harvest Facilities | 1 | 525597.76 | 341638.54 | 183959.22 | 341638.54 | 3rd Tranche | 95052.27 | 436690.81 | 341638.54 | 95052.27 | 100% | 100% | 51.67% | 83.08% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-14 | 2005-05-30 | 2005-07-04 | 350 | 207 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Cansangaya | 082605008 | Water System Level II | 1 | 230311.27 | 161220 | 69091.27 | 161220 | 3rd Tranche | 51608.8 | 212828.8 | 161220 | 51608.8 | 100% | 100% | 74.7% | 92.41% | 100% | 2005-08-22 | 2005-09-19 | 2006-01-28 | 2006-03-23 | 2006-07-04 | 54 | 243 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Canteros | 082605009 | Farm to Market Road | 1 | 1604526.25 | 1157274 | 447252.25 | 1041546.6 | 3rd Tranche | 90219 | 1131765.6 | 1041546.6 | 90219 | 100% | 100% | 20.17% | 70.54% | 100% | 2005-08-22 | 2005-09-19 | 2006-03-29 | 2006-12-30 | 2006-12-20 | 276 | 224 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Carolina | 082605010 | Water System Level II | 1 | 338553.88 | 216763 | 121790.88 | 216763 | 3rd Tranche | 101683 | 318446 | 216763 | 101683 | 100% | 100% | 83.49% | 94.06% | 100% | 2005-08-22 | 2005-09-19 | 2006-01-30 | 2006-03-30 | 2006-07-21 | 59 | 242 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Guibuangan | 082605011 | Water System Level II | 1 | 230000 | 159500 | 70500 | 159500 | 3rd Tranche | 47810 | 207310 | 159500 | 47810 | 100% | 100% | 67.82% | 90.13% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-05 | 2006-05-31 | 2006-07-04 | 56 | 84 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Jepaco | 082605012 | Farm to Market Road | 1 | 2421755 | 1741000 | 680755 | 1566900 | 3rd Tranche | 187558.25 | 1754458.25 | 1566900 | 187558.25 | 100% | 100% | 27.55% | 72.45% | 100% | 2005-08-22 | 2005-09-19 | 2006-02-27 | 2006-12-30 | No data | 306 | 63 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Mabuhay | 082605013 | Erosion control w/ Structure | 1 | 1564436.72 | 979092.91 | 585343.81 | 979092.91 | 3rd Tranche | 63841.91 | 1042934.82 | 979092.91 | 63841.91 | 100% | 100% | 10.91% | 66.67% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-22 | 2005-04-01 | 2005-07-04 | 314 | 141 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Mabuhay | 082605013 | Erosion Control | 1 | 640322.66 | 413715 | 226607.66 | 413715 | 3rd Tranche | 96757.5 | 510472.5 | 413715 | 96757.5 | 100% | 100% | 42.7% | 79.72% | 100% | 2005-08-22 | 2005-09-19 | 2006-03-31 | 2006-05-31 | 2006-07-04 | 61 | 138 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Malogo | 082605014 | Water System Rehabilitation | 1 | 272135.73 | 166818.06 | 105317.67 | 166818.06 | 3rd Tranche | 52365.05 | 219183.11 | 166818.06 | 52365.05 | 100% | 100% | 49.72% | 80.54% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-22 | 2005-05-11 | 2005-05-12 | 354 | 136 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Malogo | 082605014 | Health Station | 1 | 641256.65 | 441315 | 199941.65 | 441315 | 3rd Tranche | 45235.96 | 486550.96 | 441315 | 45235.96 | 100% | 100% | 22.62% | 75.87% | 100% | 2005-08-22 | 2005-09-19 | 2006-03-28 | 2006-06-18 | 2006-06-21 | 82 | 135 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Obong | 082605015 | Farm To Market Road | 1 | 3546768.44 | 2353587.85 | 1193180.59 | 2353587.85 | 3rd Tranche | 254000 | 2607587.85 | 2353587.85 | 254000 | 100% | 100% | 21.29% | 73.52% | 100% | 2003-11-11 | 2004-01-28 | 2004-07-15 | 2006-07-30 | 2006-06-21 | 745 | 88 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Pandol | 082605016 | Corn Mill with Structure | 1 | 808436.44 | 540605.51 | 267830.93 | 540605.51 | 3rd Tranche | 133436.48 | 674041.99 | 540605.51 | 133436.48 | 100% | 100% | 49.82% | 83.38% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-24 | 2005-11-07 | 15-N0v-05 | 532 | 90 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 1 | 082605018 | Water System (Level-I) | 1 | 229740.48 | 138993.88 | 90746.6 | 125094.49 | 3rd Tranche | 121034.56 | 246129.05 | 125094.49 | 121034.56 | 100% | 100% | 133.4% | 107.1% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-28 | 2005-07-01 | 2005-07-04 | 399 | 128 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 1 - C9 | 082605018 | Drainage System | 9 | 1195324.67 | 791279 | 404045.67 | 791279 | 3rd Tranche | 100172 | 891451 | 791279 | 100172 | 100% | 100% | 24.79% | 74.58% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-18 | 2006-10-15 | 2006-12-05 | 180 | 128 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 10 | 082605019 | Water System (Level-II) | 1 | 457957 | 287668 | 170289 | 287668 | 3rd Tranche | 39012 | 326680 | 287668 | 39012 | 100% | 100% | 22.91% | 71.33% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-01 | 2005-03-01 | 2005-07-04 | 273 | 160 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 2 | 082605020 | Water System (Level-II) | 1 | 417208.8 | 270120 | 147088.8 | 270120 | 3rd Tranche | 210217.89 | 480337.89 | 270120 | 210217.89 | 100% | 100% | 142.9% | 115.1% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-01 | 2006-02-28 | 2006-03-30 | 668 | 75 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 3 | 082605021 | Water System (Level-I) | 1 | 122118.74 | 72128.28 | 49990.46 | 72128.28 | 3rd Tranche | 21702.53 | 93830.81 | 72128.28 | 21702.53 | 100% | 100% | 43.41% | 76.84% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-15 | 2005-07-13 | 2005-07-04 | 393 | 130 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 4 | 082605022 | Water System (Level-I) | 1 | 307466.78 | 172390.38 | 135076.4 | 172390.38 | 3rd Tranche | 71593.6 | 243983.98 | 172390.38 | 71593.6 | 100% | 100% | 53% | 79.35% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-01 | 2005-11-30 | 2005-12-01 | 578 | 140 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 5 | 082605023 | Water System (Level-I) | 1 | 169019 | 100568 | 68451 | 90511.2 | 3rd Tranche | 34154.9 | 124666.1 | 90511.2 | 34154.9 | 100% | 100% | 49.9% | 73.76% | 100% | 2003-11-11 | 2004-01-28 | 2004-07-30 | 2005-07-02 | 2005-07-04 | 337 | 70 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 6 | 082605024 | Water System (Level-I) | 1 | 125539.4 | 80676.8 | 44862.6 | 80676.8 | 3rd Tranche | 25849.52 | 106526.32 | 80676.8 | 25849.52 | 100% | 100% | 57.62% | 84.85% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-01 | 2005-07-01 | 2005-07-04 | 395 | 32 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 7 | 082605025 | Water System (Level-I) | 1 | 321378.86 | 207758.92 | 113619.94 | 207758.92 | 3rd Tranche | 52394.71 | 260153.63 | 207758.92 | 52394.71 | 100% | 100% | 46.11% | 80.95% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-01 | 2005-04-01 | 2005-07-04 | 304 | 128 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 8 | 082605026 | Water system L-I | 1 | 165078.61 | 102246.8 | 62831.81 | 102246.8 | 3rd Tranche | 38884.03 | 141130.83 | 102246.8 | 38884.03 | 100% | 100% | 61.89% | 85.49% | 100% | 2003-11-11 | 2004-01-28 | 2004-05-28 | 2005-07-01 | 2005-07-01 | 399 | 108 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Poblacion 9 | 082605027 | Water System (Level-I) | 1 | 250662.36 | 155764.36 | 94898 | 155764.36 | 3rd Tranche | 36298 | 192062.36 | 155764.36 | 36298 | 100% | 100% | 38.25% | 76.62% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-04 | 2005-10-01 | 30-N0v-06 | 484 | 128 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Rawis | 082605033 | School Building | 1 | 607963.22 | 413522.05 | 194441.17 | 413522.05 | 3rd Tranche | 188284.07 | 601806.12 | 413522.05 | 188284.07 | 100% | 100% | 96.83% | 98.99% | 100% | 2003-11-11 | 2004-01-28 | 2004-04-22 | 2005-08-18 | 2005-08-19 | 483 | 180 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Rawis | 082605033 | Brgy. Road Concreting | 1 | 1781056 | 1287856 | 493200 | 1287856 | 3rd Tranche | 233177 | 1521033 | 1287856 | 233177 | 100% | 100% | 47.28% | 85.4% | 100% | 2005-08-22 | 2005-09-19 | 2006-03-06 | 2006-06-20 | 2006-06-21 | 106 | 186 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Salvacion | 082605028 | Erosion Control | 1 | 413500 | 287854 | 125646 | 287854 | 3rd Tranche | 55090 | 342944 | 287854 | 55090 | 100% | 100% | 43.85% | 82.94% | 100% | 2005-08-22 | 2005-09-19 | 2006-04-24 | 2006-05-30 | 2006-07-04 | 36 | 75 |  | 1 | VISAYAS
VIII | 08 | Eastern Samar | 0826 | Can-avid | 082605 | Solong | 082605032 | Bailey Bridge (1 unit) | 1 | 1073125.25 | 700000 | 373125.25 | 700000 | 3rd Tranche | 108132.07 | 808132.07 | 700000 | 108132.07 | 100% | 100% | 28.98% | 75.31% | 100% | 2003-11-11 | 2004-01-28 | 2004-06-21 | 2004-08-09 | 2006-06-21 | 49 | 85 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Agsaman | 082611001 | Construction of Water system L II | 1 | 287563.42 | 233884.92 | 53678.5 | 210496.43 | 3rd Tranche | 71503.5 | 281999.93 | 210496.43 | 71503.5 | 100% | 100% | 133.2% | 98.07% | 100% | 2004-01-27 | 2004-04-29 | 2005-02-28 | 2006-02-18 | 2006-03-25 | 355 | 89 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Cagmanaba | 082611007 | Construction of Water system L II | 1 | 865102.32 | 493271.62 | 371830.7 | 443944.46 | 3rd Tranche | 126139.67 | 570084.13 | 443944.46 | 126139.67 | 100% | 100% | 33.92% | 65.9% | 100% | 2004-01-27 | 2004-04-29 | 2004-11-27 | 2005-12-05 | 2005-12-05 | 373 | 115 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Jewaran | 082611012 | Brgy. Road | 1 | 584510 | 463260 | 121250 | 463260 | 3rd Tranche | 70475 | 533735 | 463260 | 70475 | 100% | 100% | 58.12% | 91.31% | 100% | 2005-07-10 | 2005-08-30 | 2006-01-17 | 2006-03-11 | 2006-10-25 | 53 | 46 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Mabuhay | 082611013 | Barangay Road concreting | 1 | 367820 | 207610 | 160210 | 207610 | 3rd Tranche | 118377.5 | 325987.5 | 207610 | 118377.5 | 100% | 100% | 73.89% | 88.63% | 100% | 2004-01-27 | 2004-04-29 | 2004-10-20 | 2006-04-20 | 2006-05-12 | 547 | 65 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Magsaysay | 082611014 | Barangay Road concreting | 1 | 402412.5 | 226013.5 | 176399 | 226013.5 | 3rd Tranche | 195378.97 | 421392.47 | 226013.5 | 195378.97 | 100% | 100% | 110.8% | 104.7% | 100% | 2004-01-27 | 2004-04-29 | 2004-10-10 | 2005-04-29 | 2005-05-03 | 201 | 51 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Magsaysay | 082611014 | Electrification | 1 | 500195 | 351637 | 148558 | 351637 | 3rd Tranche | 73200 | 424837 | 351637 | 73200 | 100% | 100% | 49.27% | 84.93% | 100% | 2005-07-10 | 2005-08-30 | 2006-01-16 | 2006-03-14 | 2006-11-15 | 57 | 53 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 1 | 082611015 | Brgy Electrification | 1 | 748224.2 | 382656.94 | 365567.26 | 382656.94 | 3rd Tranche | 345881.84 | 728538.78 | 382656.94 | 345881.84 | 100% | 100% | 94.62% | 97.37% | 100% | 2004-01-27 | 2004-04-29 | 2004-09-13 | 2006-03-31 | 2006-04-03 | 564 | 149 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 1 | 082611015 | River Landing | 1 | 508402 | 356294 | 152108 | 356294 | 3rd Tranche | 98508 | 454802 | 356294 | 98508 | 100% | 100% | 64.76% | 89.46% | 100% | 2005-07-10 | 2005-08-30 | 2006-03-27 | 2006-05-22 | 2006-11-17 | 56 | 161 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 2 | 082611016 | Brgy Electrification | 1 | 597893.5 | 334425.45 | 263468.05 | 334425.45 | 3rd Tranche | 241172.01 | 575597.46 | 334425.45 | 241172.01 | 100% | 100% | 91.54% | 96.27% | 100% | 2004-01-27 | 2004-04-29 | 2004-09-06 | 2005-04-05 | 2005-04-05 | 211 | 79 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 2 | 082611016 | Level II Water System | 1 | 762085 | 585835 | 176250 | 585835 | 3rd Tranche | 101911.99 | 687746.99 | 585835 | 101911.99 | 100% | 100% | 57.82% | 90.25% | 100% | 2005-07-10 | 2005-08-30 | 2005-12-09 | 2006-01-26 | 2006-11-16 | 48 | 72 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 3 | 082611017 | Hanging Bridge | 1 | 2093181.2 | 1454506.84 | 638674.36 | 1454506.84 | 3rd Tranche | 685674.36 | 2140181.2 | 1454506.84 | 685674.36 | 100% | 100% | 107.4% | 102.2% | 100% | 2004-01-27 | 2004-04-29 | 2004-11-11 | 2005-01-20 | 2005-04-06 | 70 | 122 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 3 | 082611017 | Electrification | 1 | 820355 | 605690 | 214665 | 605690 | 3rd Tranche | 115150 | 720840 | 605690 | 115150 | 100% | 100% | 53.64% | 87.87% | 100% | 2005-07-10 | 2005-08-30 | 2005-12-26 | 2006-02-13 | 2006-11-15 | 49 | 120 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Poblacion 4 | 082611018 | Electrification | 1 | 881589 | 619363 | 262226 | 619363 | 3rd Tranche | 125014 | 744377 | 619363 | 125014 | 100% | 100% | 47.67% | 84.44% | 100% | 2005-07-10 | 2005-08-30 | 2005-12-12 | 2006-02-07 | 2006-06-15 | 57 | 208 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Recare | 082611019 | Barangay Road concreting | 1 | 418836.36 | 138199.33 | 280637.03 | 138199.33 | 3rd Tranche | 262953.75 | 401153.08 | 138199.33 | 262953.75 | 100% | 100% | 93.7% | 95.78% | 100% | 2004-01-27 | 2004-04-29 | 2004-09-09 | 2006-03-02 | 2006-06-12 | 539 | 55 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Roxas | 082611020 | Rice Production Machineries | 1 | 307756 | 188429.2 | 119326.8 | 188429.2 | 3rd Tranche | 54681.7 | 243110.9 | 188429.2 | 54681.7 | 100% | 100% | 45.83% | 78.99% | 100% | 2004-01-27 | 2004-04-29 | 2004-12-04 | 2005-12-10 | 2005-12-10 | 371 | 31 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | Roxas | 082611020 | Street Concreting with Canal | 1 | 628927 | 482227 | 146700 | 482227 | 3rd Tranche | 47300 | 529527 | 482227 | 47300 | 100% | 100% | 32.24% | 84.2% | 100% | 2005-07-10 | 2005-08-30 | 2006-04-19 | 2006-06-05 | no data | 47 | 31 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | San Roque | 082611021 | Construction of School Building | 1 | 417931.72 | 241002.2 | 176929.52 | 241002.2 | 3rd Tranche | 129794.88 | 370797.08 | 241002.2 | 129794.88 | 100% | 100% | 73.36% | 88.72% | 100% | 2004-01-27 | 2004-04-29 | 2004-10-19 | 2005-05-20 | 2005-06-25 | 213 | 96 |  | 1
VIII | 08 | Eastern Samar | 0826 | Jipapad | 082611 | San Roque | 082611021 | Brgy. Road | 1 | 586920 | 435694 | 151226 | 435694 | 3rd Tranche | 57150 | 492844 | 435694 | 57150 | 100% | 100% | 37.79% | 83.97% | 100% | 2005-07-10 | 2005-08-30 | 2005-12-14 | 2006-02-01 | 2006-11-14 | 49 | 96 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Bulawan | 082614001 | Construction of Water System | 1 | 302140 | 192720 | 109420 | 192720 | 3rd Tranche | 21199 | 213919 | 192720 | 21199 | 100% | 100% | 19.37% | 70.8% | 100% | 2003-11-11 | 2004-01-26 | 2004-07-09 | 2005-05-31 | 2005-05-23 | 326 | 44 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Bulawan | 082614001 | Solar Drier | 1 | 367319.5 | 256800 | 110519.5 | 256800 | 3rd Tranche | 110519.5 | 367319.5 | 256800 | 110519.5 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-09-16 | 2006-04-22 | 2006-05-20 | 218 | 40 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Bulawan | 082614001 | Pathways with Lined Canals | 1 | 704900 | 493400 | 211500 | 493400 | 2nd Tranche | 211500 | 704900 | 493400 | 211500 | 100% | 100% | 100% | 100% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-01 | 2007-08-18 | n/a | 351 | 44 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Carayacay | 082614003 | Street Rehabilitation | 1 | 368325 | 220525 | 147800 | 220525 | 3rd Tranche | 88272 | 308797 | 220525 | 88272 | 100% | 100% | 59.72% | 83.84% | 100% | 2003-11-11 | 2004-01-26 | 2004-07-05 | 2005-06-30 | 2005-06-21 | 360 | 104 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Carayacay | 082614003 | Upgrading Water System | 1 | 357957.5 | 249070 | 108887.5 | 249070 | 3rd Tranche | 108887.5 | 357957.5 | 249070 | 108887.5 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-10-08 | 2006-04-15 | 2006-05-18 | 189 | 130 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Carayacay | 082614003 | Brgy. Electrification | 1 | 885100 | 590750 | 294350 | 472600 | 1st Tranche | 294350 | 766950 | 472600 | 294350 | 100% | 100% | 100% | 86.65% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-01 | 2007-08-13 | n/a | 346 | 104 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Carayacay | 082614003 | One Unit School Building | 1 | 750378 | 661606 | 88772 | 529285.36 | 1st Tranche | 124400 | 653685.36 | 529285.36 | 124400 | 100% | 100% | 140.1% | 87.11% | 100% | no data | no data | 2009-05-04 | 2009-07-31 | n/a | 88 | 104 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Libertad | 082614005 | Malawe Type Deep Well | 1 | 106515 | 53275 | 53240 | 53275 | 3rd Tranche | 33011.75 | 86286.75 | 53275 | 33011.75 | 100% | 100% | 62.01% | 81.01% | 100% | 2003-11-11 | 2004-01-26 | 2004-10-16 | 2005-07-15 | 2005-07-30 | 272 | 12 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Libertad | 082614005 | Brgy. Electrification | 1 | 151566 | 90900 | 60666 | 90900 | 3rd Tranche | 60666 | 151566 | 90900 | 60666 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-10-12 | 2006-06-12 | 2006-06-24 | 243 | 29 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Libertad | 082614005 | Concrete Pathwalk | 1 | 643660 | 534156 | 109504 | 480740.4 | 1st Tranche | 94743.95 | 575484.35 | 480740.4 | 94743.95 | 100% | 100% | 86.52% | 89.41% | 100% | no data | no data | 2009-04-27 | 2009-08-31 | n/a | 126 | 20 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Malobago | 082614006 | Barangay Electrification | 1 | 169032 | 131022 | 38010 | 131022 | 3rd Tranche | 29242.5 | 160264.5 | 131022 | 29242.5 | 100% | 100% | 76.93% | 94.81% | 100% | 2003-11-11 | 2004-01-26 | 2004-05-17 | 2005-05-31 | May 05 | 379 | 17 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Malobago | 082614006 | Road Concreting Upgrading | 1 | 486700 | 340690 | 146010 | 340690 | 3rd Tranche | 146010 | 486700 | 340690 | 146010 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-09-16 | 2006-04-28 | 2006-05-01 | 224 | 33 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Malobago | 082614006 | Solar Dryer | 1 | 372497 | 315907 | 56590 | 284316.3 | 1st Tranche | 66499.7 | 350816 | 284316.3 | 66499.7 | 100% | 100% | 117.5% | 94.18% | 100% | no data | no data | 2009-04-01 | 2009-06-30 | no data | 90 | 17 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Maputi | 082614007 | Street Rehabilitation | 1 | 473411 | 287551 | 185860 | 287551 | 3rd Tranche | 172463 | 460014 | 287551 | 172463 | 100% | 100% | 92.79% | 97.17% | 100% | 2003-11-11 | 2004-01-26 | 2004-06-01 | 2005-07-15 | 2005-07-07 | 409 | 35 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Maputi | 082614007 | Brgy. Electrification | 1 | 289305 | 198400 | 90905 | 198400 | 3rd Tranche | 85905 | 284305 | 198400 | 85905 | 100% | 100% | 94.5% | 98.27% | 100% | 2005-06-21 | 2005-07-29 | 2005-10-12 | 2006-04-20 | 2006-05-03 | 190 | 28 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Maputi | 082614007 | Construction of Solar Drier | 1 | 368230 | 257700 | 110530 | 257700 | 1st Tranche | 110530 | 368230 | 257700 | 110530 | 100% | 100% | 100% | 100% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-01 | 2007-02-28 | No data | 180 | 35 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Maputi | 082614007 | Water System II | 1 | 450994 | 367560 | 83434 | 330804 | 1st Tranche | 47835 | 378639 | 330804 | 47835 | 100% | 100% | 57.33% | 83.96% | 100% | no data | no data | 2009-05-04 | 2009-06-30 | n/a | 57 | 34 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Poblacion 1 | 082614008 | Brgy. Electrification | 1 | 727210 | 508990 | 218220 | 487012.06 | 1st Tranche | 220320 | 707332.06 | 487012.06 | 220320 | 100% | 100% | 101% | 97.27% | 100% | 2006-06-23 | 2006-05-23 | 2006-09-01 | 2007-08-15 | n/a | 348 | 66 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Poblacion 1 | 082614008 | Farm Production Facilities | 1 | 685458 | 634712 | 50746 | 571267.8 | 1st Tranche | 40000 | 611267.8 | 571267.8 | 40000 | 100% | 100% | 78.82% | 89.18% | 100% | no data | no data | 2009-05-04 | 2009-08-31 | n/a | 119 | 78 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Poblacion 1 - C2 | 082614008 | Suspension Bridge | 2 | 2508400 | 1860160 | 648240 | 1860160 | 3rd Tranche | 973761 | 2833921 | 1860160 | 973761 | 100% | 100% | 150.2% | 113% | 100% | 2003-11-11 | 2004-01-26 | 2004-07-01 | 2005-06-30 | Jun 05 | 364 | 210 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Poblacion 1 - C2 | 082614008 | Upgrading Water System | 2 | 2144285 | 1501000 | 643285 | 1501000 | 3rd Tranche | 643825 | 2144825 | 1501000 | 643825 | 100% | 100% | 100.1% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2006-01-31 | 2006-06-10 | 2006-06-19 | 130 | 66 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Poblacion 2 | 082614009 | Brgy. Electrification | 1 | 1027870 | 719500 | 308370 | 690853.66 | 1st Tranche | 308370 | 999223.66 | 690853.66 | 308370 | 100% | 100% | 100% | 97.21% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-01 | 2006-12-13 | n/a | 103 | 210 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Poblacion 2 | 082614009 | Farm Production Facilities | 1 | 698269 | 627523 | 70746 | 564770.3 | 1st Tranche | 108840 | 673610.3 | 564770.3 | 108840 | 100% | 100% | 153.8% | 96.47% | 100% | no data | no data | 2009-04-27 | 2009-08-31 | n/a | 126 | 210 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Miguel | 082614010 | Rehabilitation of Feeder Road | 1 | 867000 | 537040 | 329960 | 537040 | 3rd Tranche | 288425.6 | 825465.6 | 537040 | 288425.6 | 100% | 100% | 87.41% | 95.21% | 100% | 2003-11-11 | 2004-01-26 | 2004-07-05 | 2005-07-01 | 2005-08-08 | 361 | 74 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Miguel | 082614010 | Road Concreting Upgrading | 1 | 467369 | 324270 | 143099 | 324270 | 3rd Tranche | 143389.1 | 467659.1 | 324270 | 143389.1 | 100% | 100% | 100.2% | 100.1% | 100% | 2005-06-21 | 2005-07-29 | 2005-09-16 | 2006-05-05 | 2006-05-20 | 231 | 76 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Miguel | 082614010 | Concrete Pathwalk | 1 | 703534 | 613134 | 90400 | 551820.6 | 1st Tranche | 132379.3 | 684199.9 | 551820.6 | 132379.3 | 100% | 100% | 146.4% | 97.25% | 100% | no data | no data | 2009-04-02 | 2009-08-31 | n/a | 151 | 86 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Roque | 082614011 | Farm Production Facility | 1 | 242078 | 145955 | 96123 | 145955 | 3rd Tranche | 91123 | 237078 | 145955 | 91123 | 100% | 100% | 94.8% | 97.93% | 100% | 2005-06-21 | 2005-07-29 | 2005-10-12 | 2006-06-13 | 2006-06-24 | 244 | 40 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | San Roque | 082614011 | Rice Mill w/ Structure | 1 | 413050 | 289100 | 123950 | 260190 | 1st Tranche | 123950 | 384140 | 260190 | 123950 | 100% | 100% | 100% | 93% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-15 | 2007-08-15 | n/a | 334 | 40 | completed as built | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tangbo | 082614012 | Construction of Water System | 1 | 270396 | 178747 | 91649 | 178747 | 3rd Tranche | 31410 | 210157 | 178747 | 31410 | 100% | 100% | 34.27% | 77.72% | 100% | 2003-11-11 | 2004-01-26 | 2004-08-02 | 2005-07-31 | 2005-08-10 | 363 | 14 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tangbo | 082614012 | Brgy. Electrification | 1 | 183150 | 117305 | 65845 | 117305 | 3rd Tranche | 65845 | 183150 | 117305 | 65845 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-10-12 | 2006-06-05 | 2006-06-24 | 236 | 33 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tangbo | 082614012 | Construction of Pathways with Lined Canals | 1 | 484930 | 339400 | 145530 | 334047.8 | 1st Tranche | 145530 | 479577.8 | 334047.8 | 145530 | 100% | 100% | 100% | 98.9% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-01 | 2007-08-30 | n/a | 363 | 33 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tangbo | 082614012 | Solar Dryer | 1 | 370997 | 315907 | 55090 | 284316.3 | 1st Tranche | 60350.5 | 344666.8 | 284316.3 | 60350.5 | 100% | 100% | 109.5% | 92.9% | 100% | no data | no data | 2009-05-04 | 2009-08-31 | n/a | 119 | 33 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Taytay | 082614013 | Construction of Water system | 1 | 229540 | 138960 | 90580 | 138960 | 3rd Tranche | 78839 | 217799 | 138960 | 78839 | 100% | 100% | 87.04% | 94.88% | 100% | 2003-11-11 | 2004-01-26 | 2004-06-11 | 2005-06-30 | 2005-06-17 | 384 | 15 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Taytay | 082614013 | Road Concreting W/ lined Ditch | 1 | 300121 | 179685 | 120436 | 179685 | 3rd Tranche | 120436 | 300121 | 179685 | 120436 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-09-19 | 2006-05-16 | 2006-06-24 | 239 | 21 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Taytay | 082614013 | Concrete Pathwalk | 1 | 754989 | 664699 | 90290 | 598229.1 | 1st Tranche | 91070.5 | 689299.6 | 598229.1 | 91070.5 | 100% | 100% | 100.9% | 91.3% | 100% | no data | no data | 2009-04-30 | 2009-08-31 | n/a | 123 | 21 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tugas | 082614014 | Rice Mill | 1 | 294179 | 195925 | 98254 | 195925 | 3rd Tranche | 98254 | 294179 | 195925 | 98254 | 100% | 100% | 100% | 100% | 100% | 2005-06-21 | 2005-07-29 | 2005-12-01 | 2006-05-15 | 2006-06-24 | 165 | 37 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tugas | 082614014 | Construction of Pathways with Lined Canals | 1 | 608975 | 401160 | 207815 | 401160 | 2nd Tranche | 207815 | 608975 | 401160 | 207815 | 100% | 100% | 100% | 100% | 100% | 2006-06-23 | 2006-07-18 | 2006-09-01 | 2006-11-15 | n/a | 75 | 37 |  | 1
VIII | 08 | Eastern Samar | 0826 | Maslog | 082614 | Tugas | 082614014 | Barangay Tugas Concrete Pathwalk | 1 | 549966 | 481551 | 68415 | 393122.68 | 1st Tranche | 75304.9 | 468427.58 | 393122.68 | 75304.9 | 100% | 100% | 110.1% | 85.17% | 100% | no data | no data | 2009-05-11 | 2009-07-31 | n/a | 81 | 49 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Alugan | 082621001 | Water system (Level-II) | 1 | 733774 | 513642 | 220132 | 513642 | 3rd Tranche | 95929.93 | 609571.93 | 513642 | 95929.93 | 100% | 100% | 43.58% | 83.07% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-17 | 2005-06-30 | 2005-08-20 | 225 | 376 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Alugan | 082621001 | Day Care Center | 1 | 474262 | 331162 | 143100 | 331162 | 2nd Tranche | 107132 | 438294 | 331162 | 107132 | 100% | 100% | 74.87% | 92.42% | 100% | 2005-10-12 | 2005-11-24 | 2006-03-08 | 2007-06-30 | No data | 479 | 376 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Bahay | 082621002 | Barangay Health Station | 1 | 893296 | 625307 | 267989 | 625307 | 3rd Tranche | 147477.94 | 772784.94 | 625307 | 147477.94 | 100% | 100% | 55.03% | 86.51% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-22 | 2005-07-15 | 2005-08-20 | 235 | 167 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Bahay | 082621002 | Street Concreting | 1 | 893402 | 622902 | 270500 | 622902 | 3rd Tranche | 101475 | 724377 | 622902 | 101475 | 100% | 100% | 37.51% | 81.08% | 100% | 2005-10-12 | 2005-11-24 | 2006-03-08 | 2006-07-31 | no data | 145 | 167 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Bangon | 082621003 | Brgy Electrification | 1 | 181626 | 127138 | 54488 | 127138 | 3rd Tranche | 38147 | 165285 | 127138 | 38147 | 100% | 100% | 70.01% | 91% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-22 | 2005-08-24 | 2005-09-02 | 275 | 35 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Baras | 082621004 | Street Gravelling | 1 | 437290 | 291103 | 146187 | 291103 | 3rd Tranche | 118009.25 | 409112.25 | 291103 | 118009.25 | 100% | 100% | 80.72% | 93.56% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-08 | 2005-07-15 | 2005-08-20 | 249 | 97 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Baras | 082621004 | Street Graveling | 1 | 447781 | 313081 | 134700 | 313081 | 3rd Tranche | 107869 | 420950 | 313081 | 107869 | 100% | 100% | 80.08% | 94.01% | 100% | 2005-10-12 | 2005-11-24 | 2006-01-23 | 2006-05-25 | 2006-06-21 | 122 | 97 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Binowagan | 082621005 | Water system (Level-II) | 1 | 703252 | 492276 | 210976 | 492276 | 3rd Tranche | 108269 | 600545 | 492276 | 108269 | 100% | 100% | 51.32% | 85.4% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-16 | 2005-10-14 | 2005-12-12 | 332 | 223 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Cajagwayan | 082621006 | Street Concreting | 1 | 808115 | 529055 | 279060 | 529055 | 3rd Tranche | 248979.75 | 778034.75 | 529055 | 248979.75 | 100% | 100% | 89.22% | 96.28% | 100% | 2005-10-12 | 2005-11-24 | 2006-02-22 | 2006-09-28 | no data | 218 | 124 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Japunan | 082621007 | Barangay Health Station | 1 | 875213 | 613083 | 262130 | 613083 | 3rd Tranche | 87405 | 700488 | 613083 | 87405 | 100% | 100% | 33.34% | 80.04% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-08 | 2005-07-15 | 2005-08-20 | 249 | 182 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Japunan | 082621007 | Drainage Canal | 1 | 331563 | 228603 | 102960 | 228603 | 3rd Tranche | 44470 | 273073 | 228603 | 44470 | 100% | 100% | 43.19% | 82.36% | 100% | 2005-10-12 | 2005-11-24 | 2006-01-31 | 2006-07-31 | no data | 181 | 162 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Natividad | 082621008 | Street Concreting | 1 | 825867 | 578107 | 247760 | 578107 | 3rd Tranche | 233213 | 811320 | 578107 | 233213 | 100% | 100% | 94.13% | 98.24% | 100% | 2004-07-08 | 2004-09-10 | 2004-10-25 | 2005-06-15 | 2005-08-20 | 233 | 125 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Natividad | 082621008 | Street Concreting | 1 | 742014 | 516564 | 225450 | 516564 | 3rd Tranche | 234165 | 750729 | 516564 | 234165 | 100% | 100% | 103.9% | 101.2% | 100% | 2005-10-12 | 2005-11-24 | 2006-01-31 | 2006-08-31 | no data | 212 | 125 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Pangpang | 082621009 | Street Concreting | 1 | 1198486 | 835886 | 362600 | 835886 | 3rd Tranche | 394050 | 1229936 | 835886 | 394050 | 100% | 100% | 108.7% | 102.6% | 100% | 2005-10-12 | 2005-11-24 | 2006-02-13 | 2006-08-15 | no data | 183 | 208 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Poblacion 1 | 082621010 | Brgy Road Extension | 1 | 518497 | 362948 | 155549 | 362948 | 3rd Tranche | 218784 | 581732 | 362948 | 218784 | 100% | 100% | 140.7% | 112.2% | 100% | 2004-07-08 | 2004-09-10 | 2004-10-25 | 2005-04-15 | 2005-08-20 | 172 | 127 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Poblacion 2 | 082621011 | Street Concreting | 1 | 792019 | 349954 | 442065 | 349954 | 3rd Tranche | 316375 | 666329 | 349954 | 316375 | 100% | 100% | 71.57% | 84.13% | 100% | 2005-10-12 | 2005-11-24 | 2006-02-20 | 2006-05-05 | 2006-06-21 | 74 | 155 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Poblacion 3 | 082621012 | Street Gravelling | 1 | 517268 | 336454 | 180814 | 336454 | 3rd Tranche | 98566.5 | 435020.5 | 336454 | 98566.5 | 100% | 100% | 54.51% | 84.1% | 100% | 2004-07-08 | 2004-09-10 | 2004-10-25 | 2005-04-15 | 2005-08-20 | 172 | 155 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Poblacion 3 | 082621012 | Water System | 1 | 227418 | 154438 | 72980 | 154438 | 3rd Tranche | 80980 | 235418 | 154438 | 80980 | 100% | 100% | 111% | 103.5% | 100% | 2005-10-12 | 2005-11-24 | 2006-02-22 | 2006-05-03 | 2006-06-21 | 70 | 66 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Poblacion 4 | 082621013 | Brgy Road Extension | 1 | 394197 | 275938 | 118259 | 275938 | 3rd Tranche | 91311 | 367249 | 275938 | 91311 | 100% | 100% | 77.21% | 93.16% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-08 | 2005-04-15 | 2005-08-20 | 158 | 151 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Poblacion 5 | 082621014 | Water system (Level-II) | 1 | 735002 | 514501 | 220501 | 514501 | 3rd Tranche | 98091.25 | 612592.25 | 514501 | 98091.25 | 100% | 100% | 44.49% | 83.35% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-16 | 2005-10-14 | 2005-12-12 | 332 | 201 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Sta. Cruz | 082621015 | School Building 2 Classroom | 1 | 694588 | 482130 | 212458 | 433917 | 2nd Tranche | 100583 | 534500 | 433917 | 100583 | 100% | 100% | 47.34% | 76.95% | 100% | 2005-10-12 | 2005-11-24 | 2006-02-22 | 2006-05-15 | n/a | 82 | 56 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Tabo | 082621016 | Street Gravelling | 1 | 548967 | 369503 | 179464 | 369503 | 3rd Tranche | 126519 | 496022 | 369503 | 126519 | 100% | 100% | 70.5% | 90.36% | 100% | 2004-07-08 | 2004-09-10 | 2004-11-08 | 2005-06-03 | 2005-08-20 | 207 | 102 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Tabo | 082621016 | Street Concreting | 1 | 734694 | 510110 | 224584 | 510110 | 3rd Tranche | 133036.4 | 643146.4 | 510110 | 133036.4 | 100% | 100% | 59.24% | 87.54% | 100% | 2005-10-12 | 2005-11-24 | 2006-01-23 | 2006-07-31 | no data | 189 | 102 |  | 1
VIII | 08 | Eastern Samar | 0826 | San Policarpo | 082621 | Tan-awan | 082621017 | Brgy. Electrification | 1 | 315897 | 226115 | 89782 | 226115 | 3rd Tranche | 84357 | 310472 | 226115 | 84357 | 100% | 100% | 93.96% | 98.28% | 100% | 2005-10-12 | 2005-11-24 | 2006-02-22 | 2006-05-09 | 2006-06-21 | 76 | 120 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | A-et | 082622001 | Construction of two (2) unit Concrete Bridge | 1 | 629655.1 | 584145.1 | 45510 | 525730.59 | 3rd Tranche | 57250 | 582980.59 | 525730.59 | 57250 | 100% | 100% | 125.8% | 92.59% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-29 | 2004-02-20 | 2004-03-04 | 144 | 129 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | A-et | 082622001 | Construction of L-II Water System | 1 | 568172 | 395572 | 172600 | 395572 | 3rd Tranche | 123969 | 519541 | 395572 | 123969 | 100% | 100% | 71.82% | 91.44% | 100% | 2005-01-26 | 2005-03-16 | 2005-06-12 | 2005-11-25 | 2006-03-10 | 166 | 72 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Baybay (Pob) | 082622002 | Improvement of Drainage System | 1 | 329825 | 222825 | 107000 | 222825 | 3rd Tranche | 131985 | 354810 | 222825 | 131985 | 100% | 100% | 123.4% | 107.6% | 100% | 2005-01-26 | 2005-03-16 | 2005-06-01 | 2005-12-01 | 2006-04-20 | 183 | 147 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Del Remedio | 082622004 | Rehabilitation/Improvement of Water System | 1 | 934186.584 | 562149.564 | 372037.02 | 562149.564 | 3rd Tranche | 475115.86 | 1037265.42 | 562149.56 | 475115.86 | 100% | 100% | 127.7% | 111% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-18 | 2004-03-04 | 2004-03-04 | 168 | 321 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Kandalakit | 082622003 | Health Station | 1 | 284743 | 228943 | 55800 | 228943 | 3rd Tranche | 59650 | 288593 | 228943 | 59650 | 100% | 100% | 106.9% | 101.4% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-18 | 2004-03-04 | 2004-03-04 | 168 | 35 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Kandalakit | 082622003 | Construction of Pathway and Foot Bridges | 1 | 1452018 | 1019218 | 432800 | 1019218 | 3rd Tranche | 215459.89 | 1234677.89 | 1019218 | 215459.89 | 100% | 100% | 49.78% | 85.03% | 100% | 2005-01-26 | 2005-03-16 | 2005-07-04 | 2006-06-28 | 2006-08-15 | 359 | 38 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Mabini | 082622006 | Construction of Warehouse Farm | 1 | 199129.9 | 121629.9 | 77500 | 121629.9 | 3rd Tranche | 59401 | 181030.9 | 121629.9 | 59401 | 100% | 100% | 76.65% | 90.91% | 100% | 2003-05-12 | 2003-07-18 | 2003-10-01 | 2004-02-12 | 2004-03-04 | 134 | 53 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Mabini | 082622006 | Const. of Motorized Boat | 1 | 444800 | 301000 | 143800 | 301000 | 3rd Tranche | 117000 | 418000 | 301000 | 117000 | 100% | 100% | 81.36% | 93.97% | 100% | 2005-01-26 | 2005-03-16 | 2005-07-05 | 2005-11-20 | 2006-04-20 | 138 | 51 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Maglipay (Pob) | 082622007 | Construction of L-II Water System | 1 | 660320 | 451721 | 208599 | 451721 | 3rd Tranche | 183745.5 | 635466.5 | 451721 | 183745.5 | 100% | 100% | 88.09% | 96.24% | 100% | 2005-01-26 | 2005-03-16 | 2005-05-11 | 2005-10-20 | 2005-10-28 | 162 | 153 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Maramara (Pob) | 082622008 | Day Care Center | 1 | 475329 | 352309 | 123020 | 352309 | 3rd Tranche | 248840 | 601149 | 352309 | 248840 | 100% | 100% | 202.3% | 126.5% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-23 | 2004-03-03 | 2004-03-04 | 162 | 79 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Riverside (Pob) | 082622009 | Concrete Drainage with Cover | 1 | 251177 | 221137 | 30040 | 221137 | 3rd Tranche | 37400 | 258537 | 221137 | 37400 | 100% | 100% | 124.5% | 102.9% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-10 | 2003-10-11 | 2004-03-04 | 31 | 125 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Riverside (Pob) | 082622009 | Const. of Day Care Center | 1 | 590064 | 408185 | 181879 | 408185 | 3rd Tranche | 99798 | 507983 | 408185 | 99798 | 100% | 100% | 54.87% | 86.09% | 100% | 2005-01-26 | 2005-03-16 | 2005-06-16 | 2005-07-30 | 2006-04-20 | 44 | 125 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Francisco | 082622010 | Construction of L-II Water System | 1 | 394517 | 275967 | 118550 | 275967 | 3rd Tranche | 77425 | 353392 | 275967 | 77425 | 100% | 100% | 65.31% | 89.58% | 100% | 2005-01-26 | 2005-03-16 | 2005-05-20 | 2006-05-31 | 2006-09-28 | 376 | 138 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Isidro | 082622011 | Constructon of Water System | 1 | 825129.15 | 722229.15 | 102900 | 722229.15 | 3rd Tranche | 133632 | 855861.15 | 722229.15 | 133632 | 100% | 100% | 129.9% | 103.7% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-01 | 2005-12-13 | 2005-12-13 | 834 | 291 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Juan | 082622012 | Construction of Level II Potable Water System | 1 | 1020329.7 | 870699.7 | 149630 | 870699.7 | 3rd Tranche | 128862.6 | 999562.3 | 870699.7 | 128862.6 | 100% | 100% | 86.12% | 97.96% | 100% | 2003-05-12 | 2003-07-18 | 2003-12-02 | 2004-03-31 | 2004-04-17 | 120 | 166 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Juan | 082622012 | Construction of Health Station | 1 | 684972 | 447972 | 237000 | 447972 | 3rd Tranche | 145343 | 593315 | 447972 | 145343 | 100% | 100% | 61.33% | 86.62% | 100% | 2005-01-26 | 2005-03-16 | 2005-06-07 | 2005-12-01 | 2006-04-20 | 177 | 215 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Mateo | 082622013 | Construction of L-II Water System | 1 | 480737 | 329668 | 151069 | 329668 | 3rd Tranche | 165384.4 | 495052.4 | 329668 | 165384.4 | 100% | 100% | 109.5% | 103% | 100% | 2005-01-26 | 2005-03-16 | 2005-05-09 | 2005-12-28 | 2006-04-20 | 233 | 86 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | San Vicente | 082622014 | Multi Purpose Covered Facility with Solar Drier | 1 | 640200.652 | 366609.282 | 273591.37 | 366609.282 | 3rd Tranche | 373312 | 739921.282 | 366609.282 | 373312 | 100% | 100% | 136.4% | 115.6% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-02 | 2003-11-09 | 2004-03-04 | 68 | 128 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Sto. Niño | 082622015 | Water System Rehabilitation | 1 | 285802.162 | 214377.482 | 71424.68 | 214377.482 | 3rd Tranche | 69290 | 283667.482 | 214377.482 | 69290 | 100% | 100% | 97.01% | 99.25% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-22 | 2004-03-04 | 2004-03-04 | 164 | 270 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Sto. Niño | 082622015 | Construction of Pathways with Culverts | 1 | 1047500 | 600000 | 447500 | 600000 | 3rd Tranche | 272680.28 | 872680.28 | 600000 | 272680.28 | 100% | 100% | 60.93% | 83.31% | 100% | 2005-01-26 | 2005-03-16 | 2005-06-29 | 2005-08-29 | 2006-06-22 | 61 | 270 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Sto. Tomas | 082622016 | Water Spring Development (L-II) | 1 | 1131039.81 | 865770.83 | 265268.98 | 865770.83 | 3rd Tranche | 208899.05 | 1074669.88 | 865770.83 | 208899.05 | 100% | 100% | 78.75% | 95.02% | 100% | 2003-05-12 | 2003-07-18 | 2003-09-09 | 2003-12-17 | No data | 99 | 260 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Sto. Tomas | 082622016 | Construction of Pathways Foot Bridges | 1 | 1141599 | 586200 | 555399 | 586200 | 3rd Tranche | 159110 | 745310 | 586200 | 159110 | 100% | 100% | 28.65% | 65.29% | 100% | 2005-01-26 | 2005-03-16 | 2005-07-19 | 2006-05-30 | 2006-06-19 | 315 | 260 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Tabi (Pob) | 082622017 | Meat Processing Facility | 1 | 348200 | 290000 | 58200 | 290000 | 3rd Tranche | 39800 | 329800 | 290000 | 39800 | 100% | 100% | 68.38% | 94.72% | 100% | 2003-05-12 | 2003-07-18 | 2003-08-01 | 2004-03-04 | 2004-04-04 | 216 | 116 |  | 1
VIII | 08 | Eastern Samar | 0826 | Sulat | 082622 | Tabi (Pob) | 082622017 | Rehabilitation/Improvement Of Tabi Road | 1 | 526498 | 361672 | 164826 | 361672 | 3rd Tranche | 206275 | 567947 | 361672 | 206275 | 100% | 100% | 125.1% | 107.9% | 100% | 2005-01-26 | 2005-03-16 | 2005-06-20 | 2005-07-30 | 2006-04-20 | 40 | 116 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Alegria | 083707001 | Construction of School Building (2 Rm) | 1 | 1000225 | 682760 | 317465 | 661172.6 | 3rd Tranche | 321775 | 982947.6 | 661172.6 | 321775 | 100% | 100% | 101.4% | 98.27% | 100% | 2007-02-26 | 2007-05-19 | 2007-08-22 | 2008-06-30 | n/a | 313 | 242 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Alegria | 083707001 | Improvement of Barangay Road | 1 | 850977 | 598361 | 252616 | 538524.9 | 1st Tranche | 229668 | 768192.9 | 538524.9 | 229668 | 100% | 100% | 90.92% | 90.27% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-30 | 2009-06-30 | no data | 92 | 256 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Anahawan | 083707004 | Construction of Hanging Bridge | 1 | 621563 | 431406 | 190157 | 431406 | 2nd Tranche | 183156 | 614562 | 431406 | 183156 | 100% | 100% | 96.32% | 98.87% | 100% | 2007-02-26 | 2007-05-19 | 2008-02-29 | 2008-08-29 | no data | 182 | 450 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Anahawan | 083707004 | Improvement of Barangay Road | 1 | 960993 | 657240 | 303753 | 591516 | 1st Tranche | 272817 | 864333 | 591516 | 272817 | 100% | 100% | 89.82% | 89.94% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-30 | 2009-06-30 | no data | 92 | 460 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Bago | 083707005 | Improvement of Barangay Road | 1 | 750382 | 523726 | 226656 | 471353.4 | 2nd Tranche | 245936 | 717289.4 | 471353.4 | 245936 | 100% | 100% | 108.5% | 95.59% | 100% | no data | no data | 2008-06-26 | 2008-09-24 | no data | 90 | 217 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Bago | 083707005 | Construction of Day Care Center | 1 | 696585 | 491927 | 204658 | 442734.3 | 1st Tranche | 194046 | 636780.3 | 442734.3 | 194046 | 100% | 100% | 94.81% | 91.41% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-16 | 2009-06-30 | no data | 106 | 217 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Bagong bayan | 083707006 | Construction of CHB Lined Canal | 1 | 955533 | 668822 | 286711 | 644995 | 3rd Tranche | 332777 | 977772 | 644995 | 332777 | 100% | 100% | 116.1% | 102.3% | 100% | no data | no data | 2008-06-27 | 2008-11-25 | n/a | 151 | 223 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Bagongbayan | 083707006 | Construction of CHB Lined Canal | 1 | 763676 | 514809 | 248867 | 463328.1 | 1st Tranche | 223959 | 687287.1 | 463328.1 | 223959 | 100% | 100% | 89.99% | 90% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-30 | 2009-06-30 | no data | 92 | 217 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Buli | 083707008 | Improvement of Farm to Market Road | 1 | 950392 | 615272 | 335120 | 518944.8 | 2nd Tranche | 338550 | 857494.8 | 518944.8 | 338550 | 100% | 100% | 101% | 90.23% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-19 | 2008-05-23 | n/a | 217 | 222 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Buli | 083707008 | Construction of Day Care Center | 1 | 619727 | 418827 | 200900 | 412210.77 | 3rd Tranche | 243552.97 | 650380.74 | 412210.77 | 238169.97 | 100% | 97.79% | 121.2% | 104.9% | 100% | no data | no data | 2008-07-21 | 2008-11-18 | n/a | 120 | 224 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Buli | 083707008 | Improvement of Barangay Road | 1 | 938613 | 685085 | 253528 | 616576.5 | 2nd Tranche | 217304 | 833880.5 | 616576.5 | 217304 | 100% | 100% | 85.71% | 88.84% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-16 | 2009-06-30 | no data | 106 | 224 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Cebuana | 083707009 | Improvement of Farm to Market Road | 1 | 854362 | 589321 | 265041 | 494388.9 | 2nd Tranche | 270884.4 | 765273.3 | 494388.9 | 270884.4 | 100% | 100% | 102.2% | 89.57% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-08 | 2008-01-06 | no data | 90 | 49 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Daanglungsod | 083707010 | Construction of Public Toilet with Jetmatic Pump | 1 | 333175 | 225419 | 107756 | 202877.1 | 2nd Tranche | 98503.79 | 301380.89 | 202877.1 | 98503.79 | 100% | 100% | 91.41% | 90.46% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-20 | 2009-06-30 | no data | 102 | 217 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Dawahon | 083707011 | Construction of Seawall | 1 | 1687095 | 736966 | 950129 | 663269.2 | 1st Tranche | 1000000 | 1663269.2 | 663269.2 | 1000000 | 100% | 100% | 105.2% | 98.59% | 100% | no data | no data | 2008-10-27 | 2009-03-16 | n/a | 140 | 517 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Dolho | 083707013 | Public Toilet w Pathway/jetmatic Pump | 1 | 452241 | 294998 | 157243 | 294938.13 | 3rd Tranche | 150533 | 445471.13 | 294938.13 | 150533 | 100% | 100% | 95.73% | 98.5% | 100% | no data | no data | 2008-07-26 | 2008-11-25 | n/a | 122 | 442 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Dolho | 083707013 | Construction of Grouted Riprap | 1 | 1269585 | 962635 | 306950 | 866371.5 | 2nd Tranche | 280466.04 | 1146837.54 | 866371.5 | 280466.04 | 100% | 100% | 91.37% | 90.33% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-19 | 2009-06-30 | no data | 103 | 442 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Domagocdoc | 083707014 | Improvement of Farm to Market Road | 1 | 1122868 | 688068 | 434800 | 602272.2 | 2nd Tranche | 304788 | 907060.2 | 602272.2 | 304788 | 100% | 100% | 70.1% | 80.78% | 100% | 2007-02-26 | 2007-05-19 | 2008-03-03 | 2008-06-30 | n/a | 119 | 43 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Domagocdoc | 083707014 | Improvement of Barangay Road | 1 | 583475 | 374824 | 208651 | 337341.6 | 2nd Tranche | 189039 | 526380.6 | 337341.6 | 189039 | 100% | 100% | 90.6% | 90.21% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-16 | 2009-06-30 | n/a | 106 | 50 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Guerrero | 083707015 | Constrcution of CHB Lined Canal | 1 | 907609 | 616609 | 291000 | 549948.1 | 2nd Tranche | 298450 | 848398.1 | 549948.1 | 298450 | 100% | 100% | 102.6% | 93.48% | 100% | 2007-02-26 | 2007-05-19 | 2007-08-09 | 2007-09-29 | no data | 51 | 180 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Himamaa | 083707012 | Improvement of Farm to Market Road | 1 | 830352 | 579581 | 250771 | 485622.9 | 2nd Tranche | 261074.4 | 746697.3 | 485622.9 | 261074.4 | 100% | 100% | 104.1% | 89.93% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-15 | 2008-02-23 | no data | 131 | 350 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Himamaa | 083707012 | Improvement of Barangay Road | 1 | 518138 | 352111 | 166027 | 316899.9 | 2nd Tranche | 184759 | 501658.9 | 316899.9 | 184759 | 100% | 100% | 111.3% | 96.82% | 100% | no data | no data | 2008-06-26 | 2008-10-24 | n/a | 120 | 169 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Himama-a | 083707012 | Improvement of Barangay Road | 1 | 922208 | 677680 | 244528 | 609912 | 2nd Tranche | 219830 | 829742 | 609912 | 219830 | 100% | 100% | 89.9% | 89.97% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-13 | 2009-05-31 | n/a | 79 | 185 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Imelda | 083707033 | Improvement of Farm to Market Road | 1 | 923777 | 590727 | 333050 | 560727 | 2nd Tranche | 355480 | 916207 | 560727 | 355480 | 100% | 100% | 106.7% | 99.18% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-23 | 2008-07-31 | n/a | 282 | 74 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Imelda | 083707033 | Improvement of Barangay Road | 1 | 999905 | 723177 | 276728 | 650859.3 | 1st Tranche | 222709.4 | 873568.7 | 650859.3 | 222709.4 | 100% | 100% | 80.48% | 87.37% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-02 | 2009-03-31 | no data | 29 | 73 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Iniguihan | 083707016 | Construction of River Control | 1 | 2042045 | 881358 | 1160687 | 834476 | 3rd Tranche | 1200992 | 2035468 | 834476 | 1200992 | 100% | 100% | 103.5% | 99.68% | 100% | no data | no data | 2008-10-01 | 2009-01-22 | n/a | 113 | 340 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Kalanggaman | 083707023 | Construction of CHB Lined Canal | 1 | 835953 | 585167 | 250786 | 581533.25 | 3rd Tranche | 268166 | 849699.25 | 581533.25 | 268166 | 100% | 100% | 106.9% | 101.6% | 100% | no data | no data | 2008-06-25 | 2008-11-23 | n/a | 151 | 301 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Kalanggaman | 083707023 | Construction of Water System | 1 | 381935 | 235742 | 146193 | 212167.8 | 1st Tranche | 121193 | 333360.8 | 212167.8 | 121193 | 100% | 100% | 82.9% | 87.28% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-30 | 2009-06-20 | no data | 82 | 305 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Katipunan | 083707017 | Improvement of Farm to Market Road | 1 | 876052 | 613161 | 262891 | 552365.34 | 2nd Tranche | 270578.4 | 822943.74 | 552365.34 | 270578.4 | 100% | 100% | 102.9% | 93.94% | 100% | 2007-02-26 | 2007-05-19 | 2008-03-27 | 2008-09-30 | no data | 187 | 352 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Liberty | 083707018 | Improvement of Farm to Market Road | 1 | 951155 | 615755 | 335400 | 553239.5 | 3rd Tranche | 337180 | 890419.5 | 553239.5 | 337180 | 100% | 100% | 100.5% | 93.61% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-27 | 2008-08-31 | no data | 309 | 116 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Mabini | 083707019 | Construction of Hanging Bridge | 1 | 671706 | 462956 | 208750 | 462956 | 2nd Tranche | 200070 | 663026 | 462956 | 200070 | 100% | 100% | 95.84% | 98.71% | 100% | 2007-02-26 | 2007-05-19 | 2008-04-09 | 2008-07-29 | no data | 111 | 82 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Mabini | 083707019 | Improvement of Barangay Road | 1 | 620116 | 435609 | 184507 | 392048.1 | 2nd Tranche | 240808.6 | 632856.7 | 392048.1 | 240808.6 | 100% | 100% | 130.5% | 102.1% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-25 | 2009-05-31 | n/a | 67 | 110 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Marcelo | 083707034 | Construction of Farm to Market Road | 1 | 928250 | 638250 | 290000 | 510600 | 2nd Tranche | 292761.69 | 803361.69 | 510600 | 292761.69 | 100% | 100% | 101% | 86.55% | 100% | 2007-02-26 | 2007-05-19 | 2007-08-14 | 2008-08-30 | no data | 382 | 78 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Marcelo | 083707034 | Improvement of Barangay Road | 1 | 976072 | 668472 | 307600 | 635311.83 | 3rd Tranche | 306120 | 941431.83 | 635311.83 | 306120 | 100% | 100% | 99.52% | 96.45% | 100% | no data | no data | 2008-10-06 | 2009-02-03 | no data | 120 | 78 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Marcelo | 083707034 | Improvement of Barangay Road | 1 | 937798 | 692586 | 245212 | 623327.4 | 2nd Tranche | 310935 | 840462.4 | 623327.4 | 217135 | 100% | 69.83% | 126.8% | 89.62% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-20 | 2009-05-31 | no data | 72 | 78 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Naga | 083707020 | Construction of Hanging Bridge | 1 | 768154 | 514254 | 253900 | 462828.6 | 2nd Tranche | 243370 | 706198.6 | 462828.6 | 243370 | 100% | 100% | 95.85% | 91.93% | 100% | 2007-02-26 | 2007-05-19 | 2008-01-26 | 2008-06-26 | n/a | 152 | 105 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Naga | 083707020 | Construction of 1 Classroom School Building | 1 | 771930 | 564237 | 207693 | 507813.3 | 1st Tranche | 194872.69 | 702685.99 | 507813.3 | 194872.69 | 100% | 100% | 93.83% | 91.03% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-18 | 2009-05-31 | no data | 74 | 115 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Osmena | 083707021 | Construction of Schoolbuilding(2 C) | 1 | 1001226 | 676241 | 324985 | 676241 | 3rd Tranche | 316585 | 992826 | 676241 | 316585 | 100% | 100% | 97.42% | 99.16% | 100% | no data | no data | 2008-08-13 | 2008-11-26 | n/a | 105 | 232 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Osmena | 083707021 | Improvement of Barangay Road | 1 | 628631 | 348085 | 280546 | 313276.5 | 1st Tranche | 245104 | 558380.5 | 313276.5 | 245104 | 100% | 100% | 87.37% | 88.82% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-30 | 2009-05-31 | no data | 62 | 230 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Plaridel | 083707022 | Improvement of Farm to Market Road | 1 | 742072 | 498450 | 243622 | 498450 | 2nd Tranche | 233208.54 | 731658.54 | 498450 | 233208.54 | 100% | 100% | 95.73% | 98.6% | 100% | 2007-02-26 | 2007-05-19 | 2007-12-14 | 2008-09-30 | no data | 291 | 365 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Plaridel | 083707022 | Construction of Schoolbuilding(1 C) | 1 | 596261 | 417382 | 178879 | 417372 | 3rd Tranche | 186307.36 | 603679.36 | 417372 | 186307.36 | 100% | 100% | 104.2% | 101.2% | 100% | no data | no data | 2008-08-11 | 2008-09-21 | no data | 41 | 96 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Ponong | 083707026 | Construction of Schoolbuilding(2 C) | 1 | 1021875 | 715323 | 306552 | 715323 | 3rd Tranche | 303047 | 1018370 | 715323 | 303047 | 100% | 100% | 98.86% | 99.66% | 100% | no data | no data | 2008-07-25 | 2008-11-24 | n/a | 122 | 375 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Ponong | 083707026 | Improvement of Barangay Road | 1 | 907055 | 645559 | 261496 | 581003.1 | 2nd Tranche | 237448 | 818451.1 | 581003.1 | 237448 | 100% | 100% | 90.8% | 90.23% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-16 | 2009-06-01 | no data | 77 | 375 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Revilla | 083707035 | Improvement of Farm to Market Road | 1 | 867508 | 606326 | 261182 | 517861.06 | 3rd Tranche | 271009.6 | 788870.66 | 517861.06 | 271009.6 | 100% | 100% | 103.8% | 90.94% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-13 | 2008-03-31 | n/a | 170 | 342 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | San Agustin | 083707027 | Improvement of Farm to Market Road | 1 | 917427 | 523427 | 394000 | 435084.3 | 2nd Tranche | 244616 | 679700.3 | 435084.3 | 244616 | 100% | 100% | 62.09% | 74.09% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-17 | 2008-04-30 | no data | 196 | 84 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Sto Nino | 083707028 | Construction of Spillway (4 lane) | 1 | 840141 | 568261 | 271880 | 511434.9 | 2nd Tranche | 265585 | 777019.9 | 511434.9 | 265585 | 100% | 100% | 97.68% | 92.49% | 100% | no data | no data | 2008-10-03 | 2009-01-30 | n/a | 119 | 64 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Sto. Nino | 083707028 | Improvement of Barangay Road | 1 | 923876 | 675680 | 248196 | 608112 | 1st Tranche | 228952.23 | 837064.23 | 608112 | 228952.23 | 100% | 100% | 92.25% | 90.6% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-19 | 2009-05-31 | no data | 73 | 64 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Sto. Niño | 083707028 | Improvement of Farm to Market Road | 1 | 534267 | 333677 | 200590 | 185998.3 | 2nd Tranche | 388690 | 574688.3 | 185998.3 | 388690 | 100% | 100% | 193.8% | 107.6% | 100% | 2007-02-26 | 2007-05-19 | 2007-10-26 | 2008-02-23 | no data | 120 | 62 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tabunok | 083707029 | Construction of Box Culvert (1 & 2 B) | 1 | 673254 | 448210 | 225044 | 403389 | 2nd Tranche | 373983 | 777372 | 403389 | 373983 | 100% | 100% | 166.2% | 115.5% | 100% | no data | no data | 2008-08-20 | 2008-12-22 | n/a | 124 | 542 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tagaytay | 083707030 | Improvement of Barangay Road | 1 | 1052283 | 729614 | 322669 | 656652 | 2nd Tranche | 354635.48 | 1011287.48 | 656652 | 354635.48 | 100% | 100% | 109.9% | 96.1% | 100% | no data | no data | 2008-07-24 | 2008-09-30 | no data | 68 | 246 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tagaytay | 083707030 | Improvement of Barangay Road | 1 | 919920 | 658876 | 261044 | 592988.4 | 1st Tranche | 228272 | 821260.4 | 592988.4 | 228272 | 100% | 100% | 87.45% | 89.28% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-18 | 2009-05-31 | no data | 74 | 250 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tinago | 083707031 | Construction of CHB Lined Canal | 1 | 710201 | 497140 | 213061 | 467043.25 | 2nd Tranche | 285427 | 752470.25 | 467043.25 | 285427 | 100% | 100% | 134% | 106% | 100% | no data | no data | 2008-06-25 | 2008-11-24 | n/a | 152 | 470 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tinago | 083707031 | Construction of CHB Lined Canal with Dike | 1 | 921513 | 659362 | 262151 | 593425.8 | 2nd Tranche | 203289 | 796714.8 | 593425.8 | 203289 | 100% | 100% | 77.55% | 86.46% | 100% | 2008-11-25 | 2008-12-12 | 2009-03-19 | 2009-05-31 | no data | 73 | 478 |  | 1
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tugas | 083707032 | Construction of Schoolbuilding(1 C) | 1 | 597382 | 417382 | 180000 | 408271.5 | 3rd Tranche | 162000 | 570271.5 | 408271.5 | 162000 | 100% | 100% | 90% | 95.46% | 100% | no data | no data | 2008-07-28 | 2008-11-27 | n/a | 122 | 324 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Balud | 083714002 | Construction of Water System (L2) | 1 | 918715 | 643100.5 | 275614.5 | 643100.5 | 3rd Tranche | 324089.5 | 967190 | 643100.5 | 324089.5 | 100% | 100% | 117.6% | 105.3% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-21 | 2008-03-29 | n/a | 221 | 517 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Balud | 083714002 | Construction of Drainage Canal with Cover | 1 | 1580005 | 1106003 | 474002 | 995402.7 | 1st Tranche | 458935.4 | 1454338.1 | 995402.7 | 458935.4 | 100% | 100% | 96.82% | 92.05% | 100% | 2008-12-17 | 2009-02-18 | 2009-04-27 | 2009-06-30 | no data | 64 | 550 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Cabul-an | 083714004 | Construction of Water System (L2) | 1 | 574439 | 402107 | 172332 | 402107 | 3rd Tranche | 182836.06 | 584943.06 | 402107 | 182836.06 | 100% | 100% | 106.1% | 101.8% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-27 | 2008-04-30 | n/a | 247 | 320 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Cabul-an | 083714004 | Construction of Footbridge with Pathway | 1 | 1161321 | 817151 | 344170 | 735435.9 | 1st Tranche | 358122 | 1093557.9 | 735435.9 | 358122 | 100% | 100% | 104.1% | 94.16% | 100% | 2008-12-17 | 2009-02-18 | 2009-04-21 | 2009-06-30 | no data | 70 | 360 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Culasian | 083714007 | Construction of Water System (L2) | 1 | 1299103 | 909380 | 389723 | 870886 | 2nd Tranche | 414817 | 1285703 | 870886 | 414817 | 100% | 100% | 106.4% | 98.97% | 100% | no data | no data | 2008-10-03 | 2009-02-28 | no data | 148 | 579 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Culasian | 083714007 | Construction of River Flood Control | 1 | 1417185 | 992030 | 425155 | 892827 | 1st Tranche | 235179.6 | 1128006.6 | 892827 | 235179.6 | 100% | 100% | 55.32% | 79.59% | 100% | 2008-12-17 | 2009-02-18 | 2009-05-13 | 2009-06-30 | no data | 48 | 563 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Gayad | 083714006 | Construction of Seawall | 1 | 1870963 | 1229107 | 641856 | 1106196.3 | 2nd Tranche | 521095 | 1627291.3 | 1106196.3 | 521095 | 100% | 100% | 81.19% | 86.98% | 100% | no data | no data | 2008-10-13 | 2009-02-28 | no data | 138 | 140 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Guinadiongan | 083714008 | Construction of Water System (L2) | 1 | 1140797 | 798557.5 | 342239.5 | 703677.15 | 2nd Tranche | 344599.5 | 1048276.65 | 703677.15 | 344599.5 | 100% | 100% | 100.7% | 91.89% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-27 | 2008-04-30 | n/a | 247 | 111 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Guinadiongan | 083714008 | Construction of Seawall | 1 | 1563550 | 1094485 | 469065 | 985036.5 | 1st Tranche | 488894.02 | 1473930.52 | 985036.5 | 488894.02 | 100% | 100% | 104.2% | 94.27% | 100% | 2008-12-17 | 2009-02-18 | 2009-05-07 | 2009-06-30 | no data | 54 | 127 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Lemon | 083714009 | Construction of Water System (L2) | 1 | 509036 | 356335 | 152701 | 337825 | 2nd Tranche | 163171.6 | 500996.6 | 337825 | 163171.6 | 100% | 100% | 106.9% | 98.42% | 100% | no data | no data | 2008-10-22 | 2008-11-30 | n/a | 39 | 274 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Libertad | 083714010 | Construction of Water System (L2) | 1 | 1207425 | 845197.5 | 362227.5 | 760677.75 | 2nd Tranche | 347667.5 | 1108345.25 | 760677.75 | 347667.5 | 100% | 100% | 95.98% | 91.79% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-27 | 2008-04-30 | n/a | 247 | 183 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Manloy | 083714011 | Construction of Gravity Fed Water Supply System | 1 | 768460 | 537922 | 230538 | 484129.8 | 1st Tranche | 227671 | 711800.8 | 484129.8 | 227671 | 100% | 100% | 98.76% | 92.63% | 100% | 2008-12-17 | 2009-02-18 | 2009-05-18 | 2009-06-30 | no data | 43 | 300 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Pinamopoan | 083714014 | Construction of Flood Control | 1 | 741866 | 458538.5 | 283327.5 | 366830.8 | 1st Tranche | 304177.46 | 671008.26 | 366830.8 | 304177.46 | 100% | 100% | 107.4% | 90.45% | 100% | 2007-02-17 | 2007-04-27 | 2007-07-30 | 2007-10-04 | no data | 66 | 520 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Poblacion I | 083714015 | Construction of Drainage System | 1 | 1051812 | 529670 | 522142 | 528916.56 | 2nd Tranche | 531336.31 | 1060252.87 | 528916.56 | 531336.31 | 100% | 100% | 101.8% | 100.8% | 100% | no data | no data | 2008-11-03 | 2008-12-31 | n/a | 58 | 487 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Poblacion II | 083714016 | Construction of Water System (L2) | 1 | 635888 | 445123 | 190765 | 440443.49 | 2nd Tranche | 198682.44 | 639125.93 | 440443.49 | 198682.44 | 100% | 100% | 104.2% | 100.5% | 100% | no data | no data | 2008-10-22 | 2008-12-15 | n/a | 54 | 314 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Poblacion Z-1 | 083714015 | Construction of Water System (L2) | 1 | 661847 | 463292 | 198555 | 463292 | 3rd Tranche | 234918.89 | 698210.89 | 463292 | 234918.89 | 100% | 100% | 118.3% | 105.5% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-27 | 2008-05-25 | no data | 272 | 351 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Potot | 083714017 | Construction of Water System (L2) | 1 | 869787 | 608850 | 260937 | 608850 | 3rd Tranche | 257526.95 | 866376.95 | 608850 | 257526.95 | 100% | 100% | 98.69% | 99.61% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-27 | 2008-09-10 | no data | 380 | 132 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Potot | 083714017 | Construction of River Flood Control | 1 | 874649 | 482581 | 392068 | 434322.9 | 2nd Tranche | 281203.08 | 715525.98 | 434322.9 | 281203.08 | 100% | 100% | 71.72% | 81.81% | 100% | 2008-12-17 | 2009-02-18 | 2009-05-04 | 2009-06-30 | no data | 57 | 166 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | San Joaquin | 083714018 | Construction of River Flood Control | 1 | 1046050 | 716221 | 329829 | 644598.9 | 1st Tranche | 160165 | 804763.9 | 644598.9 | 160165 | 100% | 100% | 48.56% | 76.93% | 100% | 2008-12-17 | 2009-02-18 | 2009-05-04 | completed as built | n/a | #VALUE! | 320 | completed as built | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | San Joaquin - C2 | 083714018 | Construction of Water System (L2) | 2 | 1989460 | 1392622 | 596838 | 1392622 | 3rd Tranche | 619092.8 | 2011714.8 | 1392622 | 619092.8 | 100% | 100% | 103.7% | 101.1% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-06 | 2008-09-30 | no data | 421 | 440 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Visares | 083714023 | Construction of Water System (L2) | 2 | 1989460 | 1392622 | 596838 | 1392622 | 3rd Tranche | 619092.8 | 2011714.8 | 1392622 | 619092.8 | 100% | 100% | 103.7% | 101.1% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-06 | 2008-09-30 | no data | 421 | 440 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Sto Nino | 083714019 | Construction of Gravity Fed Water Supply System | 1 | 1282572 | 885896 | 396676 | 797306.4 | 1st Tranche | 405772 | 1203078.4 | 797306.4 | 405772 | 100% | 100% | 102.3% | 93.8% | 100% | 2008-12-17 | 2009-02-18 | 2009-05-07 | 2009-06-30 | no data | 54 | 267 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Talairan | 083714020 | Constn. Of Pathways & Stairs | 1 | 345626 | 241938 | 103688 | 227882 | 3rd Tranche | 116538 | 344420 | 227882 | 116538 | 100% | 100% | 112.4% | 99.65% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-27 | 2008-03-26 | no data | 212 | 152 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Talairan | 083714020 | Construction of Water System (L2) | 1 | 493480 | 347734 | 145746 | 312960.6 | 1st Tranche | 155144.84 | 469547.6 | 312960.6 | 156587 | 100% | 100.9% | 106.4% | 95.15% | 100% | no data | no data | 2008-10-15 | 2009-02-28 | no data | 136 | 161 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Talisay | 083714021 | Construction of Seawall | 1 | 636853 | 445797 | 191056 | 398671.5 | 3rd Tranche | 187096 | 585767.5 | 398671.5 | 187096 | 100% | 100% | 97.93% | 91.98% | 100% | 2007-02-17 | 2007-04-27 | 2007-08-06 | 2008-02-16 | no data | 194 | 117 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Talisay | 083714021 | Construction of Water System (L2) | 1 | 671517 | 470506 | 201011 | 423455.4 | 2nd Tranche | 138803.25 | 562258.65 | 423455.4 | 138803.25 | 100% | 100% | 69.05% | 83.73% | 100% | no data | no data | 2008-10-15 | 2009-02-28 | no data | 136 | 143 |  | 1
VIII | 08 | Leyte | 0837 | Capoocan | 083714 | Tolibao | 083714022 | Pathway w/ Grouted Riprap | 1 | 716770 | 445750 | 271020 | 426850 | 2nd Tranche | 273137 | 699987 | 426850 | 273137 | 100% | 100% | 100.8% | 97.66% | 100% | no data | no data | 2008-10-15 | 2008-12-15 | n/a | 61 | 107 |  | 1
VIII | 08 | Leyte | 0837 | Javier | 083724 | A. Bonifacio | 083724002 | Farm to Market Road | 1 | 939636 | 657745 | 281891 | 526196 | 1st Tranche | 448044.81 | 974240.81 | 526196 | 448044.81 | 100% | 100% | 158.9% | 103.7% | 100% | 2008-11-27 | 2009-02-27 | 2009-05-18 | 2009-06-30 | no data | 43 | 93 |  | 1
VIII | 08 | Leyte | 0837 | Javier | 083724 | Abuyogay | 083724001 | Water System Level 2 | 1 | 1141224 | 798856.8 | 342367.2 | 718971.12 | 2nd Tranche | 342287.2 | 1061258.32 | 718971.12 | 342287.2 | 100% | 100% | 99.98% | 92.99% | 100% | 2007-02-20 | 2007-04-20 | 2007-08-08 | 2008-02-08 | no data | 184 | 104 |  | 1
VIII | 08 | Leyte | 0837 | Javier | 083724 | Batug | 083724003 | Improvement of Farm to Market Road with Masonry Ditches | 1 | 731030 | 511721 | 219309 | 409376.8 | 1st Tranche | 248609 | 657985.8 | 409376.8 | 248609 | 100% | 100% | 113.4% | 90.01% | 100% | 2008-11-27 | 2009-02-27 | 2009-05-11 | 2009-06-30 | no data | 50 | 161 |  | 1
VIII | 08 | Leyte | 0837 | Javier | 083724 | Binulho | 083724004 | 3 Barrel Box Culvert | 1 | 2647022 | 1852915.4 | 794106.6 | 1738373.86 | 3rd Tranche | 1097880.23 | 2836254.09 | 1738373.86 | 1097880.23 | 100% | 100% | 138.3% | 107.1% | 100% | no data | no data | 2008-10-13 | 2009-01-13 | n/a | 92 | 472 |  | 1
VIII | 08 | Leyte | 0837 | Javier | 083724 | Binulho | 083724004 | Construction of Drainage System | 1 | 326802 | 228761 | 98041 | 205022.07 | 2nd Tranche | 136942.88 | 341964.95 | 205022.07 | 136942.88 | 100% | 100% | 139.7% | 104.6% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-27 | 2009-06-30 | no data | 64 | 628 |  | 1
VIII | 08 | Leyte | 0837 | Javier | 083724 | Calzada | 083724005 | Flood Control | 1 | 975152 | 682606.4 | 292545.6 | 614345.76 | 2nd Tranche | 301771.6 | 916117.36 | 614345.76 | 301771.6 | 100% | 100% | 103.2% | 93.95% | 100% | 2007-02-20 | 2007-04-20 | 2007-08-06 | 2007-09-21 | no data | 46 | 140 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Calzada | 083724005 | Construction of Drainage System | 1 | 361125 | 252788 | 108337 | 252788 | 2nd Tranche | 108600.84 | 361388.84 | 252788 | 108600.84 | 100% | 100% | 100.2% | 100.1% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 140 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Cancayang | 083724006 | Water System Level 1 | 1 | 423375 | 296362.5 | 127012.5 | 237090 | 1st Tranche | 127052.9 | 364142.9 | 237090 | 127052.9 | 100% | 100% | 100% | 86.01% | 100% | 2007-02-20 | 2007-04-20 | 2007-08-01 | 2007-09-11 | no data | 41 | 127 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Caranhug | 083724007 | Construction of Water System Level 1 | 1 | 357762 | 250433.4 | 107328.6 | 225390.06 | 2nd Tranche | 107427.89 | 332817.95 | 225390.06 | 107427.89 | 100% | 100% | 100.1% | 93.03% | 100% | no data | no data | 2008-08-04 | 2008-09-13 | n/a | 40 | 164 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Caraye | 083724008 | Rehabilitation of FMR | 1 | 2630215 | 1841150.5 | 789064.5 | 1841150.45 | 3rd Tranche | 823064.5 | 2664214.95 | 1841150.45 | 823064.5 | 100% | 100% | 104.3% | 101.3% | 100% | 2007-02-20 | 2007-04-20 | 2008-02-05 | 2008-06-25 | n/a | 141 | 126 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Casalungan | 083724009 | Supply of Fishing Facilities | 1 | 399486 | 279640.2 | 119845.8 | 223712.16 | 1st Tranche | 119845.8 | 343557.96 | 223712.16 | 119845.8 | 100% | 100% | 100% | 86% | 100% | 2007-02-20 | 2007-04-20 | 2007-09-22 | 2007-11-10 | no data | 49 | 65 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Comatin | 083724010 | Water System Level 2 | 1 | 2443412 | 1710388.4 | 733023.6 | 1539349.56 | 2nd Tranche | 764023.6 | 2279735.08 | 1539349.56 | 740385.52 | 100% | 96.91% | 104.2% | 93.3% | 100% | 2007-02-20 | 2007-04-20 | 2008-01-05 | 2008-06-30 | n/a | 177 | 280 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Comatin | 083724010 | Construction of Pathway | 1 | 364710 | 255297 | 109413 | 204237.6 | 1st Tranche | 108042 | 312279.6 | 204237.6 | 108042 | 100% | 100% | 98.75% | 85.62% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 280 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Guindapunan | 083724011 | Farm to Market Road | 1 | 2545680 | 1781976 | 763704 | 1603778.4 | 1st Tranche | 763716 | 2367494.4 | 1603778.4 | 763716 | 100% | 100% | 100% | 93% | 100% | no data | no data | 2008-10-17 | 2009-01-17 | n/a | 92 | 49 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Inayupan | 083724012 | Hanging Bridge | 1 | 1878772 | 1315140.4 | 563631.6 | 1315140.4 | 3rd Tranche | 665534.4 | 1980674.8 | 1315140.4 | 665534.4 | 100% | 100% | 118.1% | 105.4% | 100% | 2007-02-20 | 2007-04-20 | 2007-11-28 | 2008-06-30 | n/a | 215 | 162 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Inayupan | 083724012 | Construction of Drainage System | 1 | 341950 | 239365 | 102585 | 215428.5 | 2nd Tranche | 119013.23 | 334441.73 | 215428.5 | 119013.23 | 100% | 100% | 116% | 97.8% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 162 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Laray | 083724013 | Construction of Solar Dryer | 1 | 250659 | 174138 | 76521 | 139310.4 | 1st Tranche | 91572.9 | 230883.3 | 139310.4 | 91572.9 | 100% | 100% | 119.7% | 92.11% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-05-30 | no data | 40 | 120 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Magsaysay | 083724014 | Farm to Market Road | 1 | 937862 | 656504 | 281358 | 590853.6 | 2nd Tranche | 375981 | 966834.6 | 590853.6 | 375981 | 100% | 100% | 133.6% | 103.1% | 100% | 2008-11-27 | 2009-02-27 | 2009-05-29 | 2009-06-30 | no data | 32 | 76 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Malitbogay | 083724015 | Construction of School Building (2 Rm) | 1 | 1224057 | 856839.9 | 367217.1 | 856839.9 | 3rd Tranche | 367457.1 | 1224297 | 856839.9 | 367457.1 | 100% | 100% | 100.1% | 100% | 100% | no data | no data | 2008-07-28 | 2008-10-15 | n/a | 79 | 191 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Malitbogay | 083724015 | Construction of Drainage System | 1 | 323864 | 226705 | 97159 | 204034.5 | 2nd Tranche | 105358.84 | 309393.34 | 204034.5 | 105358.84 | 100% | 100% | 108.4% | 95.53% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-22 | 2009-06-30 | no data | 69 | 198 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Manarug | 083724016 | Construction of Box Culvert | 1 | 2196205 | 1459120 | 737085 | 1417120 | 3rd Tranche | 812829.75 | 2229949.75 | 1417120 | 812829.75 | 100% | 100% | 110.3% | 101.5% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 73 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Manlilisid | 083724017 | Construction of Flood Control | 1 | 2201012 | 1483289 | 717723 | 1334960.1 | 2nd Tranche | 856002 | 2190962.1 | 1334960.1 | 856002 | 100% | 100% | 119.3% | 99.54% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 301 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Naliwatan | 083724018 | Hanging Bridge | 1 | 1619882 | 1133917.4 | 485964.6 | 1133917.4 | 3rd Tranche | 551190.6 | 1685108 | 1133917.4 | 551190.6 | 100% | 100% | 113.4% | 104% | 100% | 2007-02-20 | 2007-04-20 | 2008-01-13 | 2008-06-30 | n/a | 169 | 112 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Odiong | 083724019 | Spring Development Water System | 1 | 909529 | 615260.9 | 294268.1 | 553734.81 | 2nd Tranche | 294268.1 | 848002.91 | 553734.81 | 294268.1 | 100% | 100% | 100% | 93.24% | 100% | no data | no data | 2009-03-23 | 2009-06-30 | no data | 99 | 482 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Picas Norte | 083724020 | Water System Level 1 | 1 | 488482 | 341937.4 | 146544.6 | 273549.92 | 1st Tranche | 146544.6 | 420094.52 | 273549.92 | 146544.6 | 100% | 100% | 100% | 86% | 100% | 2007-02-20 | 2007-04-20 | 2007-08-01 | 2007-09-15 | no data | 45 | 103 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Pinocawan | 083724021 | Construction of Water System Level 1 | 1 | 216351 | 151445.7 | 64905.3 | 141301.13 | 3rd Tranche | 65126.96 | 206428.09 | 141301.13 | 65126.96 | 100% | 100% | 100.3% | 95.41% | 100% | no data | no data | 2008-07-08 | 2008-10-08 | n/a | 92 | 130 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Pinocawan | 083724021 | Rehabilitation of Farm to Market Road | 1 | 436972 | 305880 | 131092 | 244704 | 1st Tranche | 139943.73 | 384647.73 | 244704 | 139943.73 | 100% | 100% | 106.8% | 88.03% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-14 | 2009-06-30 | no data | 77 | 124 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Rizal | 083724024 | Resurfacing of Farm to Market Road | 1 | 1366444 | 956510.8 | 409933.2 | 956510.8 | 2nd Tranche | 497393.3 | 1453904.1 | 956510.8 | 497393.3 | 100% | 100% | 121.3% | 106.4% | 100% | no data | no data | 2008-11-03 | 2009-02-03 | n/a | 92 | 176 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Rizal | 083724024 | Rehabilitation of Farm to Market Road | 1 | 395799 | 277059 | 118740 | 221647.2 | 1st Tranche | 123427.2 | 345074.4 | 221647.2 | 123427.2 | 100% | 100% | 103.9% | 87.18% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 150 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | San Sotero | 083724028 | Drainage System | 1 | 848693 | 594085.1 | 254607.9 | 594085.1 | 3rd Tranche | 259238.6 | 853323.7 | 594085.1 | 259238.6 | 100% | 100% | 101.8% | 100.5% | 100% | no data | no data | 2008-07-28 | 2008-09-28 | n/a | 62 | 276 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Sta. Cruz | 083724026 | 1 Classroom School Building | 1 | 721970 | 551039 | 170931 | 495935.1 | 2nd Tranche | 263644 | 759579.1 | 495935.1 | 263644 | 100% | 100% | 154.2% | 105.2% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-23 | 2009-06-30 | no data | 68 | 89 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Talisayan | 083724027 | Construction of School Building (1 Rm) | 1 | 632260 | 442582 | 189678 | 442582 | 3rd Tranche | 189678 | 632260 | 442582 | 189678 | 100% | 100% | 100% | 100% | 100% | no data | no data | 2008-09-01 | 2008-11-01 | n/a | 61 | 179 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Talisayan | 083724027 | Rehabilitation of Farm to Market Road | 1 | 630000 | 441000 | 189000 | 352800 | 2nd Tranche | 191216.45 | 544016.45 | 352800 | 191216.45 | 100% | 100% | 101.2% | 86.35% | 100% | 2008-11-27 | 2009-02-27 | 2009-05-05 | 2009-06-30 | no data | 56 | 164 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Ulhay | 083724029 | Spring Development Water System | 1 | 1046104 | 732272.8 | 313831.2 | 679952.09 | 2nd Tranche | 329365.05 | 1009317.14 | 679952.09 | 329365.05 | 100% | 100% | 104.9% | 96.48% | 100% | no data | no data | 2009-01-27 | 2009-04-07 | n/a | 70 | 168 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Zone 1 | 083724022 | Barangay Health Station | 1 | 743300 | 494410 | 248890 | 480620 | 2nd Tranche | 323638.74 | 804258.74 | 480620 | 323638.74 | 100% | 100% | 130% | 108.2% | 100% | 2008-11-27 | 2009-02-27 | 2009-05-06 | 2009-06-30 | no data | 55 | 321 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Javier | 083724 | Zone 2 | 083724022 | Construction of Drainage System | 1 | 1326678 | 879075 | 447603 | 853426 | 2nd Tranche | 536044.23 | 1389470.23 | 853426 | 536044.23 | 100% | 100% | 119.8% | 104.7% | 100% | 2008-11-27 | 2009-02-27 | 2009-04-20 | 2009-06-30 | no data | 71 | 306 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Alegria | 083725001 | Water Supply System (L 1) | 1 | 176965 | 123876 | 53089 | 74325.6 | 1st Tranche | 54090 | 128415.6 | 74325.6 | 54090 | 100% | 100% | 101.9% | 72.57% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-06 | 2007-08-23 | no data | 17 | 65 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Anibong | 083725002 | Construction of Drainage Canal | 1 | 214635 | 150245 | 64390 | 120196 | 1st Tranche | 66417 | 186613 | 120196 | 66417 | 100% | 100% | 103.1% | 86.94% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-13 | 2007-09-04 | no data | 22 | 129 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Anibong | 083725002 | San. Toilet Facility w/ L1 Water System | 1 | 2180821 | 1526575 | 654246 | 1373917.5 | 2nd Tranche | 654246 | 2028163.5 | 1373917.5 | 654246 | 100% | 100% | 100% | 93% | 100% | no data | no data | 2008-11-04 | 2009-02-28 | n/a | 116 | 132 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Anibong | 083725002 | Barangay Health Station | 1 | 772330 | 617864 | 154466 | 556077.6 | 1st Tranche | 158249 | 714326.6 | 556077.6 | 158249 | 100% | 100% | 102.4% | 92.49% | 100% | 2008-12-17 | 2009-02-17 | 2009-05-11 | 2009-08-28 | n/a | 109 | 159 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Aslum | 083725003 | Water Supply System (L 1) | 1 | 166369 | 116458 | 49911 | 81520.6 | 1st Tranche | 50811 | 132331.6 | 81520.6 | 50811 | 100% | 100% | 101.8% | 79.54% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-08 | 2007-08-31 | no data | 23 | 53 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Balante | 083725004 | Construction of Box Culvert | 1 | 166609 | 116627 | 49982 | 104964.7 | 2nd Tranche | 50882 | 155846.7 | 104964.7 | 50882 | 100% | 100% | 101.8% | 93.54% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-20 | 2008-01-11 | no data | 144 | 55 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Balante | 083725004 | Drainage Canal | 1 | 384557 | 307645 | 76912 | 276880 | 2nd Tranche | 77033.2 | 353913.2 | 276880 | 77033.2 | 100% | 100% | 100.2% | 92.03% | 100% | 2008-12-17 | 2009-02-17 | 2009-03-31 | 2009-05-31 | no data | 61 | 57 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bongdo | 083725005 | Construction of Farm to Market Road | 1 | 418775 | 293143 | 125632 | 293143 | 3rd Tranche | 126432 | 419575 | 293143 | 126432 | 100% | 100% | 100.6% | 100.2% | 100% | 2007-02-27 | 2007-04-29 | 2007-09-03 | 2008-09-26 | no data | 389 | 125 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bongdo | 083725005 | Sanitary Toilet Facility | 1 | 1610467 | 1535772 | 74695 | 1228617.6 | 1st Tranche | 74695 | 1303312.6 | 1228617.6 | 74695 | 100% | 100% | 100% | 80.93% | 100% | 2008-12-17 | 2009-02-17 | 2009-06-13 | 2009-07-31 | no data | 48 | 86 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bonifacio | 083725006 | Construction of Footbridge | 1 | 184526 | 129168 | 55358 | 116301.2 | 2nd Tranche | 56159 | 172460.2 | 116301.2 | 56159 | 100% | 100% | 101.4% | 93.46% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-27 | 2007-09-18 | no data | 22 | 125 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bonifacio | 083725006 | Farm to Market Road | 1 | 820336 | 574235 | 246101 | 516811.5 | 2nd Tranche | 246101 | 762912.5 | 516811.5 | 246101 | 100% | 100% | 100% | 93% | 100% | no data | no data | 2008-09-15 | 2008-11-05 | n/a | 51 | 60 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bugho | 083725007 | Water Supply System (L 1) | 1 | 114543 | 80180 | 34363 | 72162.04 | 2nd Tranche | 38909 | 111071.04 | 72162.04 | 38909 | 100% | 100% | 113.2% | 96.97% | 100% | 2007-02-27 | 2007-04-29 | 2007-11-20 | 2008-02-03 | no data | 75 | 35 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bugho | 083725007 | Sanitary Toilet Facility | 1 | 621998 | 497598 | 124400 | 398078.4 | 1st Tranche | 114400 | 796156.4 | 398078.4 | 398078 | 100% | 348% | 91.96% | 128% | 100% | 2008-12-17 | 2009-02-17 | 2009-06-11 | 2009-08-28 | n/a | 78 | 33 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Calbasag | 083725008 | Construction of Flood Control | 1 | 5371764 | 3496014 | 1875750 | 3146412.6 | 2nd Tranche | 1876650 | 5023062.6 | 3146412.6 | 1876650 | 100% | 100% | 100% | 93.51% | 100% | 2007-02-27 | 2007-04-29 | 2008-01-15 | 2008-09-25 | n/a | 254 | 204 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Calbasag | 083725008 | Reinforced Concrete Box Culvert(3 Barrels) | 1 | 872754 | 698204 | 174550 | 698204 | 2nd Tranche | 174550.4 | 872754.4 | 698204 | 174550.4 | 100% | 100% | 100% | 100% | 100% | 2008-12-17 | 2009-02-17 | 2009-05-04 | 2009-05-30 | no data | 26 | 248 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Caridad | 083725009 | Water Supply System (L 2) | 1 | 369686 | 258780 | 110906 | 207024 | 1st Tranche | 107682 | 314706 | 207024 | 107682 | 100% | 100% | 97.09% | 85.13% | 100% | 2007-02-27 | 2007-04-29 | 2007-11-28 | 2008-02-07 | no data | 71 | 57 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Caridad | 083725009 | Drainage Canal | 1 | 642836 | 449985 | 192851 | 404986.5 | 2nd Tranche | 192945.7 | 597932.2 | 404986.5 | 192945.7 | 100% | 100% | 100% | 93.01% | 100% | no data | no data | 2008-08-14 | 2008-09-16 | n/a | 33 | 62 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Caridad | 083725009 | Sanitary Toilet Facility | 1 | 908433 | 726747 | 181686 | 654072.3 | 2nd Tranche | 187472.42 | 841544.72 | 654072.3 | 187472.42 | 100% | 100% | 103.2% | 92.64% | 100% | 2008-12-17 | 2009-02-17 | 2009-06-01 | 2009-08-28 | n/a | 88 | 49 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Cuya-e | 083725010 | Drainage Canal | 1 | 507701 | 355391 | 152310 | 355391 | 3rd Tranche | 173070.4 | 528461.4 | 355391 | 173070.4 | 100% | 100% | 113.6% | 104.1% | 100% | no data | no data | 2008-08-18 | 2009-06-26 | n/a | 312 | 166 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Cuya-e | 083725010 | Post-Harvest Facility | 1 | 148372 | 103861 | 44511 | 93474.9 | 2nd Tranche | 45411 | 138885.9 | 93474.9 | 45411 | 100% | 100% | 102% | 93.61% | 100% | 2007-02-27 | 2007-04-29 | 2008-02-24 | 2008-04-30 | n/a | 66 | 90 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | District 1 | 083725018 | Drainage Canal with Curb & Gutter | 1 | 1982198 | 1585758 | 396440 | 1427182.2 | 2nd Tranche | 396440 | 1823622.2 | 1427182.2 | 396440 | 100% | 100% | 100% | 92% | 100% | 2008-12-17 | 2009-02-17 | 2009-04-28 | 2009-08-28 | n/a | 122 | 122 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | District 3 | 083725020 | Drainage Canal with Curb & Gutter | 1 | 1665149 | 1332119 | 333030 | 1065695.2 | 1st Tranche | 368090 | 1433785.2 | 1065695.2 | 368090 | 100% | 100% | 110.5% | 86.11% | 100% | 2008-12-17 | 2009-02-17 | 2009-06-01 | 2009-08-30 | n/a | 90 | 159 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | District II | 083725019 | Construction of Drainage Canal | 1 | 700000 | 490000 | 210000 | 441000 | 2nd Tranche | 211000 | 652000 | 441000 | 211000 | 100% | 100% | 100.5% | 93.14% | 100% | 2007-02-27 | 2007-04-29 | 2007-07-20 | 2007-08-22 | no data | 33 | 171 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | District IV | 083725021 | Construction of Spillway | 1 | 754259 | 527981 | 226278 | 473146.9 | 2nd Tranche | 227278 | 700424.9 | 473146.9 | 227278 | 100% | 100% | 100.4% | 92.86% | 100% | 2007-02-27 | 2007-04-29 | 2007-09-03 | 2007-10-01 | no data | 28 | 160 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Dita | 083725013 | Construction of Farm to Market Road | 1 | 533549 | 373485 | 160064 | 373485 | 3rd Tranche | 145608 | 519093 | 373485 | 145608 | 100% | 100% | 90.97% | 97.29% | 100% | 2007-02-27 | 2007-04-29 | 2007-07-20 | 2008-06-15 | n/a | 331 | 172 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Gitabla | 083725014 | Water Supply System L1 | 1 | 209881 | 146917 | 62964 | 102841.9 | 1st Tranche | 63964 | 166805.9 | 102841.9 | 63964 | 100% | 100% | 101.6% | 79.48% | 100% | no data | no data | 2008-07-28 | 2008-08-11 | no data | 14 | 51 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Hindang | 083725015 | Water Supply System (L 2) | 1 | 271317 | 189922 | 81395 | 151937.6 | 1st Tranche | 82395 | 234332.6 | 151937.6 | 82395 | 100% | 100% | 101.2% | 86.37% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-07 | 2007-08-27 | no data | 20 | 96 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Hindang | 083725015 | Farm to Market Road | 1 | 1212972 | 849080 | 363892 | 849080 | 2nd Tranche | 363892 | 1212972 | 849080 | 363892 | 100% | 100% | 100% | 100% | 100% | no data | no data | 2008-08-20 | 2008-10-28 | n/a | 69 | 132 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Inawangan | 083725016 | Water Supply System (L 1) | 1 | 276439 | 193508 | 82931 | 174157.2 | 2nd Tranche | 99187 | 273344.2 | 174157.2 | 99187 | 100% | 100% | 119.6% | 98.88% | 100% | 2007-02-27 | 2007-04-29 | 2007-09-01 | 2007-09-18 | no data | 17 | 43 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Jurao | 083725017 | Water Supply System (L 1) | 1 | 174846 | 122393 | 52453 | 110153.7 | 2nd Tranche | 53453 | 163606.7 | 110153.7 | 53453 | 100% | 100% | 101.9% | 93.57% | 100% | 2007-02-27 | 2007-04-29 | 2007-10-04 | 2007-10-26 | no data | 22 | 38 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Jurao | 083725017 | Sanitary Toilet Facility | 1 | 660944 | 528756 | 132188 | 475880.4 | 2nd Tranche | 132187.5 | 608067.9 | 475880.4 | 132187.5 | 100% | 100% | 100% | 92% | 100% | 2008-12-17 | 2009-02-17 | 2009-06-04 | 2009-07-31 | no data | 57 | 35 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Poblacion District 4 | 083725021 | Drainage Canal | 1 | 2445080 | 1711556 | 733524 | 1711556 | 2nd Tranche | 771093.99 | 2482649.99 | 1711556 | 771093.99 | 100% | 100% | 105.1% | 101.5% | 100% | no data | no data | 2008-11-03 | 2009-06-30 | n/a | 239 | 184 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | San Andres | 083725022 | Water Supply System (L 1) | 1 | 88085 | 61660 | 26425 | 30830 | 1st Tranche | 27616 | 58446 | 30830 | 27616 | 100% | 100% | 104.5% | 66.35% | 100% | 2007-02-27 | 2007-04-29 | 2007-07-12 | 2007-07-22 | no data | 10 | 110 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | San Andres | 083725022 | Barangay Health Station | 1 | 779831 | 623864 | 155967 | 561477.6 | 2nd Tranche | 173289.5 | 734767.1 | 561477.6 | 173289.5 | 100% | 100% | 111.1% | 94.22% | 100% | 2008-12-17 | 2009-02-17 | 2009-04-29 | 2009-06-30 | no data | 62 | 100 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | San Pablo | 083725023 | Construction of Box Culvert | 1 | 277746 | 194422 | 83324 | 174979.8 | 2nd Tranche | 84324 | 259303.8 | 174979.8 | 84324 | 100% | 100% | 101.2% | 93.36% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-06 | 2007-08-25 | no data | 19 | 31 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | San Pablo | 083725023 | San. Toilet Facility w/ L1 Water System | 1 | 763241 | 507015 | 256226 | 456313.5 | 2nd Tranche | 256545 | 712858.5 | 456313.5 | 256545 | 100% | 100% | 100.1% | 93.4% | 100% | no data | no data | 2008-10-04 | 2009-04-15 | n/a | 193 | 43 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Sta. Cruz | 083725024 | Water Supply System (L 1) | 1 | 140503 | 98352 | 42151 | 88516.8 | 2nd Tranche | 43151 | 131667.8 | 88516.8 | 43151 | 100% | 100% | 102.4% | 93.71% | 100% | 2007-02-27 | 2007-04-29 | 2007-07-20 | 2007-08-04 | no data | 15 | 80 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Sto. Niño | 083725025 | Construction of Drainage Canal | 1 | 243135 | 170195 | 72940 | 153175.5 | 2nd Tranche | 94341 | 247516.5 | 153175.5 | 94341 | 100% | 100% | 129.3% | 101.8% | 100% | 2007-02-27 | 2007-04-29 | 2007-09-17 | 2008-04-02 | n/a | 198 | 215 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Sto. Niño | 083725025 | Water Supply System L1 | 1 | 282645 | 197852 | 84793 | 130211.2 | 3rd Tranche | 84793 | 215004.2 | 130211.2 | 84793 | 100% | 100% | 100% | 76.07% | 100% | no data | no data | 2008-08-08 | 2008-08-23 | no data | 15 | 187 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Tagkip | 083725026 | Farm Tractor | 1 | 284760 | 199332 | 85428 | 159465.6 | 1st Tranche | 87012 | 246477.6 | 159465.6 | 87012 | 100% | 100% | 101.9% | 86.56% | 100% | 2007-02-27 | 2007-04-29 | 2008-08-18 | 2008-09-03 | no data | 16 | 43 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Tagkip | 083725026 | Sanitary Toilet Facility | 1 | 560933 | 392653 | 168280 | 353387.7 | 2nd Tranche | 168282 | 521669.7 | 353387.7 | 168282 | 100% | 100% | 100% | 93% | 100% | no data | no data | 2008-10-18 | 2009-04-04 | n/a | 168 | 51 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Tolosahay | 083725027 | Water Supply System (L 2) | 1 | 119473 | 83631 | 35842 | 58541.7 | 1st Tranche | 36742 | 95283.7 | 58541.7 | 36742 | 100% | 100% | 102.5% | 79.75% | 100% | 2007-02-27 | 2007-04-29 | 2007-08-13 | 2007-08-25 | no data | 12 | 71 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Villa Hermosa | 083725028 | Water Supply System (L 1) | 1 | 255623 | 178936 | 76687 | 161042.4 | 2nd Tranche | 77687 | 238729.4 | 161042.4 | 77687 | 100% | 100% | 101.3% | 93.39% | 100% | 2007-02-27 | 2007-04-29 | 2007-10-05 | 2007-11-01 | no data | 27 | 76 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Julita | 083725 | Villa Hermosa | 083725028 | Sanitary Toilet Facility | 1 | 1555345 | 1088741 | 466604 | 979866.9 | 2nd Tranche | 495422.5 | 1475289.4 | 979866.9 | 495422.5 | 100% | 100% | 106.2% | 94.85% | 100% | no data | no data | 2008-09-15 | 2009-02-28 | n/a | 166 | 96 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Aguiting | 083726001 | Road Concreting on Critical Slopes | 1 | 938829 | 613317 | 325512 | 613317 | 2nd Tranche | 514759 | 1128076 | 613317 | 514759 | 100% | 100% | 158.1% | 120.2% | 100% | no data | no data | 2008-11-10 | 2008-12-31 | n/a | 51 | 538 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Aguiting | 083726001 | Construction of Drainage | 1 | 700000 | 490000 | 210000 | 364000 | 1st Tranche | 214928.35 | 578928.35 | 364000 | 214928.35 | 100% | 100% | 102.3% | 82.7% | 100% | 2008-12-16 | 2009-01-30 | 2009-08-03 | 2009-08-31 | n/a | 28 | 538 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Cacao | 083726002 | Const. Of School Building 2 Rm | 1 | 1115100 | 779584 | 335516 | 779584 | 3rd Tranche | 355679 | 1135263 | 779584 | 355679 | 100% | 100% | 106% | 101.8% | 100% | no data | no data | 2008-07-23 | 2008-10-23 | n/a | 92 | 189 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Hiluctugan | 083726004 | Construction of Health Station | 1 | 751175 | 525820 | 225355 | 472806 | 1st Tranche | 256352 | 729158 | 472806 | 256352 | 100% | 100% | 113.8% | 97.07% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-15 | 2009-06-15 | no data | 61 | 333 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Kawayan | 083726003 | Constn. Of School Building (2 Rm) | 1 | 993600 | 695520 | 298080 | 687459.3 | 3rd Tranche | 343980 | 1031439.3 | 687459.3 | 343980 | 100% | 100% | 115.4% | 103.8% | 100% | 2007-02-22 | 2007-04-26 | 2007-09-10 | 2008-05-31 | n/a | 264 | 164 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Kawayan | 083726003 | Construction of Lined Ditch Canal | 1 | 365418 | 255792 | 109626 | 255792 | 3rd Tranche | 114228.2 | 370020.2 | 255792 | 114228.2 | 100% | 100% | 104.2% | 101.3% | 100% | no data | no data | 2008-08-28 | 2008-11-15 | n/a | 79 | 186 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libertad | 083726005 | Rice Mill with Structure | 1 | 803500 | 562450 | 241050 | 543350 | 2nd Tranche | 250992 | 794342 | 543350 | 250992 | 100% | 100% | 104.1% | 98.86% | 100% | 2007-02-22 | 2007-04-26 | 2007-07-26 | 2008-04-30 | n/a | 279 | 238 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libertad | 083726005 | Construction of Lined Ditch Canal | 1 | 375130 | 262590 | 112540 | 253490 | 3rd Tranche | 119019 | 372509 | 253490 | 119019 | 100% | 100% | 105.8% | 99.3% | 100% | no data | no data | 2008-09-12 | 2008-10-31 | n/a | 49 | 256 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libertad | 083726005 | Construction of Health Station | 1 | 756825 | 529778 | 227047 | 476800.2 | 1st Tranche | 268481 | 745281.2 | 476800.2 | 268481 | 100% | 100% | 118.2% | 98.47% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-20 | 2009-06-30 | no data | 71 | 238 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libongao | 083726006 | Constn. Of School Building (2 Rm) | 1 | 957900 | 670530 | 287370 | 599136.95 | 2nd Tranche | 330395 | 929531.95 | 599136.95 | 330395 | 100% | 100% | 115% | 97.04% | 100% | 2007-02-22 | 2007-04-26 | 2007-07-25 | 2008-03-15 | no data | 234 | 385 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libongao | 083726006 | Construction of Health Station | 1 | 750807 | 525624 | 225183 | 525423 | 3rd Tranche | 231448.77 | 756871.77 | 525423 | 231448.77 | 100% | 100% | 102.8% | 100.8% | 100% | no data | no data | 2008-07-23 | 2008-11-23 | n/a | 123 | 465 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libongao | 083726006 | Construction of Drainage Canal | 1 | 750000 | 225950 | 524050 | 203355 | 1st Tranche | 523655.21 | 727010.21 | 203355 | 523655.21 | 100% | 100% | 99.92% | 96.93% | 100% | 2008-12-16 | 2009-01-30 | 2009-03-27 | 2009-05-31 | no data | 65 | 256 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Lim-ao | 083726007 | Construction of Health Station | 1 | 756825 | 529778 | 227047 | 478842.4 | 1st Tranche | 260570 | 739412.4 | 478842.4 | 260570 | 100% | 100% | 114.8% | 97.7% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-16 | 2009-06-20 | no data | 65 | 437 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Lonoy | 083726008 | Road Concreting on Critical Slopes | 1 | 932300 | 610113 | 322187 | 594113 | 2nd Tranche | 501716 | 1095829 | 594113 | 501716 | 100% | 100% | 155.7% | 117.5% | 100% | no data | no data | 2008-11-10 | 2009-01-10 | n/a | 61 | 476 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Mahawan | 083726009 | Construction of Steel Footbridge | 1 | 486800 | 340760 | 146040 | 304473.25 | 2nd Tranche | 184217 | 488690.25 | 304473.25 | 184217 | 100% | 100% | 126.1% | 100.4% | 100% | 2007-02-22 | 2007-04-26 | 2007-08-01 | 2008-01-14 | no data | 166 | 105 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Mahawan | 083726009 | Const. Of School Building 2 Rm | 1 | 1155100 | 808584 | 346516 | 808584 | 2nd Tranche | 409254.1 | 1217838.1 | 808584 | 409254.1 | 100% | 100% | 118.1% | 105.4% | 100% | no data | no data | 2008-11-18 | 2009-02-18 | n/a | 92 | 134 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Masarayao | 083726010 | Const. Of 1 Unit 2 CL School Building | 1 | 1115100 | 780569 | 334531 | 780510 | 3rd Tranche | 348607 | 1129117 | 780510 | 348607 | 100% | 100% | 104.2% | 101.3% | 100% | no data | no data | 2008-07-25 | 2008-09-23 | n/a | 60 | 530 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Masarayao | 083726010 | Construction of Health Station | 1 | 745000 | 521500 | 223500 | 469350 | 1st Tranche | 260168.79 | 729518.79 | 469350 | 260168.79 | 100% | 100% | 116.4% | 97.92% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-16 | 2009-06-12 | no data | 57 | 530 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Monte Alegre | 083726011 | Road Concreting on Critical Slopes | 1 | 883000 | 584061 | 298939 | 577061 | 2nd Tranche | 562855 | 1139916 | 577061 | 562855 | 100% | 100% | 188.3% | 129.1% | 100% | no data | no data | 2008-11-03 | 2009-01-05 | n/a | 63 | 535 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Monte Alegre | 083726011 | Construction of brgy. Health Station | 1 | 745000 | 521500 | 223500 | 469350 | 1st Tranche | 223500.19 | 692850.19 | 469350 | 223500.19 | 100% | 100% | 100% | 93% | 100% | 2008-12-16 | 2009-01-30 | 2009-05-25 | 2009-06-06 | no data | 12 | 535 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Monte Bello | 083726012 | Road Concreting | 1 | 550000 | 385000 | 165000 | 379065.09 | 1st Tranche | 166000 | 545065.09 | 379065.09 | 166000 | 100% | 100% | 100.6% | 99.1% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-27 | 2009-06-27 | no data | 61 | 442 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Naghalin | 083726013 | Flood Control | 1 | 900000 | 630000 | 270000 | 624426.18 | 1st Tranche | 270000 | 894426.18 | 624426.18 | 270000 | 100% | 100% | 100% | 99.38% | 100% | 2008-12-16 | 2009-01-30 | 2009-05-19 | 2009-07-31 | no data | 73 | 653 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Natubgan | 083726014 | Construction of Health Station | 1 | 750607 | 527424 | 223183 | 527105.6 | 2nd Tranche | 230799.76 | 757905.36 | 527105.6 | 230799.76 | 100% | 100% | 103.4% | 101% | 100% | no data | no data | 2008-07-25 | 2008-11-25 | n/a | 123 | 537 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Poblacion | 083726015 | Construction of Day Care Center | 1 | 720420 | 504294 | 216126 | 453864.6 | 1st Tranche | 232142 | 686006.6 | 453864.6 | 232142 | 100% | 100% | 107.4% | 95.22% | 100% | 2008-12-16 | 2009-01-30 | 2009-03-26 | 2009-05-09 | no data | 44 | 1542 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Rizal | 083726016 | Constn. of Water System (L 2) | 1 | 1197500 | 649709 | 547791 | 584738.1 | 2nd Tranche | 573331 | 1158069.1 | 584738.1 | 573331 | 100% | 100% | 104.7% | 96.71% | 100% | 2007-02-22 | 2007-04-26 | 2007-08-17 | 2008-08-31 | no data | 380 | 792 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | San Ignacio | 083726017 | Road Concreting with RCBC | 1 | 1107000 | 774900 | 332100 | 711594.85 | 3rd Tranche | 332100 | 1043694.85 | 711594.85 | 332100 | 100% | 100% | 100% | 94.28% | 100% | 2007-02-22 | 2007-04-26 | 2008-03-29 | 2008-06-19 | n/a | 82 | 83 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | San Isidro | 083726018 | Construction of Hanging Bridge | 1 | 768800 | 538160 | 230640 | 484344 | 2nd Tranche | 230740 | 715084 | 484344 | 230740 | 100% | 100% | 100% | 93.01% | 100% | 2007-02-22 | 2007-04-26 | 2008-02-04 | 2008-04-05 | n/a | 61 | 195 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | San Isidro | 083726018 | Road Concreting | 1 | 900000 | 525820 | 374180 | 525820 | 1st Tranche | 279030.99 | 804850.99 | 525820 | 279030.99 | 100% | 100% | 74.57% | 89.43% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-27 | 2009-08-28 | n/a | 123 | 237 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Sto. Domingo | 083726019 | Road Concreting on Critical Slopes | 1 | 1197087 | 837961 | 359126 | 754164 | 2nd Tranche | 359126 | 1113290 | 754164 | 359126 | 100% | 100% | 100% | 93% | 100% | 2007-02-22 | 2007-04-26 | 2007-10-31 | 2008-10-31 | n/a | 366 | 109 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Sto. Domingo | 083726019 | Road Concreting | 1 | 1350000 | 945000 | 405000 | 850500 | 1st Tranche | 433745.75 | 1284245.75 | 850500 | 433745.75 | 100% | 100% | 107.1% | 95.13% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-27 | 2009-06-20 | no data | 54 | 109 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Sto. Niño | 083726020 | Construction of Hanging Bridge | 1 | 1262500 | 883750 | 378750 | 795375 | 2nd Tranche | 378850 | 1174225 | 795375 | 378850 | 100% | 100% | 100% | 93.01% | 100% | 2007-02-22 | 2007-04-26 | 2008-04-25 | 2008-10-15 | n/a | 173 | 284 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tagaytay | 083726021 | Constn. of Water System (L 2) | 1 | 1351800 | 946260 | 405540 | 819474 | 2nd Tranche | 440792 | 1260266 | 819474 | 440792 | 100% | 100% | 108.7% | 93.23% | 100% | 2007-02-22 | 2007-04-26 | 2007-11-25 | 2008-06-25 | n/a | 213 | 388 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tagaytay | 083726021 | Construction of Steel Footbridge | 1 | 505762 | 352789 | 152973 | 352789 | 3rd Tranche | 157992 | 510781 | 352789 | 157992 | 100% | 100% | 103.3% | 101% | 100% | no data | no data | 2008-10-15 | 2008-11-30 | n/a | 46 | 483 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tagaytay | 083726021 | Construction of Health Station | 1 | 751175 | 525820 | 225355 | 473238 | 1st Tranche | 263636.99 | 736874.99 | 473238 | 263636.99 | 100% | 100% | 117% | 98.1% | 100% | 2008-12-16 | 2009-01-30 | 2009-04-20 | 2009-06-20 | no data | 61 | 483 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tongonan | 083726022 | Construction of Day Care Center | 1 | 720150 | 162410 | 557740 | 113687 | 1st Tranche | 574122 | 687809 | 113687 | 574122 | 100% | 100% | 102.9% | 95.51% | 100% | no data | no data | 2009-02-16 | 2009-04-15 | n/a | 58 | 185 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tongonan | 083726022 | Construction of Health Station | 1 | 756825 | 529778 | 227047 | 476800.2 | 1st Tranche | 259520 | 736320.2 | 476800.2 | 259520 | 100% | 100% | 114.3% | 97.29% | 100% | 2008-12-16 | 2009-01-30 | 2009-03-25 | 2009-06-01 | no data | 68 | 185 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tugbong | 083726023 | Road Opening | 1 | 1085000 | 655672 | 429328 | 637916 | 1st Tranche | 529327.4 | 1167243.4 | 637916 | 529327.4 | 100% | 100% | 123.3% | 107.6% | 100% | no data | no data | 2009-04-27 | 2009-06-13 | n/a | 47 | 535 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Bagacay East | 083728001 | Water System Level 1 | 1 | 268933 | 188253 | 80680 | 150602.48 | 1st Tranche | 82286.66 | 232889.14 | 150602.48 | 82286.66 | 100% | 100% | 102% | 86.6% | 100% | no data | no data | 2008-11-17 | 2008-11-30 | n/a | 13 | 95 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Bagacay West | 083728002 | Road Improvement | 1 | 867460 | 607222 | 260238 | 505895.35 | 2nd Tranche | 283508.15 | 789403.5 | 505895.35 | 283508.15 | 100% | 100% | 108.9% | 91% | 100% | 2007-02-26 | 2007-04-27 | 2007-10-08 | 2007-12-12 | no data | 65 | 36 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Bagacay West | 083728002 | Pathway | 1 | 392490 | 274743 | 117747 | 247268.7 | 2nd Tranche | 111670 | 358938.7 | 247268.7 | 111670 | 100% | 100% | 94.84% | 91.45% | 100% | no data | no data | 2008-08-18 | 2008-11-02 | n/a | 76 | 36 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Bocawon | 083728004 | Road Improvement | 1 | 400158 | 280110.6 | 120047.4 | 224088.48 | 1st Tranche | 127877.8 | 351966.28 | 224088.48 | 127877.8 | 100% | 100% | 106.5% | 87.96% | 100% | 2007-02-26 | 2007-04-27 | 2007-09-26 | 2008-02-14 | no data | 141 | 30 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Bongtod | 083728003 | Box Culvert | 1 | 764077 | 534853.9 | 229223.1 | 534853.9 | 3rd Tranche | 296932.59 | 831786.49 | 534853.9 | 296932.59 | 100% | 100% | 129.5% | 108.9% | 100% | 2007-02-26 | 2007-04-27 | 2007-08-17 | 2007-10-17 | n/a | 61 | 78 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Bongtod | 083728003 | Construction of 1 Unit Bgy Health Station | 1 | 715265 | 500686 | 214579 | 450617.35 | 2nd Tranche | 111121.33 | 561738.68 | 450617.35 | 111121.33 | 100% | 100% | 51.79% | 78.54% | 100% | no data | no data | 2008-12-09 | 2009-03-31 | no data | 112 | 78 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Buracan | 083728005 | Construction of Drainage System | 1 | 997851 | 698496 | 299355 | 628646.4 | 2nd Tranche | 309588.1 | 938234.5 | 628646.4 | 309588.1 | 100% | 100% | 103.4% | 94.03% | 100% | no data | no data | 2008-08-11 | 2008-11-18 | n/a | 99 | 122 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Caabangan | 083728006 | Road Improvement | 1 | 476901 | 333830 | 143071 | 267064.56 | 1st Tranche | 151600.06 | 418664.62 | 267064.56 | 151600.06 | 100% | 100% | 106% | 87.79% | 100% | 2007-02-26 | 2007-04-27 | 2007-09-10 | 2008-03-31 | no data | 203 | 39 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Cacao | 083728007 | Water System Level 1 | 1 | 248754 | 174129 | 74625 | 139303.2 | 1st Tranche | 48875 | 188178.2 | 139303.2 | 48875 | 100% | 100% | 65.49% | 75.65% | 100% | no data | no data | 2008-11-18 | 2008-11-30 | n/a | 12 | 54 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Cagngaran | 083728008 | Road Improvement | 1 | 434827 | 304378.9 | 130448.1 | 243503.12 | 1st Tranche | 96664.7 | 340167.82 | 243503.12 | 96664.7 | 100% | 100% | 74.1% | 78.23% | 100% | 2007-02-26 | 2007-04-27 | 2007-08-16 | 2008-03-31 | no data | 228 | 51 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Calabnian | 083728009 | Flood Control | 1 | 692066 | 484446.2 | 207619.8 | 387556.96 | 1st Tranche | 280876.48 | 668433.44 | 387556.96 | 280876.48 | 100% | 100% | 135.3% | 96.59% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-17 | 2007-09-27 | no data | 72 | 43 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Calaghusan | 083728010 | Box Culvert | 1 | 378328 | 264829.6 | 113498.4 | 238346.64 | 3rd Tranche | 113002.53 | 351349.17 | 238346.64 | 113002.53 | 100% | 100% | 99.56% | 92.87% | 100% | 2007-02-26 | 2007-04-27 | 2007-10-08 | 2008-11-26 | n/a | 415 | 76 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Caltayan | 083728011 | Road Improvement | 1 | 391396 | 273977.2 | 117418.8 | 219181.76 | 1st Tranche | 91324 | 310505.76 | 219181.76 | 91324 | 100% | 100% | 77.78% | 79.33% | 100% | 2007-02-26 | 2007-04-27 | 2007-09-17 | 2008-03-30 | no data | 195 | 90 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Canbañes | 083728012 | Water System Level 1 | 1 | 435263 | 304684 | 130579 | 243747.2 | 1st Tranche | 69096.33 | 312843.53 | 243747.2 | 69096.33 | 100% | 100% | 52.92% | 71.87% | 100% | no data | no data | 2009-01-05 | 2009-02-28 | n/a | 54 | 66 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Cogon | 083728013 | Construction of a Level 2 Type Gravity Fed Water System | 1 | 682742 | 477919 | 204823 | 430127.14 | 1st Tranche | 232124.99 | 662252.13 | 430127.14 | 232124.99 | 100% | 100% | 113.3% | 97% | 100% | no data | no data | 2009-01-26 | 2009-08-28 | n/a | 214 | 59 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | District 1 | 083728025 | Drainage System | 1 | 457840 | 320488 | 137352 | 288439.2 | 2nd Tranche | 127623.88 | 416063.08 | 288439.2 | 127623.88 | 100% | 100% | 92.92% | 90.88% | 100% | no data | no data | 2008-11-13 | 2008-12-29 | n/a | 46 | 147 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | District 2 | 083728026 | Construction of Flood protection | 1 | 620518 | 434363 | 186155 | 414933 | 2nd Tranche | 198283.27 | 613216.27 | 414933 | 198283.27 | 100% | 100% | 106.5% | 98.82% | 100% | no data | no data | 2008-07-31 | 2009-08-28 | n/a | 393 | 153 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | District 3 | 083728027 | Drainage System | 1 | 500845 | 350591.5 | 150253.5 | 334659.79 | 1st Tranche | 199445.01 | 534104.8 | 334659.79 | 199445.01 | 100% | 100% | 132.7% | 106.6% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-23 | 2007-10-01 | no data | 70 | 259 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | District 4 | 083728028 | Drainage System | 1 | 1065045 | 745531 | 319514 | 596424.8 | 1st Tranche | 287603.67 | 884028.47 | 596424.8 | 287603.67 | 100% | 100% | 90.01% | 83% | 100% | no data | no data | 2009-01-26 | 2009-05-30 | no data | 124 | 206 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Duyog | 083728014 | Water System | 1 | 1026167 | 718316.9 | 307850.1 | 677339.6 | 2nd Tranche | 439625.4 | 1116965 | 677339.6 | 439625.4 | 100% | 100% | 142.8% | 108.8% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-23 | 2007-10-04 | no data | 73 | 173 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Duyog | 083728014 | Drainage System | 1 | 583803 | 408662 | 175141 | 367795.8 | 2nd Tranche | 185823.96 | 553619.76 | 367795.8 | 185823.96 | 100% | 100% | 106.1% | 94.83% | 100% | no data | no data | 2008-08-05 | 2008-11-25 | n/a | 112 | 173 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Gimenarat East | 083728015 | Construction of Box Culvert | 1 | 388141 | 271698 | 116443 | 256468.8 | 2nd Tranche | 115443.7 | 371912.5 | 256468.8 | 115443.7 | 100% | 100% | 99.14% | 95.82% | 100% | no data | no data | 2008-11-25 | 2009-07-30 | n/a | 247 | 85 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Gimenarat West | 083728016 | Const. of Level 2 Type Gravity Fed Water System | 1 | 1170298 | 819209 | 351089 | 655367.2 | 1st Tranche | 358598.01 | 1013965.21 | 655367.2 | 358598.01 | 100% | 100% | 102.1% | 86.64% | 100% | no data | no data | 2009-01-26 | 2009-08-28 | n/a | 214 | 72 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Limba | 083728017 | Flood protection | 1 | 767928 | 544150 | 223778 | 489735 | 2nd Tranche | 269702.34 | 759437.34 | 489735 | 269702.34 | 100% | 100% | 120.5% | 98.89% | 100% | no data | no data | 2008-08-01 | 2008-11-30 | n/a | 121 | 127 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Lubi-lubi | 083728018 | Road Improvement | 1 | 507833 | 355483.1 | 152349.9 | 284386.48 | 1st Tranche | 113685.3 | 398071.78 | 284386.48 | 113685.3 | 100% | 100% | 74.62% | 78.39% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-18 | 2007-09-29 | no data | 73 | 90 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Luneta | 083728019 | Road Improvement | 1 | 883315 | 498664.4 | 384650.6 | 398931.52 | 1st Tranche | 296073.91 | 695005.43 | 398931.52 | 296073.91 | 100% | 100% | 76.97% | 78.68% | 100% | 2007-02-26 | 2007-04-27 | 2007-09-23 | 2009-08-28 | n/a | 705 | 251 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Luneta | 083728019 | Drainage System | 1 | 926118 | 648283 | 277835 | 583454.7 | 2nd Tranche | 372824.84 | 956279.54 | 583454.7 | 372824.84 | 100% | 100% | 134.2% | 103.3% | 100% | no data | no data | 2008-08-18 | 2008-11-30 | n/a | 104 | 251 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Mag-aso | 083728020 | Water System | 1 | 867304 | 607112.8 | 260191.2 | 485690.24 | 1st Tranche | 282970.4 | 768660.64 | 485690.24 | 282970.4 | 100% | 100% | 108.8% | 88.63% | 100% | 2007-02-26 | 2007-04-27 | 2007-08-10 | 2007-10-27 | no data | 78 | 109 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Moroboro | 083728021 | Box Culvert | 1 | 968698 | 678088.6 | 290609.4 | 610274.57 | 2nd Tranche | 228527.04 | 838801.61 | 610274.57 | 228527.04 | 100% | 100% | 78.64% | 86.59% | 100% | 2007-02-26 | 2007-04-27 | 2007-10-01 | 2009-04-23 | n/a | 570 | 46 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Moroboro | 083728021 | Construction of Spillway Bridge | 1 | 1248558 | 873991 | 374567 | 699192.8 | 2nd Tranche | 310182.86 | 1009375.66 | 699192.8 | 310182.86 | 100% | 100% | 82.81% | 80.84% | 100% | no data | no data | 2009-02-02 | 2009-04-30 | n/a | 87 | 46 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Pansud | 083728022 | Road Improvement | 1 | 989455 | 692618.5 | 296836.5 | 521903.82 | 1st Tranche | 249161.02 | 771064.84 | 521903.82 | 249161.02 | 100% | 100% | 83.94% | 77.93% | 100% | 2007-02-26 | 2007-04-27 | 2008-05-02 | 2008-11-25 | n/a | 207 | 74 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Pawa | 083728023 | Drainage System | 1 | 953344 | 667340.8 | 286003.2 | 657491.72 | 3rd Tranche | 335802.8 | 993294.52 | 657491.72 | 335802.8 | 100% | 100% | 117.4% | 104.2% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-31 | 2008-02-21 | no data | 205 | 87 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Piliway | 083728024 | Construction of Drainage System | 1 | 926118 | 648283 | 277835 | 583454.7 | 2nd Tranche | 267983.34 | 851438.04 | 583454.7 | 267983.34 | 100% | 100% | 96.45% | 91.94% | 100% | no data | no data | 2008-08-08 | 2008-11-30 | n/a | 114 | 71 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Quiong | 083728029 | Road Improvement | 1 | 865618 | 605932.6 | 259685.4 | 575941.1 | 3rd Tranche | 250278.26 | 826219.36 | 575941.1 | 250278.26 | 100% | 100% | 96.38% | 95.45% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-23 | 2007-09-23 | no data | 62 | 61 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Rizal | 083728030 | Flood Control | 1 | 348780 | 244394 | 104386 | 195515.2 | 1st Tranche | 113816.02 | 309331.22 | 195515.2 | 113816.02 | 100% | 100% | 109% | 88.69% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-31 | 2007-09-28 | no data | 59 | 89 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Rizal | 083728030 | Drainage System | 1 | 721706.5 | 505195 | 216511.5 | 404155.92 | 1st Tranche | 217341.5 | 621497.42 | 404155.92 | 217341.5 | 100% | 100% | 100.4% | 86.11% | 100% | 2008-02-27 | 2008-05-12 | 2009-08-03 | 2009-08-31 | n/a | 28 | 89 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | San Victoray | 083728031 | Skills Training on Abaca Processing | 1 | 102500 | 71750 | 30750 | 57400 | 1st Tranche | 32640 | 90040 | 57400 | 32640 | 100% | 100% | 106.1% | 87.84% | 100% | 2007-02-26 | 2007-04-27 | 2008-01-05 | 2008-04-30 | n/a | 116 | 57 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | San Victoray | 083728031 | Flood control | 1 | 1197786 | 838450 | 359336 | 670760 | 1st Tranche | 181678.67 | 852438.67 | 670760 | 181678.67 | 100% | 100% | 50.56% | 71.17% | 100% | no data | no data | 2009-03-16 | 2009-08-31 | n/a | 168 | 57 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Sta. Ana | 083728032 | Drainage System | 1 | 679716 | 475801.2 | 203914.8 | 380640.96 | 1st Tranche | 192424.88 | 573065.84 | 380640.96 | 192424.88 | 100% | 100% | 94.37% | 84.31% | 100% | 2007-02-26 | 2007-04-27 | 2007-08-28 | 2007-09-26 | no data | 29 | 217 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Sta. Ana | 083728032 | Construction of 1 Unit Bgy Health Station | 1 | 715265 | 500686 | 214579 | 450617.14 | 2nd Tranche | 231700.66 | 682317.8 | 450617.14 | 231700.66 | 100% | 100% | 108% | 95.39% | 100% | no data | no data | 2008-11-05 | 2009-01-30 | n/a | 86 | 217 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Sta. Elena | 083728033 | Daycare Center | 1 | 495192 | 346634.4 | 148557.6 | 337811.53 | 3rd Tranche | 200565.15 | 538376.68 | 337811.53 | 200565.15 | 100% | 100% | 135% | 108.7% | 100% | 2007-02-26 | 2007-04-27 | 2007-07-23 | 2007-10-01 | no data | 70 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Sta. Elena | 083728033 | Water System 1 | 1 | 721705.8 | 322101 | 399604.8 | 257680.8 | 1st Tranche | 346298 | 603978.8 | 257680.8 | 346298 | 100% | 100% | 86.66% | 83.69% | 100% | no data | no data | 2009-08-07 | 2009-08-31 | n/a | 24 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Tabang | 083728034 | Road Improvement | 1 | 950113 | 665079.1 | 285033.9 | 532063.28 | 1st Tranche | 263838.94 | 795902.22 | 532063.28 | 263838.94 | 100% | 100% | 92.56% | 83.77% | 100% | 2007-02-26 | 2007-04-27 | 2007-12-20 | 2008-04-30 | n/a | 132 | 32 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Lapaz | 083728 | Tarugan | 083728034 | Road Improvement | 1 | 626491 | 438543.7 | 187947.3 | 350834.96 | 1st Tranche | 133129.12 | 483964.08 | 350834.96 | 133129.12 | 100% | 100% | 70.83% | 77.25% | 100% | 2007-02-26 | 2007-04-27 | 2007-10-08 | 2008-12-27 | n/a | 446 | 77 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Bachao | 083729001 | Construction of Seawall | 1 | 1343705 | 940601 | 403104 | 940601 | 3rd Tranche | 433896.5 | 1374497.5 | 940601 | 433896.5 | 100% | 100% | 107.6% | 102.3% | 100% | 2005-04-15 | 2005-06-08 | 2005-09-26 | 2006-04-25 | 2006-06-21 | 211 | 201 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Bachao | 083729001 | Construction of Level 2 Gravity Fed Water System | 1 | 1333885 | 933720 | 400165 | 840348 | 2nd Tranche | 409502.5 | 1249850.5 | 840348 | 409502.5 | 100% | 100% | 102.3% | 93.7% | 100% | 2007-03-28 | 2007-06-06 | 2008-02-23 | 2008-05-31 | n/a | 98 | 201 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Baco | 083729002 | Construction of Level 2 Type Pump Water System | 1 | 1271271 | 889890 | 381381 | 889890 | 3rd Tranche | 484663.5 | 1374553.5 | 889890 | 484663.5 | 100% | 100% | 127.1% | 108.1% | 100% | 2006-07-21 | 2006-07-23 | 2006-12-11 | 2007-07-31 | no data | 232 | 152 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Bagaba-o | 083729003 | Construction of Rice Mill w/ Structure | 1 | 900900 | 630630 | 270270 | 630630 | 3rd Tranche | 297557.5 | 928187.5 | 630630 | 297557.5 | 100% | 100% | 110.1% | 103% | 100% | 2006-07-21 | 2006-07-23 | 2007-01-29 | 2007-07-31 | no data | 183 | 143 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Basud | 083729004 | Road Concreting | 1 | 366380 | 256466 | 109914 | 256466 | 3rd Tranche | 110864 | 367330 | 256466 | 110864 | 100% | 100% | 100.9% | 100.3% | 100% | 2005-04-15 | 2005-06-08 | 2005-10-03 | 2006-04-30 | 2006-06-21 | 209 | 44 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Belen | 083729005 | Construction of 1 unit 3 classroom school building | 1 | 1392382 | 974667 | 417715 | 974667 | 3rd Tranche | 424365 | 1399032 | 974667 | 424365 | 100% | 100% | 101.6% | 100.5% | 100% | 2006-07-21 | 2006-07-23 | 2006-11-20 | 2007-05-25 | no data | 186 | 306 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Burabod | 083729006 | Construction of Seawall | 1 | 1780721 | 1246504 | 534217 | 1246504 | 3rd Tranche | 583965.75 | 1830469.75 | 1246504 | 583965.75 | 100% | 100% | 109.3% | 102.8% | 100% | 2006-07-21 | 2006-07-23 | 2006-11-21 | 2007-04-02 | no data | 132 | 154 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Calaguise | 083729007 | Road Opening and Surfacing | 1 | 1986623 | 1390636 | 595987 | 1233572.4 | 2nd Tranche | 118162.71 | 1351735.11 | 1233572.4 | 118162.71 | 100% | 100% | 19.83% | 68.04% | 100% | 2007-03-28 | 2007-06-06 | 2008-06-12 | 2009-09-30 | n/a | 475 | 225 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Culasi | 083729009 | Road Concreting | 1 | 1630149 | 1143180 | 486969 | 1143180 | 3rd Tranche | 383460.5 | 1526640.5 | 1143180 | 383460.5 | 100% | 100% | 78.74% | 93.65% | 100% | 2005-04-15 | 2005-06-08 | 2005-09-12 | 2006-05-31 | 2006-06-22 | 261 | 176 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Culasi | 083729009 | Construction of Seawall | 1 | 1026561 | 718592 | 307969 | 718592 | 3rd Tranche | 287219 | 1005811 | 718592 | 287219 | 100% | 100% | 93.26% | 97.98% | 100% | 2007-03-28 | 2007-06-06 | 2007-11-14 | 2008-04-30 | n/a | 168 | 176 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Danus | 083729010 | Street Concreting | 1 | 524535 | 367175 | 157360 | 367175 | 3rd Tranche | 171035.75 | 538210.75 | 367175 | 171035.75 | 100% | 100% | 108.7% | 102.6% | 100% | 2005-04-15 | 2005-06-08 | 2005-08-09 | 2005-12-23 | 2006-06-20 | 136 | 150 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Elizabeth | 083729011 | Installation of Small Scale Irrigation | 1 | 605200 | 423640 | 181560 | 423640 | 3rd Tranche | 201340.1 | 624980.1 | 423640 | 201340.1 | 100% | 100% | 110.9% | 103.3% | 100% | 2005-04-15 | 2005-06-08 | 2005-08-29 | 2006-04-30 | 2006-06-23 | 244 | 83 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Elizabeth | 083729011 | Construction of Level 2 type Gravity Fed Water System | 1 | 668469 | 467928 | 200541 | 420635.2 | 2nd Trache | 200545 | 621180.2 | 420635.2 | 200545 | 100% | 100% | 100% | 92.93% | 100% | 2006-07-21 | 2006-07-23 | 2006-12-20 | 2007-06-20 | no data | 182 | 83 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Kawayan | 083729012 | Construction of Seawall | 1 | 1370154 | 959108 | 411046 | 959108 | 3rd Tranche | 429471 | 1388579 | 959108 | 429471 | 100% | 100% | 104.5% | 101.3% | 100% | 2007-03-28 | 2007-06-06 | 2008-01-03 | 2008-04-30 | n/a | 118 | 210 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Libas | 083729013 | Construction of Bridge | 1 | 414159 | 291111 | 123048 | 291111 | 3rd Tranche | 169620.5 | 460731.5 | 291111 | 169620.5 | 100% | 100% | 137.8% | 111.2% | 100% | 2005-04-15 | 2005-06-08 | 2005-08-11 | 2006-04-30 | 2006-06-20 | 262 | 270 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Maanda | 083729014 | Construction of Seawall | 1 | 1086150 | 760285 | 325865 | 760285 | 3rd Tranche | 333392 | 1093677 | 760285 | 333392 | 100% | 100% | 102.3% | 100.7% | 100% | 2005-04-15 | 2005-06-08 | 2005-08-15 | 2006-04-25 | 2006-06-22 | 253 | 86 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Macupa | 083729015 | Construction of Level 2 Gravity Fed Water System | 1 | 1489251 | 799034 | 690217 | 719130.6 | 1st Tranche | 686213 | 1405343.6 | 719130.6 | 686213 | 100% | 100% | 99.42% | 94.37% | 100% | 2007-03-28 | 2007-06-06 | 2008-01-05 | 2009-09-30 | n/a | 634 | 416 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Mataloto | 083729016 | School Building | 1 | 647819 | 453473 | 194346 | 408125.7 | 2nd Tranche | 182546 | 590671.7 | 408125.7 | 182546 | 100% | 100% | 93.93% | 91.18% | 100% | 2005-04-15 | 2005-06-08 | 2006-03-29 | 2006-11-08 | no data | 224 | 99 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Palarao | 083729017 | Construction of Level 2 type Gravity Fed Water System | 1 | 1284211 | 698163 | 586048 | 698163 | 3rd Tranche | 603725.5 | 1301888.5 | 698163 | 603725.5 | 100% | 100% | 103% | 101.4% | 100% | 2006-07-21 | 2006-07-23 | 2006-12-12 | 2007-03-12 | no data | 90 | 443 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Palid 1 | 083729018 | Construction of 1 unit 3 classroom school building | 1 | 1479900 | 1035930 | 443970 | 1035930 | 3rd Tranche | 483714 | 1519644 | 1035930 | 483714 | 100% | 100% | 109% | 102.7% | 100% | 2007-03-28 | 2007-06-06 | 2008-01-26 | 2008-05-31 | n/a | 126 | 180 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Parasan | 083729020 | Construction of Footbridge | 1 | 1242074 | 869451 | 372623 | 782505.9 | 2nd Tranche | 355321 | 1137826.9 | 782505.9 | 355321 | 100% | 100% | 95.36% | 91.61% | 100% | 2007-03-28 | 2007-06-06 | 2008-03-26 | 2008-10-11 | n/a | 199 | 117 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Poblacion | 083729021 | Improvement of Water System L2 | 1 | 1949383 | 1364568 | 584815 | 1364568 | 3rd Tranche | 587968.2 | 1952536.2 | 1364568 | 587968.2 | 100% | 100% | 100.5% | 100.2% | 100% | 2005-04-15 | 2005-06-08 | 2006-02-06 | 2006-05-31 | 2006-06-20 | 114 | 824 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Poblacion | 083729021 | Constructionof Flood Control Structure | 1 | 2368810 | 1658167 | 710643 | 1658167 | 3rd Tranche | 750447.44 | 2408614.44 | 1658167 | 750447.44 | 100% | 100% | 105.6% | 101.7% | 100% | 2006-07-21 | 2006-07-23 | 2007-01-16 | 2007-07-31 | no data | 196 | 771 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Sambulawan | 083729023 | Construction of Water System L2 | 1 | 679831 | 475881 | 203950 | 475881 | 3rd Tranche | 212587.5 | 688468.5 | 475881 | 212587.5 | 100% | 100% | 104.2% | 101.3% | 100% | 2005-04-15 | 2005-06-08 | 2005-08-23 | 2006-04-30 | 2006-06-20 | 250 | 164 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Tapol | 083729025 | Road Concreting | 1 | 641357 | 448950 | 192407 | 448950 | 3rd Tranche | 213007 | 661957 | 448950 | 213007 | 100% | 100% | 110.7% | 103.2% | 100% | 2005-04-15 | 2005-06-08 | 2005-11-08 | 2006-05-31 | 2006-06-23 | 204 | 129 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Tigbawan | 083729026 | Construction of Water System L2 | 1 | 1130763 | 811099 | 319664 | 811099 | 3rd Tranche | 392214 | 1203313 | 811099 | 392214 | 100% | 100% | 122.7% | 106.4% | 100% | 2005-04-15 | 2005-06-08 | 2005-09-25 | 2006-05-26 | 2006-08-03 | 243 | 426 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Tigbawan | 083729026 | Construction of 1 Unit 3 Classroom School Building | 1 | 1510056 | 1057039 | 453017 | 1057039 | 3rd Tranche | 506719.5 | 1563758.5 | 1057039 | 506719.5 | 100% | 100% | 111.9% | 103.6% | 100% | 2006-07-21 | 2006-07-23 | 2006-11-28 | 2007-07-31 | no data | 245 | 258 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Tinocdugan | 083729027 | Construction of Level 2 Gravity Fed Water System | 1 | 1617910 | 1132537 | 485373 | 906029.6 | 1st Tranche | 269486.5 | 1175516.1 | 906029.6 | 269486.5 | 100% | 100% | 55.52% | 72.66% | 100% | 2007-03-28 | 2007-06-06 | 2009-05-27 | 2009-09-30 | n/a | 126 | 114 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Toctoc | 083729028 | Construction and Gravelling of Pathways | 1 | 1331200 | 931840 | 399360 | 931840 | 3rd Tranche | 399038.94 | 1330878.94 | 931840 | 399038.94 | 100% | 100% | 99.92% | 99.98% | 100% | 2006-07-21 | 2006-07-23 | 2007-01-22 | 2007-08-16 | n/a | 206 | 224 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Ugbon | 083729029 | School Building | 1 | 606319 | 424423 | 181896 | 424423 | 3rd Tranche | 233458.5 | 657881.5 | 424423 | 233458.5 | 100% | 100% | 128.3% | 108.5% | 100% | 2005-04-15 | 2005-06-08 | 2005-09-27 | 2006-04-30 | 2006-06-22 | 215 | 178 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Ugbon | 083729029 | Construction of Level 2 Gravity Fed Water System | 1 | 1540323 | 1078226 | 462097 | 970403.4 | 1st Tranche | 194448.5 | 1164851.9 | 970403.4 | 194448.5 | 100% | 100% | 42.08% | 75.62% | 100% | 2007-03-28 | 2007-06-06 | 2009-04-06 | 2009-09-30 | n/a | 177 | 167 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Wague | 083729030 | School Building | 1 | 1196641 | 839148 | 357493 | 839148 | 3rd Tranche | 360500.5 | 1199648.5 | 839148 | 360500.5 | 100% | 100% | 100.8% | 100.3% | 100% | 2005-04-15 | 2005-06-08 | 2006-03-16 | 2006-05-31 | 2006-08-01 | 76 | 178 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Wague | 083729030 | Rehabilitation and Improvement of Brgy. Road | 1 | 1142972 | 445172 | 697800 | 445172 | 3rd Tranche | 594659 | 1039831 | 445172 | 594659 | 100% | 100% | 85.22% | 90.98% | 100% | 2006-07-21 | 2006-07-23 | 2007-01-22 | 2008-10-31 | n/a | 648 | 178 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Campin | 083731001 | Construction of Water System (L2) | 1 | 738703.82 | 450460 | 288243.82 | 450460 | 3rd Tranche | 315923.82 | 766383.82 | 450460 | 315923.82 | 100% | 100% | 109.6% | 103.7% | 100% | 2007-02-27 | 2007-04-25 | 2007-11-25 | 2008-10-30 | n/a | 340 | 297 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Campin | 083731001 | Construction of Health Station | 1 | 766356 | 570719.54 | 195636.46 | 570719.53 | 1st Tranche | 221756.02 | 792475.55 | 570719.53 | 221756.02 | 100% | 100% | 113.4% | 103.4% | 100% | 2008-11-18 | 2009-02-13 | 2009-05-18 | 2009-05-31 | no data | 13 | 800 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Cuatro de Agosto | 083731002 | Improvement of Water System (L2) | 1 | 596893.57 | 385670 | 211223.57 | 373103.28 | 3rd Tranche | 225540.62 | 598643.9 | 373103.28 | 225540.62 | 100% | 100% | 106.8% | 100.3% | 100% | 2007-02-27 | 2007-04-25 | 2008-03-03 | 2008-10-30 | n/a | 241 | 164 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Cuatro de Agosto | 083731002 | Public Toilet | 1 | 304595 | 213597.25 | 90997.75 | 199901.37 | 1st Tranche | 98337.37 | 298238.74 | 199901.37 | 98337.37 | 100% | 100% | 108.1% | 97.91% | 100% | 2008-11-18 | 2009-02-13 | 2009-05-04 | 2009-05-31 | no data | 27 | 11 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Hiluctogan | 083731026 | Const. of Hanging Bridge | 1 | 3721727 | 2067712.7 | 1654014.3 | 1654170.16 | 1st Tranche | 1486432.71 | 3140602.87 | 1654170.16 | 1486432.71 | 100% | 100% | 89.87% | 84.39% | 100% | no data | no data | 2009-08-03 | 2009-09-30 | n/a | 58 | 109 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Hiluctogan | 083731026 | Construction of Water System (L2) | 1 | 607547.08 | 393960 | 213587.08 | 354564 | 2nd Tranche | 249803.99 | 604367.99 | 354564 | 249803.99 | 100% | 100% | 117% | 99.48% | 100% | 2007-02-27 | 2007-04-25 | 2008-02-05 | 2008-08-25 | no data | 202 | 109 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Hilusig | 083731003 | Const. of Level 2 Type Gravity Fed Water System | 1 | 1589756.1 | 1112829 | 476927.1 | 1112829 | 2nd Tranche | 465350.4 | 1578179.4 | 1112829 | 465350.4 | 100% | 100% | 97.57% | 99.27% | 100% | no data | no data | 2009-02-11 | 2009-04-30 | no data | 78 | 200 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Liberacion | 083731006 | Construction of Health Station | 1 | 679666.66 | 474750 | 204916.66 | 421661.66 | 2nd Tranche | 214916.63 | 636578.29 | 421661.66 | 214916.63 | 100% | 100% | 104.9% | 93.66% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-09 | 2007-12-18 | no data | 70 | 82 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mabuhay | 083731007 | Improvement of Water System (L2) | 1 | 629557.57 | 428880 | 200677.57 | 371262.08 | 2nd Tranche | 203887.27 | 575149.35 | 371262.08 | 203887.27 | 100% | 100% | 101.6% | 91.36% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-16 | 2008-03-19 | no data | 155 | 138 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mabunga | 083731008 | Box Culvert | 1 | 107944.07 | 60960 | 46984.07 | 48768 | 1st Tranche | 51397.41 | 100165.41 | 48768 | 51397.41 | 100% | 100% | 109.4% | 92.79% | 100% | 2007-02-27 | 2007-04-25 | 2007-11-15 | 2007-12-05 | no data | 20 | 89 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mabunga | 083731008 | Const. of Level 2 type Gravity Fed Water System | 1 | 809760 | 566832 | 242928 | 510148.8 | 2nd Tranche | 244847.2 | 754996 | 510148.8 | 244847.2 | 100% | 100% | 100.8% | 93.24% | 100% | no data | no data | 2008-10-28 | 2008-12-31 | n/a | 64 | 89 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mahayag | 083731010 | Construction of Footbridge | 1 | 133772 | 82460 | 51312 | 82460 | 2nd Tranche | 56472 | 138932 | 82460 | 56472 | 100% | 100% | 110.1% | 103.9% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-01 | 2007-11-08 | no data | 38 | 158 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mahayag | 083731010 | Pathways with Box Culvert and Riprap | 1 | 723460 | 526830 | 196630 | 526830 | 1st Tranche | 200004.4 | 726834.4 | 526830 | 200004.4 | 100% | 100% | 101.7% | 100.5% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-17 | 2009-05-31 | no data | 75 | 173 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mahayahay | 083731011 | Construction of Water System (L2) | 1 | 717587.03 | 485820 | 231767.03 | 485820 | 3rd Tranche | 236869.77 | 722689.77 | 485820 | 236869.77 | 100% | 100% | 102.2% | 100.7% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-01 | 2008-10-30 | n/a | 395 | 173 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mahayahay | 083731011 | Construction of Health Station | 1 | 777575 | 560486.13 | 217088.87 | 527001.05 | 1st Tranche | 220686.12 | 747687.17 | 527001.05 | 220686.12 | 100% | 100% | 101.7% | 96.16% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-17 | 2009-05-31 | no data | 75 | 115 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Maligaya | 083731027 | Const. of Farm to Market Road | 1 | 3608527 | 2525968.9 | 1082558.1 | 1262984.45 | 1st Tranche | 1052558.1 | 2315542.55 | 1262984.45 | 1052558.1 | 100% | 100% | 97.23% | 64.17% | 100% | no data | no data | 2009-03-11 | 2009-08-31 | n/a | 173 | 31 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Malinao | 083731012 | Construction of Solar Dryer | 1 | 350306.28 | 225010 | 125296.28 | 202509 | 2nd Tranche | 129420.65 | 331929.65 | 202509 | 129420.65 | 100% | 100% | 103.3% | 94.75% | 100% | 2007-02-27 | 2007-04-25 | 2008-01-05 | 2008-03-31 | n/a | 86 | 318 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Malinao | 083731012 | Const. of Drainage Canal | 1 | 801297 | 560907.9 | 240389.1 | 547817.11 | 3rd Tranche | 259123.1 | 806940.21 | 547817.11 | 259123.1 | 100% | 100% | 107.8% | 100.7% | 100% | no data | no data | 2008-08-15 | 2008-12-30 | n/a | 137 | 318 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Malinao | 083731012 | Construction of Schoolbuilding (2 Classroom) | 1 | 1126976 | 825097.84 | 301878.16 | 825097.83 | 3rd Tranche | 314512.37 | 1139610.2 | 825097.83 | 314512.37 | 100% | 100% | 104.2% | 101.1% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-16 | 2009-05-31 | no data | 76 | 318 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Malipoon | 083731013 | Construction of Water System (L2) | 1 | 380919.72 | 230690 | 150229.72 | 207620.66 | 2nd Tranche | 131516.36 | 339137.02 | 207620.66 | 131516.36 | 100% | 100% | 87.54% | 89.03% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-09 | 2008-05-26 | n/a | 230 | 37 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Palañogan | 083731014 | Construction of Drainage Canal | 1 | 987239 | 716216.66 | 271022.34 | 716200.03 | 2nd Tranche | 286016.34 | 1002216.37 | 716200.03 | 286016.34 | 100% | 100% | 105.5% | 101.5% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-18 | 2009-05-31 | no data | 74 | 191 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Palañogan | 083731014 | Improvement of Water System (L2) | 1 | 413613.63 | 166210 | 247403.63 | 132968 | 1st Tranche | 252291.79 | 385259.79 | 132968 | 252291.79 | 100% | 100% | 102% | 93.14% | 100% | 2007-02-27 | 2007-04-25 | 2008-04-04 | 2008-10-04 | n/a | 183 | 147 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Paril | 083731015 | Repair of School Building (2 Rm) | 1 | 564039.85 | 393030 | 171009.85 | 374067.9 | 3rd Tranche | 171009.85 | 545077.75 | 374067.9 | 171009.85 | 100% | 100% | 100% | 96.64% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-06 | 2008-06-11 | n/a | 249 | 74 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Paril | 083731015 | Construction of Health Center | 1 | 714477 | 527043 | 187434 | 525307.6 | 2nd Tranche | 187434 | 712741.6 | 525307.6 | 187434 | 100% | 100% | 100% | 99.76% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-16 | 2009-05-31 | no data | 76 | 83 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Pinamonoan | 083731016 | Improvement of Farm to Market Road | 1 | 533053.13 | 344290 | 188763.13 | 306914.38 | 2nd Tranche | 191012.37 | 497926.75 | 306914.38 | 191012.37 | 100% | 100% | 101.2% | 93.41% | 100% | 2007-02-27 | 2007-04-25 | 2008-02-05 | 2008-05-25 | n/a | 110 | 185 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Pinamonoan | 083731016 | Water Supply System(Level2) | 1 | 986769 | 715855.2 | 270913.8 | 715855.2 | 1st Tranche | 280164.3 | 996019.5 | 715855.2 | 280164.3 | 100% | 100% | 103.4% | 100.9% | 100% | 2008-11-18 | 2009-02-13 | 2009-04-04 | 2009-06-20 | no data | 77 | 150 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Poblacion | 083731017 | Construction of River Control | 1 | 463160.18 | 287370 | 175790.18 | 258633 | 2nd Tranche | 200536.4 | 459169.4 | 258633 | 200536.4 | 100% | 100% | 114.1% | 99.14% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-02 | 2007-11-03 | no data | 32 | 708 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Poblacion | 083731017 | Construction of Drainage Canal | 1 | 3304232 | 2426163.88 | 878068.12 | 2183547.49 | 1st Tranche | 822559.55 | 3006107.04 | 2183547.49 | 822559.55 | 100% | 100% | 93.68% | 90.98% | 100% | 2008-11-18 | 2009-02-13 | 2009-04-15 | 2009-08-31 | n/a | 138 | 327 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Polahongon | 083731018 | Construction of Water System (L2) | 1 | 479755.73 | 295430 | 184325.73 | 286387 | 3rd Tranche | 214984.06 | 501371.06 | 286387 | 214984.06 | 100% | 100% | 116.6% | 104.5% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-01 | 2008-08-30 | no data | 334 | 489 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Polahongon | 083731018 | Construction of Schoolbuilding (2 Classroom) | 1 | 1126976 | 824185.5 | 302790.5 | 824185.5 | 2nd Tranche | 323232.91 | 1127518.41 | 824185.5 | 303332.91 | 100% | 93.84% | 106.8% | 100% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-31 | 2009-06-19 | no data | 80 | 400 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | San Isidro | 083731019 | Const. of Level 2 Type Gravity Fed Water System | 1 | 599532 | 411065 | 188467 | 369958.5 | 1st Tranche | 165053 | 543235.55 | 369958.5 | 173277.05 | 100% | 105% | 87.58% | 90.61% | 100% | no data | no data | 2009-02-09 | 2009-05-31 | no data | 111 | 319 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Sto. Niño | 083731028 | Improvement of Farm to Market Road | 1 | 1329400 | 707830 | 621570 | 566264 | 1st Tranche | 594617 | 1160881 | 566264 | 594617 | 100% | 100% | 95.66% | 87.32% | 100% | 2007-02-27 | 2007-04-25 | 2007-09-05 | 2008-10-30 | n/a | 421 | 61 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Uguis | 083731023 | Construction of Water System (L2) | 1 | 669266.35 | 458950 | 210316.35 | 413055 | 2nd Tranche | 215698.97 | 628753.97 | 413055 | 215698.97 | 100% | 100% | 102.6% | 93.95% | 100% | 2007-02-27 | 2007-04-25 | 2008-01-28 | 2008-04-15 | n/a | 78 | 152 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Uguis | 083731023 | Const. of Standard Health Center | 1 | 663244 | 464270.8 | 198973.2 | 456843.72 | 3rd Tranche | 209487.7 | 666331.42 | 456843.72 | 209487.7 | 100% | 100% | 105.3% | 100.5% | 100% | no data | no data | 2008-08-20 | 2008-10-24 | n/a | 65 | 152 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Uguis | 083731023 | Construction of Schoolbuilding (1 Classroom) | 1 | 562321 | 412125.8 | 150195.2 | 400534.8 | 1st Tranche | 154453.04 | 554987.84 | 400534.8 | 154453.04 | 100% | 100% | 102.8% | 98.7% | 100% | 2008-11-18 | 2009-02-13 | 2009-03-23 | 2009-05-31 | no data | 69 | 152 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Union | 083731024 | Construction of Water System (L2) | 1 | 1017853.47 | 665790 | 352063.47 | 589008.33 | 2nd Tranche | 354280.17 | 943288.5 | 589008.33 | 354280.17 | 100% | 100% | 100.6% | 92.67% | 100% | 2007-02-27 | 2007-04-25 | 2007-10-01 | 2007-12-19 | no data | 79 | 294 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Union | 083731024 | Const.of 1 unit 2 Classroom School Building | 1 | 986304 | 690412.8 | 295891.2 | 664871.52 | 3rd Tranche | 344838.62 | 1009710.14 | 664871.52 | 344838.62 | 100% | 100% | 116.5% | 102.4% | 100% | no data | no data | 2008-09-01 | 2008-12-30 | n/a | 120 | 232 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Upper Mahaplag | 083731025 | Improvement of Farm to Market Road | 1 | 445573.13 | 304180 | 141393.13 | 243344 | 1st Tranche | 145193.13 | 388537.13 | 243344 | 145193.13 | 100% | 100% | 102.7% | 87.2% | 100% | 2007-02-27 | 2007-04-25 | 2008-01-05 | 2008-03-25 | no data | 80 | 255 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | A. Bonifacio | 083735001 | Drainage System | 1 | 476313 | 333419 | 142894 | 298757 | 2nd Tranche | 157896.3 | 456653.3 | 298757 | 157896.3 | 100% | 100% | 110.5% | 95.87% | 100% | 2007-02-27 | 2007-04-30 | 2007-08-31 | 2008-03-11 | n/a | 193 | 217 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | A. Bonifacio | 083735001 | Water System Level 1 | 1 | 275895 | 193126 | 82769 | 193125.2 | 3rd Tranche | 74784.26 | 267909.46 | 193125.2 | 74784.26 | 100% | 100% | 90.35% | 97.11% | 100% | no data | no data | 2008-10-07 | 2008-11-12 | n/a | 36 | 121 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | A. Bonifacio | 083735001 | Electrification | 1 | 499253 | 399403 | 99850 | 399403 | 1st Tranche | 50028.41 | 449431.41 | 399403 | 50028.41 | 100% | 100% | 50.1% | 90.02% | 100% | 2009-01-28 | 2009-02-28 | 2009-05-22 | 2009-09-30 | n/a | 131 | 30 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Burgos | 083735003 | Flood Control Structure | 1 | 1169009 | 818009 | 351000 | 736208.1 | 2nd Tranche | 235837.66 | 972045.76 | 736208.1 | 235837.66 | 100% | 100% | 67.19% | 83.15% | 100% | no data | no data | 2008-09-15 | 2009-08-28 | n/a | 347 | 104 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Burgos | 083735003 | Concrete Pathway | 1 | 825505 | 660404 | 165101 | 528323.2 | 1st Tranche | 145416.95 | 673740.15 | 528323.2 | 145416.95 | 100% | 100% | 88.08% | 81.62% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-27 | 2009-08-31 | n/a | 126 | 99 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Calipayan | 083735004 | Drainage System | 1 | 247279 | 162556 | 84723 | 146300.4 | 2nd Tranche | 76000 | 222300.4 | 146300.4 | 76000 | 100% | 100% | 89.7% | 89.9% | 100% | 2007-02-27 | 2007-04-30 | 2007-09-01 | 2008-03-25 | no data | 206 | 113 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Calipayan | 083735004 | Pre and Post Harvest Facility | 1 | 341617 | 256213 | 85404 | 230591.7 | 2nd Tranche | 85404 | 315995.7 | 230591.7 | 85404 | 100% | 100% | 100% | 92.5% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-29 | 2009-05-31 | no data | 32 | 70 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Camansi | 083735005 | Water System Level 1 | 1 | 213130 | 149191 | 63939 | 119352.8 | 1st Tranche | 57439 | 176791.8 | 119352.8 | 57439 | 100% | 100% | 89.83% | 82.95% | 100% | no data | no data | 2008-10-01 | 2008-11-25 | n/a | 55 | 76 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Camansi | 083735005 | Concrete Pathway | 1 | 572791 | 458233 | 114558 | 458233 | 1st Tranche | 106880.08 | 565113.08 | 458233 | 106880.08 | 100% | 100% | 93.3% | 98.66% | 100% | 2009-01-28 | 2009-02-28 | 2009-05-09 | 2009-08-31 | n/a | 114 | 82 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | General Antonio Luna | 083735006 | Construction of Drainage System | 1 | 1451989 | 1016392 | 435597 | 959424.26 | 2nd Tranche | 412813 | 1372237.26 | 959424.26 | 412813 | 100% | 100% | 94.77% | 94.51% | 100% | no data | no data | 2008-07-27 | 2008-11-16 | n/a | 112 | 195 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | General Antonio Luna | 083735006 | Drainage Canal | 1 | 151764 | 113823 | 37941 | 102440.7 | 2nd Tranche | 38208.36 | 140649.06 | 102440.7 | 38208.36 | 100% | 100% | 100.7% | 92.68% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-06 | 2009-05-31 | no data | 55 | 195 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Liberty | 083735007 | Flood Control | 1 | 1355133 | 948593 | 406540 | 853733.7 | 2nd Tranche | 267194.28 | 1120927.98 | 853733.7 | 267194.28 | 100% | 100% | 65.72% | 82.72% | 100% | 2007-02-27 | 2007-04-30 | 2007-09-06 | 2008-05-13 | n/a | 250 | 227 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Liberty | 083735007 | Construction of Bgy Health Station | 1 | 727982 | 509587 | 218395 | 458628.3 | 2nd Tranche | 164581 | 623209.3 | 458628.3 | 164581 | 100% | 100% | 75.36% | 85.61% | 100% | no data | no data | 2008-09-17 | 2008-12-18 | n/a | 92 | 277 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Liberty | 083735007 | Brgy. Talipapa | 1 | 288867 | 231094 | 57773 | 231094 | 1st Tranche | 57773 | 288867 | 231094 | 57773 | 100% | 100% | 100% | 100% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-27 | 2009-06-20 | no data | 54 | 244 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Mabini | 083735002 | Electrification | 1 | 379636 | 265745 | 113891 | 239170.5 | 1st Tranche | 113461 | 352631.5 | 239170.5 | 113461 | 100% | 100% | 99.62% | 92.89% | 100% | no data | no data | 2008-11-27 | 2008-12-27 | n/a | 30 | 185 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Mabini | 083735002 | Water System Level 2 | 1 | 563906 | 451125 | 112781 | 406012.5 | 2nd Tranche | 106166 | 512178.5 | 406012.5 | 106166 | 100% | 100% | 94.13% | 90.83% | 100% | 2009-01-28 | 2009-02-28 | 2009-05-19 | 2009-08-31 | n/a | 104 | 54 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Ormocay | 083735008 | One unit 2 Room School Building | 1 | 811965 | 568376 | 243589 | 568376 | 3rd Tranche | 243377.68 | 811753.68 | 568376 | 243377.68 | 100% | 100% | 99.91% | 99.97% | 100% | 2007-02-27 | 2007-04-30 | 2007-10-09 | 2008-03-30 | n/a | 173 | 162 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Ormocay | 083735008 | Communal Toilets | 1 | 158904 | 111233 | 47671 | 111232.8 | 2nd Tranche | 51211 | 162443.8 | 111232.8 | 51211 | 100% | 100% | 107.4% | 102.2% | 100% | no data | no data | 2009-01-22 | 2009-02-28 | n/a | 37 | 165 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Ormocay | 083735008 | Drainage Facility | 1 | 534868 | 374408 | 160460 | 336967.2 | 2nd Tranche | 127310.74 | 464277.94 | 336967.2 | 127310.74 | 100% | 100% | 79.34% | 86.8% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-28 | 2009-08-31 | n/a | 125 | 136 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone I | 083735009 | Daycare Center | 1 | 687246 | 481072 | 206174 | 384857.6 | 1st Tranche | 171419.6 | 556277.2 | 384857.6 | 171419.6 | 100% | 100% | 83.14% | 80.94% | 100% | 2007-02-27 | 2007-04-30 | 2007-08-27 | 2008-03-10 | no data | 196 | 226 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone 2 | 083735010 | Extension of Secondary Line | 1 | 351763 | 204438 | 147325 | 183994.2 | 2nd Tranche | 95176.3 | 279170.5 | 183994.2 | 95176.3 | 100% | 100% | 64.6% | 79.36% | 100% | 2007-02-27 | 2007-04-30 | 2008-03-05 | 2008-05-05 | n/a | 61 | 103 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone 3 | 083735011 | Drainage System | 1 | 568499 | 397949 | 170550 | 318359.2 | 1st Tranche | 171971.08 | 490330.28 | 318359.2 | 171971.08 | 100% | 100% | 100.8% | 86.25% | 100% | 2007-02-27 | 2007-04-30 | 2007-09-10 | 2007-10-30 | no data | 50 | 165 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone 1 | 083735009 | Electrification | 1 | 402619 | 309325 | 93294 | 309325 | 1st Tranche | 93425.47 | 402750.47 | 309325 | 93425.47 | 100% | 100% | 100.1% | 100% | 100% | 2009-01-28 | 2009-02-28 | 2009-05-22 | 2009-09-30 | n/a | 131 | 38 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone 2 | 083735010 | Drainage Canal | 1 | 544696 | 381288 | 163408 | 343159.2 | 2nd Tranche | 137694 | 480853.2 | 343159.2 | 137694 | 100% | 100% | 84.26% | 88.28% | 100% | no data | no data | 2008-10-20 | 2008-12-22 | n/a | 63 | 275 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone 2 | 083735010 | Drainage Canal | 1 | 262895 | 210316 | 52579 | 189284.4 | 1st Tranche | 52103.28 | 241387.68 | 189284.4 | 52103.28 | 100% | 100% | 99.1% | 91.82% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-14 | 2009-06-01 | no data | 48 | 187 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | San Roque | 083735012 | Water System Level 1 | 1 | 401492 | 321194 | 80298 | 256955.2 | 1st Tranche | 33649 | 290604.2 | 256955.2 | 33649 | 100% | 100% | 41.91% | 72.38% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-17 | 2009-06-20 | no data | 64 | 90 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Sta Cruz | 083735013 | Improvement of Day Care Center | 1 | 150316 | 112737 | 37579 | 101463.3 | 2nd Tranche | 37579 | 139042.3 | 101463.3 | 37579 | 100% | 100% | 100% | 92.5% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-20 | 2009-06-20 | no data | 61 | 131 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Sta. Cruz | 083735013 | Flood Control | 1 | 612006 | 428404 | 183602 | 382231.45 | 2nd Tranche | 113241.18 | 495472.63 | 382231.45 | 113241.18 | 100% | 100% | 61.68% | 80.96% | 100% | 2007-02-27 | 2007-04-30 | 2007-10-05 | 2008-05-21 | n/a | 229 | 177 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Sta. Cruz | 083735013 | Pre and Post Harvest Facility | 1 | 244155 | 170909 | 73246 | 153818.1 | 2nd Tranche | 73342.18 | 227160.28 | 153818.1 | 73342.18 | 100% | 100% | 100.1% | 93.04% | 100% | no data | no data | 2008-10-16 | 2008-11-15 | n/a | 30 | 131 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Talisay | 083735014 | Extension of Secondary Line | 1 | 376390 | 263473 | 112917 | 237125.7 | 2nd Tranche | 132492.2 | 369617.9 | 237125.7 | 132492.2 | 100% | 100% | 117.3% | 98.2% | 100% | 2007-02-27 | 2007-04-30 | 2008-03-10 | 2008-05-10 | n/a | 61 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Talisay | 083735014 | Construction of 1-unit 2 CL School Building | 1 | 1005667 | 703967 | 301700 | 703967 | 3rd Tranche | 280381.43 | 984348.43 | 703967 | 280381.43 | 100% | 100% | 92.93% | 97.88% | 100% | no data | no data | 2008-08-11 | 2008-12-04 | n/a | 115 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Talisay | 083735014 | Concrete Pathway | 1 | 754317 | 565738 | 188579 | 565738 | 1st Tranche | 169716.23 | 735454.23 | 565738 | 169716.23 | 100% | 100% | 90% | 97.5% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-27 | 2009-05-31 | no data | 34 | 161 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Union | 083735015 | Surfacing of FMR | 1 | 633348 | 443344 | 190004 | 354675.2 | 1st Tranche | 150000 | 504675.2 | 354675.2 | 150000 | 100% | 100% | 78.95% | 79.68% | 100% | 2007-02-27 | 2007-04-30 | 2007-10-04 | 2008-05-24 | n/a | 233 | 165 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Union | 083735015 | Drainage Facility | 1 | 495590 | 346913 | 148677 | 312221.7 | 2nd Tranche | 145313.15 | 457534.85 | 312221.7 | 145313.15 | 100% | 100% | 97.74% | 92.32% | 100% | no data | no data | 2008-10-31 | 2008-12-20 | n/a | 50 | 331 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Union | 083735015 | Post Harvest Facility | 1 | 1254835 | 1003868 | 250967 | 1003868 | 1st Tranche | 299172.82 | 1303040.82 | 1003868 | 299172.82 | 100% | 100% | 119.2% | 103.8% | 100% | 2009-01-28 | 2009-02-28 | 2009-04-01 | 2009-08-31 | n/a | 152 | 375 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Wilson | 083735016 | One unit 2 Room School Building | 1 | 811965 | 568376 | 243589 | 568376 | 2nd Tranche | 243989 | 812365 | 568376 | 243989 | 100% | 100% | 100.2% | 100% | 100% | 2007-02-27 | 2007-04-30 | 2007-08-27 | 2008-03-31 | n/a | 217 | 563 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Banat-e | 083742001 | Pathway & Footbridge | 1 | 435872 | 305110 | 130762 | 305110 | 3rd Tranche | 123662 | 428772 | 305110 | 123662 | 100% | 100% | 94.57% | 98.37% | 100% | 2007-02-21 | 2007-04-04 | 2007-08-06 | 2008-07-16 | n/a | 345 | 587 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Banat-e | 083742001 | Brgy Health Center | 1 | 848256 | 593779 | 254477 | 593779 | 3rd Tranche | 274196 | 867975 | 593779 | 274196 | 100% | 100% | 107.7% | 102.3% | 100% | no data | no data | 2008-09-24 | 2008-11-30 | n/a | 67 | 804 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Basud | 083742003 | CBH Lined Canal | 1 | 672997 | 403387 | 269610 | 363048.3 | 2nd Tranche | 267210 | 630258.3 | 363048.3 | 267210 | 100% | 100% | 99.11% | 93.65% | 100% | 2007-02-21 | 2007-04-04 | 2007-10-03 | 2008-04-30 | n/a | 210 | 633 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Basud | 083742003 | FMR | 1 | 1384267 | 968986 | 415281 | 872087.4 | 2nd Tranche | 293903.3 | 1165990.7 | 872087.4 | 293903.3 | 100% | 100% | 70.77% | 84.23% | 100% | no data | no data | 2007-11-20 | 2008-03-31 | no data | 132 | 744 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Bawod | 083742004 | Grouted Riprap | 1 | 1004961 | 703473 | 301488 | 703473 | 3rd Tranche | 330323 | 1033796 | 703473 | 330323 | 100% | 100% | 109.6% | 102.9% | 100% | 2007-02-21 | 2007-04-04 | 2008-02-05 | 2008-06-30 | n/a | 146 | 318 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Bawod | 083742004 | Improvement of Road Protection | 1 | 486178 | 340324 | 145854 | 272259.2 | 1st Tranche | 137236 | 409495.2 | 272259.2 | 137236 | 100% | 100% | 94.09% | 84.23% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-27 | 2009-06-30 | n/a | 64 | 318 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Biasong | 083742005 | Box Culvert | 1 | 435930 | 305151 | 130779 | 305151 | 3rd Tranche | 128916.5 | 434067.5 | 305151 | 128916.5 | 100% | 100% | 98.58% | 99.57% | 100% | no data | no data | 2008-07-21 | 2008-09-30 | n/a | 71 | 465 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Biasong | 083742005 | Improvement of Road Protection | 1 | 1465382 | 1025767 | 439615 | 615460.2 | 1st Tranche | 390077 | 1005537.2 | 615460.2 | 390077 | 100% | 100% | 88.73% | 68.62% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-22 | 2009-08-31 | n/a | 131 | 410 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Bunacan | 083742006 | Concrete Pathway with Canal | 1 | 533294 | 344362 | 188932 | 309925.8 | 2nd Tranche | 192057 | 501982.8 | 309925.8 | 192057 | 100% | 100% | 101.7% | 94.13% | 100% | 2007-02-21 | 2007-04-04 | 2008-06-02 | 2008-08-02 | no data | 61 | 250 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Bunacan | 083742006 | Construction of Single Barrel Box Culvert | 1 | 689259 | 482480 | 206779 | 385984 | 1st Tranche | 8311.3 | 394295.3 | 385984 | 8311.3 | 100% | 100% | 4.019% | 57.21% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-15 | 2009-08-31 | n/a | 138 | 250 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Busay | 083742021 | FMR | 1 | 1221662 | 855163 | 366499 | 769646.7 | 2nd Tranche | 307391 | 1077037.7 | 769646.7 | 307391 | 100% | 100% | 83.87% | 88.16% | 100% | no data | no data | 2008-08-22 | 2008-09-30 | n/a | 39 | 437 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Cabungaan | 083742008 | Upgrading Earthroad | 1 | 413100 | 269610 | 143490 | 215688 | 1st Tranche | 141440 | 357128 | 215688 | 141440 | 100% | 100% | 98.57% | 86.45% | 100% | 2007-02-21 | 2007-04-04 | 2007-03-27 | 2008-04-30 | n/a | 400 | 287 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Cabungaan | 083742008 | Daycare Center | 1 | 769716 | 538801 | 230915 | 484920.9 | 1st Tranche | 234669.09 | 719589.99 | 484920.9 | 234669.09 | 100% | 100% | 101.6% | 93.49% | 100% | no data | no data | 2008-11-03 | 2009-09-30 | n/a | 331 | 287 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Capiñahan | 083742009 | Box Culvert | 1 | 419156 | 256340 | 162816 | 230706 | 2nd Tranche | 156066 | 386772 | 230706 | 156066 | 100% | 100% | 95.85% | 92.27% | 100% | 2007-02-21 | 2007-04-04 | 2007-07-30 | 2008-05-20 | n/a | 295 | 329 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Crossing | 083742010 | Upgrading Earthroad | 1 | 214941 | 119927 | 95014 | 95941.6 | 1st Tranche | 93114 | 189055.6 | 95941.6 | 93114 | 100% | 100% | 98% | 87.96% | 100% | 2007-02-21 | 2007-04-04 | 2008-03-29 | 2008-04-30 | n/a | 32 | 395 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Daja Daku | 083742011 | Water System Level 2 | 1 | 572016 | 382714 | 189302 | 306171.2 | 1st Tranche | 179127 | 485298.2 | 306171.2 | 179127 | 100% | 100% | 94.62% | 84.84% | 100% | 2007-02-21 | 2007-04-04 | 2008-03-01 | 2008-04-30 | n/a | 60 | 441 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Daja Daku | 083742011 | Solar Drier | 1 | 453412 | 317388 | 136024 | 285640.4 | 2nd Tranche | 130630 | 416270.4 | 285640.4 | 130630 | 100% | 100% | 96.03% | 91.81% | 100% | no data | no data | 2008-10-13 | 2008-10-31 | n/a | 18 | 418 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Daja Diot | 083742012 | Gravel Roadway w/ Grouted Riprap | 1 | 1480351 | 1046997 | 433354 | 1046997 | 3rd Tranche | 298802.05 | 1345799.05 | 1046997 | 298802.05 | 100% | 100% | 68.95% | 90.91% | 100% | 2007-02-21 | 2007-04-04 | 2008-03-20 | 2008-06-20 | n/a | 92 | 365 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Hacienda Maria | 083742013 | Upgrading Earthroad | 1 | 743411 | 490360 | 253051 | 490360 | 3rd Tranche | 196963 | 687323 | 490360 | 196963 | 100% | 100% | 77.84% | 92.46% | 100% | 2007-02-21 | 2007-04-04 | 2007-08-21 | 2008-05-21 | n/a | 274 | 399 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Linao | 083742014 | Drainage System | 1 | 253261 | 176407 | 76854 | 176407 | 3rd Tranche | 75001 | 251408 | 176407 | 75001 | 100% | 100% | 97.59% | 99.27% | 100% | no data | no data | 2008-09-10 | 2008-09-30 | n/a | 20 | 162 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Matungao | 083742015 | One Room School Building | 1 | 633253 | 443277 | 189976 | 398949.6 | 2nd Tranche | 173401 | 572350.6 | 398949.6 | 173401 | 100% | 100% | 91.28% | 90.38% | 100% | 2007-02-21 | 2007-04-04 | 2007-09-03 | 2008-06-05 | n/a | 276 | 177 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Matungao | 083742015 | Improvement of Farm to Market Road | 1 | 1355965 | 949175 | 406790 | 759340 | 1st Tranche | 177555.89 | 936895.89 | 759340 | 177555.89 | 100% | 100% | 43.65% | 69.09% | 100% | 2009-01-28 | 2009-02-20 | 2009-08-03 | 2009-09-30 | n/a | 58 | 177 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Paril | 083742017 | Water System Level 2 | 1 | 679085 | 475359 | 203726 | 380287.2 | 1st Tranche | 192451 | 572738.2 | 380287.2 | 192451 | 100% | 100% | 94.47% | 84.34% | 100% | 2007-02-21 | 2007-04-04 | 2008-02-25 | 2008-06-25 | no data | 121 | 294 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Paril | 083742017 | Construction of School Building (2Classroom) | 1 | 1435554 | 1004887 | 430667 | 808909.6 | 1st Tranche | 351412.94 | 1160322.54 | 808909.6 | 351412.94 | 100% | 100% | 81.6% | 80.83% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-24 | 2009-09-30 | n/a | 159 | 294 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | San Jose | 083742018 | FMR | 1 | 722210 | 505549 | 216661 | 505549 | 3rd Tranche | 211489.3 | 717038.3 | 505549 | 211489.3 | 100% | 100% | 97.61% | 99.28% | 100% | no data | no data | 2008-09-01 | 2008-11-21 | n/a | 81 | 215 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | San Miguel | 083742022 | FMR | 1 | 642009 | 449406 | 192603 | 359524.8 | 1st Tranche | 170414 | 529938.8 | 359524.8 | 170414 | 100% | 100% | 88.48% | 82.54% | 100% | no data | no data | 2008-10-08 | 2008-11-30 | n/a | 53 | 191 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Taglawigan | 083742019 | One Room School Building | 1 | 655835 | 459084 | 196751 | 413175.2 | 2nd Tranche | 192398.5 | 605573.7 | 413175.2 | 192398.5 | 100% | 100% | 97.79% | 92.34% | 100% | 2007-02-21 | 2007-04-04 | 2007-08-16 | 2008-04-30 | n/a | 258 | 157 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Tinago | 083742020 | Water System Level 2 | 1 | 1413387 | 989370 | 424017 | 890433 | 2nd Tranche | 436067.7 | 1326500.7 | 890433 | 436067.7 | 100% | 100% | 102.8% | 93.85% | 100% | no data | no data | 2008-11-10 | 2009-01-04 | n/a | 55 | 264 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Butason I | 083745002 | Road Upgrading | 1 | 456000 | 319200 | 136800 | 301749 | 3rd Tranche | 203750 | 462524 | 301749 | 160775 | 100% | 78.91% | 148.9% | 101.4% | 100% | 2007-03-01 | 2007-04-19 | 2007-09-21 | 2008-09-16 | no data | 361 | 348 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Butason II | 083745003 | Road Upgrading | 1 | 510000 | 357000 | 153000 | 285600 | 1st Tranche | 144000 | 429600 | 285600 | 144000 | 100% | 100% | 94.12% | 84.24% | 100% | 2007-03-01 | 2007-04-19 | 2007-09-21 | 2007-11-26 | n/a | 66 | 287 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Campokpok | 083745004 | Road Upgrading | 1 | 680000 | 476000 | 204000 | 428400 | 2nd Tranche | 296950 | 671875 | 428400 | 243475 | 100% | 81.99% | 145.6% | 98.81% | 100% | 2007-03-01 | 2007-04-19 | 2007-09-19 | 2008-07-31 | no data | 316 | 1220 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Campokpok | 083745004 | Construction of Health Station | 1 | 902414 | 625487 | 276927 | 562938.3 | 2nd Tranche | 288404.08 | 851342.38 | 562938.3 | 288404.08 | 100% | 100% | 104.1% | 94.34% | 100% | no data | no data | 2008-11-03 | 2009-07-30 | n/a | 269 | 1329 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Catmon | 083745005 | Road Upgrading | 1 | 480000 | 336000 | 144000 | 302400 | 2nd Tranche | 187107.5 | 489507.5 | 302400 | 187107.5 | 100% | 100% | 129.9% | 102% | 100% | 2007-03-01 | 2007-04-19 | 2007-09-19 | 2008-06-27 | n/a | 282 | 521 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Catmon | 083745005 | Water Supply System | 1 | 256571 | 190400 | 66171 | 152320 | 1st Tranche | 95454.5 | 247774.5 | 152320 | 95454.5 | 100% | 100% | 144.3% | 96.57% | 100% | no data | no data | 2008-11-18 | 2008-12-16 | n/a | 28 | 408 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Catmon | 083745005 | Road Concreting | 1 | 518784 | 428784 | 90000 | 343027.2 | 1st Tranche | 164832.72 | 507859.92 | 343027.2 | 164832.72 | 100% | 100% | 183.1% | 97.89% | 100% | 2009-02-06 | 2009-02-27 | 2009-05-19 | 2009-07-31 | n/a | 73 | 408 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Gibacungan | 083745007 | Construction of School Building | 1 | 1192990 | 1032990 | 160000 | 929691 | 2nd Tranche | 149412.5 | 1079103.5 | 929691 | 149412.5 | 100% | 100% | 93.38% | 90.45% | 100% | 2009-02-06 | 2009-02-27 | 2009-04-28 | 2009-08-28 | n/a | 122 | 392 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Gimarco | 083745006 | Water Supply System | 1 | 945140 | 685256 | 259884 | 584832 | 2nd Tranche | 258180 | 830174.5 | 584832 | 245342.5 | 100% | 95.03% | 99.34% | 87.84% | 100% | 2007-03-01 | 2007-04-19 | 2008-04-23 | 2008-08-23 | no data | 122 | 347 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Gimarco | 083745006 | Const of Pathways | 1 | 994776 | 705187 | 289589 | 634668.3 | 2nd Tranche | 297276.5 | 931944.8 | 634668.3 | 297276.5 | 100% | 100% | 102.7% | 93.68% | 100% | no data | no data | 2009-03-09 | 2009-06-26 | n/a | 109 | 392 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Gimarco | 083745006 | Construction of School Building | 1 | 1097997 | 957997 | 140000 | 862197.3 | 2nd Tranche | 147377.07 | 1009574.37 | 862197.3 | 147377.07 | 100% | 100% | 105.3% | 91.95% | 100% | 2009-02-06 | 2009-02-27 | 2009-04-20 | 2009-11-30 | n/a | 224 | 392 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Inangatan | 083745008 | Water Supply System | 1 | 618048 | 432633 | 185415 | 389369.7 | 3rd Tranche | 216461 | 583905.7 | 389369.7 | 194536 | 100% | 89.87% | 116.7% | 94.48% | 100% | 2007-03-01 | 2007-04-19 | 2008-03-04 | 2008-06-02 | n/a | 90 | 622 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Manlawaan | 083745009 | Water Supply System | 1 | 654944 | 458461 | 196483 | 412606.9 | 2nd Tranche | 205533 | 604114.9 | 412606.9 | 191508 | 100% | 93.18% | 104.6% | 92.24% | 100% | 2007-03-01 | 2007-04-19 | 2008-03-05 | 2008-06-20 | n/a | 107 | 542 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Manlawaan | 083745009 | Road Improvement | 1 | 772320 | 540624 | 231696 | 432499.2 | 1st Tranche | 177831.5 | 610330.7 | 432499.2 | 177831.5 | 100% | 100% | 76.75% | 79.03% | 100% | no data | no data | 2008-12-16 | 2009-02-23 | n/a | 69 | 576 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Manlawaan | 083745009 | Construction of Concrete Pathwalk | 1 | 478415 | 368415 | 110000 | 294732 | 1st Tranche | 142223.32 | 436955.32 | 294732 | 142223.32 | 100% | 100% | 129.3% | 91.33% | 100% | 2009-02-06 | 2009-02-27 | 2009-05-27 | 2009-07-06 | n/a | 40 | 576 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Omaganhan | 083745010 | Road Upgrading | 1 | 477600 | 287376.6 | 190223.4 | 287376.6 | 3rd Tranche | 175453.08 | 462829.68 | 287376.6 | 175453.08 | 100% | 100% | 92.24% | 96.91% | 100% | 2007-03-01 | 2007-04-19 | 2007-09-19 | 2008-03-06 | no data | 169 | 411 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Poblacion | 083745011 | Fish Sanctuary | 1 | 462512 | 323758.4 | 138753.6 | 323758.4 | 3rd Tranche | 138459.89 | 462218.29 | 323758.4 | 138459.89 | 100% | 100% | 99.79% | 99.94% | 100% | 2007-03-01 | 2007-04-19 | 2008-04-14 | 2008-08-14 | no data | 122 | 1145 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Poblacion | 083745011 | Const of Drainage Canal | 1 | 978190 | 684733 | 293457 | 616259.7 | 2nd Tranche | 255945 | 872204.7 | 616259.7 | 255945 | 100% | 100% | 87.22% | 89.17% | 100% | no data | no data | 2008-12-04 | 2009-04-30 | n/a | 147 | 1286 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Poblacion | 083745011 | Road Concreting | 1 | 473904 | 353904 | 120000 | 283123.2 | 1st Tranche | 235178.2 | 518301.4 | 283123.2 | 235178.2 | 100% | 100% | 196% | 109.4% | 100% | 2009-02-06 | 2009-02-27 | 2009-06-01 | 2009-07-31 | n/a | 60 | 1286 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Sta. Rosa | 083745012 | Water Supply System | 1 | 399071 | 279350 | 119721 | 223480 | 1st Tranche | 129683.5 | 353163.5 | 223480 | 129683.5 | 100% | 100% | 108.3% | 88.5% | 100% | no data | no data | 2009-04-20 | 2009-06-04 | n/a | 45 | 274 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Tabing | 083745013 | Water Supply System | 1 | 704626 | 493239 | 211387 | 394591.2 | 1st Tranche | 235316.43 | 629907.63 | 394591.2 | 235316.43 | 100% | 100% | 111.3% | 89.4% | 100% | no data | no data | 2009-03-30 | 2009-07-31 | n/a | 123 | 458 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Tabing | 083745013 | Construction of Pathwalk with Riprap | 1 | 1137410 | 757910 | 379500 | 682119 | 2nd Tranche | 349500 | 1031619 | 682119 | 349500 | 100% | 100% | 92.09% | 90.7% | 100% | 2009-02-06 | 2009-02-27 | 2009-05-16 | 2009-07-07 | n/a | 52 | 458 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Tugas | 083745014 | Water Supply System | 1 | 317450 | 224315 | 93135 | 187573.5 | 2nd Tranche | 90447.5 | 278021 | 187573.5 | 90447.5 | 100% | 100% | 97.11% | 87.58% | 100% | 2007-03-01 | 2007-04-19 | 2008-02-27 | 2008-04-25 | n/a | 58 | 283 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Tugas | 083745014 | Rehab of Farm to Market Road | 1 | 544257 | 380980 | 163277 | 304784 | 1st Tranche | 160952 | 465736 | 304784 | 160952 | 100% | 100% | 98.58% | 85.57% | 100% | no data | no data | 2008-12-16 | 2009-02-28 | n/a | 74 | 286 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Amandangay - C2 | 083746001 | Water System Level 2 | 2 | 999210 | 699447 | 299763 | 699446 | 3rd Tranche | 270456 | 969902 | 699446 | 270456 | 100% | 100% | 90.22% | 97.07% | 100% | 2007-02-26 | 2007-04-21 | 2007-08-06 | 2008-10-30 | n/a | 451 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Amandangay - C2 | 083746001 | Construction of Spillway | 2 | 1821900 | 1275330 | 546570 | 1020264 | 1st Tranche | 606802.6 | 1627066.6 | 1020264 | 606802.6 | 100% | 100% | 111% | 89.31% | 100% | 2009-02-04 | 2009-02-27 | 2009-07-28 | 2009-09-30 | no data | 64 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Mohon | 083746011 | Construction of Spillway | 2 | 1821900 | 1275330 | 546570 | 1020264 | 1st Tranche | 606802.6 | 1627066.6 | 1020264 | 606802.6 | 100% | 100% | 111% | 89.31% | 100% | 2009-02-04 | 2009-02-27 | 2009-07-28 | 2009-09-30 | no data | 64 | 151 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Aslum | 083746002 | Pre/Post Harvest Facility | 1 | 411016 | 287711 | 123305 | 273343 | 3rd Tranche | 140273 | 413616 | 273343 | 140273 | 100% | 100% | 113.8% | 100.6% | 100% | no data | no data | 2008-11-17 | 2009-05-31 | no data | 195 | 73 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Aslum - C2 | 083746002 | Water System Level 2 | 2 | 975900 | 683130 | 292770 | 614817 | 2nd Tranche | 265580 | 880397 | 614817 | 265580 | 100% | 100% | 90.71% | 90.21% | 100% | 2007-02-26 | 2007-04-21 | 2007-09-12 | 2008-10-15 | n/a | 399 | 236 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | San Pablo (Mooc) | 083746017 | Water System Level 2 | 2 | 975900 | 683130 | 292770 | 614817 | 2nd Tranche | 265580 | 880397 | 614817 | 265580 | 100% | 100% | 90.71% | 90.21% | 100% | 2007-02-26 | 2007-04-21 | 2007-09-12 | 2008-10-15 | n/a | 399 | 236 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Balingasag | 083746003 | Rice Mill with Structure | 1 | 785907 | 532808 | 253099 | 532808 | 3rd Tranche | 266359.05 | 799167.05 | 532808 | 266359.05 | 100% | 100% | 105.2% | 101.7% | 100% | 2007-02-26 | 2007-04-21 | 2007-07-25 | 2008-10-30 | n/a | 463 | 129 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Balingasag | 083746003 | Construction of Water System Level 2 | 1 | 671391 | 469974 | 201417 | 375979.2 | 1st Tranche | 190938.2 | 566917.4 | 375979.2 | 190938.2 | 100% | 100% | 94.8% | 84.44% | 100% | no data | no data | 2009-01-12 | 2009-06-01 | no data | 140 | 137 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Balingasag | 083746003 | Drainage Canal | 1 | 536114 | 375280 | 160834 | 337752 | 2nd Tranche | 184990.72 | 522742.72 | 337752 | 184990.72 | 100% | 100% | 115% | 97.51% | 100% | 2009-02-04 | 2009-02-27 | 2009-05-14 | 2009-08-31 | n/a | 109 | 100 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Belisong | 083746004 | Pre/Post Harvest Facility with Structure | 1 | 403694 | 282586 | 121108 | 254327.4 | 2nd Tranche | 120066.6 | 374394 | 254327.4 | 120066.6 | 100% | 100% | 99.14% | 92.74% | 100% | no data | no data | 2008-12-02 | 2009-08-28 | n/a | 269 | 94 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Belisong - C2 | 083746004 | Water System Level 2 | 2 | 1154173 | 807921 | 346252 | 807920.9 | 3rd Tranche | 309357.75 | 1117278.65 | 807920.9 | 309357.75 | 100% | 100% | 89.34% | 96.8% | 100% | 2007-02-26 | 2007-04-21 | 2007-09-12 | 2008-10-30 | n/a | 414 | 2418 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Jabong | 083746008 | Water System Level 2 | 2 | 1154173 | 807921 | 346252 | 807920.9 | 3rd Tranche | 309357.75 | 1117278.65 | 807920.9 | 309357.75 | 100% | 100% | 89.34% | 96.8% | 100% | 2007-02-26 | 2007-04-21 | 2007-09-12 | 2008-10-30 | n/a | 414 | 2418 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | District III Pob. (Bonifacio) | 083746008 | Drainage Canal | 1 | 929280 | 650496 | 278784 | 585446.4 | 2nd Tranche | 285586 | 871032.4 | 585446.4 | 285586 | 100% | 100% | 102.4% | 93.73% | 100% | 2009-02-04 | 2009-02-27 | 2009-04-22 | 2009-08-31 | n/a | 131 | 113 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Cambucao | 083746005 | Pre/Post Harvest Facility w/ Structure | 1 | 411016 | 287711 | 123305 | 272610 | 3rd Tranche | 133709.2 | 406319.2 | 272610 | 133709.2 | 100% | 100% | 108.4% | 98.86% | 100% | no data | no data | 2008-11-10 | 2009-03-31 | no data | 141 | 49 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Cambucao | 083746005 | Water System Level 2 | 1 | 218023 | 152616 | 65407 | 122092.8 | 2nd Tranche | 76184.31 | 198277.11 | 122092.8 | 76184.31 | 100% | 100% | 116.5% | 90.94% | 100% | 2009-02-04 | 2009-02-27 | 2009-05-11 | 2009-08-31 | n/a | 112 | 44 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Capahuan | 083746006 | Construction of Water System Level 2 | 1 | 527896 | 369527 | 158369 | 369527 | 3rd Tranche | 172573 | 542100 | 369527 | 172573 | 100% | 100% | 109% | 102.7% | 100% | no data | no data | 2009-01-12 | 2009-03-31 | no data | 78 | 205 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Guingauan | 083746007 | Health Station | 1 | 744016 | 520811 | 223205 | 497856.6 | 2nd Tranche | 227601.22 | 725457.82 | 497856.6 | 227601.22 | 100% | 100% | 102% | 97.51% | 100% | 2007-02-26 | 2007-04-21 | 2007-07-04 | 2008-11-15 | n/a | 500 | 109 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Jabong | 083746008 | Construction of Drainage System | 1 | 891668 | 624168 | 267500 | 561751.2 | 2nd tranche | 231310 | 793061.2 | 561751.2 | 231310 | 100% | 100% | 86.47% | 88.94% | 100% | no data | no data | 2008-11-24 | 2009-04-28 | n/a | 155 | 157 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Jabong | 083746008 | 1 Classroom School Building | 1 | 617389 | 432172 | 185217 | 388954.8 | 2nd Tranche | 296323.3 | 685278.1 | 388954.8 | 296323.3 | 100% | 100% | 160% | 111% | 100% | 2009-02-04 | 2009-02-27 | 2009-05-18 | 2009-08-31 | n/a | 105 | 154 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | District IV Pob. (Macarthur) | 083746016 | Electrification | 1 | 293082 | 202982 | 90100 | 202982 | 2nd Tranche | 52505 | 255487 | 202982 | 52505 | 100% | 100% | 58.27% | 87.17% | 100% | 2007-02-26 | 2007-04-21 | 2009-03-16 | 2009-03-31 | n/a | 15 | 21 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Mercadohay | 083746009 | Drainage Canal | 1 | 649466 | 454626 | 194840 | 409163.4 | 2nd Tranche | 194213.34 | 603376.74 | 409163.4 | 194213.34 | 100% | 100% | 99.68% | 92.9% | 100% | 2009-02-04 | 2009-02-27 | 2009-05-14 | 2009-06-29 | n/a | 46 | 164 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Mercadohay - C2 | 083746009 | Water System Level 2 | 2 | 1160036 | 812025 | 348011 | 812025 | 2nd Tranche | 306870 | 1118895 | 812025 | 306870 | 100% | 100% | 88.18% | 96.45% | 100% | 2007-02-26 | 2007-04-21 | 2007-09-12 | 2009-08-28 | n/a | 716 | 368 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Mering | 083746010 | Water System Level 2 | 2 | 1160036 | 812025 | 348011 | 812025 | 2nd Tranche | 306870 | 1118895 | 812025 | 306870 | 100% | 100% | 88.18% | 96.45% | 100% | 2007-02-26 | 2007-04-21 | 2007-09-12 | 2009-08-28 | n/a | 716 | 368 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Mering | 083746010 | Pathway | 1 | 216747 | 151723 | 65024 | 121378.4 | 1st Tranche | 56110.34 | 177488.74 | 121378.4 | 56110.34 | 100% | 100% | 86.29% | 81.89% | 100% | 2009-02-04 | 2009-02-27 | 2009-06-18 | 2009-08-31 | n/a | 74 | 209 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | Mohon | 083746011 | Construction of Drainage Canal | 1 | 679848.5 | 475894 | 203954.5 | 428304.6 | 2nd Tranche | 206586.65 | 634891.25 | 428304.6 | 206586.65 | 100% | 100% | 101.3% | 93.39% | 100% | no data | no data | 2008-11-24 | 2009-01-02 | n/a | 39 | 65 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | District I Pob. (Quezon) | 083746013 | Drainage System | 2 | 772680 | 540876 | 231804 | 516921.3 | 3rd Tranche | 239144 | 756065.3 | 516921.3 | 239144 | 100% | 100% | 103.2% | 97.85% | 100% | 2007-02-26 | 2007-04-21 | 2007-07-24 | 2008-10-15 | n/a | 449 | 261 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | District II Pob. (Rizal) | 083746014 | Drainage System | 2 | 772680 | 540876 | 231804 | 516921.3 | 3rd Tranche | 239144 | 756065.3 | 516921.3 | 239144 | 100% | 100% | 103.2% | 97.85% | 100% | 2007-02-26 | 2007-04-21 | 2007-07-24 | 2008-10-15 | n/a | 449 | 261 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | District II Pob. (Rizal) | 083746014 | 1 Classroom School Building | 1 | 617389 | 432172 | 185217 | 388954.8 | 2nd Tranche | 178890 | 567844.8 | 388954.8 | 178890 | 100% | 100% | 96.58% | 91.98% | 100% | 2009-02-04 | 2009-02-27 | 2009-05-12 | 2009-08-31 | n/a | 111 | 126 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | Tabontabon | 083746 | San Pablo | 083746017 | Construction of Drainage Canal | 1 | 1776792 | 1243754 | 533038 | 621877 | 1st Tranche | 459838.8 | 1081715.8 | 621877 | 459838.8 | 100% | 100% | 86.27% | 60.88% | 100% | no data | no data | 2008-12-12 | 2009-03-05 | n/a | 83 | 170 |  | 1 | MINDANAO
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | San Pablo | 083746017 | Barangay Health Center | 1 | 776115 | 543281 | 232834 | 405086.4 | 1st Tranche | 276909.01 | 681995.41 | 405086.4 | 276909.01 | 100% | 100% | 118.9% | 87.87% | 100% | 2009-02-04 | 2009-02-27 | 2009-07-24 | 2009-08-31 | n/a | 38 | 170 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Abaton | 084808001 | Construction of Water System (L2) | 1 | 494900 | 346430 | 148470 | 311787 | 2nd Tranche | 153850 | 465637 | 311787 | 153850 | 100% | 100% | 103.6% | 94.09% | 100% | 2007-02-21 | 2007-04-10 | 2008-03-25 | 2008-08-25 | no data | 153 | 156 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Abaton | 084808001 | Footbridge | 1 | 725000 | 507500 | 217500 | 456750 | 2nd Tranche | 245050 | 701800 | 456750 | 245050 | 100% | 100% | 112.7% | 96.8% | 100% | no data | no data | 2008-12-15 | 2009-05-30 | n/a | 166 | 55 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aguadahan | 084808002 | Construction of Causeway | 1 | 448188 | 272428 | 175760 | 256027.45 | 2nd Tranche | 175520 | 431547.45 | 256027.45 | 175520 | 100% | 100% | 99.86% | 96.29% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-01 | 2007-10-09 | n/a | 69 | 113 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aguadahan | 084808002 | Concrete Pathway | 1 | 297200 | 208040 | 89160 | 166432 | 1st Tranche | 90702 | 257134 | 166432 | 90702 | 100% | 100% | 101.7% | 86.52% | 100% | no data | no data | 2008-10-06 | 2008-10-06 | n/a | 0 | 112 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aguadahan | 084808002 | Sea Wall | 1 | 450640 | 372270 | 78370 | 297816 | 1st Tranche | 71712 | 369528 | 297816 | 71712 | 100% | 100% | 91.5% | 82% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-04 | 2009-08-31 | n/a | 119 | 280 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aroganga | 084808003 | Construction of School Building (1 Rm) | 1 | 595000 | 416500 | 178500 | 408173.68 | 3rd Tranche | 178800 | 586973.68 | 408173.68 | 178800 | 100% | 100% | 100.2% | 98.65% | 100% | 2007-02-21 | 2007-04-10 | 2007-11-25 | 2008-05-25 | n/a | 182 | 134 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aroganga | 084808003 | Construction of Sea Wall | 1 | 1354700 | 947518 | 407182 | 852766.4 | 3rd Tranche | 470807.8 | 1323574.2 | 852766.4 | 470807.8 | 100% | 100% | 115.6% | 97.7% | 100% | no data | no data | 2008-10-27 | 2009-03-31 | n/a | 155 | 124 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Aroganga | 084808003 | Causeway | 1 | 1161365 | 763501 | 397864 | 610800.8 | 1st Tranche | 240709 | 719925.8 | 610800.8 | 109125 | 100% | 45.33% | 60.5% | 61.99% | 100% | 2009-01-28 | 2009-02-27 | 2009-06-15 | 2009-08-31 | n/a | 77 | 104 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Atipolo | 084808004 | Construction of Water System (L1) | 1 | 114974 | 79614 | 35360 | 63692 | 1st Tranche | 46360 | 110052 | 63692 | 46360 | 100% | 100% | 131.1% | 95.72% | 100% | 2007-02-21 | 2007-04-10 | 2008-07-04 | 2008-09-26 | no data | 84 | 191 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Atipolo | 084808004 | Improvement of Footbridge | 1 | 453000 | 202564 | 250436 | 162051.2 | 1st Tranche | 241644 | 403695.2 | 162051.2 | 241644 | 100% | 100% | 96.49% | 89.12% | 100% | no data | no data | 2009-05-04 | 2009-05-30 | n/a | 26 | 154 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bawang | 084808005 | Construction of School Building (1 Rm) | 1 | 597000 | 417900 | 179100 | 399220.39 | 3rd Tranche | 191467 | 590687.39 | 399220.39 | 191467 | 100% | 100% | 106.9% | 98.94% | 100% | 2007-02-21 | 2007-04-10 | 2007-11-25 | 2008-04-25 | n/a | 152 | 153 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bawang | 084808005 | Drainage Canal | 1 | 743000 | 668711 | 74289 | 601839.9 | 2nd Tranche | 88619 | 690458.9 | 601839.9 | 88619 | 100% | 100% | 119.3% | 92.93% | 100% | no data | no data | 2008-11-25 | 2009-01-30 | n/a | 66 | 125 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bawang | 084808005 | River Control | 1 | 1252000 | 1102793 | 149207 | 882234.4 | 1st Tranche | 121800 | 1004034.4 | 882234.4 | 121800 | 100% | 100% | 81.63% | 80.19% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-07 | 2009-06-30 | no data | 54 | 156 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Baybay | 084808006 | Erosion Control with Pathway | 1 | 423000 | 294000 | 129000 | 294000 | 3rd Tranche | 128455 | 422455 | 294000 | 128455 | 100% | 100% | 99.58% | 99.87% | 100% | 2007-02-21 | 2007-04-10 | 2007-07-01 | 2007-08-21 | no data | 51 | 264 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Binatiklan | 084808007 | Construction of Water System (L1) | 1 | 113996 | 75684 | 38312 | 75684 | 3rd Tranche | 39990 | 115674 | 75684 | 39990 | 100% | 100% | 104.4% | 101.5% | 100% | 2007-02-21 | 2007-04-10 | 2008-02-05 | 2008-05-25 | n/a | 110 | 78 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Binatiklan | 084808007 | Toilets | 1 | 999800 | 699860 | 299940 | 629874 | 2nd Tranche | 319850.5 | 949724.5 | 629874 | 319850.5 | 100% | 100% | 106.6% | 94.99% | 100% | no data | no data | 2008-10-27 | 2009-03-31 | n/a | 155 | 87 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bobolosan | 084808008 | Construction of Brgy. Health Station | 1 | 694820 | 462560 | 232260 | 462560 | 3rd Tranche | 195110 | 657670 | 462560 | 195110 | 100% | 100% | 84% | 94.65% | 100% | 2007-02-21 | 2007-04-10 | 2008-06-15 | 2008-09-15 | no data | 92 | 318 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bobolosan | 084808008 | Day Care Center | 1 | 680000 | 595428 | 84572 | 476342.4 | 1st Tranche | 96573.7 | 572916.1 | 476342.4 | 96573.7 | 100% | 100% | 114.2% | 84.25% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-05 | 2009-08-31 | n/a | 118 | 360 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Bongliw | 084808009 | Day Care Center | 1 | 712000 | 632130 | 79870 | 505704 | 1st Tranche | 100389 | 606093 | 505704 | 100389 | 100% | 100% | 125.7% | 85.13% | 100% | 2009-01-28 | 2009-02-27 | 2009-06-08 | 2009-08-31 | n/a | 84 | 152 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Burabud | 084808010 | Concrete Pathway | 1 | 654600 | 458220 | 196380 | 366576 | 1st Tranche | 206155 | 572731 | 366576 | 206155 | 100% | 100% | 105% | 87.49% | 100% | no data | no data | 2008-10-27 | 2009-02-27 | n/a | 123 | 184 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabadiangan | 084808011 | Day Care Center | 1 | 713000 | 499100 | 213900 | 399280 | 1st Tranche | 231972 | 631252 | 399280 | 231972 | 100% | 100% | 108.4% | 88.53% | 100% | no data | no data | 2008-10-27 | 2009-02-27 | n/a | 123 | 530 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabadiangan | 084808011 | Health Station | 1 | 718000 | 599630 | 118370 | 479704 | 1st Tranche | 134561 | 614265 | 479704 | 134561 | 100% | 100% | 113.7% | 85.55% | 100% | 2009-01-28 | 2009-02-27 | 2009-07-22 | 2009-08-31 | n/a | 40 | 591 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabagngan | 084808012 | Day Care Center | 1 | 710000 | 496144 | 213856 | 396915.2 | 1st Tranche | 209300 | 606215.2 | 396915.2 | 209300 | 100% | 100% | 97.87% | 85.38% | 100% | no data | no data | 2009-03-26 | 2009-08-28 | n/a | 155 | 98 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabago-an | 084808013 | Construction of School Building (1 Rm) | 1 | 590700 | 411290 | 179410 | 370161 | 2nd Tranche | 119355 | 489516 | 370161 | 119355 | 100% | 100% | 66.53% | 82.87% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-25 | 2008-06-25 | n/a | 152 | 146 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabolaloan | 084808014 | Construction of Solar Dryer | 1 | 483400 | 338800 | 144600 | 338800 | 3rd Tranche | 137146.26 | 475946.26 | 338800 | 137146.26 | 100% | 100% | 94.85% | 98.46% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-27 | 2008-05-26 | n/a | 273 | 168 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabolaloan | 084808014 | Pre-Harvest Facility | 1 | 562500 | 393750 | 168750 | 384804.12 | 3rd Tranche | 157714 | 542518.12 | 384804.12 | 157714 | 100% | 100% | 93.46% | 96.45% | 100% | no data | no data | 2008-10-13 | 2008-11-30 | n/a | 48 | 185 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cabulaloan | 084808014 | Health Station | 1 | 1178000 | 1092786 | 85214 | 874228.8 | 2nd Tranche | 124644 | 998872.8 | 874228.8 | 124644 | 100% | 100% | 146.3% | 84.79% | 100% | 2009-01-28 | 2009-02-27 | 2009-06-02 | 2009-08-28 | n/a | 87 | 188 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagaasan | 084808015 | Improvement of Farm to Market Road | 1 | 490375 | 337570 | 152805 | 337570 | 3rd Tranche | 171683.22 | 509253.22 | 337570 | 171683.22 | 100% | 100% | 112.4% | 103.8% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-27 | 2007-10-01 | no data | 35 | 152 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagaasan | 084808015 | Construction of School Building (1Rm) | 1 | 755250 | 528675 | 226575 | 501619.4 | 2nd Tranche | 237859 | 739478.4 | 501619.4 | 237859 | 100% | 100% | 105% | 97.91% | 100% | no data | no data | 2008-10-15 | 2008-12-31 | n/a | 77 | 125 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagaasan | 084808015 | Day Care Center | 1 | 712000 | 593630 | 118370 | 474904 | 2nd Tranche | 70003 | 544907 | 474904 | 70003 | 100% | 100% | 59.14% | 76.53% | 100% | 2009-01-28 | 2009-02-27 | 2009-04-28 | 2009-08-31 | n/a | 125 | 125 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagdara-o | 084808016 | Construction of Water System (L2) | 1 | 347900 | 240800 | 107100 | 192640 | 1st Tranche | 111780 | 304420 | 192640 | 111780 | 100% | 100% | 104.4% | 87.5% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-15 | 2008-05-21 | n/a | 127 | 126 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cagdara-o | 084808016 | Causeway | 1 | 1692400 | 1184680 | 507720 | 947744 | 1st Tranche | 507664 | 1455408 | 947744 | 507664 | 100% | 100% | 99.99% | 86% | 100% | no data | no data | 2009-06-01 | 2009-08-28 | n/a | 88 | 87 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cahayagan | 084808017 | Day Care Center | 1 | 739000 | 517300 | 221700 | 413840 | 1st Tranche | 201834 | 615674 | 413840 | 201834 | 100% | 100% | 91.04% | 83.31% | 100% | no data | no data | 2009-11-27 | 2009-02-20 | n/a | -280 | 365 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cahayagan | 084808017 | Construction of Sea Wall | 1 | 571000 | 336200 | 234800 | 268960 | 1st Tranche | 90500 | 359460 | 268960 | 90500 | 100% | 100% | 38.54% | 62.95% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-20 | 2008-08-30 | no data | 223 | 348 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Calomotan | 084808019 | 2 Room School Building | 1 | 739800 | 641430 | 98370 | 513144 | 1st Tranche | 91842.5 | 604986.5 | 513144 | 91842.5 | 100% | 100% | 93.36% | 81.78% | 100% | 2009-01-28 | 2009-02-27 | 2009-04-27 | 2009-08-31 | n/a | 126 | 220 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Cancahipos | 084808021 | Construction of Water System (L2) | 1 | 319500 | 218300 | 101200 | 196470 | 2nd Tranche | 107685 | 304155 | 196470 | 107685 | 100% | 100% | 106.4% | 95.2% | 100% | 2007-02-21 | 2007-04-10 | 2008-02-15 | 2008-09-30 | no data | 228 | 121 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Candawid | 084808020 | Construction of Water System (L1) | 1 | 222317 | 145172 | 77145 | 116137.6 | 1st Tranche | 77655 | 193792.6 | 116137.6 | 77655 | 100% | 100% | 100.7% | 87.17% | 100% | 2007-02-21 | 2007-04-10 | 2008-09-12 | 2009-04-29 | n/a | 229 | 124 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Candawid | 084808020 | Improvcement of Causeway | 1 | 728000 | 509600 | 218400 | 509600 | 1st Tranche | 185428.6 | 695028.6 | 509600 | 185428.6 | 100% | 100% | 84.9% | 95.47% | 100% | no data | no data | 2008-11-14 | 2009-03-31 | n/a | 137 | 175 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Catigbian | 084808023 | Farm to Market Road | 1 | 1059000 | 741300 | 317700 | 666930 | 2nd Tranche | 315410 | 982340 | 666930 | 315410 | 100% | 100% | 99.28% | 92.76% | 100% | 2007-02-21 | 2007-04-10 | 2008-05-12 | 2008-08-12 | no data | 92 | 176 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Catigbian | 084808023 | Improvement of Water System (L1) | 1 | 105000 | 64927 | 40073 | 51941.6 | 1st Tranche | 41584 | 93525.6 | 51941.6 | 41584 | 100% | 100% | 103.8% | 89.07% | 100% | no data | no data | 2008-11-25 | 2008-12-30 | n/a | 35 | 186 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Catigbian | 084808023 | 1 Room School Building | 1 | 708000 | 634588 | 73412 | 507670.4 | 1st Tranche | 81769 | 589439.4 | 507670.4 | 81769 | 100% | 100% | 111.4% | 83.25% | 100% | 2009-01-28 | 2009-02-27 | 2009-06-10 | 2009-08-31 | n/a | 82 | 186 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | E.J. Dulay | 084808026 | Construction of School Building (1Rm) | 1 | 767000 | 676096 | 90904 | 608486.4 | 2nd Tranche | 79826 | 688312.4 | 608486.4 | 79826 | 100% | 100% | 87.81% | 89.74% | 100% | no data | no data | 2009-02-09 | 2009-05-30 | n/a | 110 | 216 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | EJ Dulay | 084808026 | Construction of Water System (L2) | 1 | 484000 | 338800 | 145200 | 320367.7 | 3rd Tranche | 138595 | 458962.7 | 320367.7 | 138595 | 100% | 100% | 95.45% | 94.83% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-05 | 2008-09-30 | no data | 269 | 187 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | G.B Tan | 084808027 | Construction of Water System (L1) | 1 | 82554 | 46479 | 36075 | 37183 | 1st Tranche | 39640 | 76823 | 37183 | 39640 | 100% | 100% | 109.9% | 93.06% | 100% | 2007-02-21 | 2007-04-10 | 2009-02-01 | 2009-02-28 | no data | 27 | 50 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Gibatangan | 084808028 | Construction of Footbridge | 1 | 560000 | 338300 | 221700 | 270640 | 1st Tranche | 220890 | 491530 | 270640 | 220890 | 100% | 100% | 99.63% | 87.77% | 100% | 2007-02-21 | 2007-04-10 | 2008-02-05 | 2008-05-31 | n/a | 116 | 87 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Gibatangan | 084808028 | Concrete Pathway | 1 | 432900 | 303030 | 129870 | 242424 | 1st Tranche | 134268 | 376692 | 242424 | 134268 | 100% | 100% | 103.4% | 87.02% | 100% | no data | no data | 2009-03-26 | 2009-08-28 | n/a | 155 | 91 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Guilaoangi | 084808029 | Construction of Day Care Center | 1 | 454000 | 317800 | 136200 | 317800 | 2nd Tranche | 145215 | 463015 | 317800 | 145215 | 100% | 100% | 106.6% | 102% | 100% | 2007-02-21 | 2007-04-10 | 2007-11-20 | 2008-05-30 | n/a | 192 | 483 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Guilaoangi | 084808029 | Drainage Canal | 1 | 575000 | 505130 | 69870 | 454617 | 3rd Tranche | 50000 | 476076.03 | 454617 | 21459.03 | 100% | 42.92% | 71.56% | 82.8% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-08 | 2009-06-30 | no data | 53 | 503 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Inamlan | 084808030 | Concrete Pathway | 1 | 326478 | 227298 | 99180 | 204568.2 | 2nd Tranche | 79110 | 283678.2 | 204568.2 | 79110 | 100% | 100% | 79.76% | 86.89% | 100% | 2007-02-21 | 2007-04-10 | 2007-10-10 | 2008-05-30 | n/a | 233 | 131 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | La Perla | 084808031 | Construction of Water System (L2) | 1 | 490600 | 273880 | 216720 | 246492 | 2nd Tranche | 224140 | 470632 | 246492 | 224140 | 100% | 100% | 103.4% | 95.93% | 100% | 2007-02-21 | 2007-04-10 | 2007-11-01 | 2008-09-30 | no data | 334 | 257 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | La Perla | 084808031 | Health Station | 1 | 712000 | 593630 | 118370 | 474904 | 1st Tranche | 114798 | 589702 | 474904 | 114798 | 100% | 100% | 96.98% | 82.82% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-04 | 2009-08-28 | n/a | 116 | 238 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Langob | 084808032 | Provision of Fish Sanctuary (Payaw) | 1 | 221500 | 155050 | 66450 | 155040 | 1st Tranche | 66290 | 221330 | 155040 | 66290 | 100% | 100% | 99.76% | 99.92% | 100% | 2007-02-21 | 2007-04-10 | 2008-06-20 | 2008-08-20 | n/a | 61 | 114 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Langob | 084808032 | Day Care Center | 1 | 710000 | 637413 | 72587 | 509930.4 | 1st Tranche | 81443 | 543126.4 | 509930.4 | 33196 | 100% | 40.76% | 112.2% | 76.5% | 100% | no data | no data | 2009-01-05 | 2009-05-31 | no data | 146 | 114 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Lawaan | 084808033 | Construction of School Building (1 Rm) | 1 | 495800 | 347060 | 148740 | 312354 | 2nd Tranche | 148960 | 461314 | 312354 | 148960 | 100% | 100% | 100.1% | 93.04% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-25 | 2008-05-31 | n/a | 127 | 201 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Little Venice | 084808034 | Shore Protection with Footpath | 1 | 827000 | 578900 | 248100 | 521010 | 2nd Tranche | 244110 | 765120 | 521010 | 244110 | 100% | 100% | 98.39% | 92.52% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-01 | 2008-04-30 | n/a | 273 | 647 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Magsaysay | 084808035 | Construction of School Building (1 Rm) | 1 | 588000 | 411600 | 176400 | 411600 | 3rd Tranche | 179980 | 591580 | 411600 | 179980 | 100% | 100% | 102% | 100.6% | 100% | 2007-02-21 | 2007-04-10 | 2007-11-05 | 2008-05-25 | n/a | 202 | 106 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Magsaysay | 084808035 | Water Supply System (L1) | 1 | 185200 | 129640 | 55560 | 103712 | 1st Tranche | 67911 | 171623 | 103712 | 67911 | 100% | 100% | 122.2% | 92.67% | 100% | no data | no data | 2008-10-13 | 2008-12-13 | n/a | 61 | 106 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Magsaysay | 084808035 | Concrete Pathway | 1 | 491600 | 381730 | 109870 | 305384 | 1st Tranche | 100168 | 405552 | 305384 | 100168 | 100% | 100% | 91.17% | 82.5% | 100% | 2009-01-28 | 2009-02-27 | 2009-04-29 | 2009-05-30 | no data | 31 | 106 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Marubay | 084808036 | Concrete Pathway | 1 | 303375 | 204915 | 98460 | 163932 | 1st Tranche | 98540 | 262472 | 163932 | 98540 | 100% | 100% | 100.1% | 86.52% | 100% | 2007-02-21 | 2007-04-10 | 2008-05-30 | 2008-05-30 | no data | 0 | 217 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Marubay | 084808036 | 2 Classroom School Building | 1 | 1190500 | 1067088 | 123412 | 853670.4 | 1st Tranche | 168142.36 | 1021812.76 | 853670.4 | 168142.36 | 100% | 100% | 136.2% | 85.83% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-04 | 2009-06-30 | no data | 57 | 225 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Mualbual | 084808037 | Construction of Water System (L2) | 1 | 440000 | 308000 | 132000 | 277200 | 2nd Tranche | 161302.47 | 438502.47 | 277200 | 161302.47 | 100% | 100% | 122.2% | 99.66% | 100% | 2007-02-21 | 2007-04-10 | 2007-10-15 | 2008-05-15 | n/a | 213 | 111 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Mualbual | 084808037 | Construction of School Building (1Rm) | 1 | 740250 | 648442 | 91808 | 518753.6 | 1st Tranche | 106542 | 625295.6 | 518753.6 | 106542 | 100% | 100% | 116% | 84.47% | 100% | no data | no data | 2009-02-28 | 2009-05-30 | n/a | 91 | 112 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Mualbual | 084808037 | Day Care Center | 1 | 717000 | 647130 | 69870 | 517704 | 1st Tranche | 89228 | 606932 | 517704 | 89228 | 100% | 100% | 127.7% | 84.65% | 100% | 2009-01-28 | 2009-02-27 | 2009-06-01 | 2009-08-31 | n/a | 91 | 123 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Napotiocan | 084808038 | Farm to Market Road | 1 | 2232642 | 999117 | 1233525 | 799293 | 1st Tranche | 1312597 | 2111890 | 799293 | 1312597 | 100% | 100% | 106.4% | 94.59% | 100% | 2007-02-21 | 2007-04-10 | 2008-07-24 | 2008-09-15 | n/a | 53 | 31 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Oleras | 084808039 | Construction of Water System (L2) | 1 | 758000 | 528980 | 229020 | 492243.74 | 3rd Tranche | 233290 | 725533.74 | 492243.74 | 233290 | 100% | 100% | 101.9% | 95.72% | 100% | 2007-02-21 | 2007-04-10 | 2007-09-20 | 2008-02-13 | no data | 146 | 315 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Oleras | 084808039 | Erosion Control | 1 | 1321000 | 924700 | 396300 | 832230 | 2nd Tranche | 423403.02 | 1255633.02 | 832230 | 423403.02 | 100% | 100% | 106.8% | 95.05% | 100% | no data | no data | 2008-11-03 | 2009-03-31 | n/a | 148 | 314 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Palmera | 084808041 | Construction of Water System (L2) | 1 | 290000 | 195000 | 95000 | 195000 | 2nd Tranche | 112220 | 307220 | 195000 | 112220 | 100% | 100% | 118.1% | 105.9% | 100% | 2007-02-21 | 2007-04-10 | 2008-04-29 | 2008-08-29 | no data | 122 | 84 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Pangdan | 084808042 | Construction of School Building (1 Rm) | 1 | 600000 | 405800 | 194200 | 365220 | 2nd Tranche | 58740 | 423960 | 365220 | 58740 | 100% | 100% | 30.25% | 70.66% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-20 | 2008-05-30 | n/a | 131 | 92 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Pangdan | 084808042 | Individual CRs | 1 | 980900 | 901030 | 79870 | 720824 | 1st Tranche | 83709 | 804533 | 720824 | 83709 | 100% | 100% | 104.8% | 82.02% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-04 | 2009-08-31 | n/a | 119 | 72 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Rawis | 084808043 | Construction of Drainage System | 1 | 822620 | 548084 | 274536 | 493276 | 2nd Tranche | 279860 | 773136 | 493276 | 279860 | 100% | 100% | 101.9% | 93.98% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-28 | 2007-11-08 | no data | 72 | 681 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Rawis | 084808043 | Barangay Health Station | 1 | 767000 | 525406 | 241594 | 472865.4 | 2nd Tranche | 252423 | 725288.4 | 472865.4 | 252423 | 100% | 100% | 104.5% | 94.56% | 100% | no data | no data | 2008-11-03 | 2009-03-31 | n/a | 148 | 773 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Rawis | 084808043 | Concrete Pathway | 1 | 564000 | 357730 | 206270 | 286184 | 1st Tranche | 220162 | 506346 | 286184 | 220162 | 100% | 100% | 106.7% | 89.78% | 100% | 2009-01-28 | 2009-02-27 | 2009-04-27 | 2009-06-30 | no data | 64 | 775 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Rombang | 084808044 | Construction of Water System (L2) | 1 | 347700 | 241060 | 106640 | 216954 | 2nd Tranche | 109520 | 326474 | 216954 | 109520 | 100% | 100% | 102.7% | 93.9% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-27 | 2008-04-13 | n/a | 230 | 189 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Rombang | 084808044 | Construction of School Building (1Rm) | 1 | 782000 | 547400 | 234600 | 492660 | 2nd Tranche | 237150 | 729810 | 492660 | 237150 | 100% | 100% | 101.1% | 93.33% | 100% | no data | no data | 2008-10-13 | 2008-12-31 | n/a | 79 | 155 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | San Antonio | 084808045 | Construction of Day Care Center | 1 | 450000 | 315000 | 135000 | 315000 | 3rd Tranche | 108913.5 | 423913.5 | 315000 | 108913.5 | 100% | 100% | 80.68% | 94.2% | 100% | 2007-02-21 | 2007-04-10 | 2007-12-03 | 2008-09-30 | no data | 302 | 135 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | San Antonio | 084808045 | Drainage Canal | 1 | 1201000 | 1075786 | 125214 | 860628.8 | 1st Tranche | 84708 | 945336.8 | 860628.8 | 84708 | 100% | 100% | 67.65% | 78.71% | 100% | 2009-01-28 | 2009-02-27 | 2009-07-06 | 2009-08-31 | n/a | 56 | 135 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | San Miguel Heights | 084808046 | Construction of Drainage System | 1 | 399800 | 270900 | 128900 | 243810 | 2nd Tranche | 121589 | 365399 | 243810 | 121589 | 100% | 100% | 94.33% | 91.4% | 100% | 2007-02-21 | 2007-04-10 | 2007-10-09 | 2008-08-30 | no data | 326 | 549 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Sangcol | 084808048 | Mud Crab Culture | 1 | 721000 | 504700 | 216300 | 429264 | 2nd Tranche | 78810 | 508074 | 429264 | 78810 | 100% | 100% | 36.44% | 70.47% | 100% | 2007-02-21 | 2007-04-10 | 2008-07-28 | 2008-11-30 | n/a | 125 | 97 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Sibunot | 084808049 | Farm to Market Road | 1 | 1223000 | 503299 | 719701 | 452969.1 | 2nd Tranche | 691350.83 | 1144319.93 | 452969.1 | 691350.83 | 100% | 100% | 96.06% | 93.57% | 100% | 2007-02-21 | 2007-04-10 | 2008-03-15 | 2008-06-15 | no data | 92 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Sibunot | 084808049 | Bridge | 1 | 824000 | 576800 | 247200 | 519120 | 2nd Tranche | 263383 | 782503 | 519120 | 263383 | 100% | 100% | 106.5% | 94.96% | 100% | no data | no data | 2008-11-11 | 2009-02-11 | n/a | 92 | 90 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Sibunot | 084808049 | Day Care Center | 1 | 738000 | 658130 | 79870 | 526504 | 1st Tranche | 98622 | 625126 | 526504 | 98622 | 100% | 100% | 123.5% | 84.71% | 100% | 2009-01-28 | 2009-02-27 | 2009-08-03 | 2009-08-31 | n/a | 28 | 83 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Simora | 084808050 | Construction of Day Care Center | 1 | 460700 | 318400 | 142300 | 286560 | 2nd Tranche | 140200 | 426760 | 286560 | 140200 | 100% | 100% | 98.52% | 92.63% | 100% | 2007-02-21 | 2007-04-10 | 2008-03-25 | 2008-06-30 | no data | 97 | 116 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Simora | 084808050 | Drainage Canal | 1 | 558000 | 479630 | 78370 | 383704 | 1st Tranche | 70250 | 453954 | 383704 | 70250 | 100% | 100% | 89.64% | 81.35% | 100% | 2009-01-28 | 2009-02-27 | 2009-04-27 | 2009-06-30 | no data | 64 | 167 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Calintaan Pob. (Sto. Niño) | 084808018 | Drainage Canal | 1 | 597000 | 417900 | 179100 | 376110 | 2nd Tranche | 196195 | 572305 | 376110 | 196195 | 100% | 100% | 109.5% | 95.86% | 100% | no data | no data | 2008-11-11 | 2009-02-05 | n/a | 86 | 272 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Suba | 084808052 | Construction of School Building (1 Rm) | 1 | 550000 | 385000 | 165000 | 346500 | 2nd Tranche | 134850 | 481350 | 346500 | 134850 | 100% | 100% | 81.73% | 87.52% | 100% | 2007-02-21 | 2007-04-10 | 2007-09-14 | 2008-05-23 | n/a | 252 | 122 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Talisay | 084808061 | Concrete Pathway | 1 | 222000 | 151100 | 70900 | 120880 | 1st Tranche | 76501 | 197381 | 120880 | 76501 | 100% | 100% | 107.9% | 88.91% | 100% | 2007-02-21 | 2007-04-10 | 2007-08-27 | 2007-10-08 | no data | 42 | 291 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Talisay | 084808061 | River Control | 1 | 1544200 | 1080940 | 463260 | 1080940 | 3rd Tranche | 475224 | 1556164 | 1080940 | 475224 | 100% | 100% | 102.6% | 100.8% | 100% | no data | no data | 2008-11-19 | 2009-03-31 | n/a | 132 | 296 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Talisay | 084808061 | Day Care Center | 1 | 700000 | 601270 | 98730 | 481016 | 2nd Tranche | 122443 | 603459 | 481016 | 122443 | 100% | 100% | 124% | 86.21% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-04 | 2009-06-30 | no data | 57 | 291 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tan-awan | 084808054 | Construction of School Building (1 Rm) | 1 | 548000 | 383600 | 164400 | 383600 | 3rd Tranche | 105840 | 489440 | 383600 | 105840 | 100% | 100% | 64.38% | 89.31% | 100% | 2007-02-21 | 2007-04-10 | 2008-01-20 | 2008-05-30 | n/a | 131 | 133 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tan-awan | 084808054 | Drainage Canal | 1 | 644200 | 566692 | 77508 | 453353.6 | 1st Tranche | 76382 | 529735.6 | 453353.6 | 76382 | 100% | 100% | 98.55% | 82.23% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-18 | 2009-06-30 | no data | 43 | 142 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tinoblan | 084808056 | Construction of Water System (L2) | 1 | 464000 | 323500 | 140500 | 291150 | 2nd Tranche | 153240 | 444390 | 291150 | 153240 | 100% | 100% | 109.1% | 95.77% | 100% | 2007-02-21 | 2007-04-10 | 2007-09-01 | 2008-05-30 | n/a | 272 | 99 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tinoblan | 084808056 | Footbridge | 1 | 1147200 | 803040 | 344160 | 722736 | 2nd Tranche | 382614 | 1105350 | 722736 | 382614 | 100% | 100% | 111.2% | 96.35% | 100% | no data | no data | 2008-12-15 | 2009-04-30 | n/a | 136 | 87 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Tumaguinting | 084808057 | Drainage Canal | 1 | 510800 | 357560 | 153240 | 286048 | 1st Tranche | 536726 | 430506 | 286048 | 144458 | 100% | 26.91% | 350.3% | 84.28% | 100% | no data | no data | 2009-01-12 | 2009-02-28 | n/a | 47 | 193 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Vigo | 084808058 | Construction of Day Care Center | 1 | 464000 | 324800 | 139200 | 320082.55 | 3rd Tranche | 157928.5 | 478011.05 | 320082.55 | 157928.5 | 100% | 100% | 113.5% | 103% | 100% | 2007-02-21 | 2007-04-10 | 2007-10-15 | 2008-06-23 | n/a | 252 | 421 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Yabyaban | 084808059 | Construction of Water System (L1) | 1 | 289000 | 199650 | 89350 | 179685 | 2nd Tranche | 103634 | 283319 | 179685 | 103634 | 100% | 100% | 116% | 98.03% | 100% | 2007-02-21 | 2007-04-10 | 2008-04-15 | 2008-09-25 | no data | 163 | 113 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Yabyaban | 084808059 | Construction of Footbridge | 1 | 241000 | 155414 | 85586 | 124331.2 | 1st Tranche | 84584 | 208915.2 | 124331.2 | 84584 | 100% | 100% | 98.83% | 86.69% | 100% | no data | no data | 2009-03-26 | 2009-05-30 | n/a | 65 | 121 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Yapas | 084808060 | Construction of Drainage System | 1 | 315000 | 218400 | 96600 | 196560 | 2nd Tranche | 114736 | 311296 | 196560 | 114736 | 100% | 100% | 118.8% | 98.82% | 100% | 2007-02-21 | 2007-04-10 | 2007-10-30 | 2008-04-30 | n/a | 183 | 95 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Yapas | 084808060 | Water Supply System | 1 | 466500 | 326550 | 139950 | 293895 | 2nd Tranche | 142619.45 | 436514.45 | 293895 | 142619.45 | 100% | 100% | 101.9% | 93.57% | 100% | no data | no data | 2008-11-10 | 2008-12-15 | n/a | 35 | 82 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Laoang | 084808 | Yapas | 084808060 | 2 Classroom School Building | 1 | 1195000 | 1081588 | 113412 | 865270.4 | 1st Tranche | 134167 | 999437.4 | 865270.4 | 134167 | 100% | 100% | 118.3% | 83.63% | 100% | 2009-01-28 | 2009-02-27 | 2009-05-04 | 2009-08-31 | n/a | 119 | 82 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Balugo | 084810001 | River Landing | 1 | 399047 | 273439.95 | 125607.05 | 218751.96 | 1st Tranche | 124380 | 343131.96 | 218751.96 | 124380 | 100% | 100% | 99.02% | 85.99% | 100% | 2007-02-21 | 2007-05-03 | 2007-08-19 | 2007-09-17 | no data | 29 | 80 | 5 brgys in Las Navas waived for non-delivery of LCC from the Governor | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Bugay | 084810002 | Footbridge | 1 | 638340 | 433029 | 205311 | 389226.1 | 2nd Tranche | 197178.32 | 586404.42 | 389226.1 | 197178.32 | 100% | 100% | 96.04% | 91.86% | 100% | 2007-02-21 | 2007-05-03 | 2008-03-27 | 2009-06-30 | n/a | 460 | 103 | Geracdo excluded | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Bugtosan | 084810003 | River Landing | 1 | 189394 | 145558 | 43836 | 116446.4 | 1st Tranche | 30427 | 146873.4 | 116446.4 | 30427 | 100% | 100% | 69.41% | 77.55% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-18 | 2009-08-31 | n/a | 74 | 74 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Bukid | 084810004 | Footbridge | 1 | 522906.95 | 362670.95 | 160236 | 290136.76 | 1st Tranche | 148838.75 | 438975.51 | 290136.76 | 148838.75 | 100% | 100% | 92.89% | 83.95% | 100% | 2007-02-21 | 2007-05-03 | 2007-10-03 | 2008-03-26 | no data | 175 | 189 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Bukid | 084810004 | Construction of Drainage Canal | 1 | 1480845 | 1138080 | 342765 | 796656 | 1st Tranche | 100000 | 896656 | 796656 | 100000 | 100% | 100% | 29.17% | 60.55% | 100% | 2008-04-07 | 2008-11-26 | 2009-04-13 | 2009-08-31 | n/a | 140 | 190 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Bulao | 084810005 | Drainage Canal | 1 | 1560006.1 | 1092004 | 468002.1 | 1092004 | 2nd Tranche | 310355 | 1402359 | 1092004 | 310355 | 100% | 100% | 66.31% | 89.89% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-15 | 2009-04-30 | n/a | 350 | 196 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Caputoan | 084810006 | Rice Mill | 1 | 340278 | 238713 | 101565 | 190970.4 | 1st Tranche | 90852 | 281822.4 | 190970.4 | 90852 | 100% | 100% | 89.45% | 82.82% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-08-31 | no data | 28 | 66 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Caputoan | 084810006 | Water System | 1 | 497704.75 | 347199 | 150505.75 | 347199 | 1st Tranche | 125368 | 472567 | 347199 | 125368 | 100% | 100% | 83.3% | 94.95% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-10 | 2009-04-30 | n/a | 355 | 49 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Catoto-ogan | 084810007 | 1 Room School Building | 1 | 735999 | 565646 | 170353 | 452516.8 | 1st Tranche | 97961.4 | 550478.2 | 452516.8 | 97961.4 | 100% | 100% | 57.5% | 74.79% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-22 | 2009-08-31 | no data | 70 | 54 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Dapdap | 084810009 | Health Center | 1 | 774621.92 | 506098.47 | 268523.45 | 506098.47 | 2nd Tranche | 182820 | 688918.47 | 506098.47 | 182820 | 100% | 100% | 68.08% | 88.94% | 100% | 2007-02-21 | 2007-05-03 | 2008-09-04 | 2009-09-22 | n/a | 383 | 296 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Dapdap | 084810009 | Drainage System | 1 | 974293 | 748786 | 225507 | 599028.8 | 1st Tranche | 127579.45 | 726608.25 | 599028.8 | 127579.45 | 100% | 100% | 56.57% | 74.58% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-08-31 | no data | 28 | 330 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Del Pilar | 084810010 | River Landing | 1 | 309415 | 216172.75 | 93242.25 | 172938.2 | 1st Tranche | 85650 | 272588.2 | 172938.2 | 99650 | 100% | 116.3% | 91.86% | 88.1% | 100% | 2007-02-21 | 2007-05-03 | 2007-09-20 | 2008-05-22 | no data | 245 | 204 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Del Pilar | 084810010 | Construction of Concrete Pathway | 1 | 561072 | 431208 | 129864 | 344966.4 | 1st Tranche | 76564.6 | 421531 | 344966.4 | 76564.6 | 100% | 100% | 58.96% | 75.13% | 100% | 2008-04-07 | 2008-11-26 | 2009-05-03 | 2009-05-30 | no data | 27 | 204 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Dolores | 084810011 | Community Ricemill | 1 | 267871.8 | 180691 | 87180.8 | 162621.9 | 2nd Tranche | 67495 | 230116.9 | 162621.9 | 67495 | 100% | 100% | 77.42% | 85.91% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-18 | 2008-06-10 | n/a | 23 | 28 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Dolores | 084810011 | Construction of Concrete Pathway | 1 | 1161382 | 785852 | 375530 | 707266.8 | 1st Tranche | 194700 | 901966.8 | 707266.8 | 194700 | 100% | 100% | 51.85% | 77.66% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-05-31 | n/a | -64 | 28 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | F Robis(Geracdo) | 084810014 | Flood Control | 1 | 1433204 | 1140328 | 292876 | 1026295.2 | 1st Tranche | 212100 | 1238395.2 | 1026295.2 | 212100 | 100% | 100% | 72.42% | 86.41% | 100% | 2008-04-07 | 2008-11-26 | 2009-09-02 | 2009-08-31 | n/a | -2 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Geguinta | 084810013 | Footpath | 1 | 741300 | 502725 | 238575 | 483996.31 | 3rd Tranche | 227086 | 711082.31 | 483996.31 | 227086 | 100% | 100% | 95.18% | 95.92% | 100% | 2007-02-21 | 2007-05-03 | 2007-11-25 | 2008-05-31 | n/a | 188 | 108 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Guyo | 084810015 | School Building | 1 | 722204.5 | 505543 | 216661.5 | 404434.8 | 1st Tranche | 212504.37 | 616939.17 | 404434.8 | 212504.37 | 100% | 100% | 98.08% | 85.42% | 100% | 2007-02-21 | 2007-05-03 | 2007-08-30 | 2008-05-30 | n/a | 274 | 73 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Guyo | 084810015 | Day Care Center | 1 | 827594 | 636042 | 191552 | 508833.6 | 1st Tranche | 75000 | 583833.6 | 508833.6 | 75000 | 100% | 100% | 39.15% | 70.55% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-22 | 2009-08-31 | n/a | 70 | 58 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | H Jolejole | 084810016 | 2 Units 1 Classroom School Building | 1 | 2366719 | 1714866 | 651853 | 1371892.8 | 1st Tranche | 723564.4 | 2095457.2 | 1371892.8 | 723564.4 | 100% | 100% | 111% | 88.54% | 100% | 2008-04-07 | 2008-11-26 | 2009-03-15 | 2009-05-31 | n/a | 77 | 395 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | L. Empon | 084810019 | Water System & Toilet | 1 | 506108.7 | 354276 | 151832.7 | 247993.2 | 1st Tranche | 115310 | 363303.2 | 247993.2 | 115310 | 100% | 100% | 75.95% | 71.78% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-15 | 2008-06-25 | n/a | 41 | 69 | completed as built | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Lakandula | 084810020 | Water System | 1 | 550421.3 | 384678 | 165743.3 | 269734.96 | 1st Tranche | 22500 | 292234.96 | 269734.96 | 22500 | 100% | 100% | 13.58% | 53.09% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-20 | 2008-12-20 | n/a | 214 | 50 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Lumala-og | 084810021 | School Building | 1 | 734549.5 | 513317 | 221232.5 | 484097.4 | 3rd Tranche | 180538.5 | 664635.9 | 484097.4 | 180538.5 | 100% | 100% | 81.61% | 90.48% | 100% | 2007-02-21 | 2007-05-03 | 2008-02-11 | 2008-09-27 | no data | 229 | 99 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Lourdes | 084810022 | Footpath | 1 | 1153905 | 803309.25 | 350595.75 | 803309.25 | 2nd Tranche | 286637.5 | 1089946.75 | 803309.25 | 286637.5 | 100% | 100% | 81.76% | 94.46% | 100% | 2007-02-21 | 2007-05-03 | 2007-08-16 | 2008-08-30 | no data | 380 | 168 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Lumala-og | 084810021 | Footbridge | 1 | 307948 | 236672 | 71276 | 189337.6 | 1st Tranche | 35084 | 224421.6 | 189337.6 | 35084 | 100% | 100% | 49.22% | 72.88% | 100% | 2008-04-07 | 2008-11-26 | 2009-09-11 | 2009-06-30 | no data | -73 | 99 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Mabini | 084810023 | River Landing | 1 | 162448 | 124849 | 37599 | 99879.2 | 1st Tranche | 37100 | 136979.2 | 99879.2 | 37100 | 100% | 100% | 98.67% | 84.32% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-06-30 | no data | -34 | 12 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Magsaysay | 084810025 | Barangay Health Station | 1 | 950207 | 665144 | 285063 | 532115.2 | 1st Tranche | 214424.8 | 746540 | 532115.2 | 214424.8 | 100% | 100% | 75.22% | 78.57% | 100% | 2008-04-07 | 2008-11-26 | 2009-09-11 | 2009-10-31 | n/a | 50 | 115 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Matelarag | 084810026 | Footpath | 1 | 1092874 | 743816.75 | 349057.25 | 667672.54 | 2nd Tranche | 202727.26 | 870399.8 | 667672.54 | 202727.26 | 100% | 100% | 58.08% | 79.64% | 100% | 2007-02-21 | 2007-05-03 | 2008-04-15 | 2009-03-31 | n/a | 350 | 63 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Paco | 084810028 | Water System & Toilet | 1 | 514640 | 360248 | 154392 | 360248 | 1st Tranche | 133306 | 493554 | 360248 | 133306 | 100% | 100% | 86.34% | 95.9% | 100% | 2007-02-21 | 2007-05-03 | 2008-04-23 | 2008-08-23 | no data | 122 | 63 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Palanas | 084810029 | Footpath | 1 | 1054746 | 687099.1 | 367646.9 | 687099.1 | 3rd Tranche | 284891.9 | 971991 | 687099.1 | 284891.9 | 100% | 100% | 77.49% | 92.15% | 100% | 2007-02-21 | 2007-05-03 | 2007-10-01 | 2009-04-28 | n/a | 575 | 43 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Palanas | 084810029 | Construction of Concrete Pathway | 1 | 1196946 | 922311 | 274635 | 737848.8 | 1st Tranche | 127322.4 | 865171.2 | 737848.8 | 127322.4 | 100% | 100% | 46.36% | 72.28% | 100% | 2008-04-07 | 2008-11-26 | 2009-03-15 | 2009-09-30 | no data | 199 | 43 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Perez | 084810030 | Water System Level 2 | 1 | 511572 | 393164 | 118408 | 314531.2 | 1st Tranche | 39336.8 | 353868 | 314531.2 | 39336.8 | 100% | 100% | 33.22% | 69.17% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-09-30 | no data | 58 | 83 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Poponton | 084810031 | River Landing | 1 | 210537 | 161807 | 48730 | 129444.8 | 1st Tranche | 27150 | 156594.8 | 129444.8 | 27150 | 100% | 100% | 55.72% | 74.38% | 100% | 2008-04-07 | 2008-11-26 | 2009-09-02 | 2009-10-24 | n/a | 52 | 42 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Quezon | 084810032 | 1 Room School Building | 1 | 766307 | 588940 | 177367 | 471152 | 1st Tranche | 69936.8 | 541088.8 | 471152 | 69936.8 | 100% | 100% | 39.43% | 70.61% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-22 | 2009-09-30 | no data | 100 | 35 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Quirino District | 084810034 | Construction of Drainage Canal | 1 | 838000 | 555269 | 282731 | 499734.9 | 1st Tranche | 59375 | 559109.9 | 499734.9 | 59375 | 100% | 100% | 21% | 66.72% | 100% | 2008-04-07 | 2008-11-26 | 2009-04-20 | 2009-05-31 | no data | 41 | 421 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Roxas | 084810037 | Footbridge | 1 | 772960 | 525816 | 247144 | 525816 | 3rd Tranche | 164255 | 690071 | 525816 | 164255 | 100% | 100% | 66.46% | 89.28% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-20 | 2009-03-31 | n/a | 315 | 110 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Roxas | 084810037 | Construction of Concrete Pathway | 1 | 1294967 | 995293 | 299674 | 796234.4 | 1st Tranche | 105950 | 902184.4 | 796234.4 | 105950 | 100% | 100% | 35.36% | 69.67% | 100% | 2008-04-07 | 2008-11-26 | 2009-05-18 | 2009-06-30 | no data | 43 | 110 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Andres | 084810040 | Drainage System | 1 | 640221 | 465761 | 174460 | 372608.8 | 1st Tranche | 70800 | 443408.8 | 372608.8 | 70800 | 100% | 100% | 40.58% | 69.26% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-09-30 | no data | 58 | 92 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Fernando | 084810042 | Footpath | 1 | 215492.95 | 150455 | 65037.95 | 135409 | 2nd Tranche | 65829.2 | 201238.2 | 135409 | 65829.2 | 100% | 100% | 101.2% | 93.39% | 100% | 2007-02-21 | 2007-05-03 | 2008-02-05 | 2008-05-25 | n/a | 110 | 184 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Fernando | 084810042 | 1 Room School Building | 1 | 665150 | 511197 | 153953 | 408957.6 | 1st Tranche | 74050 | 483007.6 | 408957.6 | 74050 | 100% | 100% | 48.1% | 72.62% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-22 | 2009-09-30 | no data | 100 | 184 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Isidro | 084810045 | Footbridge | 1 | 934034.25 | 636929 | 297105.25 | 636929 | 2nd Tranche | 277261.5 | 914190.5 | 636929 | 277261.5 | 100% | 100% | 93.32% | 97.88% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-20 | 2009-04-30 | n/a | 345 | 335 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Isidro | 084810045 | Footbridge | 1 | 712246 | 547391 | 164855 | 383173.7 | 1st Tranche | 98600 | 481773.7 | 383173.7 | 98600 | 100% | 100% | 59.81% | 67.64% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-01 | 2009-09-30 | no data | 121 | 415 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Jorge | 084810046 | Construction of Concrete Pathway w/ Footbridge | 1 | 756113 | 581105 | 175008 | 558428 | 1st Tranche | 100000 | 658428 | 558428 | 100000 | 100% | 100% | 57.14% | 87.08% | 100% | 2008-04-07 | 2008-11-26 | 2009-04-20 | 2009-06-01 | no data | 42 | 42 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Jose | 084810047 | 1 Room School Building | 1 | 734237 | 564292 | 169945 | 451433.6 | 1st Tranche | 67347.2 | 518780.8 | 451433.6 | 67347.2 | 100% | 100% | 39.63% | 70.66% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-09-30 | n/a | 58 | 44 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | San Miguel | 084810048 | Water System Level 1 | 1 | 521534 | 400821 | 120713 | 320656.8 | 1st Tranche | 38986.4 | 359643.2 | 320656.8 | 38986.4 | 100% | 100% | 32.3% | 68.96% | 100% | 2008-04-07 | 2008-11-26 | 2009-08-03 | 2009-09-30 | no data | 58 | 228 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Sto Tomas | 084810049 | Construction of Concrete Pathway | 1 | 924173 | 710266 | 213907 | 639239.4 | 1st Tranche | 40000 | 679239.4 | 639239.4 | 40000 | 100% | 100% | 18.7% | 73.5% | 100% | 2008-04-07 | 2008-11-26 | 2009-04-13 | 2009-05-31 | no data | 48 | 47 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Tagab-iran | 084810050 | Construction of Concrete Pathway | 1 | 1481746 | 1138785 | 342961 | 911028 | 1st Tranche | 126559.2 | 1037587.2 | 911028 | 126559.2 | 100% | 100% | 36.9% | 70.02% | 100% | 2008-04-07 | 2008-11-26 | 2009-04-29 | 2009-06-30 | no data | 62 | 248 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Tagan-ayan | 084810051 | Water System | 1 | 528704.75 | 366499 | 162205.75 | 329849.1 | 2nd Tranche | 148291.5 | 478140.6 | 329849.1 | 148291.5 | 100% | 100% | 91.42% | 90.44% | 100% | 2007-02-21 | 2007-05-03 | 2008-05-16 | 2008-06-30 | n/a | 45 | 54 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Tagan-ayan | 084810051 | Construction of Concrete Pathway | 1 | 979890 | 752613 | 227277 | 677351.7 | 1st Tranche | 67200 | 744551.7 | 677351.7 | 67200 | 100% | 100% | 29.57% | 75.98% | 100% | 2008-04-07 | 2008-11-26 | 2009-03-23 | 2009-05-31 | no data | 69 | 54 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Las Navas | 084810 | Taylor | 084810052 | Drainage System | 1 | 962331 | 739604 | 222727 | 591683.2 | 1st Tranche | 99708 | 691391.2 | 591683.2 | 99708 | 100% | 100% | 44.77% | 71.85% | 100% | 2008-04-07 | 2008-11-26 | 2009-06-17 | 2009-08-31 | n/a | 75 | 134 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Bagasbas | 084813001 | Construction of School Building ( 3 Rm) | 1 | 1396209 | 963400 | 432809 | 963400 | 3rd Tranche | 433809 | 1397209 | 963400 | 433809 | 100% | 100% | 100.2% | 100.1% | 100% | no data | no data | 2008-06-24 | 2008-08-30 | n/a | 67 | 212 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Bugko | 084813002 | Construction of School Building ( _ Rm) | 1 | 1040933 | 728317 | 312616 | 655485.3 | 2nd Tranche | 313616 | 969101.3 | 655485.3 | 313616 | 100% | 100% | 100.3% | 93.1% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-09 | 2007-12-17 | no data | 130 | 574 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Cablangan | 084813003 | Construction of Water System (L2) | 1 | 442479 | 317115 | 125364 | 255149.1 | 2nd Tranche | 125364 | 380513.1 | 255149.1 | 125364 | 100% | 100% | 100% | 86% | 100% | 2007-02-20 | 2007-04-16 | 2007-09-26 | 2008-03-20 | no data | 176 | 231 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Cablangan | 084813003 | 3 Classrom School Building | 1 | 1454561 | 1184241.18 | 270319.82 | 1065817.06 | 2nd Tranche | 254080.82 | 1319897.88 | 1065817.06 | 254080.82 | 100% | 100% | 93.99% | 90.74% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-25 | 2009-06-20 | no data | 87 | 253 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Cagmanaba | 084813004 | 1 Classroom School Building | 1 | 897536 | 734710.91 | 162825.09 | 707460.86 | 2nd Tranche | 149825.09 | 857285.95 | 707460.86 | 149825.09 | 100% | 100% | 92.02% | 95.52% | 100% | 2008-11-24 | 2009-01-17 | 2009-04-14 | 2009-05-31 | no data | 47 | 38 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Cahicsan | 084813005 | River Control | 1 | 902950 | 822245 | 80705 | 657796 | 1st Tranche | 81705 | 739501 | 657796 | 81705 | 100% | 100% | 101.2% | 81.9% | 100% | no data | no data | 2008-10-16 | 2008-12-10 | n/a | 55 | 159 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Chitongco | 084813006 | Flood Control | 1 | 1085090 | 757800 | 327290 | 757800 | 3rd Tranche | 328290 | 1086090 | 757800 | 328290 | 100% | 100% | 100.3% | 100.1% | 100% | no data | no data | 2008-08-04 | 2008-10-21 | n/a | 78 | 394 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Chitongco | 084813006 | Road Regravelling with Grouted Riprap | 1 | 1360319 | 1087625.91 | 272693.09 | 978863.32 | 2nd Tranche | 241588.3 | 1220451.62 | 978863.32 | 241588.3 | 100% | 100% | 88.59% | 89.72% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-24 | 2009-06-08 | no data | 76 | 489 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | De Maria | 084813007 | Construction of Water System | 1 | 309401 | 229401 | 80000 | 183520.8 | 1st Tranche | 80000 | 263520.8 | 183520.8 | 80000 | 100% | 100% | 100% | 85.17% | 100% | 2007-02-20 | 2007-04-16 | 2007-10-02 | 2008-04-16 | no data | 197 | 71 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Doña Lucia | 084813008 | Construction of School Building ( _ Rm) | 1 | 1314423 | 920096 | 394327 | 828086.4 | 2nd Tranche | 395327 | 1223413.4 | 828086.4 | 395327 | 100% | 100% | 100.3% | 93.08% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-01 | 2008-03-25 | no data | 237 | 123 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Eco | 084813009 | Drainage Canal | 1 | 1418553 | 992758 | 425795 | 992758 | 3rd Tranche | 426795 | 1419553 | 992758 | 426795 | 100% | 100% | 100.2% | 100.1% | 100% | no data | no data | 2008-07-19 | 2008-10-19 | n/a | 92 | 469 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Eco | 084813009 | Construction of Seawall | 1 | 1194404 | 972276.45 | 222127.55 | 972276.45 | 2nd Tranche | 220454.71 | 1192731.16 | 972276.45 | 220454.71 | 100% | 100% | 99.25% | 99.86% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-23 | 2009-06-07 | no data | 76 | 428 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Flormina | 084813010 | Construction of Water System | 1 | 486232 | 337131 | 149101 | 269704.8 | 1st Tranche | 150101 | 419805.8 | 269704.8 | 150101 | 100% | 100% | 100.7% | 86.34% | 100% | no data | no data | 2008-07-07 | 2008-08-09 | n/a | 33 | 95 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Flormina | 084813010 | 2 Classroom School Building | 1 | 1255126.01 | 1044559.46 | 210566.55 | 1044559.46 | 3rd Tranche | 209799.11 | 1254358.57 | 1044559.46 | 209799.11 | 100% | 100% | 99.64% | 99.94% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-26 | 2009-06-20 | no data | 86 | 210 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Hinabangan | 084813011 | Construction of Day Care Center | 1 | 725758 | 505810 | 219948 | 455229 | 2nd Tranche | 220948 | 676177 | 455229 | 220948 | 100% | 100% | 100.5% | 93.17% | 100% | no data | no data | 2008-07-28 | 2008-10-03 | n/a | 67 | 64 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Hinabangan | 084813011 | Covered Concrete Canal | 1 | 690746 | 559057.91 | 131688.09 | 503152.12 | 2nd Tranche | 158370.91 | 661523.03 | 503152.12 | 158370.91 | 100% | 100% | 120.3% | 95.77% | 100% | 2008-11-24 | 2009-01-17 | 2009-04-15 | 2009-06-20 | no data | 66 | 91 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Imelda | 084813012 | Construction of School Building (2 Rm) | 1 | 992415 | 690800 | 301615 | 690800 | 3rd Tranche | 302615 | 993415 | 690800 | 302615 | 100% | 100% | 100.3% | 100.1% | 100% | no data | no data | 2008-07-21 | 2008-10-05 | n/a | 76 | 592 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | La Trinidad | 084813013 | Construction of Footbridge | 1 | 421142 | 293364 | 127778 | 260646.4 | 2nd Tranche | 117142 | 377788.4 | 260646.4 | 117142 | 100% | 100% | 91.68% | 89.71% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-19 | 2008-02-08 | no data | 204 | 120 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | La Trinidad | 084813013 | 2 Classroom School Building | 1 | 1189888 | 997758.33 | 192129.67 | 997281.62 | 2nd Tranche | 189149.67 | 1186431.29 | 997281.62 | 189149.67 | 100% | 100% | 98.45% | 99.71% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-23 | 2009-06-30 | no data | 99 | 104 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Makiwalo | 084813014 | Construction of School Building ( _ Rm) | 1 | 1044728 | 813820 | 230908 | 651056 | 1st Tranche | 230908 | 882289.96 | 651056 | 231233.96 | 100% | 100.1% | 100% | 84.45% | 100% | 2007-02-20 | 2007-04-16 | 2007-09-18 | 2008-01-25 | no data | 129 | 807 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Makiwalo | 084813014 | Fishport | 1 | 600616 | 462100.25 | 138515.75 | 415890.23 | 2nd Tranche | 156774.44 | 572664.67 | 415890.23 | 156774.44 | 100% | 100% | 113.2% | 95.35% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-16 | 2009-05-15 | no data | 60 | 964 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Mirador | 084813015 | Construction of Solar Dryer | 1 | 417663 | 350123 | 67540 | 280098.4 | 1st Tranche | 68540 | 348638.4 | 280098.4 | 68540 | 100% | 100% | 101.5% | 83.47% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-23 | 2007-09-18 | no data | 57 | 187 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Nenita | 084813016 | Construction of Water System (L2) | 1 | 645137 | 451595 | 193542 | 446457.78 | 2nd Tranche | 193542 | 639999.78 | 446457.78 | 193542 | 100% | 100% | 100% | 99.2% | 100% | 2007-02-20 | 2007-04-16 | 2007-12-12 | 2008-06-24 | n/a | 195 | 431 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Roxas | 084813017 | Construction of Drainage System | 1 | 975606 | 668924 | 306682 | 602031.6 | 2nd Tranche | 308177.05 | 967341.34 | 602031.6 | 365309.74 | 100% | 118.5% | 100.5% | 99.15% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-23 | 2007-10-31 | no data | 100 | 160 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Roxas | 084813017 | Construction of School Building (2 Rm) | 1 | 992405 | 917985 | 74420 | 917985 | 3rd Tranche | 75420 | 993405 | 917985 | 75420 | 100% | 100% | 101.3% | 100.1% | 100% | no data | no data | 2008-07-21 | 2008-08-30 | n/a | 40 | 216 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Roxas | 084813017 | Road Regravelling witn Grouted Riprap | 1 | 294999.99 | 191629.28 | 103370.71 | 168658.28 | 2nd Tranche | 43524 | 212182.28 | 168658.28 | 43524 | 100% | 100% | 42.1% | 71.93% | 100% | 2008-11-24 | 2009-01-17 | 2009-03-23 | 2009-04-21 | n/a | 29 | 208 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Agustin | 084813018 | Construction of Day Care Center | 1 | 604181 | 422371 | 181810 | 380133.9 | 2nd Tranche | 182810 | 562943.9 | 380133.9 | 182810 | 100% | 100% | 100.6% | 93.17% | 100% | no data | no data | 2008-08-04 | 2008-09-27 | n/a | 54 | 136 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Antonio | 084813019 | Construction of School Building ( _ Rm) | 1 | 1105782 | 774047 | 331735 | 696642.3 | 2nd Tranche | 331735 | 1028377.3 | 696642.3 | 331735 | 100% | 100% | 100% | 93% | 100% | 2007-02-20 | 2007-04-16 | 2007-09-17 | 2008-04-24 | n/a | 220 | 78 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Isidro | 084813020 | Construction of Water System | 1 | 282260 | 227720 | 54540 | 182176 | 1st Tranche | 54540 | 236716 | 182176 | 54540 | 100% | 100% | 100% | 83.86% | 100% | 2007-02-20 | 2007-04-16 | 2007-10-02 | 2008-02-09 | no data | 130 | 119 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Jose | 084813021 | Construction of Water System (L2) | 1 | 357335 | 250134 | 107201 | 214581.44 | 2nd Tranche | 107201 | 321782.44 | 214581.44 | 107201 | 100% | 100% | 100% | 90.05% | 100% | 2007-02-20 | 2007-04-16 | 2008-01-25 | 2008-05-25 | n/a | 121 | 98 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Jose | 084813021 | 2 Classroom School Building | 1 | 1319706 | 1047289.68 | 272416.32 | 942560.17 | 2nd Tranche | 206153.96 | 1148714.13 | 942560.17 | 206153.96 | 100% | 100% | 75.68% | 87.04% | 100% | 2008-11-24 | 2009-01-17 | 2009-04-27 | 2009-06-30 | no data | 64 | 140 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | San Juan | 084813022 | Farm to Market Road | 1 | 1146680 | 789700 | 356980 | 789470 | 3rd Tranche | 346980 | 1136450 | 789470 | 346980 | 100% | 100% | 97.2% | 99.11% | 100% | no data | no data | 2008-07-24 | 2008-11-22 | n/a | 121 | 47 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Sta. Catalina | 084813023 | Construction of Water System | 1 | 197970 | 138579 | 59391 | 99668 | 1st Tranche | 59391 | 159059 | 99668 | 59391 | 100% | 100% | 100% | 80.35% | 100% | 2007-02-20 | 2007-04-16 | 2007-11-15 | 2008-02-15 | no data | 92 | 67 |  | 1
VIII | 08 | Northern Samar | 0848 | Mondragon | 084813 | Talolora | 084813024 | Construction of Footbridge | 1 | 1481093 | 1036765 | 444328 | 1036765 | 3rd Tranche | 444328 | 1481093 | 1036765 | 444328 | 100% | 100% | 100% | 100% | 100% | 2007-02-20 | 2007-04-16 | 2008-02-25 | 2008-08-25 | no data | 182 | 143 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Cababto-an | 084815002 | Const of Water system L2 | 1 | 332015.34 | 232411 | 99604.34 | 185928.8 | 1st Tranche | 97108.44 | 283037.24 | 185928.8 | 97108.44 | 100% | 100% | 97.49% | 85.25% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-26 | 2007-09-29 | no data | 65 | 247 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Cagbigajo | 084815005 | Const of Gravelled Pathway | 1 | 615677.8 | 430974 | 184703.8 | 418726.98 | 3rd Tranche | 174208.87 | 592935.85 | 418726.98 | 174208.87 | 100% | 100% | 94.32% | 96.31% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-06 | 2008-05-03 | n/a | 271 | 72 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Cagbigajo | 084815005 | Const of Gravelled Pathway | 1 | 1458320 | 1020824 | 437496 | 816659.2 | 1st Tranche | 423336.89 | 1239996.09 | 816659.2 | 423336.89 | 100% | 100% | 96.76% | 85.03% | 100% | no data | no data | 2008-10-27 | 2009-01-31 | n/a | 96 | 72 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Camparanga | 084815009 | Construction of Street Lights | 1 | 332078 | 232455 | 99623 | 216577 | 3rd Tranche | 90623 | 307200 | 216577 | 90623 | 100% | 100% | 90.97% | 92.51% | 100% | 2007-02-20 | 2007-04-16 | 2007-11-15 | 2008-02-25 | no data | 102 | 308 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Camparanga | 084815009 | Const of Water system L2 | 1 | 680620 | 476434 | 204186 | 428790.24 | 2nd Tranche | 164624.51 | 593414.75 | 428790.24 | 164624.51 | 100% | 100% | 80.62% | 87.19% | 100% | no data | no data | 2008-10-06 | 2008-12-06 | n/a | 61 | 308 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Canjumadal | 084815007 | Const of Water system L2 | 1 | 363876 | 254713 | 109163 | 229241.7 | 2nd Tranche | 120735.7 | 349977.4 | 229241.7 | 120735.7 | 100% | 100% | 110.6% | 96.18% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-01 | 2007-09-29 | no data | 59 | 92 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Canjumadal | 084815007 | Const of 1-Room School Building | 1 | 750414 | 525289.8 | 225124.2 | 473094.02 | 2nd Tranche | 209317.33 | 682411.35 | 473094.02 | 209317.33 | 100% | 100% | 92.98% | 90.94% | 100% | no data | no data | 2008-09-17 | 2008-12-30 | n/a | 104 | 92 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Sixto T. Balanguit, Sr. | 084815029 | Const of Day care Center | 1 | 543794 | 380656 | 163138 | 304524.8 | 1st Tranche | 160059 | 464583.8 | 304524.8 | 160059 | 100% | 100% | 98.11% | 85.43% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-29 | 2008-11-30 | n/a | 459 | 47 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Doña Anecita | 084815008 | Const of Water system L2 | 1 | 790350 | 553245 | 237105 | 442596 | 2nd Tranche | 146099.3 | 588695.3 | 442596 | 146099.3 | 100% | 100% | 61.62% | 74.49% | 100% | no data | no data | 2008-10-29 | 2009-03-31 | n/a | 153 | 108 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Doña Anecita | 084815008 | Const of Day Care Center | 1 | 501473.3 | 351031 | 150442.3 | 315927.9 | 2nd Tranche | 162911.8 | 478839.7 | 315927.9 | 162911.8 | 100% | 100% | 108.3% | 95.49% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-25 | 2007-10-10 | no data | 77 | 108 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ge-adgawan | 084815010 | Const of 1-Room School Building | 1 | 877308 | 614115.6 | 263192.4 | 491292.48 | 1st Tranche | 155036.2 | 646328.68 | 491292.48 | 155036.2 | 100% | 100% | 58.91% | 73.67% | 100% | no data | no data | 2008-10-28 | 2009-02-28 | n/a | 123 | 113 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ge-adgawan | 084815010 | Const of Water system L2 | 1 | 491567.55 | 344097 | 147470.55 | 342901.5 | 3rd Tranche | 143509.35 | 486410.85 | 342901.5 | 143509.35 | 100% | 100% | 97.31% | 98.95% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-25 | 2008-05-30 | no data | 310 | 113 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ginulgan | 084815011 | Const of Drainage Canal | 1 | 401448 | 281014 | 120434 | 275541.44 | 3rd Tranche | 122249.4 | 397790.84 | 275541.44 | 122249.4 | 100% | 100% | 101.5% | 99.09% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-14 | 2008-06-23 | n/a | 314 | 301 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ginulgan | 084815011 | Const of Water system L2 | 1 | 678520 | 474964 | 203556 | 427467.6 | 2nd Tranche | 94112.72 | 521580.32 | 427467.6 | 94112.72 | 100% | 100% | 46.23% | 76.87% | 100% | no data | no data | 2008-09-10 | 2008-11-10 | n/a | 61 | 301 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Geparayan | 084815012 | Rehab of Water system L2 | 1 | 450472.1 | 315330 | 135142.1 | 283797 | 2nd Tranche | 156793.35 | 440590.35 | 283797 | 156793.35 | 100% | 100% | 116% | 97.81% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-31 | 2008-02-23 | no data | 176 | 204 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Igot | 084815013 | Const of Day care Center | 1 | 513444 | 359411 | 154033 | 323469.9 | 2nd Tranche | 152661.9 | 476131.8 | 323469.9 | 152661.9 | 100% | 100% | 99.11% | 92.73% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-15 | 2008-05-25 | n/a | 284 | 109 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Igot | 084815013 | Const of Water system L2 | 1 | 615081 | 430556.7 | 184524.3 | 387501.03 | 2nd Tranche | 146405.3 | 533906.33 | 387501.03 | 146405.3 | 100% | 100% | 79.34% | 86.8% | 100% | no data | no data | 2008-11-06 | 2009-01-31 | n/a | 86 | 109 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Inanahawan | 084815015 | Const of Gravelled Pathway | 1 | 555538.75 | 388877 | 166661.75 | 388877 | 3rd Tranche | 175657.3 | 564534.3 | 388877 | 175657.3 | 100% | 100% | 105.4% | 101.6% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-24 | 2008-09-30 | no data | 403 | 95 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Inanahawan | 084815015 | Const of Gravelled Pathway | 1 | 1346520 | 942564 | 403956 | 848307.6 | 2nd Tranche | 171573.88 | 1019881.48 | 848307.6 | 171573.88 | 100% | 100% | 42.47% | 75.74% | 100% | no data | no data | 2008-10-13 | 2008-11-13 | n/a | 31 | 95 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Manahao | 084815016 | Const of Day care Center | 1 | 531089 | 371762 | 159327 | 334585.8 | 2nd Tranche | 148519.75 | 483105.55 | 334585.8 | 148519.75 | 100% | 100% | 93.22% | 90.97% | 100% | 2007-02-20 | 2007-04-16 | 2007-08-02 | 2008-05-18 | n/a | 290 | 56 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Manahao | 084815016 | Const of Water system L2 | 1 | 314601 | 220220.7 | 94380.3 | 198198.63 | 2nd Tranche | 84804.29 | 283002.92 | 198198.63 | 84804.29 | 100% | 100% | 89.85% | 89.96% | 100% | no data | no data | 2008-11-12 | 2009-01-31 | n/a | 80 | 56 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Paninirongan | 084815018 | Construction of toilets | 1 | 500819.9 | 350574 | 150245.9 | 350574 | 2nd Tranche | 126451 | 477025 | 350574 | 126451 | 100% | 100% | 84.16% | 95.25% | 100% | 2007-02-20 | 2007-04-16 | 2007-09-28 | 2008-06-30 | n/a | 276 | 193 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Paninirongan | 084815018 | Const of School Building | 1 | 664518 | 465162.6 | 199355.4 | 465162.6 | 3rd Tranche | 137212.2 | 602374.8 | 465162.6 | 137212.2 | 100% | 100% | 68.83% | 90.65% | 100% | no data | no data | 2008-09-12 | 2008-12-12 | no data | 91 | 193 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 1 | 084815019 | Const of Drainage Canal | 1 | 609930 | 426951 | 182979 | 341560.8 | 1st Tranche | 99947.2 | 441508 | 341560.8 | 99947.2 | 100% | 100% | 54.62% | 72.39% | 100% | no data | no data | 2008-09-29 | 2008-12-29 | no data | 91 | 416 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 5 | 084815023 | Const of Day Care Center | 1 | 643617 | 450531.9 | 193085.1 | 450201.4 | 2nd Tranche | 145777.57 | 595648.47 | 450201.4 | 145447.07 | 100% | 99.77% | 75.5% | 92.55% | 100% | no data | no data | 2005-08-25 | 2009-02-03 | n/a | 1258 | 129 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 8 | 084815026 | Const of Street Light | 1 | 311515 | 218060.5 | 93454.5 | 196254.45 | 2nd Tranche | 73479.29 | 269733.74 | 196254.45 | 73479.29 | 100% | 100% | 78.63% | 86.59% | 100% | no data | no data | 2008-08-25 | 2008-12-28 | no data | 125 | 391 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion District 1 - C6 | 084815019 | Const of Drainage Canal | 6 | 2437558 | 1693026 | 744532 | 1523723.4 | 2nd Tranche | 699987.73 | 2223711.13 | 1523723.4 | 699987.73 | 100% | 100% | 94.02% | 91.23% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-30 | 2008-05-17 | no data | 292 | 416 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 3 - C6 | 084815021 | Const of Drainage Canal | 6 | 2437558 | 1693026 | 744532 | 1523723.4 | 2nd Tranche | 699987.73 | 2223711.13 | 1523723.4 | 699987.73 | 100% | 100% | 94.02% | 91.23% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-30 | 2008-05-17 | no data | 292 | 416 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 4 - C6 | 084815022 | Const of Drainage Canal | 6 | 2437558 | 1693026 | 744532 | 1523723.4 | 2nd Tranche | 699987.73 | 2223711.13 | 1523723.4 | 699987.73 | 100% | 100% | 94.02% | 91.23% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-30 | 2008-05-17 | no data | 292 | 416 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 6 - C6 | 084815024 | Const of Drainage Canal | 6 | 2437558 | 1693026 | 744532 | 1523723.4 | 2nd Tranche | 699987.73 | 2223711.13 | 1523723.4 | 699987.73 | 100% | 100% | 94.02% | 91.23% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-30 | 2008-05-17 | no data | 292 | 416 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion 7 C6 | 084815025 | Const of Drainage Canal | 6 | 2437558 | 1693026 | 744532 | 1523723.4 | 2nd Tranche | 699987.73 | 2223711.13 | 1523723.4 | 699987.73 | 100% | 100% | 94.02% | 91.23% | 100% | 2007-02-20 | 2007-04-16 | 2007-07-30 | 2008-05-17 | no data | 292 | 416 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Poblacion District 2 | 084815020 | Rehab of Streetlight with Gen set | 1 | 355631 | 248942 | 106689 | 224047.8 | 2nd Tranche | 97118.1 | 321165.9 | 224047.8 | 97118.1 | 100% | 100% | 91.03% | 90.31% | 100% | 2007-02-20 | 2007-04-16 | 2007-12-05 | 2008-09-05 | n/a | 275 | 181 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | San Ramon | 084815027 | Postharvest Facility (rice mill) | 1 | 416430.96 | 268704 | 147726.96 | 237963.2 | 2nd Tranche | 132180.96 | 370144.16 | 237963.2 | 132180.96 | 100% | 100% | 89.48% | 88.88% | 100% | 2007-02-20 | 2007-04-16 | 2007-10-25 | 2008-11-25 | n/a | 397 | 65 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Senonogan | 084815028 | Const of Water system L2 | 1 | 372564.08 | 260795 | 111769.08 | 208636 | 1st Tranche | 99406.53 | 308042.53 | 208636 | 99406.53 | 100% | 100% | 88.94% | 82.68% | 100% | 2007-02-20 | 2007-04-16 | 2007-09-26 | 2008-02-26 | no data | 153 | 93 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Senonogan | 084815028 | Const of Day Care Center | 1 | 824811 | 577367.7 | 247443.3 | 461894.16 | 1st Tranche | 158280.67 | 620174.83 | 461894.16 | 158280.67 | 100% | 100% | 63.97% | 75.19% | 100% | no data | no data | 2008-10-28 | 2009-01-31 | n/a | 95 | 93 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Tula | 084815030 | School Building (1 Room) | 1 | 570422.13 | 395245 | 175177.13 | 355720.5 | 2nd Tranche | 165697.37 | 521417.87 | 355720.5 | 165697.37 | 100% | 100% | 94.59% | 91.41% | 100% | 2007-02-20 | 2007-04-16 | 2007-09-28 | 2008-06-30 | n/a | 276 | 280 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Tula | 084815030 | Const of Water system L2 | 1 | 524899 | 367429.3 | 157469.7 | 293943.44 | 1st Tranche | 107628.96 | 401572.4 | 293943.44 | 107628.96 | 100% | 100% | 68.35% | 76.5% | 100% | no data | no data | 2008-11-10 | 2009-02-28 | n/a | 110 | 280 |  | 1
VIII | 08 | Northern Samar | 0848 | Pambujan | 084815 | Ynaguingayan | 084815014 | Const of Water system L2 | 1 | 436060.4 | 305242 | 130818.4 | 244193.6 | 1st Tranche | 117306.8 | 361500.4 | 244193.6 | 117306.8 | 100% | 100% | 89.67% | 82.9% | 100% | 2007-02-20 | 2007-04-16 | 2008-01-25 | 2008-05-31 | no data | 127 | 166 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Balnasan | 084820001 | Construction of School Building | 1 | 579007 | 405304 | 173703 | 388304 | 2nd Tranche | 184080 | 572384 | 388304 | 184080 | 100% | 100% | 106% | 98.86% | 100% | no data | no data | 2008-10-14 | 2009-03-13 | n/a | 150 | 458 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Balnasan | 084820001 | Concrete Footbridge | 1 | 1340000 | 938000 | 402000 | 938000 | 1st Tranche | 188030 | 1126030 | 938000 | 188030 | 100% | 100% | 46.77% | 84.03% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-22 | 2009-06-30 | n/a | 69 | 20 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Balud | 084820002 | Construction of Water System (L1) | 1 | 170061 | 119042 | 51019 | 107137.8 | 2nd Tranche | 47917.1 | 155054.9 | 107137.8 | 47917.1 | 100% | 100% | 93.92% | 91.18% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-09 | 2007-08-27 | no data | 49 | 120 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Balud | 084820002 | Concrete Footbridge | 1 | 1010000 | 707000 | 303000 | 698110 | 2nd Tranche | 282132 | 980242 | 698110 | 282132 | 100% | 100% | 93.11% | 97.05% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-01 | 2009-06-30 | n/a | 90 | 120 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Bantayan | 084820003 | Construction of Box Culvert | 1 | 380729 | 266510 | 114219 | 266510 | 3rd Tranche | 132219 | 398729 | 266510 | 132219 | 100% | 100% | 115.8% | 104.7% | 100% | 2007-02-13 | 2007-03-28 | 2008-03-05 | 2008-06-05 | n/a | 92 | 902 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Bantayan | 084820003 | Const of Drainage Canal | 1 | 602996 | 422097 | 180899 | 421887 | 3rd Tranche | 220699 | 642586 | 421887 | 220699 | 100% | 100% | 122% | 106.6% | 100% | no data | no data | 2008-09-18 | 2008-11-14 | n/a | 57 | 473 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Coroconog | 084820004 | Construction of Pre-School Building | 1 | 542601 | 379820 | 162781 | 348820 | 3rd Tranche | 162781 | 511601 | 348820 | 162781 | 100% | 100% | 100% | 94.29% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-09 | 2008-06-30 | n/a | 357 | 204 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Coroconog | 084820004 | Drainage Canal | 1 | 870000 | 762000 | 108000 | 685800 | 2nd Tranche | 50000 | 735800 | 685800 | 50000 | 100% | 100% | 46.3% | 84.57% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-06 | 2009-06-30 | n/a | 85 | 204 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Dale | 084820005 | Construction of School Building ( _ Rm) | 1 | 541601 | 379120 | 162481 | 379120 | 3rd Tranche | 162428 | 541548 | 379120 | 162428 | 100% | 100% | 99.97% | 99.99% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-02 | 2008-06-29 | n/a | 363 | 166 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Dale | 084820005 | Const of Drainage Canal | 1 | 412055 | 288438 | 123617 | 288438 | 2nd Tranche | 118711.5 | 407149.5 | 288438 | 118711.5 | 100% | 100% | 96.03% | 98.81% | 100% | no data | no data | 2008-10-13 | 2009-01-14 | n/a | 93 | 290 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Ginagdanan | 084820006 | Const of Drainage Canal | 1 | 615919 | 431143 | 184776 | 388028.7 | 2nd Tranche | 144136 | 532164.7 | 388028.7 | 144136 | 100% | 100% | 78.01% | 86.4% | 100% | no data | no data | 2008-11-03 | 2009-02-03 | n/a | 92 | 342 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Lao-angan | 084820007 | Construction of Day Care Center | 1 | 521857 | 365299 | 156558 | 328769.1 | 2nd Tranche | 147050 | 475819.1 | 328769.1 | 147050 | 100% | 100% | 93.93% | 91.18% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-02 | 2008-05-20 | n/a | 323 | 227 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Lao-angan | 084820007 | Construction of School Building 2Rm | 1 | 1051973 | 736381 | 315592 | 662742.5 | 2nd Tranche | 206100.89 | 868843.39 | 662742.5 | 206100.89 | 100% | 100% | 65.31% | 82.59% | 100% | no data | no data | 2008-10-20 | 2009-03-31 | n/a | 162 | 263 |  | 1
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Lawaan | 084820008 | Construction of Brgy. Health Station | 1 | 635371.4 | 444759.4 | 190612 | 444759.4 | 3rd Tranche | 191522.5 | 636281.9 | 444759.4 | 191522.5 | 100% | 100% | 100.5% | 100.1% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-30 | 2008-06-11 | n/a | 317 | 97 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Lawaan | 084820008 | Const of Daycare Center | 1 | 583049 | 408134 | 174915 | 367320 | 2nd Tranche | 174970 | 542290 | 367320 | 174970 | 100% | 100% | 100% | 93.01% | 100% | no data | no data | 2008-11-26 | 2009-08-28 | n/a | 275 | 182 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Malobago | 084820009 | Construction of Concrete Footbridge | 1 | 834485 | 584139 | 250346 | 584139 | 2nd Tranche | 250816 | 834955 | 584139 | 250816 | 100% | 100% | 100.2% | 100.1% | 100% | 2007-02-13 | 2007-03-28 | 2007-08-04 | 2008-06-19 | n/a | 320 | 164 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Malobago | 084820009 | Slope Protection | 1 | 879400 | 665000 | 214400 | 598500 | 2nd Tranche | 100000 | 698500 | 598500 | 100000 | 100% | 100% | 46.64% | 79.43% | 100% | 2009-01-28 | 2009-02-20 | 2009-04-05 | 2009-06-30 | n/a | 86 | 164 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Pagsang-an | 084820010 | Construction of Pre-School Building | 1 | 562917 | 394041 | 168876 | 392805.2 | 2nd Tranche | 172774 | 565579.2 | 392805.2 | 172774 | 100% | 100% | 102.3% | 100.5% | 100% | 2007-02-13 | 2007-03-28 | 2007-08-04 | 2008-06-10 | n/a | 311 | 204 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Pagsang-an | 084820010 | Construction of School Building 2Rm | 1 | 1105543 | 773880 | 331663 | 696492 | 2nd Tranche | 225591 | 922083 | 696492 | 225591 | 100% | 100% | 68.02% | 83.41% | 100% | no data | no data | 2008-11-03 | 2009-05-20 | n/a | 198 | 132 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 1 | 084820011 | Construction of Grouted Riprap | 1 | 505268 | 353687 | 151581 | 318318.3 | 2nd Tranche | 120450 | 438768.3 | 318318.3 | 120450 | 100% | 100% | 79.46% | 86.84% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-02 | 2008-05-06 | n/a | 309 | 345 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 1 | 084820011 | Const of Daycare Center | 1 | 550503 | 385352 | 165151 | 385352 | 3rd Tranche | 140045.12 | 525397.12 | 385352 | 140045.12 | 100% | 100% | 84.8% | 95.44% | 100% | no data | no data | 2008-10-20 | 2009-03-31 | n/a | 162 | 272 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 2 | 084820012 | Construction of Drainage Canal | 1 | 435776 | 283455 | 152321 | 255109.5 | 2nd Tranche | 132040 | 387149.5 | 255109.5 | 132040 | 100% | 100% | 86.69% | 88.84% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-02 | 2007-08-11 | no data | 40 | 181 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 2 | 084820012 | Flood Control | 1 | 600000 | 483000 | 117000 | 434700 | 2nd Tranche | 70000 | 504700 | 434700 | 70000 | 100% | 100% | 59.83% | 84.12% | 100% | 2009-01-28 | 2009-02-20 | 2009-03-30 | 2009-06-30 | n/a | 92 | 181 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 3 | 084820013 | Construction of Day Care Center | 1 | 513679 | 359575 | 154104 | 359575 | 3rd Tranche | 154124.5 | 513699.5 | 359575 | 154124.5 | 100% | 100% | 100% | 100% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-02 | 2008-06-20 | n/a | 354 | 468 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 3 | 084820013 | River Control | 1 | 1220000 | 910000 | 310000 | 819000 | 2nd Tranche | 150000 | 969000 | 819000 | 150000 | 100% | 100% | 48.39% | 79.43% | 100% | 2009-01-28 | 2009-02-20 | 2009-03-30 | 2009-06-30 | n/a | 92 | 468 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 4 | 084820014 | Const of Drainage Canal | 1 | 372449 | 260714 | 111735 | 254914 | 3rd Tranche | 109114 | 364028 | 254914 | 109114 | 100% | 100% | 97.65% | 97.74% | 100% | no data | no data | 2008-09-22 | 2008-11-14 | n/a | 53 | 251 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 4 | 084820014 | Day Care Center | 1 | 563000 | 455000 | 108000 | 409500 | 2nd Tranche | 69000 | 478500 | 409500 | 69000 | 100% | 100% | 63.89% | 84.99% | 100% | 2009-01-28 | 2009-02-20 | 2009-03-30 | 2009-06-30 | n/a | 92 | 251 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 5 | 084820015 | Construction of Drainage Canal | 1 | 674888 | 472421 | 202467 | 461421 | 3rd Tranche | 202482 | 663903 | 461421 | 202482 | 100% | 100% | 100% | 98.37% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-09 | 2008-06-30 | n/a | 357 | 293 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 5 | 084820015 | Const of Day Care Center | 1 | 574256 | 401980 | 172276 | 401977.5 | 2nd Tranche | 119169.12 | 521146.62 | 401977.5 | 119169.12 | 100% | 100% | 69.17% | 90.75% | 100% | no data | no data | 2008-11-03 | 2009-03-31 | n/a | 148 | 102 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 6 | 084820016 | Construction of Day Care Center | 1 | 568760 | 398132 | 170628 | 398132 | 3rd Tranche | 171328 | 569460 | 398132 | 171328 | 100% | 100% | 100.4% | 100.1% | 100% | 2007-02-13 | 2007-03-28 | 2007-07-09 | 2008-06-06 | n/a | 333 | 316 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 6 | 084820016 | Const of Drainage Canal | 1 | 409397 | 286577 | 122820 | 286577 | 3rd Tranche | 32931.46 | 319508.46 | 286577 | 32931.46 | 100% | 100% | 26.81% | 78.04% | 100% | no data | no data | 2008-11-20 | 2009-04-30 | n/a | 161 | 226 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Gebonawan | 084822010 | Hibunawan Water System | 1 | 804195 | 565809 | 238386 | 452647.2 | 3rd Tranche | 193908.8 | 646556 | 452647.2 | 193908.8 | 100% | 100% | 81.34% | 80.4% | 100% | 2006-09-27 | 2006-09-28 | 2006-10-01 | 2006-12-31 | no data | 91 | 40 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Gusaran - C23 | 084822016 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Apolonia | 086022002 | Mobile Rice Mill | 1 | 642464 | 465658 | 176806 | 403423.5 | 3rd Tranche | 176536 | 579959.5 | 403423.5 | 176536 | 100% | 100% | 99.85% | 90.27% | 100% | 2006-08-14 | 2006-10-06 | 2007-07-09 | 2007-08-09 | no data | 31 | 116 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Apolonia | 086022002 | Improvement of Water System Level II | 1 | 603539 | 422457 | 181082 | 380211.3 | 2nd Tranche | 169602 | 549813.3 | 380211.3 | 169602 | 100% | 100% | 93.66% | 91.1% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-27 | 2008-10-25 | n/a | 120 | 110 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Bagsa | 086022003 | Improvement of Cawayan-Bagsa Farm to Market Road | 1 | 1199260 | 839482 | 359778 | 671586 | 1st Tranche | 359843.5 | 1031429.5 | 671586 | 359843.5 | 100% | 100% | 100% | 86.01% | 100% | 2007-12-13 | 2008-02-12 | 2009-03-20 | 2009-08-31 | n/a | 164 | 71 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Balbagan | 086022004 | Mobile Water System | 1 | 720995 | 468646 | 252349 | 468646 | 3rd Tranche | 254629 | 723275 | 468646 | 254629 | 100% | 100% | 100.9% | 100.3% | 100% | 2006-08-14 | 2006-10-06 | 2007-08-01 | 2007-09-15 | no data | 45 | 46 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Balbagan | 086022004 | RCBC Double barrels | 1 | 698232 | 488763 | 209469 | 439886.7 | 2nd Tranche | 177968.72 | 617855.42 | 439886.7 | 177968.72 | 100% | 100% | 84.96% | 88.49% | 100% | no data | no data | 2009-03-21 | 2009-05-31 | no data | 71 | 51 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Bato | 086022005 | Day Care Center | 1 | 638207 | 462572 | 175635 | 462572 | 3rd Tranche | 177525 | 640097 | 462572 | 177525 | 100% | 100% | 101.1% | 100.3% | 100% | 2006-08-14 | 2006-10-06 | 2006-11-27 | 2007-06-16 | no data | 201 | 137 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Bato | 086022005 | Health Station | 1 | 709835 | 496885 | 212950 | 447196.5 | 2nd Tranche | 188629.35 | 635825.85 | 447196.5 | 188629.35 | 100% | 100% | 88.58% | 89.57% | 100% | no data | no data | 2009-03-09 | 2009-05-31 | no data | 83 | 184 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Buray | 086022006 | Pre-Harvest Facilities | 1 | 269862 | 188904 | 80958 | 176372.72 | 2nd Tranche | 81958.02 | 258330.74 | 176372.72 | 81958.02 | 100% | 100% | 101.2% | 95.73% | 100% | no data | no data | 2009-04-28 | 2009-05-15 | no data | 17 | 300 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantaguic | 086022008 | Construction of Water System Level II | 1 | 182320 | 127624 | 54696 | 114861.6 | 2nd Tranche | 53516 | 168377.6 | 114861.6 | 53516 | 100% | 100% | 97.84% | 92.35% | 100% | 2007-12-13 | 2008-02-12 | 2008-07-27 | 2008-11-15 | n/a | 111 | 57 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantao-an | 086022009 | Standard Day Care Center | 1 | 718229 | 502761 | 215468 | 452485 | 2nd Tranche | 190623.09 | 643108.09 | 452485 | 190623.09 | 100% | 100% | 88.47% | 89.54% | 100% | no data | no data | 2009-03-23 | 2009-06-27 | no data | 96 | 30 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantato | 086022010 | Water System L 2 | 1 | 1391656 | 1008672 | 382984 | 1008672 | 3rd Tranche | 437924 | 1446596 | 1008672 | 437924 | 100% | 100% | 114.3% | 103.9% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-05 | 2007-06-19 | no data | 165 | 74 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantato | 086022010 | Pre and Post Harvest Facility | 1 | 293745 | 267307.95 | 26437.05 | 213846.37 | 1st Tranche | 24087.05 | 237933.42 | 213846.37 | 24087.05 | 100% | 100% | 91.11% | 81% | 100% |  | no data | 2009-05-23 | 2009-06-22 | n/a | 30 | 74 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Casandig 1 - C2 | 086022011 | Water System L 2 | 2 | 1520839 | 1102304 | 418535 | 1102304 | 3rd Tranche | 445090 | 1547394 | 1102304 | 445090 | 100% | 100% | 106.3% | 101.7% | 100% | 2006-08-14 | 2006-10-06 | 2006-12-18 | 2007-06-09 | no data | 173 | 294 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Casandig 1 - C2 | 086022011 | Construction of Closed Line Canal | 2 | 1443488 | 1010442 | 433046 | 982010 | 2nd Tranche | 409846 | 1391856 | 982010 | 409846 | 100% | 100% | 94.64% | 96.42% | 100% | 2007-12-13 | 2008-02-12 | 2008-07-03 | 2008-12-01 | n/a | 151 | 314 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cawayan | 086022014 | Resurfacing of FMR | 1 | 1001141 | 725627 | 275514 | 725627 | 3rd Tranche | 277276.76 | 1002903.76 | 725627 | 277276.76 | 100% | 100% | 100.6% | 100.2% | 100% | 2006-08-14 | 2006-10-06 | 2007-02-05 | 2007-03-10 | no data | 33 | 57 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cawayan | 086022014 | Water System level II | 1 | 285125 | 199588 | 85537 | 159670.4 | 1st Tranche | 76838.85 | 236509.25 | 159670.4 | 76838.85 | 100% | 100% | 89.83% | 82.95% | 100% | no data | no data | 2009-04-27 | 2009-05-31 | no data | 34 | 61 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Concepcion | 086022012 | Hanging Bridge | 1 | 1605825 | 1104147 | 501678 | 1099126.4 | 3rd Tranche | 502678 | 1601804.4 | 1099126.4 | 502678 | 100% | 100% | 100.2% | 99.75% | 100% | 2006-08-14 | 2006-10-06 | 2007-07-23 | 2007-08-13 | no data | 21 | 108 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Concepcion | 086022012 | Improvement of Power Operated W.S L II | 1 | 389805 | 272864 | 116941 | 261637 | 3rd Tranche | 113741 | 375378 | 261637 | 113741 | 100% | 100% | 97.26% | 96.3% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-27 | 2008-12-05 | n/a | 161 | 108 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Jose Roño - C2 | 086022013 | Construction of Water Sytem Level II | 2 | 1726256 | 1208380 | 517876 | 966704 | 1st Tranche | 482826 | 1449530 | 966704 | 482826 | 100% | 100% | 93.23% | 83.97% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-27 | 2009-03-31 | n/a | 277 | 178 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lawaan 1 | 086022015 | Construction of Water System Level II | 1 | 1238510 | 866957 | 371553 | 780261.3 | 3rd Tranche | 386103 | 1166364.3 | 780261.3 | 386103 | 100% | 100% | 103.9% | 94.17% | 100% | 2007-12-13 | 2008-02-12 | 2008-07-15 | 2008-12-06 | n/a | 144 | 271 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lawaan 1 | 086022015 | Closed Line Canal | 1 | 1419542 | 993680 | 425862 | 894312 | 2nd Tranche | 371611.19 | 1265923.19 | 894312 | 371611.19 | 100% | 100% | 87.26% | 89.18% | 100% | no data | no data | 2009-03-17 | 2009-05-31 | no data | 75 | 271 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lawaan 2 | 086022049 | Water System level II | 1 | 1086698 | 760689 | 326009 | 608551.2 | 1st Tranche | 291408.58 | 899959.78 | 608551.2 | 291408.58 | 100% | 100% | 89.39% | 82.82% | 100% | no data | no data | 2009-03-23 | 2009-05-31 | no data | 69 | 79 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lipata | 086022016 | Closed Line Canal | 1 | 1413511 | 989458 | 424053 | 890512.17 | 1st Tranche | 469380.58 | 1359892.75 | 890512.17 | 469380.58 | 100% | 100% | 110.7% | 96.21% | 100% | no data | no data | 2009-03-16 | 2009-05-31 | no data | 76 | 150 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lokilokon | 086022017 | Water System L 2 | 1 | 1131615 | 820195 | 311420 | 820195 | 3rd Tranche | 440161.25 | 1260356.25 | 820195 | 440161.25 | 100% | 100% | 141.3% | 111.4% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-05 | 2007-06-19 | no data | 165 | 176 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lokilokon | 086022017 | concrete footbridge | 1 | 742879 | 520016 | 222863 | 468014.4 | 2nd Tranche | 200157.32 | 668171.72 | 468014.4 | 200157.32 | 100% | 100% | 89.81% | 89.94% | 100% | no data | no data | 2009-03-22 | 2009-05-31 | no data | 70 | 205 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Mangcal | 086022018 | Improvement of Salay-Mangcal Farm to Market Road | 1 | 1658793 | 1161156 | 497637 | 928924.8 | 1st Tranche | 497636 | 1426560.8 | 928924.8 | 497636 | 100% | 100% | 100% | 86% | 100% | 2007-12-13 | 2008-02-12 | 2009-02-22 | 2009-08-31 | n/a | 190 | 71 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Maylobe | 086022019 | Water System L 2 | 1 | 295058 | 213858 | 81200 | 213858 | 3rd Tranche | 107245 | 321103 | 213858 | 107245 | 100% | 100% | 132.1% | 108.8% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-08 | 2007-06-09 | no data | 152 | 59 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Minarog | 086022020 | Box Culvert Bridge | 1 | 869523 | 631674 | 237849 | 631674 | 3rd Tranche | 239434 | 871108 | 631674 | 239434 | 100% | 100% | 100.7% | 100.2% | 100% | 2006-08-14 | 2006-10-06 | 2006-12-27 | 2007-05-31 | no data | 155 | 89 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Minarog | 086022020 | Construction of Water System Level II | 1 | 203106 | 142175 | 60931 | 127957 | 2nd Tranche | 61061.91 | 189018.91 | 127957 | 61061.91 | 100% | 100% | 100.2% | 93.06% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-26 | 2009-07-31 | n/a | 400 | 58 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Nawi | 086022021 | Sustainable Agriculture | 1 | 466426 | 338066 | 128360 | 270452.8 | 2nd tranche | 137138.3 | 407591.1 | 270452.8 | 137138.3 | 100% | 100% | 106.8% | 87.39% | 100% | 2006-08-14 | 2006-10-06 | 2007-07-16 | 2008-02-23 | no data | 222 | 64 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Nawi | 086022021 | Improvement of Water System Level II | 1 | 483158 | 338211 | 144947 | 304389.9 | 2nd Tranche | 141430.45 | 445820.35 | 304389.9 | 141430.45 | 100% | 100% | 97.57% | 92.27% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-28 | 2008-10-30 | n/a | 124 | 61 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pabanog | 086022022 | Water System L 2 | 1 | 1613716 | 1169621 | 444095 | 1169621 | 3rd Tranche | 476860 | 1646481 | 1169621 | 476860 | 100% | 100% | 107.4% | 102% | 100% | 2006-08-14 | 2006-10-06 | 2006-12-20 | 2007-06-09 | no data | 171 | 297 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pabanog | 086022022 | Slope Protection with grouted Riprap | 1 | 1356557 | 949590 | 406967 | 759672 | 1st Tranche | 360317.05 | 1119989.05 | 759672 | 360317.05 | 100% | 100% | 88.54% | 82.56% | 100% | no data | no data | 2009-03-23 | 2009-05-31 | no data | 69 | 280 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pagsan- an | 086022025 | Building for a Sustainable Agriculture | 1 | 519200 | 363440 | 155760 | 290752 | 1st Tranche | 154351 | 445103 | 290752 | 154351 | 100% | 100% | 99.1% | 85.73% | 100% | no data | no data | 2009-04-20 | 2009-05-31 | no data | 41 | 49 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pagsa-ogan | 086022024 | RCBC Double barrels | 1 | 980775 | 686543 | 294232 | 614140.9 | 2nd Tranche | 266862.75 | 881003.65 | 614140.9 | 266862.75 | 100% | 100% | 90.7% | 89.83% | 100% | no data | no data | 2009-03-21 | 2009-05-31 | no data | 71 | 89 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Patag | 086022026 | Standard Day Care Center | 1 | 718229 | 502761 | 215468 | 452484.9 | 2nd Tranche | 189623.09 | 642107.99 | 452484.9 | 189623.09 | 100% | 100% | 88.01% | 89.4% | 100% | no data | no data | 2009-03-23 | 2009-06-19 | no data | 88 | 136 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pequit | 086022027 | Mobile Water System | 1 | 773425 | 502726 | 270699 | 502726 | 1st Tranche | 272699 | 775425 | 502726 | 272699 | 100% | 100% | 100.7% | 100.3% | 100% | 2006-08-14 | 2006-10-06 | 2008-05-02 | 2008-05-28 | no data | 26 | 145 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pequit | 086022027 | Standard Day Care Center | 1 | 718229 | 502761 | 215468 | 452484.8 | 2nd Tranche | 189623.09 | 642107.89 | 452484.8 | 189623.09 | 100% | 100% | 88.01% | 89.4% | 100% | no data | no data | 2009-03-16 | 2009-05-31 | no data | 76 | 191 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 1 | 086022028 | Construction Brgy. Road with Retaining Wall | 1 | 2615064 | 1811797 | 803267 | 1740495.8 | 3rd Tranche | 751667 | 2492162.8 | 1740495.8 | 751667 | 100% | 100% | 93.58% | 95.3% | 100% | 2007-12-13 | 2008-02-12 | 2008-10-28 | 2009-04-22 | n/a | 176 | 102 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 2 | 086022029 | 1 unit 2 classroom school building | 1 | 1134903 | 794433 | 340470 | 783073.59 | 2nd Tranche | 314221.63 | 1097295.22 | 783073.59 | 314221.63 | 100% | 100% | 92.29% | 96.69% | 100% | no data | no data | 2009-03-20 | 2009-05-31 | no data | 72 | 133 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 2 - C2 | 086022029 | Construction of Drainage Canal | 2 | 1299376 | 909564 | 389812 | 884932.6 | 3rd Tranche | 362147 | 1247079.6 | 884932.6 | 362147 | 100% | 100% | 92.9% | 95.98% | 100% | 2007-12-13 | 2008-02-12 | 2008-07-07 | 2008-11-15 | n/a | 131 | 272 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 3 | 086022030 | Standard Day Care Center | 1 | 718229 | 502761 | 215468 | 452484.8 | 2nd Tranche | 169156.37 | 621641.17 | 452484.8 | 169156.37 | 100% | 100% | 78.51% | 86.55% | 100% | no data | no data | 2009-03-23 | 2009-05-31 | no data | 69 | 30 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 4 | 086022031 | Standard Day Care Center | 1 | 718229 | 502761 | 215468 | 452485 | 2nd Tranche | 189723.09 | 642208.09 | 452485 | 189723.09 | 100% | 100% | 88.05% | 89.42% | 100% | no data | no data | 2009-03-10 | 2009-05-31 | no data | 82 | 90 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 5 | 086022032 | Grouted Riprap | 1 | 1014064 | 709845 | 304219 | 567877 | 1st Tranche | 282769 | 850646 | 567877 | 282769 | 100% | 100% | 92.95% | 83.88% | 100% | no data | no data | 2009-03-12 | 2009-05-31 | no data | 80 | 89 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 6 | 086022033 | Construction of Grouted Riprap | 1 | 714209 | 499947 | 214262 | 449952.3 | 2nd Tranche | 205337 | 655289.3 | 449952.3 | 205337 | 100% | 100% | 95.83% | 91.75% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-28 | 2008-11-17 | n/a | 142 | 118 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 6 | 086022033 | Standard Day Care Center | 1 | 718229 | 502761 | 215468 | 452484.8 | 2nd Tranche | 202131 | 654615.8 | 452484.8 | 202131 | 100% | 100% | 93.81% | 91.14% | 100% | no data | no data | 2009-03-23 | 2009-05-31 | no data | 69 | 195 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Salay | 086022038 | Construction of Drainage Canal | 1 | 607204 | 425043 | 182161 | 407441.5 | 3rd Tranche | 156061 | 563502.5 | 407441.5 | 156061 | 100% | 100% | 85.67% | 92.8% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-27 | 2008-12-06 | n/a | 162 | 143 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | San Isidro | 086022039 | Water System L 2 | 1 | 818345 | 590527 | 227818 | 590527 | 3rd Tranche | 211348 | 801875 | 590527 | 211348 | 100% | 100% | 92.77% | 97.99% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-29 | 2007-06-14 | no data | 136 | 143 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | San Isidro | 086022039 | Construction of RCBC (Double Barrel) | 1 | 747811 | 523468 | 224343 | 523468 | 3rd Tranche | 229233 | 752701 | 523468 | 229233 | 100% | 100% | 102.2% | 100.7% | 100% | 2007-12-13 | 2008-02-12 | 2008-07-24 | 2008-10-15 | no data | 83 | 52 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Sulopan | 086022041 | RCBC Bridge | 1 | 959968 | 695785 | 264183 | 695785 | 3rd Tranche | 267013 | 962798 | 695785 | 267013 | 100% | 100% | 101.1% | 100.3% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-15 | 2007-06-16 | no data | 152 | 77 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Sulopan | 086022041 | Construction of RCBC (Triple Barrel) | 1 | 1306500 | 652750 | 653750 | 587475 | 2nd Tranche | 250450 | 837925 | 587475 | 250450 | 100% | 100% | 38.31% | 64.14% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-22 | 2008-10-25 | n/a | 125 | 52 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Sto. Niño | 086022040 | Sustainable Agriculture | 1 | 297270 | 215461 | 81809 | 172368.8 | 1st Tranche | 254273 | 255177.5 | 172368.8 | 82808.7 | 100% | 32.57% | 310.8% | 85.84% | 100% | 2006-08-14 | 2006-10-06 | 2007-08-05 | 2008-02-05 | no data | 184 | 52 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tabucan - C2 | 086022042 | Farm to Market Road | 2 | 1101203 | 618232 | 482971 | 603931 | 2nd tranche | 384471 | 988402 | 603931 | 384471 | 100% | 100% | 79.61% | 89.76% | 100% | 2006-08-14 | 2006-10-06 | 2007-06-27 | 2008-05-27 | n/a | 335 | 110 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tapul | 086022043 | Building for a Sustainable Agriculture | 1 | 436748 | 305724 | 131024 | 244579.2 | 1st Tranche | 92757.2 | 337336.4 | 244579.2 | 92757.2 | 100% | 100% | 70.79% | 77.24% | 100% | no data | no data | 2009-04-20 | 2009-05-31 | no data | 41 | 61 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tenani | 086022044 | Water System L 2 | 1 | 1185835 | 859493 | 326342 | 859493 | 3rd Tranche | 344583.5 | 1204076.5 | 859493 | 344583.5 | 100% | 100% | 105.6% | 101.5% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-11 | 2007-06-19 | no data | 159 | 221 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tenani | 086022044 | 1 unit 2 classroom school building | 1 | 1134903 | 794433 | 340470 | 778558.8 | 2nd Tranche | 354753.63 | 1125724.78 | 778558.8 | 347165.98 | 100% | 97.86% | 104.2% | 99.19% | 100% | no data | no data | 2009-03-10 | 2009-06-19 | no data | 101 | 270 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tigbawon | 086022045 | Improvement of Brgy Road w/ Grouted Riprap | 1 | 954208 | 667946 | 286262 | 649489 | 3rd Tranche | 252822 | 902311 | 649489 | 252822 | 100% | 100% | 88.32% | 94.56% | 100% | 2007-12-13 | 2008-02-12 | 2008-06-28 | 2009-05-15 | n/a | 321 | 56 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tigbawon - C2 | 086022045 | Water System L 2 | 2 | 910295 | 659782 | 250513 | 659782 | 3rd Tranche | 245943 | 905725 | 659782 | 245943 | 100% | 100% | 98.18% | 99.5% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-18 | 2007-05-30 | no data | 132 | 254 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pagsan- an | 086022025 | Water System L 2 | 2 | 910295 | 659782 | 250513 | 659782 | 3rd Tranche | 245943 | 905725 | 659782 | 245943 | 100% | 100% | 98.18% | 99.5% | 100% | 2006-08-14 | 2006-10-06 | 2007-01-18 | 2007-05-30 | no data | 132 | 254 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tula | 086022046 | Water System L 2 | 1 | 754627 | 546954 | 207673 | 546954 | 3rd Tranche | 211073 | 758027 | 546954 | 211073 | 100% | 100% | 101.6% | 100.5% | 100% | 2006-08-14 | 2006-10-06 | 2006-12-19 | 2007-06-09 | no data | 172 | 56 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tutubigan | 086022047 | Construction of Water System Level II | 1 | 1885339 | 1319737 | 565602 | 1298415 | 3rd Tranche | 575452 | 1873867 | 1298415 | 575452 | 100% | 100% | 101.7% | 99.39% | 100% | 2007-12-13 | 2008-02-12 | 2008-09-05 | 2009-03-16 | n/a | 192 | 277 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tutubigan | 086022047 | Closed Line Canal | 1 | 1495964 | 1047175 | 448789 | 942458 | 2nd Tranche | 380456.79 | 1322914.79 | 942458 | 380456.79 | 100% | 100% | 84.77% | 88.43% | 100% | no data | no data | 2009-03-12 | 2009-05-31 | no data | 80 | 277 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Bangon | 086013001 | Construction of Water System | 1 | 513536.24 | 310150 | 203386.24 | 279135 | 3rd Tranche | 147342.77 | 426477.77 | 279135 | 147342.77 | 100% | 100% | 72.44% | 83.05% | 100% | 2003-11-20 | 2004-02-04 | 2004-05-28 | 2005-07-01 | 2005-08-06 | 399 | 185 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Bangon | 086013001 | River Control | 1 | 826828 | 578780 | 248048 | 578780 | 3rd Tranche | 89024 | 667804 | 578780 | 89024 | 100% | 100% | 35.89% | 80.77% | 100% | 2005-08-06 | 2005-10-17 | 2006-03-08 | 2006-06-21 | no data | 105 | 185 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Botoc | 086013004 | Construction of Water System | 1 | 551775 | 373780 | 177995 | 373780 | 3rd Tranche | 167862.64 | 541642.64 | 373780 | 167862.64 | 100% | 100% | 94.31% | 98.16% | 100% | 2003-11-20 | 2004-02-04 | 2004-06-07 | 2005-02-28 | 2005-05-03 | 266 | 134 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Botoc | 086013004 | Day Care Center | 1 | 457701 | 273701 | 184000 | 273701 | 3rd Tranche | 85462.49 | 359163.49 | 273701 | 85462.49 | 100% | 100% | 46.45% | 78.47% | 100% | 2005-08-06 | 2005-10-17 | 2006-01-09 | 2006-04-18 | no data | 99 | 134 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Bugho | 086013005 | Barangay Road Construction | 1 | 279250 | 130628 | 148622 | 117565.02 | 3rd Tranche | 54389.48 | 171954.5 | 117565.02 | 54389.48 | 100% | 100% | 36.6% | 61.58% | 100% | 2003-11-20 | 2004-02-04 | 2004-08-24 | 2005-07-15 | 2006-06-22 | 325 | 50 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Bugho | 086013005 | Water System | 1 | 603778.5 | 373778.5 | 230000 | 373778.5 | 3rd Tranche | 80000 | 453778.5 | 373778.5 | 80000 | 100% | 100% | 34.78% | 75.16% | 100% | 2005-08-06 | 2005-10-17 | 2006-05-29 | 2006-11-15 | no data | 170 | 50 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Calampong | 086013006 | Construction of Sea Wall | 1 | 771602.5 | 536402.5 | 235200 | 536402.5 | 3rd Tranche | 150335 | 686737.5 | 536402.5 | 150335 | 100% | 100% | 63.92% | 89% | 100% | 2003-11-20 | 2004-02-04 | 2004-09-16 | 2005-07-01 | 2006-06-22 | 288 | 127 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Calampong | 086013006 | Seawall | 1 | 571452.45 | 306895.5 | 264556.95 | 306895.5 | 3rd Tranche | 122781.95 | 429677.45 | 306895.5 | 122781.95 | 100% | 100% | 46.41% | 75.19% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-01 | 2006-05-24 | no data | 53 | 127 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Canlobo | 086013007 | Rice Mill | 1 | 255189 | 143089 | 112100 | 143089 | 3rd Tranche | 102100 | 245189 | 143089 | 102100 | 100% | 100% | 91.08% | 96.08% | 100% | 2005-08-06 | 2005-10-17 | 2006-03-24 | 2006-04-29 | no data | 36 | 47 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Catigawan | 086013008 | Barangay Electrification | 1 | 496776.72 | 333709.84 | 163066.88 | 300338.86 | 3rd Tranche | 80114.91 | 380453.77 | 300338.86 | 80114.91 | 100% | 100% | 49.13% | 76.58% | 100% | 2003-11-20 | 2004-02-04 | 2004-06-26 | 2005-02-04 | 2005-02-04 | 223 | 21 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Catigawan | 086013008 | Water System | 1 | 595462 | 416825 | 178637 | 416825 | 3rd Tranche | 66873.34 | 481392.89 | 416825 | 64567.89 | 100% | 96.55% | 37.44% | 80.84% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-17 | 2006-07-12 | no data | 86 | 22 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Dolores | 086013010 | Day Care Center | 1 | 405705 | 211345 | 194360 | 211345 | 3rd Tranche | 117334.19 | 328679.19 | 211345 | 117334.19 | 100% | 100% | 60.37% | 81.01% | 100% | 2003-11-20 | 2004-02-04 | 2004-06-29 | 2005-02-01 | 2005-04-12 | 217 | 60 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Dolores | 086013010 | River Control | 1 | 370790 | 259553 | 111237 | 259553 | 3rd Tranche | 75709.53 | 335262.53 | 259553 | 75709.53 | 100% | 100% | 68.06% | 90.42% | 100% | 2005-08-06 | 2005-10-17 | 2006-01-16 | 2006-03-04 | no data | 47 | 120 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Lale | 086013011 | Construction of Water System | 1 | 614079 | 440329 | 173750 | 440329 | 3rd Tranche | 113274.18 | 553603.18 | 440329 | 113274.18 | 100% | 100% | 65.19% | 90.15% | 100% | 2003-11-20 | 2004-02-04 | 2004-05-20 | 2005-03-31 | 2006-06-22 | 315 | 115 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Lawaan | 086013012 | Concrete Bridge | 1 | 990704 | 690704 | 300000 | 690704 | 3rd Tranche | 127250 | 817954 | 690704 | 127250 | 100% | 100% | 42.42% | 82.56% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-07 | 2006-07-06 | no data | 90 | 56 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Laygayon | 086013013 | Construction of Water System | 1 | 621448 | 476318 | 145130 | 428686.2 | 3rd Tranche | 83764.9 | 512451.1 | 428686.2 | 83764.9 | 100% | 100% | 57.72% | 82.46% | 100% | 2003-11-20 | 2004-02-04 | 2004-11-23 | 2005-06-20 | 2006-06-22 | 209 | 113 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Laygayon | 086013013 | Day Care Center | 1 | 400430 | 245430 | 155000 | 245430 | 3rd Tranche | 48790.02 | 294220.02 | 245430 | 48790.02 | 100% | 100% | 31.48% | 73.48% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-03 | 2006-07-13 | no data | 101 | 113 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Layo | 086013014 | F/E Hand tractor | 1 | 177161.5 | 113328 | 63833.5 | 113328 | 3rd Tranche | 58993.5 | 172321.5 | 113328 | 58993.5 | 100% | 100% | 92.42% | 97.27% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-03 | 2006-05-09 | no data | 36 | 37 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Loctob | 086013015 | Barangay Road Regravelling | 1 | 800450 | 516450 | 284000 | 516450 | 3rd Tranche | 69421.75 | 585871.75 | 516450 | 69421.75 | 100% | 100% | 24.44% | 73.19% | 100% | 2003-11-20 | 2004-02-04 | 2004-12-01 | 2005-08-20 | 2006-06-22 | 262 | 28 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Madalunot | 086013016 | Construction of Water system | 1 | 445163 | 280363 | 164800 | 280363 | 3rd Tranche | 118597.75 | 398960.75 | 280363 | 118597.75 | 100% | 100% | 71.96% | 89.62% | 100% | 2003-11-20 | 2004-02-04 | 2004-09-13 | 2005-08-15 | 2006-06-22 | 336 | 124 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Madalunot | 086013016 | Health Station | 1 | 546490 | 376490 | 170000 | 376490 | 3rd Tranche | 20340 | 396830 | 376490 | 20340 | 100% | 100% | 11.96% | 72.61% | 100% | 2005-08-06 | 2005-10-17 | 2006-05-18 | 2006-11-30 | no data | 196 | 124 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Magdawat | 086013017 | Footbridge | 1 | 745010 | 549010 | 196000 | 549010 | 3rd Tranche | 119210 | 668220 | 549010 | 119210 | 100% | 100% | 60.82% | 89.69% | 100% | 2003-11-20 | 2004-02-04 | 2004-07-05 | 2005-06-01 | 2005-07-07 | 331 | 57 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Magdawat | 086013017 | Water System | 1 | 631863 | 439863 | 192000 | 439863 | 3rd Tranche | 71819.98 | 511682.98 | 439863 | 71819.98 | 100% | 100% | 37.41% | 80.98% | 100% | 2005-08-06 | 2005-10-17 | 2006-06-19 | 2006-10-15 | no data | 118 | 57 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Mambog | 086013018 | Construction of Water System | 1 | 677594.15 | 481594.15 | 196000 | 433434.73 | 3rd Tranche | 125488.27 | 558923 | 433434.73 | 125488.27 | 100% | 100% | 64.02% | 82.49% | 100% | 2003-11-20 | 2004-02-04 | 2004-05-24 | 2004-12-31 | 2005-04-23 | 221 | 234 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Mambog | 086013018 | Concrete Bridge | 1 | 1052530 | 452530 | 600000 | 452530 | 3rd Tranche | 51000 | 503530 | 452530 | 51000 | 100% | 100% | 8.5% | 47.84% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-17 | 2006-11-30 | no data | 227 | 234 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Manaing | 086013019 | Barangay Road Construction | 1 | 484508 | 318508 | 166000 | 318508 | 3rd Tranche | 87800 | 406308 | 318508 | 87800 | 100% | 100% | 52.89% | 83.86% | 100% | 2003-11-20 | 2004-02-04 | 2004-08-30 | 2005-06-25 | 2005-06-27 | 299 | 62 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Manaing | 086013019 | Rice Mill | 1 | 265000 | 182000 | 83000 | 182000 | 3rd Tranche | 81440 | 263440 | 182000 | 81440 | 100% | 100% | 98.12% | 99.41% | 100% | 2005-08-06 | 2005-10-17 | 2006-02-20 | 2006-03-09 | no data | 17 | 62 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Nabong | 086013026 | 2 Classroom School Building | 1 | 726326 | 501326 | 225000 | 501326 | 3rd Tranche | 91000 | 592326 | 501326 | 91000 | 100% | 100% | 40.44% | 81.55% | 100% | 2005-08-06 | 2005-10-17 | 2006-06-27 | 2006-10-15 | no data | 110 | 175 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Obayan | 086013020 | River Deepening & Grouted Riprap Construction | 1 | 836651.6 | 571523.58 | 265128.02 | 571523.58 | 3rd Tranche | 188324 | 759847.58 | 571523.58 | 188324 | 100% | 100% | 71.03% | 90.82% | 100% | 2003-11-20 | 2004-02-04 | 2004-07-19 | 2005-07-15 | 2005-07-06 | 361 | 197 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Obayan - C5 | 086013020 | Construction of Water System | 5 | 10304670 | 7200000 | 3104670 | 6480000 | 2nd tranche | 2218469 | 6806044.73 | 6480000 | 326044.73 | 100% | 14.7% | 71.46% | 66.05% | 90% | 2006-06-23 | n/a | 2009-05-15 | n/a | n/a | #VALUE! | 535 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Pahug | 086013021 | Day Care Center | 1 | 412186.59 | 247186.59 | 165000 | 247186.59 | 3rd Tranche | 69086.52 | 316273.11 | 247186.59 | 69086.52 | 100% | 100% | 41.87% | 76.73% | 100% | 2003-11-20 | 2004-02-04 | 2004-05-27 | 2005-07-15 | 2006-06-22 | 414 | 123 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Pahug | 086013021 | Water System | 1 | 844570 | 590570 | 254000 | 590570 | 3rd Tranche | 79283.25 | 669853.25 | 590570 | 79283.25 | 100% | 100% | 31.21% | 79.31% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-04 | 2006-07-25 | no data | 112 | 123 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Parasanon | 086013022 | Level II Water System | 1 | 591590 | 433090 | 158500 | 433090 | 3rd Tranche | 97663.25 | 530753.25 | 433090 | 97663.25 | 100% | 100% | 61.62% | 89.72% | 100% | 2003-11-20 | 2004-02-04 | 2004-05-13 | 2005-09-01 | 2006-06-22 | 476 | 228 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Pelaon | 086013023 | Water System | 1 | 630401 | 435860 | 194541 | 435860 | 3rd Tranche | 60000 | 495860 | 435860 | 60000 | 100% | 100% | 30.84% | 78.66% | 100% | 2005-08-06 | 2005-10-17 | 2006-02-14 | 2006-11-15 | no data | 274 | 106 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Poblacion 1 | 086013002 | Retaining Wall | 1 | 441552.3 | 245574.04 | 195978.26 | 245574.04 | 3rd Tranche | 108057.76 | 353631.8 | 245574.04 | 108057.76 | 100% | 100% | 55.14% | 80.09% | 100% | 2003-11-20 | 2004-02-04 | 2004-07-22 | 2006-01-30 | No data | 557 | 119 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Poblacion 2 | 086013003 | Retaining Wall | 1 | 414007.68 | 235093.3 | 178914.38 | 235093.3 | 3rd Tranche | 92084.72 | 327178.02 | 235093.3 | 92084.72 | 100% | 100% | 51.47% | 79.03% | 100% | 2003-11-20 | 2004-02-04 | 2004-09-23 | 2006-01-30 | No data | 494 | 109 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | San Isidro | 086013025 | Barangay Road Construction | 1 | 764335 | 508945 | 255390 | 508945 | 3rd Tranche | 133360.65 | 642305.65 | 508945 | 133360.65 | 100% | 100% | 52.22% | 84.03% | 100% | 2003-11-20 | 2004-02-04 | 2004-06-28 | 2005-03-01 | 2006-06-22 | 246 | 77 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | San Isidro | 086013025 | Seawall | 1 | 1188257 | 819277 | 368980 | 819277 | 3rd Tranche | 62558.32 | 881835.32 | 819277 | 62558.32 | 100% | 100% | 16.95% | 74.21% | 100% | 2005-08-06 | 2005-10-17 | 2006-04-10 | 2006-07-07 | no data | 88 | 77 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Agrupacion | 086016001 | Concrete Pathways | 1 | 446426.02 | 312141 | 134285.02 | 249712.8 | 1st Tranche | 134285.02 | 383997.82 | 249712.8 | 134285.02 | 100% | 100% | 100% | 86.02% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-05 | 2008-11-30 | n/a | 117 | 37 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Arapison | 086016002 | Re-graveling | 1 | 666161 | 466313 | 199848 | 373050.4 | 1st Tranche | 211858 | 584908.4 | 373050.4 | 211858 | 100% | 100% | 106% | 87.8% | 100% | 2007-06-21 | 2007-10-23 | 2008-09-21 | 2009-08-28 | n/a | 341 | 45 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Arapison | 086016002 | Construction of Pathway | 1 | 481943 | 379363 | 102580 | 341426.7 | 2nd Tranche | 118125.96 | 459552.66 | 341426.7 | 118125.96 | 100% | 100% | 115.2% | 95.35% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-05-31 | no data | 69 | 43 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Bahay - C2 | 086016004 | Farm to Market Road | 2 | 10440828.12 | 7658629.31 | 2782198.81 | 5482253.85 | 1st Tranche | 2782198.81 | 7442039.45 | 5482253.85 | 1959785.6 | 100% | 70.44% | 100% | 71.28% | 100% | 2006-08-02 | 2006-08-24 | 2007-12-05 | 2009-04-29 | n/a | 511 | 330 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Balud | 086016005 | Rice Mill | 1 | 505771 | 354040 | 151731 | 354040 | 3rd Tranche | 151731 | 505771 | 354040 | 151731 | 100% | 100% | 100% | 100% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-13 | 2008-10-10 | no data | 58 | 404 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Balud | 086016005 | Construction of Pathway | 1 | 536725 | 414819 | 121906 | 414819 | 3rd Tranche | 137478.94 | 552297.94 | 414819 | 137478.94 | 100% | 100% | 112.8% | 102.9% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-05-31 | no data | 69 | 412 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Burabod | 086016008 | Health Station | 1 | 684325 | 449827 | 234498 | 430452.22 | 3rd Tranche | 232421.45 | 662873.67 | 430452.22 | 232421.45 | 100% | 100% | 99.11% | 96.87% | 100% | 2007-06-21 | 2007-10-23 | 2008-09-09 | 2008-10-28 | n/a | 49 | 350 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Burabod | 086016008 | Road Re-Gravelling with Concrete Footbridge | 1 | 615487 | 433545 | 181942 | 390190.5 | 2nd Tranche | 190563.74 | 580754.24 | 390190.5 | 190563.74 | 100% | 100% | 104.7% | 94.36% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-05-24 | no data | 62 | 350 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cagsumji | 086016035 | School Building | 1 | 1250559.88 | 869379 | 381180.88 | 860648.41 | 2nd Tranche | 332281.07 | 1192929.48 | 860648.41 | 332281.07 | 100% | 100% | 87.17% | 95.39% | 100% | 2007-06-21 | 2007-10-23 | 2008-09-22 | 2008-11-30 | n/a | 69 | 108 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cagsumji | 086016035 | Road Regravelling | 1 | 970095 | 804486 | 165609 | 724037.4 | 2nd Tranche | 214460.75 | 938498.15 | 724037.4 | 214460.75 | 100% | 100% | 129.5% | 96.74% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-08-31 | n/a | 161 | 108 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Campeig | 086016011 | Water system level 2 | 1 | 337336.2 | 239869 | 97467.2 | 215882.1 | 2nd Tranche | 97467.2 | 286146.53 | 215882.1 | 70264.43 | 100% | 72.09% | 100% | 84.83% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-02 | 2008-10-31 | no data | 90 | 33 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Camperito | 086016010 | School Building | 1 | 480000 | 329000 | 151000 | 329000 | 3rd Tranche | 164100 | 493100 | 329000 | 164100 | 100% | 100% | 108.7% | 102.7% | 100% | 2006-08-02 | 2006-08-24 | 2007-01-25 | 2007-06-15 | no data | 141 | 36 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Camperito | 086016010 | Water system level 2 | 1 | 312740.92 | 200193 | 112547.92 | 180173.7 | 2nd Tranche | 113547.92 | 254653.58 | 180173.7 | 74479.88 | 100% | 65.59% | 100.9% | 81.43% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-02 | 2008-10-31 | no data | 90 | 33 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Canmoros | 086016013 | Water system level 2 | 1 | 768267.14 | 559582 | 208685.14 | 447665.6 | 1st Tranche | 209684.84 | 657350.54 | 447665.6 | 209684.94 | 100% | 100% | 100.5% | 85.56% | 100% | 2007-06-21 | 2007-10-23 | 2008-11-03 | 2009-08-28 | n/a | 298 | 36 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Canmoros | 086016013 | Construction of Slope Protection | 1 | 829133 | 635802 | 193331 | 635802 | 3rd Tranche | 210091 | 845893 | 635802 | 210091 | 100% | 100% | 108.7% | 102% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-08-28 | n/a | 158 | 36 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cautod | 086016009 | Day Care Center | 1 | 516300 | 320902.19 | 195397.81 | 320902.19 | 3rd Tranche | 195397.81 | 516300 | 320902.19 | 195397.81 | 100% | 100% | 100% | 100% | 100% | 2006-08-02 | 2006-08-24 | 2006-12-12 | 2007-01-30 | no data | 49 | 609 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cautod | 086016009 | Drainage canal | 1 | 561554 | 389243 | 172311 | 389243 | 3rd Tranche | 174745 | 563988 | 389243 | 174745 | 100% | 100% | 101.4% | 100.4% | 100% | 2007-06-21 | 2007-10-23 | 2008-07-14 | 2008-11-29 | n/a | 138 | 689 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cautod | 086016009 | Construction of Flood Control | 1 | 829159 | 645330 | 183829 | 580797 | 2nd Tranche | 237550.5 | 818347.5 | 580797 | 237550.5 | 100% | 100% | 129.2% | 98.7% | 100% | 2008-11-27 | 2008-12-22 | 2009-05-18 | 2009-06-30 | no data | 43 | 345 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cinco | 086016014 | Construction of Health Station | 1 | 882438 | 751046.74 | 131391.26 | 600837.39 | 1st Tranche | 246743 | 847580.39 | 600837.39 | 246743 | 100% | 100% | 187.8% | 96.05% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-09-30 | n/a | 191 | 98 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Curry | 086016015 | Construction of School Building (1 Classroom) | 1 | 855900 | 625642 | 230258 | 563077.8 | 2nd Tranche | 263968 | 827045.8 | 563077.8 | 263968 | 100% | 100% | 114.6% | 96.63% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-08-31 | n/a | 161 | 127 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Hindang | 086016017 | Construction of School Building (1 Classroom) | 1 | 808491 | 633738 | 174753 | 570363.3 | 2nd Tranche | 187873.53 | 758236.83 | 570363.3 | 187873.53 | 100% | 100% | 107.5% | 93.78% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-08-28 | n/a | 158 | 32 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Ilo | 086016018 | Health Station | 1 | 683325 | 451578 | 231747 | 451578 | 3rd Tranche | 233374 | 684952 | 451578 | 233374 | 100% | 100% | 100.7% | 100.2% | 100% | 2007-06-21 | 2007-10-23 | 2008-09-15 | 2008-10-30 | no data | 45 | 204 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Ilo | 086016018 | Road Regravelling | 1 | 460285 | 356753 | 103532 | 356753 | 3rd Tranche | 121471.74 | 478224.74 | 356753 | 121471.74 | 100% | 100% | 117.3% | 103.9% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-05-31 | no data | 69 | 172 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Inoraguiao | 086016020 | School Building | 1 | 1090180 | 736359 | 353821 | 736359 | 2nd Tranche | 353821 | 1090180 | 736359 | 353821 | 100% | 100% | 100% | 100% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-15 | 2008-10-08 | no data | 54 | 302 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Inoraguiao | 086016020 | Health Station | 1 | 701000 | 497600 | 203400 | 497600 | 3rd Tranche | 210870 | 708470 | 497600 | 210870 | 100% | 100% | 103.7% | 101.1% | 100% | 2006-08-02 | 2006-08-24 | 2006-11-27 | 2007-05-25 | no data | 179 | 277 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Inoraguiao | 086016020 | Construction of Drainage Canal | 1 | 816905 | 629374 | 187531 | 566436.6 | 2nd Tranche | 227547.68 | 793984.28 | 566436.6 | 227547.68 | 100% | 100% | 121.3% | 97.19% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-25 | 2009-05-31 | no data | 67 | 372 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Jolacao | 086016021 | Solar Dryer | 1 | 282769.15 | 206215 | 76554.15 | 176972 | 3rd Tranche | 76554.15 | 249991.33 | 176972 | 73019.33 | 100% | 95.38% | 100% | 88.41% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-05 | 2008-10-23 | no data | 79 | 26 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Lambao | 086016022 | Water System | 1 | 338850.22 | 221080 | 117770.22 | 198972 | 2nd Tranche | 117770.22 | 316742.22 | 198972 | 117770.22 | 100% | 100% | 100% | 93.48% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-30 | 2008-09-30 | no data | 31 | 177 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Lambao | 086016022 | Construction of School Building (2 Classroom) | 1 | 1034597 | 806238 | 228359 | 725614.2 | 2nd Tranche | 262573.92 | 988188.12 | 725614.2 | 262573.92 | 100% | 100% | 115% | 95.51% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-25 | 2009-05-31 | no data | 67 | 220 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Mahayag | 086016024 | Water system level 2 | 1 | 565020 | 395514 | 169506 | 316411.2 | 1st Tranche | 143004 | 459415.2 | 316411.2 | 143004 | 100% | 100% | 84.37% | 81.31% | 100% | 2007-06-21 | 2007-10-23 | 2008-11-03 | 2009-02-27 | no data | 116 | 40 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Matayonas | 086016036 | Concrete Pathways | 1 | 552350 | 386645 | 165705 | 347980.5 | 2nd Tranche | 165795.2 | 513775.7 | 347980.5 | 165795.2 | 100% | 100% | 100.1% | 93.02% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-05 | 2008-11-30 | n/a | 117 | 28 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Monbon | 086016025 | Re-gravelling with Grouted riprap | 1 | 1483997.15 | 1038798 | 445199.15 | 831038.4 | 1st Tranche | 436799.15 | 1267837.55 | 831038.4 | 436799.15 | 100% | 100% | 98.11% | 85.43% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-08 | 2008-10-30 | no data | 83 | 512 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Monbon | 086016025 | Construction of Slope Protection | 1 | 927460 | 680781 | 246679 | 612702.9 | 2nd Tranche | 311349.54 | 924052.44 | 612702.9 | 311349.54 | 100% | 100% | 126.2% | 99.63% | 100% | 2008-11-27 | 2008-12-22 | 2009-04-04 | 2009-05-31 | no data | 57 | 147 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Nabulo | 086016026 | Concrete Canal with Rehabilitation of pathways | 1 | 397251 | 278076 | 119175 | 250267.6 | 2nd Tranche | 119175 | 369442.6 | 250267.6 | 119175 | 100% | 100% | 100% | 93% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-18 | 2008-10-06 | no data | 49 | 51 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Nabulo | 086016026 | Construction of Latrine | 1 | 407465 | 273291 | 134174 | 245961.9 | 1st Tranche | 137482.6 | 383444.5 | 245961.9 | 137482.6 | 100% | 100% | 102.5% | 94.1% | 100% | 2008-11-27 | 2008-12-22 | 2009-04-01 | 2009-05-31 | no data | 60 | 52 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Napuro 2 | 086016037 | Water system level 2 | 1 | 1049259 | 697856 | 351403 | 655323.59 | 1st Tranche | 354419 | 1009742.59 | 655323.59 | 354419 | 100% | 100% | 100.9% | 96.23% | 100% | 2007-06-21 | 2007-10-23 | 2008-10-03 | 2008-11-19 | n/a | 47 | 230 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Napuro 2 | 086016037 | Construction of Drainage Canal | 1 | 1288277 | 1002888 | 285389 | 902599.2 | 2nd Tranche | 309289 | 1211888.2 | 902599.2 | 309289 | 100% | 100% | 108.4% | 94.07% | 100% | 2008-11-27 | 2008-12-22 | 2009-04-01 | 2009-05-31 | no data | 60 | 270 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Napuro | 086016027 | Water System L2 | 1 | 626480 | 424796 | 201684 | 424796 | 3rd Tranche | 204944 | 629740 | 424796 | 204944 | 100% | 100% | 101.6% | 100.5% | 100% | 2006-08-02 | 2006-08-24 | 2007-01-29 | 2009-08-31 | n/a | 945 | 480 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Palale | 086016028 | Concrete footbridge | 1 | 485650 | 328803 | 156847 | 307555.48 | 3rd Tranche | 157341.5 | 464896.98 | 307555.48 | 157341.5 | 100% | 100% | 100.3% | 95.73% | 100% | 2007-06-21 | 2007-10-23 | 2008-07-09 | 2008-08-25 | no data | 47 | 285 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Palale | 086016028 | Construction of School Building (3Classroom) | 1 | 1618730 | 1248536 | 370194 | 1123682.4 | 2nd Tranche | 426841.45 | 1550523.85 | 1123682.4 | 426841.45 | 100% | 100% | 115.3% | 95.79% | 100% | 2008-11-27 | 2008-12-22 | 2009-04-04 | 2009-05-31 | no data | 57 | 120 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Panabatan | 086016029 | Flood Control & Drainage Structure | 1 | 1065422 | 730102.2 | 335319.8 | 730102.2 | 3rd Tranche | 335319.8 | 1065422 | 730102.2 | 335319.8 | 100% | 100% | 100% | 100% | 100% | 2006-08-02 | 2006-08-24 | 2006-11-29 | 2007-02-11 | no data | 74 | 39 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Panaruan | 086016030 | Water system level 2 | 1 | 235534.29 | 168427 | 67107.29 | 151584.3 | 2nd Tranche | 67107.29 | 218691.59 | 151584.3 | 67107.29 | 100% | 100% | 100% | 92.85% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-02 | 2008-10-31 | no data | 90 | 21 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Roxas | 086016031 | Water System L1 | 1 | 170000 | 77500 | 92500 | 77500 | 3rd Tranche | 92500 | 170000 | 77500 | 92500 | 100% | 100% | 100% | 100% | 100% | 2006-08-02 | 2006-08-24 | 2006-11-30 | 2007-01-24 | no data | 55 | 21 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Salvacion | 086016032 | Water System Level 2 | 1 | 304736.08 | 213315 | 91421.08 | 191983.5 | 1st Tranche | 91421.1 | 283404.6 | 191983.5 | 91421.1 | 100% | 100% | 100% | 93% | 100% | 2007-06-21 | 2007-10-23 | 2008-11-10 | 2009-03-31 | no data | 141 | 33 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Salvacion | 086016032 | Construction of School Building (2 Classroom) | 1 | 891326 | 698536 | 192790 | 628682.4 | 2nd Tranche | 211536 | 840218.4 | 628682.4 | 211536 | 100% | 100% | 109.7% | 94.27% | 100% | 2008-11-27 | 2008-12-22 | 2009-04-01 | 2009-08-31 | n/a | 152 | 34 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Solsogon | 086016033 | School Building | 1 | 1073468.9 | 736607 | 336861.9 | 718436.34 | 2nd Tranche | 336862.7 | 1055299.04 | 718436.34 | 336862.7 | 100% | 100% | 100% | 98.31% | 100% | 2007-06-21 | 2007-10-23 | 2008-09-25 | 2008-11-30 | n/a | 66 | 437 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Solsogon | 086016033 | Construction of Drainage Canal | 1 | 1137472 | 960407 | 177065 | 863821.8 | 2nd Tranche | 215876.01 | 1079697.81 | 863821.8 | 215876.01 | 100% | 100% | 121.9% | 94.92% | 100% | 2008-11-27 | 2008-12-22 | 2009-03-23 | 2009-05-31 | no data | 69 | 434 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Sundara | 086016034 | Flood Control & River Landing | 1 | 1111072 | 761470.3 | 349601.7 | 761470.3 | 3rd Tranche | 349601.7 | 1111072 | 761470.3 | 349601.7 | 100% | 100% | 100% | 100% | 100% | 2006-08-02 | 2006-08-24 | 2006-11-28 | 2007-02-07 | no data | 71 | 43 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Sundara | 086016034 | Construction of sea wall | 1 | 821233.42 | 564987 | 256246.42 | 508488.3 | 3rd Tranche | 248059.42 | 756547.72 | 508488.3 | 248059.42 | 100% | 100% | 96.81% | 92.12% | 100% | 2007-06-21 | 2007-10-23 | 2008-08-22 | 2008-10-02 | no data | 41 | 48 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Sundara | 086016034 | Construction of School Building (1 Classroom) | 1 | 753838 | 584938 | 168900 | 584938 | 3rd Tranche | 192629.22 | 777567.22 | 584938 | 192629.22 | 100% | 100% | 114% | 103.1% | 100% | 2008-11-27 | 2008-12-22 | 2009-04-14 | 2009-08-31 | n/a | 139 | 45 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Anibongon | 086017002 | Hand Tractor, 7 units | 1 | 306740 | 193020 | 113720 | 173718 | 1st Tranche | 113720 | 259725.02 | 173718 | 86007.02 | 100% | 75.63% | 100% | 84.67% | 100% | 2006-09-29 | 2006-12-18 | 2007-05-15 | 2007-08-15 | no data | 92 | 259 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Aslum | 086017003 | Water System | 1 | 259080 | 175629 | 83451 | 175629 | 1st Tranche | 85546 | 261175 | 175629 | 85546 | 100% | 100% | 102.5% | 100.8% | 100% | 2006-09-29 | 2006-12-18 | 2007-03-16 | 2007-04-25 | n/a | 40 | 226 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Bagolibas | 086017004 | Drainage System | 1 | 390954 | 263703 | 127251 | 263703 | 1st Tranche | 130686 | 394389 | 263703 | 130686 | 100% | 100% | 102.7% | 100.9% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-26 | 2007-04-27 | no data | 60 | 85 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Binanalan | 086017005 | Water System | 1 | 330949 | 226219 | 104730 | 226219 | 1st Tranche | 113855 | 340074 | 226219 | 113855 | 100% | 100% | 108.7% | 102.8% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-19 | 2007-04-08 | no data | 48 | 241 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Cabacungan | 086017006 | Water System | 1 | 548110 | 405367 | 142743 | 405367 | 1st Tranche | 147910 | 553277 | 405367 | 147910 | 100% | 100% | 103.6% | 100.9% | 100% | 2006-09-29 | 2006-12-18 | 2007-03-15 | 2007-05-09 | no data | 55 | 104 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Cabunga-an | 086017007 | Concrete Pathway | 1 | 530950 | 359071 | 171879 | 359071 | 1st Tranche | 194428.5 | 553499.5 | 359071 | 194428.5 | 100% | 100% | 113.1% | 104.2% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-20 | 2007-05-07 | no data | 76 | 100 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Camayse | 086017008 | Water System | 1 | 524927 | 408810 | 116117 | 408810 | 1st Tranche | 141929.5 | 550739.5 | 408810 | 141929.5 | 100% | 100% | 122.2% | 104.9% | 100% | 2006-09-29 | 2006-12-18 | 2007-04-18 | 2007-06-04 | no data | 47 | 178 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Cansadong | 086017009 | Water System w/ Pathway | 1 | 475645 | 365455 | 110190 | 365455 | 1st Tranche | 120594 | 476025.98 | 365455 | 110570.98 | 100% | 91.69% | 109.4% | 100.1% | 100% | 2006-09-29 | 2006-12-18 | 2007-04-23 | 2007-06-09 | no data | 47 | 69 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Dampigan | 086017011 | Water System | 1 | 806526 | 560361 | 246165 | 560361 | 1st Tranche | 262548 | 798359 | 560361 | 237998 | 100% | 90.65% | 106.7% | 98.99% | 100% | 2006-09-29 | 2006-12-18 | 2007-03-01 | 2007-05-31 | n/a | 91 | 288 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Hinangutdan | 086017013 | Water System | 1 | 210285 | 142524 | 67761 | 142524 | 1st Tranche | 76311 | 218835 | 142524 | 76311 | 100% | 100% | 112.6% | 104.1% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-20 | 2007-04-15 | no data | 54 | 249 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Igang-igang | 086017014 | Sea Wall | 1 | 1783224 | 1088916 | 694308 | 1088916 | 2nd Tranche | 977559 | 2066475 | 1088916 | 977559 | 100% | 100% | 140.8% | 115.9% | 100% | 2006-09-29 | 2006-12-18 | 2007-04-18 | 2007-06-04 | n/a | 47 | 151 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Lupig | 086017016 | Water System | 1 | 546071 | 380525 | 165546 | 380525 | 1st Tranche | 167181 | 547706 | 380525 | 167181 | 100% | 100% | 101% | 100.3% | 100% | 2006-09-29 | 2006-12-18 | 2007-05-02 | 2007-06-10 | no data | 39 | 141 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Magsaysay | 086017017 | Water System | 1 | 880340 | 646119 | 234221 | 640017.2 | 1st Tranche | 293797 | 933814.2 | 640017.2 | 293797 | 100% | 100% | 125.4% | 106.1% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-19 | 2007-04-15 | no data | 55 | 248 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Maligaya | 086017018 | Water System | 1 | 531519 | 388813 | 142706 | 388813 | 1st Tranche | 149968.5 | 538781.5 | 388813 | 149968.5 | 100% | 100% | 105.1% | 101.4% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-20 | 2007-04-18 | no data | 57 | 237 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | New Manunca | 086017019 | Water System | 1 | 492345 | 353123 | 139222 | 353123 | 1st Tranche | 139622 | 492745 | 353123 | 139622 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-09-29 | 2006-12-18 | 2007-05-16 | 2007-07-16 | n/a | 61 | 91 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Pagsulhogon | 086017021 | Water System | 1 | 739513 | 536202 | 203311 | 536202 | 1st Tranche | 213736 | 749938 | 536202 | 213736 | 100% | 100% | 105.1% | 101.4% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-19 | 2007-04-08 | no data | 48 | 76 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Salvacion | 086017023 | Water System | 1 | 513423 | 377791 | 135632 | 377791 | 1st Tranche | 135632 | 513423 | 377791 | 135632 | 100% | 100% | 100% | 100% | 100% | 2006-09-29 | 2006-12-18 | 2007-05-28 | 2008-03-30 | n/a | 307 | 106 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | San Eduardo | 086017024 | Water System | 1 | 565777 | 385632 | 180145 | 385632 | 1st Tranche | 182945 | 568577 | 385632 | 182945 | 100% | 100% | 101.6% | 100.5% | 100% | 2006-09-29 | 2006-12-18 | 2007-03-15 | 2007-05-11 | no data | 57 | 286 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | San Isidro | 086017025 | Water System | 1 | 614061 | 484791 | 129270 | 450187 | 2nd Tranche | 148810 | 598997 | 450187 | 148810 | 100% | 100% | 115.1% | 97.55% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-20 | 2009-06-01 | n/a | 832 | 156 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | San Juan | 086017026 | Farm to Market Road | 1 | 402165 | 281232 | 120933 | 279729.72 | 1st Tranche | 120933 | 400662.72 | 279729.72 | 120933 | 100% | 100% | 100% | 99.63% | 100% | 2006-09-29 | 2006-12-18 | 2007-04-25 | 2007-06-11 | no data | 47 | 97 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | San Pascual | 086017027 | Pathway w/ Footbridge | 1 | 266385 | 191673 | 74712 | 191673 | 1st Tranche | 86177 | 277850 | 191673 | 86177 | 100% | 100% | 115.3% | 104.3% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-26 | 2007-05-12 | no data | 75 | 123 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | San Roque | 086017029 | Water System w/ Pathway | 1 | 341297 | 235953 | 105344 | 235953 | 1st Tranche | 115294 | 351247 | 235953 | 115294 | 100% | 100% | 109.4% | 102.9% | 100% | 2006-09-29 | 2006-12-18 | 2007-04-16 | 2007-06-01 | n/a | 46 | 53 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Tagacay | 086017031 | Water System | 1 | 1093342 | 817188 | 276154 | 817188 | 1st Tranche | 285125.5 | 1102313.5 | 817188 | 285125.5 | 100% | 100% | 103.2% | 100.8% | 100% | 2006-09-29 | 2006-12-18 | 2007-04-24 | 2007-05-24 | no data | 30 | 154 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Tominamos | 086017032 | Water System | 1 | 850476 | 564409 | 286067 | 564409 | 1st Tranche | 331504.59 | 895913.59 | 564409 | 331504.59 | 100% | 100% | 115.9% | 105.3% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-15 | 2007-05-15 | no data | 89 | 260 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Santan Pob. (Zone V) | 086017039 | Water System | 1 | 164600 | 111140 | 53460 | 111140 | 1st Tranche | 53460 | 164600 | 111140 | 53460 | 100% | 100% | 100% | 100% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-15 | 2007-05-15 | no data | 89 | 148 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Bougainvilla Pob. (Zone II) | 086017036 | Water System | 1 | 637243 | 490176 | 147067 | 490176 | 1st Tranche | 189342 | 679518 | 490176 | 189342 | 100% | 100% | 128.7% | 106.6% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-15 | 2007-05-15 | no data | 89 | 99 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Rosal Pob. (Zone IV) | 086017038 | Water System | 1 | 830874 | 636682 | 194192 | 636682 | 1st Tranche | 194192 | 830874 | 636682 | 194192 | 100% | 100% | 100% | 100% | 100% | 2006-09-29 | 2006-12-18 | 2007-02-21 | 2007-05-08 | no data | 76 | 139 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Sta. Rita | 086017 | Bokinggan Pob. (Zone I) | 086017035 | Water System | 1 | 463893 | 329476 | 134417 | 329476 | 1st Tranche | 137704.5 | 467180.5 | 329476 | 137704.5 | 100% | 100% | 102.4% | 100.7% | 100% | 2006-09-29 | 2006-12-18 | 2007-03-01 | 2007-05-31 | no data | 91 | 203 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Alcazar | 086020001 | Construction of Water System L2 | 1 | 227767 | 128689 | 99078 | 115820.1 | 3rd Tranche | 99505.1 | 215325.2 | 115820.1 | 99505.1 | 100% | 100% | 100.4% | 94.54% | 100% | 2006-08-03 | 2006-08-25 | 2007-03-27 | 2007-07-31 | no data | 126 | 75 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Alcazar | 086020001 | IMPROVEMENT OF WHARF | 1 | 203312 | 142319 | 60993 | 128135 | 2nd Tranche | 60997.8 | 189132.8 | 128135 | 60997.8 | 100% | 100% | 100% | 93.03% | 100% | no data | no data | 2009-02-20 | 2009-04-30 | n/a | 69 | 75 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Awang | 086020002 | Construction of Water System L2 | 1 | 460963 | 350000 | 110963 | 350000 | 3rd Tranche | 110963 | 460963 | 350000 | 110963 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-27 | 2007-05-30 | no data | 184 | 31 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Awang | 086020002 | Electrification | 1 | 864762 | 666903 | 197859 | 651303.7 | 1st Tranche | 197859 | 849162.7 | 651303.7 | 197859 | 100% | 100% | 100% | 98.2% | 100% | 2007-06-27 | 2007-09-20 | 2008-09-08 | 2008-12-31 | n/a | 114 | 31 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Awang | 086020002 | CONSTRUCTION OF CONCRETE FOOTBRIDGE | 1 | 128370 | 89859 | 38511 | 71887 | 1st Tranche | 38651 | 110538 | 71887 | 38651 | 100% | 100% | 100.4% | 86.11% | 100% | no data | no data | 2009-04-13 | 2009-06-20 | no data | 68 | 31 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bahay | 086020003 | CONSTRUCTION OF DAYCARE CENTER | 1 | 804112 | 345600 | 458512 | 345600 | 2nd Tranche | 254268 | 599868 | 345600 | 254268 | 100% | 100% | 55.46% | 74.6% | 100% | no data | no data | 2009-01-28 | 2009-04-30 | n/a | 92 | 100 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Balonga-as | 086020004 | Construction of Water System L2 | 1 | 501734 | 351214 | 150520 | 280971 | 1st Tranche | 104650 | 385621 | 280971 | 104650 | 100% | 100% | 69.53% | 76.86% | 100% | 2007-06-27 | 2007-09-20 | 2008-05-08 | 2008-07-31 | no data | 84 | 56 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Balonga-as | 086020004 | CONSTRUCTION OF CONCRETE PATHWALK | 1 | 209933 | 146953 | 62980 | 146953 | 3rd Tranche | 64660 | 211613 | 146953 | 64660 | 100% | 100% | 102.7% | 100.8% | 100% | no data | no data | 2008-12-01 | 2009-02-01 | n/a | 62 | 56 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Balugo | 086020005 | Construction of Water System L2 | 1 | 527447 | 369233 | 158214 | 369233 | 3rd Tranche | 160844 | 530077 | 369233 | 160844 | 100% | 100% | 101.7% | 100.5% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-14 | 2007-05-30 | no data | 167 | 110 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bangon Gote | 086020007 | Construction of Solar Drier | 1 | 204281 | 130293 | 73988 | 130293 | 3rd Tranche | 73988 | 204281 | 130293 | 73988 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-08 | 2007-04-30 | no data | 143 | 22 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bangon Gote | 086020007 | Shallow Well - Jetmatic Pump | 1 | 87444 | 61210 | 26234 | 61210 | 3rd Tranche | 27936.85 | 89146.85 | 61210 | 27936.85 | 100% | 100% | 106.5% | 101.9% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-18 | 2008-04-30 | no data | 43 | 29 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bangon Gote | 086020007 | CONSTRUCTION OF CONCRETE PATHWALK | 1 | 215039 | 150527 | 64512 | 135475 | 2nd Tranche | 64309.15 | 199784.15 | 135475 | 64309.15 | 100% | 100% | 99.69% | 92.91% | 100% | no data | no data | 2009-01-05 | 2009-02-01 | n/a | 27 | 29 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Barangay C (Pob. C) | 086020043 | Construction of Day Care Center | 1 | 648327 | 453829 | 194498 | 445436.1 | 3rd Tranche | 188253 | 633689.1 | 445436.1 | 188253 | 100% | 100% | 96.79% | 97.74% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-10 | 2008-11-30 | n/a | 265 | 41 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Barangay E (Pob. E) | 086020045 | Construction of Day Care Center | 1 | 708542 | 509625 | 198917 | 484501.6 | 1st Tranche | 109543 | 594044.6 | 484501.6 | 109543 | 100% | 100% | 55.07% | 83.84% | 100% | 2007-06-27 | 2007-09-20 | 2009-05-11 | 2009-06-30 | n/a | 50 | 175 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Baras | 086020008 | Construction of Pathwalk | 1 | 591453 | 431992 | 159461 | 431992 | 3rd Tranche | 183241 | 615233 | 431992 | 183241 | 100% | 100% | 114.9% | 104% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-13 | 2007-06-30 | no data | 229 | 55 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Baras | 086020008 | CONSTRUCTION OF LINE CANAL | 1 | 326292 | 228404 | 97888 | 205563.4 | 2nd Tranche | 98888 | 304451.4 | 205563.4 | 98888 | 100% | 100% | 101% | 93.31% | 100% | no data | no data | 2009-02-23 | 2009-04-27 | n/a | 63 | 56 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Binalayan | 086020009 | Construction of Pathwalk | 1 | 303619 | 197889 | 105730 | 197889 | 3rd Tranche | 106710 | 304599 | 197889 | 106710 | 100% | 100% | 100.9% | 100.3% | 100% | 2007-06-27 | 2007-09-20 | 2008-04-07 | 2008-10-31 | n/a | 207 | 52 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Binalayan | 086020009 | CONSTRUCTION OF CAUSEWAY/RIVER LANDING | 1 | 552574 | 411114 | 141460 | 411114 | 3rd Tranche | 56373 | 467487 | 411114 | 56373 | 100% | 100% | 39.85% | 84.6% | 100% | no data | no data | 2009-03-09 | 2009-04-25 | n/a | 47 | 52 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bisitahan | 086020010 | Construction of Drainage Canal | 1 | 827749 | 575975 | 251774 | 575975 | 3rd Tranche | 222842 | 798817 | 575975 | 222842 | 100% | 100% | 88.51% | 96.5% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-27 | 2008-07-31 | no data | 126 | 58 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bisitahan | 086020010 | CONSTRUCTION OF DAYCARE CENTER | 1 | 717118 | 501982 | 215136 | 501982 | 3rd Tranche | 217636 | 719618 | 501982 | 217636 | 100% | 100% | 101.2% | 100.3% | 100% | no data | no data | 2009-01-13 | 2009-04-30 | n/a | 107 | 72 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bonga | 086020011 | Construction of School Building | 1 | 678173 | 485203 | 192970 | 485203 | 3rd Tranche | 192970 | 678173 | 485203 | 192970 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-16 | 2007-05-30 | no data | 195 | 160 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bonga | 086020011 | Construction of Sea Wall | 1 | 2115664 | 1480965 | 634699 | 1432875.54 | 3rd Tranche | 625526 | 2058401.54 | 1432875.54 | 625526 | 100% | 100% | 98.55% | 97.29% | 100% | 2007-06-27 | 2007-09-20 | 2008-05-13 | 2008-09-30 | no data | 140 | 192 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bonga | 086020011 | CONSTRUCTION OF DAYCARE CENTER | 1 | 743655 | 520558 | 223097 | 520558 | 2nd Tranche | 203355.83 | 723913.83 | 520558 | 203355.83 | 100% | 100% | 91.15% | 97.35% | 100% | no data | no data | 2009-01-12 | 2009-04-30 | n/a | 108 | 192 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cabunga-an | 086020013 | CONSTRUCTION OF DRAINAGE CANAL | 1 | 719270 | 503489 | 215781 | 503489 | 1st Tranche | 109138 | 612627 | 503489 | 109138 | 100% | 100% | 50.58% | 85.17% | 100% | no data | no data | 2009-01-09 | 2009-04-23 | n/a | 104 | 144 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cagtutulo | 086020014 | Improvement of Water System L2 | 1 | 478052 | 370000 | 108052 | 370000 | 3rd Tranche | 108052 | 478052 | 370000 | 108052 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-11 | 2007-05-30 | no data | 170 | 56 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cagtutulo | 086020014 | CONSTRUCTION OF DAYCARE CENTER | 1 | 464616 | 325231 | 139385 | 260185 | 3rd Tranche | 151509.25 | 411694.25 | 260185 | 151509.25 | 100% | 100% | 108.7% | 88.61% | 100% | no data | no data | 2009-02-02 | 2009-04-30 | n/a | 87 | 36 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cambatutay Nuevo | 086020018 | Construction of Wharf | 1 | 835360 | 584752 | 250608 | 549892 | 2nd Tranche | 155634 | 705526 | 549892 | 155634 | 100% | 100% | 62.1% | 84.46% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-26 | 2008-08-31 | no data | 158 | 39 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cambatutay Nuevo | 086020018 | IMPROVEMENT OF WATER SUPPLY SYSTEM, LEVEL II | 1 | 53636 | 37545 | 16091 | 30036 | 1st Tranche | 16139 | 46175 | 30036 | 16139 | 100% | 100% | 100.3% | 86.09% | 100% | no data | no data | 2009-03-02 | 2009-03-15 | n/a | 13 | 39 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cambatutay Viejo | 086020019 | Construction of Water System L2 | 1 | 313348 | 160574 | 152774 | 160574 | 3rd Tranche | 152773.4 | 313347.4 | 160574 | 152773.4 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-12 | 2007-07-31 | no data | 231 | 60 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Cambatutay Viejo | 086020019 | CONSTRUCTION OF DRAINAGE CANAL | 1 | 452651 | 316857 | 135794 | 253485.6 | 1st Tranche | 140385 | 393870.6 | 253485.6 | 140385 | 100% | 100% | 103.4% | 87.01% | 100% | no data | no data | 2009-02-19 | 2009-04-30 | n/a | 70 | 25 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Canunghan | 086020020 | Farm to Market Road | 1 | 2498642 | 1791589 | 707053 | 1612430.1 | 2nd Tranche | 257735 | 1870165.1 | 1612430.1 | 257735 | 100% | 100% | 36.45% | 74.85% | 100% | 2006-08-03 | 2006-08-25 | 2007-04-13 | 2008-02-23 | no data | 316 | 38 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Canunghan | 086020020 | CONSTRUCTION OF WATER SUPPLY SYSTEM, LEVEL II | 1 | 226484 | 158539 | 67945 | 126831.2 | 1st Tranche | 75178.82 | 202010.02 | 126831.2 | 75178.82 | 100% | 100% | 110.6% | 89.19% | 100% | no data | no data | 2009-02-10 | 2009-03-30 | n/a | 48 | 51 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Catan-agan | 086020021 | Electrification | 1 | 779426 | 545598 | 233828 | 545598 | 2nd Tranche | 233828 | 779426 | 545598 | 233828 | 100% | 100% | 100% | 100% | 100% | 2007-06-27 | 2007-09-20 | 2008-09-08 | 2008-12-31 | n/a | 114 | 33 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Catan-agan | 086020021 | CONSTRUCTION OF SANITATION FACILITIES | 1 | 534912 | 374438 | 160474 | 299550 | 1st Tranche | 122942.51 | 422492.51 | 299550 | 122942.51 | 100% | 100% | 76.61% | 78.98% | 100% | no data | no data | 2009-03-16 | 2009-04-30 | n/a | 45 | 33 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Dapdap | 086020022 | Construction of Causeway | 1 | 917493 | 623772 | 293721 | 623772 | 3rd Tranche | 337191 | 960963 | 623772 | 337191 | 100% | 100% | 114.8% | 104.7% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-18 | 2007-04-30 | no data | 133 | 138 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Dapdap | 086020022 | Construction of Drainage Canal | 1 | 254920 | 176767 | 78153 | 159090.3 | 2nd Tranche | 74093 | 233183.3 | 159090.3 | 74093 | 100% | 100% | 94.81% | 91.47% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-31 | 2008-07-31 | no data | 122 | 156 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Dapdap | 086020022 | CONSTRUCTION OF TIRE PATHWALK | 1 | 847001 | 592452 | 254549 | 566552 | 2nd Tranche | 276750.1 | 843302.1 | 566552 | 276750.1 | 100% | 100% | 108.7% | 99.56% | 100% | no data | no data | 2009-02-10 | 2009-04-30 | n/a | 79 | 126 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Gallego | 086020023 | Construction of Pathwalk | 1 | 884314 | 619020 | 265294 | 619020 | 3rd Tranche | 110138.42 | 729158.42 | 619020 | 110138.42 | 100% | 100% | 41.52% | 82.45% | 100% | 2007-06-27 | 2007-09-20 | 2008-05-12 | 2008-11-30 | n/a | 202 | 99 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Gallego | 086020023 | CONSTRUCTION OF WATER SUPPLY SYSTEM, LEVEL II | 1 | 246164 | 172314 | 73850 | 165800.8 | 2nd Tranche | 73850 | 239650.8 | 165800.8 | 73850 | 100% | 100% | 100% | 97.35% | 100% | no data | no data | 2009-03-05 | 2009-04-30 | n/a | 56 | 92 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Imelda Pob. (Posgo) | 086020024 | Construction of Sea Wall | 1 | 1570862 | 1058303 | 512559 | 1058303 | 3rd Tranche | 557761 | 1616064 | 1058303 | 557761 | 100% | 100% | 108.8% | 102.9% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-13 | 2007-06-30 | no data | 229 | 146 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Imelda Pob. (Posgo) | 086020024 | Construction of Drainage Canal | 1 | 539833 | 365885 | 173948 | 365885 | 3rd Tranche | 176950.4 | 542835.4 | 365885 | 176950.4 | 100% | 100% | 101.7% | 100.6% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-26 | 2008-09-30 | no data | 188 | 157 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Imelda Pob. (Posgo) | 086020024 | CONSTRUCTION OF DAYCARE CENTER | 1 | 728787 | 551027 | 177760 | 551027 | 3rd Tranche | 172779.08 | 723806.08 | 551027 | 172779.08 | 100% | 100% | 97.2% | 99.32% | 100% | no data | no data | 2008-12-03 | 2009-03-30 | n/a | 117 | 157 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Libucan Dacu | 086020027 | Construction of Barangay Health Station | 1 | 800060 | 543938 | 256122 | 519761 | 2nd Tranche | 120000 | 639761 | 519761 | 120000 | 100% | 100% | 46.85% | 79.96% | 100% | no data | no data | 2009-02-09 | 2009-06-06 | n/a | 117 | 172 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Lahong | 086020026 | CONSTRUCTION OF WATER SUPPLY SYSTEM, LEVEL II | 1 | 530082 | 341012 | 189070 | 272816 | 1st Tranche | 177000 | 449816 | 272816 | 177000 | 100% | 100% | 93.62% | 84.86% | 100% | no data | no data | 2009-04-06 | 2009-05-14 | n/a | 38 | 38 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Libucan Dacu | 086020027 | Construction of Pathwalk | 1 | 790710 | 533960 | 256750 | 533960 | 3rd Tranche | 256890 | 790850 | 533960 | 256890 | 100% | 100% | 100.1% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-17 | 2007-06-30 | no data | 225 | 169 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Libucan Dacu | 086020027 | Construction of School Building | 1 | 1532954 | 1194850 | 338104 | 1194850 | 3rd Tranche | 177400 | 1372250 | 1194850 | 177400 | 100% | 100% | 52.47% | 89.52% | 100% | 2007-06-27 | 2007-09-20 | 2008-02-11 | 2008-10-31 | n/a | 263 | 174 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Libucan Gote | 086020028 | Construction of Water System L2 | 1 | 461000 | 304100 | 156900 | 304100 | 3rd Tranche | 154710 | 458810 | 304100 | 154710 | 100% | 100% | 98.6% | 99.52% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-18 | 2007-07-31 | no data | 225 | 54 |  | 1
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Lucerdoni | 086020025 | Farm to Market Road | 1 | 905637 | 650000 | 255637 | 650000 | 3rd Tranche | 255637 | 905637 | 650000 | 255637 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-28 | 2008-03-30 | no data | 458 | 76 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Lucerdoni | 086020025 | Construction of one(1)-unit, three(2)-classroom School Building | 1 | 1010183 | 707128 | 303055 | 675822 | 3rd Tranche | 169730 | 845552 | 675822 | 169730 | 100% | 100% | 56.01% | 83.7% | 100% | no data | no data | 2009-01-26 | 2009-04-30 | n/a | 94 | 102 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Majacob | 086020029 | Improvement of Water System L2 | 1 | 265463 | 132732 | 132731 | 132732 | 3rd Tranche | 132731 | 265463 | 132732 | 132731 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-20 | 2007-11-30 | no data | 375 | 277 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Majacob | 086020029 | Construction of Day Care Center | 1 | 688252 | 481775 | 206477 | 464275 | 3rd Tranche | 185507 | 649782 | 464275 | 185507 | 100% | 100% | 89.84% | 94.41% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-13 | 2008-07-31 | no data | 140 | 229 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Majacob | 086020029 | Construction of one(1)-unit, three(2)-classroom School Building | 1 | 1006968 | 704877 | 302091 | 673679 | 3rd Tranche | 189271 | 862950 | 673679 | 189271 | 100% | 100% | 62.65% | 85.7% | 100% | no data | no data | 2009-01-15 | 2009-04-11 | n/a | 86 | 272 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Mancares | 086020030 | Construction of Water System L2 | 1 | 342163 | 171082 | 171081 | 171082 | 3rd Tranche | 170990 | 342072 | 171082 | 170990 | 100% | 100% | 99.95% | 99.97% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-20 | 2007-04-30 | no data | 161 | 186 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Mancares | 086020030 | Construction of one(1)-unit, three(2)-classroom School Building | 1 | 1037143 | 726000 | 311143 | 694065 | 3rd Tranche | 209978 | 904043 | 694065 | 209978 | 100% | 100% | 67.49% | 87.17% | 100% | no data | no data | 2009-01-27 | 2009-04-22 | n/a | 85 | 202 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Marabut | 086020031 | Electrification | 1 | 1101621 | 871135 | 230486 | 871135 | 2nd Tranche | 230486 | 1101621 | 871135 | 230486 | 100% | 100% | 100% | 100% | 100% | 2007-06-27 | 2007-09-20 | 2008-09-08 | 2008-12-31 | n/a | 114 | 31 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Oeste A - C2 | 086020032 | Construction of Water System L2 | 2 | 625977 | 422828 | 203149 | 422828 | 3rd Tranche | 215764 | 638592 | 422828 | 215764 | 100% | 100% | 106.2% | 102% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-17 | 2007-07-31 | no data | 256 | 261 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Oeste B | 086020033 | CONSTRUCTION OF DAYCARE CENTER | 1 | 738291 | 570804 | 167487 | 548461 | 2nd Tranche | 61242 | 609703 | 548461 | 61242 | 100% | 100% | 36.57% | 82.58% | 100% | no data | no data | 2009-02-17 | 2009-04-29 | n/a | 71 | 43 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Pajo | 086020038 | Construction of Causeway | 1 | 1577991 | 1227299 | 350692 | 1223510.83 | 3rd Tranche | 50771 | 1274281.83 | 1223510.83 | 50771 | 100% | 100% | 14.48% | 80.75% | 100% | 2007-06-27 | 2007-09-20 | 2008-05-21 | 2009-04-30 | n/a | 344 | 54 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Palencia | 086020039 | Construction of Barangay Health Station | 1 | 790749 | 553524 | 237225 | 553524 | 3rd Tranche | 132010 | 685534 | 553524 | 132010 | 100% | 100% | 55.65% | 86.69% | 100% | no data | no data | 2009-02-23 | 2009-05-28 | n/a | 94 | 118 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion A | 086020041 | Construction of Drainage Canal | 1 | 318483 | 219190 | 99293 | 219190 | 3rd Tranche | 106003 | 325193 | 219190 | 106003 | 100% | 100% | 106.8% | 102.1% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-18 | 2007-06-30 | no data | 194 | 164 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion A | 086020041 | CONSTRUCTION OF TIRE PATHWALK | 1 | 635945 | 445161 | 190784 | 356129 | 2nd Tranche | 145000 | 501129 | 356129 | 145000 | 100% | 100% | 76% | 78.8% | 100% | no data | no data | 2009-02-11 | 2009-04-30 | n/a | 78 | 42 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion B | 086020042 | Construction of Drainage Canal | 1 | 531870 | 362081 | 169789 | 362081 | 3rd Tranche | 104859 | 466940 | 362081 | 104859 | 100% | 100% | 61.76% | 87.79% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-21 | 2007-06-30 | no data | 191 | 185 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion C | 086020043 | Construction of Drainage Canal | 1 | 385185 | 255205 | 129980 | 229684.5 | 2nd Tranche | 129980 | 359664.5 | 229684.5 | 129980 | 100% | 100% | 100% | 93.37% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-18 | 2007-05-30 | no data | 163 | 42 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion D | 086020044 | CONSTRUCTION OF DAYCARE CENTER | 1 | 731062 | 511743 | 219319 | 489641 | 3rd Tranche | 220319 | 709960 | 489641 | 220319 | 100% | 100% | 100.5% | 97.11% | 100% | no data | no data | 2008-12-05 | 2009-03-30 | n/a | 115 | 70 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion E | 086020045 | Construction of Sea Wall | 1 | 2763245 | 1934245 | 829000 | 1934245 | 3rd Tranche | 788869 | 2723114 | 1934245 | 788869 | 100% | 100% | 95.16% | 98.55% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-28 | 2008-02-23 | no data | 452 | 111 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | San Vicente | 086020047 | CONSTRUCTION OF DRAINAGE CANAL | 1 | 733091 | 513163 | 219928 | 513163 | 3rd Tranche | 185942 | 699105 | 513163 | 185942 | 100% | 100% | 84.55% | 95.36% | 100% | no data | no data | 2009-03-11 | 2009-05-21 | n/a | 71 | 152 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Sta. Cruz | 086020048 | Improvement of Water System L2 | 1 | 474474 | 332131 | 142343 | 332131 | 3rd Tranche | 144971 | 477102 | 332131 | 144971 | 100% | 100% | 101.8% | 100.6% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-28 | 2007-11-30 | no data | 367 | 142 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Sta. Cruz | 086020048 | Construction of Day Care Center | 1 | 784094 | 548866 | 235228 | 548866 | 3rd Tranche | 225455.94 | 774321.94 | 548866 | 225455.94 | 100% | 100% | 95.85% | 98.75% | 100% | 2007-06-27 | 2007-09-20 | 2008-07-28 | 2009-04-30 | n/a | 276 | 142 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Sugod | 086020049 | Construction of Rice Mill w/ Structure | 1 | 391485 | 272907 | 118578 | 272907 | 3rd Tranche | 118578 | 391485 | 272907 | 118578 | 100% | 100% | 100% | 100% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-18 | 2007-05-30 | no data | 193 | 149 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Sugod | 086020049 | Construction of Water System L2 | 1 | 492801 | 344961 | 147840 | 310465.1 | 2nd Tranche | 147840 | 458305.1 | 310465.1 | 147840 | 100% | 100% | 100% | 93% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-26 | 2008-08-31 | no data | 158 | 159 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Sugod | 086020049 | Construction of one(1)-unit, three(2)-classroom School Building | 1 | 978770 | 685139 | 293631 | 685139 | 2nd Tranche | 293631 | 978770 | 685139 | 293631 | 100% | 100% | 100% | 100% | 100% | no data | no data | 2008-12-01 | 2009-04-30 | n/a | 150 | 80 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Talinga | 086020050 | Construction of Rice Mill w/ Structure | 1 | 391185 | 270007 | 121178 | 243006.3 | 2nd Tranche | 124618 | 367624.3 | 243006.3 | 124618 | 100% | 100% | 102.8% | 93.98% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-08 | 2007-06-30 | no data | 204 | 84 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Talinga | 086020050 | Construction of Day Care Center | 1 | 660109 | 467499 | 192610 | 467499 | 3rd Tranche | 198195 | 665694 | 467499 | 198195 | 100% | 100% | 102.9% | 100.8% | 100% | 2007-06-27 | 2007-09-20 | 2008-03-29 | 2008-08-30 | no data | 154 | 93 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Tigdaranao | 086020051 | Construction of Day Care Center | 1 | 530039 | 330248 | 199791 | 297223.2 | 2nd Tranche | 193302.89 | 490526.09 | 297223.2 | 193302.89 | 100% | 100% | 96.75% | 92.55% | 100% | 2006-08-03 | 2006-08-25 | 2006-11-13 | 2007-06-30 | no data | 229 | 333 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Tigdaranao | 086020051 | CONSTRUCTION OF WHARF/LANDING AREA | 1 | 1326806 | 937581 | 389225 | 937581 | 3rd Tranche | 274330 | 1211911 | 937581 | 274330 | 100% | 100% | 70.48% | 91.34% | 100% | no data | no data | 2009-03-09 | 2009-06-23 | n/a | 106 | 148 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Tizon | 086020052 | Construction of Water System L2 | 1 | 262045 | 209636 | 52409 | 209636 | 2nd Tranche | 163859 | 373495 | 209636 | 163859 | 100% | 100% | 312.7% | 142.5% | 100% | 2006-08-03 | 2006-08-25 | 2006-12-27 | 2008-03-23 | no data | 452 | 53 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Tizon | 086020052 | Construction of Day Care Center | 1 | 727969 | 508768 | 219201 | 457890.8 | 2nd Tranche | 219236.31 | 677127.11 | 457890.8 | 219236.31 | 100% | 100% | 100% | 93.02% | 100% | 2007-06-27 | 2007-09-20 | 2008-05-21 | 2008-10-31 | n/a | 163 | 63 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Igot | 086021010 | Construction of Brgy. Road w/ Grouted Riprap Both Sides | 1 | 1324300 | 927010 | 397290 | 915976.84 | 2nd Tranche | 433871.91 | 1349848.75 | 915976.84 | 433871.91 | 100% | 100% | 109.2% | 101.9% | 100% | no data | no data | 2008-08-05 | 2008-12-20 | n/a | 137 | 228 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Lamingao | 086021014 | Construction of Sea Wall | 1 | 1590000 | 1113000 | 477000 | 1113000 | 3rd Tranche | 428292.62 | 1541292.62 | 1113000 | 428292.62 | 100% | 100% | 89.79% | 96.94% | 100% | no data | no data | 2008-10-27 | 2009-05-04 | n/a | 189 | 218 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Pacoyoy - C5 | 086021023 | Road Improvement | 5 | 5630000 | 3941000 | 1689000 | 3546900 | 2nd Tranche | 1529243 | 5076143 | 3546900 | 1529243 | 100% | 100% | 90.54% | 90.16% | 100% | no data | no data | 2008-12-18 | 2009-08-30 | n/a | 255 | 732 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | San Andres | 086021034 | Road Improvement | 5 | 5630000 | 3941000 | 1689000 | 3546900 | 2nd Tranche | 1529243 | 5076143 | 3546900 | 1529243 | 100% | 100% | 90.54% | 90.16% | 100% | no data | no data | 2008-12-18 | 2009-08-30 | n/a | 255 | 732 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | San Roque | 086021037 | Road Improvement | 5 | 5630000 | 3941000 | 1689000 | 3546900 | 2nd Tranche | 1529243 | 5076143 | 3546900 | 1529243 | 100% | 100% | 90.54% | 90.16% | 100% | no data | no data | 2008-12-18 | 2009-08-30 | n/a | 255 | 732 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Ulayan | 086021043 | Road Improvement | 5 | 5630000 | 3941000 | 1689000 | 3546900 | 2nd Tranche | 1529243 | 5076143 | 3546900 | 1529243 | 100% | 100% | 90.54% | 90.16% | 100% | no data | no data | 2008-12-18 | 2009-08-30 | n/a | 255 | 732 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Cambaguio | 086021004 | Improvement of Footbridge | 1 | 324100 | 226870 | 97230 | 226870 | 3rd Tranche | 115998 | 342868 | 226870 | 115998 | 100% | 100% | 119.3% | 105.8% | 100% | no data | no data | 2008-09-08 | 2008-12-10 | n/a | 93 | 166 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Plaridel | 086021025 | Construction of Day Care Center | 1 | 666600 | 425260 | 241340 | 405534.94 | 3rd Tranche | 248690 | 654224.94 | 405534.94 | 248690 | 100% | 100% | 103% | 98.14% | 100% | no data | no data | 2008-09-29 | 2009-01-03 | n/a | 96 | 121 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | San Fernando | 086021035 | Construction of 1 Unit 1 Room School Building | 1 | 688200 | 481740 | 206460 | 433566 | 2nd Tranche | 182859 | 616425 | 433566 | 182859 | 100% | 100% | 88.57% | 89.57% | 100% | no data | no data | 2008-09-09 | 2009-02-28 | n/a | 172 | 40 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Sto. Niño | 086021039 | Construction of Brgy. Health Station | 1 | 651600 | 456120 | 195480 | 448508 | 3rd Tranche | 201942 | 650450 | 448508 | 201942 | 100% | 100% | 103.3% | 99.82% | 100% | no data | no data | 2008-08-25 | 2008-12-27 | n/a | 124 | 149 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Tomabe - C3 | 086021042 | Road Improvement | 3 | 5470000 | 3829000 | 1641000 | 1914500 | 1st Tranche | 764719 | 2679219 | 1914500 | 764719 | 100% | 100% | 46.6% | 48.98% | 100% | no data | no data | 2009-03-30 | 2009-11-30 | n/a | 245 | 230 |  | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | Butay | 101802001 | Water System Rehabilitation | 1 | 868217 | 555317 | 312900 | 555317 | 3rd Tranche | 330553.05 | 885870.05 | 555317 | 330553.05 | 100% | 100% | 105.6% | 102% | 100% | 2006-05-30 | 2006-07-05 | 2006-09-05 | 2006-12-29 | no data | 115 | 80 | completed | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | Cabuan | 101802002 | Road Rehabilitation | 1 | 1000000 | 700000 | 300000 | 700000 | 3rd Tranche | 461670.75 | 1161670.75 | 700000 | 461670.75 | 100% | 100% | 153.9% | 116.2% | 100% | 2005-05-24 | 2005-07-05 | 2005-10-10 | 2006-03-04 | 2006-04-18 | 145 | 217 | completed & inaugurated | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | Cabuan | 101802002 | Barangay Market | 1 | 664800 | 434000 | 230800 | 434000 |  | 255786 | 689786 | 434000 | 255786 | 100% | 100% | 110.8% | 103.8% | 100% | 2007-06-28 | n/a | 2007-08-27 | 2008-01-30 | no data | 156 | 227 | completed | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | Cantaan | 101802003 | Road Improvement | 1 | 812000 | 573000 | 239000 | 558886.7 |  | 143957.5 | 702844.2 | 558886.7 | 143957.5 | 100% | 100% | 60.23% | 86.56% | 100% | 2007-06-28 | n/a | 2007-08-23 | 2008-03-30 | no data | 220 | 84 | completed | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | Liong | 101802004 | Sea Wall | 1 | 1056356 | 739376 | 316980 | 739376 | 3rd Tranche | 370832.54 | 1110208.54 | 739376 | 370832.54 | 100% | 100% | 117% | 105.1% | 100% | 2006-05-30 | 2006-07-05 | 2006-09-04 | 2006-12-05 | 2007-06-20 | 92 | 204 | completed & inaugurated | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | Maac | 101802005 | Road Rehabilitation | 1 | 976075 | 683200 | 292875 | 683200 | 3rd Tranche | 470551 | 1153751 | 683200 | 470551 | 100% | 100% | 160.7% | 118.2% | 100% | 2005-05-24 | 2005-07-05 | 2005-10-07 | 2006-02-28 | 2006-04-18 | 144 | 164 | completed & inaugurated | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | North Poblacion | 101802006 | Flood Control/Dike Construction | 1 | 1130230 | 716800 | 413430 | 716800 | 3rd Tranche | 360482 | 1077282 | 716800 | 360482 | 100% | 100% | 87.19% | 95.32% | 100% | 2005-05-24 | 2005-07-05 | 2005-10-05 | 2006-01-26 | 2006-04-18 | 113 | 236 | completed & inaugurated | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | North Poblacion | 101802006 | Drainage System | 1 | 793000 | 570000 | 223000 | 570000 |  | 254367 | 824367 | 570000 | 254367 | 100% | 100% | 114.1% | 104% | 100% | 2007-06-28 | n/a | 2007-08-21 | 2007-12-01 | no data | 102 | 236 | completed | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | South Poblacion | 101802007 | Flood Control/Dike Construction | 1 | 1150527 | 805307 | 345220 | 805307 | 3rd Tranche | 347415.5 | 1152722.5 | 805307 | 347415.5 | 100% | 100% | 100.6% | 100.2% | 100% | 2006-05-30 | 2006-07-05 | 2006-09-06 | 2006-11-25 | 2007-06-21 | 80 | 172 | completed & inaugurated | 1 | MINDANAO
X | 10 | Camiguin | 1018 | Guinsiliban | 101802 | South Poblacion | 101802007 | Flood Control/Dike Construction | 1 | 751500 | 523000 | 228500 | 523000 |  | 229922 | 752922 | 523000 | 229922 | 100% | 100% | 100.6% | 100.2% | 100% | 2007-06-28 | n/a | 2007-09-11 | 2008-03-30 | no data | 201 | 174 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Alegria | 103501001 | Road Concreting | 1 | 1399550 | 980000 | 419550 | 980000 | 3rd Tranche | 198401.94 | 1178401.94 | 980000 | 198401.94 | 100% | 100% | 47.29% | 84.2% | 100% | 2004-01-24 | 2004-06-10 | 2004-08-12 | 2005-02-01 | 2005-04-28 | 173 | 109 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Alegria | 103501001 | Road Concreting | 1 | 719189.39 | 493219.75 | 225969.64 | 493219.75 |  | 58625 | 551844.75 | 493219.75 | 58625 | 100% | 100% | 25.94% | 76.73% | 100% | 2006-07-17 | 2006-08-23 | 2006-11-15 | 2007-03-31 | no data | 136 | 101 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Alegria | 103501001 | Road Concreting | 1 | 724168.16 | 498962.25 | 225205.91 | 498962.25 |  | 173339.75 | 672302 | 498962.25 | 173339.75 | 100% | 100% | 76.97% | 92.84% | 100% | n/a | n/a | 2009-03-14 | 2009-04-30 | 2009-06-23 | 47 | 132 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Babalaya | 103501002 | Road Rehabilitation | 1 | 1937500 | 1315300 | 622200 | 1315300 | 3rd Tranche | 268301.63 | 1583601.63 | 1315300 | 268301.63 | 100% | 100% | 43.12% | 81.73% | 100% | 2004-01-24 | 2004-06-10 | 2004-08-16 | 2005-01-15 | 2005-04-28 | 152 | 106 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Babalaya | 103501002 | Road Improvement | 1 | 704161.1 | 503415.48 | 200745.62 | 503415.38 |  | 186884.76 | 690300.14 | 503415.38 | 186884.76 | 100% | 100% | 93.1% | 98.03% | 100% | n/a | n/a | 2009-03-18 | 2009-05-30 | 2009-06-23 | 73 | 106 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Babalayan Townsite | 103501003 | Suspension Bridge | 1 | 848571.56 | 582454.12 | 266117.44 | 582454.12 | 1st Tranche | 42000 | 624454.12 | 582454.12 | 42000 | 100% | 100% | 15.78% | 73.59% | 100% | 2006-07-17 | 2006-08-23 | 2006-11-27 | 2008-03-30 | no data | 489 | 44 | on going | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Binuni | 103501005 | Barangay Health Station | 1 | 473212 | 286650 | 186562 | 286650 | 3rd Tranche | 192893.5 | 479543.5 | 286650 | 192893.5 | 100% | 100% | 103.4% | 101.3% | 100% | 2004-01-24 | 2004-06-10 | 2004-07-28 | 2005-02-28 | 2005-04-28 | 215 | 296 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Binuni | 103501005 | Day Care Center | 1 | 633834.26 | 515538.31 | 118295.95 | 515538.31 |  | 128734.51 | 644272.82 | 515538.31 | 128734.51 | 100% | 100% | 108.8% | 101.6% | 100% | n/a | n/a | 2009-03-02 | 2009-04-30 | 2009-06-23 | 59 | 312 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Delabayan West | 103501020 | School Building | 1 | 741939 | 565740 | 176199 | 565740 | 3rd Tranche | 123182.12 | 688922.12 | 565740 | 123182.12 | 100% | 100% | 69.91% | 92.85% | 100% | 2004-01-24 | 2004-06-10 | 2004-07-27 | 2005-02-04 | 2005-04-28 | 192 | 52 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Delabayan West | 103501020 | Day Care Center | 1 | 633834.26 | 515538.31 | 118295.95 | 515538.31 |  | 126656.52 | 642194.83 | 515538.31 | 126656.52 | 100% | 100% | 107.1% | 101.3% | 100% | n/a | n/a | 2009-03-18 | 2009-05-30 | 2009-06-23 | 73 | 93 |  | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Demarao | 103501007 | Road Improvement | 1 | 633687.04 | 514938.65 | 118748.39 | 514938.65 |  | 140029.74 | 654968.39 | 514938.65 | 140029.74 | 100% | 100% | 117.9% | 103.4% | 100% | n/a | n/a | 2009-03-23 | 2009-05-30 | 2009-06-23 | 68 | 148 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Demologan | 103501006 | Road Concreting | 1 | 1086290.1 | 807479.88 | 278810.22 | 807479.88 | 1st Tranche | 141256.08 | 948735.96 | 807479.88 | 141256.08 | 100% | 100% | 50.66% | 87.34% | 100% | 2006-07-17 | 2006-08-23 | 2006-09-16 | 2006-11-30 | no data | 75 | 391 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Demologan | 103501006 | Road Concreting | 1 | 732021.95 | 510815.45 | 221206.5 | 510815.45 |  | 197091.35 | 707906.8 | 510815.45 | 197091.35 | 100% | 100% | 89.1% | 96.71% | 100% | n/a | n/a | 2009-03-13 | 2009-04-30 | 2009-06-23 | 48 | 398 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Dimarao | 103501007 | Barangay Health Station | 1 | 473212 | 286650 | 186562 | 286650 | 3rd Tranche | 197058.97 | 483708.97 | 286650 | 197058.97 | 100% | 100% | 105.6% | 102.2% | 100% | 2004-01-24 | 2004-06-10 | 2004-08-26 | 2005-02-28 | 2005-04-28 | 186 | 52 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Esperanza | 103501008 | Road Improvement 1. 379 kms | 1 | 1293942.54 | 889845.34 | 404097.2 | 889845.34 | 3rd Tranche | 189975.15 | 1079820.49 | 889845.34 | 189975.15 | 100% | 100% | 47.01% | 83.45% | 100% | 2005-09-07 | 2005-10-28 | 2005-12-06 | 2006-04-30 | no data | 145 | 432 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Esperanza | 103501008 | Drainage Canal | 1 | 674314.37 | 484625.35 | 189689.02 | 484625.35 |  | 160863.43 | 645488.78 | 484625.35 | 160863.43 | 100% | 100% | 84.8% | 95.73% | 100% | n/a | n/a | 2009-02-26 | 2009-05-30 | 2009-06-23 | 93 | 448 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Kahayag | 103501009 | Road Improvement 3 kms | 1 | 2467543.94 | 1727262.33 | 740281.61 | 1727262.33 | 3rd Tranche | 353384.7 | 2080647.03 | 1727262.33 | 353384.7 | 100% | 100% | 47.74% | 84.32% | 100% | 2005-09-07 | 2005-10-28 | 2005-12-12 | 2006-07-28 | no data | 228 | 127 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Kahayag | 103501009 | Day Care Center | 1 | 633834.26 | 515538.31 | 118295.95 | 515538.31 |  | 112949.22 | 628487.53 | 515538.31 | 112949.22 | 100% | 100% | 95.48% | 99.16% | 100% | n/a | n/a | 2009-03-11 | 2009-04-30 | 2009-06-23 | 50 | 141 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Liangan East | 103501010 | Road Concreting 300 ln.m | 1 | 1108759.48 | 778064.77 | 330694.71 | 778064.77 | 3rd Tranche | 271986.68 | 1050051.45 | 778064.77 | 271986.68 | 100% | 100% | 82.25% | 94.71% | 100% | 2005-09-07 | 2005-10-28 | 2005-12-06 | 2006-02-28 | 2006-04-18 | 84 | 306 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Liangan East | 103501010 | Road Concreting | 1 | 718923.67 | 499082.4 | 219841.27 | 499082.4 |  | 210725.74 | 709808.14 | 499082.4 | 210725.74 | 100% | 100% | 95.85% | 98.73% | 100% | n/a | n/a | 2009-03-13 | 2009-04-30 | 2009-06-23 | 48 | 403 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Mate | 103501013 | Day Care Center | 1 | 557984.76 | 396385.88 | 161598.88 | 396385.88 | 1st Tranche | 126650 | 523035.88 | 396385.88 | 126650 | 100% | 100% | 78.37% | 93.74% | 100% | 2006-07-17 | 2006-08-23 | 2006-11-13 | 2007-02-26 | no data | 105 | 107 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Mate | 103501013 | Health Station | 1 | 689783.8 | 565268.8 | 124515 | 565268.8 |  | 120600.48 | 685869.28 | 565268.8 | 120600.48 | 100% | 100% | 96.86% | 99.43% | 100% | n/a | n/a | 2009-03-09 | 2009-04-30 | 2009-06-23 | 52 | 151 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Mati | 103501013 | Construction of Water system | 1 | 1109386.65 | 599200 | 510186.65 | 599200 | 3rd Tranche | 492653.95 | 1091853.95 | 599200 | 492653.95 | 100% | 100% | 96.56% | 98.42% | 100% | 2004-01-24 | 2004-06-10 | 2004-08-09 | 2005-05-31 | 2005-04-28 | 295 | 117 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Minaulon | 103501016 | Barangay Health Station | 1 | 473212 | 286650 | 186562 | 286650 | 3rd Tranche | 179429.84 | 466079.84 | 286650 | 179429.84 | 100% | 100% | 96.18% | 98.49% | 100% | 2004-01-24 | 2004-06-10 | 2004-08-03 | 2005-02-28 | 2005-04-28 | 209 | 144 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Minaulon | 103501016 | Road Improvement | 1 | 1160449.72 | 1003113.78 | 157335.94 | 1003113.78 |  | 154446.27 | 1157560.05 | 1003113.78 | 154446.27 | 100% | 100% | 98.16% | 99.75% | 100% | n/a | n/a | 2009-03-21 | 2009-04-30 | 2009-06-23 | 40 | 154 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Pagayawan | 103501017 | Road Improvement | 1 | 1585502.85 | 1138874.12 | 446628.73 | 1138874.12 | 1st Tranche | 447771.52 | 1586645.64 | 1138874.12 | 447771.52 | 100% | 100% | 100.3% | 100.1% | 100% | 2006-07-17 | 2006-08-23 | 2006-11-20 | 2007-12-31 | no data | 406 | 143 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Pagayawan | 103501017 | Day Care Center | 1 | 633834.16 | 515538.31 | 118295.85 | 515538.31 |  | 107937.48 | 623475.79 | 515538.31 | 107937.48 | 100% | 100% | 91.24% | 98.37% | 100% | n/a | n/a | 2009-03-10 | 2009-05-30 | 2009-06-23 | 81 | 171 |  | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Poblacion | 103501018 | Drainage Canal | 1 | 1189103.75 | 792356.31 | 396747.44 | 792356.31 |  | 387730.93 | 1180087.24 | 792356.31 | 387730.93 | 100% | 100% | 97.73% | 99.24% | 100% | n/a | n/a | 2009-03-03 | 2009-05-30 | 2009-06-23 | 88 | 514 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Poblacion (Bacolod) | 103501018 | Drainage Canal | 1 | 750190 | 479810 | 270380 | 479810 | 3rd Tranche | 527803.36 | 1007613.36 | 479810 | 527803.36 | 100% | 100% | 195.2% | 134.3% | 100% | 2004-01-24 | 2004-06-10 | 2004-08-23 | 2005-02-28 | 2005-04-28 | 189 | 1210 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Poblacion (Bacolod) | 103501018 | Drainage Canal | 1 | 792954.08 | 489416.88 | 303537.2 | 489416.88 | 1st Tranche | 114250 | 603666.88 | 489416.88 | 114250 | 100% | 100% | 37.64% | 76.13% | 100% | 2006-07-17 | 2006-08-23 | 2006-11-06 | 2007-06-30 | no data | 236 | 1210 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Punod (Maliwanag) | 103501012 | Road improvement 1.1 kms | 1 | 2035907.13 | 1404827.56 | 631079.57 | 1404827.56 | 3rd Tranche | 188346.76 | 1593174.32 | 1404827.56 | 188346.76 | 100% | 100% | 29.85% | 78.25% | 100% | 2005-09-07 | 2005-10-28 | 2006-01-24 | 2006-06-15 | no data | 142 | 63 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Bacolod | 103501 | Rupagan | 103501019 | Road Improvement | 1 | 1253463.66 | 892169.37 | 361294.29 | 892169.37 | 1st Tranche | 77340.75 | 969510.12 | 892169.37 | 77340.75 | 100% | 100% | 21.41% | 77.35% | 100% | 2006-07-17 | 2006-08-23 | 2006-10-07 | 2007-03-31 | no data | 175 | 355 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Bacolod | 103501 | Rupagan | 103501019 | Health Station | 1 | 689783.8 | 565268.8 | 124515 | 565268.8 |  | 128379.67 | 693648.47 | 565268.8 | 128379.67 | 100% | 100% | 103.1% | 100.6% | 100% | n/a | n/a | 2009-03-02 | 2009-04-30 | 2009-06-23 | 59 | 405 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Balabacun | 103514002 | Road Rehabilitation | 1 | 1628633.35 | 1123587.2 | 505046.15 | 898869.76 |  | 93483.75 | 992353.51 | 898869.76 | 93483.75 | 100% | 100% | 18.51% | 60.93% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-03-30 | no data | 515 | 137 | Completed as built | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Balintad | 103514003 | Road Rehabilitation | 1 | 1156445.48 | 808950.16 | 347495.32 | 647160.13 |  | 65021 | 712181.13 | 647160.13 | 65021 | 100% | 100% | 18.71% | 61.58% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-03-30 | no data | 515 | 102 | Completed as built | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Lininding | 103514013 | Road Rehabilitation | 1 | 1254919.3 | 878789.6 | 376129.7 | 836564 |  | 380129.7 | 1216693.7 | 836564 | 380129.7 | 100% | 100% | 101.1% | 96.95% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-03-30 | no data | 515 | 229 | Completed as built | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Madaya | 103514015 | Road Rehabilitation | 1 | 1741260.45 | 1210250 | 531010.45 | 1210250 | 3rd Tranche | 292995.99 | 1503245.99 | 1210250 | 292995.99 | 100% | 100% | 55.18% | 86.33% | 100% | 2003-04-28 | 2003-10-08 | 2004-05-26 | 2005-01-30 | 2005-04-28 | 249 | 61 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Maganding | 103514016 | Road Rehabilitation | 1 | 1016337.605 | 712829.255 | 303508.35 | 712829.255 | 3rd Tranche | 138951.92 | 851781.175 | 712829.255 | 138951.92 | 100% | 100% | 45.78% | 83.81% | 100% | 2003-04-28 | 2003-10-08 | 2004-08-18 | 2005-07-26 | 2005-07-28 | 342 | 62 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Matampay | 103514019 | Water System L2 | 1 | 1347415.53 | 943341.93 | 404073.6 | 849007.73 |  | 406813.6 | 1255821.33 | 849007.73 | 406813.6 | 100% | 100% | 100.7% | 93.2% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-06-30 | no data | 607 | 95 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | North Cadulawan | 103514021 | Brgy. Water System | 1 | 1114385.8 | 770385 | 344000.8 | 770385 | 3rd Tranche | 21429.17 | 791814.17 | 770385 | 21429.17 | 100% | 100% | 6.229% | 71.05% | 100% | 2003-04-28 | 2003-10-08 | 2004-01-02 | 2005-07-26 | 2005-07-28 | 571 | 54 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Old Poblacion | 103514020 | Road Rehabilitation | 1 | 1250884.8 | 863810 | 387074.8 | 863810 | 3rd Tranche | 83076.7 | 946886.7 | 863810 | 83076.7 | 100% | 100% | 21.46% | 75.7% | 100% | 2003-04-28 | 2003-10-08 | 2004-09-04 | 2005-04-01 | 2005-04-28 | 209 | 400 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Panggao | 103514022 | Road Rehabilitation | 1 | 1366160.01 | 956313.92 | 409846.09 | 728252.8 |  | 88718.25 | 816971.05 | 728252.8 | 88718.25 | 100% | 100% | 21.65% | 59.8% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2007-04-30 | no data | 180 | 220 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Pantao | 103514023 | Road Rehabilitation | 1 | 1226239.3 | 936140 | 290099.3 | 936140 | 3rd Tranche | 298622.61 | 1234762.61 | 936140 | 298622.61 | 100% | 100% | 102.9% | 100.7% | 100% | 2003-04-28 | 2003-10-08 | 2004-07-05 | 2005-07-28 | 2005-07-28 | 388 | 66 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Pantao-A-Munai | 103514024 | Water System L3 | 1 | 542380.31 | 390134.02 | 152246.29 | 372237.52 |  | 153246.29 | 525483.81 | 372237.52 | 153246.29 | 100% | 100% | 100.7% | 96.88% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-04-30 | no data | 546 | 44 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Pindolonan | 103514026 | Road Rehabilitation | 1 | 1663125.45 | 1152285 | 510840.45 | 1152285 | 3rd Tranche | 180344.08 | 1332629.08 | 1152285 | 180344.08 | 100% | 100% | 35.3% | 80.13% | 100% | 2003-04-28 | 2003-10-08 | 2003-11-29 | 2005-04-01 | 2005-04-28 | 489 | 184 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Punong | 103514027 | Spillway Bridge | 1 | 567578.235 | 404710.915 | 162867.32 | 404710.915 | 3rd Tranche | 117389.5 | 522100.415 | 404710.915 | 117389.5 | 100% | 100% | 72.08% | 91.99% | 100% | 2003-04-28 | 2003-10-08 | 2004-11-17 | 2005-04-01 | 2005-07-28 | 135 | 65 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Ramain | 103514028 | Road Rehabilitation | 1 | 1243501.8 | 847720 | 395781.8 | 847720 | 3rd Tranche | 237285.18 | 1085005.18 | 847720 | 237285.18 | 100% | 100% | 59.95% | 87.25% | 100% | 2003-04-28 | 2003-10-08 | 2004-02-14 | 2005-07-26 | 2005-07-28 | 528 | 129 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Sandigamunai | 103514029 | Road Rehabilitation | 1 | 1355444.13 | 857895 | 497549.13 | 772105.5 | 2nd Tranche | 388352.04 | 1160457.54 | 772105.5 | 388352.04 | 100% | 100% | 78.05% | 85.61% | 100% | 2003-04-28 | 2003-10-08 | 2004-01-27 | 2005-04-01 | 2005-07-28 | 430 | 88 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Tambo | 103514032 | Public Market | 1 | 1066038.44 | 754706 | 311332.44 | 718305.6 |  | 312332.44 | 1030638.04 | 718305.6 | 312332.44 | 100% | 100% | 100.3% | 96.68% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2007-04-30 | no data | 180 | 248 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Tamparan | 103514033 | Road Rehabilitation | 1 | 1487992.48 | 1041218.16 | 446774.32 | 1001022.82 |  | 457016 | 1458038.82 | 1001022.82 | 457016 | 100% | 100% | 102.3% | 97.99% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-02-01 | no data | 457 | 176 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Munai | 103514 | Taporog | 103514034 | Road Rehabilitation | 1 | 1287956.9 | 902912.8 | 385044.1 | 722330.24 |  | 90602.5 | 812932.74 | 722330.24 | 90602.5 | 100% | 100% | 23.53% | 63.12% | 100% | 2006-07-17 | 2006-07-17 | 2006-11-01 | 2008-03-30 | no data | 515 | 132 | Completed as built | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Alowin | 103517001 | Road Improvement | 1 | 1406654.95 | 984135 | 422519.95 | 964135 | 1st Tranche | 422519.95 | 1386654.95 | 964135 | 422519.95 | 100% | 100% | 100% | 98.58% | 100% | 2006-06-27 | 2006-06-27 | 2006-10-26 | 2007-04-30 | no data | 186 | 95 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Kablangan | 103517008 | Road Rehabilitation | 1 | 1102415 | 771287.75 | 331127.25 | 771287.75 | 3rd Tranche | 273572 | 1044859.75 | 771287.75 | 273572 | 100% | 100% | 82.62% | 94.78% | 100% | 2004-02-26 | 2004-04-29 | 2004-08-17 | 2006-03-31 | 2006-04-18 | 591 | 108 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Cadayonan | 103517009 | Road Rehabilitation | 1 | 1736072.6 | 1219261.3 | 516811.3 | 1219261.3 | 3rd Tranche | 214500 | 1433761.3 | 1219261.3 | 214500 | 100% | 100% | 41.5% | 82.59% | 100% | 2004-02-26 | 2004-04-29 | 2004-08-25 | 2006-04-30 | no data | 613 | 83 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Caromatan | 103517003 | Road Rehabilitation | 1 | 1249390.8 | 805362.7 | 444028.1 | 805362.7 | 3rd Tranche | 198011 | 1003373.7 | 805362.7 | 198011 | 100% | 100% | 44.59% | 80.31% | 100% | 2004-02-26 | 2004-04-29 | 2004-09-20 | 2005-12-30 | 2005-12-01 | 466 | 149 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Daramba | 103517004 | Road Rehabilitation | 1 | 1619101.6 | 1129460.8 | 489640.8 | 1129460.8 | 3rd Tranche | 111032 | 1240492.8 | 1129460.8 | 111032 | 100% | 100% | 22.68% | 76.62% | 100% | 2004-02-26 | 2004-04-29 | 2004-08-16 | 2006-03-31 | 2006-04-18 | 592 | 120 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Madaya | 103517015 | Road Improvement | 1 | 1785432.81 | 1248492.4 | 536940.41 | 1223492.4 |  | 536940.41 | 1760432.81 | 1223492.4 | 536940.41 | 100% | 100% | 100% | 98.6% | 100% | 2006-06-27 | 2006-06-27 | 2006-10-09 | 2008-03-30 | no data | 538 | 68 | works suspended due to unstable peace & order situation | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Maliwanag | 103517016 | Road Improvement | 1 | 1946696.08 | 1361294.9 | 585401.18 | 1089028.77 | 1st Tranche | 222130.22 | 1311158.99 | 1089028.77 | 222130.22 | 100% | 100% | 37.94% | 67.35% | 100% | 2006-06-27 | 2006-06-27 | 2006-08-26 | 2008-03-30 | no data | 582 | 101 | completed as built | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Nunungan | 103517018 | Road Rehabilitation | 1 | 2095572 | 1409111.25 | 686460.75 | 1409111.24 | 3rd Tranche | 153246.5 | 1562357.74 | 1409111.24 | 153246.5 | 100% | 100% | 22.32% | 74.56% | 100% | 2004-02-26 | 2004-04-29 | 2004-08-20 | 2006-08-31 | no data | 741 | 74 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Pantaon | 103517020 | Road Rehabilitation | 1 | 915367.6 | 630213.8 | 285153.8 | 630213.8 | 3rd Tranche | 197850 | 828063.8 | 630213.8 | 197850 | 100% | 100% | 69.38% | 90.46% | 100% | 2004-02-26 | 2004-04-29 | 2004-08-24 | 2006-05-31 | no data | 645 | 117 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Pendolonan | 103517023 | Road Improvement | 1 | 1041143.7 | 727673.1 | 313470.6 | 715673.1 | 1st Tranche | 313470 | 1029143.1 | 715673.1 | 313470 | 100% | 100% | 100% | 98.85% | 100% | 2006-06-27 | 2006-06-27 | 2006-08-23 | 2007-01-31 | no data | 161 | 95 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Pened | 103517021 | Road Improvement | 1 | 1422147.88 | 993275.68 | 428872.2 | 973275.68 | 1st Tranche | 438624 | 1411899.68 | 973275.68 | 438624 | 100% | 100% | 102.3% | 99.28% | 100% | 2006-06-27 | 2006-06-27 | 2006-08-28 | 2007-09-30 | no data | 398 | 42 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Piangamangaan | 103517022 | Road Rehabilitation | 1 | 870312.3 | 605803.65 | 264508.65 | 605803.65 | 3rd Tranche | 216840 | 822643.65 | 605803.65 | 216840 | 100% | 100% | 81.98% | 94.52% | 100% | 2004-02-26 | 2004-04-29 | 2004-08-25 | 2006-03-31 | no data | 583 | 68 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Tagoranao | 103517022 | Road Improvement | 1 | 1793627.85 | 1174292.5 | 619335.35 | 939434 | 1st Tranche | 208059.43 | 1147493.43 | 939434 | 208059.43 | 100% | 100% | 33.59% | 63.98% | 100% | 2006-06-27 | 2006-06-27 | 2006-07-26 | 2008-04-30 | no data | 644 | 115 | completed as built | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Tangclao | 103517027 | Road Rehabilitation | 1 | 1746672.6 | 1229381.3 | 517291.3 | 1229381.3 | 3rd Tranche | 129340 | 1358721.3 | 1229381.3 | 129340 | 100% | 100% | 25% | 77.79% | 100% | 2004-02-26 | 2004-04-29 | 2004-10-25 | 2006-06-23 | no data | 606 | 64 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Poona-Piagapo | 103517 | Timbangalan | 103517028 | Road Improvement | 1 | 1873140.54 | 1309483.6 | 563656.94 | 1309483.6 | 1st Tranche | 563656.94 | 1873140.54 | 1309483.6 | 563656.94 | 100% | 100% | 100% | 100% | 100% | 2006-06-27 | 2006-06-27 | 2006-07-20 | 2007-04-30 | no data | 284 | 99 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Barandia | 103518001 | Road Improvement | 1 | 1115281.69 | 784553.93 | 330727.76 | 784553.93 | 3rd Tranche | 228005.76 | 1012559.69 | 784553.93 | 228005.76 | 100% | 100% | 68.94% | 90.79% | 100% | 2005-08-30 | 2005-11-07 | 2006-01-16 | 2006-03-17 | 2006-04-18 | 60 | 50 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Bulacon | 103518002 | Water System Level 2 | 1 | 1488798.57 | 1048638.38 | 440160.19 | 1048638.38 | 3rd Tranche | 331445 | 1380083.38 | 1048638.38 | 331445 | 100% | 100% | 75.3% | 92.7% | 100% | 2005-08-30 | 2005-11-07 | 2006-01-03 | 2006-07-31 | no data | 209 | 69 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Bulacon | 103518002 | Road Improvement | 1 | 809800 | 565402.08 | 244397.92 | 565402.08 |  | 163220.34 | 728622.42 | 565402.08 | 163220.34 | 100% | 100% | 66.78% | 89.98% | 100% | n/a | n/a | 2009-01-23 | 2009-05-30 | 2009-06-22 | 127 | 71 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Buntong | 103518003 | Road Regravelling | 1 | 1989592.44 | 1412947.36 | 576645.08 | 1412947.36 | 3rd Tranche | 358714.86 | 1771662.22 | 1412947.36 | 358714.86 | 100% | 100% | 62.21% | 89.05% | 100% | 2004-03-03 | 2004-06-17 | 2004-11-30 | 2005-04-16 | 2005-04-28 | 137 | 213 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Buntong | 103518003 | Water System L2 | 1 | 774777.15 | 390191.36 | 384585.79 | 390191.36 |  | 374925.79 | 765117.15 | 390191.36 | 374925.79 | 100% | 100% | 97.49% | 98.75% | 100% | 2006-08-11 | 2006-10-06 | 2006-11-05 | 2008-05-30 | no data | 572 | 221 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Calimodan | 103518004 | Road | 1 | 1443330.62 | 1014735.4 | 428595.22 | 1014735.4 |  | 503034.06 | 1517769.46 | 1014735.4 | 503034.06 | 100% | 100% | 117.4% | 105.2% | 100% | 2006-08-11 | 2006-10-06 | 2006-11-22 | 2007-04-30 | no data | 159 | 173 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Camp III | 103518005 | Road Concreting | 1 | 1156699.5 | 940559 | 216140.5 | 940559 |  | 236676.5 | 1177235.5 | 940559 | 236676.5 | 100% | 100% | 109.5% | 101.8% | 100% | n/a | n/a | 2009-01-29 | 2009-04-30 | 2009-06-22 | 91 | 210 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Camp III | 103518005 | Water System L2 | 1 | 2284242.3 | 1582456.95 | 701785.35 | 1582456.95 |  | 706225.35 | 2288682.3 | 1582456.95 | 706225.35 | 100% | 100% | 100.6% | 100.2% | 100% | 2006-08-11 | 2006-10-06 | 2006-11-04 | 2007-08-30 | no data | 299 | 235 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Curva Miagao | 103518006 | Road | 1 | 1657575.07 | 1133585.89 | 523989.18 | 1133585.89 |  | 636803.35 | 1770389.24 | 1133585.89 | 636803.35 | 100% | 100% | 121.5% | 106.8% | 100% | 2006-08-11 | 2006-10-06 | 2006-10-23 | 2007-03-31 | no data | 159 | 288 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Curva Miagao | 103518006 | Water System Level I | 1 | 291083.82 | 228460 | 62623.82 | 228460 |  | 63743.82 | 292203.82 | 228460 | 63743.82 | 100% | 100% | 101.8% | 100.4% | 100% | n/a | n/a | 2009-01-16 | 2009-04-30 | 2009-06-22 | 104 | 336 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Daligdigan | 103518007 | Road Concreting | 1 | 1267909.68 | 883832.87 | 384076.81 | 883832.87 | 3rd Tranche | 380352.32 | 1264185.19 | 883832.87 | 380352.32 | 100% | 100% | 99.03% | 99.71% | 100% | 2005-08-30 | 2005-11-07 | 2005-11-22 | 2006-03-10 | 2006-04-18 | 108 | 74 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Daligdigan | 103518007 | Road Improvement | 1 | 1237189.88 | 996145 | 241044.88 | 996145 |  | 265891.88 | 1262036.88 | 996145 | 265891.88 | 100% | 100% | 110.3% | 102% | 100% | n/a | n/a | 2009-01-27 | 2009-05-30 | 2009-06-22 | 123 | 156 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Inasagan | 103518025 | Road Rehab. & concreting | 1 | 1437714.4 | 1003660.95 | 434053.45 | 1003660.95 | 3rd Tranche | 403464.8 | 1407125.75 | 1003660.95 | 403464.8 | 100% | 100% | 92.95% | 97.87% | 100% | 2005-08-30 | 2005-11-07 | 2005-11-21 | 2006-03-10 | 2006-04-18 | 109 | 354 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Kilala | 103518008 | Road Concreting | 1 | 798908.71 | 559236.11 | 239672.6 | 559236.11 | 3rd Tranche | 209380.38 | 768616.49 | 559236.11 | 209380.38 | 100% | 100% | 87.36% | 96.21% | 100% | 2004-03-03 | 2004-06-17 | 2004-12-10 | 2005-03-01 | 2005-04-28 | 81 | 54 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Kilala | 103518008 | Road | 1 | 1583370.93 | 1079375.9 | 503995.03 | 1079375.9 |  | 548995.03 | 1628370.93 | 1079375.9 | 548995.03 | 100% | 100% | 108.9% | 102.8% | 100% | 2006-08-11 | 2006-10-06 | 2006-11-15 | 2007-07-31 | no data | 258 | 54 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Kilala | 103518008 | Road Concreting | 1 | 1304900 | 911479.6 | 393420.4 | 911479.6 |  | 221002.54 | 1132482.14 | 911479.6 | 221002.54 | 100% | 100% | 56.17% | 86.79% | 100% | n/a | n/a | 2009-01-31 | 2009-05-30 | 2009-06-22 | 119 | 92 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mabatao | 103518009 | Water System Level 2 | 1 | 1384360.22 | 967564.48 | 416795.74 | 967564.48 | 3rd Tranche | 378429.5 | 1345993.98 | 967564.48 | 378429.5 | 100% | 100% | 90.79% | 97.23% | 100% | 2005-08-30 | 2005-11-07 | 2006-01-03 | 2006-04-15 | 2006-04-18 | 102 | 96 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Mabatao | 103518009 | Acquisition of Portable Corn Sheller with warehouse (4mx6m) | 1 | 445848.5 | 346458.33 | 99390.17 | 346458.33 |  | 95890.17 | 442348.5 | 346458.33 | 95890.17 | 100% | 100% | 96.48% | 99.21% | 100% | n/a | n/a | 2009-01-24 | 2009-05-30 | 2009-06-22 | 126 | 115 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Madaya | 103518010 | Road Re-gravelling | 1 | 1486095.1 | 1040231.55 | 445863.55 | 1040231.55 | 3rd Tranche | 135565.73 | 1175797.28 | 1040231.55 | 135565.73 | 100% | 100% | 30.41% | 79.12% | 100% | 2004-03-03 | 2004-06-17 | 2004-11-04 | 2005-03-14 | 2005-04-28 | 130 | 100 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Madaya | 103518010 | Road Improvement | 1 | 1244060.65 | 1002163 | 241897.65 | 1002163 |  | 263656.13 | 1265819.13 | 1002163 | 263656.13 | 100% | 100% | 109% | 101.7% | 100% | n/a | n/a | 2009-01-22 | 2009-05-30 | 2009-06-22 | 128 | 182 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mamaanon | 103518011 | Road Re-gravelling | 1 | 1451302.62 | 1006841.2 | 444461.42 | 1006841.2 | 3rd Tranche | 161477.79 | 1168318.99 | 1006841.2 | 161477.79 | 100% | 100% | 36.33% | 80.5% | 100% | 2004-03-03 | 2004-06-17 | 2004-10-31 | 2005-03-01 | 2005-04-28 | 121 | 106 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Mapantao | 103518012 | Road Concreting | 1 | 719671 | 503769.7 | 215901.3 | 503769.7 | 3rd Tranche | 197632.09 | 701401.79 | 503769.7 | 197632.09 | 100% | 100% | 91.54% | 97.46% | 100% | 2004-03-03 | 2004-06-17 | 2004-11-08 | 2005-03-01 | 2005-04-28 | 113 | 49 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Mapantao | 103518012 | Road Improvement | 1 | 1339500 | 937653 | 401847 | 937653 |  | 250598.72 | 1188251.72 | 937653 | 250598.72 | 100% | 100% | 62.36% | 88.71% | 100% | n/a | n/a | 2009-01-30 | 2009-05-30 | 2009-06-22 | 120 | 115 |  | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Mindalano | 103518013 | Road Improvement | 1 | 1674875 | 1168197.48 | 506677.52 | 1168197.48 |  | 342370.86 | 1510568.34 | 1168197.48 | 342370.86 | 100% | 100% | 67.57% | 90.19% | 100% | n/a | n/a | 2009-01-25 | 2009-05-30 | 2009-06-22 | 125 | 160 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Padianan | 103518014 | Road Rehab. & concreting | 1 | 1237884.86 | 863602.91 | 374281.95 | 863602.91 | 3rd Tranche | 318070.48 | 1181673.39 | 863602.91 | 318070.48 | 100% | 100% | 84.98% | 95.46% | 100% | 2005-08-30 | 2005-11-07 | 2005-11-21 | 2006-03-10 | 2006-04-18 | 109 | 158 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Padianan | 103518014 | Road Improvement | 1 | 890650.66 | 687806.52 | 202844.14 | 687806.52 |  | 225744.14 | 913550.66 | 687806.52 | 225744.14 | 100% | 100% | 111.3% | 102.6% | 100% | n/a | n/a | 2009-01-24 | 2009-05-30 | 2009-06-22 | 126 | 250 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Pagalongan | 103518015 | Road Concreting | 1 | 719671 | 503769.7 | 215901.3 | 503769.7 | 3rd Tranche | 133695.49 | 637465.19 | 503769.7 | 133695.49 | 100% | 100% | 61.92% | 88.58% | 100% | 2004-03-03 | 2004-06-17 | 2004-11-19 | 2005-04-21 | 2005-04-28 | 153 | 120 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Pagalongan | 103518015 | Day Care Center | 1 | 633658.36 | 508565 | 125093.36 | 508565 |  | 126093.36 | 634658.36 | 508565 | 126093.36 | 100% | 100% | 100.8% | 100.2% | 100% | n/a | n/a | 2009-01-19 | 2009-03-30 | 2009-06-22 | 70 | 454 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Pagayawan | 103518016 | Road Re-gravelling | 1 | 1252863.96 | 783028.42 | 469835.54 | 783028.42 | 3rd Tranche | 125103.23 | 908131.65 | 783028.42 | 125103.23 | 100% | 100% | 26.63% | 72.48% | 100% | 2004-03-03 | 2004-06-17 | 2004-10-31 | 2005-04-20 | 2005-04-28 | 171 | 145 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Pagayawan | 103518016 | Solar Drier with warehouse | 1 | 594600 | 416212 | 178388 | 416212 |  | 122984.53 | 539196.53 | 416212 | 122984.53 | 100% | 100% | 68.94% | 90.68% | 100% | n/a | n/a | 2009-01-18 | 2009-03-30 | 2009-06-22 | 71 | 94 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Panaliwad-on | 103518017 | Road | 1 | 939723.46 | 657720.53 | 282002.93 | 657720.53 | 1st Tranche | 345116.91 | 1002837.44 | 657720.53 | 345116.91 | 100% | 100% | 122.4% | 106.7% | 100% | 2006-08-11 | 2006-10-06 | 2006-10-20 | 2007-03-31 | no data | 162 | 174 | completed | 1 | MINDANAO
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Panaliwad-on | 103518017 | Water System Level I | 1 | 294487.11 | 231435 | 63052.11 | 231435 |  | 63952.11 | 295387.11 | 231435 | 63952.11 | 100% | 100% | 101.4% | 100.3% | 100% | n/a | n/a | 2009-01-20 | 2009-05-30 | 2009-06-23 | 130 | 178 |  | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Pangantapan | 103518018 | Road | 1 | 1377249.81 | 951451.77 | 425798.04 | 951451.77 |  | 480028.13 | 1431479.9 | 951451.77 | 480028.13 | 100% | 100% | 112.7% | 103.9% | 100% | 2006-08-11 | 2006-10-06 | 2006-10-21 | 2007-04-30 | no data | 191 | 55 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Pansor | 103518019 | Road Re-gravelling | 1 | 2003118.97 | 1179000 | 824118.97 | 1179000 | 3rd Tranche | 223284.97 | 1402284.97 | 1179000 | 223284.97 | 100% | 100% | 27.09% | 70.01% | 100% | 2004-03-03 | 2004-06-17 | 2004-12-12 | 2005-05-15 | 2005-04-28 | 154 | 154 | completed & inaugurated | 1
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Pansor | 103518019 | Road Improvement | 1 | 1822600 | 1275791.19 | 546808.81 | 1275791.19 |  | 278182.98 | 1553974.17 | 1275791.19 | 278182.98 | 100% | 100% | 50.87% | 85.26% | 100% | n/a | n/a | 2009-01-28 | 2009-05-30 | 2009-06-22 | 122 | 259 |  | 1
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Patidon | 103518020 | Construction of Spillway | 1 | 1312076.76 | 824657.48 | 487419.28 | 824657.48 | 3rd Tranche | 454004.76 | 1278662.24 | 824657.48 | 454004.76 | 100% | 100% | 93.14% | 97.45% | 100% | 2005-08-30 | 2005-11-07 | 2006-01-20 | 2006-03-28 | 2006-04-18 | 67 | 60 | completed & inaugurated | 1
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Patidon | 103518020 | Road Improvement | 1 | 1384000 | 964769.8 | 419230.2 | 964769.8 |  | 233012.85 | 1197782.65 | 964769.8 | 233012.85 | 100% | 100% | 55.58% | 86.54% | 100% | n/a | n/a | 2009-01-26 | 2009-05-30 | 2009-06-22 | 124 | 210 |  | 1
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Pawak | 103518021 | Road Concreting | 1 | 739671 | 503769.7 | 235901.3 | 503769.7 | 3rd Tranche | 194971.78 | 698741.48 | 503769.7 | 194971.78 | 100% | 100% | 82.65% | 94.47% | 100% | 2004-03-03 | 2004-06-17 | 2004-12-19 | 2005-03-26 | 2005-04-28 | 97 | 144 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Poblacion | 103518022 | Drainage System | 1 | 1609921.6 | 1123423.21 | 486498.39 | 1123423.21 | 3rd Tranche | 468621.23 | 1592044.44 | 1123423.21 | 468621.23 | 100% | 100% | 96.33% | 98.89% | 100% | 2005-08-30 | 2005-11-07 | 2005-11-24 | 2006-03-28 | 2006-04-18 | 124 | 810 | completed & inaugurated | 1
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Poblacion | 103518022 | Water System Level I | 1 | 296056.86 | 232798 | 63258.86 | 232798 |  | 59658.86 | 292456.86 | 232798 | 59658.86 | 100% | 100% | 94.31% | 98.78% | 100% | n/a | n/a | 2009-01-28 | 2009-04-30 | 2009-06-22 | 92 | 910 |  | 1
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Saumay | 103518023 | Solar Drier with warehouse | 1 | 577500 | 404180 | 173320 | 404180 |  | 98464.32 | 502644.32 | 404180 | 98464.32 | 100% | 100% | 56.81% | 87.04% | 100% | n/a | n/a | 2009-01-23 | 2009-03-30 | 2009-06-22 | 66 | 119 |  | 1
X | 10 | Lanao Del Norte | 1035 | Salvador | 103518 | Sudlon | 103518024 | Road | 1 | 978332.65 | 685482.26 | 292850.39 | 685482.26 | 1st Tranche | 342027.96 | 1027510.22 | 685482.26 | 342027.96 | 100% | 100% | 116.8% | 105% | 100% | 2006-08-11 | 2006-10-06 | 2006-10-20 | 2007-04-30 | no data | 192 | 127 | completed | 1
X | 10 | Lanao del Norte | 1035 | Salvador | 103518 | Sudlon | 103518024 | Road Improvement | 1 | 853429.56 | 681925 | 171504.56 | 681925 |  | 172504.56 | 854429.56 | 681925 | 172504.56 | 100% | 100% | 100.6% | 100.1% | 100% | n/a | n/a | 2009-01-21 | 2009-04-30 | 2009-06-22 | 99 | 155 |  | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Baning | 103519001 | Water System L2 | 1 | 2001374.18 | 1379609.75 | 621764.43 | 1293305.71 |  | 374715.02 | 1668020.73 | 1293305.71 | 374715.02 | 100% | 100% | 60.27% | 83.34% | 100% | 2006-06-15 | 2006-08-24 | 2007-01-11 | 2007-09-30 | no data | 262 | 206 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Dansalan | 103519004 | Road Improvement | 1 | 5862833.24 | 3048000 | 2814833.24 | 3048000 | 3rd Tranche | 1298891.79 | 4346891.79 | 3048000 | 1298891.79 | 100% | 100% | 46.14% | 74.14% | 100% | 2004-03-27 | 2004-06-30 | 2004-09-14 | 2005-03-02 | 2005-04-28 | 169 | 204 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Dansalan | 103519004 | Water System Level II | 1 | 2121432.75 | 1485002.5 | 636430.25 | 1485002.5 | 3rd Tranche | 465514.81 | 1950517.31 | 1485002.5 | 465514.81 | 100% | 100% | 73.14% | 91.94% | 100% | 2005-09-13 | 2005-10-11 | 2005-11-21 | 2006-04-14 | 2006-04-18 | 144 | 204 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Dansalan | 103519004 | Solar System w/ Warehouse | 1 | 931427 | 654038.16 | 277388.84 | 654038.16 | 1st Tranche | 276860.94 | 930899.1 | 654038.16 | 276860.94 | 100% | 100% | 99.81% | 99.94% | 100% | 2006-06-15 | 2006-06-15 | 2006-11-15 | 2007-03-30 | no data | 135 | 204 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mabugnao | 103519010 | Hanging Bridge | 1 | 993279.39 | 594618.14 | 398661.25 | 594618.14 | 3rd Tranche | 148577.18 | 743195.32 | 594618.14 | 148577.18 | 100% | 100% | 37.27% | 74.82% | 100% | 2004-03-27 | 2004-06-30 | 2004-09-10 | 2005-03-20 | 2005-04-28 | 191 | 46 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mabugnao | 103519010 | Road Rehabilitation | 1 | 1744659.96 | 1294286.62 | 450373.34 | 1224203 | 1st Tranche | 462313.6 | 1686516.6 | 1224203 | 462313.6 | 100% | 100% | 102.7% | 96.67% | 100% | 2006-06-15 | 2006-06-15 | 2007-01-11 | 2007-03-30 | no data | 78 | 47 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mama-anon | 103519013 | Barangay Health Station | 1 | 388283.97 | 203112 | 185171.97 | 203112 | 3rd Tranche | 128397.41 | 331509.41 | 203112 | 128397.41 | 100% | 100% | 69.34% | 85.38% | 100% | 2004-03-27 | 2004-06-30 | 2004-09-13 | 2005-04-13 | 2005-04-28 | 212 | 47 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mapurog | 103519014 | Road Opening FMR 2 kms | 1 | 3429883.08 | 1403838.32 | 2026044.76 | 1403838.32 | 3rd Tranche | 1050904.45 | 2454742.77 | 1403838.32 | 1050904.45 | 100% | 100% | 51.87% | 71.57% | 100% | 2005-09-13 | 2005-10-11 | 2005-11-23 | 2006-04-01 | 2006-04-18 | 129 | 112 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Mapurog | 103519014 | School Building | 1 | 865727.64 | 588040.87 | 277686.77 | 588040.87 | 1st Tranche | 141000 | 729040.87 | 588040.87 | 141000 | 100% | 100% | 50.78% | 84.21% | 100% | 2006-06-15 | 2006-06-15 | 2006-11-15 | 2007-03-30 | 2007-06-27 | 135 | 112 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Pancilan | 103519016 | Road Rehab. FMR 1.5 Kms | 1 | 2088069.89 | 1320865.96 | 767203.93 | 1320865.96 | 3rd Tranche | 893941.3 | 2214807.26 | 1320865.96 | 893941.3 | 100% | 100% | 116.5% | 106.1% | 100% | 2005-09-13 | 2005-10-11 | 2005-11-21 | 2006-04-14 | 2006-04-18 | 144 | 169 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Panoloon | 103519017 | 250m Road Concreting | 1 | 1057969.08 | 579000 | 478969.08 | 579000 | 3rd Tranche | 439848.86 | 1018848.86 | 579000 | 439848.86 | 100% | 100% | 91.83% | 96.3% | 100% | 2004-03-27 | 2004-06-30 | 2004-11-05 | 2005-04-02 | 2005-04-28 | 148 | 363 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Panoloon | 103519017 | Concreting 500 Ln.m of FMR | 1 | 1269290.8 | 887803 | 381487.8 | 887803 | 3rd Tranche | 273955.34 | 1161758.34 | 887803 | 273955.34 | 100% | 100% | 71.81% | 91.53% | 100% | 2005-09-13 | 2005-10-11 | 2006-01-23 | 2006-04-01 | 2006-04-18 | 68 | 363 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Panoloon | 103519017 | Road Rehabilitation | 1 | 1686524.76 | 1184024.6 | 502500.16 | 1184024.6 | 1st Tranche | 489400 | 1673424.6 | 1184024.6 | 489400 | 100% | 100% | 97.39% | 99.22% | 100% | 2006-06-15 | 2006-06-15 | 2006-11-15 | 2007-02-28 | 2007-06-26 | 105 | 363 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Pili | 103519018 | Solar Drier with Warehouse | 1 | 1049849.81 | 514953.86 | 534895.95 | 514953.86 | 3rd Tranche | 330627.18 | 845581.04 | 514953.86 | 330627.18 | 100% | 100% | 61.81% | 80.54% | 100% | 2004-03-27 | 2004-06-30 | 2004-09-08 | 2005-04-22 | 2005-04-28 | 226 | 166 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sapad | 103519 | Buriasan (Pob.) | 103519001 | Day Care Center | 1 | 330871.52 | 160316 | 170555.52 | 160316 | 3rd Tranche | 170333 | 330649 | 160316 | 170333 | 100% | 100% | 99.87% | 99.93% | 100% | 2004-03-27 | 2004-06-30 | 2004-09-18 | 2005-03-20 | 2005-04-28 | 183 | 713 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Bangaan | 103506001 | Water system level - II | 1 | 1376060.54 | 958617.4 | 417443.14 | 958617.4 | 3rd Tranche | 457594.2 | 1416211.6 | 958617.4 | 457594.2 | 100% | 100% | 109.6% | 102.9% | 100% | 2004-02-25 | 2004-07-27 | 2004-11-09 | 2005-04-08 | 2005-04-28 | 150 | 252 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Bangco | 103506002 | Road improvement | 1 | 1665701.4 | 768148.02 | 897553.38 | 768148.02 | 3rd Tranche | 486895 | 1255043.02 | 768148.02 | 486895 | 100% | 100% | 54.25% | 75.35% | 100% | 2004-02-25 | 2004-07-27 | 2005-01-26 | 2005-04-26 | 2005-04-28 | 90 | 68 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Bansarvil II | 103506003 | Barangay Health Station | 1 | 527764.92 | 189492 | 338272.92 | 189492 | 3rd Tranche | 376518.25 | 566010.25 | 189492 | 376518.25 | 100% | 100% | 111.3% | 107.2% | 100% | 2004-02-25 | 2004-06-25 | 2004-08-18 | 2005-03-28 | 2005-04-28 | 222 | 309 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Bansarvil II | 103506003 | Day Care Center | 1 | 581947.66 | 407363.36 | 174584.3 | 407363.36 | 1st Tranche | 215214.76 | 622578.12 | 407363.36 | 215214.76 | 100% | 100% | 123.3% | 107% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-12 | 2007-02-01 | 2007-05-15 | 81 | 310 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Bauyan | 103506004 | Water System Level 2 | 1 | 4083875.43 | 2853814.08 | 1230061.35 | 2853814.08 |  | 776657.05 | 3630471.13 | 2853814.08 | 776657.05 | 100% | 100% | 63.14% | 88.9% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-14 | 2007-06-01 | no data | 199 | 412 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Cabongbongan | 103506005 | Water system level - I | 1 | 386279.65 | 111099 | 275180.65 | 111099 | 3rd Tranche | 130631.5 | 241730.5 | 111099 | 130631.5 | 100% | 100% | 47.47% | 62.58% | 100% | 2004-02-25 | 2004-06-25 | 2004-09-28 | 2005-02-04 | 2005-04-28 | 129 | 72 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Cabongbongan | 103506005 | Road Rehabilitation/ Improvement | 1 | 1197080.94 | 797099.11 | 399981.83 | 797099.11 | 3rd Tranche | 571595.83 | 1368694.94 | 797099.11 | 571595.83 | 100% | 100% | 142.9% | 114.3% | 100% | 2005-09-12 | 2005-10-27 | 2006-01-28 | 2006-03-17 | 2006-04-18 | 48 | 68 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Cabongbongan | 103506005 | Road Improvement | 1 | 2225000 | 1557500 | 667500 | 1487480 |  | 322562 | 1810042 | 1487480 | 322562 | 100% | 100% | 48.32% | 81.35% | 100% | 2006-07-26 | 2006-09-08 | 2007-01-15 | 2007-11-01 | no data | 290 | 57 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Calibao | 103506006 | Construction of Drinking Water Supply System L2 | 1 | 1254171.45 | 872819.24 | 381352.21 | 872819.24 | 3rd Tranche | 347370.09 | 1220189.33 | 872819.24 | 347370.09 | 100% | 100% | 91.09% | 97.29% | 100% | 2005-09-12 | 2005-10-27 | 2005-11-21 | 2006-04-10 | 2006-04-18 | 140 | 203 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Calipapa | 103506007 | Farm to Market Road re-gravelling | 1 | 702297 | 472500 | 229797 | 472500 | 3rd Tranche | 368508 | 841008 | 472500 | 368508 | 100% | 100% | 160.4% | 119.8% | 100% | 2004-02-25 | 2004-06-25 | 2004-01-03 | 2005-04-25 | 2005-04-28 | 478 | 64 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Calube | 103506008 | Water system level - II | 1 | 1817087.48 | 651415.32 | 1165672.16 | 651415.32 | 3rd Tranche | 514367.14 | 1165782.46 | 651415.32 | 514367.14 | 100% | 100% | 44.13% | 64.16% | 100% | 2004-02-25 | 2004-06-25 | 2004-12-16 | 2006-04-08 | 2006-04-18 | 478 | 104 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Capocao | 103506010 | Road Improvement | 1 | 872861 | 630000 | 242861 | 630000 | 3rd Tranche | 318567 | 948567 | 630000 | 318567 | 100% | 100% | 131.2% | 108.7% | 100% | 2004-02-25 | 2004-06-25 | 2004-02-12 | 2005-04-15 | 2005-04-28 | 428 | 56 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Capucao | 103506010 | Solar Dryer with Warehouse | 1 | 546560.79 | 382592.55 | 163968.24 | 382592.55 | 1st Tranche | 33520 | 416112.55 | 382592.55 | 33520 | 100% | 100% | 20.44% | 76.13% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-14 | 2007-04-30 | no data | 167 | 59 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Dabliston | 103506011 | Construction of Day Care Center | 1 | 581947.66 | 407363.36 | 174584.3 | 407363.36 | 1st Tranche | 34450 | 441813.36 | 407363.36 | 34450 | 100% | 100% | 19.73% | 75.92% | 100% | 2006-07-26 | 2006-09-08 | 2006-10-25 | 2007-07-01 | no data | 249 | 314 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Dalama | 103506036 | Water system level - II | 1 | 1122440.534 | 784459.984 | 337980.55 | 784459.984 | 3rd Tranche | 304836 | 1089295.984 | 784459.984 | 304836 | 100% | 100% | 90.19% | 97.05% | 100% | 2004-02-25 | 2004-07-27 | 2004-11-22 | 2005-04-08 | 2005-04-28 | 137 | 42 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Ditago | 103506013 | Construction of 1 Classroom School Bldg | 1 | 754809.42 | 515370.8 | 239438.62 | 515370.8 | 1st Tranche | 24000 | 539370.8 | 515370.8 | 24000 | 100% | 100% | 10.02% | 71.46% | 100% | 2006-07-26 | 2006-09-08 | 2006-10-16 | 2007-09-30 | no data | 349 | 48 | completed | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Ilian | 103506014 | Farm to Market Road improvement | 1 | 1768718.7 | 1197200 | 571518.7 | 1197200 | 3rd Tranche | 727162.78 | 1924362.78 | 1197200 | 727162.78 | 100% | 100% | 127.2% | 108.8% | 100% | 2004-02-25 | 2004-07-27 | 2004-10-07 | 2005-04-18 | 2005-04-28 | 193 | 433 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Kauswagan | 103506015 | Water system level - II | 1 | 1357430.84 | 732142.76 | 625288.08 | 732142.76 | 3rd Tranche | 268593 | 1000735.76 | 732142.76 | 268593 | 100% | 100% | 42.96% | 73.72% | 100% | 2004-02-25 | 2004-06-25 | 2004-12-14 | 2005-07-22 | 2005-04-28 | 220 | 115 | completed & inaugurated | 1
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Kirapan | 103506016 | Water system level - II | 1 | 1095689.46 | 447236.83 | 648452.63 | 447236.83 | 3rd Tranche | 825372.86 | 1272609.69 | 447236.83 | 825372.86 | 100% | 100% | 127.3% | 116.1% | 100% | 2004-02-25 | 2004-06-25 | 2004-11-13 | 2006-04-10 | 2006-04-18 | 513 | 117 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Koreo | 103506017 | Construction of Water System Level 2 | 1 | 1464735.27 | 1020514.1 | 444221.17 | 982170.57 | 1st Tranche | 420405.18 | 1402575.75 | 982170.57 | 420405.18 | 100% | 100% | 94.64% | 95.76% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-08 | 2007-09-30 | no data | 326 | 130 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Lantawan | 103506019 | Road Rehabilitation/ Improvement | 1 | 3927862.66 | 2749503.55 | 1178359.11 | 2749503.55 | 3rd Tranche | 407546.92 | 3157050.47 | 2749503.55 | 407546.92 | 100% | 100% | 34.59% | 80.38% | 100% | 2005-09-12 | 2005-10-27 | 2005-11-23 | 2006-03-15 | 2006-04-18 | 112 | 64 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Mabuhay | 103506019 | Farm to Market Road re-gravelling | 1 | 1190097.4 | 786000 | 404097.4 | 786000 | 3rd Tranche | 505020.45 | 1291020.45 | 786000 | 505020.45 | 100% | 100% | 125% | 108.5% | 100% | 2004-02-25 | 2004-06-25 | 2004-02-09 | 2005-04-15 | 2005-04-28 | 431 | 71 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Mabuhay | 103506019 | Day Care Center | 1 | 581947.66 | 407363.36 | 174584.3 | 407363.36 | 1st Tranche | 86572.76 | 493936.12 | 407363.36 | 86572.76 | 100% | 100% | 49.59% | 84.88% | 100% | 2006-07-26 | 2006-09-08 | 2007-01-02 | 2007-06-01 | no data | 150 | 67 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Mahayahay | 103506021 | Water system level - II | 1 | 878507.19 | 424364.16 | 454143.03 | 424364.16 | 3rd Tranche | 495612 | 919976.16 | 424364.16 | 495612 | 100% | 100% | 109.1% | 104.7% | 100% | 2004-02-25 | 2004-06-25 | 2004-11-25 | 2006-04-10 | 2006-04-18 | 501 | 63 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Mamagum | 103506022 | Health Station | 1 | 634272.26 | 443990.58 | 190281.68 | 443990.58 | 1st Tranche | 161715 | 605705.58 | 443990.58 | 161715 | 100% | 100% | 84.99% | 95.5% | 100% | 2006-07-26 | 2006-09-08 | 2006-10-12 | 2007-01-31 | 2007-05-15 | 111 | 185 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Mamagum - C2 | 103506022 | Water system level - II | 2 | 1820267 | 1468647 | 351620 | 1468647 | 3rd Tranche | 375984 | 1844631 | 1468647 | 375984 | 100% | 100% | 106.9% | 101.3% | 100% | 2004-02-25 | 2004-06-25 | 2004-08-16 | 2005-04-25 | 2005-04-28 | 252 | 194 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Campo- Islam | 103506009 | Water system level - II | 2 | 1820267 | 1468647 | 351620 | 1468647 | 3rd Tranche | 375984 | 1844631 | 1468647 | 375984 | 100% | 100% | 106.9% | 101.3% | 100% | 2004-02-25 | 2004-06-25 | 2004-08-16 | 2005-04-25 | 2005-04-28 | 252 | 194 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Mina | 103506037 | Construction of Drinking Water Supply System L2 | 1 | 973186.47 | 683852.31 | 289334.16 | 683852.31 | 3rd Tranche | 269095.12 | 952947.43 | 683852.31 | 269095.12 | 100% | 100% | 93% | 97.92% | 100% | 2005-09-12 | 2005-10-27 | 2005-12-09 | 2006-04-10 | 2006-04-18 | 122 | 109 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Pandanan | 103506023 | Construction of Drinking Water Supply System L2 | 1 | 2235454.77 | 1564818.34 | 670636.43 | 1564818.34 | 3rd Tranche | 639594.82 | 2204413.16 | 1564818.34 | 639594.82 | 100% | 100% | 95.37% | 98.61% | 100% | 2005-09-12 | 2005-10-27 | 2005-12-10 | 2006-04-14 | 2006-04-18 | 125 | 363 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Pandanan | 103506023 | Upgrading/Gravelling of Brgy Road | 1 | 1794560 | 1256192 | 538368 | 1236432.8 |  | 551468 | 1787900.8 | 1236432.8 | 551468 | 100% | 100% | 102.4% | 99.63% | 100% | 2006-07-26 | 2006-09-08 | 2007-01-08 | 2007-04-30 | 2007-05-15 | 112 | 360 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Payong | 103506024 | Construction of Drinking Water Supply System L2 | 1 | 991525.2 | 692202.44 | 299322.76 | 692202.44 | 3rd Tranche | 328153.88 | 1020356.32 | 692202.44 | 328153.88 | 100% | 100% | 109.6% | 102.9% | 100% | 2005-09-12 | 2005-10-27 | 2005-11-21 | 2006-04-10 | 2006-04-18 | 140 | 205 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Pikalawag | 103506026 | Water system level - II | 1 | 1354635.65 | 431250 | 923385.65 | 431250 | 3rd Tranche | 273297.85 | 704547.85 | 431250 | 273297.85 | 100% | 100% | 29.6% | 52.01% | 100% | 2004-02-25 | 2004-07-27 | 2004-10-18 | 2005-04-26 | 2005-04-28 | 190 | 485 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Pikalawag | 103506026 | Brgy Public Market | 1 | 785410.24 | 530002.24 | 255408 | 530002.24 | 1st Tranche | 278648 | 808650.24 | 530002.24 | 278648 | 100% | 100% | 109.1% | 103% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-06 | 2006-12-26 | 2007-05-14 | 50 | 402 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Pikinit | 103506027 | Brgy Public Market | 1 | 511816.78 | 342917.24 | 168899.54 | 342917.24 | 3rd Tranche | 233693 | 576610.24 | 342917.24 | 233693 | 100% | 100% | 138.4% | 112.7% | 100% | 2004-02-25 | 2004-06-25 | 2004-08-18 | 2005-04-25 | 2005-04-28 | 250 | 245 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Piraka | 103506025 | Construction of Drinking Water Supply System L2 | 1 | 806681.53 | 558402.89 | 248278.64 | 558402.89 | 3rd Tranche | 246227.44 | 804630.33 | 558402.89 | 246227.44 | 100% | 100% | 99.17% | 99.75% | 100% | 2005-09-12 | 2005-10-27 | 2005-12-01 | 2006-03-28 | 2006-04-18 | 117 | 192 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Piraka | 103506025 | Day Care Center | 1 | 595101.97 | 411912.97 | 183189 | 411912.97 | 1st Tranche | 67577 | 479489.97 | 411912.97 | 67577 | 100% | 100% | 36.89% | 80.57% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-08 | 2007-10-20 | no data | 346 | 192 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Ramain | 103506029 | Water System | 1 | 956130.8 | 669291.56 | 286839.24 | 669291.56 | 3rd Tranche | 172943.74 | 842235.3 | 669291.56 | 172943.74 | 100% | 100% | 60.29% | 88.09% | 100% | 2005-09-12 | 2005-10-27 | 2005-12-02 | 2006-04-10 | 2006-04-18 | 129 | 225 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Rebucon | 103506030 | Construction of Drinking Water Supply System L2 | 1 | 1085594.96 | 763746 | 321848.96 | 763746 | 3rd Tranche | 397057.96 | 1160803.96 | 763746 | 397057.96 | 100% | 100% | 123.4% | 106.9% | 100% | 2005-09-12 | 2005-10-27 | 2005-11-25 | 2006-04-10 | 2006-04-18 | 136 | 158 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Sigayan | 103506031 | Construction of Drinking Water Supply System L2 | 1 | 673280.85 | 471296 | 201984.85 | 471296 | 3rd Tranche | 160727.29 | 632023.29 | 471296 | 160727.29 | 100% | 100% | 79.57% | 93.87% | 100% | 2005-09-12 | 2005-10-27 | 2005-11-22 | 2006-03-25 | 2006-04-18 | 123 | 170 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Sigayan | 103506031 | Construction of Day Care Center | 1 | 623724.53 | 436607.17 | 187117.36 | 436607.17 | 1st Tranche | 119581.24 | 556188.41 | 436607.17 | 119581.24 | 100% | 100% | 63.91% | 89.17% | 100% | 2006-07-26 | 2006-09-08 | 2006-10-18 | 2007-06-01 | 2007-05-15 | 226 | 170 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Sugod | 103506032 | Water system level - II | 1 | 1183835 | 791294.6 | 392540.4 | 791294.6 | 3rd Tranche | 449596.2 | 1240890.8 | 791294.6 | 449596.2 | 100% | 100% | 114.5% | 104.8% | 100% | 2004-02-25 | 2004-07-27 | 2004-10-28 | 2005-04-11 | 2005-04-28 | 165 | 120 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Sugod | 103506032 | Construction of Health Station | 1 | 678860.83 | 469413.43 | 209447.4 | 469413.43 | 1st Tranche | 174378.85 | 643792.28 | 469413.43 | 174378.85 | 100% | 100% | 83.26% | 94.83% | 100% | 2006-07-26 | 2006-09-08 | 2006-11-17 | 2007-02-15 | no data | 90 | 127 | completed | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Tagulo | 103506033 | Construction of Day Care Center | 1 | 840827.96 | 588579.46 | 252248.5 | 588579.46 | 3rd Tranche | 249573.5 | 838152.96 | 588579.46 | 249573.5 | 100% | 100% | 98.94% | 99.68% | 100% | 2005-09-12 | 2005-10-27 | 2005-12-01 | 2006-03-29 | 2006-04-18 | 118 | 165 | completed & inaugurated | 1 | MINDANAO
X | 10 | Lanao Del Norte | 1035 | Sultan Naga Dimaporo | 103506 | Tantaon | 103506034 | Construction of Drinking Water Supply System L2 | 1 | 983412.55 | 688389.1 | 295023.45 | 688389.1 | 3rd Tranche | 300840.96 | 989230.06 | 688389.1 | 300840.96 | 100% | 100% | 102% | 100.6% | 100% | 2005-09-12 | 2005-10-27 | 2005-11-26 | 2006-03-31 | 2006-04-18 | 125 | 216 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Bagong Nayon | 104206001 | Health Station | 1 | 933269.52 | 643130.16 | 290139.36 | 514504.13 |  | 70529.27 | 585033.4 | 514504.13 | 70529.27 | 100% | 100% | 24.31% | 62.69% | 100% | 2007-06-13 | n/a | 2007-10-10 | 2008-04-01 | 2008-07-30 | 174 | 87 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Capule | 104206002 | Construction of Solar Dryer | 1 | 253925.66 | 163288.76 | 90636.9 | 163288.76 |  | 93463.6 | 256752.36 | 163288.76 | 93463.6 | 100% | 100% | 103.1% | 101.1% | 100% | 2006-06-15 | 2006-07-13 | 2006-08-03 | 2007-03-31 | 2007-06-06 | 240 | 27 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Capule | 104206002 | Day Care Center | 1 | 629066.6 | 440104.48 | 188962.12 | 440104.48 |  | 186620 | 626724.48 | 440104.48 | 186620 | 100% | 100% | 98.76% | 99.63% | 100% | 2008-06-06 | no data | 2008-09-16 | 2009-05-30 | 2009-06-02 | 256 | 27 | double handling of materials had caused the delay | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Guiban | 104206004 | Day Care Center | 1 | 624490.6 | 436118.08 | 188372.52 | 436118.08 |  | 803185.1 | 1239303.18 | 436118.08 | 803185.1 | 100% | 100% | 426.4% | 198.5% | 100% | 2008-06-06 | no data | 2008-09-16 | 2009-05-30 | 2009-06-02 | 256 | 45 | double handling of materials and frequent occurrence of unfavorable weather condition had caused the delay | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Laya-an | 104206005 | Water System Level II | 1 | 914164.24 | 630086.52 | 284077.72 | 630086.52 |  | 282906 | 912992.52 | 630086.52 | 282906 | 100% | 100% | 99.59% | 99.87% | 100% | 2008-06-06 | no data | 2008-11-24 | 2009-05-30 | 2009-06-01 | 187 | 30 | no download of 1st tranche grant /procurment activities are still on-going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Maligubaan | 104206007 | Water System Level II | 1 | 1517205.15 | 1065212.67 | 451992.48 | 1065212.67 |  | 485582.09 | 1550794.76 | 1065212.67 | 485582.09 | 100% | 100% | 107.4% | 102.2% | 100% | 2008-06-06 | no data | 2008-10-16 | 2009-05-30 | 2009-06-02 | 226 | 111 | Late conduct of community procurement caused delay of deliveries of supplies and construction materials to the project site. | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Mantukoy | 104206008 | Rehabilitation of Mantukoy Brgy. Road | 1 | 5338290.59 | 3736252.74 | 1602037.85 | 3736252.74 |  | 1073418.06 | 4809670.8 | 3736252.74 | 1073418.06 | 100% | 100% | 67% | 90.1% | 100% | 2006-06-15 | 2006-07-13 | 2006-08-05 | 2009-05-30 | 2009-06-02 | 1029 | 47 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Marugang | 104206009 | Construction of Solar Dryer | 1 | 281349.67 | 172085.17 | 109264.5 | 172085.17 |  | 110264.5 | 282349.67 | 172085.17 | 110264.5 | 100% | 100% | 100.9% | 100.4% | 100% | 2006-06-15 | 2006-07-13 | 2006-08-05 | 2007-03-31 | 2007-06-14 | 238 | 38 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Marugang | 104206009 | Sustainable Agriculture Training | 1 | 179116.4 | 85356.4 | 93760 | 83715.1 |  | 159220 | 242935.1 | 83715.1 | 159220 | 100% | 100% | 169.8% | 135.6% | 100% | 2007-06-13 | n/a | 2007-11-01 | 2008-04-01 | 2008-07-27 | 152 | 38 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Marugang | 104206009 | Water System Level II | 1 | 521582.2 | 258312.32 | 263269.88 | 206649.86 |  | 236696.63 | 443346.49 | 206649.86 | 236696.63 | 100% | 100% | 89.91% | 85% | 100% | 2008-06-06 | no data | 2008-10-15 | 2009-05-30 | 2009-06-02 | 227 | 40 | Late conduct of community procurement caused delay of deliveries of supplies and construction materials to the project site. | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | New Casul | 104206003 | Solar Drier | 1 | 471679.94 | 249991.5 | 221688.44 | 234328.55 |  | 162979.41 | 397307.96 | 234328.55 | 162979.41 | 100% | 100% | 73.52% | 84.23% | 100% | 2007-06-13 | n/a | 2007-11-01 | 2008-04-30 | 2008-07-26 | 181 | 31 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Poblacion | 104206011 | Construction of Water system L2 | 1 | 1900054.9 | 1328219.61 | 571835.29 | 1328219.61 |  | 572835.29 | 1901054.9 | 1328219.61 | 572835.29 | 100% | 100% | 100.2% | 100.1% | 100% | 2006-06-15 | 2006-07-13 | 2006-08-03 | 2007-04-30 | 2007-06-23 | 270 | 66 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Poblacion | 104206011 | Solar Drier | 1 | 297083.08 | 207798.52 | 89284.56 | 207798.52 |  | 85690 | 293488.52 | 207798.52 | 85690 | 100% | 100% | 95.97% | 98.79% | 100% | 2008-06-06 | no data | 2008-10-15 | 2009-05-30 | 2009-06-02 | 227 | 66 | Late conduct of community procurement caused delay of deliveries of materials to the project site. | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Pogan | 104206012 | Health Station | 1 | 899394.78 | 634206.08 | 265188.7 | 507364.86 |  | 166391.37 | 673756.23 | 507364.86 | 166391.37 | 100% | 100% | 62.74% | 74.91% | 100% | 2007-06-13 | n/a | 2007-11-01 | 2008-04-01 | 2008-07-25 | 152 | 35 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Pogan | 104206012 | Day Care Center | 1 | 653689 | 457472.2 | 196216.8 | 440977.76 |  | 191783.58 | 632761.34 | 440977.76 | 191783.58 | 100% | 100% | 97.74% | 96.8% | 100% | 2008-06-06 | no data | 2008-10-16 | 2009-05-30 | 2009-06-02 | 226 | 43 | double handling of materials and frequent occurrence of unfavorable weather condition had caused the delay | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Soso-on | 104206014 | Solar Drier | 1 | 369033.28 | 257482.32 | 111550.96 | 253985.86 |  | 123291 | 377276.86 | 253985.86 | 123291 | 100% | 100% | 110.5% | 102.2% | 100% | 2008-06-06 | no data | 2008-09-16 | 2009-05-30 | 2009-06-02 | 256 | 27 | double handling of materials and frequent occurrence of unfavorable weather condition had caused the delay | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Dapitan | 104206015 | Health Station | 1 | 930630.48 | 634006.08 | 296624.4 | 507204.86 |  | 150582.47 | 657787.33 | 507204.86 | 150582.47 | 100% | 100% | 50.77% | 70.68% | 100% | 2007-06-13 | n/a | 2007-10-23 | 2008-04-01 | 2008-07-31 | 161 | 35 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Dapitan | 104206015 | Solar Drier | 1 | 355015.42 | 234637.76 | 120377.66 | 234637.76 |  | 124930.68 | 359568.44 | 234637.76 | 124930.68 | 100% | 100% | 103.8% | 101.3% | 100% | 2008-06-06 | no data | 2008-09-16 | 2009-05-30 | 2009-06-02 | 256 | 35 | double handling of materials and frequent occurrence of unfavorable weather condition had caused the delay | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Dioyo | 104206016 | Day Care Center | 1 | 737637.65 | 392145.11 | 345492.54 | 392145.11 |  | 127457.92 | 519603.03 | 392145.11 | 127457.92 | 100% | 100% | 36.89% | 70.44% | 100% | 2007-06-13 | n/a | 2007-10-10 | 2008-03-01 | 2008-07-24 | 143 | 35 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Potongan | 104206017 | Day Care Center | 1 | 617397.8 | 431160.84 | 186236.96 | 402036.17 |  | 179514.5 | 581550.67 | 402036.17 | 179514.5 | 100% | 100% | 96.39% | 94.19% | 100% | 2008-06-06 | no data | 2008-09-16 | 2009-05-30 | 2009-06-02 | 256 | 24 | double handling of materials and frequent occurrence of unfavorable weather condition had caused the delay | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Upper Salimpono | 104206018 | Corn Mill | 1 | 1045052.89 | 725030.84 | 320022.05 | 725030.84 |  | 313512.5 | 1038543.34 | 725030.84 | 313512.5 | 100% | 100% | 97.97% | 99.38% | 100% | 2008-06-06 | no data | 2008-10-15 | 2009-05-30 | 2009-06-02 | 227 | 56 | Late conduct of community procurement caused delay of deliveries of supplies and construction materials to the project site. | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Concepcion | 104206 | Virayan | 104206019 | Solar Drier | 1 | 366591.28 | 256584.32 | 110006.96 | 256584.32 |  | 124719 | 381303.32 | 256584.32 | 124719 | 100% | 100% | 113.4% | 104% | 100% | 2008-06-06 | no data | 2008-09-16 | 2009-05-30 | 2009-06-02 | 256 | 19 | Late conduct of community procurement caused delay of deliveries of materials to the project site. | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Bagong Clarin | 104217001 | Barangay Health Station | 1 | 489137.1 | 306054 | 183083.1 | 306054 | 3rd Tranche | 204093.19 | 510147.19 | 306054 | 204093.19 | 100% | 100% | 111.5% | 104.3% | 100% | 2004-01-23 | 2006-06-14 | 2004-09-17 | 2005-04-01 | 2005-04-28 | 196 | 143 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Gandawan | 104217002 | Spillway Bridge | 1 | 525718 | 347000 | 178718 | 312300 | 2nd Tranche | 145159.71 | 457459.71 | 312300 | 145159.71 | 100% | 100% | 81.22% | 87.02% | 100% | 2004-01-23 | 2006-06-14 | 2005-02-01 | 2005-04-16 | 2005-04-28 | 74 | 71 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Lake Duminagat | 104217003 | Concrete Trail road | 1 | 1295342.15 | 757848 | 537494.15 | 757848 | 3rd Tranche | 304742.79 | 1062590.79 | 757848 | 304742.79 | 100% | 100% | 56.7% | 82.03% | 100% | 2004-01-23 | 2006-06-14 | 2004-09-30 | 2005-09-12 | no data | 347 | 52 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Lalud | 104217004 | Road Rehabilitation,FMR | 1 | 1164478.38 | 815134.87 | 349343.51 | 815134.87 | 3rd Tranche | 242380.41 | 1057515.28 | 815134.87 | 242380.41 | 100% | 100% | 69.38% | 90.81% | 100% | 2005-10-06 | 2005-12-06 | 2006-01-17 | 2006-04-17 | 2006-04-18 | 90 | 461 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Lampasan | 104217005 | 1 Classroom School Building | 1 | 1277852.07 | 894496.45 | 383355.62 | 894496.45 |  | 393855.62 | 1288352.07 | 894496.45 | 393855.62 | 100% | 100% | 102.7% | 100.8% | 100% | 2006-09-12 | 2006-09-12 | 2006-10-21 | 2008-08-30 | 2008-06-15 | 679 | 201 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Liboron | 104217006 | School Building | 1 | 493322.02 | 272048 | 221274.02 | 244843.2 | 2nd Tranche | 127973.14 | 372816.34 | 244843.2 | 127973.14 | 100% | 100% | 57.83% | 75.57% | 100% | 2004-01-23 | 2004-06-14 | 2004-11-18 | 2005-04-26 | 2005-04-28 | 159 | 28 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Liboron | 104217006 | 2 KM Farm to Market Road | 1 | 1532875.5 | 781706.2 | 751169.3 | 625364.96 |  | 584146.7 | 1209511.66 | 625364.96 | 584146.7 | 100% | 100% | 77.76% | 78.9% | 100% | 2006-08-18 | 2006-09-12 | 2006-11-05 | 2007-06-30 | no data | 237 | 28 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Maramara | 104217007 | School Building | 1 | 822241.51 | 544096 | 278145.51 | 489686.4 | 2nd Tranche | 178108.61 | 667795.01 | 489686.4 | 178108.61 | 100% | 100% | 64.03% | 81.22% | 100% | 2004-01-23 | 2006-06-14 | 2004-11-04 | 2005-04-05 | 2005-04-28 | 152 | 108 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Napangan | 104217007 | Road Rehabilitation | 1 | 1499999 | 1041000 | 458999 | 1041000 | 3rd Tranche | 392855.42 | 1433855.42 | 1041000 | 392855.42 | 100% | 100% | 85.59% | 95.59% | 100% | 2004-01-23 | 2006-06-14 | 2004-02-07 | 2005-04-01 | 2005-04-28 | 419 | 204 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Napangan | 104217008 | Road Rehabilitation, FMR | 1 | 2182342.4 | 1527639.68 | 654702.72 | 1069347.78 | 1st Tranche | 496200.98 | 1565548.76 | 1069347.78 | 496200.98 | 100% | 100% | 75.79% | 71.74% | 100% | 2005-10-06 | 2005-12-06 | 2006-03-20 | 2009-03-30 | no data | 1106 | 208 | completed as built | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Nueva Vista (Mansawan) | 104217009 | Road Rehabilitation, FMR | 1 | 1367296.16 | 957107.31 | 410188.85 | 957107.31 | 2nd Tranche | 287797.48 | 1244904.79 | 957107.31 | 287797.48 | 100% | 100% | 70.16% | 91.05% | 100% | 2005-10-06 | 2005-12-06 | 2006-01-17 | 2007-01-31 | no data | 379 | 231 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Don Victoriano | 104217 | Petianan | 104217010 | 2 Classroom School Building | 1 | 888078.34 | 621654.84 | 266423.5 | 621654.84 |  | 235553.5 | 857208.34 | 621654.84 | 235553.5 | 100% | 100% | 88.41% | 96.52% | 100% | 2006-09-12 | 2006-09-12 | 2006-10-26 | 2008-03-30 | 2009-04-29 | 521 | 142 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Bagong Silang | 104208002 | Road Improvement | 1 | 1036406 | 700000 | 336406 | 700000 |  | 312571.25 | 1012571.25 | 700000 | 312571.25 | 100% | 100% | 92.91% | 97.7% | 100% | 2007-06-14 | n/a | 2007-09-14 | 2008-03-05 | 2008-05-01 | 173 | 59 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Biasong | 104208003 | Road Improvement | 1 | 1018300 | 700000 | 318300 | 700000 |  | 284063.75 | 984063.75 | 700000 | 284063.75 | 100% | 100% | 89.24% | 96.64% | 100% | 2008-05-29 | no data | 2008-07-26 | 2008-12-10 | 2008-12-11 | 137 | 188 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Burgos | 104208005 | Road Improvement | 1 | 1502790.05 | 1051953 | 450837.05 | 1051953 |  | 344036.53 | 1395989.53 | 1051953 | 344036.53 | 100% | 100% | 76.31% | 92.89% | 100% | 2006-05-24 | 2006-06-09 | 2006-08-20 | 2006-12-18 | 2007-05-31 | 120 | 93 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Burgos | 104208005 | Road Improvement | 1 | 1002970 | 700000 | 302970 | 700000 |  | 313388.08 | 1013388.08 | 700000 | 313388.08 | 100% | 100% | 103.4% | 101% | 100% | 2008-05-29 | no data | 2008-07-22 | 2008-11-22 | 2008-12-08 | 123 | 92 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Dalacon | 104208006 | Road Improvement | 1 | 1830817.6 | 1255119 | 575698.6 | 1255119 |  | 611025.01 | 1866144.01 | 1255119 | 611025.01 | 100% | 100% | 106.1% | 101.9% | 100% | 2007-06-14 | n/a | 2007-09-07 | 2008-04-25 | 2008-05-01 | 231 | 58 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Dampalan | 104208007 | Health Station | 1 | 662807 | 463982 | 198825 | 463982 |  | 234790.5 | 698772.5 | 463982 | 234790.5 | 100% | 100% | 118.1% | 105.4% | 100% | 2006-05-24 | 2006-06-09 | 2006-08-16 | 2007-03-30 | 2007-03-29 | 226 | 131 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Dampalan | 104208007 | Water System Level II | 1 | 825100 | 553377.2 | 271722.8 | 553377.2 |  | 265835.3 | 819212.5 | 553377.2 | 265835.3 | 100% | 100% | 97.83% | 99.29% | 100% | 2008-05-29 | no data | 2008-07-21 | 2008-12-09 | 2008-12-10 | 141 | 137 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Don Andres Soriano | 104208027 | Health Station | 1 | 662830.75 | 463982 | 198848.75 | 463982 |  | 191763.79 | 655745.79 | 463982 | 191763.79 | 100% | 100% | 96.44% | 98.93% | 100% | 2006-05-24 | 2006-06-09 | 2006-09-04 | 2007-04-30 | 2007-05-31 | 238 | 62 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Estante | 104208008 | Day Care Center | 1 | 652735 | 456939.88 | 195795.12 | 456939.88 |  | 198530 | 655469.88 | 456939.88 | 198530 | 100% | 100% | 101.4% | 100.4% | 100% | 2008-05-29 | no data | 2008-07-22 | 2008-12-11 | 2008-12-12 | 142 | 65 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Jasa-an | 104208010 | Road Improvement | 1 | 992850 | 700000 | 292850 | 700000 |  | 283720 | 983720 | 700000 | 283720 | 100% | 100% | 96.88% | 99.08% | 100% | 2008-05-29 | no data | 2008-07-26 | 2008-11-19 | 2008-12-13 | 116 | 22 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Katipa | 104208011 | Road Improvement | 1 | 1019980 | 700000 | 319980 | 700000 |  | 271266.25 | 971266.25 | 700000 | 271266.25 | 100% | 100% | 84.78% | 95.22% | 100% | 2008-05-29 | no data | 2008-07-19 | 2008-12-11 | 2009-02-06 | 145 | 211 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Luzaran | 104208012 | Irrigation System | 1 | 2053183 | 1349612 | 703571 | 1349612 |  | 690186 | 2039798 | 1349612 | 690186 | 100% | 100% | 98.1% | 99.35% | 100% | 2007-06-14 | n/a | 2007-09-07 | 2008-04-30 | 2008-05-08 | 236 | 137 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Luzaran | 104208012 | Health Station | 1 | 681430 | 423411.59 | 258018.41 | 423411.59 |  | 225293.95 | 648705.54 | 423411.59 | 225293.95 | 100% | 100% | 87.32% | 95.2% | 100% | 2008-05-29 | no data | 2008-07-24 | 2008-12-08 | 2009-07-28 | 137 | 137 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mabas | 104208028 | Concrete Foot Trail | 1 | 622745.69 | 435922 | 186823.69 | 435922 |  | 199548.85 | 635470.85 | 435922 | 199548.85 | 100% | 100% | 106.8% | 102% | 100% | 2006-05-24 | 2006-06-09 | 2006-09-09 | 2006-12-03 | 2007-06-07 | 85 | 19 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mabas | 104208028 | Foot trail | 1 | 650000 | 455000 | 195000 | 455000 |  | 223717.58 | 678717.58 | 455000 | 223717.58 | 100% | 100% | 114.7% | 104.4% | 100% | 2008-05-29 | no data | 2008-07-23 | 2009-01-01 | 2009-04-28 | 162 | 19 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Macalibre Alto | 104208013 | Water System Level II | 1 | 983902.5 | 561949 | 421953.5 | 538438.1 |  | 537628.76 | 1076066.86 | 538438.1 | 537628.76 | 100% | 100% | 127.4% | 109.4% | 100% | 2007-06-14 | n/a | 2007-09-25 | 2008-04-30 | 2008-05-13 | 218 | 113 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Macalibre Alto | 104208013 | Public Market | 1 | 1068354.91 | 747866.91 | 320488 | 747866.91 |  | 315741.75 | 1063608.66 | 747866.91 | 315741.75 | 100% | 100% | 98.52% | 99.56% | 100% | 2008-05-29 | no data | 2008-07-14 | 2008-09-15 | 2008-12-15 | 63 | 113 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Macalibre Bajo | 104208014 | Water System Level II | 1 | 1497613 | 895540.28 | 602072.72 | 895540.28 |  | 629178.06 | 1524718.34 | 895540.28 | 629178.06 | 100% | 100% | 104.5% | 101.8% | 100% | 2007-06-14 | n/a | 2007-09-24 | 2008-04-30 | 2008-05-09 | 219 | 300 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mahayahay | 104208015 | Day Care Center | 1 | 655354 | 416173 | 239181 | 416173 |  | 237694 | 653867 | 416173 | 237694 | 100% | 100% | 99.38% | 99.77% | 100% | 2008-05-29 | no data | 2008-07-14 | 2008-09-29 | 2008-12-15 | 77 | 62 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Manguehan | 104208016 | Water System Level II | 1 | 1287919 | 583267.72 | 704651.28 | 579420 |  | 786133.47 | 1365553.47 | 579420 | 786133.47 | 100% | 100% | 111.6% | 106% | 100% | 2007-08-15 | n/a | 2007-10-02 | 2008-04-27 | 2008-05-13 | 208 | 113 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mansabay Alto | 104208029 | Water System Level II | 1 | 1953889 | 1358389 | 595500 | 1358389 |  | 652553.75 | 2010942.75 | 1358389 | 652553.75 | 100% | 100% | 109.6% | 102.9% | 100% | 2007-06-14 | n/a | 2007-09-19 | 2008-04-14 | 2008-04-22 | 208 | 149 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Mansabay Bajo | 104208017 | Day Care Center | 1 | 546304 | 382422 | 163882 | 382422 |  | 173987.25 | 556409.25 | 382422 | 173987.25 | 100% | 100% | 106.2% | 101.8% | 100% | 2006-05-24 | 2006-06-09 | 2006-08-18 | 2006-11-15 | 2007-05-30 | 89 | 371 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Molatuhan Alto | 104208018 | Water System Level 2 | 1 | 1123875.72 | 786713 | 337162.72 | 786713 |  | 381269.5 | 1167982.5 | 786713 | 381269.5 | 100% | 100% | 113.1% | 103.9% | 100% | 2006-05-24 | 2006-06-09 | 2006-08-22 | 2007-04-30 | 2007-06-07 | 251 | 138 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Molatuhan Alto | 104208018 | Health Station | 1 | 680000 | 468000 | 212000 | 468000 |  | 218197.4 | 686197.4 | 468000 | 218197.4 | 100% | 100% | 102.9% | 100.9% | 100% | 2008-05-29 | no data | 2008-07-08 | 2008-10-12 | 2008-12-15 | 96 | 153 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Molatuhan Bajo | 104208019 | Water System Level II | 1 | 1562859 | 980000 | 582859 | 980000 |  | 695589.91 | 1675589.91 | 980000 | 695589.91 | 100% | 100% | 119.3% | 107.2% | 100% | 2007-06-14 | n/a | 2007-09-11 | 2008-04-14 | 2008-05-09 | 216 | 171 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Peniel | 104208021 | Road Improvement | 1 | 1428571.42 | 1000000 | 428571.42 | 1000000 |  | 392785.22 | 1392785.22 | 1000000 | 392785.22 | 100% | 100% | 91.65% | 97.49% | 100% | 2006-05-24 | 2006-06-09 | 2006-08-28 | 2006-12-18 | 2007-10-02 | 112 | 32 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Peniel | 104208021 | Road Improvement | 1 | 1053930 | 700000 | 353930 | 700000 |  | 355239.97 | 1055239.97 | 700000 | 355239.97 | 100% | 100% | 100.4% | 100.1% | 100% | 2008-05-29 | no data | 2008-07-14 | 2008-11-14 | 2008-12-10 | 123 | 32 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Puntod | 104208023 | Road Improvement | 1 | 1033750 | 716123 | 317627 | 692656.4 |  | 300028 | 992684.4 | 692656.4 | 300028 | 100% | 100% | 94.46% | 96.03% | 100% | 2007-06-14 | n/a | 2007-09-14 | 2008-04-10 | 2008-04-22 | 209 | 398 | completed | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Puntod | 104208023 | Road Improvement | 1 | 970364.21 | 679231.42 | 291132.79 | 679231.42 |  | 259003.38 | 938234.8 | 679231.42 | 259003.38 | 100% | 100% | 88.96% | 96.69% | 100% | 2008-05-29 | no data | 2008-07-09 | 2009-03-30 | 2009-04-28 | 264 | 398 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Rizal | 104208024 | Water System Level 2 | 1 | 1570781 | 1099624 | 471157 | 1099624 |  | 435230.25 | 1534854.25 | 1099624 | 435230.25 | 100% | 100% | 92.37% | 97.71% | 100% | 2006-05-24 | 2006-06-09 | 2006-07-24 | 2007-02-28 | 2007-05-31 | 219 | 190 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Sibugon | 104208025 | Water System Level 2 | 1 | 3338805 | 2337181 | 1001624 | 2337181 |  | 1006335.89 | 3343516.89 | 2337181 | 1006335.89 | 100% | 100% | 100.5% | 100.1% | 100% | 2006-05-24 | 2006-06-09 | 2006-07-29 | 2007-02-28 | 2007-06-07 | 214 | 298 | completed & inaugurated | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Sibula | 104208026 | Road Improvement | 1 | 1064300 | 700000 | 364300 | 700000 |  | 327485 | 1027485 | 700000 | 327485 | 100% | 100% | 89.89% | 96.54% | 100% | 2008-05-29 | no data | 2008-07-22 | 2009-04-30 | 2009-07-28 | 282 | 254 | on going | 1 | MINDANAO
X | 10 | Misamis Occidental | 1042 | Lopez Jaena | 104208 | Western Poblacion | 104208030 | Day Care Center | 1 | 497366 | 378221 | 119145 | 378221 |  | 136125.5 | 514346.5 | 378221 | 136125.5 | 100% | 100% | 114.3% | 103.4% | 100% | 2006-05-24 | 2006-06-09 | 2006-08-22 | 2006-11-28 | 2007-05-30 | 98 | 329 | completed & inaugurated | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Aguinaldo | 118202001 | Health Station | 1 | 697077 | 464598 | 232479 | 464598 |  | 249479 | 714077 | 464598 | 249479 | 100% | 100% | 107.3% | 102.4% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-11-30 | 2007-02-06 | 121 | 388 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Ampawid | 118202017 | Day Care Center | 1 | 552346 | 448599 | 103747 | 448599 |  | 103747 | 552346 | 448599 | 103747 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2008-07-18 | 86 | 278 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Andap | 118202018 | PWS II | 1 | 2218221 | 2077050 | 141171 | 2077050 |  | 141171 | 2218221 | 2077050 | 141171 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-12-01 | 2008-04-25 | 2008-07-16 | 146 | 288 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Anitap | 118202019 | Water System Level II | 1 | 1909680.75 | 1363786 | 545894.75 | 1363786 | 3rd Tranche | 545894.75 | 1909680.75 | 1363786 | 545894.75 | 100% | 100% | 100% | 100% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-15 | 2005-12-30 | 2006-02-15 | 76 | 70 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Bagong Silang | 118202020 | Corn Mill | 1 | 1393954 | 821610 | 572344 | 821610 | 3rd Tranche | 572344 | 1393954 | 821610 | 572344 | 100% | 100% | 100% | 100% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-01 | 2005-11-30 | 2006-04-11 | 60 | 199 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Banbanon | 118202002 | PWS II | 1 | 1930701.67 | 1877301.67 | 53400 | 1877301.67 |  | 53400 | 1930701.67 | 1877301.67 | 53400 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-12-01 | 2008-05-15 | 2008-08-28 | 166 | 285 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Bayanihan |  | Solar Drier | 1 | 390538 | 255319 | 135219 | 255319 |  | 135219 | 390538 | 255319 | 135219 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2007-02-01 | 2007-04-30 | 2007-08-29 | 88 | 45 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Belmonte | 118202021 | Multi-Purpose Shed | 1 | 739772 | 716283 | 23489 | 716283 |  | 24489 | 740772 | 716283 | 24489 | 100% | 100% | 104.3% | 100.1% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2008-06-06 | 86 | 290 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Binasbas | 118202003 | Water System Level II | 1 | 985161 | 679020 | 306141 | 679020 |  | 311141 | 990161 | 679020 | 311141 | 100% | 100% | 101.6% | 100.5% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2007-01-30 | 2007-02-12 | 121 | 225 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Bullucan | 118202022 | Water System Level II | 1 | 1970351 | 1520938 | 449413 | 1520938 |  | 449413 | 1970351 | 1520938 | 449413 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-12-30 | 2007-03-06 | 151 | 124 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Buhi |  | Corn Mill | 1 | 1390789 | 892365 | 498424 | 892365 | 3rd Tranche | 498424 | 1390789 | 892365 | 498424 | 100% | 100% | 100% | 100% | 100% | 2005-05-17 | 2005-07-07 | 2005-10-03 | 2005-12-30 | 2006-05-18 | 88 | 169 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Candiis |  | Multi-Purpose Building | 1 | 728821.2 | 580000 | 148821.2 | 580000 |  | 148821.2 | 728821.2 | 580000 | 148821.2 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2008-01-04 | 2008-02-29 | 2008-07-19 | 56 | 270 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Cebulida | 118202004 | Dump Truck | 1 | 174647 | 174647 | 0 | 174647 | 3rd Tranche | 255293 | 429940 | 174647 | 255293 | 100% | 100% | #DIV/0! | 246.2% | 100% | 2005-05-17 | 2005-07-07 | 2005-10-03 | 2005-10-30 | 2006-10-10 | 27 | 385 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Concepcion | 118202023 | Health Station | 1 | 643863.34 | 600960 | 42903.34 | 600960 |  | 42903.94 | 643863.94 | 600960 | 42903.94 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2007-12-28 | 86 | 146 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Datu Ampunan | 118202024 | Water System Level II | 1 | 1788282 | 1055285 | 732997 | 1055285 | 3rd Tranche | 732997 | 1788282 | 1055285 | 732997 | 100% | 100% | 100% | 100% | 100% | 2005-05-17 | 2005-07-07 | 2005-10-03 | 2005-11-30 | 2006-05-24 | 58 | 217 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Datu Davao | 118202025 | Solar Drier | 1 | 1180450 | 935500 | 244950 | 935500 | 3rd Tranche | 244950 | 1180450 | 935500 | 244950 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2006-11-30 | 2006-12-05 | 60 | 30 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | El Katipunan - C4 | 118202027 | Water System Level II | 4 | 5509813 | 2721852 | 2787961 | 2721852 | 3rd Tranche | 2797961 | 5519813 | 2721852 | 2797961 | 100% | 100% | 100.4% | 100.2% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-15 | 2005-12-30 | 2006-04-26 | 76 | 131 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Il Papa | 118202005 | Dump Truck | 1 | 605765 | 429000 | 176765 | 429000 |  | 172265 | 601265 | 429000 | 172265 | 100% | 100% | 97.45% | 99.26% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2006-10-30 | 2006-12-21 | 29 | 125 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Imelda | 118202028 | Water System Level II | 1 | 2080801 | 1621979 | 458822 | 1621979 |  | 458822 | 2080801 | 1621979 | 458822 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2007-01-30 | 2007-05-18 | 121 | 419 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Imelda | 118202028 | Day Care Center | 1 | 540189.66 | 433239 | 106950.66 | 433239 |  | 106950.66 | 540189.66 | 433239 | 106950.66 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2008-07-22 | 86 | 40 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Inacayan | 118202029 | PWS II | 1 | 1845246.8 | 1675050 | 170196.8 | 1675050 |  | 170196.8 | 1845246.8 | 1675050 | 170196.8 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-12-01 | 2008-04-25 | 2008-08-08 | 146 | 186 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kagawasan |  | Multi-Purpose Building | 1 | 702241 | 542618 | 159623 | 542618 | 3rd Tranche | 163623 | 706241 | 542618 | 163623 | 100% | 100% | 102.5% | 100.6% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-11-30 | 2006-12-21 | 121 | 80 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kagawasan |  | Mobile Corn Sheller | 1 | 179851.81 | 118425 | 61426.81 | 118425 |  | 62876.31 | 181301.31 | 118425 | 62876.31 | 100% | 100% | 102.4% | 100.8% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2008-06-22 | 86 | 80 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kaligutan | 118202006 | Dump Truck | 1 | 389140 | 333140 | 56000 | 333140 |  | 56000 | 389140 | 333140 | 56000 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2006-10-30 | 2006-12-20 | 29 | 525 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kaligutan | 118202006 | Rural Health Station | 1 | 627338.67 | 566135.67 | 61203 | 566135.67 |  | 61203 | 627338.67 | 566135.67 | 61203 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2007-11-30 | 2007-12-19 | 25 | 525 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kibaguio |  | Rural Health Station | 1 | 646196.16 | 585924 | 60272.16 | 585924 |  | 60272.16 | 646196.16 | 585924 | 60272.16 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-12-01 | 2008-01-30 | 2008-02-08 | 60 | 146 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kidawa | 118202008 | RCPC Installation | 1 | 1023779 | 608746 | 415033 | 608746 | 3rd Tranche | 415033 | 1023779 | 608746 | 415033 | 100% | 100% | 100% | 100% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-15 | 2005-12-30 | 2006-05-30 | 76 | 284 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Kiokmay | 118202010 | Water System Level II | 1 | 1968351 | 1520938 | 447413 | 1520938 |  | 447413 | 1968351 | 1520938 | 447413 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-12-30 | 2007-03-06 | 151 | 207 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Laac | 118202014 | Multi-Purpose Shed | 1 | 1435670 | 1289500 | 146170 | 1289500 |  | 146170 | 1435670 | 1289500 | 146170 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2008-06-21 | 86 | 1118 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Libuton |  | Rural Electrification | 1 | 2268343.75 | 1378188 | 890155.75 | 1378188 | 3rd Tranche | 890155.75 | 2268343.75 | 1378188 | 890155.75 | 100% | 100% | 100% | 100% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-01 | 2005-11-30 | 2005-12-13 | 60 | 31 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Libuton |  | Day Care Center | 1 | 667126 | 427002 | 240124 | 427002 | 3rd Tranche | 240124 | 667126 | 427002 | 240124 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-11-30 | 2006-11-08 | 121 | 89 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Limot |  | Road Rehabilitation | 1 | 2268821 | 912230 | 1356591 | 912230 | 3rd Tranche | 1356591 | 2268821 | 912230 | 1356591 | 100% | 100% | 100% | 100% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-15 | 2006-03-31 | 2006-05-17 | 167 | 103 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | LS Sarmiento |  | Solar Drier | 1 | 215199 | 215199 | 0 | 215199 | 3rd Tranche | 133018 | 348217 | 215199 | 133018 | 100% | 100% | #DIV/0! | 161.8% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-15 | 2005-12-30 | 2006-04-10 | 76 | 89 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | LS Sarmiento |  | Multi Purpose Building | 1 | 728418.75 | 445369 | 283049.75 | 445369 | 3rd Tranche | 283049.75 | 728418.75 | 445369 | 283049.75 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-11-30 | no data | 121 | 116 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Mabuhay | 118202030 | Water System Level II | 1 | 1603099 | 815525 | 787574 | 815525 |  | 787574 | 1603099 | 815525 | 787574 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2007-01-30 | 2007-05-18 | 121 | 207 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Mabuhay | 118202030 | Rural Health Station | 1 | 632338.66 | 518635.66 | 113703 | 518635.66 |  | 113703 | 632338.66 | 518635.66 | 113703 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-06 | 2007-11-05 | 2008-01-30 | 2008-06-19 | 86 | 448 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Mangloy | 118202033 | Water System Level II | 1 | 1516431 | 880906 | 635525 | 880906 | 3rd Tranche | 635525 | 1516431 | 880906 | 635525 | 100% | 100% | 100% | 100% | 100% | 2005-05-18 | 2005-07-06 | 2005-10-01 | 2005-11-30 | 2006-05-30 | 60 | 216 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Melale | 118202034 | Electrication | 1 | 4388315.4 | 2071538.5 | 2316776.9 | 2071538.5 |  | 2316776.9 | 4388315.4 | 2071538.5 | 2316776.9 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-11-01 | 2007-01-30 | 2007-03-08 | 90 | 170 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Naga | 118202013 | Health Station | 1 | 696328 | 480435 | 215893 | 480435 | 3rd Tranche | 215893 | 696328 | 480435 | 215893 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-11-30 | 2006-12-07 | 121 | 209 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | New Betlehem | 118202035 | Rural Electrification | 1 | 2051261 | 2051261 | 0 | 2051261 | 3rd Tranche | 979220 | 3030481 | 2051261 | 979220 | 100% | 100% | #DIV/0! | 147.7% | 100% | 2005-05-17 | 2005-07-07 | 2005-10-03 | 2005-11-30 | 2006-01-27 | 58 | 40 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Panamoren | 118202036 | Spill Way Construction | 1 | 1341502 | 791269 | 550233 | 791269 | 3rd Tranche | 550233 | 1341502 | 791269 | 550233 | 100% | 100% | 100% | 100% | 100% | 2005-05-17 | 2005-07-07 | 2005-10-03 | 2005-11-30 | 2005-05-24 | 58 | 173 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Sabud | 118202037 | Water System Level II | 1 | 1060140 | 532657 | 527483 | 532657 | 3rd Tranche | 530483 | 1063140 | 532657 | 530483 | 100% | 100% | 100.6% | 100.3% | 100% | 2005-05-17 | 2005-07-07 | 2005-10-03 | 2005-11-30 | 2006-04-20 | 58 | 165 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Sabud | 118202037 | Dump Truck | 1 | 383640 | 290450 | 93190 | 290450 |  | 93190 | 383640 | 290450 | 93190 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2006-11-30 | 2007-01-31 | 60 | 165 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | San Antonio | 118202015 | School Building | 1 | 477274.89 | 324480 | 152794.89 | 324480 |  | 152794.9 | 477274.9 | 324480 | 152794.9 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-15 | 2008-07-14 | 71 | 437 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Sisimon | 118202040 | Rural Electrification | 1 | 1318821 | 1113783 | 205038 | 1113783 | 3rd Tranche | 205033 | 1318816 | 1113783 | 205033 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-08-01 | 2006-11-30 | 2006-12-11 | 121 | 46 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Sta Emelia | 118202038 | Rural Electrification | 1 | 2803304.45 | 2588417 | 214887.45 | 2588417 |  | 214887.45 | 2803304.45 | 2588417 | 214887.45 | 100% | 100% | 100% | 100% | 100% | 2007-05-29 | 2007-07-05 | 2007-11-05 | 2008-01-30 | 2008-01-28 | 86 | 185 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Laak | 118202 | Sto. Niño | 118202039 | Health Station | 1 | 653535 | 452847.5 | 200687.5 | 452847.5 |  | 200687.5 | 653535 | 452847.5 | 200687.5 | 100% | 100% | 100% | 100% | 100% | 2006-06-13 | 2006-07-12 | 2006-10-01 | 2006-12-30 | 2007-03-09 | 90 | 198 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Anitapan | 118203012 | Corn Mill | 1 | 1315952.68 | 1188635 | 127317.68 | 1188635 |  | 127317.68 | 1315952.68 | 1188635 | 127317.68 | 100% | 100% | 100% | 100% | 100% | 2008-03-19 | 2008-05-02 | 2008-08-04 | 2008-12-31 | 2009-03-05 | 149 | 322 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Cabuyuan | 118203013 | Steel Footbridge | 1 | 1047201 | 878068 | 169133 | 878068 |  | 169133 | 1047201 | 878068 | 169133 | 100% | 100% | 100% | 100% | 100% | 2008-12-12 | 2008-12-17 | 2009-04-28 | 2009-06-24 | 2009-06-25 | 57 | 470 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Cadunan | 118203002 | PWS Level 2 | 1 | 1740681 | 1225659 | 515022 | 1225659 |  | 470255 | 1695914 | 1225659 | 470255 | 100% | 100% | 91.31% | 97.43% | 100% | 2008-03-19 | 2008-05-02 | 2008-09-01 | 2008-12-31 | 2009-03-06 | 121 | 235 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini ( Doña Alicia) | 118203 | Candinuyan |  | Road | 1 | 1248925 | 1050050 | 198875 | 1050050 |  | 198875 | 1248925 | 1050050 | 198875 | 100% | 100% | 100% | 100% | 100% | 2007-01-11 | 2007-03-02 | 2007-09-24 | 2007-12-23 | 2008-02-15 | 90 | 233 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Cuambog | 118203007 | Drainage | 1 | 1180030.2 | 926463.5 | 253566.7 | 926463.5 |  | 253566.7 | 1180030.2 | 926463.5 | 253566.7 | 100% | 100% | 100% | 100% | 100% | 2008-03-19 | 2008-05-02 | 2008-08-04 | 2008-12-31 | 2009-03-10 | 149 | 450 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Del Pilar | 118203014 | Improvement of PWS II | 1 | 570990 | 386070 | 184920 | 386070 |  | 184920 | 570990 | 386070 | 184920 | 100% | 100% | 100% | 100% | 100% | 2007-01-11 | 2007-03-02 | 2007-11-05 | 2008-01-15 | 2008-02-14 | 71 | 396 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Del Pilar | 118203014 | Box Culvert | 1 | 634314 | 434552 | 199762 | 347641.6 |  | 199762 | 547403.6 | 347641.6 | 199762 | 100% | 100% | 100% | 86.3% | 100% | 2008-12-12 | 2008-12-17 | 2009-04-28 | 2009-06-15 | 2009-06-19 | 48 | 400 | The 2nd and final tranche no longer requested; 80% grant fund downloaded sufficient for the completion of the sub-project | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Golden Valley | 118203016 | PWS II | 1 | 1651041 | 1243053 | 407988 | 1243053 |  | 407988 | 1651041 | 1243053 | 407988 | 100% | 100% | 100% | 100% | 100% | 2008-12-12 | 2008-12-17 | 2009-04-28 | 2009-06-22 | 2009-06-23 | 55 | 278 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Libodon | 118203015 | Suspended Footbridge | 1 | 1064544 | 894384 | 170160 | 894384 |  | 170160 | 1064544 | 894384 | 170160 | 100% | 100% | 100% | 100% | 100% | 2008-12-12 | 2008-12-17 | 2009-04-06 | 2009-06-15 | 2009-06-19 | 70 | 205 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini ( Doña Alicia) | 118203 | Mambatang |  | Road | 1 | 1249560 | 911100 | 338460 | 911100 |  | 351460 | 1262560 | 911100 | 351460 | 100% | 100% | 103.8% | 101% | 100% | 2007-01-11 | 2007-03-02 | 2007-08-27 | 2007-10-30 | 2008-02-12 | 64 | 41 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini ( Doña Alicia) | 118203 | Mambatang |  | MP Pavement | 1 | 379289 | 240816 | 138473 | 192652.8 |  | 138473 | 331125.8 | 192652.8 | 138473 | 100% | 100% | 100% | 87.3% | 100% | 2008-12-12 | 2008-12-17 | 2009-03-23 | 2009-06-15 | 2009-06-23 | 84 | 300 | The 2nd and final tranche no longer requested; 80% grant fund downloaded sufficient for the completion of the sub-project | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini ( Doña Alicia) | 118203 | Manasa |  | Pavement | 1 | 920975 | 702800 | 218175 | 702800 |  | 218175 | 920975 | 702800 | 218175 | 100% | 100% | 100% | 100% | 100% | 2007-01-11 | 2007-03-02 | 2007-08-27 | 2007-11-30 | 2008-02-12 | 95 | 187 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini ( Doña Alicia) | 118203 | Mascareg |  | Day Care Center | 1 | 610257 | 504584 | 105673 | 504584 |  | 105673 | 610257 | 504584 | 105673 | 100% | 100% | 100% | 100% | 100% | 2008-03-19 | 2008-05-02 | 2008-08-04 | 2008-12-31 | 2009-03-05 | 149 | 163 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Pangibiran | 118203017 | Provision of Corn Mill | 1 | 1092864 | 859414 | 233450 | 859414 |  | 233450 | 1092864 | 859414 | 233450 | 100% | 100% | 100% | 100% | 100% | 2007-01-11 | 2007-03-02 | 2007-07-04 | 2007-10-30 | 2008-02-28 | 118 | 200 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Pindasan | 118203006 | PWS Level 2 | 1 | 1085500.92 | 954658.5 | 130842.42 | 954658.5 |  | 114779.17 | 1069437.67 | 954658.5 | 114779.17 | 100% | 100% | 87.72% | 98.52% | 100% | 2008-03-19 | 2008-05-02 | 2008-08-11 | 2008-12-31 | 2009-03-06 | 142 | 130 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | San Antonio | 118203018 | PWS II | 1 | 1390727 | 1109125 | 281602 | 1109125 |  | 281602 | 1390727 | 1109125 | 281602 | 100% | 100% | 100% | 100% | 100% | 2008-12-12 | 2008-12-17 | 2009-05-18 | 2009-07-10 | 2009-07-15 | 53 | 130 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini ( Doña Alicia) | 118203 | Singapore |  | Road | 1 | 528805 | 412530 | 116275 | 412530 |  | 122650 | 535180 | 412530 | 122650 | 100% | 100% | 105.5% | 101.2% | 100% | 2007-01-11 | 2007-03-02 | 2007-09-24 | 2007-11-23 | 2008-02-15 | 60 | 53 | completed | 1 | MINDANAO
XI | 11 | Compostela Valley | 1182 | Mabini | 118203 | Tagnanan | 118203011 | Upgrading of PWS II | 1 | 616486 | 478036 | 138450 | 478036 |  | 153450 | 631486 | 478036 | 153450 | 100% | 100% | 110.8% | 102.4% | 100% | 2007-01-11 | 2007-03-02 | 2007-06-18 | 2007-09-16 | 2008-02-28 | 90 | 240 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Balagunan | 112318001 | Construction of Potable Water System Level II | 1 | 1351545 | 551375 | 800170 | 551375 | 3rd Tranche | 804545.8 | 1355920.8 | 551375 | 804545.8 | 100% | 100% | 100.5% | 100.3% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-24 | 2005-07-24 | 2005-08-29 | 150 | 325 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Balagunan | 112318001 | Construction of Multi-Purpose Shed | 1 | 1115696.75 | 805993 | 309703.75 | 805993 | 3rd Tranche | 309703.75 | 1115696.75 | 805993 | 309703.75 | 100% | 100% | 100% | 100% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-05-15 | 2006-06-29 | 126 | 820 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Balagunan | 112318001 | Expansion of Potable Water System II | 1 | 584180 | 428000 | 156180 | 428000 |  | 156180 | 584180 | 428000 | 156180 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-20 | 2009-06-15 | 2009-06-29 | 87 | 251 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Bobongon | 112318002 | Construction of Potable Water System Level II | 1 | 772488 | 501696 | 270792 | 501696 | 3rd Tranche | 325054.5 | 826750.5 | 501696 | 325054.5 | 100% | 100% | 120% | 107% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-15 | 2005-07-15 | 2005-08-25 | 150 | 341 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Bobongon | 112318002 | Flood Control Facility | 1 | 927167 | 719322 | 207845 | 719322 |  | 207845 | 927167 | 719322 | 207845 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-04-01 | 2009-06-29 | 2009-07-08 | 89 | 915 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Casig-Ang | 112318016 | Construction of Food Terminal | 1 | 825597 | 432728 | 392869 | 432728 | 3rd Tranche | 392869 | 825597 | 432728 | 392869 | 100% | 100% | 100% | 100% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-05-15 | 2006-04-20 | 126 | 475 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Casig-ang | 112318016 | Construction of Day Care Center | 1 | 650000 | 575226 | 74774 | 575226 |  | 74774 | 650000 | 575226 | 74774 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-21 | 2009-05-30 | 2009-06-17 | 70 | 577 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Esperanza | 112318003 | Construction of Level II Water System | 1 | 770476.72 | 527246.42 | 243230.3 | 527246.42 | 3rd Tranche | 243230.3 | 770476.72 | 527246.42 | 243230.3 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-11-07 | 2003-11-30 | 84 | 503 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Esperanza | 112318003 | Construction of Multi-Purpose Bldg | 1 | 500000 | 446015 | 53985 | 446015 |  | 53985 | 500000 | 446015 | 53985 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-26 | 2009-05-30 | 2009-06-30 | 65 | 551 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Kimamon | 112318004 | Construction of Level II Water System | 1 | 2489029.8 | 1703749 | 785280.8 | 1703749 | 3rd Tranche | 785280.8 | 2489029.8 | 1703749 | 785280.8 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-12-31 | 2004-04-18 | 138 | 1053 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Kimamon | 112318004 | Construction of Multi-Purpose Shed | 1 | 1038840.75 | 663000 | 375840.75 | 663000 | 3rd Tranche | 261203.75 | 924203.75 | 663000 | 261203.75 | 100% | 100% | 69.5% | 88.96% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-05-15 | 2006-04-27 | 126 | 1117 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Kimamon | 112318004 | Construction of Multi-Purpose Bldg | 1 | 500000 | 406015 | 93985 | 406015 |  | 93985 | 500000 | 406015 | 93985 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-26 | 2009-06-23 | 2009-06-28 | 89 | 1297 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Kinamayan | 112318005 | Construction of Potable Water System II | 1 | 959944 | 574453 | 385491 | 574453 | 3rd Tranche | 439753.5 | 1014206.5 | 574453 | 439753.5 | 100% | 100% | 114.1% | 105.7% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-25 | 2005-07-25 | 2005-10-24 | 150 | 250 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Kinamayan | 112318005 | Expansion of Potable Water System II | 1 | 282250 | 244064 | 38186 | 244064 |  | 38186 | 282250 | 244064 | 38186 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-04-01 | 2009-06-15 | 2009-07-20 | 75 | 976 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | La libertad | 112318006 | Construction of Flood Control | 1 | 921130.75 | 405087 | 516043.75 | 405087 | 3rd Tranche | 516043.75 | 921130.75 | 405087 | 516043.75 | 100% | 100% | 100% | 100% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-05-15 | 2006-05-12 | 126 | 335 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | La Libertad | 112318006 | Construction of Multi-Purpose Bldg | 1 | 500000 | 376015 | 123985 | 376015 |  | 123985 | 500000 | 376015 | 123985 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-26 | 2009-06-20 | 2009-06-17 | 86 | 1262 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | La Libertad - C3 | 112318006 | Construction of Level II Water System | 3 | 1596552.5 | 1013473 | 583079.5 | 1013473 | 3rd Tranche | 583079.5 | 1596552.5 | 1013473 | 583079.5 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-10-24 | 2004-02-24 | 70 | 935 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Lungaog | 112318007 | Construction of Level II Water System | 1 | 1288089.3 | 755155 | 532934.3 | 755155 | 3rd Tranche | 532934.3 | 1288089.3 | 755155 | 532934.3 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-11-07 | 2004-02-13 | 84 | 597 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Lungaog | 112318007 | Construction of Community Reading Center | 1 | 611962 | 567713 | 44249 | 567713 |  | 44249 | 611962 | 567713 | 44249 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-27 | 2009-05-30 | 2009-07-02 | 64 | 698 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Magwawa | 112318008 | Construction of Corn Mill Project with 12.5HP | 1 | 712973.2 | 564438 | 148535.2 | 564438 | 3rd Tranche | 148535.2 | 712973.2 | 564438 | 148535.2 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-11-07 | 2003-12-16 | 84 | 200 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Magwawa | 112318008 | Installation of Barangay Electrification (2.50km) | 1 | 827393 | 304599 | 522794 | 304599 | 3rd Tranche | 403137.5 | 707736.5 | 304599 | 403137.5 | 100% | 100% | 77.11% | 85.54% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-24 | 2005-07-24 | no data | 150 | 80 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Magwawa | 112318008 | Construction of Multi-Purpose Bldg | 1 | 500000 | 438015 | 61985 | 438015 |  | 61985 | 500000 | 438015 | 61985 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-04-01 | 2009-06-29 | 2009-07-21 | 89 | 270 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | New Katipunan | 112318009 | Construction of Multi-Purpose Shed | 1 | 1132186.75 | 790483 | 341703.75 | 790483 | 3rd Tranche | 341703.75 | 1132186.75 | 790483 | 341703.75 | 100% | 100% | 100% | 100% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-05-15 | 2006-04-27 | 126 | 770 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | New Katipunan | 112318009 | Construction of Multi-Purpose Bldg | 1 | 500000 | 436506 | 63494 | 436506 |  | 63494 | 500000 | 436506 | 63494 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-23 | 2009-05-30 | 2009-07-20 | 68 | 998 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | New Katipunan - C2 | 112318009 | Skills Development Training for Out of School Youth | 2 | 719400 | 596500 | 122900 | 596500 | 3rd Tranche | 127275 | 723775 | 596500 | 127275 | 100% | 100% | 103.6% | 100.6% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-26 | 2005-07-26 | 2005-07-08 | 150 | 70 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | New Visayas | 112318017 | Installation of Barangay Electrification | 1 | 1588287 | 550998 | 1037289 | 550998 | 3rd Tranche | 1041551.5 | 1592549.5 | 550998 | 1041551.5 | 100% | 100% | 100.4% | 100.3% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-26 | 2005-07-26 | 2005-08-26 | 150 | 60 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | New Visayas | 112318017 | Completion of Multi-Purpose Shed | 1 | 1222470 | 860802 | 361668 | 860802 |  | 131668 | 992470 | 860802 | 131668 | 100% | 100% | 36.41% | 81.19% | 100% | 2008-09-08 | 2009-01-06 | 2009-04-23 | 2009-06-30 | 2009-07-14 | 68 | 461 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Pantaron | 112318010 | Construction of Level II Water System | 1 | 1235708.3 | 707989 | 527719.3 | 707989 | 3rd Tranche | 527719.3 | 1235708.3 | 707989 | 527719.3 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-11-07 | 2004-03-22 | 84 | 415 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Pantaron | 112318010 | Construction of Multi-Purpose pavement w/Storage | 1 | 1218736.75 | 762533 | 456203.75 | 762533 | 3rd Tranche | 456203.75 | 1218736.75 | 762533 | 456203.75 | 100% | 100% | 100% | 100% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-06-30 | 2006-06-29 | 172 | 415 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Pantaron | 112318010 | Upgrading of potable Water System II | 1 | 1009049 | 832835 | 176214 | 832835 |  | 176214 | 1009049 | 832835 | 176214 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-30 | 2009-06-27 | 2009-07-19 | 89 | 510 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Salvacion | 112318018 | Construction of Potable Water System Level II | 1 | 1402882 | 621137 | 781745 | 621137 | 3rd Tranche | 846007.5 | 1467144.5 | 621137 | 846007.5 | 100% | 100% | 108.2% | 104.6% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-28 | 2005-07-28 | 2005-09-28 | 150 | 215 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Salvacion | 112318018 | Construction of Multi-Purpose Bldg | 1 | 500000 | 376015 | 123985 | 376015 |  | 123985 | 500000 | 376015 | 123985 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-04-13 | 2009-06-20 | 2009-06-28 | 68 | 660 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | San Jose | 112318013 | Construction of Potable Water System II | 1 | 1809706 | 904853 | 904853 | 904853 | 3rd Tranche | 668672.75 | 1573525.75 | 904853 | 668672.75 | 100% | 100% | 73.9% | 86.95% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-26 | 2005-07-26 | 2005-09-08 | 150 | 363 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | San Jose | 112318013 | Construction of Tribal Housing | 1 | 2006845.75 | 1395002 | 611843.75 | 1395002 | 3rd Tranche | 611843.75 | 2006845.75 | 1395002 | 611843.75 | 100% | 100% | 100% | 100% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-06-30 | 2006-06-30 | 172 | 49 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | San Jose | 112318013 | Completion of Multi-Purpose Shed | 1 | 632250 | 552940 | 79310 | 552940 |  | 79310 | 632250 | 552940 | 79310 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-05-01 | 2009-06-29 | 2009-07-05 | 59 | 497 |  | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | San Miguel | 112318014 | Construction of Multi-Purpose Bldg | 1 | 500000 | 421015 | 78985 | 421015 |  | 78985 | 500000 | 421015 | 78985 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-23 | 2009-06-20 | 2009-07-07 | 89 | 610 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | San Vicente | 112318019 | Construction of Potable Water System II | 1 | 784580 | 544382 | 240198 | 544381.4 | 3rd Tranche | 394460.5 | 938841.9 | 544381.4 | 394460.5 | 100% | 100% | 164.2% | 119.7% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-24 | 2005-07-24 | 2005-10-23 | 150 | 160 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | San Vicente | 112318019 | Construction of Multi-Purpose Training Center | 1 | 828265 | 445174 | 383091 | 445174 | 3rd Tranche | 403091 | 848265 | 445174 | 403091 | 100% | 100% | 105.2% | 102.4% | 100% | 2005-10-14 | 2005-11-18 | 2006-01-09 | 2006-05-15 | 2006-03-30 | 126 | 160 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | San Vicente | 112318019 | Construction of Community Reading Center | 1 | 611962 | 567713 | 44249 | 567713 |  | 44249 | 611962 | 567713 | 44249 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-30 | 2009-05-30 | 2009-06-16 | 61 | 395 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Talomo | 112318015 | Installation of Barangay Electrification | 1 | 1041976.3 | 550007 | 491969.3 | 550007 | 3rd Tranche | 496344.3 | 1046351.3 | 550007 | 496344.3 | 100% | 100% | 100.9% | 100.4% | 100% | 2004-09-08 | 2004-11-23 | 2005-02-25 | 2005-07-25 | 2005-08-04 | 150 | 65 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Talomo | 112318015 | Completion of Multi-Purpose Shed | 1 | 659067 | 589755 | 69312 | 589755 |  | 69312 | 659067 | 589755 | 69312 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-05-01 | 2009-06-29 | 2009-06-26 | 59 | 899 |  | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Tibal-og | 112318011 | Construction of Training Center | 1 | 500000 | 194948 | 305052 | 194948 |  | 305052 | 500000 | 194948 | 305052 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-23 | 2009-05-30 | 2009-06-24 | 68 | 6220 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Sto.Tomas | 112318 | Tulalian | 112318020 | Construction of Level II Water System | 1 | 926508.4 | 427951 | 498557.4 | 427951 | 3rd Tranche | 498557.4 | 926508.4 | 427951 | 498557.4 | 100% | 100% | 100% | 100% | 100% | 2003-04-27 | 2003-06-27 | 2003-08-15 | 2003-11-07 | 2004-03-05 | 84 | 340 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Sto.Tomas | 112318 | Tulalian | 112318020 | Construction of 1 classroom school Building | 1 | 550000 | 467086 | 82914 | 467086 |  | 82914 | 550000 | 467086 | 82914 | 100% | 100% | 100% | 100% | 100% | 2008-09-08 | 2009-01-06 | 2009-03-25 | 2009-06-23 | 2009-07-18 | 90 | 736 |  | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Barobo |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 692325 | 500000 | 192325 | 500000 |  | 192325 | 692325 | 500000 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-23 | 59 | 200 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Basagan |  | Tribal Housing (42) | 1 | 1390701.14 | 695797.98 | 694903.16 | 695797.98 | 3rd Tranche | 694903.16 | 1390701.14 | 695797.98 | 694903.16 | 100% | 100% | 100% | 100% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-09-15 | 2004-11-06 | 184 | 72 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Basagan |  | 2-Units Motorcycle | 1 | 190000 | 150000 | 40000 | 150000 |  | 40000 | 190000 | 150000 | 40000 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-07-30 | 2006-08-31 | 29 | 92 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Butay |  | Skills Training on FAITH | 1 | 1164977 | 475000 | 689977 | 475000 | 3rd Tranche | 689977 | 1164977 | 475000 | 689977 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-08-15 | 2005-11-15 | 2005-12-29 | 92 | 258 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Butay |  | Shelter Improvement | 1 | 963900 | 640000 | 323900 | 640000 |  | 323900 | 963900 | 640000 | 323900 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-09-30 | 2006-11-15 | 91 | 135 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Butay |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 697325 | 505000 | 192325 | 505000 |  | 192325 | 697325 | 505000 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-18 | 59 | 137 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Cabadiangan |  | Potable Water System L-II | 1 | 237259.67 | 88654.39 | 148605.28 | 88654.39 | 3rd Tranche | 177887.28 | 266541.67 | 88654.39 | 177887.28 | 100% | 100% | 119.7% | 112.3% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-06-15 | 2004-06-25 | 92 | 135 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Cabadiangan |  | Water System | 1 | 422300 | 230000 | 192300 | 230000 | 3rd Tranche | 192300 | 422300 | 230000 | 192300 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-09-01 | 2005-11-30 | 2005-12-27 | 90 | 150 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Cabadiangan |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 697325 | 505000 | 192325 | 505000 |  | 192325 | 697325 | 505000 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-11 | 59 | 150 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Dagohoy | 112322001 | Shallow Tube Well | 1 | 1033210 | 800000 | 233210 | 800000 | 3rd Tranche | 233210 | 1033210 | 800000 | 233210 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-08-15 | 2005-11-15 | 2006-01-19 | 92 | 92 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Dagohoy | 112322001 | Impvt rice mill & Solar Drier, shed | 1 | 401150 | 300000 | 101150 | 300000 |  | 101150 | 401150 | 300000 | 101150 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-09-30 | 2006-11-24 | 91 | 92 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Dagohoy | 112322001 | PWS Level II | 1 | 639375 | 450000 | 189375 | 450000 |  | 189375 | 639375 | 450000 | 189375 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-05-02 | 2009-06-30 | 2009-08-17 | 59 | 100 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Km. 31 |  | Tribal Housing (60) | 1 | 1834550.29 | 937428.65 | 897121.64 | 937428.65 | 3rd Tranche | 897121.64 | 1834550.29 | 937428.65 | 897121.64 | 100% | 100% | 100% | 100% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-09-15 | 2004-11-04 | 184 | 119 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Km. 31 |  | Skills training on Sustainability Agri. | 1 | 548922 | 330000 | 218922 | 330000 |  | 218922 | 548922 | 330000 | 218922 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-09-30 | 2006-12-23 | 91 | 137 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Km.31 |  | PWS Level II | 1 | 779375 | 550000 | 229375 | 550000 |  | 229375 | 779375 | 550000 | 229375 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-05-02 | 2009-06-22 | 2009-08-12 | 51 | 142 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Lumabag |  | Tribal Housing & Sanitation | 1 | 2627864.2 | 1700000 | 927864.2 | 1700000 |  | 927864.2 | 2627864.2 | 1700000 | 927864.2 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-12-31 | 2006-12-12 | 183 | 124 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Lumabag |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 692325 | 505000 | 187325 | 505000 |  | 192325 | 697325 | 505000 | 192325 | 100% | 100% | 102.7% | 100.7% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-17 | 59 | 90 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Mangane |  | Corn Mill | 1 | 688714.09 | 515042.98 | 173671.11 | 515042.98 | 3rd Tranche | 196771.11 | 711814.09 | 515042.98 | 196771.11 | 100% | 100% | 113.3% | 103.4% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-06-15 | 2004-08-28 | 92 | 154 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Misolong |  | Skills Training on SALT | 1 | 1107177 | 600000 | 507177 | 600000 | 3rd Tranche | 507177 | 1107177 | 600000 | 507177 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-08-15 | 2005-11-15 | 2005-12-16 | 92 | 200 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Misolong |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 695665 | 503340 | 192325 | 503340 |  | 192325 | 695665 | 503340 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-10 | 59 | 199 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Nasilaban |  | Corn Mill | 1 | 1020215.96 | 510107.98 | 510107.98 | 510107.98 | 3rd Tranche | 194671.11 | 704779.09 | 510107.98 | 194671.11 | 100% | 100% | 38.16% | 69.08% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-06-15 | 2004-09-13 | 92 | 272 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Nasilaban |  | 2-Units Motorcycle | 1 | 190000 | 150000 | 40000 | 150000 |  | 40000 | 190000 | 150000 | 40000 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-07-30 | 2006-08-31 | 29 | 171 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Nasilaban |  | Shelter Upgrading | 1 | 857800 | 534710 | 323090 | 534710 |  | 323090 | 857800 | 534710 | 323090 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-15 | 2009-05-31 | 2009-07-28 | 77 | 157 |  | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Natulinan |  | Shelter Upgrading | 1 | 719025 | 590000 | 129025 | 590000 |  | 129025 | 719025 | 590000 | 129025 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-15 | 2009-05-31 | 2009-07-31 | 77 | 132 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Paiton(Barubo) |  | Tribal Housing (86) | 1 | 2442497.08 | 1242860.04 | 1199637.04 | 1242860.04 | 3rd Tranche | 1199637.04 | 2442497.08 | 1242860.04 | 1199637.04 | 100% | 100% | 100% | 100% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-09-30 | 2004-10-29 | 199 | 86 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Palma Gil | 112322002 | Water System | 1 | 393750 | 210000 | 183750 | 210000 | 3rd Tranche | 183750 | 393750 | 210000 | 183750 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-09-01 | 2005-11-30 | 2005-12-29 | 90 | 220 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Palma Gil | 112322002 | Upgrading of Health Center & Capability Building on Oriental Medicine. | 1 | 630375 | 460000 | 170375 | 395000 |  | 40000 | 435000 | 395000 | 40000 | 100% | 100% | 23.48% | 69.01% | 100% | 2008-12-11 |  | 2009-05-02 | 2009-06-30 | 2009-08-07 | 59 | 480 |  | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Pongpong |  | PWS II | 1 | 429375 | 300000 | 129375 | 300000 |  | 129375 | 429375 | 300000 | 129375 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-05-02 | 2009-06-22 | 2009-08-19 | 51 | 50 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Salawao |  | Corn Mill | 1 | 981232 | 730000 | 251232 | 730000 | 3rd Tranche | 251232 | 981232 | 730000 | 251232 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-09-01 | 2005-11-30 | 2005-12-28 | 90 | 200 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Salawao |  | Shelter Upgrading | 1 | 724575 | 594950 | 129625 | 594950 |  | 129625 | 724575 | 594950 | 129625 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-15 | 2009-05-31 | 2009-07-24 | 77 | 133 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Sto. Niño | 112322003 | Community Library | 1 | 910490 | 700000 | 210490 | 700000 | 3rd Tranche | 210490 | 910490 | 700000 | 210490 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-09-01 | 2005-11-30 | 2005-12-28 | 90 | 408 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Sto. Niño | 112322003 | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 682325 | 490000 | 192325 | 490000 |  | 192325 | 682325 | 490000 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-09 | 59 | 400 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Tibi-tibi |  | Skills Training on SALT | 1 | 841927 | 420000 | 421927 | 420000 | 3rd Tranche | 421927 | 841927 | 420000 | 421927 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-08-15 | 2005-11-15 | 2005-12-28 | 92 | 157 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Tibi-Tibi |  | Tribal Housing 32-units | 1 | 1252936 | 800000 | 452936 | 800000 |  | 452936 | 1252936 | 800000 | 452936 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-12-31 | 2006-12-07 | 183 | 32 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Tibi-Tibi |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 689325 | 497000 | 192325 | 497000 |  | 192325 | 689325 | 497000 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-08 | 59 | 146 |  | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Tibucag |  | Corn Mill | 1 | 683779.09 | 510107.98 | 173671.11 | 510107.98 | 3rd Tranche | 180236.11 | 690344.09 | 510107.98 | 180236.11 | 100% | 100% | 103.8% | 101% | 100% | 2003-11-29 | 2004-01-29 | 2004-03-15 | 2004-06-15 | 2004-09-05 | 92 | 139 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Tibucag |  | Capability Building on Sustainable Agriculture | 1 | 820777 | 335000 | 485777 | 335000 | 3rd Tranche | 485777 | 820777 | 335000 | 485777 | 100% | 100% | 100% | 100% | 100% | 2005-05-05 | 2005-06-29 | 2005-08-15 | 2005-11-15 | no data | 92 | 126 | completed | 1 | MINDANAO
XI | 11 | Davao Del Norte | 1123 | Talaingod | 112322 | Tibucag |  | Water System LII & Sanitation | 1 | 614800 | 430000 | 184800 | 430000 |  | 184800 | 614800 | 430000 | 184800 | 100% | 100% | 100% | 100% | 100% | 2006-04-24 | 2006-05-30 | 2006-07-01 | 2006-10-30 | 2006-12-22 | 121 | 187 | completed | 1 | MINDANAO
XI | 11 | Davao del Norte | 1123 | Talaingod | 112322 | Tibucag |  | Capability Building on Sustainable Agriculture & Upland Development. | 1 | 707325 | 515000 | 192325 | 515000 |  | 192325 | 707325 | 515000 | 192325 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-02 | 2009-04-30 | 2009-06-23 | 59 | 187 |  | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Cayawan | 112508002 | Capability Building on Rubber Farming Technology and Soil Erosion Control | 1 | 1000747 | 699275 | 301472 | 699275 |  | 301472 | 1000747 | 699275 | 301472 | 100% | 100% | 100% | 100% | 100% | 2007-05-24 | 2007-06-13 | 2007-11-01 | 2008-04-01 | 2008-04-03 | 152 | 319 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Central | 112508003 | PWS II | 1 | 1288699 | 416611 | 872088 | 416611 |  | 872088 | 1288699 | 416611 | 872088 | 100% | 100% | 100% | 100% | 100% | 2007-05-24 | 2007-06-13 | 2007-10-01 | 2008-03-10 | 2008-03-11 | 161 | 680 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Concepcion | 112508004 | Road Improvement | 1 | 1520007 | 731720 | 788287 | 731720 |  | 788287 | 1520007 | 731720 | 788287 | 100% | 100% | 100% | 100% | 100% | 2007-05-24 | 2007-06-13 | 2008-01-01 | 2008-11-30 | 2008-12-11 | 334 | 184 | The decrease on the Total Project Cost is due to the unrecorded adjustments on the LCC utilization taken up only this month. | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Del Pilar | 112508006 | Water System Level II | 1 | 1834374.33 | 1600260.19 | 234114.14 | 1600260.19 |  | 234114.14 | 1834374.33 | 1600260.19 | 234114.14 | 100% | 100% | 100% | 100% | 100% | 2006-06-15 | 2006-07-12 | 2006-10-25 | 2006-11-30 | 2007-01-18 | 36 | 363 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Guza | 112508007 | PWS II | 1 | 1156658 | 1009400 | 147258 | 1009400 |  | 147258 | 1156658 | 1009400 | 147258 | 100% | 100% | 100% | 100% | 100% | 2008-04-09 | 2008-05-26 | 2008-09-12 | 2008-11-30 | 2008-12-10 | 79 | 200 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Holy Cross | 112508008 | Road Upgrading | 1 | 2868698.28 | 1374420.31 | 1494277.97 | 1374420.31 |  | 1494277.97 | 2868698.28 | 1374420.31 | 1494277.97 | 100% | 100% | 100% | 100% | 100% | 2006-06-15 | 2006-07-12 | 2006-09-01 | 2006-11-30 | 2006-12-08 | 90 | 1299 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Lambog | 112508018 | PWS II | 1 | 1170634 | 794146 | 376488 | 794146 |  | 376488 | 1170634 | 794146 | 376488 | 100% | 100% | 100% | 100% | 100% | 2007-05-24 | 2007-06-13 | 2007-10-01 | 2008-04-01 | 2008-04-03 | 183 | 94 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Mabini | 112508009 | PWS II | 1 | 772490 | 524942 | 247548 | 524942 |  | 247548 | 772490 | 524942 | 247548 | 100% | 100% | 100% | 100% | 100% | 2007-05-24 | 2007-06-13 | 2007-11-05 | 2008-05-19 | 2008-05-30 | 196 | 95 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Rizal | 112508012 | Hanging Bridge | 1 | 2357325 | 2125319.5 | 232005.5 | 2125319.5 |  | 315005.5 | 2440325 | 2125319.5 | 315005.5 | 100% | 100% | 135.8% | 103.5% | 100% | 2006-06-15 | 2006-07-12 | 2006-10-01 | 2006-12-30 | 2007-01-17 | 90 | 221 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Rizal | 112508012 | PWS II | 1 | 968011 | 687488 | 280523 | 687488 |  | 280523 | 968011 | 687488 | 280523 | 100% | 100% | 100% | 100% | 100% | 2008-04-09 | 2008-05-26 | 2008-08-14 | 2008-11-30 | 2008-12-09 | 108 | 252 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | San fermin | 112508013 | PWS II | 1 | 796620 | 460809 | 335811 | 460809 |  | 335811 | 796620 | 460809 | 335811 | 100% | 100% | 100% | 100% | 100% | 2008-04-09 | 2008-05-26 | 2008-08-20 | 2008-11-30 | 2008-12-10 | 102 | 205 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | San ignacio | 112508014 | Food Terminal | 1 | 2527981 | 1242303 | 1285678 | 1242303 |  | 1285678 | 2527981 | 1242303 | 1285678 | 100% | 100% | 100% | 100% | 100% | 2008-04-09 | 2008-05-26 | 2008-11-05 | 2009-02-16 | 2009-03-05 | 103 | 1113 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | San Isidro | 112508015 | PWS II | 1 | 1027183 | 832435 | 194748 | 832435 |  | 194748 | 1027183 | 832435 | 194748 | 100% | 100% | 100% | 100% | 100% | 2007-05-24 | 2007-06-13 | 2007-10-01 | 2008-03-10 | 2008-03-11 | 161 | 306 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | New Taokanga | 112508016 | Road | 1 | 2368387 | 1100871 | 1267516 | 550435.5 |  | 1267516 | 1817951.5 | 550435.5 | 1267516 | 100% | 100% | 100% | 76.76% | 100% | 2007-05-24 | 2007-06-13 | 2008-01-01 | 2008-12-31 | n/a | 365 | 543 | completed as built | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Manay | 112508 | Zaragoza | 112508017 | Road Construction | 1 | 3143017 | 1700000 | 1443017 | 1700000 |  | 1443017 | 3143017 | 1700000 | 1443017 | 100% | 100% | 100% | 100% | 100% | 2008-04-09 | 2008-05-26 | 2008-10-16 | 2009-04-30 | 2009-05-05 | 196 | 189 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Cabagayan | 112511001 | Water System | 1 | 1676003 | 833734 | 842269 | 833734 | 3rd Tranche | 842269 | 1676003 | 833734 | 842269 | 100% | 100% | 100% | 100% | 100% | 2005-05-06 | 2005-06-28 | 2005-09-15 | 2005-12-15 | 2006-02-13 | 91 | 625 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Cabagayan | 112511001 | Health Center | 1 | 564199 | 316110 | 248089 | 316110 |  | 248089 | 564199 | 316110 | 248089 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-12-14 | 2006-12-21 | 120 | 625 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Cabagayan | 112511001 | Extension of PWS II | 1 | 751989 | 647164 | 104825 | 647164 |  | 104825 | 751989 | 647164 | 104825 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-04-01 | 2009-06-24 | 2009-07-07 | 84 | 150 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Central (Pob) | 112511002 | School | 1 | 857673 | 234000 | 623673 | 234000 | 3rd Tranche | 653673 | 887673 | 234000 | 653673 | 100% | 100% | 104.8% | 103.5% | 100% | 2005-05-06 | 2005-06-28 | 2005-09-15 | 2005-12-15 | 2006-04-07 | 91 | 450 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Dadong | 112511003 | Water System | 1 | 1355958.2 | 770953 | 585005.2 | 770953 | 3rd Tranche | 585005.2 | 1355958.2 | 770953 | 585005.2 | 100% | 100% | 100% | 100% | 100% | 2005-05-06 | 2005-06-28 | 2005-09-15 | 2005-12-15 | 2006-01-13 | 91 | 232 | completed | 1 | MINDANAO
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Dadong | 112511003 | Road Upgrading | 1 | 2971121 | 469041 | 2502080 | 469041 |  | 2502080 | 2971121 | 469041 | 2502080 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-10-15 | 2006-12-27 | 60 | 232 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Dadong | 112511003 | Health Station | 1 | 655215 | 572845 | 82370 | 572845 |  | 82370 | 655215 | 572845 | 82370 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-15 | 2009-06-30 | 2009-07-09 | 107 | 256 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Jovellar | 112511004 | Potable Water System L-II | 1 | 2045991 | 866333 | 1179658 | 866333 | 3rd Tranche | 1179658 | 2045991 | 866333 | 1179658 | 100% | 100% | 100% | 100% | 100% | 2003-10-15 | 2005-12-17 | 2004-03-01 | 2004-08-15 | 2004-08-16 | 167 | 217 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Jovellar | 112511004 | Day Care Center | 1 | 532342 | 320107 | 212235 | 320107 |  | 212235 | 532342 | 320107 | 212235 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-12-14 | 2006-12-27 | 120 | 217 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Jovellar | 112511004 | Road Upgrading | 1 | 1090115 | 513300 | 576815 | 513300 |  | 576815 | 1090115 | 513300 | 576815 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-04-15 | 2009-06-22 | 2009-07-14 | 68 | 268 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Limot | 112511005 | Corn Mill | 1 | 1008055 | 696445 | 311610 | 696445 | 3rd Tranche | 341610 | 1038055 | 696445 | 341610 | 100% | 100% | 109.6% | 103% | 100% | 2003-10-15 | 2005-12-17 | 2004-03-01 | 2004-08-30 | 2004-12-05 | 182 | 419 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Limot | 112511005 | Road Upgrading | 1 | 3372675 | 347940 | 3024735 | 347940 |  | 3024735 | 3372675 | 347940 | 3024735 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-10-15 | 2006-12-21 | 60 | 419 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Limot | 112511005 | Upgrading of Footbridge | 1 | 544263 | 489438 | 54825 | 489438 |  | 54825 | 544263 | 489438 | 54825 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-04-01 | 2009-06-22 | 2009-07-15 | 82 | 380 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Lucatan | 112511006 | Potable Water System L-II | 1 | 1376926 | 658758 | 718168 | 658758 | 3rd Tranche | 718168 | 1376926 | 658758 | 718168 | 100% | 100% | 100% | 100% | 100% | 2003-10-15 | 2005-12-17 | 2004-03-01 | 2004-08-30 | 2004-08-16 | 182 | 155 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Lucatan | 112511006 | Day Care Center | 1 | 540292 | 324257 | 216035 | 324257 |  | 216035 | 540292 | 324257 | 216035 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-12-14 | 2006-12-27 | 120 | 393 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Lucatan | 112511006 | Construction of Line Canal | 1 | 521705 | 456880 | 64825 | 456880 |  | 64825 | 521705 | 456880 | 64825 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-04-01 | 2009-06-29 | 2009-07-14 | 89 | 250 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Maganda | 112511007 | Water System | 1 | 1034123.5 | 530041 | 504082.5 | 530041 | 3rd Tranche | 504082.5 | 1034123.5 | 530041 | 504082.5 | 100% | 100% | 100% | 100% | 100% | 2005-05-06 | 2005-06-28 | 2005-09-15 | 2005-12-15 | 2006-02-13 | 91 | 337 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Maganda | 112511007 | 2CL School Building | 1 | 783672 | 455607 | 328065 | 455607 |  | 328065 | 783672 | 455607 | 328065 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-12-14 | 2006-12-27 | 120 | 337 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Maganda | 112511007 | Road Upgrading | 1 | 874702 | 486707 | 387995 | 486707 |  | 387995 | 874702 | 486707 | 387995 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-04-01 | 2009-06-22 | 2009-07-08 | 82 | 430 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Ompao | 112511008 | Road Rehabilitation | 1 | 2237564 | 457828 | 1779736 | 457828 | 3rd Tranche | 1679736 | 2137564 | 457828 | 1679736 | 100% | 100% | 94.38% | 95.53% | 100% | 2003-10-15 | 2005-12-17 | 2004-03-01 | 2004-08-30 | 2004-10-13 | 182 | 219 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Ompao | 112511008 | Upgrading of Water System | 1 | 771863 | 652278 | 119585 | 652278 |  | 119585 | 771863 | 652278 | 119585 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-04-01 | 2009-06-25 | 2009-07-10 | 85 | 180 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tomoaong | 112511010 | Road Rehabilitation | 1 | 2820769 | 320636 | 2500133 | 320636 | 3rd Tranche | 2500133 | 2820769 | 320636 | 2500133 | 100% | 100% | 100% | 100% | 100% | 2003-10-15 | 2005-12-17 | 2004-03-01 | 2004-08-15 | 2004-08-16 | 167 | 300 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tomoaong | 112511010 | 2CL School Building | 1 | 773111 | 422849 | 350262 | 422849 |  | 350262 | 773111 | 422849 | 350262 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-12-14 | 2006-12-19 | 120 | 300 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tomoaong | 112511010 | Health Station | 1 | 656519 | 590694 | 65825 | 590694 |  | 65825 | 656519 | 590694 | 65825 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-15 | 2009-06-22 | 2009-07-07 | 99 | 391 |  | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tubaon | 112511011 | Health Station | 1 | 1350666 | 631272 | 719394 | 631272 | 3rd Tranche | 719394 | 1350666 | 631272 | 719394 | 100% | 100% | 100% | 100% | 100% | 2005-05-06 | 2005-06-28 | 2005-09-15 | 2005-12-15 | 2006-01-24 | 91 | 724 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tubaon | 112511011 | Day Care Center | 1 | 558024 | 344089 | 213935 | 344089 |  | 213935 | 558024 | 344089 | 213935 | 100% | 100% | 100% | 100% | 100% | 2006-04-28 | 2006-06-20 | 2006-08-16 | 2006-12-14 | 2006-12-27 | 120 | 724 | completed | 1
XI | 11 | Davao Oriental | 1125 | Tarragona | 112511 | Tubaon | 112511011 | Health Station | 1 | 658519 | 590694 | 67825 | 590694 |  | 67825 | 658519 | 590694 | 67825 | 100% | 100% | 100% | 100% | 100% | 2008-12-11 |  | 2009-03-15 | 2009-06-29 | 2009-07-13 | 106 | 268 |  | 1
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Allab | 124718001 | Health Station | 1 | 342185.19 | 301505.19 | 40680 | 301505.19 | Grant 100% Released | 63335 | 364840.19 | 301505.19 | 63335 | 100% | 100% | 155.7% | 106.6% | 100% | 2003-12-16 | 2004-03-09 | 2004-08-23 | 2005-03-15 | 2005-03-17 | 204 | 135 |  | 1
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Allab | 124718001 | Const. of Spring-Based Water System Level II | 1 | 1398827 | 1247677 | 151150 | 1247677 | First Tranche | 188365 | 1436042 | 1247677 | 188365 | 100% | 100% | 124.6% | 102.7% | 100% | no data | no data | 2009-04-04 | 2009-05-29 | 2009-06-29 | 55 | 122 |  | 1
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Anapolon | 124718002 | Solar Drier | 1 | 262750.4 | 196580.4 | 66170 | 196580.4 | Grant 100% Released | 77980 | 274560.4 | 196580.4 | 77980 | 100% | 100% | 117.8% | 104.5% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-12 | 2004-12-02 | 2004-12-16 | 143 | 103 |  | 1
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Badiangon | 124718003 | Road Improvement | 1 | 1774759 | 876804 | 897955 | 789123.6 | Third Tranche | 859713.41 | 1648837.01 | 789123.6 | 859713.41 | 100% | 100% | 95.74% | 92.9% | 100% | 2005-05-19 | 2005-06-15 | 2005-10-04 | 2006-01-17 | 2006-03-23 | 105 | 330 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Badiangon | 124718003 | Improvement of 1.3 Km FMR | 1 | 1214176.5 | 603138 | 611038.5 | 603138 | Third Tranche | 5601.31 | 608739.31 | 603138 | 5601.31 | 100% | 100% | 0.9167% | 50.14% | 100% | 2006-03-28 | 2006-04-28 | 2006-11-07 | 2007-10-31 | no data | 358 | 89 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Binoongan | 124718004 | Health Station | 1 | 559781 | 441780 | 118001 | 441780 | Grant 100% Released | 100240 | 542020 | 441780 | 100240 | 100% | 100% | 84.95% | 96.83% | 100% | 2005-05-18 | 2005-06-14 | 2005-08-31 | 2005-12-23 | 2006-03-16 | 114 | 108 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Binoongan | 124718004 | Const. of Solar Dryer w/ Warehouse | 1 | 900067.4 | 775862.4 | 124205 | 751206.16 | First Tranche | 131691.1 | 882897.26 | 751206.16 | 131691.1 | 100% | 100% | 106% | 98.09% | 100% | no data | no data | 2009-04-20 | 2009-06-30 | 2009-07-16 | 71 | 183 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Dallag | 124718005 | Spring Development | 1 | 1827032.95 | 1395952.95 | 431080 | 1395952.95 | Grant 100% Released | 456960 | 1852912.95 | 1395952.95 | 456960 | 100% | 100% | 106% | 101.4% | 100% | 2003-12-16 | 2004-03-09 | 2004-07-01 | 2005-03-31 | 2005-03-31 | 273 | 165 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Datu Ladayon | 124718006 | 2 - Units Single Barrel Box Culvert | 1 | 945113 | 726313 | 218800 | 726313 | Third Tranche | 138050 | 864363 | 726313 | 138050 | 100% | 100% | 63.09% | 91.46% | 100% | 2006-03-28 | 2006-04-28 | 2006-11-07 | 2007-09-30 | no data | 327 | 179 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Datu Ladayon | 124718006 | Construction of Day Care Center | 1 | 723524.6 | 643509.6 | 80015 | 641470.33 | First Tranche | 98719 | 740189.33 | 641470.33 | 98719 | 100% | 100% | 123.4% | 102.3% | 100% | no data | no data | 2009-04-03 | 2009-06-30 | no data | 88 | 158 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Datu Matangkil | 124718007 | Solar Drier | 1 | 264750.4 | 215910.4 | 48840 | 215910.4 | Grant 100% Released | 54460 | 270370.4 | 215910.4 | 54460 | 100% | 100% | 111.5% | 102.1% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-09 | 2004-12-02 | 2004-12-08 | 146 | 92 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Datu Matangkil | 124718007 | Health Station with Amenities | 1 | 568674 | 434212 | 134462 | 434212 | Grant 100% Released | 51290 | 485502 | 434212 | 51290 | 100% | 100% | 38.14% | 85.37% | 100% | 2006-03-28 | 2006-04-28 | 2006-12-11 | 2007-06-30 | no data | 201 | 105 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Doruloman | 124718008 | Solar Dryer with Warehouse | 1 | 953694 | 666799 | 286895 | 666799 | Grant 100% Released | 333801.6 | 1000600.6 | 666799 | 333801.6 | 100% | 100% | 116.3% | 104.9% | 100% | 2005-05-18 | 2005-06-14 | 2005-09-05 | 2005-11-01 | 2005-10-26 | 57 | 610 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Doruloman | 124718008 | 2 - Barrel R.C. Box Culvert | 1 | 1185410 | 865100 | 320310 | 865100 | Grant 100% Released | 31000 | 896100 | 865100 | 31000 | 100% | 100% | 9.678% | 75.59% | 100% | 2006-03-28 | 2006-04-28 | 2006-11-27 | 2007-02-23 | 2007-02-28 | 88 | 67 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Gambodes | 124718009 | Farm to Market Road | 1 | 2140082.25 | 281509.4 | 1858572.85 | 281509.4 | Grant 100% Released | 2887074.43 | 3168583.83 | 281509.4 | 2887074.43 | 100% | 100% | 155.3% | 148.1% | 100% | 2003-12-16 | 2004-03-10 | 2004-08-18 | 2005-03-14 | 2005-03-22 | 208 | 86 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Gambodes | 124718009 | Solar Dryer with Warehouse | 1 | 855350 | 765715 | 89635 | 765715 | Grant 100% Released | 106555 | 872270 | 765715 | 106555 | 100% | 100% | 118.9% | 102% | 100% | 2005-05-18 | 2005-06-14 | 2005-09-23 | 2005-11-12 | 2005-12-14 | 50 | 96 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Gambudes - C2 | 124718009 | Const. of Spring-Based Water System Level II | 2 | 1739101.41 | 1594101.41 | 145000 | 1399827 | First Tranche | 164674.08 | 1564501.08 | 1399827 | 164674.08 | 100% | 100% | 113.6% | 89.96% | 100% | no data | no data | 2009-05-12 | 2009-09-25 | n/a | 136 | 287 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Ganatan | 124718010 | School | 1 | 1018899.66 | 892999.66 | 125900 | 892999.66 | Grant 100% Released | 145780 | 1038779.66 | 892999.66 | 145780 | 100% | 100% | 115.8% | 102% | 100% | 2003-12-16 | 2004-03-09 | 2004-09-17 | 2005-03-10 | 2005-05-10 | 174 | 333 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Kabalantian | 124718012 | Construction of Overflow Bridge | 1 | 903196 | 769510 | 133686 | 769510 | First Tranche | 141596 | 911106 | 769510 | 141596 | 100% | 100% | 105.9% | 100.9% | 100% | no data | no data | 2009-03-16 | 2009-05-29 | 2009-06-17 | 74 | 595 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Katipunan | 124718013 | Health Station | 1 | 415113.6 | 272483.6 | 142630 | 272483.6 | Grant 100% Released | 155265 | 427748.6 | 272483.6 | 155265 | 100% | 100% | 108.9% | 103% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-11 | 2005-02-28 | 2005-02-28 | 232 | 85 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Katipunan | 124718013 | Public Library with Amenities | 1 | 813822 | 573178 | 240644 | 573178 | Third Tranche | 43600 | 616778 | 573178 | 43600 | 100% | 100% | 18.12% | 75.79% | 100% | 2006-03-28 | 2006-04-28 | 2007-01-29 | 2007-06-30 | 2007-07-05 | 152 | 97 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Katipunan - C2 | 124718013 | Const. of Spring-Based Water System Level II | 2 | 1739101.41 | 1594101.41 | 145000 | 1399827 | First Tranche | 164674.08 | 1564501.08 | 1399827 | 164674.08 | 100% | 100% | 113.6% | 89.96% | 100% | no data | no data | 2009-05-12 | 2009-09-25 | n/a | 136 | 287 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Kinawayan | 124718014 | Solar Drier | 1 | 498754 | 321354 | 177400 | 321354 | Grant 100% Released | 192471.88 | 513825.88 | 321354 | 192471.88 | 100% | 100% | 108.5% | 103% | 100% | 2003-12-15 | 2004-03-10 | 2004-09-13 | 2005-02-23 | 2005-02-24 | 163 | 180 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Kinawayan | 124718014 | Warehouse with Mobile Corn Sheller | 1 | 577887 | 443060 | 134827 | 443060 | Third Tranche | 84000 | 527060 | 443060 | 84000 | 100% | 100% | 62.3% | 91.2% | 100% | 2006-03-28 | 2006-04-28 | 2006-12-07 | 2007-10-31 | no data | 328 | 194 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Kinawayan | 124718014 | Const. of Health Center | 1 | 667389.58 | 583559.58 | 83830 | 583559.58 | First Tranche | 90940 | 674499.58 | 583559.58 | 90940 | 100% | 100% | 108.5% | 101.1% | 100% | no data | no data | 2009-04-13 | 2009-06-26 | 2009-07-15 | 74 | 110 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Kulaman Valley | 124718015 | Health Station | 1 | 344727 | 248913 | 95814 | 248913 | Grant 100% Released | 103355 | 352268 | 248913 | 103355 | 100% | 100% | 107.9% | 102.2% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-19 | 2005-02-28 | 2005-03-01 | 224 | 164 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Kulaman Valley | 124718015 | Rice and Corn Mill | 1 | 954944 | 734477 | 220467 | 734477 | Grant 100% Released | 152000 | 886477 | 734477 | 152000 | 100% | 100% | 68.94% | 92.83% | 100% | 2006-03-28 | 2006-04-28 | 2006-12-07 | 2007-08-31 | no data | 267 | 180 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Lanao Kuran | 124718016 | Construction of Overflow Bridge | 1 | 713618 | 618468 | 95150 | 618468 | First Tranche | 105335 | 723803 | 618468 | 105335 | 100% | 100% | 110.7% | 101.4% | 100% | no data | no data | 2009-04-02 | 2009-05-29 | 2009-06-25 | 57 | 304 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Libertad | 124718017 | Health Station | 1 | 348547 | 299407 | 49140 | 299407 | Grant 100% Released | 50590 | 349997 | 299407 | 50590 | 100% | 100% | 103% | 100.4% | 100% | 2003-12-16 | 2004-03-09 | 2004-08-23 | 2005-02-26 | 2005-02-28 | 187 | 135 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Libertad | 124718017 | Const. of 1 Rm Elem. School Bldg. | 1 | 707701.67 | 635261.67 | 72440 | 635261.67 | First Tranche | 67850.5 | 703112.17 | 635261.67 | 67850.5 | 100% | 100% | 93.66% | 99.35% | 100% | no data | no data | 2009-03-28 | 2009-06-26 | 2009-06-29 | 90 | 165 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Ma. Caridad | 124718020 | Concreting of 200 Meters Road | 1 | 1146203.52 | 843988.52 | 302215 | 843988.52 | First Tranche | 78880 | 922868.52 | 843988.52 | 78880 | 100% | 100% | 26.1% | 80.52% | 100% | no data | no data | 2009-04-13 | 2009-06-26 | 2009-07-09 | 74 | 110 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Makalangot | 124718018 | Solar Dryer with Warehouse | 1 | 840201 | 747846 | 92355 | 747843 | Third Tranche | 115920 | 863763 | 747843 | 115920 | 100% | 100% | 125.5% | 102.8% | 100% | 2005-05-19 | 2005-06-15 | 2005-09-08 | 2005-11-04 | 2006-01-31 | 57 | 240 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Makalangot | 124718018 | Const. of 2 RM High School Bldg. | 1 | 1135971.4 | 1040791.4 | 95180 | 1040791.4 | First Tranche | 94165 | 1134956.4 | 1040791.4 | 94165 | 100% | 100% | 98.93% | 99.91% | 100% | no data | no data | 2009-03-27 | 2009-06-30 | no data | 95 | 135 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Malibatuan | 124718019 | Solar Drier with Warehouse | 1 | 613983 | 424583 | 189400 | 424583 | Grant 100% Released | 190707.5 | 615290.5 | 424583 | 190707.5 | 100% | 100% | 100.7% | 100.2% | 100% | 2003-12-16 | 2004-03-09 | 2004-08-20 | 2005-02-17 | 2005-02-22 | 181 | 420 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Malibatuan | 124718019 | Day Care Center with Amenities | 1 | 792800 | 606360 | 186440 | 545724 | Grant 100% Released | 91000 | 636724 | 545724 | 91000 | 100% | 100% | 48.81% | 80.31% | 100% | 2006-03-28 | 2006-04-28 | 2006-12-01 | 2007-06-30 | 2007-07-05 | 211 | 103 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Malibatuan | 124718019 | W.S. Level II (Spring Source) | 1 | 1350000 | 300000 | 1050000 | 240000 |  | 1051000 | 1291000 | 240000 | 1051000 | 100% | 100% | 100.1% | 95.63% | 100% | no data | no data | 2009-08-31 | 2009-10-31 | n/a | 61 | 350 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Maria Caridad | 124718020 | Solar Dryer with Warehouse | 1 | 857665 | 671476 | 186189 | 671476 | Grant 100% Released | 522389 | 1193865 | 671476 | 522389 | 100% | 100% | 280.6% | 139.2% | 100% | 2005-05-19 | 2005-06-15 | 2005-10-01 | 2005-11-24 | 2006-01-31 | 54 | 120 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Maria Caridad | 124718020 | Overflow Bridge | 1 | 670090 | 514500 | 155590 | 514500 | Third Tranche | 18740 | 533240 | 514500 | 18740 | 100% | 100% | 12.04% | 79.58% | 100% | 2006-03-28 | 2006-04-28 | 2006-10-23 | 2007-01-29 | 2007-03-29 | 98 | 141 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Meocan | 124718021 | Spring Development | 1 | 1786021 | 1569821 | 216200 | 1569821 | Grant 100% Released | 253550 | 1823371 | 1569821 | 253550 | 100% | 100% | 117.3% | 102.1% | 100% | 2005-05-19 | 2005-06-15 | 2005-10-01 | 2007-05-31 | no data | 607 | 300 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Naje | 124718022 | Solar Dryer with Warehouse | 1 | 848343 | 759487 | 88856 | 759487 | Grant 100% Released | 109845 | 869332 | 759487 | 109845 | 100% | 100% | 123.6% | 102.5% | 100% | 2005-05-18 | 2005-06-14 | 2005-10-01 | 2005-11-24 | 2006-01-31 | 54 | 188 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Napalico | 124718023 | Spring Development | 1 | 1754742.2 | 1400402.2 | 354340 | 1400402.2 | Grant 100% Released | 355162.5 | 1755564.7 | 1400402.2 | 355162.5 | 100% | 100% | 100.2% | 100% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-15 | 2005-02-26 | 2005-03-10 | 226 | 101 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Napalico | 124718023 | Solar Dryer with Warehouse | 1 | 709162 | 629662 | 79500 | 629662 | Grant 100% Released | 115999.5 | 745661.5 | 629662 | 115999.5 | 100% | 100% | 145.9% | 105.1% | 100% | 2005-05-18 | 2005-06-14 | 2005-10-19 | 2005-12-08 | 2006-03-23 | 50 | 92 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Napalico | 124718023 | Construction of Health Center | 1 | 667409.58 | 583559.58 | 83850 | 583559.58 | First Tranche | 96568.75 | 680128.33 | 583559.58 | 96568.75 | 100% | 100% | 115.2% | 101.9% | 100% | no data | no data | 2009-05-04 | 2009-06-30 | 2009-07-16 | 57 | 300 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Poblacion (Dallag) | 124718005 | Construction of Spring-Based Water System at Guitawan Level II | 1 | 1673568 | 1474592.73 | 198975.27 | 1179674.18 | First Tranche | 204905.27 | 1384579.45 | 1179674.18 | 204905.27 | 100% | 100% | 103% | 82.73% | 100% | no data | no data | 2009-04-29 | 2009-07-31 | no data | 93 | 351 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Salasang | 124718024 | Health Station | 1 | 1046921.4 | 738746.4 | 308175 | 738746.4 | Grant 100% Released | 325636.35 | 1064382.75 | 738746.4 | 325636.35 | 100% | 100% | 105.7% | 101.7% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-14 | 2005-02-21 | 2005-02-21 | 222 | 281 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Salasang | 124718024 | Solar Dryer with Mobile Corn Sheller | 1 | 543149 | 417759 | 125390 | 417759 | Third Tranche | 500 | 418259 | 417759 | 500 | 100% | 100% | 0.3988% | 77.01% | 100% | 2006-03-28 | 2006-04-28 | 2006-11-13 | 2007-03-22 | 2007-03-29 | 129 | 220 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Salasang | 124718024 | Const. of Multi-Purpose Bldg. | 1 | 1355339.06 | 1249119.06 | 106220 | 1249119.06 | First Tranche | 95372.17 | 1344491.23 | 1249119.06 | 95372.17 | 100% | 100% | 89.79% | 99.2% | 100% | no data | no data | 2009-03-18 | 2009-05-29 | 2009-06-17 | 72 | 217 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | San Miguel | 124718025 | Over Flow Bridge | 1 | 562022 | 440010 | 122012 | 440010 | Grant 100% Released | 522389 | 962399 | 440010 | 522389 | 100% | 100% | 428.1% | 171.2% | 100% | 2005-05-18 | 2005-06-14 | 2005-09-08 | 2005-11-11 | 2005-12-14 | 64 | 210 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | San Miguel | 124718025 | Hanging Footbridge | 1 | 859672 | 660762 | 198910 | 660762 | Grant 100% Released | 118130 | 778892 | 660762 | 118130 | 100% | 100% | 59.39% | 90.6% | 100% | 2006-03-28 | 2006-04-28 | 2006-10-30 | 2006-12-23 | 2007-02-28 | 54 | 101 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | San Miguel | 124718025 | Construction of Double Barrel Box Culvert | 1 | 1008807.65 | 875207.65 | 133600 | 875207.65 | First Tranche | 185434.15 | 1060641.8 | 875207.65 | 185434.15 | 100% | 100% | 138.8% | 105.1% | 100% | no data | no data | 2009-04-22 | 2009-06-26 | no data | 65 | 218 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Sto. Niño | 124718026 | Spring Development | 1 | 1011883 | 438681 | 573202 | 438681 | Grant 100% Released | 482752 | 921433 | 438681 | 482752 | 100% | 100% | 84.22% | 91.06% | 100% | 2003-12-16 | 2004-03-09 | 2004-07-10 | 2005-02-24 | 2005-02-24 | 229 | 287 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Sto. Niño | 124718026 | Solar Dryer | 1 | 409145 | 296220 | 112925 | 296220 | Grant 100% Released | 112152.1 | 408372.1 | 296220 | 112152.1 | 100% | 100% | 99.32% | 99.81% | 100% | 2005-05-19 | 2005-06-15 | 2005-08-20 | 2005-10-08 | 2005-10-26 | 49 | 287 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Sto. Niño | 124718026 | Solar Dryer with Warehouse and Mobile Corn sheller | 1 | 949229 | 716019 | 233210 | 716019 | Third Tranche | 130390 | 846409 | 716019 | 130390 | 100% | 100% | 55.91% | 89.17% | 100% | 2006-03-28 | 2006-04-28 | 2007-01-29 | 2007-10-31 | no data | 275 | 125 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Sumalili | 124718027 | Rice and Corn Mill | 1 | 575769 | 524101 | 51668 | 524101 | Grant 100% Released | 61850 | 585951 | 524101 | 61850 | 100% | 100% | 119.7% | 101.8% | 100% | 2003-12-15 | 2004-03-10 | 2004-07-12 | 2005-02-15 | 2005-02-16 | 218 | 120 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Sumalili | 124718027 | Spring Development | 1 | 551129 | 467495 | 83634 | 467495 | Grant 100% Released | 89850 | 557345 | 467495 | 89850 | 100% | 100% | 107.4% | 101.1% | 100% | 2005-05-18 | 2005-06-14 | 2005-11-11 | 2005-12-01 | 2005-12-21 | 20 | 120 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Sumalili | 124718027 | Solar Dryer with Warehouse | 1 | 850069 | 653819 | 196250 | 653819 | Third Tranche | 133720 | 787539 | 653819 | 133720 | 100% | 100% | 68.14% | 92.64% | 100% | 2006-03-28 | 2006-04-28 | 2006-12-13 | 2007-10-31 | no data | 322 | 130 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Tumanding | 124718028 | School | 1 | 580434.35 | 446871.2 | 133563.15 | 446871.2 | Grant 100% Released | 139013.15 | 585884.35 | 446871.2 | 139013.15 | 100% | 100% | 104.1% | 100.9% | 100% | 2003-12-16 | 2004-03-09 | 2004-08-13 | 2005-02-21 | 2005-02-21 | 192 | 206 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Arakan | 124718 | Tumanding | 124718028 | Const. of 1 Unit 2 CL School Bldg. with Furniture | 1 | 1159971.4 | 1064791.4 | 95180 | 1064791.4 | First Tranche | 107805 | 1172596.4 | 1064791.4 | 107805 | 100% | 100% | 113.3% | 101.1% | 100% | no data | no data | 2009-03-19 | 2009-05-29 | 2009-06-16 | 71 | 158 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Abaga | 124705001 | Health Station | 1 | 618348.36 | 395521.09 | 222827.27 | 395521.09 | Grant 100% Released | 282685.51 | 678206.6 | 395521.09 | 282685.51 | 100% | 100% | 126.9% | 109.7% | 100% | 2006-07-14 | 2006-08-29 | 2006-12-08 | 2007-04-27 | 2007-04-27 | 140 | 339 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Abaga | 124705001 | Solar Dryer with Warehouse | 1 | 845635 | 641466 | 204169 | 641466 | First Tranche | 247404.52 | 888870.52 | 641466 | 247404.52 | 100% | 100% | 121.2% | 105.1% | 100% | 2008-04-22 | no data | 2008-07-21 | 2008-10-10 | 2008-10-15 | 81 | 365 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Baguer | 124705003 | Road Improvement | 1 | 2613465.55 | 2154137.95 | 459327.6 | 2154137.95 | First Tranche | 431727.6 | 2585865.55 | 2154137.95 | 431727.6 | 100% | 100% | 93.99% | 98.94% | 100% | 2007-05-28 | 2007-07-10 | 2008-04-23 | 2008-07-31 | n/a | 99 | 430 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Barongis | 124705004 | Solar Dryer with Warehouse | 1 | 845635 | 656466 | 189169 | 656466 | First Tranche | 125163.88 | 781629.88 | 656466 | 125163.88 | 100% | 100% | 66.17% | 92.43% | 100% | 2008-04-22 | no data | 2008-08-22 | 2008-10-30 | n/a | 69 | 555 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Cabaruyan | 124705006 | Construction of Box Culvert | 1 | 1223530.11 | 915804 | 307726.11 | 879289.51 | Third Tranche | 209238.29 | 1088527.8 | 879289.51 | 209238.29 | 100% | 100% | 67.99% | 88.97% | 100% | 2007-05-28 | 2007-07-10 | 2007-12-04 | 2008-04-30 | no data | 148 | 257 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Cabpangi | 124705007 | Construction of Day Care Center | 1 | 550135.32 | 418862.76 | 131272.56 | 398029.43 | First Tranche | 126863.49 | 524892.92 | 398029.43 | 126863.49 | 100% | 100% | 96.64% | 95.41% | 100% | 2007-05-28 | 2007-07-10 | 2008-01-11 | 2008-03-29 | 2008-04-02 | 78 | 420 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Demapaco | 124705010 | W. S. Level II (Spring Source) | 1 | 1643115.48 | 1351274.48 | 291841 | 1351274.48 | Third Tranche | 385907.05 | 1737181.53 | 1351274.48 | 385907.05 | 100% | 100% | 132.2% | 105.7% | 100% | 2006-07-14 | 2006-08-29 | 2006-11-23 | 2007-06-30 | 2007-06-25 | 219 | 229 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Demapaco | 124705010 | 2 Barrel Box Culvert | 1 | 842241.8 | 663419 | 178822.8 | 658933.33 | First Tranche | 215866.47 | 874799.8 | 658933.33 | 215866.47 | 100% | 100% | 120.7% | 103.9% | 100% | 2008-04-22 | no data | 2008-07-02 | 2008-11-30 | 2008-12-23 | 151 | 136 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Grebona | 124705011 | Water System Level II (Pump Driven) | 1 | 809935 | 383722.49 | 426212.51 | 383722.49 | First Tranche | 426212.51 | 809935 | 383722.49 | 426212.51 | 100% | 100% | 100% | 100% | 100% | 2007-05-28 | 2007-07-10 | 2008-01-29 | 2008-08-19 | 2008-08-21 | 203 | 238 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Gumaga | 124705013 | Construction of Health Station | 1 | 592638.16 | 465172.08 | 127466.08 | 448505.41 | First Tranche | 119603.42 | 568108.83 | 448505.41 | 119603.42 | 100% | 100% | 93.83% | 95.86% | 100% | 2007-05-28 | 2007-07-10 | 2007-12-26 | 2008-04-30 | no data | 126 | 663 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kapayawi | 124705014 | Construction of Health Station | 1 | 592638.16 | 465172.08 | 127466.08 | 465172.08 | First Tranche | 161402.26 | 626574.34 | 465172.08 | 161402.26 | 100% | 100% | 126.6% | 105.7% | 100% | 2007-05-28 | 2007-07-10 | 2007-12-10 | 2008-04-30 | no data | 142 | 294 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kiloyao | 124705015 | Day Care Center | 1 | 396858 | 287344 | 109514 | 287344 | Grant 100% Released | 112834.76 | 400178.76 | 287344 | 112834.76 | 100% | 100% | 103% | 100.8% | 100% | 2006-07-15 | 2006-08-29 | 2006-12-22 | 2007-04-30 | 2007-05-17 | 129 | 61 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kiloyao | 124705015 | Health Station | 1 | 598791.89 | 465834.91 | 132956.98 | 465834.91 | First Tranche | 132956.91 | 598791.82 | 465834.91 | 132956.91 | 100% | 100% | 100% | 100% | 100% | 2008-04-22 | no data | 2008-07-25 | 2008-10-30 | 2008-11-05 | 97 | 162 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Kitubod | 124705017 | Solar Dryer with Warehouse | 1 | 808475.67 | 639157.5 | 169318.17 | 639157.5 | First Tranche | 138206.5 | 777364 | 639157.5 | 138206.5 | 100% | 100% | 81.63% | 96.15% | 100% | 2007-05-28 | 2007-07-10 | 2008-02-12 | 2008-12-31 | n/a | 323 | 279 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Malengen | 124705019 | Water System Level II | 1 | 1925283.29 | 1506340.4 | 418942.89 | 1506340.4 | First Tranche | 343551.08 | 1849891.48 | 1506340.4 | 343551.08 | 100% | 100% | 82% | 96.08% | 100% | 2008-04-22 | no data | 2008-08-12 | 2008-11-30 | 2008-12-10 | 110 | 262 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Montay | 124705023 | Construction of Day Care Center | 1 | 556236.32 | 446862.76 | 109373.56 | 426029.43 | Second Tranche | 103813.56 | 529842.99 | 426029.43 | 103813.56 | 100% | 100% | 94.92% | 95.26% | 100% | 2007-05-28 | 2007-07-10 | 2007-12-03 | 2008-06-30 | no data | 210 | 260 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Nica-an | 124705024 | W. S. Level II (Spring Source) | 1 | 1271909.76 | 1135954.88 | 135954.88 | 1135954.88 | Grant 100% Released | 285838.23 | 1421793.11 | 1135954.88 | 285838.23 | 100% | 100% | 210.2% | 111.8% | 100% | 2006-07-14 | 2006-08-29 | 2007-02-21 | 2007-08-31 | no data | 191 | 252 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Nica-an | 124705024 | Day Care Center | 1 | 557520.8 | 430000 | 127520.8 | 430000 | First Tranche | 162254.2 | 592254.2 | 430000 | 162254.2 | 100% | 100% | 127.2% | 106.2% | 100% | 2008-04-22 | no data | 2008-07-22 | 2008-10-30 | n/a | 100 | 342 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Palao | 124705025 | Road Opening | 1 | 1974922.8 | 1605064 | 369858.8 | 1572998.27 | Third Tranche | 329512.8 | 1902511.07 | 1572998.27 | 329512.8 | 100% | 100% | 89.09% | 96.33% | 100% | 2006-07-14 | 2006-08-29 | 2007-03-23 | 2008-02-18 | no data | 332 | 152 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Sinapangan | 124705032 | 3 Classroom School Building | 1 | 1234945.8 | 979489 | 255456.8 | 975322.33 | First Tranche | 216937.8 | 1192260.13 | 975322.33 | 216937.8 | 100% | 100% | 84.92% | 96.54% | 100% | 2008-04-22 | no data | 2008-07-22 | 2008-11-30 | 2008-12-03 | 131 | 316 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Sinawingan | 124705033 | Rural Electrification | 1 | 1108545.95 | 679379.98 | 429165.97 | 642359.98 | Third Tranche | 436298.47 | 1078658.45 | 642359.98 | 436298.47 | 100% | 100% | 101.7% | 97.3% | 100% | 2006-07-14 | 2006-08-29 | 2007-02-28 | 2007-05-30 | 2007-05-31 | 91 | 83 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Sinawingan | 124705033 | Solar Dryer with Warehouse | 1 | 785939.34 | 656466 | 129473.34 | 656466 | First Tranche | 194285.2 | 850751.2 | 656466 | 194285.2 | 100% | 100% | 150.1% | 108.2% | 100% | 2008-04-22 | no data | 2008-07-01 | 2008-08-19 | 2008-08-22 | 49 | 315 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Libungan | 124705 | Ulamian | 124705034 | Road Opening | 1 | 531272.13 | 440561.13 | 90711 | 440561.13 | Grant 100% Released | 90611.01 | 531172.14 | 440561.13 | 90611.01 | 100% | 100% | 99.89% | 99.98% | 100% | 2006-07-14 | 2006-08-29 | 2007-03-01 | 2007-04-27 | 2007-05-13 | 57 | 250 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Alibayon | 124706001 | 2 Classroom School Building | 1 | 1279500 | 896186.5 | 383313.5 | 895065.36 | First Tranche | 260742.5 | 1155807.86 | 895065.36 | 260742.5 | 100% | 100% | 68.02% | 90.33% | 100% | 2008-04-24 | no data | 2008-07-30 | 2008-12-29 | n/a | 152 | 203 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Bagumbayan | 124706005 | W. S. Level II (Spring Source) | 1 | 903995.68 | 635975.68 | 268020 | 635975.68 | Second Tranche | 260645.39 | 896621.07 | 635975.68 | 260645.39 | 100% | 100% | 97.25% | 99.18% | 100% | 2006-07-12 | 2006-10-18 | 2007-04-02 | 2008-03-28 | no data | 361 | 137 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Balete | 124706049 | W. S. Level II (Spring Source) | 1 | 712288.72 | 452567.05 | 259721.67 | 452567.05 | Grant 100% Released | 250230.06 | 702797.11 | 452567.05 | 250230.06 | 100% | 100% | 96.35% | 98.67% | 100% | 2006-07-12 | 2006-10-18 | 2007-02-17 | 2007-12-21 | no data | 307 | 200 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Bangcal | 124706006 | Road Rehabilitation | 1 | 928831.08 | 479430.99 | 449400.09 | 479383.54 | Second Tranche | 283224.09 | 762607.63 | 479383.54 | 283224.09 | 100% | 100% | 63.02% | 82.1% | 100% | 2006-07-12 | 2006-10-18 | 2006-12-19 | 2008-06-30 | no data | 559 | 165 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Bantac | 124706007 | Road Rehab. w/ Spot Concreting | 1 | 1132232.84 | 621314.81 | 510918.03 | 621314.81 | Grant 100% Released | 466229.03 | 1087543.84 | 621314.81 | 466229.03 | 100% | 100% | 91.25% | 96.05% | 100% | 2006-07-12 | 2006-10-18 | 2007-04-02 | 2008-03-28 | no data | 361 | 232 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Basak | 124706008 | W. S. Level II (Spring Source) | 1 | 1009254.3 | 700503.43 | 308750.87 | 700503.43 | Grant 100% Released | 321955.51 | 1022458.94 | 700503.43 | 321955.51 | 100% | 100% | 104.3% | 101.3% | 100% | 2006-07-12 | 2006-10-18 | 2006-12-06 | 2007-07-30 | no data | 236 | 396 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Binay | 124706009 | W. S. Level II (Spring Source) | 1 | 932256.75 | 727440.07 | 204816.68 | 727440.07 | Grant 100% Released | 215026.68 | 942466.75 | 727440.07 | 215026.68 | 100% | 100% | 105% | 101.1% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-06 | 2008-03-28 | 2008-04-21 | 143 | 125 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Datu Celo | 124706014 | Water System Level II | 1 | 1245108.87 | 816416.58 | 428692.29 | 816416.58 | Second Tranche | 431938.12 | 1248354.7 | 816416.58 | 431938.12 | 100% | 100% | 100.8% | 100.3% | 100% | 2006-07-12 | 2006-10-18 | 2006-12-15 | 2008-02-29 | 2008-03-11 | 441 | 192 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Del Pilar | 124706015 | Construction of Day Care Center | 1 | 463775.2 | 327827.52 | 135947.68 | 327827.52 | Grant 100% Released | 183452.3 | 511279.82 | 327827.52 | 183452.3 | 100% | 100% | 134.9% | 110.2% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-15 | 2008-04-30 | no data | 167 | 250 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Doles | 124706016 | 2 Classroom School Building | 1 | 1305947 | 891506.5 | 414440.5 | 891506.5 | First Tranche | 326910.5 | 1218417 | 891506.5 | 326910.5 | 100% | 100% | 78.88% | 93.3% | 100% | 2008-04-24 | no data | 2008-07-28 | 2008-11-30 | n/a | 125 | 210 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Don Panaca | 124706050 | Const'n. of Health Station | 1 | 579498.07 | 454746.07 | 124752 | 454746.07 | Grant 100% Released | 134587.1 | 589333.17 | 454746.07 | 134587.1 | 100% | 100% | 107.9% | 101.7% | 100% | 2006-07-12 | 2006-10-18 | 2007-03-16 | 2007-07-30 | no data | 136 | 130 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Gubatan | 124706021 | Construction of Day Care Center | 1 | 482163.41 | 327889.49 | 154273.92 | 297518.25 | Third Tranche | 152340.18 | 449858.43 | 297518.25 | 152340.18 | 100% | 100% | 98.75% | 93.3% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-08 | 2008-01-14 | 2008-01-19 | 67 | 250 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Ilian | 124706022 | W. S. Level II (Spring Source) | 1 | 1140792.8 | 784370 | 356422.8 | 705933 | Third Tranche | 422557.2 | 1128490.2 | 705933 | 422557.2 | 100% | 100% | 118.6% | 98.92% | 100% | 2006-07-12 | 2006-10-18 | 2006-12-18 | 2007-05-25 | 2007-05-30 | 158 | 119 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Ilian | 124706022 | Bailey Bridge (Double Panel) | 1 | 2221590 | 1813615.5 | 407974.5 | 1813615.5 | First Tranche | 407974.5 | 2221590 | 1813615.5 | 407974.5 | 100% | 100% | 100% | 100% | 100% | 2008-04-24 | no data | 2008-10-27 | 2008-12-29 | n/a | 63 | 138 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Imamaling | 124706051 | W. S. Level II (Spring Source) | 1 | 762923 | 579763.52 | 183159.48 | 521787.17 | Third Tranche | 180169.48 | 701956.65 | 521787.17 | 180169.48 | 100% | 100% | 98.37% | 92.01% | 100% | 2006-07-12 | 2006-10-18 | 2007-03-12 | 2007-08-31 | no data | 172 | 150 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Inac | 124706023 | W. S. Level II (Spring Source) | 1 | 1316210.92 | 733613.92 | 582597 | 733613.84 | Grant 100% Released | 487167.9 | 1220781.74 | 733613.84 | 487167.9 | 100% | 100% | 83.62% | 92.75% | 100% | 2006-07-12 | 2006-10-18 | 2006-12-11 | 2007-04-25 | 2007-05-09 | 135 | 244 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kamada | 124706024 | Day Care Center | 1 | 643573 | 440811 | 202762 | 438643.54 | First Tranche | 189892 | 628535.54 | 438643.54 | 189892 | 100% | 100% | 93.65% | 97.66% | 100% | 2008-04-24 | no data | 2008-06-23 | 2008-08-06 | 2008-08-11 | 44 | 254 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kauswagan | 124706026 | Construction of Health Station | 1 | 593921.36 | 443210 | 150711.36 | 443210 | Grant 100% Released | 193008.2 | 636218.2 | 443210 | 193008.2 | 100% | 100% | 128.1% | 107.1% | 100% | 2007-05-07 | 2007-07-12 | 2008-01-18 | 2008-04-30 | no data | 103 | 119 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kinarum | 124706052 | Road Improvement with Spot Concreting | 1 | 1774000.82 | 1385811.6 | 388189.22 | 1385811.6 | First Tranche | 374189.22 | 1760000.82 | 1385811.6 | 374189.22 | 100% | 100% | 96.39% | 99.21% | 100% | 2007-05-07 | 2007-07-12 | 2008-04-22 | 2009-05-29 | n/a | 402 | 160 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kisandal | 124706027 | W. S. Level II (Spring Source) | 1 | 1416397.94 | 1075199.13 | 341198.81 | 1041480.15 | Third Tranche | 341198.81 | 1382678.96 | 1041480.15 | 341198.81 | 100% | 100% | 100% | 97.62% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-20 | 2008-03-24 | 2008-03-27 | 125 | 247 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Kisandal | 124706027 | 2 Classroom School Building | 1 | 1222210 | 784839 | 437371 | 784839 | First Tranche | 467371 | 1252210 | 784839 | 467371 | 100% | 100% | 106.9% | 102.5% | 100% | 2008-04-24 | no data | 2008-07-22 | 2008-12-29 | n/a | 160 | 249 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Magcaalam | 124706029 | Road Improvement | 1 | 2386013.38 | 2107292.6 | 278720.78 | 2107292.6 | First Tranche | 278720.78 | 2386013.38 | 2107292.6 | 278720.78 | 100% | 100% | 100% | 100% | 100% | 2007-05-07 | 2007-07-12 | 2008-04-21 | 2009-05-29 | n/a | 403 | 220 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Mahongcog | 124706030 | W. S. Level II (Spring Source) | 1 | 1323593.82 | 831268.54 | 492325.28 | 831268.54 | Grant 100% Released | 382545.28 | 1213813.82 | 831268.54 | 382545.28 | 100% | 100% | 77.7% | 91.71% | 100% | 2006-07-12 | 2006-10-18 | 2007-03-07 | 2007-07-30 | no data | 145 | 300 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Mahongcog | 124706030 | 2 Classroom School Building | 1 | 1287389 | 907161.59 | 380227.41 | 907161.59 | First Tranche | 245365.66 | 1152527.25 | 907161.59 | 245365.66 | 100% | 100% | 64.53% | 89.52% | 100% | 2008-04-24 | no data | 2008-07-25 | 2009-04-30 | n/a | 279 | 378 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Manobisa | 124706053 | 2 units - RC Box Culvert | 1 | 651734.45 | 495117.29 | 156617.16 | 495117.29 | Grant 100% Released | 162444.66 | 657561.95 | 495117.29 | 162444.66 | 100% | 100% | 103.7% | 100.9% | 100% | 2006-07-12 | 2006-10-18 | 2007-03-12 | 2007-06-30 | 2007-07-02 | 110 | 65 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Noa | 124706037 | 2 - Cl.. School Bldg. (Elem.) | 1 | 833328.8 | 629654.88 | 203673.92 | 629654.88 | Grant 100% Released | 162918.23 | 792573.11 | 629654.88 | 162918.23 | 100% | 100% | 79.99% | 95.11% | 100% | 2006-07-12 | 2006-10-18 | 2007-02-15 | 2007-05-31 | 2007-06-26 | 105 | 240 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Noa | 124706037 | Water System Level II | 1 | 1873323 | 1490032.15 | 383290.85 | 1490032.15 | First Tranche | 333280.85 | 1823313 | 1490032.15 | 333280.85 | 100% | 100% | 86.95% | 97.33% | 100% | 2008-04-24 | no data | 2008-07-08 | 2008-11-30 | n/a | 145 | 210 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Owas | 124706038 | Road Improvement | 1 | 701077 | 534000 | 167077 | 480600 | Third Tranche | 154507 | 635107 | 480600 | 154507 | 100% | 100% | 92.48% | 90.59% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-29 | 2008-03-24 | 2008-03-28 | 116 | 150 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Pangao-an | 124706039 | W. S. Level II (Spring Source) | 1 | 911198.89 | 654903.38 | 256295.51 | 654903.38 | Grant 100% Released | 267850.51 | 922753.89 | 654903.38 | 267850.51 | 100% | 100% | 104.5% | 101.3% | 100% | 2006-07-12 | 2006-10-18 | 2007-02-25 | 2007-05-24 | 2007-05-25 | 88 | 487 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Pangao-an | 124706039 | 2 - Cl.. School Bldg. (Elem.) | 1 | 852183.83 | 645826.82 | 206357.01 | 636912.49 | Third Tranche | 229168.13 | 866080.62 | 636912.49 | 229168.13 | 100% | 100% | 111.1% | 101.6% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-20 | 2008-02-28 | 2008-03-28 | 100 | 489 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Pangao-an | 124706039 | Drainage Crossing with Slope Protection | 1 | 1367861 | 822416 | 545445 | 822416 | First Tranche | 170170 | 992586 | 822416 | 170170 | 100% | 100% | 31.2% | 72.56% | 100% | 2008-04-24 | no data | 2008-07-31 | 2009-02-28 | n/a | 212 | 273 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Sallab | 124706042 | Const'n of Steel Hanging Foot Bridge | 1 | 388459 | 272780 | 115679 | 272780 | Grant 100% Released | 121359 | 394139 | 272780 | 121359 | 100% | 100% | 104.9% | 101.5% | 100% | 2006-07-12 | 2006-10-18 | 2006-12-18 | 2007-06-15 | 2007-06-22 | 179 | 262 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Sallab | 124706042 | W. S. Level II (Spring Source) | 1 | 1352030.39 | 1067091.37 | 284939.02 | 1030506.98 | Third Tranche | 283389.02 | 1313896 | 1030506.98 | 283389.02 | 100% | 100% | 99.46% | 97.18% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-26 | 2008-03-28 | no data | 123 | 262 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Tagbac | 124706043 | Const'n. of Health Station | 1 | 556631.88 | 421288.89 | 135342.99 | 421288.89 | Grant 100% Released | 149942.99 | 571231.88 | 421288.89 | 149942.99 | 100% | 100% | 110.8% | 102.6% | 100% | 2006-07-12 | 2006-10-18 | 2006-11-30 | 2007-04-21 | 2007-04-27 | 142 | 375 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Tagbac | 124706043 | 2 Classroom School Building | 1 | 1272977 | 943896 | 329081 | 903490.54 | First Tranche | 211886 | 1115376.54 | 903490.54 | 211886 | 100% | 100% | 64.39% | 87.62% | 100% | 2008-04-24 | no data | 2008-06-20 | 2008-10-31 | n/a | 133 | 364 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Temporan | 124706044 | W. S. Level II (Spring Source) | 1 | 1412249.38 | 810544.92 | 601704.46 | 809414.25 | Third Tranche | 634984.46 | 1444398.71 | 809414.25 | 634984.46 | 100% | 100% | 105.5% | 102.3% | 100% | 2007-05-07 | 2007-07-12 | 2007-11-23 | 2008-03-28 | 2008-04-01 | 126 | 263 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | Magpet | 124706 | Temporan | 124706044 | Health Station | 1 | 857996.78 | 609533.78 | 248463 | 609533.78 | First Tranche | 178513 | 788046.78 | 609533.78 | 178513 | 100% | 100% | 71.85% | 91.85% | 100% | 2008-04-24 | no data | 2008-08-06 | 2008-10-31 | 2009-04-15 | 86 | 274 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Alegria | 124713001 | Water System Level II (Pump Driven) | 1 | 1121352.64 | 813863.67 | 307488.97 | 813863.67 | Grant 100% Released | 210196.56 | 1024060.23 | 813863.67 | 210196.56 | 100% | 100% | 68.36% | 91.32% | 100% | 2006-07-28 | no data | 2006-12-18 | 2007-05-31 | 2007-07-25 | 164 | 65 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Alegria | 124713001 | Construction of Rice Mill | 1 | 825811 | 613519 | 212292 | 613519 | First Tranche | 239512.14 | 853031.14 | 613519 | 239512.14 | 100% | 100% | 112.8% | 103.3% | 100% | 2008-05-15 | 2008-05-21 | 2008-09-11 | 2008-12-26 | 2009-06-05 | 106 | 106 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Bato-bato - C3 | 124713002 | Water System Level II (Pump Driven) | 3 | 406811.05 | 257901 | 148910.05 | 232110.9 | Third Tranche | 133951.93 | 366062.83 | 232110.9 | 133951.93 | 100% | 100% | 89.95% | 89.98% | 100% | 2006-07-28 | no data | 2007-08-02 | 2008-07-31 | n/a | 364 | 425 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Datu- Indang | 124713032 | Water System Level II (Pump Driven) | 3 | 406811.05 | 257901 | 148910.05 | 232110.9 | Third Tranche | 133951.93 | 366062.83 | 232110.9 | 133951.93 | 100% | 100% | 89.95% | 89.98% | 100% | 2006-07-28 | no data | 2007-08-02 | 2008-07-31 | n/a | 364 | 425 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Kimaruhing | 124713034 | Water System Level II (Pump Driven) | 3 | 406811.05 | 257901 | 148910.05 | 232110.9 | Third Tranche | 133951.93 | 366062.83 | 232110.9 | 133951.93 | 100% | 100% | 89.95% | 89.98% | 100% | 2006-07-28 | no data | 2007-08-02 | 2008-07-31 | n/a | 364 | 425 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Cabangbangan | 124713031 | Const'n. of 2-Barrel R.C. Box Culvert | 1 | 4651036.51 | 1796640.08 | 2854396.43 | 1796640.08 | Third Tranche | 794685.62 | 2591325.7 | 1796640.08 | 794685.62 | 100% | 100% | 27.84% | 55.72% | 100% | 2006-07-28 | no data | 2007-01-14 | 2007-05-08 | 2007-05-10 | 114 | 110 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Camasi | 124713009 | Water System Level II | 1 | 1419557.2 | 1025929.61 | 393627.59 | 997316.68 | Second Tranche | 464709.62 | 1462026.3 | 997316.68 | 464709.62 | 100% | 100% | 118.1% | 103% | 100% | 2007-05-21 | 2007-07-09 | 2008-03-24 | 2008-06-30 | no data | 98 | 198 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Datu Sundungan | 124713033 | Solar Dryer w/ Warehouse | 1 | 809387.43 | 402955.5 | 406431.93 | 362659.95 | Grant 100% Released | 201294 | 563953.95 | 362659.95 | 201294 | 100% | 100% | 49.53% | 69.68% | 100% | 2006-07-28 | no data | 2006-11-28 | 2007-05-28 | no data | 181 | 170 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | F. Cajelo | 124713005 | Road Improvement | 1 | 2932627.92 | 1874215.1 | 1058412.82 | 1800498.58 | Second Tranche | 1042692.84 | 2843191.42 | 1800498.58 | 1042692.84 | 100% | 100% | 98.51% | 96.95% | 100% | 2007-05-21 | 2007-07-09 | 2008-06-25 | 2009-05-30 | n/a | 339 | 150 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Greenhill | 124713030 | Water System - Level II (Spring Development with Water Pumping) | 1 | 931308.52 | 761362.24 | 169946.28 | 761362.24 | Second Tranche | 261781.37 | 1023143.61 | 761362.24 | 261781.37 | 100% | 100% | 154% | 109.9% | 100% | 2007-05-21 | 2007-07-09 | 2007-12-10 | 2008-10-31 | n/a | 326 | 188 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Idaoman | 124713006 | W. S. Level II (Spring Source) | 1 | 856339.35 | 658066.53 | 198272.82 | 658066.53 | Grant 100% Released | 238130.59 | 896197.12 | 658066.53 | 238130.59 | 100% | 100% | 120.1% | 104.7% | 100% | 2006-07-28 | no data | 2007-01-11 | 2008-05-31 | no data | 506 | 380 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Ilustre | 124713007 | Const'n. of Health Station | 1 | 516092.98 | 341319.84 | 174773.14 | 307187.86 | Third Tranche | 175190.44 | 482378.3 | 307187.86 | 175190.44 | 100% | 100% | 100.2% | 93.47% | 100% | 2007-05-21 | 2007-07-09 | 2007-11-13 | 2008-04-25 | no data | 164 | 277 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Ilustre | 124713007 | Construction of Learning Center | 1 | 795190 | 578816 | 216374 | 578816 | First Tranche | 222723.4 | 801539.4 | 578816 | 222723.4 | 100% | 100% | 102.9% | 100.8% | 100% | 2008-05-15 | 2008-05-21 | 2008-07-29 | 2008-10-30 | n/a | 93 | 278 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Kamarahan | 124713008 | Const'n. of Warehouse | 1 | 1595274.05 | 1136497.19 | 458776.86 | 1136497.19 | Third Tranche | 275910.48 | 1412407.67 | 1136497.19 | 275910.48 | 100% | 100% | 60.14% | 88.54% | 100% | 2006-07-28 | no data | 2007-02-05 | 2007-05-31 | 2007-09-23 | 115 | 248 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Kamarahan | 124713008 | Construction of Filtration Tank | 1 | 1997916 | 1477459 | 520457 | 1329713.1 |  | 503506 | 1833219.1 | 1329713.1 | 503506 | 100% | 100% | 96.74% | 91.76% | 100% | 2008-05-15 | 2008-05-21 | 2008-11-18 | 2009-04-30 | 2009-05-06 | 163 | 50 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Kisupaan | 124713011 | Construction of Day Care Center | 1 | 506603.52 | 369939.18 | 136664.34 | 369939.18 | Second Tranche | 155786.87 | 525726.05 | 369939.18 | 155786.87 | 100% | 100% | 114% | 103.8% | 100% | 2007-05-21 | 2007-07-09 | 2008-03-14 | 2008-10-31 | n/a | 231 | 190 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | La Esperanza | 124713012 | Construction of Health Station | 1 | 499111.38 | 395354.68 | 103756.7 | 385045.93 | Third Tranche | 105885 | 490930.93 | 385045.93 | 105885 | 100% | 100% | 102.1% | 98.36% | 100% | 2007-05-21 | 2007-07-09 | 2007-12-03 | 2008-04-30 | 2008-07-02 | 149 | 74 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Labu-o | 124713013 | Rural Electrification | 1 | 1158136.55 | 852942.96 | 305193.59 | 842475.38 | Third Tranche | 315212.52 | 1157687.9 | 842475.38 | 315212.52 | 100% | 100% | 103.3% | 99.96% | 100% | 2007-05-21 | 2007-07-09 | 2007-12-10 | 2008-04-25 | 2008-04-29 | 137 | 90 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Labu-o | 124713013 | Constructions of Day Care Center | 1 | 591347 | 427319 | 164028 | 384587.1 | First Tranche | 162542.78 | 547129.88 | 384587.1 | 162542.78 | 100% | 100% | 99.09% | 92.52% | 100% | 2008-05-15 | 2008-05-21 | 2008-09-18 | 2009-04-24 | 2009-04-30 | 218 | 75 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | LamaLama | 124713014 | Solar Dryer w/ Warehouse | 1 | 781000.72 | 532648.4 | 248352.32 | 518260.07 | Third Tranche | 211522.26 | 729782.33 | 518260.07 | 211522.26 | 100% | 100% | 85.17% | 93.44% | 100% | 2006-07-28 | no data | 2007-03-05 | 2007-11-24 | 2007-11-29 | 264 | 211 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Lomonay | 124713016 | Solar Dryer with Warehouse | 1 | 805000 | 554698.73 | 250301.27 | 499228.9 | Third Tranche | 298462.54 | 797691.44 | 499228.9 | 298462.54 | 100% | 100% | 119.2% | 99.09% | 100% | 2007-05-21 | 2007-07-09 | 2008-02-12 | 2008-06-30 | no data | 139 | 130 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Mabuhay | 124713035 | Const'n. of Health Station | 1 | 487076.19 | 349908.25 | 137167.94 | 349908.25 | Grant 100% Released | 96590.1 | 446498.35 | 349908.25 | 96590.1 | 100% | 100% | 70.42% | 91.67% | 100% | 2006-07-28 | no data | 2007-02-08 | 2007-06-30 | 2007-09-22 | 142 | 259 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Mabuhay | 124713035 | Water System Level II Spring Source | 1 | 1075919 | 769793 | 306126 | 740705 | First Tranche | 336785.75 | 1077490.75 | 740705 | 336785.75 | 100% | 100% | 110% | 100.1% | 100% | 2008-05-15 | 2008-05-21 | 2008-09-12 | 2009-04-30 | n/a | 230 | 295 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | New Cebu | 124713022 | Const'n. of Health Station | 1 | 493065.3 | 331932.44 | 161132.86 | 331932.44 | Grant 100% Released | 111338.72 | 443271.16 | 331932.44 | 111338.72 | 100% | 100% | 69.1% | 89.9% | 100% | 2006-07-28 | no data | 2006-12-18 | 2007-05-31 | 2007-06-22 | 164 | 450 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | New Cebu | 124713022 | Construction of Day Care Center | 1 | 425790.94 | 295756.31 | 130034.63 | 295756.31 | Third Tranche | 131580.44 | 427336.75 | 295756.31 | 131580.44 | 100% | 100% | 101.2% | 100.4% | 100% | 2007-05-21 | 2007-07-09 | 2007-12-14 | 2008-04-30 | no data | 138 | 612 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | New Cebu | 124713022 | Construction of Learning Center | 1 | 1252567 | 926273 | 326294 | 926273 | Second Tranche | 342159 | 1268432 | 926273 | 342159 | 100% | 100% | 104.9% | 101.3% | 100% | 2008-05-15 | 2008-05-21 | 2008-08-06 | 2008-11-30 | n/a | 116 | 90 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Poblacion | 124713024 | Road Opening | 1 | 485160.44 | 271444.76 | 213715.68 | 244300.33 | Second Tranche | 224742.01 | 469042.34 | 244300.33 | 224742.01 | 100% | 100% | 105.2% | 96.68% | 100% | 2007-05-21 | 2007-07-09 | 2008-04-28 | 2008-10-31 | 2009-04-29 | 186 | 1276 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Sagcungan | 124713026 | Const'n of Day care Center | 1 | 540620.15 | 420461 | 120159.15 | 378414.9 | Third Tranche | 126939.13 | 505354.03 | 378414.9 | 126939.13 | 100% | 100% | 105.6% | 93.48% | 100% | 2006-07-28 | no data | 2006-11-28 | 2007-05-03 | 2007-06-13 | 156 | 190 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Sagcungan | 124713026 | Water System Level II Spring Source | 1 | 1871971 | 1352741 | 519230 | 1300467.58 |  | 687803.92 | 1988271.5 | 1300467.58 | 687803.92 | 100% | 100% | 132.5% | 106.2% | 100% | 2008-05-15 | 2008-05-21 | 2008-10-03 | 2009-03-31 | n/a | 179 | 190 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Salat | 124713027 | Const'n of Day care Center | 1 | 518933.83 | 410509.42 | 108424.41 | 410509.42 | Grant 100% Released | 128465.07 | 538974.49 | 410509.42 | 128465.07 | 100% | 100% | 118.5% | 103.9% | 100% | 2006-07-28 | no data | 2006-12-26 | 2007-05-31 | 2007-06-22 | 156 | 400 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Salat | 124713027 | Solar Dryer with Warehouse | 1 | 1043876 | 780290 | 263586 | 731474 |  | 265187.75 | 996661.75 | 731474 | 265187.75 | 100% | 100% | 100.6% | 95.48% | 100% | 2008-05-15 | 2008-05-21 | 2008-11-19 | 2009-06-30 | n/a | 223 | 495 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Sarayan | 124713028 | Const'n. of Health Station | 1 | 521855.18 | 388616.52 | 133238.66 | 388616.52 | Grant 100% Released | 110761.28 | 499377.8 | 388616.52 | 110761.28 | 100% | 100% | 83.13% | 95.69% | 100% | 2006-07-28 | no data | 2006-11-30 | 2007-05-31 | no data | 182 | 296 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Sarayan | 124713028 | Construction of Day Care Center | 1 | 592477 | 457856 | 134621 | 441963 |  | 161076.8 | 603039.8 | 441963 | 161076.8 | 100% | 100% | 119.7% | 101.8% | 100% | 2008-05-15 | 2008-05-21 | 2008-10-27 | 2009-03-31 | 2009-05-06 | 155 | 190 |  | 1 | MINDANAO
XII | 12 | North Cotabato | 1247 | President Roxas | 124713 | Tuael | 124713029 | Warehouse Building | 1 | 1713536.75 | 757036.59 | 956500.16 | 745787.74 | Second Tranche | 929228.17 | 1675015.91 | 745787.74 | 929228.17 | 100% | 100% | 97.15% | 97.75% | 100% | 2007-05-21 | 2007-07-09 | 2008-02-25 | 2008-06-30 | no data | 126 | 383 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Daan Suyan | 128006001 | 90 m. Hanging Bridge | 1 | 1870239 | 818431 | 1051808 | 818431 | Grant 100% Released | 714165.25 | 1532596.25 | 818431 | 714165.25 | 100% | 100% | 67.9% | 81.95% | 100% | 2005-10-20 | 2005-11-17 | 2006-04-27 | 2007-03-31 | no data | 338 | 795 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Daan Suyan | 128006001 | W.S. Level II (Spring Source) | 1 | 630000 | 520713 | 109287 | 520713 | First Tranche | 109288.01 | 630001.01 | 520713 | 109288.01 | 100% | 100% | 100% | 100% | 100% | no data | no data | 2009-05-05 | 2009-06-30 | no data | 56 | 634 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Kihan | 128006002 | Spring Development | 1 | 1137268 | 412000 | 725268 | 412000 | Grant 100% Released | 527062.52 | 939062.52 | 412000 | 527062.52 | 100% | 100% | 72.67% | 82.57% | 100% | 2004-10-14 | 2004-11-30 | 2005-03-08 | 2005-11-03 | 2005-11-05 | 240 | 200 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Kihan | 128006002 | 9.68 kms Road Openning | 1 | 1877000 | 583362 | 1293638 | 583362 | Grant 100% Released | 650000 | 1233362 | 583362 | 650000 | 100% | 100% | 50.25% | 65.71% | 100% | 2005-10-20 | 2005-11-17 | 2006-04-26 | 2007-04-30 | 2007-08-07 | 369 | 300 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Kihan | 128006002 | 2 CL School Building (HS) | 1 | 1345700 | 1112128 | 233572 | 1112128 | First Tranche | 234572 | 1346700 | 1112128 | 234572 | 100% | 100% | 100.4% | 100.1% | 100% | no data | no data | 2009-05-09 | 2009-07-31 | no data | 83 | 394 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Kinam | 128006003 | 2 Classroom School Building | 1 | 1280440 | 638590 | 641850 | 574731 | Third Tranche | 350000 | 924731 | 574731 | 350000 | 100% | 100% | 54.53% | 72.22% | 100% | 2005-10-20 | 2005-11-17 | 2006-04-26 | 2007-03-31 | no data | 339 | 1151 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Kinam | 128006003 | 2 CL School Building (HS) | 1 | 1435000 | 1185928 | 249072 | 1185928 | First Tranche | 253478.08 | 1439406.08 | 1185928 | 253478.08 | 100% | 100% | 101.8% | 100.3% | 100% | no data | no data | 2009-05-07 | 2009-10-31 | n/a | 177 | 3623 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Libi | 128006004 | Road Construction | 1 | 712775 | 398675 | 314100 | 398675 | Grant 100% Released | 624600 | 1023275 | 398675 | 624600 | 100% | 100% | 198.9% | 143.6% | 100% | 2003-04-29 | 2003-06-28 | 2003-11-28 | 2004-02-28 | 2004-03-18 | 92 | 140 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Libi | 128006004 | Road Opening | 1 | 1768424 | 505000 | 1263424 | 505000 | Grant 100% Released | 1378721.5 | 1883721.5 | 505000 | 1378721.5 | 100% | 100% | 109.1% | 106.5% | 100% | 2004-10-14 | 2004-11-30 | 2005-04-18 | 2005-06-30 | no data | 73 | 140 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Lun Masla | 128006005 | W.S. Level I (Hand Pumps) | 1 | 329300 | 272078 | 57222 | 272078 | First Tranche | 58217.01 | 330295.01 | 272078 | 58217.01 | 100% | 100% | 101.7% | 100.3% | 100% | no data | no data | 2009-04-10 | 2009-07-31 | no data | 112 | 400 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Lun Masla - C2 | 128006005 | Spring Development | 2 | 2482296.7 | 2167697.7 | 314599 | 2167697.7 | Grant 100% Released | 1564099 | 3731796.7 | 2167697.7 | 1564099 | 100% | 100% | 497.2% | 150.3% | 100% | 2003-04-29 | 2003-06-28 | 2003-10-13 | 2004-03-05 | 2004-07-12 | 144 | 380 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Lun Padidu | 128006006 | Day Care Center | 1 | 283460 | 210708 | 72752 | 210708 | Grant 100% Released | 62030.5 | 272738.5 | 210708 | 62030.5 | 100% | 100% | 85.26% | 96.22% | 100% | 2003-04-29 | 2003-06-28 | 2003-10-13 | 2004-02-21 | 2004-03-03 | 131 | 80 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Lun Padidu | 128006006 | Construction of 3 Classroom School Building | 1 | 1457155 | 880000 | 577155 | 880000 | Grant 100% Released | 428258.96 | 1308258.96 | 880000 | 428258.96 | 100% | 100% | 74.2% | 89.78% | 100% | 2004-10-14 | 2004-11-30 | 2005-01-08 | 2005-05-20 | 2005-05-23 | 132 | 1530 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Lun Padidu | 128006006 | Livelihood & Technical Center | 1 | 915394.44 | 460000 | 455394.44 | 460000 | Grant 100% Released | 366574.44 | 826574.44 | 460000 | 366574.44 | 100% | 100% | 80.5% | 90.3% | 100% | 2005-10-20 | 2005-11-17 | 2006-03-30 | 2006-10-30 | 2007-07-10 | 214 | 1071 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Lun Padidu | 128006006 | Development Center | 1 | 500000 | 289340 | 210660 | 282985.87 | First Tranche | 128165.8 | 411151.67 | 282985.87 | 128165.8 | 100% | 100% | 60.84% | 82.23% | 100% | no data | no data | 2009-05-06 | 2009-06-26 | 2009-07-03 | 51 | 500 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Patag | 128006007 | Road Opening | 1 | 900000 | 300000 | 600000 | 300000 | Grant 100% Released | 273137.5 | 573137.5 | 300000 | 273137.5 | 100% | 100% | 45.52% | 63.68% | 100% | 2004-10-14 | 2004-11-30 | 2005-02-07 | 2005-05-20 | no data | 102 | 70 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Patag | 128006007 | Construction of Day Care Center | 1 | 615000 | 508221 | 106779 | 508221 | First Tranche | 63483.21 | 571704.21 | 508221 | 63483.21 | 100% | 100% | 59.45% | 92.96% | 100% | no data | no data | 2009-05-06 | 2009-09-30 | n/a | 147 | 424 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Poblacion | 128006008 | 2.15 kms Road Openning | 1 | 1038795 | 430000 | 608795 | 430000 | Grant 100% Released | 380880 | 810880 | 430000 | 380880 | 100% | 100% | 62.56% | 78.06% | 100% | 2005-10-20 | 2005-11-17 | 2006-04-27 | 2006-11-30 | no data | 217 | 700 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Poblacion | 128006008 | Construction of Health Station | 1 | 620000 | 512426 | 107574 | 512426 | First Tranche | 100778.56 | 613204.56 | 512426 | 100778.56 | 100% | 100% | 93.68% | 98.9% | 100% | no data | no data | 2009-05-18 | 2009-07-31 | no data | 74 | 800 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Sapu Masla | 128006009 | 3 Classroom School Building with Comfort Rooms | 1 | 824418 | 590493 | 233925 | 590493 | Grant 100% Released | 270220 | 860713 | 590493 | 270220 | 100% | 100% | 115.5% | 104.4% | 100% | 2003-04-29 | 2003-06-28 | 2003-07-28 | 2003-10-18 | 2003-10-23 | 82 | 150 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Sapu Masla | 128006009 | Water System | 1 | 576273 | 302000 | 274273 | 302000 | Grant 100% Released | 225277.5 | 527277.5 | 302000 | 225277.5 | 100% | 100% | 82.14% | 91.5% | 100% | 2004-10-14 | 2004-11-30 | 2005-01-28 | 2005-04-22 | 2005-05-09 | 84 | 150 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Sapu Padidu | 128006010 | Water System | 1 | 386461.4 | 232426.4 | 154035 | 232426.4 | Grant 100% Released | 133835 | 366261.4 | 232426.4 | 133835 | 100% | 100% | 86.89% | 94.77% | 100% | 2003-04-29 | 2003-06-28 | 2003-10-20 | 2004-02-21 | 2004-03-03 | 124 | 90 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Tuyan | 128006011 | Road Opening | 1 | 819800 | 288000 | 531800 | 288000 | Grant 100% Released | 422265.5 | 710265.5 | 288000 | 422265.5 | 100% | 100% | 79.4% | 86.64% | 100% | 2004-10-14 | 2004-11-30 | 2005-02-16 | 2005-10-17 | 2005-10-19 | 243 | 703 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Tuyan | 128006011 | 2 Classroom School Building | 1 | 1068269.92 | 518825 | 549444.92 | 518825 | Grant 100% Released | 483834.92 | 1002659.92 | 518825 | 483834.92 | 100% | 100% | 88.06% | 93.86% | 100% | 2005-10-20 | 2005-11-17 | 2006-05-08 | 2007-04-30 | 2007-07-02 | 357 | 266 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Tuyan | 128006011 | Development Center | 1 | 500000 | 413238 | 86762 | 413238 | First Tranche | 96000 | 509238 | 413238 | 96000 | 100% | 100% | 110.6% | 101.8% | 100% | no data | no data | 2009-04-29 | 2009-07-31 | no data | 93 | 266 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Upper Suyan | 128006012 | Road Opening | 1 | 2195500 | 907500 | 1288000 | 907500 | Grant 100% Released | 705700 | 1613200 | 907500 | 705700 | 100% | 100% | 54.79% | 73.48% | 100% | 2004-10-14 | 2004-11-30 | 2005-03-01 | 2006-04-30 | no data | 425 | 180 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malapatan | 128006 | Upper Suyan | 128006012 | 2 CL School Building (Elem.) | 1 | 1435000 | 1185928 | 249072 | 1185928 | First Tranche | 243093.54 | 1429021.54 | 1185928 | 243093.54 | 100% | 100% | 97.6% | 99.58% | 100% | no data | no data | 2009-04-28 | 2009-10-31 | n/a | 186 | 230 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Alkikan | 128007001 | Road Rehabilitation & Gravelling | 1 | 1626000 | 804000 | 822000 | 804000 | Grant 100% Released | 595470 | 1399470 | 804000 | 595470 | 100% | 100% | 72.44% | 86.07% | 100% | 2005-06-16 | 2005-08-09 | 2005-10-13 | 2006-04-30 | 2006-05-02 | 199 | 140 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Ampon | 128007002 | Water System L-II | 1 | 1188811 | 990871 | 197940 | 990871 | Grant 100% Released | 262290 | 1253161 | 990871 | 262290 | 100% | 100% | 132.5% | 105.4% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-19 | 2005-07-15 | no data | 361 | 380 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Ampon | 128007002 | 3CL School Bldg. | 1 | 1007500 | 352500 | 655000 | 176250 | First Tranche | 20500 | 196750 | 176250 | 20500 | 100% | 100% | 3.13% | 19.53% | 100% | 2006-04-05 | 2006-06-20 | 2006-12-14 | 2009-02-28 | n/a | 807 | 350 | completed as built | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Atlae - C3 | 128007003 | Water System (Submersible) | 3 | 3134691 | 1968000 | 1166691 | 1968000 | Grant 100% Released | 1054625 | 3022625 | 1968000 | 1054625 | 100% | 100% | 90.39% | 96.42% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-23 | 2006-06-30 | 2006-07-04 | 219 | 1274 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Kibala | 128007012 | Water System (Submersible) | 3 | 3134691 | 1968000 | 1166691 | 1968000 | Grant 100% Released | 1054625 | 3022625 | 1968000 | 1054625 | 100% | 100% | 90.39% | 96.42% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-23 | 2006-06-30 | 2006-07-04 | 219 | 1274 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Kablat | 128007013 | Water System (Submersible) | 3 | 3134691 | 1968000 | 1166691 | 1968000 | Grant 100% Released | 1054625 | 3022625 | 1968000 | 1054625 | 100% | 100% | 90.39% | 96.42% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-23 | 2006-06-30 | 2006-07-04 | 219 | 1274 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Banahaw | 128007004 | Road Rehabilitation & Gravelling | 1 | 1127780 | 469500 | 658280 | 469500 | Grant 100% Released | 564169 | 1033669 | 469500 | 564169 | 100% | 100% | 85.7% | 91.66% | 100% | 2003-12-11 | 2004-03-12 | 2004-09-03 | 2005-02-28 | 2005-03-17 | 178 | 357 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Banahaw | 128007004 | School Building 3 Classroom | 1 | 1140917 | 947137 | 193780 | 947137 | Grant 100% Released | 206203 | 1153340 | 947137 | 206203 | 100% | 100% | 106.4% | 101.1% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-07 | 2006-05-30 | 2006-07-13 | 204 | 357 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Banate | 128007005 | Spring Development | 1 | 1211133.6 | 407375.6 | 803758 | 407375.6 | Grant 100% Released | 693423.15 | 1100798.75 | 407375.6 | 693423.15 | 100% | 100% | 86.27% | 90.89% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-15 | 2006-04-18 | 2006-04-18 | 154 | 665 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Banate | 128007005 | Bagsakan Center w/ mini office | 1 | 910424 | 443424 | 467000 | 443424 | Grant 100% Released | 352372 | 795796 | 443424 | 352372 | 100% | 100% | 75.45% | 87.41% | 100% | 2006-04-05 | 2006-06-20 | 2006-11-15 | 2007-08-31 | no data | 289 | 802 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | B'laan | 128007006 | Road Rehabilitation & Gravelling | 1 | 1740925 | 357425 | 1383500 | 357425 | Grant 100% Released | 782450 | 1139875 | 357425 | 782450 | 100% | 100% | 56.56% | 65.48% | 100% | 2003-12-11 | 2004-03-12 | 2004-11-06 | 2005-11-28 | no data | 387 | 150 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Datal Batong | 128007007 | 3CL School Bldg. | 1 | 1269422 | 722500 | 546922 | 722500 | Third Tranche | 438406 | 1160906 | 722500 | 438406 | 100% | 100% | 80.16% | 91.45% | 100% | 2006-04-05 | 2006-06-20 | 2007-01-08 | 2008-03-28 | no data | 445 | 450 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Datal Bila | 128007008 | 3 Classroom School Building | 1 | 807809 | 775219 | 32590 | 775219 | Grant 100% Released | 304401.4 | 1079620.4 | 775219 | 304401.4 | 100% | 100% | 934% | 133.6% | 100% | 2003-12-11 | 2004-03-12 | 2004-08-18 | 2004-12-31 | 2005-02-11 | 135 | 90 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Datal Bila | 128007008 | Water System | 1 | 1301922 | 750000 | 551922 | 639000 | First Tranche | 375000 | 1014000 | 639000 | 375000 | 100% | 100% | 67.94% | 77.88% | 100% | 2006-04-05 | 2006-06-20 | 2007-02-13 | 2007-10-30 | no data | 259 | 205 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Datal Tampal | 128007009 | Water System Level 2 | 1 | 1627500 | 935000 | 692500 | 935000 | Third Tranche | 537149 | 1472149 | 935000 | 537149 | 100% | 100% | 77.57% | 90.45% | 100% | 2006-04-05 | 2006-06-20 | 2007-02-07 | 2008-03-28 | no data | 415 | 300 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | J.P. Laurel | 128007010 | Road Rehabilitation & Regravelling | 1 | 1526600 | 965000 | 561600 | 965000 | Grant 100% Released | 148066.5 | 1113066.5 | 965000 | 148066.5 | 100% | 100% | 26.37% | 72.91% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-19 | 2005-05-20 | 2005-05-29 | 305 | 100 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | J.P. Laurel | 128007010 | Spring Development | 1 | 1278400 | 760000 | 518400 | 760000 | Grant 100% Released | 470150 | 1230150 | 760000 | 470150 | 100% | 100% | 90.69% | 96.23% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-03 | 2006-02-10 | no data | 99 | 517 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Kawayan | 128007011 | Water System L-II | 1 | 2460008.4 | 802263.4 | 1657745 | 802263.4 | Grant 100% Released | 64350 | 866613.4 | 802263.4 | 64350 | 100% | 100% | 3.882% | 35.23% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-20 | 2004-12-28 | 2005-01-31 | 161 | 150 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Kawayan | 128007011 | 2CL School Bldg. | 1 | 998349.2 | 398249.2 | 600100 | 398249.2 | Grant 100% Released | 808430.71 | 1206679.91 | 398249.2 | 808430.71 | 100% | 100% | 134.7% | 120.9% | 100% | 2006-04-05 | 2006-06-20 | 2006-12-14 | 2007-06-30 | 2007-08-01 | 198 | 494 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Kinabalan | 128007014 | Road Improvement | 1 | 1550670 | 726070 | 824600 | 653463 | Second Tranche | 449343 | 1102806 | 653463 | 449343 | 100% | 100% | 54.49% | 71.12% | 100% | 2006-04-05 | 2006-06-20 | 2006-10-11 | 2007-01-31 | no data | 112 | 298 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Lower Mainit | 128007015 | Road Rehabilitation | 1 | 1863160 | 981160 | 882000 | 981160 | Third Tranche | 596429 | 1577589 | 981160 | 596429 | 100% | 100% | 67.62% | 84.67% | 100% | 2006-04-05 | 2006-06-20 | 2006-10-05 | 2007-08-31 | no data | 330 | 423 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Lutay | 128007016 | Road Opening & Gravelling | 1 | 2105559 | 460800 | 1644759 | 460800 | Grant 100% Released | 1209700 | 1670500 | 460800 | 1209700 | 100% | 100% | 73.55% | 79.34% | 100% | 2003-12-11 | 2004-03-12 | 2004-08-17 | 2005-06-30 | no data | 317 | 620 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Malabod | 128007017 | Foot Bridge 37m | 1 | 796710 | 700000 | 96710 | 700000 | Grant 100% Released | 82350 | 782350 | 700000 | 82350 | 100% | 100% | 85.15% | 98.2% | 100% | 2003-12-11 | 2004-03-12 | 2004-08-16 | 2004-10-31 | 2005-02-04 | 76 | 465 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Malabod | 128007017 | Road Concreting | 1 | 1521080 | 875000 | 646080 | 875000 | Grant 100% Released | 553500 | 1428500 | 875000 | 553500 | 100% | 100% | 85.67% | 93.91% | 100% | 2006-04-05 | 2006-06-20 | 2006-11-20 | 2007-03-31 | no data | 131 | 465 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Malalag Cogon | 128007018 | Spring Development | 1 | 1553942 | 1047142 | 506800 | 1047142 | Grant 100% Released | 487900 | 1535042 | 1047142 | 487900 | 100% | 100% | 96.27% | 98.78% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-23 | 2006-03-27 | 2006-05-05 | 124 | 314 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Malandag | 128007019 | Water System (Submersible) | 1 | 1521922 | 865000 | 656922 | 778500 | Third Tranche | 487922 | 1266422 | 778500 | 487922 | 100% | 100% | 74.27% | 83.21% | 100% | 2006-04-05 | 2006-06-20 | 2006-12-20 | 2007-08-31 | no data | 254 | 220 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Malungon Gamay | 128007020 | Spring Development | 1 | 1559524.9 | 368897 | 1190627.9 | 368897 | Grant 100% Released | 1132868.26 | 1501765.26 | 368897 | 1132868.26 | 100% | 100% | 95.15% | 96.3% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-10 | 2006-04-11 | 2006-04-11 | 152 | 512 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Malungon Gamay | 128007020 | 3CL School Bldg. | 1 | 1368675 | 710000 | 658675 | 710000 | Grant 100% Released | 471822 | 1181822 | 710000 | 471822 | 100% | 100% | 71.63% | 86.35% | 100% | 2006-04-05 | 2006-06-20 | 2006-11-15 | 2007-06-30 | no data | 227 | 651 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Nagpan | 128007021 | Water System | 1 | 1012634 | 701824 | 310810 | 701824 | Grant 100% Released | 242217.4 | 944041.4 | 701824 | 242217.4 | 100% | 100% | 77.93% | 93.23% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-15 | 2006-10-30 | no data | 349 | 310 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Panamin | 128007022 | Water System L-II | 1 | 679381.75 | 497381.75 | 182000 | 497381.75 | Grant 100% Released | 47890 | 545271.75 | 497381.75 | 47890 | 100% | 100% | 26.31% | 80.26% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-26 | 2005-02-28 | 2005-05-18 | 217 | 120 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Poblacion | 128007023 | Road Rehabilitation | 1 | 1903996.8 | 935096.8 | 968900 | 841587.12 | Second Tranche | 616834.11 | 1458421.23 | 841587.12 | 616834.11 | 100% | 100% | 63.66% | 76.6% | 100% | 2006-04-05 | 2006-06-20 | 2006-10-04 | 2007-01-31 | 2007-04-11 | 119 | 640 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | San Juan | 128007024 | Warehouse/Solar Drier | 1 | 671560 | 580260 | 91300 | 580260 | Grant 100% Released | 537860 | 1118120 | 580260 | 537860 | 100% | 100% | 589.1% | 166.5% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-20 | 2005-02-28 | 2005-03-09 | 223 | 312 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | San Juan | 128007024 | Health Center w/ complete facilities | 1 | 888190 | 606000 | 282190 | 575319.36 | Third Tranche | 341922 | 917241.36 | 575319.36 | 341922 | 100% | 100% | 121.2% | 103.3% | 100% | 2006-04-05 | 2006-06-20 | 2006-11-20 | 2007-06-30 | no data | 222 | 294 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | San Miguel | 128007025 | Road Rehabilitation & Gravelling | 1 | 1093259.85 | 633709.85 | 459550 | 633709.85 | Grant 100% Released | 817513.42 | 1451223.27 | 633709.85 | 817513.42 | 100% | 100% | 177.9% | 132.7% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-18 | 2006-01-30 | 2006-01-31 | 73 | 220 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | San Roque | 128007026 | School Building 4 Classroom | 1 | 1654011.36 | 946011.36 | 708000 | 946011.36 | Grant 100% Released | 817513.42 | 1763524.78 | 946011.36 | 817513.42 | 100% | 100% | 115.5% | 106.6% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-03 | 2006-03-30 | 2006-03-20 | 147 | 665 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Talus | 128007027 | Water System L-II | 1 | 672612 | 470862 | 201750 | 470862 | Grant 100% Released | 121770 | 592632 | 470862 | 121770 | 100% | 100% | 60.36% | 88.11% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-20 | 2005-02-20 | 2005-02-24 | 215 | 290 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Tamban | 128007028 | Water System L-II | 1 | 1218512 | 876632 | 341880 | 876631.8 | Third Tranche | 313470 | 1190101.8 | 876631.8 | 313470 | 100% | 100% | 91.69% | 97.67% | 100% | 2003-12-11 | 2004-03-12 | 2004-10-18 | 2005-03-18 | no data | 151 | 300 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Upper Biangan | 128007029 | Water System L-II | 1 | 852518 | 576118 | 276400 | 576118 | Grant 100% Released | 102340 | 678458 | 576118 | 102340 | 100% | 100% | 37.03% | 79.58% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-22 | 2005-01-31 | 2005-02-09 | 193 | 285 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Upper Lumabat | 128007030 | 3 Classroom School Building | 1 | 852150 | 777600 | 74550 | 777600 | Grant 100% Released | 258750 | 1036350 | 777600 | 258750 | 100% | 100% | 347.1% | 121.6% | 100% | 2003-12-11 | 2004-03-12 | 2004-07-02 | 2005-02-28 | 2005-03-09 | 241 | 331 |  | 1 | MINDANAO
XII | 12 | Sarangani Province | 1280 | Malungon | 128007 | Upper Mainit | 128007031 | Road Improvement | 1 | 1408004 | 715904 | 692100 | 715904 | Grant 100% Released | 736850 | 1452754 | 715904 | 736850 | 100% | 100% | 106.5% | 103.2% | 100% | 2005-06-16 | 2005-08-09 | 2005-11-26 | 2006-02-27 | 2006-05-26 | 93 | 506 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Bacdulong | 126319001 | Health Center | 1 | 555833.34 | 426207 | 129626.34 | 426206.37 | Second Tranche | 134654.34 | 560860.71 | 426206.37 | 134654.34 | 100% | 100% | 103.9% | 100.9% | 100% | 2007-11-27 | no data | 2008-06-21 | 2008-10-31 | n/a | 132 | 465 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Denlag | 126319002 | Construction of 50.4 L.M. Foot Bridge | 1 | 1394240 | 1117560 | 276680 | 1117560 | Third Tranche | 233620 | 1351180 | 1117560 | 233620 | 100% | 100% | 84.44% | 96.91% | 100% | 2007-02-11 | no data | 2007-08-06 | 2008-06-04 | no data | 303 | 506 | completed as built | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Halilan | 126319003 | Construction of 50.4 L.M. Foot Bridge | 1 | 1394240 | 1117560 | 276680 | 1005804 | Third Tranche | 252250 | 1258054 | 1005804 | 252250 | 100% | 100% | 91.17% | 90.23% | 100% | 2007-02-11 | no data | 2007-08-06 | 2009-02-28 | n/a | 572 | 419 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Hanoon | 126319004 | 3 Classroom School Building | 1 | 1461304 | 1143016 | 318288 | 1143016 | First Tranche | 323661 | 1466677 | 1143016 | 323661 | 100% | 100% | 101.7% | 100.4% | 100% | 2007-11-27 | no data | 2008-08-18 | 2009-03-31 | n/a | 225 | 273 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Klubi | 126319005 | Daycare Center | 1 | 643650 | 610583 | 33067 | 610583 |  | 34940 | 645523 | 610583 | 34940 | 100% | 100% | 105.7% | 100.3% | 100% | 2007-11-27 | no data | 2009-03-19 | 2009-06-30 | n/a | 103 | 573 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lake Lahit | 126319006 | Water System Level II (Pump Driven) | 1 | 1366326.95 | 1076282 | 290044.95 | 1076282 | First Tranche | 275823.95 | 1352105.95 | 1076282 | 275823.95 | 100% | 100% | 95.1% | 98.96% | 100% | 2007-11-27 | no data | 2008-07-09 | 2008-12-29 | n/a | 173 | 356 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Siluton | 126319015 | Solar Drier with Warehouse | 1 | 833458 | 623541 | 209917 | 623541 | First Tranche | 211404 | 834945 | 623541 | 211404 | 100% | 100% | 100.7% | 100.2% | 100% | 2007-11-27 | no data | 2008-06-26 | 2008-12-29 | n/a | 186 | 726 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamcade | 126319007 | 3 CL School Biulding | 1 | 1424423.5 | 1158896.5 | 265527 | 1158896.5 | Third Tranche | 261230.62 | 1420127.12 | 1158896.5 | 261230.62 | 100% | 100% | 98.38% | 99.7% | 100% | 2007-02-11 | no data | 2007-08-03 | 2007-10-26 | 2007-11-14 | 84 | 362 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamdalag | 126319008 | 2 Classroom School Building | 1 | 1088899 | 837392 | 251507 | 837392 | First Tranche | 252102.5 | 1089494.5 | 837392 | 252102.5 | 100% | 100% | 100.2% | 100.1% | 100% | 2007-11-27 | no data | 2008-07-03 | 2008-11-30 | n/a | 150 | 1040 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamfugon | 126319009 | Solar Dryer with Warehouse | 1 | 936666 | 890180 | 46486 | 890180 |  | 65565 | 955745 | 890180 | 65565 | 100% | 100% | 141% | 102% | 100% | 2007-11-27 | no data | 2009-03-26 | 2009-06-30 | n/a | 96 | 932 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lamlahak | 126319010 | Double Barrel Box Culvert w/ Gravelling | 1 | 1220194.1 | 764668.1 | 455526 | 764668.1 | Grant 100% Released | 444685 | 1209353.1 | 764668.1 | 444685 | 100% | 100% | 97.62% | 99.11% | 100% | 2007-02-11 | no data | 2007-07-11 | 2007-11-12 | 2007-11-13 | 124 | 674 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Lower Maculan | 126319011 | Solar Drier w/ Warehouse | 1 | 873483 | 626688 | 246795 | 626688 | Grant 100% Released | 243665 | 870353 | 626688 | 243665 | 100% | 100% | 98.73% | 99.64% | 100% | 2007-02-11 | no data | 2007-07-13 | 2007-10-15 | 2007-11-13 | 94 | 297 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Luhib | 126319012 | Health Center | 1 | 554133.34 | 420796 | 133337.34 | 419796 | Second Tranche | 137175.34 | 556971.34 | 419796 | 137175.34 | 100% | 100% | 102.9% | 100.5% | 100% | 2007-11-27 | no data | 2008-06-23 | 2008-10-31 | n/a | 130 | 477 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Ned | 126319013 | Solar Dryer with Warehouse | 1 | 1043938 | 996452 | 47486 | 996452 |  | 43400 | 1039852 | 996452 | 43400 | 100% | 100% | 91.4% | 99.61% | 100% | 2007-11-27 | no data | 2009-03-24 | 2009-06-30 | n/a | 98 | 1873 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Poblacion | 126319014 | 2- Classroom School Bldg. (High School) | 1 | 1293254 | 1163247 | 130007 | 1163247 |  | 126932 | 1290179 | 1163247 | 126932 | 100% | 100% | 97.63% | 99.76% | 100% | 2007-11-27 | no data | 2009-03-11 | 2009-07-31 | n/a | 142 | 1298 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Poblacion | 126319014 | Street Lighting | 1 | 300000 | 300000 | 0 | 300000 |  |  | 300000 | 300000 | 0 | 100% | #DIV/0! | #DIV/0! | 100% | 100% | n/a | n/a | 2009-07-01 | 2009-07-31 | no data | 30 | 1298 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Talisay | 126319016 | 2 - Barrel Box Culvert | 1 | 1275996 | 987170 | 288826 | 987170 |  | 287826 | 1274996 | 987170 | 287826 | 100% | 100% | 99.65% | 99.92% | 100% | 2007-11-27 | no data | 2009-04-13 | 2009-06-30 | n/a | 78 | 464 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Tasiman | 126319016 | 3 Classroom School Building | 1 | 1448304 | 1120404 | 327900 | 1120404 | Second Tranche | 324075.5 | 1444479.5 | 1120404 | 324075.5 | 100% | 100% | 98.83% | 99.74% | 100% | 2007-11-27 | no data | 2008-07-02 | 2009-04-28 | n/a | 300 | 440 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Takunel | 126319017 | 2- Classroom School Bldg. (Elementary) | 1 | 1240204 | 1125197 | 115007 | 1125197 |  | 113610 | 1238807 | 1125197 | 113610 | 100% | 100% | 98.79% | 99.89% | 100% | 2007-11-27 | no data | 2009-03-16 | 2009-06-30 | n/a | 106 | 465 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | Lake Sebu | 126319 | Upper Maculan | 126319018 | Construction of 30.00 L.M. Foot Bridge | 1 | 1135256 | 894161 | 241095 | 894161 | Third Tranche | 227495 | 1121656 | 894161 | 227495 | 100% | 100% | 94.36% | 98.8% | 100% | 2007-02-11 | no data | 2007-07-30 | 2008-02-28 | no data | 213 | 419 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Afus | 126316017 | School Building 3 Classroom | 1 | 857862.86 | 670111.98 | 187750.88 | 670111.98 | Grant 100% Released | 183331.88 | 853443.86 | 670111.98 | 183331.88 | 100% | 100% | 97.65% | 99.48% | 100% | 2005-06-03 | 2005-08-04 | 2005-10-26 | 2006-04-30 | 2006-05-02 | 186 | 204 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Afus | 126316017 | Road Improvement | 1 | 685565.45 | 290455 | 395110.45 | 281121.4 | Second Tranche | 135238.45 | 416359.85 | 281121.4 | 135238.45 | 100% | 100% | 34.23% | 60.73% | 100% | 2007-04-26 | 2007-05-26 | 2007-10-23 | 2008-09-30 | n/a | 343 | 204 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Basag | 126316001 | Road Improvement | 1 | 6276175.27 | 1994197.6 | 4281977.67 | 1994197.6 | Grant 100% Released | 5203360.83 | 7197558.43 | 1994197.6 | 5203360.83 | 100% | 100% | 121.5% | 114.7% | 100% | 2005-05-30 | 2005-08-02 | 2005-11-25 | 2007-05-31 | 2007-05-02 | 552 | 173 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Datal Bob | 126316025 | 2 Classroom School Building | 1 | 1061640.9 | 838673.55 | 222967.35 | 838673.55 | First Tranche | 147667.35 | 986340.9 | 838673.55 | 147667.35 | 100% | 100% | 66.23% | 92.91% | 100% | 2007-04-26 | 2007-05-26 | 2007-09-25 | 2009-07-31 | n/a | 675 | 300 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Dlanag | 126316027 | School Building 2 Classroom | 1 | 930043.19 | 756453.83 | 173589.36 | 756453.83 | Grant 100% Released | 187439.36 | 943893.19 | 756453.83 | 187439.36 | 100% | 100% | 108% | 101.5% | 100% | 2005-06-03 | 2005-08-04 | 2005-11-01 | 2006-08-31 | 2006-05-02 | 303 | 410 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Desawo | 126316026 | Health Station | 1 | 761806.42 | 621714.51 | 140091.91 | 621714.51 | Grant 100% Released | 112738.07 | 734452.58 | 621714.51 | 112738.07 | 100% | 100% | 80.47% | 96.41% | 100% | 2005-06-03 | 2005-08-04 | 2005-11-11 | 2006-05-19 | 2006-05-19 | 189 | 818 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Edwards | 126316002 | Water System | 1 | 2006518.75 | 1554400 | 452118.75 | 1554400 | Grant 100% Released | 374621.25 | 1929021.25 | 1554400 | 374621.25 | 100% | 100% | 82.86% | 96.14% | 100% | 2006-03-28 | 2006-06-06 | 2006-11-15 | 2007-05-31 | 2007-08-07 | 197 | 165 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Lambangan | 126316014 | Water System | 1 | 1560745 | 1098166 | 462579 | 1070591.8 | Third Tranche | 367694 | 1438285.8 | 1070591.8 | 367694 | 100% | 100% | 79.49% | 92.15% | 100% | 2006-03-31 | 2006-06-06 | 2006-11-27 | 2007-06-30 | n/a | 215 | 299 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Lambuling | 126316018 | Road Improvement | 1 | 1950345 | 879344 | 1071001 | 879344 | Third Tranche | 1042201 | 1921545 | 879344 | 1042201 | 100% | 100% | 97.31% | 98.52% | 100% | 2006-03-31 | 2006-06-06 | 2006-11-15 | 2007-09-30 | n/a | 319 | 400 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Lambuling | 126316018 | R.C. Overflow Bridge | 1 | 704386.91 | 497110 | 207276.91 | 497110 | Second Tranche | 86365.91 | 583475.91 | 497110 | 86365.91 | 100% | 100% | 41.67% | 82.83% | 100% | 2007-04-26 | 2007-05-26 | 2008-03-20 | 2008-10-24 | n/a | 218 | 400 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Lamsalome | 126316008 | 2- Classroom School Building | 1 | 1061640.9 | 702639 | 359001.9 | 702639 | First Tranche | 143774.9 | 846413.9 | 702639 | 143774.9 | 100% | 100% | 40.05% | 79.73% | 100% | 2007-04-26 | 2007-05-26 | 2007-10-01 | 2008-10-31 | n/a | 396 | 250 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Lemsnolon | 126316028 | 2 Classroom School Building | 1 | 1047452 | 738970 | 308482 | 738970 | First Tranche | 192713 | 931683 | 738970 | 192713 | 100% | 100% | 62.47% | 88.95% | 100% | 2007-04-26 | 2007-05-26 | 2007-09-20 | 2008-06-30 | 2008-12-15 | 284 | 495 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Maan | 126316016 | Road Improvement | 1 | 5489069.79 | 1449148.7 | 4039921.09 | 1449148.7 | Grant 100% Released | 3027896.5 | 4477045.2 | 1449148.7 | 3027896.5 | 100% | 100% | 74.95% | 81.56% | 100% | 2005-05-30 | 2005-08-02 | 2005-11-17 | 2007-02-28 | no data | 468 | 660 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Mongocayo | 126316030 | Overflow Bridge | 1 | 1180516 | 730257 | 450259 | 657231.3 | Third Tranche | 370575 | 1027806.3 | 657231.3 | 370575 | 100% | 100% | 82.3% | 87.06% | 100% | 2006-03-31 | 2006-06-06 | 2006-12-19 | 2007-06-30 | n/a | 193 | 319 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | New Dumangas | 126316011 | 3CL School Bldg | 1 | 1384537.1 | 1025479.18 | 359057.92 | 1025479.18 | First Tranche | 249132.92 | 1274612.1 | 1025479.18 | 249132.92 | 100% | 100% | 69.39% | 92.06% | 100% | 2007-04-26 | 2007-05-26 | 2007-10-01 | 2009-07-31 | n/a | 669 | 700 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Poblacion | 126316020 | Construction 1CL school building | 1 | 321000 | 300000 | 21000 | 300000 | Grant 100% Released | 21000 | 321000 | 300000 | 21000 | 100% | 100% | 100% | 100% | 100% | n/a | n/a | 2006-06-14 | 2006-10-31 | 2006-01-26 | 139 | 735 | Award from National Stakeholders Conference | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Poblacion | 126316020 | 3CL School Bldg | 1 | 1330267.5 | 974778 | 355489.5 | 974778 | Grant 100% Released | 325214.5 | 1299992.5 | 974778 | 325214.5 | 100% | 100% | 91.48% | 97.72% | 100% | 2006-03-28 | 2006-06-06 | 2006-10-15 | 2007-03-28 | 2007-08-07 | 164 | 960 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Poblacion | 126316020 | 3- Classroom School Bldg. | 1 | 1384537.28 | 1014828 | 369709.28 | 1014828 | First Tranche | 192082.78 | 1206910.78 | 1014828 | 192082.78 | 100% | 100% | 51.96% | 87.17% | 100% | 2007-04-26 | 2007-05-26 | 2007-10-14 | 2008-06-30 | 2008-12-15 | 260 | 735 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Salacafe | 126316031 | Water System | 1 | 1797605.5 | 1370822 | 426783.5 | 1233739.8 | Third Tranche | 198727 | 1432466.8 | 1233739.8 | 198727 | 100% | 100% | 46.56% | 79.69% | 100% | 2006-03-28 | 2006-06-06 | 2006-11-18 | 2007-09-30 | n/a | 316 | 244 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Sinolon | 126316012 | Water System (Pump Driven) | 1 | 1668329.34 | 1340463 | 327866.34 | 1206416.7 | Second Tranche | 276791.34 | 1483208.04 | 1206416.7 | 276791.34 | 100% | 100% | 84.42% | 88.9% | 100% | 2007-04-26 | 2007-05-26 | 2007-11-03 | 2008-09-30 | 2009-02-15 | 332 | 495 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Talcon | 126316021 | 2CL School Bldg. | 1 | 1065862.9 | 798138.4 | 267724.5 | 798138.4 | Grant 100% Released | 247574.5 | 1045712.9 | 798138.4 | 247574.5 | 100% | 100% | 92.47% | 98.11% | 100% | 2006-03-31 | 2006-06-06 | 2006-11-22 | 2007-06-30 | 2007-12-27 | 220 | 150 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | Talufo | 126316022 | Flashflood Control | 1 | 1245563.25 | 845375.7 | 400187.55 | 760838.13 | Second Tranche | 322512.55 | 1083350.68 | 760838.13 | 322512.55 | 100% | 100% | 80.59% | 86.98% | 100% | 2007-04-26 | 2007-05-26 | 2007-12-01 | 2009-02-28 | n/a | 455 | 186 |  | 1 | MINDANAO
XII | 12 | South Cotabato | 1263 | T'boli | 126316 | T'bolok | 126316032 | Road Improvement | 1 | 3786824.71 | 1819776.1 | 1967048.61 | 1819776.1 | Grant 100% Released | 1579812.03 | 3399588.13 | 1819776.1 | 1579812.03 | 100% | 100% | 80.31% | 89.77% | 100% | 2005-06-03 | 2005-08-04 | 2005-11-28 | 2007-03-28 | no data | 485 | 130 |  | 1 | MINDANAO
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Datablao | 126502009 | 4 unit - Solar Dryer w/ 1 unit mech'l. dryer & machine faclities | 1 | 1429433.75 | 1029000 | 400433.75 | 926100 |  | 377793.75 | 1303893.75 | 926100 | 377793.75 | 100% | 100% | 94.35% | 91.22% | 100% | 2007-11-27 | no data | 2009-03-02 | 2009-06-30 | n/a | 120 | 270 |  | 1 | MINDANAO
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Eday | 126502010 | 2 CL School Building (Elementary) with Amenities | 1 | 1140047 | 831094 | 308953 | 810544.74 | Third Tranche | 321303 | 1131847.74 | 810544.74 | 321303 | 100% | 100% | 104% | 99.28% | 100% | 2007-04-10 | no data | 2007-10-15 | 2008-06-23 | no data | 252 | 98 |  | 1 | MINDANAO
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Elbebe | 126502011 | Solar Dryer w/ Warehouse | 1 | 882499 | 671960 | 210539 | 604764 |  | 200717.75 | 805481.75 | 604764 | 200717.75 | 100% | 100% | 95.34% | 91.27% | 100% | 2007-11-27 | no data | 2009-04-06 | 2009-06-30 | n/a | 85 | 80 |  | 1 | MINDANAO
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Lasak | 126502032 | Solar Dryer w/ Warehouse w/ CornMill | 1 | 1570593.75 | 1099410 | 471183.75 | 1094098.72 |  | 416403.75 | 1510502.47 | 1094098.72 | 416403.75 | 100% | 100% | 88.37% | 96.17% | 100% | 2007-11-27 | no data | 2009-06-30 | 2009-08-31 | n/a | 62 | 144 |  | 1 | MINDANAO
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Libertad | 126502015 | Health Center | 1 | 599818 | 435658 | 164160 | 431554.62 | First Tranche | 165310 | 596864.62 | 431554.62 | 165310 | 100% | 100% | 100.7% | 99.51% | 100% | 2008-01-10 | no data | 2008-07-18 | 2009-01-31 | n/a | 197 | 500 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Lomoyon | 126502016 | Road Construction | 1 | 2976254 | 947724 | 2028530 | 852951.6 | Third Tranche | 1811681 | 2664632.6 | 852951.6 | 1811681 | 100% | 100% | 89.31% | 89.53% | 100% | 2007-04-10 | no data | 2007-08-10 | 2008-08-31 | n/a | 387 | 234 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Makat | 126502017 | Solar Dryer w/ Warehouse & Mini Milling w/ Machine Facilities | 1 | 1006058 | 722511 | 283547 | 720961.54 | Third Tranche | 310342 | 1031303.54 | 720961.54 | 310342 | 100% | 100% | 109.4% | 102.5% | 100% | 2007-04-10 | no data | 2007-09-07 | 2008-04-12 | 2008-04-15 | 218 | 70 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Maligaya | 126502019 | Day Care Center | 1 | 608742 | 449612 | 159130 | 437145.51 | Second Tranche | 165745 | 602890.51 | 437145.51 | 165745 | 100% | 100% | 104.2% | 99.04% | 100% | 2008-01-10 | no data | 2008-07-01 | 2008-12-29 | n/a | 181 | 227 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Mayo | 126502021 | Spring Development | 1 | 1750730 | 1144605 | 606125 | 1121762.72 | Second Tranche | 400565 | 1522327.72 | 1121762.72 | 400565 | 100% | 100% | 66.09% | 86.95% | 100% | 2008-01-10 | no data | 2008-05-01 | 2009-04-30 | n/a | 364 | 240 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Natividad | 126502022 | Solar Dryer w/ Warehouse | 1 | 1251825.75 | 916842 | 334983.75 | 916842 |  | 323623.75 | 1240465.75 | 916842 | 323623.75 | 100% | 100% | 96.61% | 99.09% | 100% | 2007-11-27 | no data | 2009-02-10 | 2009-04-30 | n/a | 79 | 160 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Bantangan | 126502002 | Solar Drier with Warehouse | 1 | 1246575 | 894250 | 352325 | 885743.34 | First Tranche | 308020 | 1193763.34 | 885743.34 | 308020 | 100% | 100% | 87.42% | 95.76% | 100% | 2008-01-10 | no data | 2008-08-08 | 2009-01-31 | n/a | 176 | 312 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Poblacion | 126502023 | Road Improvement | 1 | 1840893.75 | 1404740 | 436153.75 | 1264266 |  | 435333.75 | 1699599.75 | 1264266 | 435333.75 | 100% | 100% | 99.81% | 92.32% | 100% | 2007-11-27 | no data | 2009-02-12 | 2009-06-30 | n/a | 138 | 300 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Polomolok | 126502024 | Road Construction | 1 | 2949153 | 2256041 | 693112 | 2070808.2 | First Tranche | 682787 | 2753595.2 | 2070808.2 | 682787 | 100% | 100% | 98.51% | 93.37% | 100% | 2007-04-10 | no data | 2008-01-07 | 2008-09-30 | n/a | 267 | 239 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Sinapulan | 126502027 | Double Barrel Box Culvert | 1 | 892020 | 650000 | 242020 | 641815 | Second Tranche | 371390 | 1013205 | 641815 | 371390 | 100% | 100% | 153.5% | 113.6% | 100% | 2008-01-10 | no data | 2008-09-08 | 2009-07-31 | n/a | 326 | 287 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Sucob | 126502028 | Spring Development | 1 | 830655 | 610000 | 220655 | 603664.36 | Second Tranche | 252295 | 855959.36 | 603664.36 | 252295 | 100% | 100% | 114.3% | 103% | 100% | 2008-01-10 | no data | 2008-08-11 | 2009-06-30 | n/a | 323 | 220 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Telafas | 126502030 | Solar Drier with Warehouse | 1 | 866284 | 624875 | 241409 | 619035.64 | Second Tranche | 222310 | 841345.64 | 619035.64 | 222310 | 100% | 100% | 92.09% | 97.12% | 100% | 2008-01-10 | no data | 2008-08-15 | 2009-01-31 | n/a | 169 | 488 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Antong | 126507001 | Health Station | 1 | 710887.8 | 488796.74 | 222091.06 | 461000.18 | First Tranche | 209241.06 | 670241.24 | 461000.18 | 209241.06 | 100% | 100% | 94.21% | 94.28% | 100% | 2007-04-19 | no data | 2007-10-03 | 2007-12-14 | 2008-12-17 | 72 | 326 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Bayasong | 126507002 | Health Station | 1 | 886090.57 | 571091 | 314999.57 | 571091 | Grant 100% Released | 330349.57 | 901440.57 | 571091 | 330349.57 | 100% | 100% | 104.9% | 101.7% | 100% | 2005-04-19 | 2005-06-02 | 2005-07-31 | 2005-12-30 | 2006-02-17 | 152 | 488 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Blingkong | 126507003 | Expansion HS with Facilities | 1 | 979860 | 630258.02 | 349601.98 | 630258.02 | Grant 100% Released | 356866.98 | 987125 | 630258.02 | 356866.98 | 100% | 100% | 102.1% | 100.7% | 100% | 2006-03-16 | 2006-04-28 | 2006-08-14 | 2007-01-30 | 2007-04-25 | 169 | 782 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Lutayan Proper | 126507003 | Water Sysytem Level II (Submersible) | 1 | 3929212.7 | 2167972 | 1761240.7 | 2167972 | Grant 100% Released | 1853587.33 | 4021559.33 | 2167972 | 1853587.33 | 100% | 100% | 105.2% | 102.4% | 100% | 2005-04-19 | 2005-06-02 | 2005-08-10 | 2006-06-30 | 2006-08-14 | 324 | 818 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Lutayan Proper | 126507003 | Construction of Two Units Communal Toilet | 1 | 430607.17 | 288197.05 | 142410.12 | 288197.04 | #DIV/0! | 120919.8 | 409116.84 | 288197.04 | 120919.8 | 100% | 100% | 84.91% | 95.01% | 100% | 2007-04-19 | no data | 2007-11-17 | 2008-09-30 | 2008-10-27 | 318 | 719 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Maindang | 126507005 | Rural Electrification | 1 | 2803564.98 | 1166109.73 | 1637455.25 | 1166109.73 | Grant 100% Released | 1636205.05 | 2802314.78 | 1166109.73 | 1636205.05 | 100% | 100% | 99.92% | 99.96% | 100% | 2006-03-16 | 2006-04-28 | 2006-12-01 | 2007-08-02 | 2007-08-06 | 244 | 429 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Mamali | 126507006 | Rural Electrification | 1 | 1546274.37 | 694038.64 | 852235.73 | 694038.64 | Grant 100% Released | 852889.5 | 1546928.14 | 694038.64 | 852889.5 | 100% | 100% | 100.1% | 100% | 100% | 2006-03-16 | 2006-04-28 | 2006-12-01 | 2007-08-02 | 2007-08-06 | 244 | 392 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Manili | 126507007 | Water System Level I (Hand Pumps) | 1 | 400980.84 | 374958.78 | 26022.06 | 337462.9 | Second Tranche | 184300 | 521762.9 | 337462.9 | 184300 | 100% | 100% | 708.2% | 130.1% | 100% | 2007-04-19 | no data | 2007-09-24 | 2007-11-24 | 2007-11-29 | 61 | 392 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Palavilla | 126507011 | Rehab. Of FMR | 1 | 2737361.39 | 809593.61 | 1927767.78 | 728634.26 | Third Tranche | 1678627.71 | 2407261.97 | 728634.26 | 1678627.71 | 100% | 100% | 87.08% | 87.94% | 100% | 2006-03-16 | 2006-04-28 | 2006-08-21 | 2008-03-28 | n/a | 585 | 557 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Sampao | 126507008 | Water System Level II (Spring Source) | 1 | 2346748.39 | 1630355.79 | 716392.6 | 1630355.79 | First Tranche | 532130.59 | 2162486.38 | 1630355.79 | 532130.59 | 100% | 100% | 74.28% | 92.15% | 100% | 2007-04-19 | n/a | 2008-03-24 | 2009-06-30 | n/a | 463 | 323 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Sisiman | 126507009 | Rural Electrification | 1 | 1249387.29 | 533413.29 | 715974 | 533413.29 | Grant 100% Released | 716199 | 1249612.29 | 533413.29 | 716199 | 100% | 100% | 100% | 100% | 100% | 2005-04-19 | 2005-06-02 | 2005-11-12 | 2006-01-23 | 2006-01-26 | 72 | 173 |  | 1
XII | 12 | Sultan Kudarat | 1265 | Lutayan | 126507 | Tamnag | 126507010 | Construction of Day Care Center | 1 | 690263.71 | 422341.46 | 267922.25 | 385152.14 | First Tranche | 164938.46 | 550090.6 | 385152.14 | 164938.46 | 100% | 100% | 61.56% | 79.69% | 100% | 2007-04-19 | no data | 2007-11-09 | 2008-10-31 | 2009-02-25 | 357 | 212 |  | 1
V | 05 | Albay | 0505 | Jovellar | 050505 | Salvacion | 050505019 | Rehab./Improvement of Farm to Market Road | 5 | 3689609 | 2717280 | 972329 | 2717280 | 3/3 | 974391.98 | 3691671.98 | 2717280 | 974391.98 | 100% | 100% | 100.2% | 100.1% | 100% | 2003-12-04 | 2004-03-23 | 2004-07-07 | 2005-04-13 | 2005-04-14 | 280 | 874 | Inaugurated | 1 | VISAYAS
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Poblacion (Suba) | 084822019 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Poblacion 2 | 084822025 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Poblacion 1 | 084822024 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Genagasan | 084822014 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | San Antonio | 084822026 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Giguimitan | 084822013 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Balud | 084822001 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Tobgon | 084822022 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Montalban | 084822018 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Cagda-o | 084822004 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Cababayugon | 084822002 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Cabunga-an | 084822003 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Gebolwagan | 084822011 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Caghilot | 084822005 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Gecbo-an | 084822012 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Camaya-an | 084822007 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Imelda | 084822017 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Deit De Turag | 084822009 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Camanggaran | 084822006 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Geparayan de Turag | 084822015 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Victory | 084822023 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Northern Samar | 0848 | Silvino Lobos | 084822 | Deit de Suba | 084822008 | Rehabilitation/Improvement Cagpanit-an - Poblacion Road | 23 | 11378436 | 7234191 | 4144245 | 3617095.5 | 2nd Tranche | 398149.99 | 3857087.49 | 3617095.5 | 239991.99 | 100% | 60.28% | 9.607% | 33.9% | 100% | 2006-09-27 | 2006-09-28 | 2006-09-01 | 2007-07-31 | n/a | 333 | 89 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Lam- awan | 086021013 | Road Improvement | 3 | 5470000 | 3829000 | 1641000 | 1914500 | 1st Tranche | 764719 | 2679219 | 1914500 | 764719 | 100% | 100% | 46.6% | 48.98% | 100% | no data | no data | 2009-03-30 | 2009-11-30 | n/a | 245 | 230 |  | 1 | MINDANAO
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Canmucat | 086021005 | Road Improvement | 3 | 5470000 | 3829000 | 1641000 | 1914500 | 1st Tranche | 764719 | 2679219 | 1914500 | 764719 | 100% | 100% | 46.6% | 48.98% | 100% | no data | no data | 2009-03-30 | 2009-11-30 | n/a | 245 | 230 |  | 1 | MINDANAO
Note on N4: adjusted based on finance data
Note on P4: adjusted based on finance data
Note on R4: adjusted based on finance data
Note on S4: adjusted based on finance data
Note on G7: Abaquid Danglas
Note on L7: LAI: To source out 159,301.72 in order to avail of the left-over fund
Note on G8: Abaquid Danglas
Note on L8: LAI: To source out 159,301.72 in order to avail of the left-over fund
Note on P9: previously reported as 122,192.97
Note on S9: previously reported as 65,914.83
Note on X11: Completed as built (actual 70%)
Note on L15: not included in the reported figure as of December 2008. Data was only available January 2009
Note on M15: not included in the reported figure as of December 2008. Data was only available January 2009
Note on R17: previously reported as 681,075
Note on G19: Cabayogan Dalimag
Note on G20: Cabayogan Dalimag
Note on R23: higher than the grant released?
Note on R38: higher than the grant released?
Note on G40: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G41: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G42: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G43: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G44: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G45: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G46: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibakan 5.Anayan 6.Balaat 7.Cogon
Note on G47: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X47: peace and order (political)
Note on G48: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X48: peace and order (political)
Note on G49: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X49: peace and order (political)
Note on G50: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X50: peace and order (political)
Note on G51: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X51: peace and order (political)
Note on G52: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X52: peace and order (political)
Note on G53: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X53: peace and order (political)
Note on G54: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X54: peace and order (political)
Note on G55: Clustered Brgys: 1.Agsimao 2.Alaoa 3.Lapat-Balantay 4.Naglibacan 5.Anayan 6.Belaat 7.Cogon 8.Caganayan 9.Lanec
Note on X55: peace and order (political)
Note on G64: Clustered Brgys: 1.Camandag 2.Duli
Note on G65: Clustered Brgys: 1.Pula 2.Cawayan 3.Duli 4.Natcak 5.Camandag
Note on G66: Clustered Brgys: 1.Cawayan 2.Pula
Note on G67: Clustered Brgys: 1.Pula 2.Cawayan 3.Duli 4.Natcak 5.Camandag
Note on G69: Clustered Brgys: 1.Camandag 2.Duli
Note on G70: Clustered Brgys: 1.Pula 2.Cawayan 3.Duli 4.Natcak 5.Camandag
Note on G74: Clustered Brgys: 1.Liwon 2.Namal 3.Nampaling
Note on G77: Clustered Brgys: 1.Liwon 2.Namal 3.Nampaling
Note on G79: Clustered Brgys: 1.Liwon 2.Namal 3.Nampaling
Note on G81: Clustered Brgys: 1.Pula 2.Cawayan 3.Duli 4.Natcak 5.Camandag
Note on G93: Clustered Brgys: 1.Cawayan 2.Pula
Note on G94: Clustered Brgys: 1.Pula 2.Cawayan 3.Duli 4.Natcak 5.Camandag
Note on G119: Clustered Brgys: 1.Tulludan 2.Ahin
Note on G120: Clustered Brgys: 1.Tulludan 2.Ahin
Note on G123: Kalahi: 1. Ap-apid 2. Gumhang
Note on G124: Kalahi: 1. Ap-apid 2. Gumhang
Note on G129: Clustered Brgys: 1.Luhong 2.Dango
Note on G130: Clustered Brgys: 1.Luhong 2.Dango
Note on G140: Kalahi: 1. Tukucan 2. Eheb
Note on G141: Kalahi: 1. Tukucan 2. Eheb
Note on L147: P72,963.00 to be sourced out
Note on R172: previously reported as 426,102.14
Note on AB178: assumption only (no data)
Note on R180: previously reported as 421,234.20
Note on X191: actual 60% completed as built
Note on X198: delayed delivery of lcc due to election ban Completed as built 50% actual physical accomplishment
Note on X199: completed as built
Note on X201: problem in technical feasibility (water source lower)
Note on X209: completed as built actual 68%
Note on AB264: assumption only (no data)
Note on G397: Clustered Brgys: 1.Mahapag 2.Santiago
Note on G398: Clustered Brgys: 1.Mahapag 2.Santiago
Note on G425: Sto. Niño San Isidro
Note on E428: Stata_User01: Province of Libjo is Dinagat Island
Note on G450: Asinan Centro Punta Pilaring Dayaohay Consolacion
Note on G451: Asinan Centro Punta Pilaring Dayaohay Consolacion
Note on L505: User: w/ adjustment of 15,000. as per POW / MIBF. 15,000 transferred to LCC
Note on AB530: Central Office Engineering data
Note on G576: Clustered Brgys: 1.Masaya 2.Villa Aurora
Note on G577: Clustered Brgys: 1.Masaya 2.Villa Aurora
Note on G699: Clustered Brgys: 1.Kilogan 2.Luod 3.Patnanungan Sur 4.Patnanungan Norte
Note on N795: august 2008 report it was already 318,066.27
Note on G796: Clustered Brgys: 1.Poblacion 1 2.Poblacion 2
Note on X813: adjusted as per engineering data
Note on N859: as of august 2008 report it was already 791,323.08
Note on G868: Clustered Brgys: 1.Cambijang 2.Poblacion
Note on G869: Clustered Brgys: 1.Cambijang 2.Poblacion
Note on G904: Clustered Brgys: 1.Dipopor 2.Rambon
Note on G905: Clustered Brgys: 1.Dipopor 2.Rambon
Note on G916: Clustered Brgys: 1.Sianan 2.Lomogon
Note on X960: Aggregate sub-base course reduction due to continous landslide during implementation and portion of gravelling cost of the sub-project has been utilized for it. Constant change of leadership which has affected delivery of LCC
Note on X1051: Relocation of road pavement to be cemented due to collapse road section during implementation caused by typhoon and heavy rains (force majeur)
Note on G1128: Kanipaan Supon
Note on G1142: Kanipaan Supon
Note on G1179: Clustered Brgys: 1.Canibingan 2.Guintanan
Note on X1180: Due to increase of excavation work and delayed delivery of LCC, as well as heavy equipments were non-operational for a period of time
Note on X1188: Due to increase of excavation work and delayed delivery of LCC, as well as heavy equipments were non-operational for a period of time
Note on G1190: Last month It was reported as Multi purpose building
Note on I1190: KALAHI-CIDSS: last month: Const. of MPB correct SP title: Const. of Health Station
Note on X1197: Due to increase of excavation work and delayed delivery of LCC, as well as heavy equipments were non-operational for a period of time
Note on G1201: Last month it was reported as water system
Note on G1215: last month It was reported as day care
Note on I1215: Procurement Servic Last month: Day Care; (Correct SP name: Health Station)
Note on I1341: KALAHI-CIDSS: last month: const. of MP Building; correct SPT: MP pavement
Note on X1399: Reduction of length of the wharf due to change of location
Note on G1414: Balogo Talaptap
Note on G1415: Balogo Talaptap
Note on E1442: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on Z1443: 1 MIBF concept conducted last May 7, 2008
Note on Z1444: May 2-7, 2008
Note on Z1445: May 2-7, 2008
Note on E1446: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on Z1447: 1 MIBF concept conducted last May 7, 2008
Note on Z1448: May 2-7, 2008
Note on Z1449: May 2-7, 2008
Note on E1450: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on Z1451: 1 MIBF concept conducted last May 7, 2008
Note on Z1452: May 2-7, 2008
Note on E1453: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on Z1454: May 2-7, 2008
Note on Z1455: 1 MIBF concept conducted last May 7, 2008
Note on Z1456: May 2-7, 2008
Note on Z1457: May 2-7, 2008
Note on Z1458: 1 MIBF concept conducted last May 7, 2008
Note on E1459: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on Z1460: 1 MIBF concept conducted last May 7, 2008
Note on E1461: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on Z1462: May 2-7, 2008
Note on Z1463: 1 MIBF concept conducted last May 7, 2008
Note on Z1464: 1 MIBF concept conducted last May 7, 2008
Note on Z1465: May 2-7, 2008
Note on Z1466: 1 MIBF concept conducted last May 7, 2008
Note on Z1467: May 2-7, 2008
Note on Z1468: May 2-7, 2008
Note on Z1469: May 2-7, 2008
Note on Z1470: 1 MIBF concept conducted last May 7, 2008
Note on E1471: changes in the amount of TPC supported by Revised Special MIBF resolution
Note on G1476: Clustered Brgys: 1.Quintinday 2.Rizal
Note on G1477: Clustered Brgys: 1.Quintinday 2.Rizal
Note on G1478: Clustered Brgys: 1.San Vicente 2.Bautista 3.Bagacay
Note on G1479: Clustered Brgys: 1.San Vicente 2.Bautista 3.Bagacay
Note on G1480: Clustered Brgys: 1.San Vicente 2.Bautista 3.Bagacay
Note on G1482: Clustered Brgys: 1.Villa Paz 2.Bagacay 3.San Vicente 4.Bautista 5.Maogog
Note on G1483: Clustered Brgys: 1.Villa Paz 2.Bagacay 3.San Vicente 4.Bautista 5.Maogog
Note on G1484: Clustered Brgys: 1.White Deer 2.San Isidro 3.San Roque 4.Del Rosario
Note on G1485: Clustered Brgys: 1.White Deer 2.San Isidro 3.San Roque 4.Del Rosario
Note on G1486: Clustered Brgys: 1.White Deer 2.San Isidro 3.San Roque 4.Del Rosario
Note on G1487: Clustered Brgys: 1.White Deer 2.San Isidro 3.San Roque 4.Del Rosario
Note on G1488: Clustered Brgys: 1.White Deer 2.Salvacion 3.San Isidro 4.San Roque 5.Del Rosario
Note on G1494: Purely LCC - to comply with the 30% LCC of the Municipality
Note on G1496: Macabugcos Tambo
Note on G1497: Clustered Brgys: 1.Magalang 2.Bonbon
Note on G1498: Clustered Brgys: 1.Magalang 2.Bonbon
Note on X1504: damaged due to heavy rains
Note on G1505: Clustered Brgys: 1.Sampongan 2.Malabiga
Note on G1506: Clustered Brgys: 1.Sampongan 2.Malabiga
Note on G1508: Clustered Brgys: 1.San Pascual 2.Salvacion 3.Matara
Note on G1509: Clustered Brgys: 1.San Pascual 2.Salvacion 3.Matara
Note on G1510: Clustered Brgys: 1.San Pascual 2.Salvacion 3.Matara
Note on I1525: mmingoy: actual - Day Care Center
Note on X1532: as built 98.78% contractor backed out, SPI was continued through CFA
Note on X1536: 85% contractor backed out, SPI was continued through CFA
Note on X1561: The source of water was changed during SPI
Note on X1573: funds for labor used up, not enough funds to complete SP as planned
Note on I1590: mmingoy: validated as sea wall
Note on X1594: damaged by rains
Note on G1595: mmingoy: Itok Lukabanan
Note on I1598: mmingoy: validated as rice mill with solar dryer
Note on I1599: mmingoy: school building
Note on I1606: mmingoy: validated as foot bridge
Note on G1639: mmingoy: Luluasan was replaced by Montenegro
Note on X1660: damaged by bad weather
Note on G1675: Burabod Cagamutan
Note on X1686: access to the SP was damaged due to heavy rains, contractor backed out and SPI resumed by CFA
Note on X1706: The depth of the canal was increased to 2.5 meters to contain the flooding in the area
Note on A1732: mmingoy: finalized cost sharing to be submitted
Note on X1777: damaged by bad weather/contract was terminated due to delay in the implementation
Note on X1780: damaged by bad weather/contract was terminated due to delay in the implementation
Note on G1817: mmingoy: Tandoc, Tonggo and Homestead
Note on G1818: mmingoy: Tandoc, Tonggo and Homestead
Note on G1820: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1821: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1822: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1828: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1829: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1834: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1836: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1837: Bagatabao Antipolo Bacak Poblacion Quezon San Rafael Sta. Mesa Sta. Teresa
Note on G1838: previously reported as Hinipaan
Note on G1839: Baybay Toytoy Bothoan Icanbato
Note on Y1839: July 15-16, 2006
Note on G1840: Baybay Toytoy Bothoan Icanbato
Note on Y1840: July 15-16, 2006
Note on G1841: Baybay Toytoy Bothoan Icanbato
Note on Y1841: July 15-16, 2006
Note on G1850: Clustered Brgys: 1.Datag East 2.Supang
Note on G1851: Clustered Brgys: 1.Datag East 2.Supang
Note on X1872: damaged by typhoon during SPI; materials were washed away by storm surge
Note on X1913: contractor backed out, SPI was continued through CFA
Note on G1941: Clustered Brgys: 1.Pinanaan 2.Syndicate
Note on G1956: Clustered Brgys: 1.Pinanaan 2.Syndicate
Note on Y1986: November 27-28, 2003
Note on Y1987: November 27-28, 2003
Note on Y1990: November 27-28, 2003
Note on Y1991: November 27-28, 2003
Note on Y1992: July 7-8, 2005
Note on Y1995: July 7-8, 2005
Note on X1998: did not request remaining tranche, physical accomplishment not met within the timeline
Note on Y1999: July 7-8, 2005
Note on Y2000: July 7-8, 2005
Note on Y2002: November 27-28, 2003
Note on Y2006: November 27-28, 2003
Note on Y2007: July 7-8, 2005
Note on Y2008: July 7-8, 2005
Note on X2055: instead of 2 meters width at 300 meters length, the community opted for 1 meter by 600 meter length concreting in the FMR
Note on X2085: counterpart (equipment) not provided by the PLGU as planned
Note on X2086: counterpart (equipment) not provided by the PLGU as planned
Note on X2093: counterpart (equipment) not provided by the PLGU as planned
Note on Y2094: May 15-16, 2008
Note on L2095: before 998,910
Note on M2095: previously reported as 368,413
Note on Y2095: May 15-16, 2008
Note on Y2097: July 6-7, 2007
Note on Y2099: July 6-7, 2007
Note on Y2101: May 15-16, 2008
Note on Y2104: July 6-7, 2007
Note on Y2105: July 6-7, 2007
Note on Y2107: July 6-7, 2007
Note on Y2108: July 6-7, 2007
Note on Y2111: July 6-7, 2007
Note on G2113: Sipaya Calateo
Note on L2113: before 1,389,763
Note on Y2113: May 15-16, 2008
Note on G2114: Sipaya Calateo
Note on Y2115: July 6-7, 2007
Note on Y2117: July 6-7, 2007
Note on L2118: before 922,545
Note on Y2118: May 15-16, 2008
Note on L2119: before 2,064,202
Note on Y2119: May 15-16, 2008
Note on Y2120: May 15-16, 2008
Note on G2142: purely LCC - to comply with the 30% LCC committed by the MLGU
Note on G2147: Dao and San Jose was replaced by Mercedes
Note on Y2163: August 15-27, 2007
Note on X2164: aurea: 10.31.09 completed as built PA 8.30.09 - 75.00%
Note on Y2169: August 15-27, 2007
Note on X2173: aurea: 10.31.09 completed as built PA 8.30.09 - 86.00%
Note on Y2173: August 15-27, 2007
Note on Y2175: August 15-27, 2007
Note on X2177: aurea: 10.31.09 completed as built PA 8.30.09 - 86.00%
Note on Y2177: August 15-27, 2007
Note on Y2180: August 15-27, 2007
Note on Y2183: August 15-27, 2007
Note on Y2188: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2189: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2191: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2193: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2194: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2196: Kalahi Admin: July 5-7, 2005
Note on Y2198: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2200: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2201: Kalahi Admin: July 5-7, 2005
Note on Y2203: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2205: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2206: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2208: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2209: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2211: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2213: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2214: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2216: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2219: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2220: M&E:1st MIBF was conducted last January 17-19, 2004
Note on G2223: Clustered Brgys: 1.Lucero 2.Agbun-od
Note on Y2223: Kalahi Admin: July 5-7, 2005
Note on Y2224: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2225: Kalahi Admin: July 5-7, 2005
Note on Y2226: M&E:1st MIBF was conducted last January 17-19, 2004
Note on X2228: completed as built
Note on Y2229: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2230: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2232: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2233: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2234: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2235: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2238: Kalahi Admin: July 5-7, 2005
Note on Y2240: Kalahi Admin: July 5-7, 2005
Note on X2241: completed as built
Note on Y2242: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2243: Note:1st MIBF was conducted last July 6-7, 2006.
Note on Y2244: Kalahi Admin: July 5-7, 2005
Note on Y2246: August 1-2, 2007
Note on Y2248: August 1-2, 2007
Note on Y2251: August 1-2, 2007
Note on Y2253: August 1-2, 2007
Note on Y2255: August 1-2, 2007
Note on Y2257: August 1-2, 2007
Note on Y2259: August 1-2, 2007
Note on Y2261: August 1-2, 2007
Note on Y2265: August 1-2, 2007
Note on Y2266: August 1-2, 2007
Note on Y2268: August 1-2, 2007
Note on Y2269: August 1-2, 2007
Note on X2272: completed as built
Note on Y2272: November 21-22, 2007
Note on Y2273: November 21-22, 2007
Note on X2276: completed as built
Note on Y2276: November 21-22, 2007
Note on Y2277: July 16-17, 2008
Note on Y2278: July 16-17, 2008
Note on Y2280: July 16-17, 2008
Note on Y2282: July 16-17, 2008
Note on X2283: completed as built
Note on Y2283: July 16-17, 2008
Note on Y2284: November 21-22, 2007
Note on Y2289: November 21-22, 2007
Note on Y2291: July 16-17, 2008
Note on Y2292: November 21-22, 2007
Note on Y2294: July 16-17, 2008
Note on Y2299: July 16-17, 2008
Note on X2301: completed as built
Note on Y2301: November 21-22, 2007
Note on Y2302: November 21-22, 2007
Note on X2303: completed as built
Note on Y2303: November 21-22, 2007
Note on G2304: assumed Rizal Norte SP
Note on Y2305: July 16-17, 2008
Note on Y2306: November 21-22, 2007
Note on X2307: completed as built
Note on Y2307: November 21-22, 2007
Note on Y2308: November 21-22, 2007
Note on Y2309: November 21-22, 2007
Note on X2311: completed as built
Note on Y2311: November 21-22, 2007
Note on X2312: completed as built
Note on Y2312: July 16-17, 2008
Note on Y2313: November 21-22, 2007
Note on Y2314: July 16-17, 2008
Note on Y2316: July 16-17, 2008
Note on X2317: completed as built
Note on Y2318: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2320: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2321: Note:1st MIBF was conducted last July 12-13, 2006.
Note on X2322: completed as built
Note on Y2323: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2324: Kalahi Admin: August 3-5, 2005
Note on Y2326: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2327: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2328: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2329: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2330: Kalahi Admin: August 3-5, 2005
Note on Y2331: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2333: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2335: Kalahi Admin: August 3-5, 2005
Note on Y2337: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2338: Kalahi Admin: August 3-5, 2005
Note on Y2340: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2341: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2344: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2345: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2346: Kalahi Admin: August 3-5, 2005
Note on Y2348: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2349: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2350: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2351: Kalahi Admin: August 3-5, 2005
Note on Y2353: Kalahi Admin: August 3-5, 2005
Note on Y2355: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2356: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2359: Kalahi Admin: August 3-5, 2005
Note on Y2360: Note:1st MIBF was conducted last July 12-13, 2006.
Note on X2361: completed as built
Note on Y2362: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2363: Kalahi Admin: August 3-5, 2005
Note on Y2365: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2366: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2367: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2368: Kalahi Admin: August 3-5, 2005
Note on Y2369: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2371: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2372: Kalahi Admin: August 3-5, 2005
Note on Y2373: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2375: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2376: Note:1st MIBF was conducted last July 12-13, 2006.
Note on Y2377: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2378: Kalahi Admin: August 3-5, 2005
Note on Y2380: M&E:1st MIBF ws conducted last February 3-5, 2004
Note on Y2381: Kalahi Admin: August 3-5, 2005
Note on Y2383: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2384: M&E:1st MIBF was conducted last December 16-18, 2003
Note on X2385: 95% as built
Note on Y2386: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2387: Kalahi Admin: July 12-13, 2005
Note on X2388: 94% as built
Note on Y2389: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2390: Kalahi Admin: July 12-13, 2005
Note on G2391: Clustered Brgys: 1.Rizal 2.Dela Pena 3.San Miguel 4.Lipata 5.San Geronimo
Note on X2391: completed as built
Note on Y2391: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2392: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2393: Kalahi Admin: July 12-13, 2005
Note on Y2394: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2395: Kalahi Admin: July 12-13, 2005
Note on Y2396: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2397: Kalahi Admin: July 12-13, 2005
Note on G2398: Clustered Brgys: 1.Rizal 2.Dela Pena 3.San Miguel 4.Lipata 5.San Geronimo
Note on X2398: completed as built
Note on Y2398: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2399: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2400: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2401: Kalahi Admin: July 12-13, 2005
Note on Y2403: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2405: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2406: Kalahi Admin: July 12-13, 2005
Note on Y2407: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2409: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2410: Kalahi Admin: July 12-13, 2005
Note on G2412: Clustered Brgys: 1.Rizal 2.Dela Pena 3.San Miguel 4.Lipata 5.San Geronimo
Note on X2412: completed as built
Note on Y2412: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2413: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2414: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2415: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2416: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2417: Kalahi Admin: July 12-13, 2005
Note on G2418: Clustered Brgys: 1.Rizal 2.Dela Pena 3.San Miguel 4.Lipata 5.San Geronimo
Note on X2418: completed as built
Note on Y2418: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2419: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2420: Kalahi Admin: July 12-13, 2005
Note on Y2421: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2422: Kalahi Admin: July 12-13, 2005
Note on G2423: Clustered Brgys: 1.Rizal 2.Dela Pena 3.San Miguel 4.Lipata 5.San Geronimo
Note on X2423: completed as built
Note on Y2423: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2424: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2425: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2428: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2429: Note:1st MIBF was conducted last July 10-11, 2006.
Note on Y2430: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2431: M&E:1st MIBF was conducted last December 16-18, 2003
Note on Y2432: Kalahi Admin: July 12-13, 2005
Note on Y2433: M&E:1st MIBF was conducted last December 16-18, 2003
Note on X2436: completed as built
Note on X2437: completed as built
Note on Y2438: February 13-14, 2008
Note on Y2439: February 13-14, 2008
Note on Y2440: February 13-14, 2008
Note on X2441: completed as built
Note on Y2441: February 13-14, 2008
Note on Y2442: February 13-14, 2008
Note on X2444: completed as built
Note on X2445: completed as built
Note on Y2446: February 13-14, 2008
Note on X2447: completed as built
Note on Y2447: February 13-14, 2008
Note on Y2448: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2449: Kalahi Admin: August 9-12, 2005
Note on Y2450: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2451: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2452: Kalahi Admin: August 9-12, 2005
Note on Y2453: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2454: Kalahi Admin: August 9-12, 2005
Note on Y2455: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2456: Kalahi Admin: August 9-12, 2005
Note on Y2457: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2458: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2459: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2460: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2461: Kalahi Admin: August 9-12, 2005
Note on Y2462: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2463: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2464: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2465: M&E:1st MIBF was conducted last February 13-14, 2004
Note on G2466: Clustered Brgys: 1.Cahigon 2.Binolosan Pequeno 3.Supanga 4.Caratagan
Note on X2466: completed as built
Note on Y2466: M&E:1st MIBF was conducted last February 13-14, 2004
Note on G2467: Clustered Brgys: 1.Cahigon 2.Binolosan Pequeno 3.Supanga 4.Caratagan
Note on X2467: completed as built
Note on Y2467: M&E:1st MIBF was conducted last February 13-14, 2004
Note on G2468: Clustered Brgys: 1.Cahigon 2.Binolosan Pequeno 3.Supanga 4.Caratagan
Note on X2468: completed as built
Note on Y2468: M&E:1st MIBF was conducted last February 13-14, 2004
Note on G2469: Clustered Brgys: 1.Cahigon 2.Binolosan Pequeno 3.Supanga 4.Caratagan
Note on X2469: completed as built
Note on Y2469: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2470: Kalahi Admin: August 9-12, 2005
Note on Y2471: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2472: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2473: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2474: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2475: Kalahi Admin: August 9-12, 2005
Note on Y2476: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2477: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2478: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2479: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2480: Kalahi Admin: August 9-12, 2005
Note on Y2481: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2482: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2483: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2484: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2485: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2486: Note:1st MIBF was conducted last July 3-4, 2006.
Note on X2487: completed as built
Note on Y2487: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2488: Kalahi Admin: August 9-12, 2005
Note on Y2489: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2490: Kalahi Admin: August 9-12, 2005
Note on Y2491: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2492: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2493: Kalahi Admin: August 9-12, 2005
Note on Y2494: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2495: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2496: Kalahi Admin: August 9-12, 2005
Note on Y2497: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2498: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2499: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2500: Kalahi Admin: August 9-12, 2005
Note on Y2501: Kalahi Admin: August 9-12, 2005
Note on Y2502: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2503: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2504: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2505: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2506: Kalahi Admin: August 9-12, 2005
Note on Y2507: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2508: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2509: Kalahi Admin: August 9-12, 2005
Note on Y2510: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2511: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2512: Kalahi Admin: August 9-12, 2005
Note on Y2513: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2514: Kalahi Admin: August 9-12, 2005
Note on Y2515: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2516: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2517: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2518: Kalahi Admin: August 9-12, 2005
Note on Y2519: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2520: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2521: Kalahi Admin: August 9-12, 2005
Note on Y2522: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2523: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2524: Kalahi Admin: August 9-12, 2005
Note on Y2525: M&E:1st MIBF was conducted last February 13-14, 2004
Note on Y2526: Kalahi Admin: August 9-12, 2005
Note on Y2527: Note:1st MIBF was conducted last July 3-4, 2006.
Note on Y2528: Kalahi Admin: August 9-12, 2005
Note on Y2530: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2531: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2533: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2535: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2537: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2539: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2541: Kalahi Admin: August 9-12, 2005
Note on Y2542: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2544: Kalahi Admin: August 9-12, 2005
Note on Y2546: Kalahi Admin: August 9-12, 2005
Note on Y2549: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2550: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2551: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2553: Kalahi Admin: August 9-12, 2005
Note on Y2554: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2556: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2557: Kalahi Admin: August 9-12, 2005
Note on Y2558: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2559: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2560: Kalahi Admin: August 9-12, 2005
Note on Y2562: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2563: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2566: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2567: Kalahi Admin: August 9-12, 2005
Note on Y2568: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2569: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2570: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2571: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2573: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2576: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2577: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2578: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2581: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2583: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2584: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2585: Kalahi Admin: August 9-12, 2005
Note on Y2586: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2587: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2588: M&E:1st MIBF was conducted last January 17-19, 2004
Note on Y2589: Kalahi Admin: August 9-12, 2005
Note on Y2590: Note:1st MIBF was conducted last July 4-6, 2006.
Note on Y2592: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2593: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2594: Note:1st MIBF was conducted last December 3-5, 2004.
Note on X2595: completed as built
Note on Y2596: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2597: Administrator: January 18-20, 2006
Note on Y2599: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2601: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2602: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2603: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2604: Administrator: January 18-20, 2006
Note on X2605: completed as built
Note on Y2606: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2607: Administrator: January 18-20, 2006
Note on Y2608: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2610: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2612: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2613: Administrator: January 18-20, 2006
Note on Y2615: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2616: Administrator: January 18-20, 2006
Note on X2617: Unable to request final tranche thus the reduced length of grouted rip-rap from 640.0ln.m to 480.0ln.m; reduced length of PCCP from 318.o ln.m to 203.0 ln.m; reduced thickness of Item 201 from 0.20m to approx. 0.10m in selected areas
Note on Y2618: Administrator: January 18-20, 2006
Note on X2619: completed as built
Note on Y2620: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2621: Administrator: January 18-20, 2006
Note on X2622: Unable to request 2nd and 3rd tranche thus the reduce in length of PCCP and grouted rip-rap; lessened thickness of aggregate base course in selected areas
Note on Y2623: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2624: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2625: Administrator: January 18-20, 2006
Note on X2626: completed as built
Note on Y2627: Administrator: January 18-20, 2006
Note on Y2628: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2629: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2630: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2631: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2632: Administrator: January 18-20, 2006
Note on Y2633: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2635: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2636: Administrator: January 18-20, 2006
Note on Y2637: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2638: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2639: Administrator: January 18-20, 2006
Note on Y2640: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2641: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2644: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2645: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2647: Note:1sy MIBF was conducted last May 6-8, 2003.
Note on Y2648: Note:1st MIBF was conducted last December 3-5, 2004.
Note on Y2649: Note:1st MIBF was conducted last July 17-18, 2006.
Note on G2651: Clustered Brgys: 1.Agcarope 2.Canawili
Note on Y2651: Note:1st MIBF was conducted last July 17-18, 2006.
Note on G2652: Clustered Brgys: 1.Agcarope 2.Canauili
Note on Y2652: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2653: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2655: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2656: Kalahi Admin: July 6, 2005
Note on Y2658: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2660: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2661: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2662: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2664: Kalahi Admin: July 6, 2005
Note on Y2666: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2668: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2670: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2671: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2673: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2674: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2677: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2678: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2679: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2681: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2682: Kalahi Admin: July 6, 2005
Note on Y2683: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2685: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2687: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2688: Kalahi Admin: July 6, 2005
Note on Y2690: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2692: Kalahi Admin: July 6, 2005
Note on Y2694: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2695: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2698: Kalahi Admin: July 6, 2005
Note on G2699: Golgota San Julian A.N. West Don T.L West Locsin
Note on Y2699: Note:1st MIBF was conducted last July 17-18, 2006.
Note on G2700: Golgota San Julian A.N. West Don T.L West Locsin
Note on Y2700: Note:1st MIBF was conducted last July 17-18, 2006.
Note on G2701: Golgota San Julian A.N. West Don T.L West Locsin
Note on Y2701: Note:1st MIBF was conducted last July 17-18, 2006.
Note on G2702: Golgota San Julian A.N. West Don T.L West Locsin
Note on Y2702: Note:1st MIBF was conducted last July 17-18, 2006.
Note on G2703: Golgota San Julian A.N. West Don T.L West Locsin
Note on Y2703: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2704: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2705: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2706: Kalahi Admin: July 6, 2005
Note on Y2707: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2709: Kalahi Admin: July 6, 2005
Note on Y2710: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2711: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2714: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2715: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2716: Kalahi Admin: July 6, 2005
Note on Y2717: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2719: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2720: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2721: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2722: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2723: Kalahi Admin: July 6, 2005
Note on Y2725: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2727: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2728: Kalahi Admin: July 6, 2005
Note on Y2729: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2731: Kalahi Admin: July 6, 2005
Note on Y2732: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2734: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2735: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2736: Kalahi Admin: July 6, 2005
Note on Y2738: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2739: Kalahi Admin: July 6, 2005
Note on Y2740: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2741: Note:1st MIBF was conducted last July 17-18, 2006.
Note on Y2743: Kalahi Admin: July 6, 2005
Note on Y2746: Kalahi Admin: July 6, 2005
Note on Y2747: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2749: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2750: Kalahi Admin: July 6, 2005
Note on Y2751: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2752: Kalahi Admin: July 6, 2005
Note on Y2754: M&E:1st MIBF was conducted last January 4-6, 2004
Note on Y2755: Kalahi Admin: July 6, 2005
Note on Y2756: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2757: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2758: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2759: Administrator: February 19-24, 2004
Note on Y2760: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2761: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2762: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2763: Administrator: February 19-24, 2004
Note on Y2764: Administrator: February 19-24, 2004
Note on Y2765: Administrator: February 19-24, 2004
Note on Y2766: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2767: Administrator: February 19-24, 2004
Note on Y2768: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2769: Kalahi Admin: July 11-12 and 18-19, 2005
Note on G2770: Clustered Brgys: 1.Buwang 2.Malag-it
Note on Y2770: Kalahi Admin: July 11-12 and 18-19, 2005
Note on G2771: Clustered Brgys: 1.Buwang 2.Malag-it
Note on Y2771: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2772: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2773: Administrator: February 19-24, 2004
Note on Y2774: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2775: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2776: Administrator: February 19-24, 2004
Note on Y2777: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2778: Administrator: February 19-24, 2004
Note on Y2779: Administrator: February 19-24, 2004
Note on Y2780: Administrator: February 19-24, 2004
Note on Y2781: Administrator: February 19-24, 2004
Note on Y2782: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2783: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2784: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2785: Kalahi Admin: July 11-12 and 18-19, 2005
Note on X2786: completed as built
Note on Y2786: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on X2787: completed as built
Note on Y2787: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2788: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2789: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2790: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2791: Administrator: February 19-24, 2004
Note on Y2792: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2793: Administrator: February 19-24, 2004
Note on Y2794: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2795: Administrator: February 19-24, 2004
Note on Y2796: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2797: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2798: Administrator: February 19-24, 2004
Note on Y2799: Administrator: February 19-24, 2004
Note on Y2800: Administrator: February 19-24, 2004
Note on Y2801: Administrator: February 19-24, 2004
Note on Y2802: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2803: Administrator: February 19-24, 2004
Note on Y2804: Administrator: February 19-24, 2004
Note on Y2805: Administrator: February 19-24, 2004
Note on Y2806: Administrator: February 19-24, 2004
Note on Y2807: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2808: Administrator: February 19-24, 2004
Note on Y2809: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2810: Administrator: February 19-24, 2004
Note on Y2811: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2812: Administrator: February 19-24, 2004
Note on Y2813: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2814: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2815: Kalahi Admin: July 11-12 and 18-19, 2005
Note on Y2816: Note:1st MIBF was conducted last June 26 - July 1, 2006.
Note on Y2817: Administrator: February 5-7, 2004
Note on Y2818: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2819: Kalahi Admin: August 22-24, 2005
Note on Y2820: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2821: Kalahi Admin: August 22-24, 2005
Note on Y2822: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2823: Administrator: February 5-7, 2004
Note on Y2824: Administrator: February 5-7, 2004
Note on Y2825: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2826: Administrator: February 5-7, 2004
Note on Y2827: Kalahi Admin: August 22-24, 2005
Note on Y2828: Kalahi Admin: August 22-24, 2005
Note on Y2829: Administrator: February 5-7, 2004
Note on Y2830: Kalahi Admin: August 22-24, 2005
Note on Y2831: Administrator: February 5-7, 2004
Note on Y2832: Administrator: February 5-7, 2004
Note on Y2833: Administrator: February 5-7, 2004
Note on Y2834: Administrator: February 5-7, 2004
Note on Y2835: Kalahi Admin: August 22-24, 2005
Note on Y2836: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2837: Administrator: February 5-7, 2004
Note on Y2838: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2839: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2840: Administrator: February 5-7, 2004
Note on Y2841: Kalahi Admin: August 22-24, 2005
Note on Y2842: Kalahi Admin: August 22-24, 2005
Note on Y2843: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2844: Kalahi Admin: August 22-24, 2005
Note on Y2845: Kalahi Admin: August 22-24, 2005
Note on Y2846: Administrator: February 5-7, 2004
Note on X2847: completed as built
Note on Y2847: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2848: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2849: Kalahi Admin: August 22-24, 2005
Note on Y2850: Note:1st MIBF was conducted last August 2-3, 2006.
Note on Y2851: Kalahi Admin: August 22-24, 2005
Note on Y2852: Administrator: February 5-7, 2004
Note on Y2853: Administrator: February 5-7, 2004
Note on Y2854: Kalahi Admin: July 22-25, 2005
Note on Y2855: M&E:1st MIBF was conducted last January 26-29, 2004
Note on X2856: completed as built
Note on Y2857: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2858: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2859: M&E:1st MIBF was conducted last January 26-29, 2004
Note on X2860: completed as built
Note on Y2861: Kalahi Admin: July 22-25, 2005
Note on Y2862: Kalahi Admin: July 22-25, 2005
Note on Y2863: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2864: Kalahi Admin: July 22-25, 2005
Note on Y2865: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2866: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2867: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2868: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2870: M&E:1st MIBF was conducted last January 26-29, 2004
Note on X2871: completed as built
Note on Y2872: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2873: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2875: M&E:1st MIBF was conducted last January 26-29, 2004
Note on X2876: 88% as built
Note on Y2877: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2878: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2879: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2880: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2882: Note:1st MIBF was conducted last June 27-30, 2006.
Note on X2883: completed as built
Note on Y2884: Note:1st MIBF was conducted last June 27-30, 2006.
Note on X2885: completed as built
Note on Y2886: Kalahi Admin: July 22-25, 2005
Note on Y2887: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2888: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2889: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2890: Note:1st MIBF was conducted last June 27-30, 2006.
Note on X2891: completed as built
Note on Y2892: Kalahi Admin: July 22-25, 2005
Note on X2893: completed as built
Note on Y2894: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2895: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2896: Kalahi Admin: July 22-25, 2005
Note on X2897: completed as built
Note on X2898: 44% as built
Note on X2899: completed as built
Note on Y2900: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2901: Kalahi Admin: July 22-25, 2005
Note on X2902: completed as built
Note on Y2903: M&E:1st MIBF was conducted last January 26-29, 2004
Note on X2904: 42% as built
Note on Y2905: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2906: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2908: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2909: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2910: Kalahi Admin: July 22-25, 2005
Note on Y2911: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2912: Kalahi Admin: July 22-25, 2005
Note on Y2914: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2915: Kalahi Admin: July 22-25, 2005
Note on Y2916: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2917: Kalahi Admin: July 22-25, 2005
Note on X2918: completed as built
Note on Y2919: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2920: Note:1st MIBF was conducted last June 27-30, 2006.
Note on X2921: completed as built
Note on X2922: completed as built
Note on Y2923: M&E:1st MIBF was conducted last January 26-29, 2004
Note on Y2924: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2925: Note:1st MIBF was conducted last June 27-30, 2006.
Note on X2926: completed as built
Note on X2927: completed as built
Note on Y2927: Note:1st MIBF was conducted last June 27-30, 2006.
Note on X2928: completed as built
Note on Y2929: Note:1st MIBF was conducted last June 27-30, 2006.
Note on Y2930: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2931: Kalahi Admin: August 11-13, 2005
Note on Y2932: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on X2933: completed as built
Note on Y2934: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2935: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on X2936: completed as built
Note on Y2937: Kalahi Admin: August 11-13, 2005
Note on Y2938: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2939: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2940: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2942: M&E:1st MIBF was conducted last February 3-5, 2004
Note on X2943: completed as built
Note on Y2944: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2945: Kalahi Admin: August 11-13, 2005
Note on Y2947: Kalahi Admin: August 11-13, 2005
Note on Y2949: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2950: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on X2951: completed as built
Note on Y2952: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2953: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2954: Kalahi Admin: August 11-13, 2005
Note on Y2955: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2956: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2957: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2959: M&E:1st MIBF was conducted last February 3-5, 2004
Note on X2960: completed as built
Note on Y2961: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2962: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2964: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2965: Kalahi Admin: August 11-13, 2005
Note on Y2967: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2968: Kalahi Admin: August 11-13, 2005
Note on Y2970: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2972: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2973: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on X2974: completed as built
Note on Y2975: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2976: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2978: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2979: Kalahi Admin: August 11-13, 2005
Note on Y2981: Kalahi Admin: August 11-13, 2005
Note on X2982: completed as built
Note on X2983: completed as built
Note on Y2984: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on X2985: completed as built
Note on Y2986: M&E:1st MIBF was conducted last February 3-5, 2004
Note on Y2987: Kalahi Admin: August 11-13, 2005
Note on Y2988: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on Y2990: Note:1st MIBF was conducted last July 31 - August1, 2006.
Note on X2991: completed as built
Note on Y2993: M&E:1st MIBF was conducted last February 3-5, 2004
Note on X2994: completed as built
Note on X3012: aurea: 10.31.09 completed as built PA 8.30.09 - 61.84%
Note on Y3012: August 22-23, 2007
Note on Y3013: August 22-23, 2007
Note on Y3014: August 22-23, 2007
Note on X3015: 95% completed as built
Note on Y3016: August 22-23, 2007
Note on X3017: aurea: 10.31.09 completed as built PA 8.30.09 - 90.00%
Note on X3018: aurea: 10.31.09 completed as built PA 8.30.09 - 96.52%
Note on Y3019: August 22-23, 2007
Note on X3021: completed as built
Note on Y3021: August 22-23, 2007
Note on Y3023: August 22-23, 2007
Note on Y3024: August 22-23, 2007
Note on X3025: aurea: 10.31.09 completed as built PA 8.30.09 - 85.39%
Note on X3026: aurea: 10.31.09 completed as built PA 8.30.09 - 98.72%
Note on G3027: Tomina Sura
Note on X3027: aurea: 10.31.09 completed as built PA 8.30.09 - 62.14%
Note on G3028: Tomina Sura
Note on X3028: aurea: 10.31.09 completed as built PA 8.30.09 - 62.14%
Note on Y3036: november 24-25, 2008
Note on Y3037: August 1-2, 2007
Note on Y3038: november 24-25, 2008
Note on Y3039: March 13-14, 2008
Note on Y3040: March 13-14, 2008
Note on Y3041: november 24-25, 2008
Note on Y3042: november 24-25, 2008
Note on Y3043: August 1-2, 2007
Note on Y3044: november 24-25, 2008
Note on Y3045: March 13-14, 2008
Note on P3046: LIGHTBEARER: in-kind 47,657.63
Note on Y3046: August 1-2, 2007
Note on Y3047: August 1-2, 2007
Note on Y3048: March 13-14, 2008
Note on G3049: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3050: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3051: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3052: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3053: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3054: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3055: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3056: Barangay 1 Barangay 2 Barangay 3 Barangay 4 Barangay 5 Barangay 6 Barangay 7 Crossing Magallon
Note on G3057: Magallon Cadre Guinpanaan
Note on Y3057: February 27-28, 2008
Note on G3058: Magallon Cadre Guinpanaan
Note on Y3058: February 27-28, 2008
Note on Y3059: February 27-28, 2008
Note on Y3060: July 6-7, 2007
Note on X3061: completed as built
Note on Y3062: July 6-7, 2007
Note on Y3063: July 6-7, 2007
Note on G3092: Cabul-an West Cabul-an East
Note on G3093: Cabul-an West Cabul-an East
Note on G3094: Cabul-an West Cabul-an East
Note on G3133: Cabul-an West Cabul-an East
Note on G3139: Kabangkalan Sto. Rosario
Note on G3140: Kabangkalan Sto. Rosario
Note on L3159: from the excess funds of previous cycles
Note on G3189: Magtalangtang Tabok
Note on G3190: Magtalangtang Tabok
Note on G3206: Clustered Brgys: 1.Tabok 2.Cantubod 3.Remedios
Note on G3207: Clustered Brgys: 1.Tabok 2.Cantubod 3.Remedios
Note on G3208: Clustered Brgys: 1.Tabok 2.Cantubod 3.Remedios
Note on H3237: Saeapph005:
Note on G3240: Aguipo San Isidro San Roque
Note on G3241: Aguipo San Isidro San Roque
Note on G3242: Aguipo San Isidro San Roque
Note on G3314: incentive fund
Note on X3326: Local counterpart contribution pledged by a political candidate seeking election was not delivered, hence, resulted to the following: (1) Reduction of quantity for Item 201 Aggregate Base Coardse from 819 cu. m. to 559 cu. m; (2) Surplus Common Excavation of 1,032 sq. m. (PhP17,600.00) was reduced to 336 sq. m. (PhP5,728.00); and (3) Subgrade Preparation of 6,192 sq. m. (PhP35,200.00) was reduced to 4,200 sq. m. (PhP23,772.00).
Note on X3340: MLGU failed to deliver LCC. As a result, there was a reduction of distribution of lines, the actual number, however, cannot be determined as of this time (Engineering soft files were corrupted).
Note on X3349: Local counterpart contribution pledged by a political candidate seeking election was not delivered. Exact figures for reduction cannot be determined as of this time. (Engineering soft files were corrupted).
Note on X3354: Due to the undelivered PDAF Counterpart, Items from IX to XI were deleted. Item XII was also stricken out except for the roofing works. Because of non-delivery, source of funding reflected for Item VI in the original POW was changed from PDAF to KC Grant.
Note on X3359: Items 104 (Enbankment), 201 (Aggregate Base Course), and 504 (Grouted Riprap) were deleted due to non-delivery of PDAF Counterpart.
Note on X3366: Local counter contribution from the PDAF of Congressman Roberto Cajes was not delivered. Hence, funding source for Item 900 (Reinforced Concrete); 1003 (Carpentry and Joinery Works); 1009 (Jalousies Windows); 1013 (Corrugated Metal Roofing) were changed from the PDAF (in-kind) to KALAHI Grant, due to the non-delivery of the said counterpart. Items 704 (Masonry Works); 1000 (Termite Control Works); 1002 (Plumbing); 1018 (Ceramic Tile); 1027 (Cement Plaster Finish); 1032 (Painting: some materials were deleted); SPCL-2 (Window Grills); and SPCL-4 (Electrical Works) were deleted due to the non-delivery of PDAF in-kind counterpart (materials).
Note on X3368: Funding source of Item I, IV, VI and VI (Site Works, Form Works and Scaffolding, Masonry Works, Carpentry Works) was changed from PDAF in-kind materials to KALAHI Grant due to the non-delivery of the supposed counterpart. Items IX, X, XI and XII (Plumbing Works, Tile Works, Electrical Works , and Painting Works) were also deleted due to similar reason.
Note on X3370: Shortened the length of concrete pavement (using Portland Cement) from 300 meters to 95 meters due to the undelivered PDAF LCC materials.
Note on X3372: The materials for Item 311 (Portland Cement Concrete Pavement) and Item 504 (Grouted Riprap) reflected in POW were supposed to be shouldered by the PDAF promised by Congressman Roberto Cajes as counterpart. Due to non-delivey of the said counterpart, the BSPMC was forced to delete Item 311 and lessen the quantity to be implemented for Item 504 (Grouted Riprap).
Note on X3374: Due to the change of location, the program of works was revised to suit the actual condition of the project site. Changes were made in all items relating to Site Works (Item I); Concrete Works (Item II); Reinforcing Steel Bars (Item III); Carpentry Works (Item VI); and Roofing (Item VIII).
Note on G3437: Clustered Brgys: 1.Cangmangki 2.Parian 3.Bino-ongan 4.Libo 5.Camogao
Note on G3438: Clustered Brgys: 1.Cangmangki 2.Parian 3.Bino-ongan 4.Libo 5.Camogao
Note on G3439: Clustered Brgys: 1.Cangmangki 2.Parian 3.Bino-ongan 4.Libo 5.Camogao
Note on G3440: Clustered Brgys: 1.Cangmangki 2.Parian 3.Bino-ongan 4.Libo 5.Camogao
Note on G3441: Clustered Brgys: 1.Cangmangki 2.Parian 3.Bino-ongan 4.Libo 5.Camogao
Note on G3455: Clustered Brgys: 1.Poblacion 2.Manan-ao 3.Tulapos
Note on G3456: Clustered Brgys: 1.Poblacion 2.Manan-ao 3.Tulapos
Note on G3457: Clustered Brgys: 1.Poblacion 2.Manan-ao 3.Tulapos
Note on G3463: Clustered Brgys: 1.Caipilan 2.Caitican 3.Caticugan 4.Cang-alwang 5.Cang-adieng 6.Tinago 7.Tongo 8.Bolos
Note on G3472: Clustered Brgys: 1.Cang-agong 2.Sabang 3.Luyang
Note on G3473: Clustered Brgys: 1.Cang-agong 2.Sabang 3.Luyang
Note on G3474: Clustered Brgys: 1.Cang-agong 2.Sabang 3.Luyang
Note on X3475: Asphalt paving works were taken out from the program
Note on G3490: Clustered Brgys: 1.Cantabon 2.Tebjong
Note on G3491: Clustered Brgys: 1.Cantabon 2.Tebjong
Note on X3496: Asphalt paving works were taken out from the program
Note on X3504: Asphalt paving works were taken out from the program
Note on G3512: Clustered Brgys: 1.Pili 2.Banban
Note on G3513: Clustered Brgys: 1.Pili 2.Banban
Note on X3526: Asphalt paving works were taken out from the program
Note on X3531: Asphalt paving works were taken out from the program
Note on AB3565: Central Office Engineering data
Note on AB3568: Central Office Engineering data
Note on AB3602: Central Office Engineering data
Note on I3611: M&E:Brgy Road & retaining wall
Note on I3615: M&E:Brgy Road & retaining wall
Note on AB3634: Central Office Engineering data
Note on G3657: Clustered Brgys: 1.Poblacion 1 2.Poblacion 2 3.Poblacion 3 4.Poblacion 4 5.Poblacion 5 6.Poblacion 6 7.Poblacion 7 8.Poblacion 8 9.Poblacion 9
Note on AB3695: Central Office Engineering data
Note on AB3701: Central Office Engineering data
Note on G3708: Clustered Brgys: 1.Poblacion 1 2.Poblacion 2
Note on G3709: Clustered Brgys: 1.Poblacion 1 2.Poblacion 2
Note on X3716: adjusted as per engineering data as built
Note on AB3726: Central Office Engineering data
Note on AB3776: Central Office Engineering data
Note on AB3778: Central Office Engineering data
Note on AB3780: Central Office Engineering data
Note on AB3782: Central Office Engineering data
Note on AB3785: Central Office Engineering data
Note on AB3787: Central Office Engineering data
Note on AB3790: Central Office Engineering data
Note on AB3792: Central Office Engineering data
Note on AB3796: Central Office Engineering data
Note on AB3798: Central Office Engineering data
Note on AB3801: Central Office Engineering data
Note on AB3805: Central Office Engineering data
Note on AB3808: Central Office Engineering data
Note on AB3810: Central Office Engineering data
Note on AB3812: Central Office Engineering data
Note on AB3816: Central Office Engineering data
Note on AB3820: Central Office Engineering data
Note on AB3824: Central Office Engineering data
Note on AB3826: Central Office Engineering data
Note on AB3829: Central Office Engineering data
Note on AB3831: Central Office Engineering data
Note on AB3832: Central Office Engineering data
Note on AB3833: Central Office Engineering data
Note on AB3834: Central Office Engineering data
Note on AB3836: Central Office Engineering data
Note on AB3839: Central Office Engineering data
Note on AB3845: Central Office Engineering data
Note on X3846: as built 71%
Note on G3847: San Joaquin Visares
Note on G3848: San Joaquin Visares
Note on AB3849: Central Office Engineering data
Note on AB3851: Central Office Engineering data
Note on AB3853: Central Office Engineering data
Note on AB3855: Central Office Engineering data
Note on AB3857: Central Office Engineering data
Note on AB3859: Central Office Engineering data
Note on AB3861: Central Office Engineering data
Note on AB3867: Central Office Engineering data
Note on AB3870: Central Office Engineering data
Note on AB3871: Central Office Engineering data
Note on AB3872: Central Office Engineering data
Note on AB3874: Central Office Engineering data
Note on AB3875: Central Office Engineering data
Note on AB3876: Central Office Engineering data
Note on AB3878: Central Office Engineering data
Note on AB3881: Central Office Engineering data
Note on AB3883: Central Office Engineering data
Note on AB3885: Central Office Engineering data
Note on AB3887: Central Office Engineering data
Note on AB3889: Central Office Engineering data
Note on AB3890: Central Office Engineering data
Note on AB3897: Central Office Engineering data
Note on AB3899: Central Office Engineering data
Note on AB3905: Central Office Engineering data
Note on AB3921: Central Office Engineering data
Note on AB3924: Central Office Engineering data
Note on AB3938: Central Office Engineering data
Note on AB3943: Central Office Engineering data
Note on AB3946: Central Office Engineering data
Note on AB3947: Central Office Engineering data
Note on AB3952: Central Office Engineering data
Note on AB3954: Central Office Engineering data
Note on AB3955: Central Office Engineering data
Note on AB3956: Central Office Engineering data
Note on AB3958: Central Office Engineering data
Note on AB3964: Central Office Engineering data
Note on AB3968: Central Office Engineering data
Note on AB3970: Central Office Engineering data
Note on AB3977: Central Office Engineering data
Note on AB3985: Central Office Engineering data
Note on AB3990: Central Office Engineering data
Note on AB4001: Central Office Engineering data
Note on AB4043: Central Office Engineering data
Note on AB4050: Central Office Engineering data
Note on AB4052: Central Office Engineering data
Note on AB4055: Central Office Engineering data
Note on AB4061: Central Office Engineering data
Note on AB4063: Central Office Engineering data
Note on AB4067: Central Office Engineering data
Note on AB4069: Central Office Engineering data
Note on AB4072: Central Office Engineering data
Note on AB4074: Central Office Engineering data
Note on AB4078: Central Office Engineering data
Note on AB4079: Central Office Engineering data
Note on AB4083: Central Office Engineering data
Note on AB4093: Central Office Engineering data
Note on AB4097: Central Office Engineering data
Note on AB4100: Central Office Engineering data
Note on AB4104: Central Office Engineering data
Note on AB4111: Central Office Engineering data
Note on AB4112: Central Office Engineering data
Note on AB4113: Central Office Engineering data
Note on AB4118: Central Office Engineering data
Note on AB4126: Central Office Engineering data
Note on AB4161: as per C.O. Engineering data
Note on G4175: Amandangay Mohon
Note on G4176: Mohon Amandangay
Note on AB4176: Central Office Engineering data
Note on G4177: Mohon Amandangay
Note on AB4177: Central Office Engineering data
Note on AB4178: Central Office Engineering data
Note on G4179: Aslum San Pablo
Note on G4180: Aslum San Pablo
Note on AB4182: Central Office Engineering data
Note on G4185: Belisong Jabong
Note on G4186: Belisong Jabong
Note on AB4188: Central Office Engineering data
Note on AB4190: Central Office Engineering data
Note on AB4194: Central Office Engineering data
Note on G4197: Mercaduhay Mering
Note on G4200: Quezon Rizal
Note on AB4213: Central Office Engineering data
Note on AB4217: Central Office Engineering data
Note on AB4252: Central Office Engineering data
Note on AB4257: Central Office Engineering data
Note on AB4262: Central Office Engineering data
Note on AB4264: Central Office Engineering data
Note on AB4276: Central Office Engineering data
Note on AB4280: Central Office Engineering data
Note on AB4285: Central Office Engineering data
Note on AB4287: Central Office Engineering data
Note on AB4292: Central Office Engineering data
Note on AB4294: Central Office Engineering data
Note on AB4310: Central Office Engineering data
Note on AB4312: Central Office Engineering data
Note on AB4314: Central Office Engineering data
Note on AB4316: Central Office Engineering data
Note on AB4323: Central Office Engineering data
Note on X4324: as built
Note on AF4324: need to check if it is as built (rey says that it was not yet completed but can be completed soon so it isnot completed as built)
Note on AB4325: as per C.O. Engineering data
Note on AB4328: Central Office Engineering data
Note on AB4329: Central Office Engineering data
Note on AB4330: Central Office Engineering data
Note on AB4334: Central Office Engineering data
Note on AB4335: Central Office Engineering data
Note on AB4337: Central Office Engineering data
Note on AB4338: Central Office Engineering data
Note on AB4340: Central Office Engineering data
Note on AB4341: Central Office Engineering data
Note on AB4343: Central Office Engineering data
Note on AB4345: Central Office Engineering data
Note on AB4346: Central Office Engineering data
Note on AB4348: Central Office Engineering data
Note on AB4349: Central Office Engineering data
Note on AB4350: Central Office Engineering data
Note on AB4352: Central Office Engineering data
Note on AB4357: Central Office Engineering data
Note on AB4358: Central Office Engineering data
Note on AB4361: Central Office Engineering data
Note on AB4365: Central Office Engineering data
Note on AB4367: Central Office Engineering data
Note on AB4369: Central Office Engineering data
Note on AB4372: Central Office Engineering data
Note on AB4374: Central Office Engineering data
Note on AB4384: Central Office Engineering data
Note on G4414: Poblacion 1 Poblacion 3 Poblacion 4 Poblacion 6 Poblacion 7 Poblacion 8
Note on G4415: Poblacion 1 Poblacion 3 Poblacion 4 Poblacion 6 Poblacion 7 Poblacion 8
Note on G4416: Poblacion 1 Poblacion 3 Poblacion 4 Poblacion 6 Poblacion 7 Poblacion 8
Note on G4417: Poblacion 1 Poblacion 3 Poblacion 4 Poblacion 6 Poblacion 7 Poblacion 8
Note on G4418: Poblacion 1 Poblacion 3 Poblacion 4 Poblacion 6 Poblacion 7 Poblacion 8
Note on G4457: previous month submission it was San Isidro
Note on G4458: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB4458: Central Office Engineering data
Note on AB4463: Central Office Engineering data
Note on AB4465: Central Office Engineering data
Note on AB4466: Central Office Engineering data
Note on AB4468: Central Office Engineering data
Note on G4471: Kalahi: 1. Casandig 1 2. Casandig 2
Note on G4472: Casandig 1 & 2
Note on AB4474: Central Office Engineering data
Note on G4477: Pacoc
Note on AB4479: Central Office Engineering data
Note on AB4480: Central Office Engineering data
Note on AB4481: Central Office Engineering data
Note on AB4483: Central Office Engineering data
Note on AB4491: Central Office Engineering data
Note on AB4492: Central Office Engineering data
Note on AB4493: Central Office Engineering data
Note on AB4494: Central Office Engineering data
Note on AB4496: Central Office Engineering data
Note on AB4498: Central Office Engineering data
Note on G4499: Poblacion 2 & 3
Note on AB4500: Central Office Engineering data
Note on AB4501: Central Office Engineering data
Note on AB4502: Central Office Engineering data
Note on AB4504: Central Office Engineering data
Note on G4511: Kalahi: 1. Tabucan 2. Cantaguic
Note on AB4512: Central Office Engineering data
Note on AB4514: Central Office Engineering data
Note on G4516: Kalahi 1. Tigbawon 2. Pagsagan
Note on H4518: Saeapph005:
Note on AB4520: Central Office Engineering data
Note on G4550: Dolores Poblaion 1 Poblaion 2 Nabong Obayan
Note on AB4561: Central Office Engineering data
Note on G4562: Clustered Brgys: 1.Bahay 2.Curry
Note on AB4564: Central Office Engineering data
Note on AB4566: Central Office Engineering data
Note on AB4576: Central Office Engineering data
Note on AB4581: Central Office Engineering data
Note on AB4584: Central Office Engineering data
Note on AB4587: Central Office Engineering data
Note on AB4588: Central Office Engineering data
Note on AB4591: Central Office Engineering data
Note on AB4593: Central Office Engineering data
Note on AB4595: Central Office Engineering data
Note on AB4598: Central Office Engineering data
Note on AB4602: Central Office Engineering data
Note on AB4605: Central Office Engineering data
Note on AB4641: Central Office Engineering data
Note on G4692: Clustered Brgys: 1.Oeste A 2.Oeste B
Note on G4716: San Andres San Roque Ulayan Cambaguio Pacoyoy
Note on G4717: San Andres San Roque Ulayan Cambaguio Pacoyoy
Note on G4718: San Andres San Roque Ulayan Cambaguio Pacoyoy
Note on G4719: San Andres San Roque Ulayan Cambaguio Pacoyoy
Note on G4724: Tomabe Lam-awan Canmucat
Note on AB4724: Central Office Engineering data
Note on X4768: 80% completed "as built" / Un-passabble access road due to force majeure and unstable peace and order situation
Note on X4769: ORD-KC-ME: ACTUAL 83.88% completed "as built"/ Unpassable access road and unstable peace and order situation
Note on X4770: actual 91% completed "as built" / Un-passabble access road due to force majeure and unstable peace and order situation
Note on AF4770: peace and order issue
Note on X4785: ORD-KC-ME: ACTUAL 80% completed "as built"/ Unfavorable weather condition and unstable peace and order situation
Note on X4792: 80% completed "as built"/ Unstable peace and order condition in the area and non access road problem leading to the site
Note on X4798: 95.41% completed "as built"/ Unstable peace and order condition in the area and non access road problem leading to the site
Note on Y4845: March 27-29, 2004
Note on Y4848: March 27-29, 2004
Note on Y4850: March 27-29, 2004
Note on Y4854: March 27-29, 2004
Note on Y4857: March 27-29, 2004
Note on Y4858: March 27-29, 2004
Note on Y4865: September 12-23, 2005
Note on Y4867: September 12-23, 2005
Note on Y4879: September 12-23, 2005
Note on G4884: Clustered Brgys: 1.Mamagum 2.Campo Islam
Note on G4885: Clustered Brgys: 1.Mamagum 2.Campo Islam
Note on Y4886: September 12-23, 2005
Note on Y4887: September 12-23, 2005
Note on Y4889: September 12-23, 2005
Note on Y4893: September 12-23, 2005
Note on Y4895: September 12-23, 2005
Note on Y4896: September 12-23, 2005
Note on Y4897: September 12-23, 2005
Note on Y4901: September 12-23, 2005
Note on Y4902: September 12-23, 2005
Note on X4934: ORD-KC-ME: ACTUAL 80% Non-Release of last tranche RFR due to the inability of the LGU to provide the balance of cash LCC which resulted to work suspension
Note on Y4970: June 13-16, 2006
Note on Y4971: May 29 - June 1, 2007
Note on Y4972: May 29 - June 1, 2007
Note on Y4973: May 18-19, 2005
Note on Y4974: May 18-19, 2005
Note on Y4975: May 29 - June 1, 2007
Note on Y4976: June 13-16, 2006
Note on Y4977: May 29 - June 1, 2007
Note on Y4978: June 13-16, 2006
Note on Y4979: June 13-16, 2006
Note on Y4980: May 17-19, 2005
Note on Y4981: May 29 - June 1, 2007
Note on Y4982: May 17-19, 2005
Note on Y4983: May 29 - June 1, 2007
Note on Y4984: May 17-19, 2005
Note on Y4985: June 13-16, 2006
Note on G4986: KALAHI-CIDSS: Bayanihan, Il Papa, Kagawasan, El Katipunan (BIKE)
Note on Y4986: May 18-19, 2005
Note on Y4987: June 13-16, 2006
Note on Y4988: June 13-16, 2006
Note on Y4989: May 29 - June 1, 2007
Note on Y4990: May 29 - June 1, 2007
Note on Y4991: June 13-16, 2006
Note on Y4992: May 29 - June 1, 2007
Note on Y4993: June 13-16, 2006
Note on Y4994: May 29 - June 1, 2007
Note on Y4995: May 29 - June 1, 2007
Note on Y4996: May 18-19, 2005
Note on Y4997: June 13-16, 2006
Note on Y4998: May 29 - June 1, 2007
Note on Y4999: May 18-19, 2005
Note on Y5000: June 13-16, 2006
Note on Y5001: May 18-19, 2005
Note on Y5002: May 18-19, 2005
Note on Y5003: June 13-16, 2006
Note on Y5004: June 13-16, 2006
Note on Y5005: May 29 - June 1, 2007
Note on Y5006: May 18-19, 2005
Note on Y5007: June 13-16, 2006
Note on Y5008: June 13-16, 2006
Note on Y5009: May 17-18, 2005
Note on Y5010: May 17-18, 2005
Note on Y5011: May 17-18, 2005
Note on Y5012: June 13-16, 2006
Note on Y5013: May 29 - June 1, 2007
Note on Y5014: June 13-16, 2006
Note on Y5015: May 29 - June 1, 2007
Note on Y5016: June 13-16, 2006
Note on L5023: it is the original estimated project cost as per MIBF (but the actual amount is only 80% of it. 80% downloaded grant fund is sufficient to complete the project
Note on L5027: it is the original estimated project cost as per MIBF (but the actual amount is only 80% of it. 80% downloaded grant fund is sufficient to complete the project
Note on G5051: Clustered Brgys: 1.La Libertad 2.Casig-ang 3.San Miguel
Note on G5059: Clustered Brgys: 1.New Katipunan 2.Tibal-og
Note on Y5081: April 24-25, 2006
Note on Y5083: April 24-25, 2006
Note on Y5089: April 24-25, 2006
Note on Y5092: April 24-25, 2006
Note on Y5094: April 24-25, 2006
Note on Y5100: April 24-25, 2006
Note on Y5112: April 24-25, 2006
Note on I5115: previously slope protection
Note on Y5116: April 24-25, 2006
Note on Y5121: June 15-16, 2006
Note on Y5123: June 15-16, 2006
Note on Y5126: June 15-16, 2006
Note on X5131: non-delivery of LCC committed (equipments) 50% physical accoumplishment
Note on G5176: Gambudes Katipunan
Note on G5181: Gambudes Katipunan
Note on G5280: Clustered Brgys: 1.Bato-Bato 2.Datu Inda 3.Kimaruhing
Note on G5281: Clustered Brgys: 1.Bato-Bato 2.Datu Inda 3.Kimaruhing
Note on G5282: Clustered Brgys: 1.Bato-Bato 2.Datu Inda 3.Kimaruhing
Note on G5322: Clustered Brgys: 1.Lun Masla 2.Patag
Note on X5341: BLGU will take over for the implementation. 36%
Note on G5342: Clustered Brgys: 1.Atlae 2.Kibala 3.Kiblat
Note on G5343: Clustered Brgys: 1.Atlae 2.Kibala 3.Kiblat
Note on G5344: Clustered Brgys: 1.Atlae 2.Kibala 3.Kiblat
Note on X5380: Washed out due to Typhoon Frank. Incident Report had been sent to Central Office by the RIE
Note on N5386: higher than the TPC (Grant)?
Note on G5450: Clustered Brgys: 1.White Deer 2.Salvacion 3.San Isidro 4.San Roque 5.Del Rosario
Note on G5451: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5451: Central Office Engineering data
Note on G5452: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5452: Central Office Engineering data
Note on G5453: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5453: Central Office Engineering data
Note on G5454: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5454: Central Office Engineering data
Note on G5455: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5455: Central Office Engineering data
Note on G5456: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5456: Central Office Engineering data
Note on G5457: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5457: Central Office Engineering data
Note on G5458: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5458: Central Office Engineering data
Note on G5459: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5459: Central Office Engineering data
Note on G5460: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5460: Central Office Engineering data
Note on G5461: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5461: Central Office Engineering data
Note on G5462: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5462: Central Office Engineering data
Note on G5463: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5463: Central Office Engineering data
Note on G5464: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5464: Central Office Engineering data
Note on G5465: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5465: Central Office Engineering data
Note on G5466: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5466: Central Office Engineering data
Note on G5467: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5467: Central Office Engineering data
Note on G5468: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5468: Central Office Engineering data
Note on G5469: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5469: Central Office Engineering data
Note on G5470: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5470: Central Office Engineering data
Note on G5471: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5471: Central Office Engineering data
Note on G5472: Clustered Brgys: 1.Gusaran 2.Poblacion 3 3.Poblacion 2 4.Poblacion 1 5.Genagasan 6.San Antonio 7.Geguimitan 8.Balud 9.Tobgon 10.Montalban 11.Cagdao 12.Cababayugan 13.Cabongaan 14.Gebolwagan 15.Caghilot 16.Gecboan 17.Camayaan 18.Imelda 19.Deit De Turag 20.Camanggaran 21.Geparayan de Turag 22.Victory 23.Deit de Suba
Note on AB5472: Central Office Engineering data
Note on G5473: Tomabe Lam-awan Canmucat
Note on AB5473: Central Office Engineering data
Note on G5474: Tomabe Lam-awan Canmucat
Note on AB5474: Central Office Engineering data

## KC1 Savings
KC1-SAVINGS Funded SPs
REGION |  | PROVINCE |  | MUNICIPALITY |  | Barangay_Name |  | SP_Name | NoOfBgys | Major SP Category | SP Sub-Category | Project_Type | Physical_Target | Phy_Target_Unit | Kalahi_Amount | LCC_Amount | Total_Amount | Date_Started | Date_of_Completion | KC_Fund_Released | Status
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Agawa | 144403001 | Construction of Ap-apa, Nabanig, Bengaw Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 446 | ln.m | 637693.41 | 148706.59 | 786400 | 2010-10-11 | 2010-12-31 | 637693.41 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Ambaguio | 144403002 | Improvement of Tokok Communal Irrigation System | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | CIS | 10 | has. | 314809.9 | 84515.1 | 399325 | 2010-11-20 | 2010-12-31 | 296937.9 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Banguitan | 144403003 | Improvement of Saysayagan to Katawaen Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 1.485 | kms | 1096530 | 266870 | 1363400 | 2010-11-23 | 2010-12-31 | 1053659 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Catengan | 144403006 | Improvement of Catengan Water Supply System | 1 | Basic Social Services | Water System | WS | 1 | system | 569101 | 145899 | 715000 | 2010-10-11 | 2010-12-27 | 569101 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Gueday | 144403007 | Improvement of Agawa to Dayocan, Patay to Binangbangda & Nabago to Batogyan Pathways | 1 | Basic Access Infrastructure | Access Trail | RFP | 1.768 | kms | 606023.34 | 150776.66 | 756800 | 2010-11-06 | 2010-12-31 | 595840.51 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Lacmaan | 144403009 | Concreting of Lacmaan Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 240 | ln.m | 610108.16 | 141041.84 | 751150 | 2010-11-06 | 2010-12-31 | 610107.16 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Padangan | 144403011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 770953.44 | 179746.56 | 950700 | 2010-10-01 | 2010-12-31 | 770514.06 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Suquip | 144403013 | Improvement of Suquip Water Supply System | 1 | Basic Social Services | Water System | WS | 1 | system | 239731 | 130269 | 370000 | 2010-10-11 | 2010-11-26 | 191784.81 | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Tamboan | 144403014 | Improvement of Kin-Iway to Tamboan Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 5.4 | kms | 1465170 | 355300 | 1820470 | 2010-11-20 | 2010-12-31 | 1465142.48 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Bagumbang | 104203003 | Dredging and Construction of Slope Protection @ Dupol Creek/Bagumbang River | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | RW | 650 | ln.m | 702138.5 | 300916.5 | 1003055 | 2010-10-26 | 2011-01-09 | 702138.5 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Baybay | 104203004 | Construction of 1 Classroom Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 63 | sq.m | 540585.5 | 231679.5 | 772265 | 2010-11-08 | 2011-03-31 | 540585.5 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Buenavista | 104203006 | Construction of 2 Classrooms School Building (HS) | 1 | Basic Social Services | School | SB | 126 | sq.m | 847700 | 363300 | 1211000 | 2010-10-14 | 2011-01-02 | 847700 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Buracan | 104203007 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1442000 | 618000 | 2060000 | 2010-11-08 | 2011-04-30 | 1380000 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Kanao-Kanao, Dullan & Upper Usogan | 104203012, 104203011 & 104203031 | Construction of Potable Water System Level II | 3 | Basic Social Services | Water System | WS | 1 | system | 2015636 | 1984364 | 4000000 | 2010-10-28 | 2011-04-30 | 2015636 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Linconan | 104203014 | Construction of Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 576 | sq.m | 466196.5 | 199798.5 | 665995 | 2010-10-28 | 2011-01-31 | 466196.5 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Lodiong | 104203015 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 973700 | 417300 | 1391000 | 2010-10-18 | 2011-01-01 | 973700 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Lower Usugan | 104203016 | Construction of Barangay Road | 1 | Basic Access Infrastructure | Road | RC | 1.064 | kms | 1312500 | 562500 | 1875000 | 2010-12-04 | 2011-05-30 | 1264137 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Poblacion | 104203024 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 557579.4 | 238962.6 | 796542 | 2010-10-28 | 2011-01-11 | 561579.4 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Rufino Lumapas | 104203026 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 560464.1 | 240198.9 | 800663 | 2010-10-13 | 2011-01-01 | 560464.1 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Sibuyon | 104203027 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 765800 | 328200 | 1094000 | 2010-10-29 | 2011-05-30 | 765800 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Tiaman | 104203029 | Improvement of Barangay Road | 1 | Basic Access Infrastructure | Road | RR | 1.4 | kms | 823200 | 352800 | 1176000 | 2010-12-04 | 2011-04-30 | 791034.78 | Completed
R10 | 10 | Misamis Occidental | 1042 | Bonifacio | 104203 | Tusik | 104203030 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1592500 | 682500 | 2275000 | 2010-12-03 | 2011-04-30 | 1524066.27 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Balili | 103505004 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1193150 | 511385 | 1704535 | 2010-10-08 | 2011-02-28 | 1193150 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Belis | 103505007 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 37188.03 | 1257575.97 | 1294764 | 2010-10-13 | 2011-01-31 | 37188.03 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Buenavista | 103505008 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1049935.59 | 450060.41 | 1499996 |  |  | 0 | Not yet started
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Buenavista | 103505008 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1049935.59 | 450060.41 | 1499996 | 2010-10-12 | 2010-12-30 | 1049935.59 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Butadon | 103505010 | Construction of Solar Dryer with Warehouse and Ricemill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 546 | sq.m | 965130.6 | 413626.4 | 1378757 | 2010-10-13 | 2011-04-30 | 965130.6 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Curvada | 103505015 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | RC | 2.08 | kms | 2564019 | 1098749 | 3662768 | 2010-12-02 | 2011-04-30 | 2564019 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | La Libertad | 103505027 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1343604 | 575719 | 1919323 | 2010-10-17 | 2011-04-30 | 1343594 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Malinas | 103505031 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | RC | 4.053 | kms | 5001364.6 | 2143442 | 7144806.6 | 2010-12-03 |  | 0 | On-going
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Poblacion | 103505036 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 1906 | ln.m | 2063206.18 | 884231.22 | 2947437.4 | 2010-10-28 | 2011-02-28 | 2063206.18 | Completed
R10 | 10 | Lanao Del Norte | 1035 | Kapatagan | 103505 | Sta. Cruz | 103505041 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | RC | 0.25 | kms | 632402 | 270987 | 903389 | 2010-10-06 | 2011-04-30 | 632402 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Anitap | 112506001 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 180 | ln.m | 515328 | 448978 | 964306 | 2010-10-07 | 2010-12-31 | 515328 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Don Aurelio Chicote | 112506003 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1244377 | 378110 | 1622487 | 2010-10-28 | 2011-02-28 | 1244377 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Oregon | 112506009 | Construction of Hanging Cable Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | BC | 46 | ln.m | 1434801 | 534804 | 1969605 | 2010-10-31 | 2011-01-19 | 1434801 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Sergio Osmeña | 112506012 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 617054 | 354041 | 971095 | 2010-10-26 | 2011-02-28 | 617054 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Surop & Nangan | 112506012 & 112506008 | Construction of Potable Water System Level II | 2 | Basic Social Services | Water System | WS | 1 | system | 1351655 | 1007423 | 2359078 | 2010-11-25 | 2011-04-28 | 1351655 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Tagabebe | 112506014 | Capability Building on Fish Shelter | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | CB | 8 | unit | 1022304 | 379525 | 1401829 | 2011-01-21 | 2011-03-31 | 1022304 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Tamban | 112506015 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 100 | ln.m | 376831 | 314458 | 691289 | 2010-10-19 | 2010-12-31 | 376831 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Tandang Sora | 112506016 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 784799 | 201000 | 985799 | 2010-10-16 | 2010-12-31 | 784799 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Tibanban | 112506017 | Construction of Drainage Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 820 | ln.m | 1242067 | 443045 | 1685112 | 2010-10-06 | 2011-01-24 | 1242067 | Completed
R11 | 11 | Davao Oriental | 1125 | Gov. Generoso | 112506 | Upper Tibanban | 112506019 | Construction of Flood Control Facility | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 150 | ln.m | 410784 | 306138 | 716922 | 2010-10-28 | 2011-01-31 | 410784 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Aguinaldo | 118202001 | Construction of Birthing Facility | 1 | Basic Social Services | Health Station | HS | 140 | sq.m | 1902415 | 159912 | 2062327 | 2011-04-30 | 2011-06-30 | 1902415 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Ampawid | 118202017 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1184793 | 107254 | 1292047 | 2011-03-14 | 2011-06-30 | 1184793 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Bayanihan |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 679738 | 67189 | 746927 | 2011-03-12 | 2011-05-31 | 679738 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Belmonte | 118202021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 534549 | 148567 | 683116 | 2011-05-26 | 2011-06-30 | 534549 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Buhi |  | Construction of 3 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 189 | sq. m | 1730640 | 150611 | 1881251 | 2011-04-06 | 2011-06-30 | 1730640 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Candiis |  | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 624410 | 63306 | 687716 | 2011-03-07 | 2011-05-31 | 624410 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Concepcion | 118202023 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 626186 | 63430 | 689616 | 2011-03-03 | 2011-04-30 | 626186 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Dalimdim (Kapatagan) | 118202007 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 617309 | 62807 | 680116 | 2011-03-25 | 2011-05-31 | 617309 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Datu Ampunan | 118202024 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 653574 | 106028 | 759602 | 2011-03-09 | 2011-06-30 | 653574 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Datu Davao | 118202025 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1180775 | 106972 | 1287747 | 2011-03-11 | 2011-06-30 | 1180775 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Doña Josefa | 118202026 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 681609 | 67318 | 748927 | 2011-03-02 | 2011-05-31 | 681609 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | El Katipunan | 118202027 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 635451 | 97076 | 732527 | 2011-03-21 | 2011-06-30 | 635451 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Hinagtungan |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 678242 | 67085 | 745327 | 2011-03-07 | 2011-05-31 | 678242 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | IL Papa | 118202005 | Construction of Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 480 | sq.m | 343986 | 51414 | 395400 | 2011-04-30 | 2011-05-31 | 343986 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Inacayan | 118202029 | Reinforced Concrete Pipe Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 7 | ln.m | 113061 | 19764 | 132825 | 2011-04-30 | 2011-05-31 | 113061 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Kagawasan |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 680955 | 67272 | 748227 | 2011-03-09 | 2011-05-31 | 680955 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | El Katipunan | 118202027 | Construction of Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 480 | sq.m | 343238 | 51362 | 394600 | 2011-03-24 | 2011-05-31 | 343238 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Kibaguio |  | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 621840 | 63126 | 684966 | 2011-03-03 | 2011-06-30 | 621840 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Kidawa | 118202008 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 679926 | 67201 | 747127 | 2011-03-11 | 2011-06-30 | 679926 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Kinabuhian |  | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 622775 | 63191 | 685966 | 2011-03-28 | 2011-06-30 | 622775 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Libuton |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 676750 | 37377 | 714127 | 2011-03-09 | 2011-05-31 | 676750 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Limot |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 681609 | 67318 | 748927 | 2011-03-16 | 2011-06-30 | 681609 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Longanapan | 118202012 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 664601 | 76126 | 740727 | 2011-03-03 | 2011-05-31 | 664601 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | LS Sarmiento |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 682729 | 67398 | 750127 | 2011-03-18 | 2011-06-30 | 682711 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Mabuhay | 118202030 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1177620 | 106752 | 1284372 | 2011-03-14 | 2011-04-30 | 1177620 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Mag-abay |  | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 678432 | 67095 | 745527 | 2011-03-04 | 2011-05-31 | 678432 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Malinao | 118202032 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 652078 | 105924 | 758002 | 2011-03-01 | 2011-06-30 | 652078 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Melale | 118202034 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1177559 | 106748 | 1284307 | 2011-03-08 | 2011-06-30 | 1177559 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Pahamutang |  | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 617309 | 62807 | 680116 | 2011-03-07 | 2011-05-31 | 617309 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Sabud | 118202037 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1178719 | 106828 | 1285547 | 2011-03-11 | 2011-06-30 | 1178719 | Completed
R11 | 11 | Compostela Valley | 1182 | Laak (San Vicente) | 118202 | Sisimon | 118202040 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 677122 | 67005 | 744127 | 2011-03-11 | 2011-05-31 | 677122 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Del Monte | 112314003 | Capability Building on Sustainable Agriculture with Diversified Farming System Model Farm and Rubber Nursery Establishment | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | CB | 6 | unit | 963056 | 232373 | 1195429 | 2011-02-15 | 2011-05-31 | 963056 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Del Pilar | 112314004 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 840951 | 359729 | 1200680 | 2010-10-16 | 2011-01-14 | 840951 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | New Sambog | 112314012 | Capability Building Program on Sustainable Agriculture | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | CB | 1 | unit | 895073 | 355501 | 1250574 | 2011-02-21 | 2011-05-31 | 895073 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Patrocenio | 112314013 | Construction of 3 Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 168 | sq.m | 1336718 | 350574 | 1687292 | 2010-10-18 | 2011-01-31 | 1336718 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Poblacion | 112314014 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 588004 | 147325 | 735329 | 2010-11-15 | 2011-04-30 | 588004 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | San Jose | 112314020 | Construction of Potable Water System Gravity Source Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 928200 | 266845 | 1195045 | 2010-10-25 | 2010-12-31 | 928200 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | San Roque | 112314015 | Improvement of Level II Potable Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 490779 | 246616 | 737395 | 2010-10-15 | 2010-12-31 | 490779 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Sta. Fe | 112314017 | Construction of 3 Classroom Building (HS) | 1 | Basic Social Services | School | SB | 168 | sq.m | 1352218 | 335074 | 1687292 | 2010-10-20 | 2011-01-31 | 1352218 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Sto. Niño | 112314018 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 807636 | 195074 | 1002710 | 2010-10-27 | 2011-01-25 | 807636 | Completed
R11 | 11 | Davao Del Norte | 1123 | New Corella | 112314 | Suawon | 112314019 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 797365 | 216119 | 1013484 | 2010-10-27 | 2011-01-25 | 797365 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Binoongan | 124718004 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1245131.97 | 139154.35 | 1384286.32 | 2011-04-04 | 2011-07-31 | 1182794.05 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Dallag | 124718005 | Construction of 1 Unit 1 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 63 | sq. m | 631112.91 | 70986.49 | 702099.4 | 2011-05-31 | 2011-08-15 | 695968.41 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Datu Matangkil | 124718007 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1251228.4 | 87450 | 1338678.4 | 2011-04-05 | 2011-07-31 | 1221228.4 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Doroluman | 124718008 | Construction of Barangay Public Terminal | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | MPC | 103.68 | sq.m | 764662.14 | 108074.68 | 872736.82 | 2011-03-04 | 2011-06-30 | 749324.32 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Ganatan | 124718010 | Constrcution of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1200532.37 | 117755.03 | 1318287.4 | 2011-04-19 | 2011-07-31 | 1179407.37 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Kabalantian | 124718012 | Concreting of 200M Poblacion-Lamaticun FMR | 1 | Basic Social Services | Road | RRC | 0.2 | kms | 1208088.87 | 250140 | 1458228.87 | 2011-02-07 | 2011-05-31 | 1186675.06 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Kulaman Valley | 124718015 | Construction of 30M Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | BC | 30 | ln.m | 655000 | 44900 | 699900 | 2011-04-06 | 2011-05-31 | 629550 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Lanao Kuran | 124718016 | Concreting of 200M Bagtok-Lanao Kuran FMR | 1 | Basic Social Services | Road | RRC | 0.2 | kms | 1435935.5 | 191404 | 1627339.5 | 2011-03-15 | 2011-08-15 | 1381755.5 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Libertad | 124718017 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1220874.91 | 119678.94 | 1340553.85 | 2011-04-01 | 2011-07-31 | 1200031.26 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Malibatuan | 124718019 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1176029.34 | 115423.06 | 1291452.4 | 2011-04-04 | 2011-06-30 | 1154609.34 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Meocan | 124718021 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1211087.81 | 118759.59 | 1329847.4 | 2011-03-02 | 2011-07-31 | 1190412.81 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Napalico | 124718023 | Construction of 1 Unit 2 Classroom School Builing (HS) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1238842.04 | 139263.28 | 1378105.32 | 2011-04-06 | 2011-07-31 | 1173004.11 | Completed
R12 | 12 | North Cotabato | 1247 | Arakan | 124718 | Tumanding | 124718028 | Concreting of 108M Centro-ES FMR | 1 | Basic Social Services | Road | RRC | 0.108 | kms | 683473.74 | 146786 | 830259.74 | 2011-03-02 | 2011-05-31 | 657692.4 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Datalblao | 126502009 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | SB | 56 | sq. m | 601868.26 | 60693.24 | 662561.5 | 2011-03-03 | 2011-06-30 | 574661.76 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Eday | 126502010 | Construction of Solar Dryer (800 sq.m) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 438036.48 | 68470.64 | 506507.12 | 2011-03-09 | 2011-05-31 | 410864.82 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Elbebe | 126502011 | Contruction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 716749.55 | 52020.95 | 768770.5 | 2011-03-21 | 2011-05-31 | 693410 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Lasak | 126502032 | Construction of 2 Units 20m x 20m Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 437330 | 69177.12 | 506507.12 | 2011-03-17 | 2011-05-31 | 415475.08 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Libertad | 126502015 | Construction of Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 434958.24 | 71548.88 | 506507.12 | 2011-05-11 | 2011-05-31 | 412330 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Lomoyon | 126502016 | Improvement of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 354160.17 | 29920.28 | 384080.45 | 2011-04-01 | 2011-05-31 | 323001.24 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Makat (Sumali Pas) | 126502017 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | SB | 56 | sq. m | 616986.5 | 45575 | 662561.5 | 2011-03-18 | 2011-05-31 | 587280 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Maligaya | 126502019 | Construction of 2 Units 20m x 20m Solar Driers | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 423330 | 83177.12 | 506507.12 | 2011-03-03 | 2011-05-31 | 400077.85 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Mayo | 126502021 | Construction of 2 Units 20m x 20m Solar Driers | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 432330 | 74177.12 | 506507.12 | 2011-04-05 | 2011-05-31 | 410475.08 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Natividad | 126502022 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 467249.6 | 59648.72 | 526898.32 | 2011-03-01 | 2011-06-30 | 444348 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Bantangan (Lasak) | 126502002 | Construction of 2 Units 20m x 20m Solar Driers | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 434330 | 72177.12 | 506507.12 | 2011-04-04 | 2011-05-31 | 412475.08 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Poblacion | 126502023 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | RC | 0.6 | kms | 655075.26 | 362486 | 1017561.26 | 2011-02-28 | 2011-05-31 | 646383.1 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Polomolok | 126502024 | Construction of Potable Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 423394.06 | 37454.49 | 460848.55 | 2011-03-21 | 2011-05-31 | 410044.99 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Sinapulan | 126502027 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | SB | 56 | sq. m | 615928.1 | 46633.4 | 662561.5 | 2011-03-08 | 2011-05-31 | 586955 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Sucob | 126502028 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 522943.78 | 51452.54 | 574396.32 | 2011-03-07 | 2011-06-30 | 497444.9 | Completed
R12 | 12 | Sultan Kudarat | 1265 | Columbio | 126502 | Telafas | 126502030 | Construction of 2 Units 20m x 20m Solar Driers | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 800 | sq.m | 425330 | 81177.12 | 506507.12 | 2011-03-13 | 2011-05-31 | 403577.85 | Completed
R12 | 12 | Sarangani | 1280 | Maasim | 128004 | Amsipit | 128004001 | Construction of 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 143.2 | sq.m | 913078.9 | 329425.1 | 1242504 | 2010-11-22 | 2011-06-30 | 886828 | Completed
R12 | 12 | Sarangani | 1280 | Maasim | 128004 | Kanalo | 128004008 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 143.2 | sq.m | 1020897.55 | 181106.45 | 1202004 | 2010-11-23 | 2011-06-30 | 994664 | Completed
R12 | 12 | Sarangani | 1280 | Maasim | 128004 | Lumasal | 128004009 | Construction of 3 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 214.8 | sq.m | 1420042 | 243407 | 1663449 | 2010-11-18 | 2011-05-31 | 1351547 | Completed
R12 | 12 | Sarangani | 1280 | Maasim | 128004 | Lumatil | 128004010 | Construction of 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 143.2 | sq.m | 1020897.55 | 181106.45 | 1202004 | 2010-11-26 | 2011-07-31 | 994664 | Completed
R12 | 12 | Sarangani | 1280 | Maasim | 128004 | Malbang | 128004011 | Construction of 3 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 214.8 | sq.m | 1415042 | 243407 | 1658449 | 2010-11-11 | 2011-05-31 | 1415042 | Completed
R12 | 12 | Sarangani | 1280 | Maasim | 128004 | Poblacion | 128004014 | Construction of 3 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 214.8 | sq.m | 1415042 | 243407 | 1658449 | 2010-11-25 | 2011-06-30 | 1351547 | Completed
R12 | 12 | Sarangani | 1280 | Maitum | 128005 | Bati-an | 128005001 | Installation of 2 Units Corn Mill with Mini-Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 2 | unit | 975722.55 | 232020 | 1207742.55 | 2011-01-10 | 2011-05-31 | 975722.55 | Completed
R12 | 12 | Sarangani | 1280 | Maitum | 128005 | Kalaong | 128005003 | Construction of Water System Spring Development Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1678861.66 | 590449 | 2269310.66 | 2010-11-12 | 2011-05-31 | 1678861.66 | Completed
R12 | 12 | Sarangani | 1280 | Maitum | 128005 | Kiambing | 128005004 | Construction of 1 Unit 3 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 189 | sq.m | 1490440.79 | 253167 | 1743607.79 | 2010-11-18 | 2011-05-31 | 1490440.79 | Completed
R12 | 12 | Sarangani | 1280 | Maitum | 128005 | New La Union | 128005010 | Installation of Corn Mill & Corn Sheller with Solar Dryer and Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 1 | unit | 1227036.42 | 209080 | 1436116.42 | 2010-11-13 | 2011-05-31 | 1187619.44 | Completed
R12 | 12 | Sarangani | 1280 | Maitum | 128005 | Upo (Lanao) | 128005017 | Construction of 1 Unit 3 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 189 | sq.m | 1591642.39 | 253667 | 1845309.39 | 2010-11-15 | 2011-06-30 | 1540570.78 | Completed
R12 | 12 | Sarangani | 1280 | Maitum | 128005 | Wali (Kambuhan) | 128005018 | Construction of 1 Unit 3 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 189 | sq.m | 1586296.19 | 253307 | 1839603.19 | 2010-11-13 | 2011-05-31 | 1535759.2 | Completed
R12 | 12 | Sarangani | 1280 | Malapatan | 128006 | Daan Suyan | 128006001 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 112 | sq. m | 1085821 | 264179 | 1350000 | 2011-05-23 | 2011-11-15 | 1055821 | Completed
R12 | 12 | Sarangani | 1280 | Malapatan | 128006 | Kinam | 128006003 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 112 | sq. m | 1223199 | 297641 | 1520840 | 2011-05-23 | 2012-03-15 | 1193199 | Completed
R12 | 12 | Sarangani | 1280 | Malapatan | 128006 | Libi | 128006004 | Proposed Drilling of Potable Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 788518 | 191942 | 980460 | 2011-05-16 | 2011-07-31 | 761579.48 | Completed
R12 | 12 | Sarangani | 1280 | Malapatan | 128006 | Patag | 128006007 | Construction of 1 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 56 | sq. m | 626842 | 152608 | 779450 | 2011-05-23 | 2011-07-31 | 612914.59 | Completed
R12 | 12 | Sarangani | 1280 | Malapatan | 128006 | Tuyan | 128006011 | Construction of 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 112 | sq. m | 992369 | 241631 | 1234000 | 2011-05-23 | 2011-10-15 | 973767.31 | Completed
R12 | 12 | Sarangani | 1280 | Malapatan | 128006 | Upper Suyan | 128006012 | Installation of 1 Unit Corn Mill with Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 112 | sq.m | 1283251 | 311999 | 1595250 | 2011-05-21 | 2012-04-15 | 1258797.44 | Completed
R13 | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Bitaugan East | 166804003 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 122.29 | sq.m | 1027444 | 431075 | 1458519 | 2010-08-23 | 2011-01-31 | 989995.68 | Completed
R13 | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Bitaugan West | 166804004 | Construction of Bailey Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | BC | 30 | ln.m | 1147073 | 2634475 | 3781548 | 2010-10-02 | 2010-12-11 | 974613.4 | Completed
R13 | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | La Purisima (Palhe) | 166804008 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 534418 | 229689 | 764107 | 2010-08-23 | 2010-12-06 | 480976.2 | Completed
R13 | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Mat-e | 166804007 | Construction of River Bank Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 60 | ln.m | 870901 | 392714 | 1263615 | 2010-09-15 | 2010-12-06 | 833460 | Completed
R13 | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Poblacion | 166804009 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 632 | ln.m | 823518 | 348278 | 1171796 | 2010-08-23 | 2010-12-07 | 823518 | Completed
R13 | 16 | Surigao Del Sur | 1668 | Cagwait | 166804 | Tawagan | 166804005 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 546646 | 233769 | 780415 | 2010-09-15 | 2010-12-06 | 491981.4 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Asinan | 166716008 | Rehabilitation of Brgy. Road from Purok Tessa to Bayabas | 1 | Basic Access Infrastructure | Road | RR | 0.14 | kms | 778585 | 66000 | 844585 | 2011-03-25 | 2011-04-25 | 741162 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Caridad | 166716001 | Construction of 1 Unit Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 63 | sq.m | 651289 | 76000 | 727289 | 2011-03-22 | 2011-05-27 | 313717 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Centro | 166716009 | Construction of Solar Dryer Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 312 | sq.m | 219000 | 72000 | 291000 | 2011-03-21 | 2011-04-30 | 209362 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Consolacion | 166716012 | Rehabilitation of 660 Ln.m Road from Crossing Highway to Brgy. Proper | 1 | Basic Access Infrastructure | Road | RR | 0.66 | kms | 1140943 | 66000 | 1206943 | 2011-04-25 | 2011-06-25 | 1051896.46 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Datu | 166716013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 565462 | 76000 | 641462 | 2011-04-04 | 2011-05-27 | 539388 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Jaboy | 166716015 | Construction of 1 Unit Elem. School Building (Elem) | 1 | Basic Social Services | School | SB | 63 | sq.m | 651289 | 76000 | 727289 | 2011-04-11 | 2011-05-27 | 651284 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Katipunan | 166716002 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 721450 | 76000 | 797450 | 2011-04-22 | 2011-06-25 | 687894 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Maasin | 166716003 | Construction of River Protection Cum Fishermen's Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | WRF | 80 | ln.m | 550947 | 66000 | 616947 | 2011-03-28 | 2011-05-27 | 550947 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Mabuhay | 166716005 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 631450 | 76000 | 707450 | 2011-03-24 | 2011-06-25 | 601894 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Punta | 166716011 | Rehabilitation and Upgrading of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | SW | 80 | ln.m | 668781 | 16000 | 684781 | 2011-03-25 | 2011-05-27 | 635487 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | Salvacion | 166716006 | Construction of Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | SW | 80 | ln.m | 592354 | 66000 | 658354 | 2011-03-14 | 2011-05-27 | 564485 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Pilar | 166716 | San Roque | 166716007 | Construction of 1 Unit School Building (Elem) | 1 | Basic Social Services | School | SB | 63 | sq.m | 651289 | 76000 | 727289 | 2011-04-06 | 2011-06-25 | 651284.2 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Del Pilar | 166723001 | Construction of 400 ln.m. Junction Del Pilar-Kapihan FMR (Gravelling) | 1 | Basic Access Infrastructure | Road | RC | 0.4 | kms | 665816.91 | 228540.09 | 894357 | 2011-03-21 | 2011-05-31 | 633995.17 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Helene | 166723001 | Rehabilitation/Upgrading of Brgy. Street (336 ln.m) | 1 | Basic Access Infrastructure | Road | RR | 0.336 | kms | 437442 | 67507 | 504949 | 2011-03-16 | 2011-04-30 | 417441.22 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Honrado | 166723003 | Construction of Honrado-Tugbungan FMR with RCPC Installation (Gravelling 350 ln.m) | 1 | Basic Access Infrastructure | Road | RC | 0.35 | kms | 749809.5 | 136695.5 | 886505 | 2011-04-25 | 2011-06-25 | 719809 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Nueva Estrella | 166723005 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 748772 | 108088 | 856860 | 2011-03-12 | 2011-05-28 | 712771.33 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Pamosaingan | 166723006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 749416.6 | 84784.4 | 834201 | 2011-03-17 | 2011-05-28 | 714373.1 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | San Roque | 166723009 | Construction of Level II Gravity Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 759640.07 | 83630.93 | 843271 | 2011-04-15 | 2011-05-28 | 724125.53 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Sering | 166723011 | Construction of 100 ln.m. Sea Wall | 1 | Environmental Protection and Conservation | Sea Wall | SW | 100 | ln.m | 1031826 | 130714 | 1162540 | 2011-03-03 | 2011-05-28 | 973211 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Songkoy | 166723012 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 748772 | 108088 | 856860 | 2011-03-15 | 2011-05-31 | 712771.33 | Completed
R13 | 16 | Surigao Del Norte | 1667 | Socorro | 166723 | Sta. Cruz | 166723010 | Construction of Level II Gravity Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 1107878 | 165174 | 1273052 | 2011-03-07 | 2011-05-28 | 1067877.25 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Anitap | 160313013 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 641577 | 192475 | 834052 | 2010-09-15 | 2011-02-28 | 577419.3 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Bacay | 160313014 | Construction of Rain Water Collector | 1 | Basic Social Services | Water System | WS | 1 | system | 996847 | 299059 | 1295906 | 2010-12-15 | 2011-03-31 | 890755 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Caigangan | 160313015 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 638533 | 191589 | 830122 |  |  | 0 | Not yet started
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Caigangan | 160313015 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 638533 | 191589 | 830122 | 2010-09-15 | 2011-03-31 | 574685.4 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Candiis | 160313016 | Installation of Corn Sheller | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 1 | unit | 185839 | 60752 | 246591 | 2010-09-15 | 2010-09-25 | 148671.2 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Limot | 160313005 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 641573 | 192479 | 834052 |  |  | 0 | Not yet started
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Limot | 160313005 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 641573 | 192479 | 834052 | 2010-09-15 | 2011-02-28 | 576502.4 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Masayan | 160313007 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 2.18 | kms | 2623579 | 787040 | 3410619 |  |  | 0 | Not yet started
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Sawagan | 160313019 | Construction of Individual Ferro-Cement Cylindrical Rain Water Collector (166 Units) | 1 | Basic Social Services | Water System | WS | 1 | system | 1636780 | 491035 | 2127815 | 2010-09-15 | 2011-04-21 | 1541396 | Completed
R13 | 16 | Agusan Del Sur | 1603 | Veruela | 160313 | Sisimon | 160313020 | Construction of Potable Water System Level II (Pump Driven) | 1 | Basic Social Services | Water System | WS | 1 | system | 1607242 | 482200 | 2089442 | 2010-09-15 | 2011-02-28 | 1446518 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Barangay 8 | 045610010 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 3000 | ln.m | 2667686.71 | 323313.29 | 2991000 | 2011-02-15 | 2011-05-31 | 2667686.71 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Camandiison | 045610014 | Improvement of FMR | 1 | Basic Access Infrastructure | Road | RR | 1.889 | kms | 2167763.69 | 866236.31 | 3034000 | 2011-01-10 | 2011-05-31 | 2167763.69 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Doongan Ibaba | 045610021 | Improvement of FMR | 1 | Basic Access Infrastructure | Road | RR | 3 | kms | 2353221.32 | 702539.61 | 3055760.93 | 2011-05-25 | 2011-10-15 | 2353221.33 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Macpac | 045610024 | Improvement of Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 904797.23 | 399202.77 | 1304000 | 2011-01-04 | 2011-05-31 | 904797.23 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Milagrosa | 045610028 | Improvement of FMR | 1 | Basic Access Infrastructure | Road | RR | 2.183 | kms | 2711316.48 | 1430715.49 | 4142031.97 | 2011-02-08 | 2012-06-15 | 2711316.47 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | San Pablo Suha | 045610035 | Improvement of FMR | 1 | Basic Access Infrastructure | Road | RR | 3.983 | kms | 3522556.3 | 1326443.7 | 4849000 | 2011-02-15 | 2011-10-15 | 3522556.3 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | San Vicente Silangan | 045610038 | Improvement of FMR | 1 | Basic Access Infrastructure | Road | RR | 1.485 | kms | 1538875 | 624125 | 2163000 | 2011-01-17 | 2011-05-31 | 1538875 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Tagabas Ibaba | 045610040 | Construction of 1 Unit 4 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 252 | sq.m | 1954639.42 | 773360.58 | 2728000 | 2011-01-13 | 2011-03-31 | 1954639.42 | Completed
R4A | 04 | Quezon | 0456 | Catanauan | 045610 | Tagabas Ilaya | 045610041 | Improvement of FMR | 1 | Basic Access Infrastructure | Road | RR | 2.098 | kms | 2527320 | 916680 | 3444000 | 2011-02-02 | 2011-05-31 | 2399971.11 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Candangal | 045625004 | Expansion of Water System (1,825 ln m) | 1 | Basic Social Services | Water System | WS | 1 | system | 1284703.16 | 430310.84 | 1715014 | 2011-01-03 | 2011-05-31 | 1254334.19 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Damayan | 045625022 | Construction of Open Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 314 | ln.m | 835755.86 | 217008.14 | 1052764 | 2010-12-28 | 2011-05-31 | 835755.86 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Luctob | 045625007 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | SW | 240 | ln.m | 5792771.05 | 634520.95 | 6427292 | 2011-01-03 | 2011-06-30 | 5792771.05 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Mabini Ilaya | 045625008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 601818 | 147735 | 749553 | 2011-01-03 | 2011-03-31 | 601818 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Olongtao Ibaba | 045625012 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 559850.42 | 215173.58 | 775024 | 2011-01-18 | 2011-04-30 | 559850.42 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Rizal | 045625018 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 465412.55 | 180543.45 | 645956 | 2010-12-20 | 2011-03-31 | 465412.55 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | San Jose | 045625024 | Re-construction of 1.874 FMR with 600m concreting | 1 | Basic Social Services | Road | RRC | 1.874 | kms | 1202908 | 1770082 | 2972990 | 2011-01-04 | 2011-06-30 | 1202908 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Taguin | 045625027 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 486301.85 | 272225.15 | 758527 | 2011-01-15 | 2011-04-30 | 486301.85 | Completed
R4A | 04 | Quezon | 0456 | Macalelon | 045625 | Vista Hermosa | 045625030 | Construction of Cable Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | BC | 75 | ln.m | 2076601.6 | 638930.4 | 2715532 | 2011-02-01 | 2011-06-30 | 2041517.12 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Ambolong | 054101001 | Construction of Pathways | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.7 | kms | 1101341.85 | 231500 | 1332841.85 | 2011-02-07 | 2011-05-31 | 1093947 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Amutag | 054101003 | Construction of 1 Classroom School Building (Concrete Slab Roofing) (Elem) | 1 | Basic Social Services | School | SB | 63 | sq. m | 726405 | 245714 | 972119 | 2011-01-31 | 2011-08-15 | 726405 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Bagauma | 054101004 | Road Concreting | 1 | Basic Social Services | Road | RRC | 0.25 | kms | 934856 | 220500 | 1155356 | 2011-02-14 | 2011-05-31 | 881862.86 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Balawing | 054101005 | Construction of 1 Classroom School Building (Concrete Slab Roofing) (HS) | 1 | Basic Social Services | School | SB | 63 | sq. m | 895773 | 181239 | 1077012 | 2011-02-07 | 2011-07-31 | 762580 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Balete | 054101006 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 792043.74 | 159448.11 | 951491.85 | 2011-01-31 | 2011-05-31 | 772710.9 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Cabangcalan | 054101008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 742018 | 145331 | 887349 | 2011-01-25 | 2011-06-30 | 631458 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Concepcion | 054101012 | Road Concreting | 1 | Basic Social Services | Road | RRC | 0.2 | kms | 881922.21 | 156960 | 1038882.21 | 2011-01-25 | 2011-05-31 | 853047 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Dayhagan | 054101013 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 953408.48 | 178126.17 | 1131534.65 | 2011-02-14 | 2011-05-31 | 901740.16 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Don Pablo Dela Rosa | 054101014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 615103 | 166687 | 781790 | 2011-04-30 | 2011-07-31 | 615103 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Lanang | 054101017 | Road Concreting | 1 | Basic Social Services | Road | RRC | 0.25 | kms | 778698.73 | 155951 | 934649.73 | 2011-01-22 | 2011-05-31 | 736453.5 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Luy-a | 054101018 | Re-gravelling w/ Concrete Lined Canal & Concreting of Pathways | 1 | Basic Social Services | Road | RRC | 0.4 | kms | 817324.2 | 185780.8 | 1003105 | 2011-02-07 | 2011-06-30 | 773629.2 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Mataba | 054101024 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1125604.13 | 217015.52 | 1342619.65 | 2011-02-21 | 2011-05-31 | 1063884.15 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Matalangtalang | 054101025 | Construction of Health Station (Concrete Slab Roofing) | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 611621 | 166336 | 777957 | 2011-02-08 | 2011-07-31 | 611621 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Matongog | 054101026 | Construction of Barangay Health Station (Concrete Slab Roofing) | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 597921 | 200981 | 798902 | 2011-02-16 | 2011-07-31 | 597921 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Nabongsoran | 054101027 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 706983.4 | 152173.6 | 859157 | 2011-04-30 | 2011-07-31 | 599601.4 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Pangle | 054101028 | Road Concreting | 1 | Basic Social Services | Road | RRC | 0.635 | kms | 1492921 | 341400 | 1834321 | 2011-02-07 | 2011-07-31 | 1418668 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Pinanaan | 054101030 | Road Concreting | 1 | Basic Social Services | Road | RRC | 0.27 | kms | 821400.9 | 168600 | 990000.9 | 2011-02-07 | 2011-05-31 | 776757.1 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Poblacion | 054101031 | Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 270 | ln.m | 994043.9 | 237600 | 1231643.9 | 2011-02-07 | 2011-05-31 | 937418 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Sawang | 054101035 | Construction of 1 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 63 | sq. m | 849502 | 182774 | 1032276 | 2011-02-02 | 2011-07-31 | 771165 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Talib | 054101038 | Construction of Day Care Center (Concrete Slab Roofing) | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 845406.2 | 146680.8 | 992087 | 2011-02-14 | 2011-06-30 | 729885.2 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Tigbao | 054101039 | Extension of Water System Level II to Sitio Tangig | 1 | Basic Social Services | Water System | WS | 1 | system | 989250.58 | 200763.57 | 1190014.15 | 2011-01-31 | 2011-05-31 | 977409.43 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Tinago | 054101040 | Construction of Concrete Pathways with Box Culvert | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.475 | kms | 816018.49 | 187500 | 1003518.49 | 2011-01-26 | 2011-05-31 | 770493.8 | Completed
R5 | 05 | Masbate | 0541 | Aroroy | 054101 | Tinigban | 054101041 | Construction of Barangay Health Station (Concrete Slab Roofing) | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 747601 | 184901 | 932502 | 2011-01-31 | 2011-08-15 | 618761 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Begia | 054106002 | Construction of Barangay Health Station with Rain Water Collector | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 586853.37 | 280861.61 | 867714.98 | 2011-01-15 | 2011-03-31 | 555237.61 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Cabayugan | 054106003 | Construction of 1 Unit Day Care Center with Rain Water Collector | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 544580.86 | 276817.68 | 821398.54 | 2010-11-15 | 2011-04-30 | 508538.07 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Cabungahan | 054106004 | Construction of 1 Unit Warehouse Building and Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 32 | sq.m | 910950.86 | 440613.78 | 1351564.64 | 2010-11-17 | 2011-04-30 | 849519.21 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Calapayan | 054106005 | Construction of 1 Unit 2 Classroom School with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 953123.79 | 400684.85 | 1353808.64 | 2010-10-13 | 2011-03-31 | 953123.76 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Chico Island | 054106031 | Construction of 1 Unit Health Station with Rain Water Collector | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 636539.18 | 327717.95 | 964257.13 | 2011-01-06 | 2011-04-30 | 594443.6 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Guiom | 054106009 | Construction of 1 Unit Day Care Center with Rain Water Collector | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 551751.72 | 270238.07 | 821989.79 | 2011-01-24 | 2011-03-31 | 515442.68 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Itombato | 054106011 | Construction of 1 Unit Day Care Center with Rain Water Collector | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 563244.77 | 262529.37 | 825774.14 | 2010-11-07 | 2011-03-31 | 563244.77 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Lague-Lague | 054106032 | Construction of 1 Unit 2 Classroom School with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 923481.68 | 452066.96 | 1375548.64 | 2010-10-28 | 2011-03-31 | 862074.6 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Libertad | 054106012 | Construction of 1 Unit 2 Classroom School with Rain Water Collector (HS) | 1 | Basic Social Services | School | SB | 126 | sq.m | 920197.29 | 443665.1 | 1363862.39 | 2010-10-11 | 2011-03-31 | 920197.29 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Looc | 054106013 | Construction of 1 Unit 3 Classroom School with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 189 | sq.m | 1293856.9 | 613481.7 | 1907338.6 | 2011-01-14 | 2011-05-31 | 1206959.82 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Mactan | 054106014 | Construction of 1 Unit Day Care Center with Rain Water Collector | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 543085.37 | 269218.17 | 812303.54 | 2010-10-19 | 2011-04-30 | 507237.58 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Madbad | 054106015 | Construction of 1 Unit Day Care Center with Rain Water Collector | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 578287.62 | 237493.52 | 815781.14 | 2010-11-08 | 2011-03-31 | 578287.62 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Malbug | 054106019 | Construction of 1 Unit 3 Classroom School Building with Rain Water Collector (HS) | 1 | Basic Social Services | School | SB | 189 | sq.m | 1235614.74 | 587752.86 | 1823367.6 | 2010-11-12 | 2011-05-31 | 1152918.66 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Pananawan | 054106021 | Construction of 1 Unit 2 Classroom School Building with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 941010.26 | 460633.38 | 1401643.64 | 2010-10-29 | 2011-05-31 | 877408.18 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Pin-As | 054106035 | Construction of 1 Unit Day Care Center with Rain Water Collector | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 572973.26 | 266738.58 | 839711.84 | 2011-01-18 | 2011-03-31 | 572973.26 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Pulot | 054106023 | Construction of 1 Unit 2 Classroom School Building with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 937998.49 | 440821.5 | 1378819.99 | 2010-11-16 | 2011-04-30 | 889425.06 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Punta Batsan | 054106037 | Construction of 1 Unit 3 Classroom School with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 189 | sq.m | 1408220.06 | 503318.54 | 1911538.6 | 2011-01-20 | 2011-05-31 | 1321122.98 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Recodo | 054106024 | Construction of 1 Unit Health Station with Rain Water Collector | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 597939.96 | 285682.42 | 883622.38 | 2010-12-13 | 2011-03-31 | 558145.96 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | San Vicente | 054106026 | Construction of 1 Unit 2 Classroom School Building with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 948045.59 | 408863.04 | 1356908.63 | 2011-01-12 | 2011-03-31 | 886478.52 | Completed
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | San Vicente | 054106026 | 1 Unit 2 Classrooms School Building | 1 | Basic Social Services | School | SB | 126 | sq. m | 948045.59 | 408863.04 | 1356908.63 |  |  | 0 | Not yet started
R5 | 05 | Masbate | 0541 | Cawayan | 054106 | Villahermosa | 054106030 | Construction of 1 Unit 2 Classroom School with Rain Water Collector (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 1002244.23 | 380740.59 | 1382984.82 | 2010-10-10 | 2011-03-31 | 939387.82 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Binanuahan | 056210004 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 1.5 | kms | 1742312 | 273168 | 2015480 | 2011-04-06 | 2011-06-30 | 1558660 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Biriran | 056210005 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.917 | kms | 1153434 | 151803 | 1305237 | 2011-04-04 | 2011-05-31 | 1095304 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Calmayon | 056210008 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 2.526 | kms | 2475136 | 236060 | 2711196 | 2011-04-25 | 2011-06-30 | 2348040 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Carohayon | 056210009 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.268 | kms | 346118 | 114837 | 460955 | 2011-04-04 | 2011-05-31 | 327953 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Catanusan | 056210011 | Construction of Irrigation System (500.00 ln.m) | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | CIS | 80 | has. | 1161044 | 368786 | 1529830 | 2011-04-28 | 2011-06-30 | 1108957.3 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Embarcadero | 056210013 | Construction of School Building (Elem) | 1 | Basic Social Services | School | SB | 63 | sq. m | 635992 | 135078 | 771070 | 2011-05-05 | 2011-06-01 | 607648.8 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Maalo | 056210017 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 2.812 | kms | 3072046 | 274473 | 3346519 | 2011-04-25 | 2011-06-30 | 2915712 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Rangas | 056210022 | Conctruction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 539851 | 225120 | 764971 | 2011-04-29 | 2011-05-31 | 539851 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Sablayan | 056210023 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 593589 | 148260 | 741849 | 2011-05-11 | 2011-05-31 | 562763 | Completed
R5 | 05 | Sorsogon | 0562 | Juban | 056210 | Tinago | 056210026 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.538 | kms | 710031 | 133994 | 844025 | 2011-04-04 | 2011-05-31 | 673855 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Abas | 056213001 | Construction of Community and Productivity Center (Concrete Slab Roofing) | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | MPC | 48 | sq.m | 715730 | 81733 | 797463 | 2011-05-04 | 2011-06-30 | 715730 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Banuyo | 056213004 | Drainage Facility | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 530 | ln.m | 1088000 | 116815 | 1204815 | 2011-05-08 | 2011-05-31 | 1032467 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Bayasong | 056213005 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 699000 | 84000 | 783000 | 2011-03-03 | 2011-05-31 | 663745 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Bayawas | 056213006 | Construction of Barangay Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 670000 | 72858 | 742858 | 2011-04-03 | 2011-05-31 | 637929 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Binanuahan | 056213007 | Drainage Facility | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 575 | ln.m | 1093000 | 115994 | 1208994 | 2011-03-15 | 2011-05-31 | 1037453 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Calongay | 056213011 | Irrigation Facility | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | CIS | 4 | has. | 391000 | 15141 | 406141 | 2011-04-26 | 2011-05-31 | 373068 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Catamlangan | 056213013 | Strategic Access Facility (Pathway) | 1 | Basic Access Infrastructure | Access Trail | RFP | 1.122 | kms | 633000 | 51472 | 684472 | 2011-03-13 | 2011-05-31 | 590543 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Danlog | 056213015 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 667004 | 81000 | 748004 | 2011-04-04 | 2011-05-31 | 667007 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Dao | 056213016 | Drainage Facility | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 620 | ln.m | 1190000 | 156210 | 1346210 | 2011-03-10 | 2011-05-31 | 1128550 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Dapdap | 056213017 | Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 1.58 | kms | 1550000 | 538713 | 2088713 | 2011-05-24 | 2011-10-15 | 1453055 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Esmerada | 056213019 | Construction of 1 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 63 | sq. m | 684000 | 74000 | 758000 | 2011-03-15 | 2011-05-31 | 649894 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Esperanza | 056213020 | Strategic Access Facility (Pathway) | 1 | Basic Access Infrastructure | Access Trail | RFP | 1.2 | kms | 917000 | 67719 | 984719 | 2011-03-27 | 2011-05-31 | 872437 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Inapugan | 056213024 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 690122 | 84000 | 774122 | 2011-03-07 | 2011-05-31 | 690122 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Lipason | 056213027 | Community & Productivity Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | MPC | 48 | sq.m | 717730 | 81733 | 799463 | 2011-05-04 | 2011-06-30 | 717730 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Lourdes | 056213028 | Construction of Barangay Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1108000 | 97026 | 1205026 | 2011-04-13 | 2011-05-31 | 1054544 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Lubiano | 056213025 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 706740 | 66000 | 772740 | 2011-04-02 | 2011-05-31 | 705940 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Lumbang | 056213030 | Construction of Barangay Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 1216000 | 144401 | 1360401 | 2011-03-18 | 2011-05-31 | 1153690 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Lungib | 056213029 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 687940 | 84000 | 771940 | 2011-03-23 | 2011-05-31 | 687940 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Marifosque | 056213033 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 638000 | 62000 | 700000 | 2011-03-17 | 2011-05-31 | 605863 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Mercedes | 056213034 | Construction of Barangay Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 758000 | 65919 | 823919 | 2011-04-01 | 2011-05-31 | 731460 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Naspi | 056213036 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 633000 | 67000 | 700000 | 2011-03-14 | 2011-05-31 | 600863 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Palanas | 056213037 | Barangay Community Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | PM | 72 | sq.m | 609000 | 68166 | 677166 | 2011-04-18 | 2011-05-31 | 579463 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Pinagsalog | 056213039 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 725740 | 46000 | 771740 | 2011-03-01 | 2011-05-31 | 725740 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Pineda | 056213040 | Construction of Barangay Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 936000 | 66035 | 1002035 | 2011-03-24 | 2011-05-31 | 890203 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Pudo | 056213043 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 687940 | 84000 | 771940 | 2011-03-19 | 2011-05-31 | 687940 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Sacnangan | 056213045 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 694940 | 77000 | 771940 | 2011-03-28 | 2011-05-31 | 694940 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | San Antonio (Millabas) | 056213047 | Construction of Irrigation System | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | CIS | 10 | has. | 788000 | 72264 | 860264 | 2011-03-07 | 2011-05-31 | 749457 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | San Antonio (Sapa) | 056213048 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 1.953 | kms | 1201000 | 90964 | 1291964 | 2011-03-16 | 2011-05-31 | 1142119 | Completed
R5 | 05 | Sorsogon | 0562 | Pilar | 056213 | Santa Fe | 056213051 | Construction of Flood Control System | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 495 | ln.m | 1067000 | 126718 | 1193718 | 2011-03-22 | 2011-05-31 | 1013024 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Boca-Chica | 054120001 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 135 | ln.m | 581958.1 | 214947 | 796905.1 | 2011-04-15 | 2011-06-30 | 546153.95 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Bolod | 054120002 | Construction of 1 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 63 | sq. m | 597712.5 | 198257 | 795969.5 | 2011-05-02 | 2011-06-30 | 628535.5 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Cueva | 054120024 | Construction of Mini-Port | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | WRF | 100 | ln.m | 712281.98 | 314547 | 1026828.98 | 2011-04-23 | 2011-06-30 | 665835.88 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Dancalan | 054120004 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 893067.35 | 335664 | 1228731.35 | 2011-04-18 | 2011-06-30 | 837509 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Halabangbaybay | 054120005 | Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.35 | kms | 387309.75 | 240545 | 627854.75 | 2011-04-26 | 2011-06-30 | 359426.9 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Iniwaran | 054120006 | Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.2 | kms | 961389.7 | 259995 | 1221384.7 | 2011-04-26 | 2011-06-30 | 906099 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Ki-Romero | 054120008 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 539267.15 | 248607 | 787874.15 | 2011-05-08 | 2011-06-30 | 617825.65 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Laurente | 054120009 | Concreting of One (1) Lane Farm to Market Road | 1 | Basic Social Services | Road | RRC | 0.474 | kms | 670907.25 | 243662 | 914569.25 | 2011-04-25 | 2011-05-31 | 629972 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Mabuhay | 054120011 | Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.5 | kms | 758399.96 | 247419 | 1005818.96 | 2011-04-21 | 2011-05-31 | 726263.86 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Malaking Ilog | 054120025 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.427 | kms | 518211.16 | 247102 | 765313.16 | 2011-04-25 | 2011-05-31 | 484082.96 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Nazareno | 054120014 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.78 | kms | 1092299.5 | 312416 | 1404715.5 | 2011-04-28 | 2011-06-30 | 1028190 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Quintina | 054120016 | Construction of 1 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 63 | sq. m | 609759.1 | 253533 | 863292.1 | 2011-04-18 | 2011-06-30 | 570892 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | San Jose | 054120019 | Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.42 | kms | 566480.38 | 298298 | 864778.38 | 2011-04-27 | 2011-06-30 | 527625.43 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | San Pedro | 054120020 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 495851.94 | 262973 | 758824.94 | 2011-04-13 | 2011-06-30 | 565468.34 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | San Rafael | 054120021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 604537.5 | 197647 | 802184.5 | 2011-05-08 | 2011-06-30 | 555705.6 | Completed
R5 | 05 | Masbate | 0541 | San Pascual | 054120 | Sta. Cruz | 054120022 | Concreting Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.504 | kms | 755787.58 | 255468 | 1011255.58 | 2011-04-14 | 2011-06-30 | 720801.98 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Adcadarao | 063001001 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq.m | 1150000 | 252600 | 1402600 | 2011-01-07 | 2011-04-30 | 1150000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Agbobolo | 063001002 | Construction of Health Station with Basic Facilities | 1 | Basic Social Services | Health Station | HS | 55.5 | sq.m | 511000 | 224450 | 735450 | 2011-01-15 | 2011-05-31 | 510627 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Badiangan | 063001003 | Construction of Reinforced Concrete Pipe Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 12 | ln.m | 24000 | 150630 | 174630 | 2011-02-11 | 2011-05-31 | 23802.5 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Barrido | 063001004 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 126 | sq.m | 1095000 | 295284 | 1390284 | 2011-01-05 | 2011-04-30 | 1095000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Bay-ang | 063001006 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq.m | 582000 | 806159 | 1388159 | 2011-01-07 | 2011-04-30 | 581275 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Bucana Bunglas | 063001007 | Construction of 1 Unit 1 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 81.9 | sq.m | 510000 | 226530 | 736530 | 2011-01-10 | 2011-05-25 | 510000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Central | 063001008 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq.m | 1110000 | 263750 | 1373750 | 2011-01-14 | 2011-04-30 | 1110000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Culasi | 063001009 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1142000 | 294469 | 1436469 | 2011-01-03 | 2011-04-30 | 1142000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Luca | 063001011 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1011000 | 351070 | 1362070 | 2011-01-14 | 2011-04-30 | 1010364 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Malayu-an | 063001012 | Construction of 1 Unit 1 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 63 | sq. m | 482000 | 253180 | 735180 | 2011-01-11 | 2011-05-25 | 481975 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Mangorocoro | 063001013 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1068000 | 296930 | 1364930 | 2011-01-12 | 2011-04-30 | 1068000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Pantalan Navarro | 063001016 | Road Improvement of 0.48 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.48 | kms | 447000 | 194520 | 641520 | 2011-01-14 | 2011-05-25 | 446673 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Pedada | 063001017 | Road Improvement of 1.031 Km. Drainage Culvert | 1 | Basic Access Infrastructure | Road | RR | 1.031 | kms | 689000 | 258640 | 947640 | 2011-01-11 | 2011-05-31 | 689000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Pili | 063001018 | Construction of 1 Unit 2 Classroom School Building with Amenities (HS) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1117000 | 307120 | 1424120 | 2011-01-06 | 2011-04-30 | 1117000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Poblacion | 063001022 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1100000 | 311300 | 1411300 | 2010-11-22 | 2011-04-30 | 1100000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Puente Bunglas | 063001024 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1006000 | 395870 | 1401870 | 2011-01-08 | 2011-04-30 | 1006000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Punta Buri | 063001025 | Construction of 1 Unit 1 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 80.91 | sq. m | 563000 | 189340 | 752340 | 2011-01-03 | 2011-05-25 | 563000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Rojas | 063001026 | Road Improvement of 0.34 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.34 | kms | 312000 | 152150 | 464150 | 2011-01-14 | 2011-05-25 | 311945 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | San Antonio | 063001027 | Construction of 1 Unit 2 Classroom School Building with Facilities (HS) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1061000 | 441800 | 1502800 | 2010-11-25 | 2011-04-30 | 1061000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Silagon | 063001028 | Construction of Day Care Center with Basic Facilities | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 574000 | 165590 | 739590 | 2011-01-08 | 2011-05-25 | 574000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Tagubanhan | 063001030 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1182000 | 213330 | 1395330 | 2011-01-11 | 2011-06-10 | 1182000 | Completed
R6 | 06 | Iloilo | 0630 | Ajuy | 063001 | Taguhangin | 063001031 | Construction of 448 sq.m. Solar Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 448 | sq.m | 264000 | 206100 | 470100 | 2011-01-25 | 2011-04-30 | 263534 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Agba-o | 063010001 | Construction of Day Care Center with Facilities | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 607955.18 | 81460 | 689415.18 | 2011-01-15 | 2011-06-30 | 581995 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Bulabog | 063010003 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 144 | sq.m | 1177522.46 | 104025 | 1281547.46 | 2011-01-17 | 2011-05-31 | 1133255.5 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Cairohan | 063010004 | Road Improvement of 1.2 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 1.2 | kms | 427656.72 | 1344825 | 1772481.72 | 2011-01-14 | 2011-08-15 | 361849 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Guinhulacan | 063010005 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 144 | sq. m | 1177522.46 | 104025 | 1281547.46 | 2011-01-17 | 2011-05-25 | 1133255.5 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Malitbog Ilaya | 063010008 | Construction of 1 Unit 2 Classroom School Building with Facilities (Elem) | 1 | Basic Social Services | School | SB | 130.5 | sq.m | 1177522.46 | 104025 | 1281547.46 | 2011-01-12 | 2011-05-25 | 1133255.5 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Ngingi-an | 063010009 | Construction of Day Care Center with Facilities | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 607955.18 | 81460 | 689415.18 | 2011-01-11 | 2011-06-30 | 581995 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Quinangyana | 063010011 | Construction of Day Care Center with Facilities | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 607955.18 | 81460 | 689415.18 | 2011-01-10 | 2011-06-30 | 581995 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Quinar-upan | 063010012 | Construction of Day Care Center with Facilities | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 607955.18 | 81460 | 689415.18 | 2011-01-15 | 2011-06-30 | 581995 | Completed
R6 | 06 | Iloilo | 0630 | Bingawan | 063010 | Tapacon | 063010013 | Construction of Day Care Center with Facilities | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 607955.18 | 81460 | 689415.18 | 2011-01-11 | 2011-06-30 | 581995 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Agnaga | 063015003 | Construction of 1 Unit Classroom School Building (PS) | 1 | Basic Social Services | School | SB | 64.6 | sq. m | 448817.08 | 199389.29 | 648206.37 | 2011-02-01 | 2011-05-31 | 423294.1 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Bacjawan Sur | 063015005 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 162.9 | sq. m | 860569.11 | 346797.93 | 1207367.04 | 2011-01-20 | 2011-05-31 | 809782.37 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Batiti | 063015007 | Construction of 1 Unit Classroom School Building (PS) | 1 | Basic Social Services | School | SB | 64.6 | sq. m | 461483.5 | 186249.29 | 647732.79 | 2011-02-06 | 2011-05-25 | 361555.5 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Botlog | 063015008 | Fabrication and Installation of Artificial Reefs | 1 | Environmental Protection and Conservation | Environmental Preservation (Artificial Coral Reef/Marine Sanctuary) | NRM | 150 | unit | 114186.75 | 323055.55 | 437242.3 | 2011-03-15 | 2011-06-30 | 100275.25 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Calamigan | 063015009 | Construction of 1 Unit Classroom School Building (PS) | 1 | Basic Social Services | School | SB | 64.6 | sq.m | 431019.08 | 206072.29 | 637091.37 | 2011-02-12 | 2011-05-31 | 405496.1 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Dungon | 063015010 | Solar Electrification (50 Units) | 1 | Basic Social Services | Electrification | EL | 267 | HH | 844647.23 | 288206.87 | 1132854.1 | 2011-04-14 | 2011-05-31 | 797402.5 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Jamul-awon | 063015012 | Construction of Post Harvest Facility (Recirculating Mechanical Dryer) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 60 | sq.m | 789903.81 | 332613.33 | 1122517.14 | 2011-03-18 | 2011-06-30 | 788548 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Loong | 063015013 | Construction of 1 Unit Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 64.6 | sq.m | 441687.08 | 195669.29 | 637356.37 | 2011-02-03 | 2011-05-31 | 416164.1 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Macalbang | 063015014 | Construction of 1 Unit Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 64.6 | sq.m | 415283.08 | 223258.29 | 638541.37 | 2011-02-02 | 2011-05-25 | 389760.1 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Macatunao | 063015015 | Construction of Brgy. Trail with Foot Bridge | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.3 | kms | 760538 | 398051.34 | 1158589.34 | 2011-03-10 | 2011-06-30 | 751522 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Malangabang | 063015016 | Construction of Mini-Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | PM | 108 | sq.m | 730992.28 | 184318.22 | 915310.5 | 2011-04-26 | 2011-08-15 | 718191.42 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Maliogliog | 063015017 | Construction of 1 Unit Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 64.6 | sq.m | 542771.61 | 126275.04 | 669046.65 | 2011-02-26 | 2011-06-30 | 516287.54 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Niño | 063015018 | Construction of 1 Unit Classroom School Building (PS) | 1 | Basic Social Services | School | SB | 64.6 | sq. m | 441151.08 | 206465.29 | 647616.37 | 2011-03-11 | 2011-05-31 | 415628.1 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Nipa | 063015019 | Fabrication and Installation of Artificial Reefs | 1 | Environmental Protection and Conservation | Environmental Preservation (Artificial Coral Reef/Marine Sanctuary) | NRM | 150 | unit | 389069.75 | 82992.3 | 472062.05 | 2011-02-18 | 2011-06-30 | 371097.01 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Plandico | 063015021 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 658803.69 | 183052.56 | 841856.25 | 2011-04-26 | 2011-07-31 | 624961.57 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Poblacion | 063015022 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 440 | ln.m | 836640.7 | 345581.85 | 1182222.55 | 2011-02-04 | 2011-07-31 | 806397 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Polopina | 063015023 | Construction of 1 Unit Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 61.6 | sq.m | 651485.21 | 231040.16 | 882525.37 | 2011-04-26 | 2011-07-31 | 624692.5 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Salvacion | 063015024 | Construction of 1 Unit Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 64.6 | sq. m | 553697.61 | 117174.04 | 670871.65 | 2011-02-04 | 2011-05-31 | 527216.53 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Talotu-an | 063015025 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 478439.95 | 264681.72 | 743121.67 | 2011-02-26 | 2011-05-31 | 455777.72 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Tambaliza | 063015026 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 162.9 | sq.m | 728399.59 | 347336.95 | 1075736.54 | 2011-02-04 | 2011-05-31 | 726439.59 | Completed
R6 | 06 | Iloilo | 0630 | Concepcion | 063015 | Tamis-ac | 063015027 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 0.32 | kms | 920413.81 | 224422.71 | 1144836.52 | 2011-02-01 | 2011-06-30 | 828372.13 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Agbun-od | 061906002 | Road Improvement with Intermittent Construction of PCCP 310 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.82 | kms | 658000 | 96333.99 | 754333.99 | 2011-01-17 | 2011-06-30 | 638303.14 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Agcagay | 061906003 | Road Improvement with Intermittent Construction of PCCP 360 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.25 | kms | 653000 | 94585.38 | 747585.38 | 2011-01-17 | 2011-06-30 | 633320.55 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Agloloway | 061906005 | Road Improvement with Intermittent Construction of PCCP 400 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 0.4 | kms | 783600 | 112141.29 | 895741.29 | 2011-01-24 | 2011-06-30 | 759866.03 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Bayebaye | 061906006 | Road Improvement with Intermittent Construction of PCCP 320 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.4 | kms | 485000 | 91466.68 | 576466.68 | 2011-01-17 | 2011-06-30 | 470255.1 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Esperanza | 061906008 | Road Improvement with Intermittent Construction of PCCP 320 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 0.94 | kms | 646090.42 | 92074.56 | 738164.98 | 2011-01-03 | 2011-06-30 | 626711 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Fe | 061906009 | Road Improvement of 250 ln.m PCCP FMR | 1 | Basic Access Infrastructure | Road | RR | 0.25 | kms | 617700 | 83075.11 | 700775.11 | 2011-01-17 | 2011-06-30 | 599203.39 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Igang | 061906012 | Road Improvement with Intermittent Construction of PCCP 300 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 2.4 | kms | 606600 | 92266.73 | 698866.73 | 2011-01-24 | 2011-06-30 | 588525.97 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Jaena Sur | 061906014 | Road Improvement with Intermittent Construction of PCCP 300 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.54 | kms | 598600 | 93904.69 | 692504.69 | 2011-02-14 | 2011-06-30 | 580634.09 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Jagnaya | 061906015 | Construction of Community Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | PM | 48 | sq.m | 466634.29 | 96690 | 563324.29 | 2011-01-17 | 2011-06-30 | 454425 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Lapaz | 061906016 | Road Improvement of 150 ln.m PCCP FMR | 1 | Basic Access Infrastructure | Road | RR | 0.41 | kms | 348600 | 83580.01 | 432180.01 | 2011-01-17 | 2011-06-30 | 338028.49 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Lucero | 061906018 | Improvement of 1.88 Km. RMR with Intermittent Concreting of 160 ln.m PCCP | 1 | Basic Access Infrastructure | Road | RR | 1.88 | kms | 1210000 | 82562.07 | 1292562.07 | 2011-01-10 | 2011-06-30 | 1174531.06 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Maantol | 061906019 | Road Improvement with Intermittent Construction of PCCP 380 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 0.54 | kms | 688900 | 106177.25 | 795077.25 | 2011-01-17 | 2011-06-30 | 668074.69 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Masgrau | 061906020 | Road Improvement of 200 on.m PCCP FMR | 1 | Basic Access Infrastructure | Road | RR | 0.2 | kms | 361800 | 83061.38 | 444861.38 | 2011-01-24 | 2011-06-30 | 350746.42 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Milan | 061906021 | Road Upgrading of 2.10 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 2.1 | kms | 1128000 | 84453.41 | 1212453.41 | 2011-01-17 | 2011-06-30 | 1095025.09 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Molet | 061906022 | Road Improvement with Intermittent Construction of PCCP 250 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.02 | kms | 515500 | 89719.28 | 605219.28 | 2011-01-17 | 2011-05-25 | 499956.09 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabat | 061906023 | Road Improvement of 115 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 0.115 | kms | 465600 | 85016.01 | 550616.01 | 2011-01-17 | 2011-06-30 | 451512.49 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Pangabuan | 061906024 | Road Improvement with Intermittent Construction of PCCP 360 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.15 | kms | 636200 | 94592.5 | 730792.5 | 2011-01-17 | 2011-06-30 | 617111.63 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Pasol-o | 061906025 | Road Improvement of 1.0 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 1 | kms | 1134500 | 99747.77 | 1234247.77 | 2011-01-24 | 2011-07-31 | 1100986.72 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Poblacion | 061906026 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 162 | sq.m | 903775.29 | 117660 | 1021435.29 | 2011-01-03 | 2011-06-30 | 891161.5 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | San Juan | 061906028 | Road Improvement with Intermittent Construction of PCCP 460 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 1.25 | kms | 970600 | 97022.5 | 1067622.5 | 2011-01-24 | 2011-11-15 | 941923.86 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | San Vicente | 061906029 | Improvement of Brgy. Road with 210 ln.m. PCCP | 1 | Basic Access Infrastructure | Road | RR | 0.21 | kms | 523400 | 92645.76 | 616045.76 | 2011-01-03 | 2011-02-28 | 507607.74 | Completed
R6 | 06 | Capiz | 0619 | Jamindan | 061906 | Sto. Rosario | 061906030 | Road Improvement with Intermittent Construction of PCCP 320 ln.m FMR | 1 | Basic Access Infrastructure | Road | RR | 2.51 | kms | 597900 | 92845.73 | 690745.73 | 2011-01-17 | 2011-06-30 | 579962.02 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Abangay | 063023001 | Construction of Two (2) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 169.8 | sq. m | 1151485.33 | 84350 | 1235835.33 | 2011-05-02 | 2011-06-30 | 1096404.84 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Aguingay | 063023004 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq.m | 616873.9 | 91317 | 708190.9 | 2011-01-17 | 2011-05-31 | 611134.07 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Aquino Nobleza East | 063023046 | Drainage System Improvement | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 200 | ln.m | 1274268 | 192070 | 1466338 | 2011-01-11 | 2011-06-30 | 1274268 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Barasalon | 063023008 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq.m | 641010.41 | 92072 | 733082.41 | 2011-01-23 | 2011-05-31 | 635807.7 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Bongol | 063023009 | Road Improvement of 0.30 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 1628617 | 102569 | 1731186 | 2011-03-05 | 2011-06-30 | 1628617 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Calmay | 063023011 | Construction of Flood Control/Dike | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 80 | ln.m | 1257188 | 107590 | 1364778 | 2011-01-14 | 2011-05-31 | 1257188 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Canawili | 063023012 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 58 | sq.m | 666834.51 | 103410 | 770244.51 | 2010-12-28 | 2011-06-30 | 662710.27 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Canawilian | 063023013 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq.m | 623501.21 | 147367 | 770868.21 | 2011-02-06 | 2011-06-30 | 619618.83 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Capt. A. Tirador | 063023060 | Drainage System Improvement | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 148 | ln.m | 518333 | 95095 | 613428 | 2011-01-10 | 2011-05-31 | 510387.04 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Caranas | 063023014 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 58 | sq.m | 628841.06 | 94980 | 723821.06 | 2011-01-31 | 2011-06-30 | 623492.4 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Caraudan | 063023015 | Road Improvement of 0.30 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 1006693 | 117870 | 1124563 | 2011-01-13 | 2011-06-30 | 1006693 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Carigangan | 063023016 | Road Improvement of 0.30 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 948280 | 101075 | 1049355 | 2011-02-05 | 2011-05-31 | 948280 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Cunsad | 063023017 | Road Improvement of 0.22 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.22 | kms | 820637.75 | 136610 | 957247.75 | 2011-02-21 | 2011-06-30 | 820637.75 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Dabong | 063023018 | Construction of Two (2) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 169.8 | sq.m | 944991.4 | 142345 | 1087336.4 | 2010-12-21 | 2011-06-30 | 944991.4 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Damires | 063023019 | Construction of Two (2) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 169.8 | sq.m | 968769.4 | 116167 | 1084936.4 | 2010-12-23 | 2011-05-31 | 968769.4 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Damo-ong | 063023020 | Road Improvement of 1.124 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 1.124 | kms | 1914223.86 | 104465 | 2018688.86 | 2011-02-22 | 2011-05-31 | 1914223.86 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Danao | 063023021 | Construction of Flood Control/Dike | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 100 | ln.m | 810208 | 91495 | 901703 | 2011-01-15 | 2011-05-31 | 809489.18 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Manacabac | 063023028 | Road Improvement of 0.30 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 1116859 | 135812 | 1252671 | 2011-02-05 | 2011-05-25 | 1116859 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Mangil | 063023029 | Construction of Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | BC | 50 | ln.m | 1148239 | 138536 | 1286775 | 2011-01-03 | 2011-05-25 | 1148239 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Monte Magapa | 063023031 | Road Improvement of 1.02 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 1.02 | kms | 1066617.24 | 1029916.51 | 2096533.75 | 2011-02-07 | 2011-05-31 | 1066617.24 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Pangilihan | 063023032 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq.m | 612720.9 | 95590 | 708310.9 | 2011-01-06 | 2011-05-31 | 607020.75 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Panuran | 063023033 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq. m | 605360.28 | 105188 | 710548.28 | 2011-01-13 | 2011-05-31 | 599545.89 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Pararinga | 063023034 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 58 | sq.m | 616456.06 | 109165 | 725621.06 | 2011-01-20 | 2011-05-31 | 611225.75 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Patong-patong | 063023035 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 532510.48 | 85587 | 618097.48 | 2010-12-23 | 2011-05-31 | 524514.24 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Quipot | 063023036 | Construction of Two (2) Classroom Building (HS) | 1 | Basic Social Services | School | SB | 169.8 | sq. m | 1052538.34 | 96403 | 1148941.34 | 2011-01-10 | 2011-06-30 | 1052538.34 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | San Julian | 063023057 | Road Improvement of 0.50 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.5 | kms | 786524 | 95780 | 882304 | 2011-02-01 | 2011-06-30 | 785177.89 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | San Pedro | 063023058 | Drainage System Improvement | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 65 | ln.m | 385187 | 79120 | 464307 | 2011-01-05 | 2011-06-30 | 373674.59 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Sarawag | 063023038 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 532510.48 | 85587 | 618097.48 | 2011-01-14 | 2011-06-30 | 524514.24 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | SM Villa, Aquino West, DTL West and Sta. Rita | 063023061, 063023047,063023054 & 063023059 | Construction of Two (2) Classroom School Building (Elem) | 4 | Basic Social Services | School | SB | 169.8 | sq.m | 1157304.9 | 146018 | 1303322.9 | 2010-12-22 | 2011-06-30 | 1157304.9 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Tambal | 063023039 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq. m | 600135.9 | 108100 | 708235.9 | 2011-01-05 | 2011-05-31 | 594552.24 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Tamu-an | 063023040 | Construction of One (1) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 84.9 | sq. m | 617265.9 | 91525 | 708790.9 | 2011-01-06 | 2011-05-31 | 611476.02 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Tiringanan | 063023041 | Road Improvement of 1.20 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 1.2 | kms | 1248163.14 | 135555 | 1383718.14 | 2011-03-05 | 2011-06-30 | 1248163.14 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Tolarucan | 063023042 | Construction of Two (2) Classroom Building (Elem) | 1 | Basic Social Services | School | SB | 169.8 | sq. m | 963809.4 | 121727 | 1085536.4 | 2010-12-27 | 2011-05-31 | 963809.4 | Completed
R6 | 06 | Iloilo | 0630 | Janiuay | 063023 | Tuburan | 063023043 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 527789.48 | 92468 | 620257.48 | 2010-12-21 | 2011-06-30 | 519891.73 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Cabagnaan | 064517004 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 133.2 | sq.m | 959773.94 | 156663.06 | 1116437 | 2010-11-19 | 2011-05-31 | 959773.93 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Lalagsan | 064517006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 468714.21 | 97459.79 | 566174 | 2010-11-09 | 2011-06-30 | 451678.39 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Manghanoy | 064517007 | Construction of 1 Unit 1 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 66.6 | sq.m | 621197.61 | 50900.39 | 672098 | 2010-11-22 | 2011-06-30 | 587777.84 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Puso | 064517011 | Road Improvement of 2.22 km Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 2.22 | kms | 245729.66 | 728171.34 | 973901 | 2010-11-22 | 2011-06-30 | 236406.87 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Robles | 064517012 | Construction of (Tricycle Lane) Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | BC | 12 | ln.m | 752546.78 | 146285.22 | 898832 | 2010-11-16 | 2011-05-31 | 716113.24 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Sag-Ang | 064517013 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 133.2 | sq. m | 981893.03 | 97904.97 | 1079798 | 2010-11-22 | 2011-05-31 | 981893.03 | Completed
R6 | 06 | Negros Occidental | 0645 | La Castellana | 064517 | Talaptap | 064517016 | Road Improvement of 3.23 Km Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 3.23 | kms | 1820144.78 | 177831.36 | 1997976.14 | 2010-11-22 | 2011-05-31 | 1739603.17 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Abay | 063029001 | Road Improvement of 0.47 Km. | 1 | Basic Access Infrastructure | Road | RR | 0.465 | kms | 1180990 | 331758 | 1512748 | 2011-02-11 | 2011-07-31 | 1130990 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Abilay | 063029002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 678552 | 83188 | 761740 | 2011-05-16 | 2011-08-04 | 648733 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Agrocel | 063029004 | Riverwall Protection of 267 Ln.m | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 267 | ln.m | 1665027.5 | 421689 | 2086716.5 | 2011-05-16 | 2012-06-15 | 1599793 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Amerang | 063029005 | Road Improvement of 0.55 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.545 | kms | 1288709 | 144918 | 1433627 | 2011-02-01 | 2011-07-31 | 1250153 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Bulay | 063029010 | Road Improvement of 0.43 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.43 | kms | 1331677.7 | 120923 | 1452600.7 | 2011-01-30 | 2011-07-31 | 1281677.7 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Cabangcalan | 063029013 | Road Improvement of 0.27 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.269 | kms | 1180418 | 103558 | 1283976 | 2011-01-24 | 2011-06-30 | 1130418 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Cabatac | 063029014 | Creekwall Protection of 0.220 Km. | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 220 | ln.m | 603215 | 85785 | 689000 | 2011-02-03 | 2011-07-31 | 576682 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Caigon | 063029015 | Road Improvement of 0.30 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.2992 | kms | 351876 | 59670 | 411546 | 2011-04-04 | 2011-08-15 | 343672 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Cananghan | 063029016 | Road Improvement of 0.410 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.41 | kms | 1099515.8 | 335273 | 1434788.8 | 2011-01-18 | 2011-07-31 | 1049515.8 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Canawili | 063029017 | Road Improvement of 0.30 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 1294551 | 111408 | 1405959 | 2011-01-21 | 2011-07-31 | 1244551 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Dagami | 063029020 | Road Improvement of 0.35 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.35 | kms | 1425186 | 117345 | 1542531 | 2011-01-11 | 2011-08-15 | 1372666 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Inabasan | 063029025 | Road Improvement of 0.400 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.4 | kms | 1066590 | 332708 | 1399298 | 2011-02-06 | 2011-07-31 | 1016590 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Linagan Calsada | 063029027 | Creekwall Protection of 180 Ln.m | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 180 | ln.m | 676871 | 118798 | 795669 | 2011-01-17 | 2011-06-30 | 616592 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Linagan Tacas | 063029028 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 641693 | 91938 | 733631 | 2011-05-16 | 2011-08-14 | 613117 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Mari Pob. (Mabini- Rizal) | 063029030 | Riverwall Protection of 410 Ln.m | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 410 | ln.m | 2710835.25 | 859634 | 3570469.25 | 2011-04-25 |  | 2560898.5 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Miapa | 063029033 | Road Improvement of 0.208 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.208 | kms | 1007817.75 | 147629.26 | 1155447.01 | 2011-02-09 | 2011-08-15 | 945976.75 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Pispis | 063029041 | Road Improvement 0.37 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.37 | kms | 1192848 | 327200 | 1520048 | 2011-01-24 | 2011-06-30 | 1142842 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Sinubsuban | 063029044 | Road Improvement of 1.08 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 1.08 | kms | 443084 | 718098 | 1161182 | 2011-01-22 | 2011-08-15 | 443084 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | THTP | 063029048 | Riverwall Protection of 224 Ln.m | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 224 | ln.m | 1445112.5 | 365619 | 1810731.5 | 2011-05-04 | 2012-06-15 | 1366820 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Tigbauan | 063029050 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 664648 | 84853 | 749501 | 2011-05-21 | 2011-08-19 | 635317 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Tubang | 063029052 | Road Improvement of 1.60 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 1.6 | kms | 893391 | 112808 | 1006199 | 2011-01-25 | 2011-06-30 | 843391 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Tulahong | 063029053 | Road Improvement of 0.26 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.261 | kms | 1143053 | 100553 | 1243606 | 2011-01-27 | 2011-06-30 | 1093053 | Completed
R6 | 06 | Iloilo | 0630 | Maasin | 063029 | Tuy-an East | 063029054 | Road Improvement of 0.20 Km. FMR | 1 | Basic Access Infrastructure | Road | RR | 0.2 | kms | 1014338.5 | 99358 | 1113696.5 | 2011-01-31 | 2011-06-30 | 964338.5 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Crossing Magallon | 064519009 | Acquisition of One (1) Unit Pre-Harvest Equipment (Farm Tractor) w/ Complete implements & garage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 1 | unit | 2246965.6 | 212865.4 | 2459831 | 2011-03-20 | 2011-05-31 | 1774345.8 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Guinpana-an | 064519010 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 526495 | 65360 | 591855 | 2011-01-04 | 2011-05-31 | 473845.5 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Inolingan | 064519011 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 3.475 | kms | 1079418.2 | 349329.8 | 1428748 | 2011-01-03 | 2011-05-31 | 1079418.2 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Macagahay | 064519012 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 0.19 | kms | 940481 | 100308 | 1040789 | 2011-01-25 | 2011-05-31 | 912845 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Magallon Cadre | 064519013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 84.14 | sq.m | 526495 | 65360 | 591855 | 2011-01-08 | 2011-05-31 | 473845.5 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Montilla | 064519014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 51.6 | sq.m | 526495 | 65360 | 591855 | 2011-01-21 | 2011-05-31 | 473845.5 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Poblacion 1,2,3,4,5 & 7 | 064519002 | Construction of One (1) Unit Two (2) Classroom Building (HS) | 6 | Basic Social Services | School | SB | 133.2 | sq. m | 939880 | 209140 | 1149020 | 2011-01-07 | 2011-03-31 | 845892 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Poblacion 2 | 064519003 | Construction of One (1) Unit Two (2) Classroom Building (HS) | 6 | Basic Social Services | School | SB | 133.2 | sq. m | 939880 | 209140 | 1149020 | 2011-01-07 | 2011-03-31 | 845892 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Poblacion 3 | 064519004 | Construction of One (1) Unit Two (2) Classroom Building (HS) | 6 | Basic Social Services | School | SB | 133.2 | sq. m | 939880 | 209140 | 1149020 | 2011-01-07 | 2011-03-31 | 845892 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Poblacion 4 | 064519005 | Construction of One (1) Unit Two (2) Classroom Building (HS) | 6 | Basic Social Services | School | SB | 133.2 | sq. m | 939880 | 209140 | 1149020 | 2011-01-07 | 2011-03-31 | 845892 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Poblacion 5 | 064519006 | Construction of One (1) Unit Two (2) Classroom Building (HS) | 6 | Basic Social Services | School | SB | 133.2 | sq. m | 939880 | 209140 | 1149020 | 2011-01-07 | 2011-03-31 | 845892 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Poblacion 7 | 064519008 | Construction of One (1) Unit Two (2) Classroom Building (HS) | 6 | Basic Social Services | School | SB | 133.2 | sq. m | 939880 | 209140 | 1149020 | 2011-01-07 | 2011-03-31 | 845892 | Completed
R6 | 06 | Negros Occidental | 0645 | Moises Padilla | 064519 | Quintin Remo | 064519016 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 3.475 | kms | 1186390 | 224990 | 1411380 | 2011-01-11 | 2011-05-31 | 1123724.5 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Agdaliran | 063038001 | Improvement of 0.40 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.4 | kms | 410083.09 | 115512.95 | 525596.04 | 2011-02-05 | 2011-06-30 | 391655.44 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Amayong | 063038002 | Road Improvement of 0.50 Km. Farm to Market Road w/ 0.20 Km. Road Concreting | 1 | Basic Access Infrastructure | Road | RR | 0.35 | kms | 629163.96 | 205124.05 | 834288.01 | 2011-02-02 | 2011-06-30 | 596936.75 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Batuan | 063038004 | Construction of One (1) Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 81 | sq. m | 580391.5 | 185901.58 | 766293.08 | 2011-03-01 | 2011-06-30 | 580391.5 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Bondulan | 063038005 | Road Improvement of 0.54 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.535 | kms | 429608.61 | 295475.51 | 725084.12 | 2011-01-25 | 2011-06-30 | 402014.42 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Boroñgon | 063038006 | Concreting of 0.17 Km. Brgy. Road | 1 | Basic Social Services | Road | RRC | 0.17 | kms | 622536.49 | 172375.27 | 794911.76 | 2011-02-04 | 2011-06-30 | 592107.25 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Capinang | 063038008 | Construction of One (1) Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 81 | sq. m | 612161.5 | 151353.49 | 763514.99 | 2011-03-07 | 2011-06-30 | 612161.5 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Cubay | 063038009 | Improvement of 2 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 2 | kms | 1314844.87 | 267370.63 | 1582215.5 | 2011-02-16 | 2011-05-31 | 1260861.9 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Cudionan | 063038010 | Construction of 1 Unit Solar Dryer with Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 1 | sq.m | 365275.63 | 214764.48 | 580040.11 | 2011-04-13 | 2011-06-30 | 339931.95 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Dugman | 063038011 | Construction of One (1) Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 81 | sq. m | 597316.5 | 163460.6 | 760777.1 | 2011-03-03 | 2011-06-30 | 597316.5 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Hacienda Conchita | 063038012 | Construction of Two (2) Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1050469.42 | 244943.07 | 1295412.49 | 2011-01-06 | 2011-06-30 | 1005714 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Moto | 063038015 | Purchased of Pre and Post Harvest Facilities with Construction of Garage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 30 | sq.m | 738344.4 | 161670.34 | 900014.74 | 2011-01-24 | 2011-06-30 | 700606.5 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Naborot | 063038016 | Concreting of 0.13 Km. Brgy. Footpath | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.125 | kms | 249918.12 | 74919.52 | 324837.64 | 2011-02-09 | 2011-06-30 | 238175.28 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Odiongan | 063038018 | Road Improvement of 0.45 Km. Farm to Market Road | 1 | Basic Access Infrastructure | Road | RR | 0.45 | kms | 484098.7 | 131194.81 | 615293.51 | 2011-01-31 | 2011-06-30 | 461620.07 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Pase | 063038020 | Construction of Two (2) Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 162 | sq. m | 919145.42 | 374587.07 | 1293732.49 | 2011-01-06 | 2011-06-30 | 874390 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Poblacion | 063038021 | Improvement of 427 Ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 427 | ln.m | 600803.73 | 160531.46 | 761335.19 | 2011-01-12 | 2011-06-30 | 569962.05 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Santol | 063038024 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 58.35 | sq.m | 537491.65 | 160354.24 | 697845.89 | 2011-01-11 | 2011-06-30 | 509206.5 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Siempreviva | 063038025 | Road Improvement of 0.30 Km. Farm to Market Road with 0.30 Km. Road Concreting | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 1033365.42 | 147532.95 | 1180898.37 | 2011-02-27 | 2011-06-30 | 984973.38 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Sua | 063038026 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 59.14 | sq.m | 629378.91 | 152076.05 | 781454.96 | 2011-01-14 | 2011-06-30 | 592117.79 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Talo-ato | 063038027 | Concreting of 0.40 Km. Brgy. Road | 1 | Basic Social Services | Road | RRC | 0.4 | kms | 1172585.43 | 245144.88 | 1417730.31 | 2011-03-01 | 2011-06-30 | 1125032.62 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tamangi | 063038028 | Construction of 1 Unit Solar Dryer with Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 420 | sq.m | 439597.22 | 156561.75 | 596158.97 | 2011-01-17 | 2011-06-30 | 420529 | Completed
R6 | 06 | Iloilo | 0630 | San Dionisio | 063038 | Tuble | 063038030 | Construction of Two (2) Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 162 | sq. m | 1083419.42 | 211873.07 | 1295292.49 | 2011-01-10 | 2011-06-30 | 1038664 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | Aripdip | 063042001 | Cosntructionn of 1 Unit 1 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 82.38 | sq. m | 614796.05 | 170734 | 785530.05 | 2011-01-15 | 2011-06-30 | 614796.05 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | Bagacay | 063042002 | Construction of 1 Unit 1 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 82.38 | sq. m | 633074.51 | 152455.54 | 785530.05 | 2011-01-10 | 2011-06-30 | 633074.51 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | Ilongbukid | 063042004 | 0.1 Km. Road Upgrading with 3 Barrel Box Culvert | 1 | Basic Access Infrastructure | Road | RR | 0.1 | kms | 878838.73 | 541478.48 | 1420317.21 | 2011-01-12 | 2011-06-30 | 878838.73 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | Poblacion | 063042010 | Construction of 1 Unit 1 Classroom School Building (PS) | 1 | Basic Social Services | School | SB | 82.38 | sq. m | 128210.94 | 657319.11 | 785530.05 | 2011-02-07 | 2011-06-30 | 128210.94 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | Poscolon | 063042005 | Construction of 1 Unit 1 Classroom School Building (PS) | 1 | Basic Social Services | School | SB | 82.38 | sq. m | 628831.01 | 156699.04 | 785530.05 | 2011-01-17 | 2011-06-30 | 628831.01 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | San Andres | 063042007 | Construction of 1 Unit 1 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 82.38 | sq. m | 611956.84 | 173573.21 | 785530.05 | 2011-01-19 | 2011-06-30 | 611956.84 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | San Dionisio | 063042008 | Construction of 1 Unit 1 Classroom Day Care Center with Water Tank | 1 | Basic Social Services | Day Care Center | DCC | 65.88 | sq.m | 496900.19 | 152455.54 | 649355.73 | 2011-01-10 | 2011-06-30 | 496900.19 | Completed
R6 | 06 | Iloilo | 0630 | San Rafael | 063042 | San Florentino | 063042009 | Construction of 1 Unit 1 Classroom Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 65.88 | sq.m | 507391.73 | 141964 | 649355.73 | 2011-01-27 | 2011-06-30 | 507391.73 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Batang | 082610001 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 115 | ln.m | 230650 | 98850 | 329500 | 2010-10-06 | 2010-11-30 | 184520 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Cacatmonan | 082610002 | Construction of Water and Sanitation System | 1 | Basic Social Services | Water System | WS | 1 | system | 164064 | 180236 | 344300 | 2011-02-15 | 2011-04-30 | 147658 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Canciledes | 082610004 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | ST | 36 | unit | 372190 | 159510 | 531700 | 2010-10-20 | 2011-02-28 | 354690 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Carmen | 082610005 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 70 | ln.m | 529806 | 76094 | 605900 | 2010-10-27 | 2011-02-28 | 514216 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Garawon | 082610003 | Construction of Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 627130 | 268770 | 895900 | 2010-10-06 | 2011-03-31 | 564417 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Nagaja | 082610006 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | ST | 47 | unit | 616725 | 66525 | 683250 | 2010-10-29 | 2011-03-31 | 583052 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Padang | 082610007 | Construction of Water System Level I With Pathway | 1 | Basic Social Services | Water System | WS | 1 | system | 195300 | 83700 | 279000 | 2010-10-16 | 2011-01-31 | 185970 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 1 | 082610008 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 300 | ln.m | 1320666 | 117634 | 1438300 | 2010-09-29 | 2011-05-31 | 1275799.6 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 2 | 082610009 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 490000 | 210000 | 700000 | 2010-11-12 | 2011-05-31 | 470000 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 3 | 082610010 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | ST | 38 | unit | 497700 | 67300 | 565000 | 2010-10-20 | 2011-03-31 | 472700 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | Poblacion 4 | 082610011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 489300 | 209700 | 699000 | 2010-10-28 | 2011-03-31 | 440370 | Completed
R8 | 08 | Eastern Samar | 0826 | Hernani | 082610 | San Miguel | 082610013 | Construction of Water System | 1 | Basic Social Services | Water System | WS | 1 | system | 282450 | 121050 | 403500 | 2010-10-14 | 2011-01-31 | 254205 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Balnasan | 084820001 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | RFP | 0.3 | kms | 846429 | 117720 | 964149 | 2011-04-04 | 2011-05-20 | 808932 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Coroconog | 084820004 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1211413 | 221240 | 1432653 | 2011-04-04 | 2011-05-31 | 1157423 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Dale | 084820005 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1276148 | 151680 | 1427828 | 2011-04-12 | 2011-05-31 | 1219073 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Lao-angan | 084820007 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 126 | sq. m | 1276148 | 151680 | 1427828 | 2011-04-06 | 2011-05-31 | 1219073 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 1 | 084820011 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 629 | ln.m | 697126 | 92700 | 789826 | 2011-01-31 | 2011-05-09 | 578410.8 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 2 | 084820012 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 395 | ln.m | 491086 | 81960 | 573046 | 2011-04-04 | 2011-05-20 | 469622 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 3 | 084820013 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 690 | ln.m | 828210 | 121760 | 949970 | 2011-01-31 | 2011-05-31 | 715698 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 4 | 084820014 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 600 | ln.m | 664584 | 91880 | 756464 | 2011-02-07 | 2011-05-31 | 598125.6 | Completed
R8 | 08 | Northern Samar | 0848 | San Roque | 084820 | Zone 6 | 084820016 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 100 | ln.m | 708856 | 143004 | 851860 | 2011-01-31 | 2011-05-31 | 653625.17 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Alegria | 098301001 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 506938 | 173550 | 680488 | 2011-03-15 | 2011-06-30 | 506938 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Bagong Buhay | 098301026 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 506938 | 173550 | 680488 | 2011-03-15 | 2011-06-30 | 506938 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Bella | 098301004 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | TC | 63 | sq. m | 636241.5 | 164245.5 | 800487 | 2011-03-17 | 2011-06-30 | 611461.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Calades | 098301005 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 480395 | 217175 | 697570 | 2011-04-30 | 2011-06-30 | 468546 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Dawa-Dawa | 098301006 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | TC | 63 | sq. m | 636241.5 | 199122.5 | 835364 | 2011-03-16 | 2011-06-30 | 604623.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Gulayon | 098301007 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 478370.2 | 202117.8 | 680488 | 2011-03-15 | 2011-06-30 | 460846.2 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Ilisan | 098301008 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 480395 | 217175 | 697570 | 2011-03-15 | 2011-06-30 | 468546 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Kapatagan | 098301028 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | TC | 63 | sq. m | 636241.5 | 199122.5 | 835364 | 2011-03-16 | 2011-06-30 | 604623.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Kawayan | 098301009 | Construction of Birthing Homes | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 458465.8 | 218543.8 | 677009.6 | 2011-03-15 | 2011-06-30 | 428465.8 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lambuyogan | 098301012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 478370.2 | 202117.8 | 680488 | 2011-04-30 | 2011-06-30 | 460846.2 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lapirawan | 098301013 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 544445 | 153125 | 697570 | 2011-04-30 | 2011-06-30 | 532596 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Litayon | 098301014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 506938 | 173550 | 680488 | 2011-03-29 | 2011-07-30 | 489414 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Lutiman | 098301015 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | TC | 63 | sq. m | 636241.5 | 199122.5 | 835364 | 2011-03-18 | 2011-06-30 | 604623.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Milagrosa | 098301002 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 544445 | 153125 | 697570 | 2011-03-15 | 2011-06-30 | 532596 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Naga-naga | 098301016 | Construction of Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | MPC | 63 | sq.m | 511031 | 197769 | 708800 | 2011-04-30 | 2011-07-30 | 481031 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Pandan-pandan | 098301017 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | TC | 63 | sq. m | 636241.5 | 164245.5 | 800487 | 2011-04-30 | 2011-07-30 | 611461.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Payongan | 098301018 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | TC | 63 | sq. m | 636241.5 | 164245.5 | 800487 | 2011-03-15 | 2011-06-30 | 611461.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Poblacion | 098301019 | Construction of Solar Dryer with Mini Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 462 | sq.m | 728811.5 | 184392.5 | 913204 | 2011-03-18 | 2011-07-30 | 698811.5 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Sta. Maria | 098301020 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 478370.2 | 202117.8 | 680488 | 2011-03-15 | 2011-06-30 | 460846.2 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Sto. Niño | 098301021 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 480395 | 217175 | 697570 | 2011-04-30 | 2011-07-30 | 468546 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Talaptap | 098301022 | Construction of 1 Unit 2 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 160.95 | sq. m | 939922 | 260400 | 1200322 | 2011-04-30 | 2011-09-15 | 909922 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Tampalan | 098301023 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 544445 | 153125 | 697570 | 2011-04-30 | 2011-06-30 | 532596 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Tandiong-Muslim | 098301024 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 506938 | 173550 | 680488 | 2011-04-30 | 2011-06-30 | 489414 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Alicia | 098301 | Timbang-Timbang | 098301025 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 506938 | 173550 | 680488 | 2011-03-15 | 2011-06-30 | 489414 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Bogabongan | 097226002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 414871 | 231093 | 645964 | 2010-10-12 | 2011-01-24 | 400840.58 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Manil | 097226005 | Construction of Water System Level II (Gravity Type) | 1 | Basic Social Services | Water System | WS | 1 | system | 678230.5 | 240612.5 | 918843 | 2010-10-27 | 2011-02-28 | 624976.37 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Mawal | 097226006 | Construction of Water System Level I (Hand Pump) | 1 | Basic Social Services | Water System | WS | 1 | system | 430673 | 225800 | 656473 | 2010-11-03 | 2011-02-28 | 430664.66 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Morob | 097226018 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 1.426 | kms | 1396117 | 413465 | 1809582 | 2010-12-27 | 2011-04-30 | 1256505.3 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Nasibac | 097226008 | Construction of 1 Unit 2 Classroom Elem. School Building (Elem) | 1 | Basic Social Services | School | SB | 160.95 | sq.m | 867556 | 277700 | 1145256 | 2010-11-29 | 2011-05-31 | 830209.63 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Sipacong | 097226010 | Construction of Water System Level II (Gravity Type) | 1 | Basic Social Services | Water System | WS | 1 | system | 741821.5 | 235487.5 | 977309 | 2010-10-27 | 2011-02-28 | 698839.64 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Sta. Maria | 097226011 | Construction of 2 Units 4 Classrooms School Building (Elem) | 1 | Basic Social Services | School | SB | 321.9 | sq.m | 1724425 | 526450 | 2250875 | 2010-11-15 | 2011-03-31 | 1719873.31 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Talinga | 097226012 | Construction of 1 Unit 1 Classroom School Building (Elem) | 1 | Basic Social Services | School | SB | 87.35 | sq.m | 481086 | 130312 | 611398 | 2010-10-12 | 2011-01-10 | 481070.97 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Tinuyop | 097226015 | Construction of 1 Unit 2 Classroom School Building (HS) | 1 | Basic Social Services | School | SB | 160.95 | sq.m | 867556 | 271700 | 1139256 | 2010-11-10 | 2011-03-31 | 867547.31 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Leon Postigo (Bacungan) | 097226 | Titik | 097226017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 497664 | 259165 | 756829 | 2010-11-12 | 2011-02-28 | 497638.95 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Diolen | 097208004 | Appropriate Farming Technology Support | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 36 | sq.m | 339078 | 139780 | 478858 | 2010-10-08 | 2011-02-28 | 331143.15 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | G. Bergado (New Casul) | 097208006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 486102 | 210990 | 697092 | 2010-10-05 | 2010-12-31 | 483458.7 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | New Siquijor | 097208008 | Appropriate Farming Technology Support | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | PHF | 36 | sq.m | 339078 | 146530 | 485608 | 2010-10-07 | 2010-12-31 | 338793.77 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Paso Rio | 097208009 | Sectional Road Concreting | 1 | Basic Social Services | Road | RRC | 0.9 | kms | 2098684 | 918320 | 3017004 | 2010-11-29 | 2011-06-30 | 1901102.76 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | San Miguel | 097208011 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 520136 | 222309 | 742445 | 2010-10-13 | 2010-12-31 | 515110.48 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Totongon | 097208013 | Construction of Trading Post | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | PM | 120 | sq.m | 387007 | 165043 | 552050 | 2010-10-09 | 2011-02-28 | 383956.06 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Tubac | 097208014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 486102 | 213559 | 699661 | 2010-10-06 | 2010-12-31 | 473852 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Mutia | 097208 | Unidos | 097208015 | Construction of Water System Level II | 1 | Basic Social Services | Water System | WS | 1 | system | 2533524 | 875451 | 3408975 | 2010-12-13 | 2011-05-31 | 2280171.6 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Datagan | 097215003 | Construction of Birthing Center | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 685378.75 | 194621.25 | 880000 | 2011-02-24 | 2011-06-30 | 614478.75 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Diongan | 097215005 | Construction of Trading Center | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | PM | 135.2 | sq.m | 689600 | 110400 | 800000 | 2011-03-22 | 2011-06-30 | 677372.73 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Domogok | 097215006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 567965 | 137995 | 705960 | 2011-04-30 | 2011-06-30 | 547592.67 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Dumpilas | 097215007 | Concreting on Critical Slope of Barangay Road | 1 | Basic Social Services | Road | RRC | 0.248 | kms | 907921.41 | 215075 | 1122996.41 | 2011-04-30 | 2011-06-30 | 870165.01 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Guibo | 097215010 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | SB | 160.2 | sq. m | 1158970 | 201030 | 1360000 | 2011-03-22 | 2011-06-30 | 1134098.64 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Gunyan | 097215011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 585650 | 144350 | 730000 | 2011-02-18 | 2011-05-31 | 553657.67 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Macasing | 097215013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 595320 | 166680 | 762000 | 2011-04-30 | 2011-06-30 | 560187.67 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Moyo | 097215015 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 576130 | 139370 | 715500 | 2011-04-30 | 2011-06-30 | 557297.67 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Muñoz | 097215024 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 0.3 | kms | 1322679 | 237321 | 1560000 | 2011-04-30 | 2011-06-30 | 1291025 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Pange | 097215016 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 370270.81 | 149729.19 | 520000 | 2011-04-30 | 2011-06-30 | 346832.4 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Paranglumba | 097215017 | Construction of Line Ditch | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | DRG | 886 | ln.m | 531640 | 148360 | 680000 | 2011-04-30 | 2011-07-30 | 519380.5 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Poblacion (Siayan Proper) | 097215022 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | FC | 484 | ln.m | 874200 | 216400 | 1090600 | 2011-02-08 | 2011-06-30 | 853249.7 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Sayaw | 097215020 | Concreting on Critical Slope of Barangay Road | 1 | Basic Social Services | Road | RRC | 0.3 | kms | 1647472.5 | 312527.5 | 1960000 | 2011-04-30 | 2011-05-31 | 1628326.87 | Completed
R9 | 09 | Zamboanga Del Norte | 0972 | Siayan | 097215 | Suguilon | 097215025 | Road Improvement | 1 | Basic Access Infrastructure | Road | RR | 0.13 | kms | 363558.72 | 186441.28 | 550000 | 2011-03-29 | 2011-06-30 | 366358.9 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Batungan | 098316015 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 87.35 | sq. m | 545632.47 | 89218.03 | 634850.5 | 2011-02-07 | 2011-05-31 | 535632.48 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Cayamcam | 098316002 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 609306 | 105818.33 | 715124.33 | 2011-02-14 | 2011-06-30 | 591777.67 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Datu Tumanggong | 098316018 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 539269.02 | 102163.98 | 641433 | 2011-02-23 | 2011-05-31 | 523769.02 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Gaycon | 098316020 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 620487 | 98290 | 718777 | 2011-02-17 | 2011-06-30 | 600486.9 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Langon | 098316004 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 87.35 | sq. m | 526632.47 | 87218.03 | 613850.5 | 2011-02-25 | 2011-07-30 | 516632.48 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Libertad | 098316005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 531269.02 | 102163.98 | 633433 | 2011-02-18 | 2011-05-31 | 513269.02 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Linguisan | 098316006 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 87.35 | sq. m | 557632.47 | 84218.03 | 641850.5 | 2011-04-24 | 2011-07-30 | 547632.48 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Little Margos | 098316021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | DCC | 48 | sq.m | 558269.02 | 97163.98 | 655433 | 2011-04-30 | 2011-05-31 | 542769.02 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Loboc | 098316016 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 87.35 | sq. m | 146902 | 492448.5 | 639350.5 | 2011-02-28 | 2011-05-31 | 117521.6 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Lower Tungawan | 098316008 | Construction of 1 Unit 1 CL Pre-School Building (PS) | 1 | Basic Social Services | School | SB | 87.35 | sq. m | 526632.47 | 87218.03 | 613850.5 | 2011-02-21 | 2011-05-31 | 516632.47 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Malungon | 098316009 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 619568 | 107675 | 727243 | 2011-03-01 | 2011-05-31 | 599568 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Masao | 098316025 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 617644 | 98290 | 715934 | 2011-02-21 | 2011-05-31 | 597644 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | San Pedro | 098316010 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | SB | 160.95 | sq. m | 1006580.94 | 165495.06 | 1172076 | 2011-02-16 | 2011-06-30 | 976580.94 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Sto. Niño | 098316022 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 627644 | 98290 | 725934 | 2011-02-16 | 2011-06-30 | 597644 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Taglibas | 098316023 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 619305 | 98290 | 717595 | 2011-04-24 | 2011-06-30 | 599305 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigbanuang | 098316011 | Construction of Barangay Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 611568 | 104366 | 715934 | 2011-02-18 | 2011-06-30 | 591568 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigbucay | 098316012 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 609306 | 105818.33 | 715124.33 | 2011-03-24 | 2011-06-30 | 591782.67 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Tigpalay | 098316024 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | SB | 160.95 | sq. m | 1015918 | 163355 | 1179273 | 2011-03-01 | 2011-06-30 | 985918 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Timbabauan | 098316026 | Construction of Health Station | 1 | Basic Social Services | Health Station | HS | 51 | sq.m | 612306 | 105290 | 717596 | 2011-03-04 | 2011-06-30 | 592306 | Completed
R9 | 09 | Zamboanga Sibugay | 0983 | Tungawan | 098316 | Upper Tungawan | 098316013 | Construction of 1 Unit 2 CL School Building (Elem) | 1 | Basic Social Services | School | SB | 160.95 | sq. m | 998128.12 | 184144.88 | 1182273 | 2011-02-08 | 2011-05-31 | 958128.12 | Completed

## MCC
KC-MCC Funded SPs
REGION |  | PROVINCE |  | MUNICIPALITY |  | BARANGAY |  | SUB-PROJECT NAME | NoOfBgys | Major SP Category | SP Sub-Category | Physical_Target | Phy_Target_Unit | Kalahi_Amount | LCC_Amount | Total_Amount | Date_Started | Date_of_Completion | KC_Fund_Released | Tranche | Status
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Tangadan | 140123005 | Construction of Pump Driven and Pipe lined CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | 10 | has. | 433067.75 | 151819.43 | 584887.18 | 2012-05-16 |  | 346450.2 | 1st | On-going
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Villa Mercedes | 140123006 | Construction of 2 Units Pupm Driven CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | 15 | has. | 415391.69 | 144667.92 | 560059.61 | 2012-05-01 |  | 332313.35 | 1st | On-going
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Palang | 140123002 | Construction of 2 Units MPDPs | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 810 | sq.m | 543582.55 | 230311.63 | 773894.18 | 2012-05-12 |  | 434866.01 | 1st | On-going
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Pantoc | 140123003 | Construction of footbridge with slope protection | 1 | Basic Access Infrastructure | Foot/Small Bridges | 33.4 | ln.m | 348433.01 | 130140.76 | 478573.77 | 2012-05-12 |  | 278746.41 | 1st | On-going
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Labaan | 140123001 | Construction of Erosion Protection | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 310.73 | ln.m | 550640.68 | 201980.17 | 752620.85 | 2012-06-25 |  | 412980.51 | 1st | On-going
CAR | 14 | Abra | 1401 | San Quintin | 140123 | Poblacion | 140123004 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 279940.44 | 119188.86 | 399129.3 | 2012-04-25 | 2012-07-15 | 223952.35 | 1st | Completed
VI | 06 | Aklan | 0604 | Libacao | 060409 | Manika | 060409015 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 601472.67 | 159832.33 | 761305 | 2012-03-26 |  | 300736.33 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Rosal | 060409023 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 575601.77 | 158703.23 | 734305 | 2012-04-23 |  | 287800 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Loctuga | 060409013 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 683998.79 | 183019.96 | 867018.75 | 2012-07-09 |  | 341999.4 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Ogsip | 060409016 | Road Improvement | 1 | Basic Access Infrastructure | Road | 1.56 | kms | 1257388.8 | 306166.2 | 1563555 | 2012-05-10 |  | 628694.4 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Dalagsaan | 060409009 | 2 units Day Care Center Building | 1 | Basic Social Services | Day Care Center | 96 | sq.m | 1619478.69 | 384661.31 | 2004140 | 2012-07-01 |  | 809739.35 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Alfonzo XII | 060409002 | Road Imporvement | 1 | Basic Access Infrastructure | Road | 1.8 | kms | 1411818.95 | 324534.05 | 1736353 | 2012-04-21 |  | 705909.48 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Oyang | 060409018 | Construction of 2 units School Building | 1 | Basic Social Services | School | 132 | sq. m | 1513497.33 | 369540.17 | 1883037.5 | 2012-06-18 |  | 756748.67 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Bato-Bato | 060409003 | Road Improvement | 1 | Basic Access Infrastructure | Road | 1.55 | kms | 1974425.46 | 449154.54 | 2423580 | 2012-05-07 |  | 987212.73 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Rivera | 060409022 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 608045.4 | 163156.65 | 771202.05 | 2012-04-23 |  | 304022.7 | 1st | On-going
VI | 06 | Aklan | 0604 | Libacao | 060409 | Poblacion | 060409021 | River Control jackstone type | 1 | Environmental Protection and Conservation | River Control/Flood Control |  | ln.m | 554272.13 | 313193.37 | 867465.5 | 2012-05-28 |  | 277136.07 | 1st | On-going
VI | 06 | Aklan | 0604 | Madalag | 060410 | Panipiason | 060410019 | Improvement of Pathway | 1 | Basic Access Infrastructure | Access Trail |  | kms | 1352251.5 | 342080.25 | 1694331.75 |  |  | 0 |  | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Talimagao | 060410024 | Improvement of Farm Irrigation with Water Pump | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 567507.33 | 154818.37 | 722325.7 | 2012-07-19 |  | 283150.79 | 1st | On-going
VI | 06 | Aklan | 0604 | Madalag | 060410 | Mercedes | 060410015 | Construction of Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 28 | ln.m | 366411.67 | 113616.83 | 480028.5 |  |  | 269121.44 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Alas-as | 060410002 | Road Improvement with Spot Concreting | 1 | Basic Access Infrastructure | Road | 1 | kms | 668415.25 | 179960 | 848375.25 |  |  | 534732.21 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Singay | 060410022 | Road Improvement with Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.585 | kms | 502148.67 | 133413.58 | 635562.25 |  |  | 401718.93 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Ma. Cristina | 060410013 | Improvement of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.88 | kms | 690608.5 | 182584 | 873192.5 |  |  | 552486.8 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Medina | 060410014 | Road Construction with Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.84 | kms | 1831036.13 | 430731.17 | 2261767.3 |  |  | 0 |  | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Cabangahan | 060410005 | Road Improvement with Spot Concreting | 1 | Basic Access Infrastructure | Road | 0.88 | kms | 1602750.17 | 379458.08 | 1982208.25 | 2012-07-25 |  | 703319.86 | 1st | On-going
VI | 06 | Aklan | 0604 | Madalag | 060410 | Napnot | 060410016 | Road improvement with Spot Concreting and Box Culvert | 1 | Basic Access Infrastructure | Road | 2.227 | kms | 1602750.17 | 379458.08 | 1982208.25 |  |  | 1282200.13 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Dit-ana | 060410008 | Construction of River Control (Jackstone Type) | 1 | Environmental Protection and Conservation | River Control/Flood Control | 28 | ln.m | 684493.46 | 195147.74 | 879641.2 |  |  | 342246.73 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Guinatu-an | 060410010 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 623197 | 173472.9 | 796669.9 | 2012-05-31 |  | 311598.5 | 1st | On-going
VI | 06 | Aklan | 0604 | Madalag | 060410 | Mamba | 060410012 | Road Concreting | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 855199 | 212486.25 | 1067685.25 |  |  | 684159.2 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Logohon | 060410011 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.502 | kms | 380617.33 | 106644.67 | 487262 |  |  | 360313.31 | 1st | Not yet started
VI | 06 | Aklan | 0604 | Madalag | 060410 | Tigbawan | 060410025 | Road Concreting with Spot Concreting with RCBC | 1 | Basic Access Infrastructure | Road | 0.73 | kms | 246214.16 | 579146.99 | 825361.15 | 2012-06-06 |  | 196971.33 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Nagbalayan | 148104019 | Improvement of Nagbalayan Potable Water System | 1 | Basic Social Services | Water System | 1 | system | 576850 | 128150 | 705000 | 2012-05-31 |  | 455711.5 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Poblacion | 148104020 | Improvement of Water System | 1 |  | Water System | 1 | system | 603447 | 136553 | 740000 | 2012-05-21 |  | 482757.6 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Laco | 148104010 | Improvement of Potable Water Sytem | 1 |  | Water System | 1 | system | 478047 | 121953 | 600000 | 2012-05-31 |  | 382437.6 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Baliwanan | 148104002 | Construction of 15 Meters Foot Bridge with 110 Meters Foot Trail | 1 |  | Foot/Small Bridges | 15 | ln.m | 420450 | 94550 | 515000 | 2012-05-11 |  | 302724 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Lucab | 148104012 | Construction of Lucab Farmland Drainage Sytem | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 500 | ln.m | 239904 | 60096 | 300000 | 2012-05-11 |  | 191923.2 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Cabetayan | 148104007 | Construction of Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 15 | ln.m | 401850 | 108150 | 510000 | 2012-05-11 |  | 321480 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Badduat | 148104001 | Construction of Cable Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 100 | ln.m | 2050050 | 549950 | 2600000 | 2012-04-01 |  | 1025025 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Madduang | 148104015 | Construction of 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 847800 | 220200 | 1068000 | 2012-04-11 |  | 423900 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Maragat | 148104017 | Improvement of Maragat to Dagara Foot Trail | 1 | Basic Access Infrastructure | Access Trail | 3 | kms | 370653 | 84347 | 455000 | 2012-05-31 |  | 296522.4 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Karagawan | 148104008 | Construction of Cable foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 50 | ln.m | 1305050 | 339950 | 1645000 | 2012-04-01 |  | 822181.5 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Tuyangan | 148104021 | River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control |  | ln.m | 1206000 | 314000 | 1520000 | 2012-04-11 |  | 593000 | 1st | On-going
CAR | 14 | Apayao | 1481 | Kabugao | 148104 | Dagara | 148104005 | Improvement of Footrail | 1 | Basic Access Infrastructure | Access Trail |  | kms | 712564 | 157436 | 870000 | 2012-05-01 |  | 356282 | 1st | On-going
CAR | 14 | Apayao | 1481 | Conner | 148102 | Puguin | 148102014 | Construction of 4 unit Multi Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility |  | sq.m | 1310846.77 | 363909.5 | 1674756.27 |  |  | 904484.27 | 1st | On-going
CAR | 14 | Apayao | 1481 | Conner | 148102 | Calafug | 148102004 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 1598492.61 | 446671.97 | 2045164.58 |  |  | 1121221.64 | 1st | Not yet started
CAR | 14 | Apayao | 1481 | Conner | 148102 | Daga | 148102006 | Construction and Installation of mechanical Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 122.9 | sq.m | 505645.85 | 173201.78 | 678847.63 |  |  | 404516.68 | 1st | On-going
CAR | 14 | Apayao | 1481 | Conner | 148102 | Banban | 148102018 | Construction of 6 unit Multi Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1600 | sq.m | 997210.98 | 331225.38 | 1328436.36 |  |  | 797768.78 | 1st | On-going
CAR | 14 | Apayao | 1481 | Conner | 148102 | Allangigan | 148102001 | Construction of 3 Unit Multi Purpose Pavement with Storage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility |  | sq.m | 2542172.6 | 720075.92 | 3262248.52 |  |  | 1525303.57 | 1st | Not yet started
CAR | 14 | Apayao | 1481 | Conner | 148102 | Karikitan | 148102008 | Construction of Karikitan Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 2495631.19 | 825248.55 | 3320879.74 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Casiawan | 087803005 | Rehab of water System Level II | 1 | Basic Social Services | Water System | 1 | system | 260640 | 73160 | 333800 |  |  | 208512 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Salawad | 087803013 | Rehab of water System Level II | 1 | Basic Social Services | Water System | 1 | system | 303920 | 83980 | 387900 |  |  | 243136 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Langgao | 087803008 | Improvement of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 481780 | 130320 | 612100 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Caanibongan | 087803004 | Construction of Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 450 | sq.m | 461760 | 116940 | 578700 | 2012-02-06 |  | 369408 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Magbangon | 087803011 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 134 | ln.m | 256480 | 65620 | 322100 | 2012-02-08 | 2012-05-30 | 205184 | 1st | Completed
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Esperanza | 087803007 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 272 | ln.m | 397440 | 100860 | 498300 | 2012-02-03 |  | 317952 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Bunga | 087803003 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 195 | ln.m | 398800 | 101200 | 500000 | 2012-02-07 |  | 319040 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Libertad | 087803009 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.23 | kms | 355120 | 90280 | 445400 | 2012-02-06 |  | 284096 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Baso | 087803002 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 547460 | 140240 | 687700 | 2012-04-23 |  | 437968 | 1st | On-going
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Talibong | 087803014 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 28 | ln.m | 549220 | 140980 | 690200 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Cabucgayan | 087803 | Looc | 087803010 | Construction of Pathwalk with Drainage Canal | 1 | Basic Access Infrastructure | Access Trail | 0.533 | kms | 444900 | 187300 | 632200 | 2012-02-06 |  | 355920 | 1st | On-going
VIII | 08 | Biliran | 0878 | Naval | 087808 | Capinahan | 087808005 | Road Concreting with with 2 Units RCPC | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 1037254.4 | 399445.6 | 1436700 |  |  | 829803.52 | 1st | Not yet started
VIII | 08 | Biliran | 0878 | Naval | 087808 | Imelda | 087808023 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2267658.4 | 623341.6 | 2891000 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Naval | 087808 | Lico | 087808012 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 1782365.6 | 476434.4 | 2258800 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Naval | 087808 | Lucsoon | 087808013 | Construction of Level 2 Water System | 1 | Basic Social Services | Water System | 1 | system | 1310154.4 | 354845.6 | 1665000 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Naval | 087808 | San Pablo | 087808015 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1792287.2 | 540212.8 | 2332500 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Naval | 087808 | Catmon | 087808007 | Construction of Level 2 water System | 1 | Basic Social Services | Water System | 1 | system | 1626900 | 417100 | 2044000 |  |  | 0 |  | Not yet started
VIII | 08 | Biliran | 0878 | Naval | 087808 | Libtong | 087808025 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 1883380 | 620120 | 2503500 |  |  | 1506704 | 1st | Not yet started
VII | 07 | Bohol | 0712 | Talibon | 071243 | Bagacay | 071243001 | Gravelling of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 590286 | 496914 | 1087200 | 2012-02-13 | 2012-07-15 | 472228.8 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Balintawak | 071243002 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 554995 | 165005 | 720000 | 2012-02-13 | 2012-07-15 | 443996 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Burgos | 071243006 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 450000 | 269915 | 719915 | 2012-02-10 | 2012-06-30 | 360000 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Busalian | 071243007 | Construction of pathway | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 478875.44 | 187224.56 | 666100 | 2012-02-15 | 2012-06-30 | 383100.35 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Calituban | 071243008 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 574995 | 170005.01 | 745000.01 | 2012-02-15 | 2012-07-15 | 459996 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Cataban | 071243009 | Construction of 1 Unit School Building | 1 | Basic Social Services | School | 63 | sq. m | 574995 | 170005 | 745000 | 2012-02-14 | 2012-07-15 | 459996 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Guindacpan | 071243010 | Rainwater Collector/Harvester | 1 | Basic Social Services | Water System | 1 | system | 898087.69 | 246012.31 | 1144100 | 2012-02-20 | 2012-07-15 | 808278.92 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Magsaysay | 071243013 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 590286.99 | 160924.01 | 751211 | 2012-02-15 | 2012-06-30 | 472228.79 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Mahanay | 071243014 | Construction of pathway | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 478875.44 | 189124.56 | 668000 | 2012-02-16 | 2012-07-15 | 430987.89 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Nocnocan | 071243017 | Construction of Rainwater Reservoir | 1 | Basic Social Services | Water System | 1 | system | 394356.4 | 141643.6 | 536000 | 2012-02-10 | 2012-06-30 | 354920.76 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Poblacion | 071243021 | Contruction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 515397 | 192603 | 708000 | 2012-02-15 | 2012-04-30 | 463857.3 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Rizal | 071243023 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 554995 | 165005 | 720000 | 2012-02-13 | 2012-07-15 | 443996 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Sag | 071243024 | Construction of 2 Units Rainwater Collector | 1 | Basic Social Services | Water System | 1 | system | 495912.8 | 171102.2 | 667015 | 2012-02-20 | 2012-06-30 | 396730.24 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Agustin | 071243026 | Contruction of 1 Unit School Building | 1 | Basic Social Services | School | 63 | sq. m | 554995 | 165005 | 720000 | 2012-02-13 | 2012-07-15 | 499495.5 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Pedro | 071243031 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 849940 | 234360 | 1084300 | 2012-02-20 | 2012-06-30 | 679952 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Roque | 071243032 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 598060 | 170990 | 769050 | 2012-02-13 | 2012-04-30 | 478448 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Sto. Nino | 071243033 | Construction of 1 Unit School Building | 1 | Basic Social Services | School | 63 | sq. m | 554995 | 165005 | 720000 | 2012-02-10 | 2012-06-30 | 499495.5 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Suba | 071243035 | Construction of pathway | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 478875.44 | 187224.56 | 666100 | 2012-02-10 | 2012-06-30 | 430987.89 | 2nd | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | Tanghaligue | 071243036 | Gravelling of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.88 | kms | 844308 | 232552 | 1076860 | 2012-02-13 | 2012-07-15 | 675446.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Talibon | 071243 | San Francisco | 071243028 | Construction of 1 Unit 1 CL HS School Building | 1 | Basic Social Services | School | 63 | sq. m | 503205.07 | 216794.94 | 720000.01 | 2012-02-15 | 2012-07-15 | 195094.53 | 2nd | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Hinlayagan Ilaya | 071244006 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 438696.21 | 217989.79 | 656686 | 2012-05-07 | 2012-06-30 | 350956.98 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | San Isidro | 071244016 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-02-11 | 2012-06-30 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Sto. Tomas | 071244018 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-02-16 | 2012-06-30 | 457267.5 | 2nd | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | San Vicente | 071244017 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.34 | kms | 447786.48 | 195964.52 | 643751 | 2012-05-01 | 2012-06-30 | 358229.18 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Banlasan | 071244001 | Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 35 | ln.m | 561787.44 | 280333.12 | 842120.56 | 2012-04-03 | 2012-06-30 | 449429.96 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Tagum Norte | 071244020 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-01-25 | 2012-07-15 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Soom | 071244019 | Consgtruction of 1 Unit High School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-02-08 | 2012-06-30 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Catoogan | 071244003 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-02-15 | 2012-06-30 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | M. Cabiguhan | 071244012 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-02-16 | 2012-06-30 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Kinan-oan | 071244008 | Construction of 1 Unit CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-01-31 | 2012-06-30 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Tagum Sur | 071244021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 487368.18 | 261143.82 | 748512 | 2012-01-30 | 2012-06-30 | 389894.54 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Bongbong | 071244002 | Rehablitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 430974.62 | 185043.38 | 616018 | 2012-05-07 | 2012-06-30 | 344799.7 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Guinobatan | 071244004 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 513758.13 | 230512.87 | 744271 | 2012-01-21 | 2012-06-30 | 462382.31 | 2nd | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | M. Roxas | 071244014 | Concreting of FMR(Bridge Approach) | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 426239.1 | 193042.9 | 619282 | 2012-05-07 | 2012-06-30 | 340991.28 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Poblacion | 071244015 | Community Learning Center | 1 | Basic Social Services | School | 41.44 | sq. m | 390336 | 170469 | 560805 | 2012-03-28 | 2012-06-30 | 312268.8 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | La Union | 071244009 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-02-13 | 2012-05-30 | 457267.5 | 2nd | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | La Victoria | 071244010 | Contruction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 508075 | 241883 | 749958 | 2012-01-28 | 2012-05-30 | 406460 | 1st | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Mahagbu | 071244013 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 513758.13 | 230512.87 | 744271 | 2012-03-16 | 2012-06-30 | 462382.31 | 2nd | Completed
VII | 07 | Bohol | 0712 | Trinidad | 071244 | Kauswagan | 071244007 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 216620.72 | 709995.93 | 926616.65 | 2012-03-18 | 2012-07-15 | 173296.57 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bago | 071209003 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 427976 | 288389 | 716365 | 2012-02-06 | 2012-06-30 | 385178.4 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Catigbian | 071209017 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 417329.6 | 282670.4 | 700000 | 2012-02-06 | 2012-06-30 | 375596.64 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | N. Montana | 071209033 | Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 800 | sq.m | 347006.6 | 247938.4 | 594945 | 2012-02-13 | 2012-03-30 | 312305.94 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | N. Granada | 071209032 | Construction of Vented Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 529453.8 | 441046.2 | 970500 | 2012-05-04 | 2012-06-30 | 423563.04 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Puting Bato | 071209037 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 450000 | 267515 | 717515 | 2012-01-30 | 2012-04-30 | 394292 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Magkaya | 071209030 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 441160.2 | 275529.8 | 716690 | 2012-01-30 | 2012-05-30 | 397044.18 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Baluarte | 071209004 | Construction of School Building | 1 | Basic Social Services | School | 63 | sq. m | 410812 | 307713 | 718525 | 2012-02-13 | 2012-07-15 | 328649.6 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lapacan Norte | 071209025 | 1 Cl School Building | 1 | Basic Social Services | School | 63 | sq. m | 450000 | 263095 | 713095 | 2012-02-13 | 2012-04-30 | 405000 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bato | 071209006 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 434550.6 | 271351 | 705901.6 | 2012-01-30 | 2012-03-30 | 391095.54 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Anonang | 071209001 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 434550.6 | 271351 | 705901.6 | 2012-02-13 |  | 356625 | 1st | On-going
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cantuba | 071209016 | Construction of Solar Drier with Storage Facility 4mX6m | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 152 | sq.m | 141040 | 133738 | 274778 | 2012-02-16 | 2012-03-30 | 124236 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cruz | 071209019 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 448381.6 | 267268.4 | 715650 | 2012-01-30 | 2012-07-15 | 358705.28 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Panghagban | 071209035 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 449788.6 | 268501.4 | 718290 | 2012-02-06 | 2012-06-30 | 359830.88 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cambus-oc | 071209012 | Construction of Bailey Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 9 | ln.m | 630749.28 | 655205.72 | 1285955 |  |  | 504599.42 | 1st | On-going
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Overland | 071209034 | Water System | 1 | Basic Social Services | Water System | 1 | system | 527490 | 459510 | 987000 | 2012-04-01 |  | 421992 | 1st | On-going
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lapacan Sur | 071209026 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 450000 | 194175 | 644175 | 2012-04-01 | 2012-06-30 | 360000 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | W. Cabula-an | 071209040 | Electrification Generator Set | 1 | Basic Social Services | Electrification | 261 | HH | 623858.92 | 1910176.28 | 2534035.2 | 2012-05-02 |  | 499087.14 | 1st | On-going
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Asinan | 071209002 | Construction of 2 Unit Comfort Room (4m X 6m) | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 2 | unit | 449997 | 245793 | 695790 | 2012-02-06 | 2012-06-30 | 356148.6 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lubang | 071209028 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 429059.6 | 273587.2 | 702646.8 | 2012-02-13 | 2012-06-30 | 339264.44 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Rufo Hill | 071209038 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 447271 | 268935 | 716206 | 2012-02-06 | 2012-06-30 | 354441.8 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bonotbonot | 071209007 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 447599 | 268636 | 716235 | 2012-01-30 | 2012-04-30 | 350399.2 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Lusong | 071209029 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 442978 | 273842 | 716820 | 2012-02-13 | 2012-06-30 | 354382.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Sweetland | 071209039 | Road rehab with causewy | 1 | Basic Access Infrastructure | Road | 0.26 | kms | 565415.78 | 271456.7 | 836872.48 | 2012-05-02 | 2012-05-30 | 423895.24 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cawag | 071209018 | Rehabilitation of Farm to Market Road with Box Culvert | 1 | Basic Access Infrastructure | Road |  | kms | 436755 | 150470 | 587225 | 2012-02-13 | 2012-04-30 | 346764 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Buga-ong | 071209008 | Rehabilitaion of Bailey Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 9 | ln.m | 502354.36 | 339388.8 | 841743.16 | 2012-03-15 |  | 401883.49 | 1st | On-going
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Bantuan | 071209005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 450000 | 269070 | 719070 | 2012-01-30 | 2012-04-30 | 401625 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cantomogad | 071209014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 450000 | 257235 | 707235 | 2012-02-06 | 2012-03-30 | 360000 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Poblacion | 071209036 | Construction of Solar Drier with Storage Facility ( 4m X 6m ) | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 270 | sq.m | 278614.35 | 173215.65 | 451830 | 2012-04-30 | 2012-06-30 | 222891.48 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cantores | 071209015 | Construction of 1 Cl School Building | 1 | Basic Social Services | School | 63 | sq. m | 442608 | 275917 | 718525 | 2012-02-13 | 2012-06-30 | 398347.2 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cangawa | 071209013 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 437421.6 | 269635.4 | 707057 | 2012-01-24 | 2012-03-30 | 390304.44 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | E. Cabul-an | 071209021 | Construction of 1 unit 11.2m X 6.2m Rain collector Tank | 1 | Basic Social Services | Water System | 1 | system | 450000 | 192475 | 642475 | 2012-03-19 | 2012-07-15 | 360000 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Cambuhat | 071209011 | Construction of 1 Cl School Building | 1 | Basic Social Services | School | 63 | sq. m | 440728.8 | 273667.2 | 714396 | 2012-01-30 | 2012-04-30 | 396655.92 | 2nd | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Hunan | 071209022 | Construction of 2 unit Sanitary Toilets ( 4m X 6m ) | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 2 | unit | 447157 | 248633 | 695790 | 2012-02-06 |  | 354350.6 | 1st | On-going
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Merryland | 071209031 | Rehabilitation of Farm to Market Road with Box Culvert | 1 | Basic Access Infrastructure | Road | 0.16 | kms | 490479.11 | 150470 | 640949.11 | 2012-04-10 | 2012-07-15 | 389883.11 | 1st | Completed
VII | 07 | Bohol | 0712 | Buenavista | 071209 | Dait Norte | 071209020 | Construction of Drainage Canal Masonry | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 520 | ln.m | 521370 | 223630 | 745000 | 2012-02-20 | 2012-06-30 | 460767.86 | 2nd | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Aurora | 071234001 | Regravelling of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.37 | kms | 421862 | 183750 | 605612 | 2012-03-23 | 2012-06-30 | 379675.8 | 2nd | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Lumbay | 071234014 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 478278 | 210522 | 688800 | 2012-03-29 | 2012-06-30 | 382622.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Cagawasan | 071234006 | Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 435138 | 303352 | 738490 | 2012-04-10 |  | 348110.4 | 1st | On-going
VII | 07 | Bohol | 0712 | Pilar | 071234 | Ilaud | 071234011 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 522458 | 227467 | 749925 | 2012-03-06 | 2012-07-15 | 417966.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | La Suerte | 071234013 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 522400 | 227526 | 749926 | 2012-02-13 | 2012-07-15 | 417920 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Bayong | 071234004 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 522223 | 227527 | 749750 | 2012-03-06 | 2012-07-15 | 417778.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Pamacsalan | 071234016 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 527704 | 226128 | 753832 | 2012-03-23 | 2012-06-30 | 474933.6 | 2nd | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Lundag | 071234015 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 552175 | 236805 | 788980 | 2012-03-30 | 2012-07-15 | 441740 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Del Pilar | 071234009 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 850259 | 366628 | 1216887 | 2012-03-29 | 2012-07-15 | 680207.2 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Cansungay | 071234007 | Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 566220.12 | 393664.88 | 959885 | 2012-04-10 |  | 452976.1 | 1st | On-going
VII | 07 | Bohol | 0712 | Pilar | 071234 | Estaca | 071234010 | Construction of 3 Unit Concrete Pavement Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1080 | sq.m | 629866 | 270165 | 900031 | 2012-04-13 | 2012-06-30 | 503892.8 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Inaghuban | 071234012 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 529497 | 228120 | 757617 | 2012-03-30 | 2012-06-30 | 423597.6 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Catagdaan | 071234008 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 80 | ln.m | 989281 | 437901 | 1427182 | 2012-03-27 | 2012-06-30 | 791424.8 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | Rizal | 071234018 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 522395 | 227468 | 749863 | 2012-03-01 | 2012-07-15 | 470155.5 | 2nd | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Carlos | 071234019 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 522395 | 227468 | 749863 | 2012-03-31 |  | 409578.4 | 1st | On-going
VII | 07 | Bohol | 0712 | Pilar | 071234 | Bagacay | 071234002 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 560822 | 245710 | 806532 | 2012-03-29 | 2012-07-15 | 448657.6 | 1st | Completed
VII | 07 | Bohol | 0712 | Pilar | 071234 | San Vicente | 071234021 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.1 | kms | 307448.88 | 346274.12 | 653723 | 2012-03-29 |  | 245959.1 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | California | 071246056 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 511187.85 | 232754.15 | 743942 | 2012-02-16 |  | 408950.28 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | San Francisco | 071246037 | Improvement of FMR with RCPC | 1 | Basic Access Infrastructure | Road | 2.005 | kms | 1869622.4 | 527460.6 | 2397083 |  |  | 934811.2 | 1st | Not yet started
VII | 07 | Bohol | 0712 | ubay | 071246 | Tubog | 071246049 | 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 980383.96 | 340410.04 | 1320794 | 2012-02-14 | 2012-06-30 | 924010.36 | 2nd | Completed
VII | 07 | Bohol | 0712 | ubay | 071246 | Sentinela | 071246043 | 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 973111.66 | 384726.33 | 1357837.99 | 2012-02-15 |  | 778489.33 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Benliw | 071246005 | 1 unit 2 CL school Building | 1 | Basic Social Services | School | 126 | sq. m | 956675 | 369480 | 1326155 | 2012-02-20 |  | 765340 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Tuburan | 071246050 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 545148.96 | 197813.04 | 742962 | 2012-02-06 |  | 436119.17 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Gabi | 071246019 | Birthing Center | 1 | Basic Social Services | Health Station | 70 | sq.m | 681282.77 | 270773.23 | 952056 |  |  | 525937.22 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Buenavista | 071246009 | 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1021446.67 | 320989.33 | 1342436 | 2012-02-25 |  | 817157.33 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Villa Teresita | 071246054 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.26 | kms | 1547225.6 | 460306.4 | 2007532 |  |  | 773612.8 | 1st | Not yet started
VII | 07 | Bohol | 0712 | ubay | 071246 | San Isidro | 071246038 | 1 unit 2 CL School uilding | 1 | Basic Social Services | School | 126 | sq. m | 979528.75 | 357447.25 | 1336976 | 2012-03-12 |  | 783623 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Imelda | 071246025 | Birthing Center | 1 | Basic Social Services | Health Station | 70 | sq.m | 681282.77 | 270773.23 | 952056 | 2012-05-25 |  | 541932.4 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Gov. Boyles | 071246020 | Construction of Birthing Center | 1 | Basic Social Services | Health Station |  |  | 694195 | 258041 | 952236 | 2012-03-14 |  | 536962.19 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Bongbong | 071246007 | 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 994963.33 | 344352.67 | 1339316 | 2012-02-13 |  | 795970.67 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Tapal | 071246045 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1 | kms | 1123741.6 | 369285.4 | 1493027 |  |  | 0 |  | Not yet started
VII | 07 | Bohol | 0712 | ubay | 071246 | San Vicente | 071246041 | 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 980726.46 | 357078.54 | 1337805 | 2012-03-05 |  | 784581.17 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Humayhumay | 071246023 | Improvement of FMR with Grouted Riprap | 1 | Basic Access Infrastructure | Road | 1.22 | kms | 1273526.4 | 374981.6 | 1648508 | 2012-05-07 | 2012-06-30 | 636763.2 | 1st | Completed
VII | 07 | Bohol | 0712 | ubay | 071246 | San Pascual | 071246040 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.648 | kms | 1534630.4 | 435357.6 | 1969988 |  |  | 767315.2 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Tipolo | 071246048 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 1739860 | 564815 | 2304675 | 2012-05-07 |  | 869930 | 1st | On-going
VII | 07 | Bohol | 0712 | ubay | 071246 | Calanggaman | 071246027 | Improvement of Farm to Market Road with RCPC | 1 | Basic Access Infrastructure | Road | 0.73 | kms | 620184 | 290028 | 910212 | 2012-02-24 | 2012-05-30 | 310092 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Concepcion et. Al | 071231004 | Construction of 1 Unit 2 CL High School Building | 3 | Basic Social Services | School | 126 | sq. m | 980862.4 | 363069.6 | 1343932 | 2012-02-16 | 2012-07-15 | 784689.92 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Cabidian | 071231007 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 502838.4 | 181972.6 | 684811 | 2012-03-01 | 2012-07-15 | 402270.72 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Lungsodaan | 071231011 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.135 | kms | 502886.4 | 154269.6 | 657156 | 2012-02-14 | 2012-05-30 | 251443.2 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Aguipo | 071231003 | Concerting of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.18 | kms | 502964.8 | 153584.2 | 656549 | 2012-02-29 | 2012-07-15 | 402371.84 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Baybayon | 071231005 | Improvement of FMR with Concreting & Grouted Riprap | 1 | Basic Access Infrastructure | Road | 0.138 | kms | 502856.8 | 162907.2 | 665764 | 2012-02-18 | 2012-05-30 | 402285.44 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Jose et. Al | 071231018 | Construction of 1 Unit 2 CL High School Building | 2 | Basic Social Services | School | 126 | sq. m | 991777.6 | 358623.4 | 1350401 | 2012-02-24 |  | 793422.08 | 1st | On-going
VII | 07 | Bohol | 0712 | Mabini | 071231 | Abaca | 071231001 | Improvement of Farm to market Road with Concreting and Gravelling | 1 | Basic Access Infrastructure | Road | 0.115 | kms | 488063.2 | 151613.8 | 639677 | 2012-03-01 | 2012-07-15 | 390450.56 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Valaga | 071231023 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 487916 | 150527 | 638443 | 2012-02-20 | 2012-05-30 | 463599.48 | 2nd | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Minol | 071231013 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.18 | kms | 502906.4 | 150369.6 | 653276 | 2012-02-27 | 2012-07-15 | 402325.12 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Bulawan | 071231006 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.167 | kms | 487893.6 | 153046.4 | 640940 | 2012-02-14 | 2012-06-30 | 390314.88 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Isidro | 071231017 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 285 | ln.m | 487330.8 | 196740.2 | 684071 | 2012-02-01 | 2012-05-30 | 389864.64 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Poblacion 1 | 071231015 | Improvement of Farm to market road | 1 | Basic Access Infrastructure | Road | 0.228 | kms | 502987.2 | 170339.8 | 673327 | 2012-02-24 | 2012-07-15 | 402389.76 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Rafael | 071231019 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.137 | kms | 487788 | 153380 | 641168 | 2012-02-23 | 2012-05-30 | 390230.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Poblacion 2 | 071231016 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.131 | kms | 487835.2 | 167657.8 | 655493 | 2012-02-24 | 2012-07-15 | 390268.16 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Delmar | 071231010 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 505156.53 | 244007.47 | 749164 | 2012-02-14 |  | 404125.22 | 1st | On-going
VII | 07 | Bohol | 0712 | Mabini | 071231 | Cawayanan | 071231009 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.18 | kms | 502738.4 | 150687.6 | 653426 | 2012-02-24 | 2012-07-15 | 402190.72 | 1st | Completed
VII | 07 | Bohol | 0712 | Mabini | 071231 | Tangkigan | 071231022 | Improvement of Farm to Maket Road with 20m Concreting | 1 | Basic Access Infrastructure | Road | 0.22 | kms | 488326.4 | 202109.6 | 690436 | 2012-02-29 |  | 244163.2 | 1st | On-going
VII | 07 | Bohol | 0712 | Mabini | 071231 | San Roque | 071231020 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 486871.88 | 259791.12 | 746663 | 2012-02-22 |  | 389497.5 | 1st | On-going
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Tilmobo | 071235019 | Seawall Extension | 1 | Environmental Protection and Conservation | Sea Wall | 19.3 | ln.m | 341618 | 185305 | 526923 | 2012-06-06 | 2012-07-15 | 273294.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Tugas | 071235020 | Seawall Extension | 1 | Environmental Protection and Conservation | Sea Wall | 30 | ln.m | 503073 | 231474 | 734547 | 2012-04-01 | 2012-06-30 | 402458.4 | 1st | Completed
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Butan | 071235023 | Comfort Rooms | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 6 | unit | 671452.53 | 330797.47 | 1002250 | 2012-05-22 |  | 537162 | 1st | On-going
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Gaus | 071235010 | Improvement of Conrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.977 | kms | 964115 | 466265 | 1430380 | 2012-04-13 |  | 771292 | 1st | On-going
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Bayog - Sto Rosario | 071235005 | Concreting of Pathway | 2 | Basic Access Infrastructure | Access Trail | 0.4 | kms | 1008201 | 434085 | 1442286 | 2012-03-10 | 2012-07-15 | 806560.8 | 1st | Completed
[6 empty] | Sto Rosario | 071235018
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Basiao | 071235003 | Concreting of Pathway with Tirepath | 1 | Basic Access Infrastructure | Access Trail | 0.1 | kms | 644553 | 298045 | 942598 | 2012-05-26 |  | 515642.4 | 1st | On-going
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Carlos P. Garvia (Pitogo) | 071235000 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.185 | kms | 512612 | 220088 | 732700 | 2012-04-02 |  | 410089.6 | 1st | On-going
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Aguining-Kabangkalan | 071235001 | Concreting of Pathway | 2 | Basic Access Infrastructure | Access Trail | 0.607 | kms | 1516347.2 | 650726.8 | 2167074 | 2012-03-15 |  | 1213077.76 | 1st | On-going
[6 empty] | Kabangkalan | 071235011
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Baud | 071235004 | Tirepath | 1 | Basic Access Infrastructure | Road | 0.342 | kms | 607867 | 275742 | 883609 | 2012-03-02 | 2012-07-15 | 486293.6 | 1st | Completed
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Bogo - Villa Milagrosa | 071235006 | Concreting of Pathway | 2 | Basic Access Infrastructure | Access Trail | 0.47 | kms | 1170179 | 520165 | 1690344 | 2012-02-25 | 2012-07-15 | 936143.2 | 1st | Completed
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Campamanog-San Vicente | 071235009 | Concreting of Tirepath | 2 | Basic Access Infrastructure | Road | 0.725 | kms | 1285952 | 605965 | 1891917 | 2012-03-10 |  | 1028761.6 | 1st | On-going
[6 empty] | San Vicente | 071235024
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Popoo | 071235015 | Concreting of Tirepath | 1 | Basic Access Infrastructure | Road | 0.414 | kms | 718370.6 | 346159.4 | 1064530 | 2012-04-02 |  | 574696.48 | 1st | On-going
VII | 07 | Bohol | 0712 | Carlos P. Garcia | 071235 | Lipata | 071235013 | Concreting Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.1485 | kms | 401969 | 180105 | 582074 | 2012-02-20 | 2012-07-15 | 379187 | 2nd | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Cambanagy Norte | 071238007 | Road Re-Gravelling | 1 | Basic Access Infrastructure | Road | 1.029 | kms | 468653 | 315387 | 784040 | 2012-02-08 | 2012-07-15 | 374992.4 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Hagbuyo | 071238011 | Two Units Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 700 | sq.m | 466885 | 223895 | 690780 | 2012-04-16 | 2012-05-30 | 373508 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Sto. Nino | 071238018 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 454235 | 207050 | 661285 | 2012-03-10 | 2012-06-30 | 363388 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Caluasan | 071238012 | Road Regravelling | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 421932 | 278523 | 700455 | 2012-03-16 | 2012-07-15 | 337545.6 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Corazon | 071238009 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 60 | ln.m | 696076 | 315290 | 1011366 | 2012-02-15 |  | 556860.8 | 1st | On-going
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Bayongan | 071238001 | Construction of Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 11.5 | ln.m | 357026 | 172280 | 529306 | 2012-03-20 | 2012-06-30 | 321323.4 | 2nd | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Tomoc | 071238019 | Electrification | 1 | Basic Social Services | Electrification | 30 | HH | 371367 | 261900 | 633267 | 2012-04-13 | 2012-07-15 | 297093.6 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Mahayag | 071238013 | Installation of Flatbed Dryer | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility |  | sq.m | 335574 | 347240 | 682814 | 2012-04-12 | 2012-06-30 | 268459.2 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Bugang | 071238003 | Installation of flatbed Drier w/ shed house | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 44 | sq.m | 439699 | 401114 | 840813 | 2012-03-12 | 2012-07-15 | 351759.2 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Garcia | 071238010 | Regravelling of farm to market road | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 456391 | 271064 | 727455 | 2012-02-22 | 2012-05-30 | 365112.8 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Jose | 071238016 | Improvement of farm to market road with concreting and spillway | 1 | Basic Access Infrastructure | Road | 0.23 | kms | 729353 | 314975 | 1044328 | 2012-03-16 | 2012-06-30 | 609536 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Capayas | 071238008 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 446939 | 204803 | 651742 | 2012-03-16 | 2012-07-15 | 357551.2 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Cabangahan | 071238004 | Improvement of FMR with Spillway and concreting | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 487749 | 240659 | 728408 | 2012-02-15 | 2012-07-15 | 390199.2 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San isidro | 071238015 | Regravelling of farm to market road | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 589055 | 282150 | 871205 | 2012-02-22 | 2012-06-30 | 471244 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Camanaga | 071238006 | Construction of 2 units solar drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 700 | sq.m | 466885 | 223895 | 690780 | 2012-02-25 | 2012-05-30 | 373508 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | San Vicente | 071238017 | Construction of Solar Drier with Storage | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 72 | sq.m | 478915 | 240605 | 719520 | 2012-03-19 | 2012-06-30 | 431023.5 | 2nd | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Kagawasan | 071238005 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 400699 | 174481 | 575180 | 2012-02-21 | 2012-05-30 | 320559.2 | 1st | Completed
VII | 07 | Bohol | 0712 | San Miguel | 071238 | Poblacion | 071238014 | Construction of Solar Drier with Shed | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility |  | sq.m | 32567 | 744385 | 776952 |  |  | 0 |  | Not yet started
VII | 07 | Bohol | 0712 | Carmen | 071212 | Nueva Fuerza | 071212019 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.18 | kms | 634070.85 | 285950.15 | 920021 |  |  | 507256.68 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Villarcayo | 071212029 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 524360.2 | 225389.8 | 749750 | 2012-03-06 |  | 419488.16 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Villafuerte | 071212028 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 766335.4 | 335072.6 | 1101408 | 2012-03-28 |  | 613068.32 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montevideo | 071212018 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.17 | kms | 625740.71 | 270058.29 | 895799 | 2012-04-25 |  | 375444.43 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | El Progreso | 071212006 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 0.61 | kms | 625574.79 | 273668.21 | 899243 | 2012-03-13 | 2012-07-15 | 500459.83 | 1st | Completed
VII | 07 | Bohol | 0712 | Carmen | 071212 | Vallehermoso | 071212026 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 523179.6 | 226091.4 | 749271 | 2012-03-30 |  | 418543.68 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Poblacion Norte | 071212023 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.407 | kms | 899996.3 | 403464.7 | 1303461 | 2012-04-21 |  | 719997.04 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Victoria | 071212013 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 521049.8 | 227290.2 | 748340 | 2012-03-13 |  | 416839.84 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Buenos Aires | 071212004 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 0.47 | kms | 659202.62 | 287239.38 | 946442 | 2012-04-18 |  | 527362.1 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | El Salvador | 071212007 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 0.46 | kms | 522740.23 | 231871.77 | 754612 | 2012-03-09 | 2012-07-15 | 418192.18 | 1st | Completed
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montesunting | 071212017 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 685552.36 | 296041.64 | 981594 | 2012-06-11 |  | 548441.89 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Guadalupe | 071212008 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.24 | kms | 680197.36 | 314932.64 | 995130 | 2012-06-08 |  | 544157.89 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Katipunan | 071212009 | Construction of Solar Drier with Warehouse | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 468.5 | sq.m | 538509.12 | 273321.88 | 811831 | 2012-03-08 |  | 430807.3 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Libertad | 071212010 | Construction of box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 18.1 | ln.m | 768904.34 | 351465.66 | 1120370 | 2012-03-05 | 2012-06-30 | 615123.47 | 1st | Completed
VII | 07 | Bohol | 0712 | Carmen | 071212 | Tambo-an | 071212025 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 0.36 | kms | 494679.65 | 214910.35 | 709590 | 2012-04-10 | 2012-07-15 | 395743.72 | 1st | Completed
VII | 07 | Bohol | 0712 | Carmen | 071212 | Matin-ao | 071212014 | Construction of health station | 1 | Basic Social Services | Health Station | 51 | sq.m | 524575.8 | 225021.2 | 749597 | 2012-02-27 |  | 419660.64 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montehermoso | 071212015 | Concreting of Farm to market road | 1 | Basic Access Infrastructure | Road | 0.09 | kms | 379011.85 | 222983.15 | 601995 | 2012-04-13 |  | 303209.48 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Montesuerte | 071212016 | Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 718315.02 | 326866.98 | 1045182 | 2012-06-02 |  | 574652.02 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Bicao | 071212002 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 610306.82 | 270380.18 | 880687 | 2012-04-18 | 2012-07-15 | 488245.46 | 1st | Completed
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Paz | 071212011 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.17 | kms | 544280.32 | 254707.68 | 798988 | 2012-05-10 | 2012-07-15 | 435424.26 | 1st | Completed
VII | 07 | Bohol | 0712 | Carmen | 071212 | La Salvacion | 071212012 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 0.38 | kms | 573581.31 | 246827.96 | 820409.27 | 2012-05-15 |  | 458865.05 | 1st | On-going
VII | 07 | Bohol | 0712 | Carmen | 071212 | Alegria | 071212001 | Concreting of Farm to market road | 1 | Basic Access Infrastructure | Road | 0.225 | kms | 229835.54 | 640903.46 | 870739 | 2012-04-17 | 2012-07-15 | 183868.43 | 1st | Completed
VII | 07 | Bohol | 0712 | Danao | 071218 | Sta. Fe | 071218013 | Construction of pathway | 1 | Basic Access Infrastructure | Access Trail |  | kms | 268900 | 725400 | 994300 | 2012-03-14 |  | 215120 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Nahud | 071218008 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 461000 | 283250 | 744250 | 2012-03-12 |  | 368800 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Taming | 071218016 | Construction of 1 unit Pre-School Building | 1 | Basic Social Services | School | 63 | sq. m | 465992 | 276508 | 742500 | 2012-02-17 |  | 372793.6 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Hibale | 071218006 | 1 CL Pre-School Building | 1 | Basic Social Services | School | 63 | sq. m | 465992 | 276508 | 742500 | 2012-03-06 |  | 372793.59 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Poblacion | 071218009 | 1 CL Pre-School Building | 1 | Basic Social Services | School | 63 | sq. m | 465992 | 276508 | 742500 | 2012-03-15 |  | 372793.6 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Dagohoy | 071218005 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 362700 | 274300 | 637000 |  |  | 290160 | 1st | Not yet started
VII | 07 | Bohol | 0712 | Danao | 071218 | Carbon | 071218003 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 370808 | 246192 | 617000 |  |  | 296646.4 | 1st | Not yet started
VII | 07 | Bohol | 0712 | Danao | 071218 | Cantubod | 071218002 | Construction of water System Level II | 1 | Basic Social Services | Water System | 1 | system | 522036 | 293352 | 815388 |  |  | 417628.8 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Magtangtang | 071218007 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 466440 | 282560 | 749000 | 2012-02-27 |  | 373152 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Concepcion | 071218004 | 1 CL Pre-school Building | 1 | Basic Social Services | School | 63 | sq. m | 465992 | 276508 | 742500 | 2012-02-13 |  | 372793.6 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Villa Anunciado | 071218017 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 466440 | 282560 | 749000 | 2012-04-10 |  | 373152 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Sto. Nino | 071218014 | Expansion of water System level II | 1 | Basic Social Services | Water System | 1 | system | 521800 | 971648 | 1493448 | 2012-06-13 |  | 417440 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | San Carlos | 071218011 | Improvement of farm to market road | 1 | Basic Access Infrastructure | Road | 1 | kms | 316800 | 299600 | 616400 |  |  | 253440 | 1st | Not yet started
VII | 07 | Bohol | 0712 | Danao | 071218 | San Miguel | 071218012 | Construction of 2 units Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 522160 | 429740 | 951900 |  |  | 417728 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Cabatuan | 071218001 | Concreting of 1 unit Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 516295 | 357505 | 873800 | 2012-04-24 |  | 413036 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Remedios | 071218010 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 461000 | 283250 | 744250 | 2012-02-27 |  | 368800 | 1st | On-going
VII | 07 | Bohol | 0712 | Danao | 071218 | Tabok | 071218015 | Construction of Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 130 | ln.m | 529653 | 542011 | 1071664 | 2012-02-27 |  | 423722.4 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Sto. Nino | 071226022 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 524300 | 220200 | 744500 | 2012-02-23 |  | 471870 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Saguise | 071226019 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 518248 | 218252 | 736500 | 2012-02-22 |  | 466423.2 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Tulang | 071226025 | Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 397395 | 172541 | 569936 | 2012-03-20 |  | 357655.5 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Corte Baud | 071226010 | Extension of Fishport | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 74 | ln.m | 406168 | 183832 | 590000 | 2012-03-10 |  | 365551.2 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Taytay | 071226023 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 540263 | 234468 | 774731 | 2012-03-15 |  | 486236.7 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Alumar | 071226001 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 544932 | 229474 | 774406 | 2012-03-05 |  | 435945.6 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Salog | 071226020 | Electrification | 1 | Basic Social Services | Electrification | 58 | HH | 545600 | 261200 | 806800 | 2012-04-15 |  | 436480 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Campao Occ | 071226008 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 398230 | 170670 | 568900 | 2012-03-01 |  | 313084 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Jandayan | 071226013 | Pathway Concreting | 1 | Basic Access Infrastructure | Access Trail | 0.28 | kms | 368866 | 158086 | 526952 | 2012-04-01 |  | 295092.8 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Cabasakan | 071226004 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.22 | kms | 544600 | 233400 | 778000 | 2012-04-07 |  | 435680 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Mahanay | 071226015 | 1 CL school Building | 1 | Basic Social Services | School | 63 | sq. m | 547120 | 232298 | 779418 | 2012-02-29 |  | 437696 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Handumon | 071226011 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.23 | kms | 383380 | 164306 | 547686 | 2012-03-15 |  | 306704 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Poblacion | 071226018 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 498756 | 214580 | 713336 | 2012-02-23 |  | 399004.8 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Cangmundo | 071226008 | Electrification | 1 | Basic Social Services | Electrification | 62 | HH | 514845 | 262655 | 777500 | 2012-04-01 |  | 411876 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | San Jose | 071226021 | Electrification | 1 | Basic Social Services | Electrification | 39 | HH | 434000 | 221500 | 655500 | 2012-04-08 |  | 390600 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Campo Or | 071226007 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.12 | kms | 365303 | 156957 | 522260 | 2012-03-20 |  | 292242.4 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Nasingin | 071226016 | Rain Collector | 1 | Basic Social Services | Water System | 1 | system | 567200 | 243100 | 810300 | 2012-04-15 |  | 453760 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Tugas | 071226024 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 516861.6 | 224230.4 | 741092 | 2012-04-23 |  | 413489.28 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Carlos P. Garcia | 071226009 | Electrification | 1 | Basic Social Services | Electrification | 30 | HH | 428961 | 188839 | 617800 | 2012-04-15 |  | 386064.9 | 2nd | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Jagoliao | 071226012 | Extension of Fishport | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 32 | ln.m | 625000 | 268900 | 893900 |  |  | 500000 | 1st | Not yet started
VII | 07 | Bohol | 0712 | Getafe | 071226 | Buyog | 071226003 | Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 436000 | 189000 | 625000 | 2012-04-20 |  | 348800 | 1st | On-going
VII | 07 | Bohol | 0712 | Getafe | 071226 | Jandayan Sur | 071226014 | Rain Wate Collector | 1 | Basic Social Services | Water System | 1 | system | 591321 | 660679 | 1252000 | 2012-04-07 | 2012-07-15 | 473056.8 | 1st | Completed
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Tuboran | 071248015 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 529843.6 | 194608.4 | 724452 | 2012-03-14 | 2012-07-15 | 423874.88 | 1st | Completed
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Hingotanan West | 071248004 | Concrete Paving of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.45 | kms | 423670.4 | 240547.6 | 664218 | 2012-04-16 |  | 338936.32 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Malingin | 071248006 | Rain water Collector with roofing for Catchment | 1 | Basic Social Services | Water System | 1 | system | 513511.6 | 247025.4 | 760537 | 2012-04-09 |  | 410809.28 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Mandawa | 071248007 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 512313.8 | 237178.2 | 749492 | 2012-03-30 | 2012-07-15 | 409851.04 | 1st | Completed
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Maomawan | 071248008 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 533827.7 | 287042.3 | 820870 | 2012-03-29 |  | 427062.16 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Sagasa | 071248014 | Contruction of Rain Water Collector With Roofing Catchment | 1 | Basic Social Services | Water System | 1 | system | 501448.26 | 214278.74 | 715727 |  |  | 401158.61 | 1st | Not yet started
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Bilangbilangan Daku | 071248001 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.45 | kms | 423670.4 | 259147.6 | 682818 | 2012-05-17 |  | 338936.32 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Puerto San Pedro | 071248013 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 512451.3 | 237040.7 | 749492 | 2012-03-20 | 2012-07-15 | 461206.17 | 2nd | Completed
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Nueva Estrella | 071248010 | Surfacing of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.26 | kms | 416588 | 148082 | 564670 | 2012-05-11 |  | 333270.4 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Nueva Esperanza | 071248009 | Surfacing of farm to market road | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 439502.4 | 155685.6 | 595188 | 2012-05-02 |  | 351601.92 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Bilangbilangan East | 071248003 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 504769.2 | 251657.8 | 756427 | 2012-05-22 |  | 403815.36 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Liberty | 071248005 | 1 Unit Pre-School Building | 1 | Basic Social Services | School | 63 | sq. m | 502058.85 | 224711.15 | 726770 | 2012-03-28 | 2012-06-30 | 401647.08 | 1st | Completed
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Poblacion | 071248012 | Surfacing of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.27 | kms | 417501.6 | 148085.4 | 565587 | 2012-03-26 |  | 334001.28 | 1st | On-going
VII | 07 | Bohol | 0712 | Bien Unido | 011248 | Pinamgo | 071248011 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 517943.2 | 234438.8 | 752382 | 2012-04-02 |  | 414354.56 | 1st | On-going
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Salvacion | 051610005 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 603763.71 | 193369.66 | 797133.37 |  |  | 441344.95 | 1st | On-going
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | San Pedro | 051610007 | Construction of 1 Unit 1 CL HS Building | 1 | Basic Social Services | School | 63 | sq. m | 629182.26 | 167817.74 | 797000 | 2012-03-06 | 2012-07-15 | 396508.33 | 1st | Completed
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Kagtalaba | 051610014 | Construction of 1 CL ES Building | 1 | Basic Social Services | School | 63 | sq. m | 622222.27 | 181777.73 | 804000 | 2012-03-12 | 2012-07-15 | 560000 | 2nd | Completed
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Villa San Isidro | 051610010 | Improvemement of FMR with Spot Concreting | 1 | Basic Access Infrastructure | Road | 0 | kms | 1150085.66 | 301314.34 | 1451400 | 2012-03-05 |  | 849921.16 | 1st | On-going
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Basiad | 051610001 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 641087.34 | 212712.66 | 853800 | 2012-02-27 |  | 576978.6 | 2nd | On-going
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Patag Ibaba | 051610016 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 51 | sq. m | 615745.4 | 191954.6 | 807700 | 2012-03-07 | 2012-07-15 | 554170.86 | 2nd | Completed
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Tabugon | 051610019 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 624223.26 | 172076.74 | 796300 | 2012-02-28 |  | 561800.93 | 2nd | On-going
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Maulawin | 051610015 | Construction of Single Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 648153.48 | 208946.52 | 857100 | 2012-03-05 | 2012-07-15 | 583338.13 | 2nd | Completed
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Plaridel | 051610018 | Construction of Single Barrel Box Culver | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 678003 | 180097 | 858100 | 2012-04-19 | 2012-07-15 | 610202.7 | 2nd | Completed
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Kabuluan | 051610013 | Improvement of Farm to Market road with Road Concreting | 1 | Basic Access Infrastructure | Road | 1 | kms | 1146306.78 | 316393.22 | 1462700 | 2012-04-17 | 2012-07-15 | 1031676.1 | 2nd | Completed
V | 05 | Camarines Norte | 0516 | Sta. Elena | 051610 | Guitol | 051610012 | Improvement of Farm to Market Road with Concreting | 1 | Basic Access Infrastructure | Road | 0.792 | kms | 1076606.73 | 307693.27 | 1384300 | 2012-04-18 |  | 968946.06 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Mabini | 051712008 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.9775 | kms | 1206863.06 | 301897.92 | 1508760.98 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Poblacion Zone III | 051712020 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1120000 | 281010 | 1401010 | 2012-03-12 |  | 1008000 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Domagondong | 051712005 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 2.761 | kms | 1743959.35 | 436790.28 | 2180749.63 | 2012-05-07 | 2012-07-15 | 1341323.7 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Magais I | 051712009 | Construction of 1 Unit 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 626000 | 156593 | 782593 | 2012-03-05 | 2012-06-30 | 563400.4 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Sta. Rita II | 051712026 | Road Opening | 1 | Basic Access Infrastructure | Road | 1.481 | kms | 2744044.69 | 687062.9 | 3431107.59 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Salvacion | 051712022 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.604 | kms | 400237.26 | 99942.06 | 500179.32 | 2012-03-13 | 2012-05-30 | 305082.08 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Pinagdapian | 051712016 | Improvement of Farm to Market Road with RCBC | 1 | Basic Access Infrastructure | Road | 0.925 | kms | 1181095.1 | 295445.54 | 1476540.64 | 2012-05-15 | 2012-06-30 | 911712.66 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Palaspas | 051712013 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.628 | kms | 1180282.87 | 294645.7 | 1474928.57 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Sinuknipan I | 051712028 | Construction of 1 Unit ES School Building and 1 Unit HS School Building | 1 | Basic Social Services | School | 126 | sq. m | 1252000 | 314215 | 1566215 | 2012-03-13 | 2012-06-30 | 1126800 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Mansalaya | 051712011 | Improvement of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.354 | kms | 481279.88 | 120079.72 | 601359.6 | 2012-03-24 | 2012-05-30 | 361446.28 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Bucal | 051712002 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.668 | kms | 847099.95 | 212256.5 | 1059356.45 | 2012-03-03 | 2012-06-30 | 677679.96 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Magais II | 051712010 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 670000 | 168393 | 838393 | 2012-03-08 |  | 603000 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Del Gallego | 051712 | Pasay | 051712015 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 626000 | 156593 | 782593 | 2012-03-12 |  | 563400 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Bahay | 051727003 | Construction of 1 unit 2 CL Elementary School Building | 1 | Basic Social Services | School | 126 | sq. m | 1010000 | 263612 | 1273612 | 2012-03-05 | 2012-07-30 | 909000 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | San Antonio | 051727014 | Construction of Water System Level 2 | 1 | Basic Social Services | Water System | 1 | system | 858000 | 242124 | 1100124 | 2012-04-10 | 2012-07-15 | 686400 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Dalupaon | 051727007 | Construction of 1 Unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1052000 | 275451 | 1327451 | 2012-02-27 | 2012-07-15 | 793222 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Quitang | 051727012 | Construction of Community Library and Information Center | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | 63 | sq.m | 597000 | 156510 | 753510 | 2012-03-12 | 2012-07-15 | 537299.1 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Bagong Silang | 051727002 | Construction of Solar Drier | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 540 | sq.m | 399000 | 102313 | 501313 | 2012-03-20 | 2012-07-30 | 317497.1 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Itulan | 051727010 | Construction of 1 Unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1010000 | 263612 | 1273612 | 2012-03-13 | 2012-07-15 | 666952 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Hubo | 051727009 | Construction of Slope Protection | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 60 | ln.m | 517000 | 130034 | 647034 | 2012-03-06 | 2012-07-15 | 409101.6 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Caranan | 051727005 | Construction of 1 Unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1029000 | 269302 | 1298302 | 2012-03-01 | 2012-07-15 | 713006 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Odicon | 051727011 | Construction of Community Library and Information Center | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library | 63 | sq.m | 597000 | 156510 | 753510 | 2012-03-12 | 2012-07-15 | 537299.1 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Balogo | 051727004 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) |  | ln.m | 960000 | 250243 | 1210243 | 2012-03-19 | 2012-07-15 | 748942.8 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Sta. Rosa Del Sur | 051727017 | Rehabilitation of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 150 | ln.m | 161000 | 61452 | 222452 | 2012-02-24 | 2012-07-15 | 124000.44 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Pasacao | 051727 | Tilnac | 051727019 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 240 | ln.m | 360000 | 452159 | 812159 | 2012-03-02 | 2012-07-15 | 285039.5 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Cabanbanan | 051702002 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 670862.21 | 124532.79 | 795395 | 2012-04-22 | 2012-07-30 | 492233.71 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Cayogcog | 051702006 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 415106 | 94343 | 509449 | 2012-04-22 |  | 302873.4 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Lulusan | 051702010 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 1096 | ln.m | 1020560 | 159048 | 1179608 | 2012-04-20 |  | 651912 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Montenegro | 051702011 | Purchase of 2 Unit Hand Tractor and 2 Unit Thresher with Blower | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility |  | sq.m | 177937.18 | 54768.82 | 232706 | 2012-05-15 | 2012-06-30 | 142349.74 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Pulangdaga | 051702014 | Construction of water System level II | 1 | Basic Social Services | Water System | 1 | system | 879719 | 166736 | 1046455 | 2012-04-23 | 2012-07-15 | 689190 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Tomatarayo | 051702019 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 738257.5 | 135933.5 | 874191 | 2012-04-20 | 2012-05-30 | 505448.4 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Duran | 051702008 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 679189.09 | 125457.91 | 804647 | 2012-04-22 | 2012-07-15 | 462053.49 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Siramag | 051702013 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 841 | ln.m | 681460 | 125921 | 807381 | 2012-04-22 |  | 458522.6 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Santiago | 051702017 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 743781.84 | 142634.16 | 886416 | 2012-05-04 |  | 524055.87 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Coguit | 051702007 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 970 | ln.m | 974030 | 153159 | 1127189 | 2012-04-21 |  | 576896 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Tapayas | 051702018 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 560312.18 | 254465.82 | 814778 | 2012-04-20 | 2012-07-15 | 448249.78 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | Laganac | 051702009 | Construction of Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 31 | ln.m | 278796.15 | 109862.85 | 388659 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Balatan | 051702 | San Francisco | 051702016 | Construction of Spillway | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 8 | ln.m | 255031.45 | 102496.55 | 357528 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Ason | 051714001 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 651477.68 | 143277.32 | 794755 | 2012-02-28 | 2012-06-30 | 463716.93 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Burabod | 051714004 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 100 | ln.m | 251524.08 | 135575.92 | 387100 | 2012-02-27 | 2012-06-30 | 226373.93 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Denrica | 051714010 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 993632.3 | 375067.7 | 1368700 | 2012-03-19 | 2012-07-15 | 894269.07 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Pambuhan | 051714013 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.225 | kms | 276259.24 | 170140.76 | 446400 | 2012-02-20 | 2012-04-30 | 248634 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Cagamutan | 051714005 | Construction of Slope Protection | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 100 | ln.m | 470878.15 | 265551.85 | 736430 | 2012-04-10 | 2012-07-15 | 423790.33 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Dangla | 051714008 | Construction of Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 8 | ln.m | 190427 | 104173 | 294600 | 2012-03-01 | 2012-06-30 | 171438.01 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Poblacion IV | 051714017 | Construction of Public market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 367.53 | sq.m | 3233524.59 | 1211375.41 | 4444900 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Cagnipa | 051714006 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 50 | ln.m | 440269.56 | 185042.44 | 625312 | 2012-04-10 | 2012-06-30 | 396242.6 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Bahi | 051714002 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1019868.85 | 355831.15 | 1375700 | 2012-03-08 | 2012-07-15 | 1014831.72 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Del Pilar | 051714009 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 150 | ln.m | 1047695.39 | 372604.61 | 1420300 | 2012-05-10 | 2012-05-30 | 942925.85 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Toytoy | 051714023 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.4 | kms | 324443.53 | 236556.47 | 561000 | 2012-02-27 | 2012-06-30 | 291999.18 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Sumaoy | 051714021 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 631604.68 | 166280.8 | 797885.48 | 2012-04-16 | 2012-07-15 | 568444.21 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Garchitorena | 051714 | Sagrada | 051714018 | Contruction of Gabion - Levee Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 818394.95 | 921923.28 | 1740318.23 | 2012-03-05 | 2012-07-15 | 736555.45 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Aniog | 051731001 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.36 | kms | 1152000 | 288000 | 1440000 |  |  | 921600 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Kilomaon | 051731008 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 646400 | 161600 | 808000 | 2012-04-15 | 2012-06-30 | 517120 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Kilantaao | 051731007 | Road Opening | 1 | Basic Access Infrastructure | Road | 1.376 | kms | 1508000 | 377000 | 1885000 | 2012-03-30 | 2012-06-30 | 1206400 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Minadongjol | 051731011 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 1532800 | 383200 | 1916000 | 2012-04-30 | 2012-06-30 | 1226240 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Bognalon | 051731003 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 1220000 | 305000 | 1525000 | 2012-03-15 | 2012-05-30 | 976000 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Tinorongan | 051731022 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 660800 | 165200 | 826000 | 2012-02-08 | 2012-06-30 | 528640 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Patitinan | 051731014 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 648000 | 162000 | 810000 | 2012-02-14 | 2012-05-30 | 583200 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Nato | 051731012 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 640000 | 160000 | 800000 | 2012-01-25 | 2012-05-30 | 576000 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Mabca | 051731010 | Construction of footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 10 | ln.m | 203200 | 50800 | 254000 | 2012-04-15 | 2012-06-30 | 162560 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Sagnay | 051731 | Sto. Nino | 051731019 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 50 | ln.m | 338800 | 321200 | 660000 | 2012-05-20 | 2012-06-30 | 271040 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Francisco | 051722020 | Contruction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 157.87 | ln.m | 232620.83 | 46524.17 | 279145 | 2012-03-05 | 2012-06-30 | 221080.53 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Taban | 051722023 | Construction of 1 CL Pre-School Building | 1 | Basic Social Services | School | 63 | sq. m | 740406.67 | 148081.33 | 888488 | 2012-05-08 | 2012-07-15 | 531579.34 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Hamoraon | 051722009 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 209.4 | ln.m | 393228.33 | 78645.67 | 471874 | 2012-03-09 | 2012-06-30 | 373228.33 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Magadap | 051722012 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 383 | ln.m | 641818.33 | 128363.67 | 770182 | 2012-03-10 | 2012-05-30 | 621818.33 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Irayang Solong | 051722011 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 720449.58 | 144089.92 | 864539.5 | 2012-04-30 | 2012-07-15 | 515819 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Malitbog | 051722013 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 479.85 | ln.m | 794167.5 | 158833.5 | 953001 | 2012-03-02 | 2012-06-30 | 714750.75 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Hobo | 051722010 | Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 147.4 | ln.m | 386548.17 | 77309.63 | 463857.8 | 2012-03-05 | 2012-05-30 | 308174.37 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Antipolo | 051722001 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 740187.08 | 148037.42 | 888224.5 | 2012-05-02 | 2012-07-15 | 529403.66 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Timbang | 051722025 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 26 | ln.m | 796250 | 159250 | 955500 | 2012-04-10 | 2012-06-30 | 747018.87 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Nuevo | 051722004 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 173 | ln.m | 297990.83 | 59598.17 | 357589 | 2012-02-27 | 2012-05-30 | 297990.83 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Jose | 051722021 | Concreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 1122038.23 | 224407.65 | 1346445.88 | 2012-03-05 | 2012-06-30 | 897368.23 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Del Carmen - Del Rosario | 051722007 | Construction of Flood Control | 2 | Environmental Protection and Conservation | River Control/Flood Control | 497 | ln.m | 1299666.67 | 259933.33 | 1559600 | 2012-04-24 |  | 1039555.67 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Felipe - Santiago | 051722019 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 450.7 | ln.m | 846464.17 | 169292.83 | 1015757 | 2012-03-01 | 2012-06-30 | 761817.75 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | San Juan-San Lorenzo | 051722022 | Conreting of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.208 | kms | 360638.83 | 72127.77 | 432766.6 | 2012-02-28 | 2012-05-30 | 324192.71 | 2nd | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Baliuag Viejo | 051722005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 732080.42 | 146416.08 | 878496.5 | 2012-05-07 |  | 528790.34 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Tariric | 051722024 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 723394.58 | 144678.92 | 868073.5 | 2012-05-03 | 2012-07-15 | 520175 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Minalabac | 051722 | Catanusan | 051722006 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 666170.83 | 133234.7 | 799405.53 | 2012-05-07 | 2012-07-15 | 532754.83 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Bantugan | 051729004 | Road Rehabilitation | 1 | Basic Access Infrastructure | Road | 2.5 | kms | 2060074.15 | 848654.8 | 2908728.95 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Maangas | 051729013 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1662861.03 | 1031692.97 | 2694554 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Tanawan | 051729019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 561297.11 | 228049.89 | 789347 |  |  | 449037.63 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Lidong | 051729011 | Road Rehabilitation | 1 | Basic Access Infrastructure | Road | 2.637 | kms | 2157853.38 | 856191.69 | 3014045.07 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Buenavista | 051729007 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 1263041.02 | 575651.12 | 1838692.14 |  |  | 0 |  | On-going
V | 05 | Camarines Sur | 0517 | Presentacion | 051729 | Patrocinio | 051729016 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 48 | ln.m | 365754.55 | 270969.77 | 636724.32 |  |  | 255273.09 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Cabugao | 051735005 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 603517.95 | 190003.05 | 793521 | 2012-05-12 |  | 482814.35 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Pamintan | 051735016 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 614272.33 | 238552.67 | 852825 |  |  | 0 |  | Not yet started
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Matandang Siruma | 051735013 | Construction of Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 124 | ln.m | 1565809.69 | 606120.31 | 2171930 | 2012-05-01 |  | 0 |  | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Mabuhay | 051735010 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.34 | kms | 1103313.44 | 431626.56 | 1534940 | 2012-04-12 |  | 827485 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Nalayahan | 051735012 | Concreting of pathway | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 366160.95 | 158355.05 | 524516 | 2012-04-19 |  | 292928 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Penitan | 051735014 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1027786.26 | 382213.74 | 1410000 | 2012-04-11 |  | 925007.5 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Sulpa | 051735020 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 0.3 | ln.m | 1042711.83 | 377038.17 | 1419750 | 2012-04-19 | 2012-07-15 | 834165 | 1st | Completed
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Matandang Siruma | 051735013 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 592525.58 | 200995.42 | 793521 | 2012-05-01 |  | 533272.95 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Homestead | 051735008 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 597411.08 | 196109.92 | 793521 | 2012-05-28 |  | 477928.8 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | LA Purisima | 051735009 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 598632.45 | 194888.55 | 793521 | 2012-05-12 |  | 478905.95 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | San Ramon | 051735019 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 597411.08 | 196109.92 | 793521 | 2012-05-19 |  | 537669.9 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Bahao | 051735002 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.365 | kms | 1242721.31 | 436687.69 | 1679409 | 2012-04-13 |  | 1118449.18 | 2nd | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Boboan | 051735003 | Rehab of 3 CL School Building | 1 | Basic Social Services | School | 199.08 | sq. m | 525478.38 | 204851.62 | 730330 | 2012-04-11 |  | 420382.7 | 1st | On-going
V | 05 | Camarines Sur | 0517 | Siruma | 051735 | Vito | 051735023 | Construction of footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 100 | ln.m | 1565809.69 | 606120.31 | 2171930 | 2012-04-20 |  | 1252647.75 | 1st | On-going
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Tucao | 052004027 | Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 100 | ln.m | 2893661 | 816928 | 3710589 |  |  | 0 |  | Not yet started
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Camburo | 052004006 | Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 148 | ln.m | 3300408 | 1115387 | 4415795 |  |  | 0 |  | Not yet started
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Maysuram | 052004018 | Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 100 | ln.m | 2460148 | 885801 | 3345949 |  |  | 0 |  | Not yet started
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Bulalacao | 052004005 | Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 105 | ln.m | 388738 | 482422 | 871160 | 2012-01-30 | 2012-05-30 | 388888 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Maui | 052004017 | Farm to Market Road with box culvert | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 350534 | 119503 | 470037 | 2012-03-05 | 2012-06-30 | 265587 | 1st | Completed
V | 05 | Catanduanes | 0520 | Caramoran | 052004 | Inalmasinan | 052004013 | Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 100 | ln.m | 2756511 | 1590459 | 4346970 |  |  | 1378255.85 | 1st | On-going
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Bagatabao | 052001003 | Construction of Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 36 | ln.m | 954388.12 | 397401.31 | 1351789.43 | 2012-04-16 |  | 760314.24 | 1st | On-going
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | San Isidro | 052001014 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 573 | ln.m | 659242.68 | 303500.16 | 962742.84 | 2012-02-18 | 2012-06-30 | 593318.41 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | San Rafael | 052001015 | Construction of 1 Unit Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 531044.83 | 251107.27 | 782152.1 | 2012-01-25 | 2012-06-30 | 477940.35 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Sta. Mesa | 052001017 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 492349.52 | 232602.78 | 724952.3 | 2012-01-24 | 2012-06-30 | 443114.57 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Quigaray | 052001010 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 501284.82 | 219020.72 | 720305.54 | 2012-02-28 | 2012-06-30 | 451156.34 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Antipolo | 052001001 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 332 | ln.m | 414128.54 | 188581.32 | 602709.86 | 2012-01-30 | 2012-05-30 | 372715.69 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Sta. Teresa | 052001018 | Construction of drainage canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 283 | ln.m | 423940.93 | 188528.04 | 612468.97 | 2012-02-14 | 2012-05-30 | 381546.84 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Magsaysay | 052001007 | Road Improvement ofwith Slope Protection | 1 | Basic Access Infrastructure | Road | 0.7 | kms | 148839.88 | 84512.57 | 233352.45 | 2012-02-27 | 2012-06-30 | 133955.89 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Salvacion | 052001013 | Road Improvement with Slope Protection | 1 | Basic Access Infrastructure | Road | 0.13 | kms | 103328.02 | 76569.03 | 179897.05 | 2012-02-27 | 2012-06-30 | 92995.22 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Cahan | 052001005 | Construction of Spillway with Slope Protection | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 91 | ln.m | 1275139.88 | 530323.27 | 1805463.15 | 2012-03-15 | 2012-07-15 | 1147625.89 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | San Vicente | 052001016 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1285149.33 | 482997.58 | 1768146.91 | 2012-05-01 |  | 1025317.56 | 1st | On-going
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Bacak | 052001002 | Construction of Spillway with Slope Protection | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 65 | ln.m | 683959.34 | 299858.43 | 983817.77 | 2012-02-13 | 2012-06-30 | 615563.41 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Quezon | 052001011 | Contruction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 495911.89 | 229040.41 | 724952.3 | 2012-01-30 | 2012-06-30 | 446320.7 | 2nd | Completed
V | 05 | Catanduanes | 0520 | Bagamanoc | 052001 | Sagrada | 052001012 | Construction of Draiange System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 909 | ln.m | 131292.24 | 1061069.86 | 1192362.1 | 2012-04-10 |  | 65646.12 | 1st | On-going
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Luhong and Danggo | 142710008 | Bebley-Manaan- Kilong Farm to market Road | 2 | Basic Access Infrastructure | Road | 4 | kms | 1910896.56 | 715820 | 2626716.56 | 2012-03-29 | 2012-06-30 | 955448.28 | 1st | Completed
[6 empty] | Danggo | 142710004
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ahin | 142710001 | Telep Ahin Farm to market road | 1 | Basic Access Infrastructure | Road | 1.26 | kms | 614522.56 | 196900 | 811422.56 | 2012-02-27 | 2012-05-30 | 313406.51 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Wangwang | 142710012 | Bahal-Anao Road | 1 | Basic Access Infrastructure | Road | 0.11 | kms | 357489.19 | 135900 | 493389.19 | 2012-03-15 | 2012-04-30 | 285991.35 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Impugong | 142710007 | Tullibeng - Aballa FMR | 1 | Basic Access Infrastructure | Road | 1.44 | kms | 490748 | 190930 | 681678 | 2012-03-05 | 2012-06-30 | 245374 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Binabalayan | 142710003 | Matnol-Litobong FMR | 1 | Basic Access Infrastructure | Road | 1.17 | kms | 673079.36 | 256884.84 | 929964.2 | 2012-03-15 | 2012-06-30 | 343270.47 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Ap-apid | 142710002 | Palabayan-Mulmog Road Improvement | 1 | Basic Access Infrastructure | Road | 0.366 | kms | 304492.95 | 124280 | 428772.95 | 2012-02-27 | 2012-03-30 | 237504.5 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Tukucan | 142710010 | Napu-Maleteng FMR | 1 | Basic Access Infrastructure | Road | 1 | kms | 457012.96 | 150600 | 607612.96 | 2012-03-10 | 2012-05-30 | 237646.74 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Tinoc | 142710 | Eheb | 142710005 | 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 591758.42 | 678700 | 1270458.42 | 2012-03-15 | 2012-06-30 | 473406.74 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Ubuag | 142709010 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 633127.98 | 158630.75 | 791758.73 |  |  | 379876.79 | 1st | On-going
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Namulditan | 142709006 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 613534.79 | 157880.57 | 771415.36 | 2012-06-28 |  | 368120.87 | 1st | On-going
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Poblacion | 142709009 | Construction of 2 Storey Multi Purpose Building | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility |  | sq.m | 1264644.8 | 318872.33 | 1583517.13 | 2012-02-26 |  | 632322.4 | 1st | On-going
CAR | 14 | Ifugao | 1427 | Hingyon | 142709 | Bitu | 142709003 | Bitu-Atugo Road Improvement | 1 | Basic Access Infrastructure | Road |  | kms | 1928059.4 | 670211.73 | 2598271.13 |  |  | 0 | 0 | Not yet started
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Pula | 142711009 | Construction of 3 Cross Draiange along lower Duli to Tadyokong FMR | 1 | Basic Access Infrastructure | Road |  | kms | 967897.71 | 375798.36 | 1343696.07 | 2012-03-31 | 2012-06-30 | 774318.17 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Hallap | 142711005 | Construction of 169.19 ln.m PCCP Along Upper Haliap Panakligan Road | 1 | Basic Access Infrastructure | Road | 0.169 | kms | 501817.32 | 268632.31 | 770449.63 | 2012-03-31 | 2012-06-30 | 401453.86 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Natcak |  | Construction of Banihal-Palpalay Sledge Trail | 1 | Basic Access Infrastructure | Access Trail | 3.2 | kms | 510000 | 307455.5 | 817455.5 | 2012-04-01 | 2012-05-30 | 357000 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Antipolo | 142711002 | Construction of PCCP and Retaining wall | 1 | Basic Access Infrastructure | Road | 0.225 | kms | 542790.89 | 851591.89 | 1394382.78 | 2012-04-10 | 2012-06-30 | 434232.71 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Nungawa | 142711007 | Road Concreting | 1 | Basic Access Infrastructure | Road |  | kms | 770000 | 340067.19 | 1110067.19 | 2012-03-31 | 2012-06-30 | 616000 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Duli |  | 3 Units Single line 900 mm RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 0.27 | ln.m | 364031.7 | 241967.54 | 605999.24 | 2012-04-15 |  | 291225.36 | 1st | On-going
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | liwon |  | Road Concreting | 1 | Basic Access Infrastructure | Road |  | kms | 545809.9 | 312216.71 | 858026.61 | 2012-04-01 | 2012-06-30 | 314769.9 | 1st | Completed
CAR | 14 | Ifugao | 1427 | Asipulo | 142711 | Pula | 142711009 | Construction of Stoned Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 760 | ln.m | 967897.71 | 379794.36 | 1347692.07 |  |  | 774318.17 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Taga | 143209022 | Construction of Cable Foot Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 280 | ln.m | 3990717.36 | 1042679.34 | 5033396.7 |  |  | 0 |  | Not yet started
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Camalog | 143209009 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 300 | ln.m | 556741.91 | 174432.62 | 731174.53 | 2012-05-01 | 2012-06-30 | 453393.53 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Malagnat | 143209016 | Construction of Multi-Purpose Building | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 96 | sq.m | 882271.79 | 267412.95 | 1149684.74 | 2012-04-21 | 2012-06-30 | 566563.66 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Bayao | 143209007 | Construction of 3 Units Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 900 | sq.m | 551871.33 | 186106.41 | 737977.74 | 2012-05-01 | 2012-05-30 | 441497.06 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Dugpa | 143209011 | Construction of 3 Units Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 900 | sq.m | 507950.53 | 174541.22 | 682491.75 | 2012-05-16 | 2012-06-30 | 406360.42 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Mapaco | 143209018 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 678319.71 | 211696.04 | 890015.75 | 2012-04-16 |  | 471323.05 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Pakawit | 143209019 | Construction of 3 Units Multi-Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility |  | sq.m | 508437.56 | 159652.3 | 668089.86 | 2012-05-01 | 2012-06-30 | 406750.05 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Ba-ay | 143209005 | Construction of Cable Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 30 | ln.m | 1030495.25 | 280354.27 | 1310849.52 | 2012-05-01 |  | 824396.2 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Apatan | 143209004 | Construction of 2 Units Concrete Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 15 | ln.m | 368988.03 | 139464.71 | 508452.74 | 2012-05-01 | 2012-06-30 | 295190.42 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Socbot | 143209021 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control |  | ln.m | 879983.2 | 264138.3 | 1144121.5 | 2012-05-16 | 2012-06-30 | 703986.56 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Malucsad | 143208013 | Improvement of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 418 | ln.m | 434327.2 | 175956.88 | 610284.08 | 2012-05-14 |  | 347461.76 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Guina-ang | 143208011 | Improvement of Amdalao-Guina-ang FMR | 1 | Basic Access Infrastructure | Road | 0.373 | kms | 1548798.84 | 614285.71 | 2163084.55 | 2012-05-10 |  | 1053183.21 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Dangtalan | 143208009 | Construction of Taang & Lagato Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 24 | ln.m | 640543.43 | 293524.86 | 934068.29 | 2012-04-16 |  | 512434.74 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Pugong | 143208014 | Improvement of Pugong Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 472 | ln.m | 508654.92 | 202937.79 | 711592.71 | 2012-05-21 |  | 406923.94 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Galdang | 143208010 | Improvement of Galdang Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 642 | ln.m | 631670.23 | 248510.95 | 880181.18 | 2012-05-10 |  | 505336.18 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Balinciagao Sur | 143208015 | Improvement of Lytong to Dallog CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation | 15 | has. | 533342.09 | 231115.52 | 764457.61 | 2012-04-19 |  | 421340.25 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Dalupa | 143208008 | Improvement of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 160 | ln.m | 678069.49 | 278626.29 | 956695.78 | 2012-05-07 |  | 542455.59 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Bagtayan | 143208016 | Energization of Barangay Bagtayan | 1 | Basic Social Services | Electrification | 88 | HH | 103081.87 | 1552608.75 | 1655690.62 | 2012-04-16 |  | 57725.85 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Balinciagao Norte | 143208003 | Improvement of Simangan MPP | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 595 | sq.m | 642655.34 | 206981.08 | 849636.42 | 2012-04-02 |  | 514124.27 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Pasil | 143208 | Colayo | 143208007 | Construction of Iking Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 17 | ln.m | 511128.96 | 160616.24 | 671745.2 | 2012-05-07 | 2012-07-15 | 408903.17 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Pinukpuk | 143209 | Cawagayan | 143209012 | Constrution of Canal Lining Drainage | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 140 | ln.m | 339843.32 | 127075.83 | 466919.15 | 2012-05-01 | 2012-05-31 | 271874.66 | 1st | Completed
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Ambato-Legleg | 143215001 | Construction of River Control | 2 | Environmental Protection and Conservation | River Control/Flood Control | 80 | ln.m | 584593.18 | 390531.74 | 975124.92 | 2012-04-01 |  | 292296.59 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Bangad Centro , Lower Bangad & upper Bangad | 143215003, 143215023 ,143215020 | Construction of water system | 1 | Basic Social Services | Water System | 1 | system | 841860.09 | 364978.3 | 1206838.39 | 2012-05-01 |  | 612424 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Basao | 143215004 | Inprovement of Sapid CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 194904.83 | 103971.16 | 298875.99 |  |  | 120840.99 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Belong-Man-ubal | 143215006 | Construction of 1 CL School Building | 2 | Basic Social Services | School |  | sq. m | 786987.33 | 284589.65 | 1071576.98 |  |  | 484100.31 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Bugnay | 143215008 | Improvement of A-oy CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 281395.76 | 139914.14 | 421309.9 | 2012-05-01 |  | 177279.33 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Buscalan | 143215009 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 506.45 | ln.m | 598749.81 | 258864.63 | 857614.44 |  |  | 389187.38 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Butbut Proper | 143215007 | Construction of 1 CL School Building | 1 | Basic Social Services | School |  | sq. m | 651363.1 | 412726.78 | 1064089.88 |  |  | 454283.28 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Dananao | 143215010 | Improvement of Waangan to Foner Footpath | 1 | Basic Access Infrastructure | Access Trail | 0.778 | kms | 353039.24 | 158134.31 | 511173.55 | 2012-05-01 |  | 176519.62 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Loccong | 143215011 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 648045.54 | 340533.02 | 988578.56 |  |  | 414370.54 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Luplupa | 143215012 | Construction of Multi-purpose Building | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 63 | sq.m | 415782.37 | 340533.02 | 756315.39 | 2012-04-01 |  | 291047.66 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Ngibat | 143215021 | Improvement of Silay-Ngibat Foothpath | 1 | Basic Access Infrastructure | Access Trail | 0.915 | kms | 370932.88 | 204047.72 | 574980.6 | 2012-05-01 |  | 237397.04 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Old Tinglayan | 143215022 | Improvement of Futa CIS | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 387941.27 | 167946.59 | 555887.86 |  |  | 256041.24 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Poblacion | 143215014 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 743043.87 | 342011.73 | 1085055.6 |  |  | 445826.32 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Sumadel I | 143215016 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 741044.47 | 564545.82 | 1305590.29 |  |  | 357904.68 | 1st | Not yet started
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Sumadel II | 143215017 | Rehabilitation of Drainage canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 22.36 | ln.m | 199549.5 | 114074.88 | 313624.38 | 2012-05-01 |  | 121725.2 | 1st | On-going
CAR | 14 | Kalinga | 1432 | Tinglayan | 143215 | Tulgao East & West | 143215018 | Improvement of Chotar CIS | 2 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 927146.43 | 340407.98 | 1267554.41 | 2012-04-01 |  | 491387.61 | 1st | Not yet started
[6 empty] | West | 143215019
VIII | 08 | Leyte | 0837 | Bato | 083707 | Domagocdoc | 083707014 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 536327 | 163571 | 699898 | 2012-03-16 |  | 429061.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Mabini | 083707019 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 1187635 | 321784 | 1509419 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Bato | 083707 | Katipunan | 083707017 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.24 | kms | 620473 | 180184 | 800657 | 2012-03-10 |  | 496378 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Alegria | 083707001 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 467241 | 218621 | 685862 | 2012-05-10 |  | 373793 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Naga | 083707020 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.6 | kms | 1076812 | 292810 | 1369622 | 2012-03-03 |  | 861449.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Amagos | 083707003 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.34 | kms | 814955 | 232339 | 1047294 | 2012-04-16 |  | 651964 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Buli | 083707008 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.36 | kms | 813207 | 231452 | 1044659 | 2012-05-10 |  | 650565.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Liberty | 083707018 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.6 | kms | 909979 | 253216 | 1163195 | 2012-04-26 |  | 727983 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Cebuana | 083707009 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.18 | kms | 415774 | 124359 | 540133 | 2012-03-27 | 2012-07-25 | 332619 | 1st | Completed
VIII | 08 | Leyte | 0837 | Bato | 083707 | Alejos | 083707002 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 489369 | 229604 | 718973 | 2012-04-24 |  | 391495 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Dawahon | 083707011 | Construction of Pier | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 160 | ln.m | 3263772 | 1122950 | 4386722 |  |  | 2611017.6 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Bato | 083707 | Plaridel | 083707022 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 479764 | 143646 | 623410 | 2012-03-14 |  | 383811.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Himama-a | 083707012 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 856595 | 243165 | 1099760 | 2012-04-02 |  | 685276 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Tinago | 083707031 | Health Station | 1 | Basic Social Services | Health Station | 48 | sq.m | 510362 | 239527 | 749889 | 2012-04-23 |  | 408290 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Osmena | 083707021 | Improvement of Electric Pump Water Level II | 1 | Basic Social Services | Water System | 1 | system | 360759 | 180887 | 541646 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Bato | 083707 | Guerrero | 083707015 | Construction of 2 Units Communal Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 2 | unit | 506981 | 151626 | 658607 | 2012-05-29 |  | 405585 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Rivilla | 083707035 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.21 | kms | 550647 | 161917 | 712564 | 2012-04-17 |  | 440518 | 1st | On-going
VIII | 08 | Leyte | 0837 | Bato | 083707 | Bago | 083707005 | water System Level II Gravity | 1 | Basic Social Services | Water System | 1 | system | 483839 | 152573 | 636412 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Bato | 083707 | Iniguihan | 083707016 | Construction of Line Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 80 | ln.m | 55509 | 309921 | 365430 | 2012-04-25 | 2012-07-25 | 44407.2 | 1st | Completed
VIII | 08 | Leyte | 0837 | Julita | 083725 | Poblacion Dist. II | 083725019 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 206 | ln.m | 423547 | 112259 | 535806 | 2012-02-23 |  | 338838 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Caridad | 083725009 | Construction of Water Sytem Level II Pump Driven | 1 | Basic Social Services | Water System | 1 | system | 335455 | 104187 | 439642 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Julita | 083725 | Tagkip | 083725026 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 188 | ln.m | 257907 | 74221 | 332128 | 2012-02-10 |  | 206326 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Tolosahay | 083725027 | Construction of 32 Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 32 | unit | 468270 | 127469 | 595739 | 2012-03-12 |  | 374616 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Sta. Cruz | 083725024 | Construction of Covered Draiange Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 365.5 | ln.m | 400564 | 106513 | 507077 | 2012-04-23 |  | 320451 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Dita | 083725013 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 313 | ln.m | 407811 | 108325 | 516136 | 2012-04-02 |  | 326249 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bugho | 083725007 | Construction of Level II water System | 1 | Basic Social Services | Water System | 1 | system | 390574 | 117437 | 508011 |  |  | 312459 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Julita | 083725 | Bonifacio | 083725006 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 42 | unit | 584087 | 157905 | 741992 | 2012-03-01 |  | 467270 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Aslum | 083725003 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 42 | unit | 595768 | 155315 | 751083 | 2012-05-14 |  | 476614 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Gitabla | 083725014 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 28 | unit | 418416 | 112567 | 530983 | 2012-04-18 |  | 334733 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Poblacion District IV | 083725021 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 368.5 | ln.m | 618096 | 174412 | 792508 | 2012-02-19 |  | 494477 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | San Andres | 083725022 | Construction of Covered Draiange Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 448 | ln.m | 617890 | 177379 | 795269 | 2012-03-15 |  | 494312 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Alegria | 083725001 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 30 | unit | 434712 | 118761 | 553473 | 2012-02-28 |  | 347776.96 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Hindang | 083725015 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 648 | ln.m | 554923 | 150191 | 705114 | 2012-02-20 |  | 443938 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Cuya-e | 083725010 | Road Improvement | 1 | Basic Access Infrastructure | Road | 0.975 | kms | 403851 | 111577 | 515428 | 2012-02-23 |  | 323081 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Jurao | 083725017 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 417965 | 121900 | 539865 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Julita | 083725 | Poblacion Dist. III | 083725020 | Construction of 29 Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 29 | unit | 431282 | 114195 | 545477 |  |  | 345026 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Sto. Nino | 083725025 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 31 | unit | 453429 | 123335 | 576764 | 2012-03-29 |  | 362743 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Balante | 083725004 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 531527 | 152885 | 684412 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Julita | 083725 | Calbasag | 083725008 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 313 | ln.m | 470766 | 134557 | 605323 | 2012-02-22 |  | 376613 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Poblacion Dist. I | 083725018 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 150 | ln.m | 358558 | 96013 | 454571 | 2012-03-12 |  | 286846 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Villahermosa | 083725028 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 392.7 | ln.m | 397954 | 107769 | 505723 | 2012-02-13 |  | 318363 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | San Pablo | 083725023 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 556932 | 155679 | 712611 | 2012-03-05 |  | 445546 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Anibong | 083725002 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 533 | ln.m | 562298 | 153307 | 715605 | 2012-02-15 |  | 449838 | 1st | On-going
VIII | 08 | Leyte | 0837 | Julita | 083725 | Inawangan | 083725016 | Constuction of 3 Barrels Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 607418 | 214424 | 821842 | 2012-05-01 |  | 485934 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone III | 083735011 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.558 | kms | 729872 | 185844 | 915716 | 2012-03-26 |  | 583897.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Sta. Cruz | 083735013 | Construction of Concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.62 | kms | 811737 | 206310 | 1018047 | 2012-02-28 |  | 649389.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone II | 083735010 | Conreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.356 | kms | 480832 | 123582 | 604414 | 2012-02-27 |  | 384665.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Ormocay | 083735008 | Construction of lined ditch | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 145 | ln.m | 405029 | 106032 | 511061 | 2012-03-03 |  | 324023.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Union | 083735015 | Construction of Concrete Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 10 | ln.m | 245205 | 62801 | 308006 | 2012-05-21 |  | 196164 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Talisay | 083735014 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.437 | kms | 632764 | 161558 | 794322 | 2012-03-05 |  | 506211.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Camansi | 083735005 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.437 | kms | 580465 | 148500 | 728965 | 2012-04-16 |  | 464372 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Calipayan | 083735004 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 587821 | 153070 | 740891 | 2012-02-27 |  | 470256.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Gen. A. Luna | 083735006 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 205 | ln.m | 356820 | 93480 | 450300 | 2012-03-26 | 2012-06-30 | 285456 | 1st | Completed
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Burgos | 083735003 | Concerting of patwalk | 1 | Basic Access Infrastructure | Access Trail | 0.31 | kms | 428235 | 110434 | 538669 |  |  | 342588 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Mabini | 083735002 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.35 | kms | 477317 | 122705 | 600022 | 2012-03-23 |  | 381853.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Poblacion Zone I | 083735009 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.446 | kms | 591456 | 153360 | 744816 | 2012-02-27 |  | 473164.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Liberty | 083735007 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 596301 | 152443 | 748744 | 2012-04-19 |  | 477040.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mayorga | 083735 | Wilson | 083735016 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.421 | kms | 254308 | 450828 | 705136 | 2012-04-11 |  | 220916.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Kananga | 083726 | San Ignacio | 083726017 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 865998 | 245378 | 1111376 | 2012-03-19 | 2012-06-30 | 692798.4 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | San Isidro | 083726018 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.208 | kms | 901399 | 256235 | 1157634 | 2012-02-29 | 2012-06-30 | 721119 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Mahawan | 083726009 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 865998 | 245378 | 1111376 | 2012-04-17 | 2012-06-30 | 692798 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Sto. Domingo | 083726019 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.21 | kms | 795488 | 226657 | 1022145 | 2012-03-01 | 2012-05-30 | 636390 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Libertad | 083726005 | Improvement of wate System Level II | 1 | Basic Social Services | Water System | 1 | system | 982966 | 286331 | 1269297 | 2012-05-28 |  | 688076.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Masarayao | 083726010 | Concreting of tire Path | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 730690 | 206767 | 937457 | 2012-05-05 | 2012-07-15 | 584552 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Kawayan | 083726003 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 538277 | 160384 | 698661 | 2012-04-18 | 2012-07-15 | 430621.6 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Tagaytay | 083726021 | 18 M Steel Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 18 | ln.m | 500419 | 180772 | 681191 | 2012-06-11 |  | 400335.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Sto. Nino | 083726020 | Hanging Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 25 | ln.m | 1250408 | 448241 | 1698649 | 2012-04-30 |  | 1000326.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Montealegre | 083726011 | Concreting of tire path | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 798530 | 226327 | 1024857 | 2012-04-25 |  | 638824 | 1st | On-going
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Aguiting | 083726001 | 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1001237 | 290769 | 1292006 | 2012-02-20 | 2012-07-15 | 800989.6 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Cacao | 083726002 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.232 | kms | 408001 | 135685 | 543686 | 2012-02-27 | 2012-06-30 | 326400.8 | 1st | Completed
VIII | 08 | Leyte | 0837 | Kananga | 083726 | Montebello | 083726012 | CHB Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 337 | ln.m | 710589 | 277581 | 988170 | 2012-04-17 | 2012-07-15 | 568471 | 1st | Completed
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Pinamono-an | 083731016 | Construction of FMR | 1 | Basic Access Infrastructure | Road | 0.134 | kms | 349192 | 87466 | 436658 | 2012-03-01 |  | 314272.8 | 2nd | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Malinao | 083731012 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 587152 | 146875 | 734027 | 2012-02-09 |  | 469721.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Campin | 083731001 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 555741 | 138971 | 694712 | 2012-03-13 |  | 444592.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Polahongon | 083731018 | Construction of Wate System Level II | 1 | Basic Social Services | Water System | 1 | system | 503503 | 125876 | 629379 |  |  | 402802.4 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Himamara | 083731004 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 599885 | 149975 | 749860 | 2012-02-20 |  | 479908 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Palanogan | 083731014 | Construction of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 666214 | 166553 | 832767 | 2012-02-20 | 2012-03-30 | 532971.2 | 1st | Completed
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mabunga | 083731008 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 38 | ln.m | 337394 | 84683 | 422077 | 2012-03-16 |  | 269915.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | San Juan | 083731020 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.22 | kms | 422250 | 105861 | 528111 | 2012-05-10 |  | 337800 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Union | 083731024 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.25 | kms | 583065 | 147245 | 730310 | 2012-04-30 |  | 466452 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Malipo-on | 083731013 | Construction of farm to market road | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 317975 | 79824 | 397799 | 2012-05-04 |  | 254380 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Hinagumuitan | 083731005 | 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 558922 | 139935 | 698857 | 2012-05-09 |  | 447137.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Sta. Cruz | 083731021 | Improvement of farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.6 | kms | 366605 | 91734 | 458339 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Liberacion | 083731006 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 533570 | 133514 | 667084 | 2012-05-14 |  | 426856 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Sto. Nino | 083731028 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.15 | kms | 402933 | 100733 | 503666 | 2012-03-15 |  | 322346.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Paril | 083731015 | Construction of 34 units Street lights | 1 | Basic Social Services | Electrification |  | HH | 303606 | 75902 | 379508 | 2012-05-02 |  | 242884.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Poblacion | 083731017 | Construction of 1 CL Pre- Elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 558883 | 141085 | 699968 | 2012-02-08 |  | 447106.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | San Isidro | 083731019 | Rehab. Of water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1101084 | 275320 | 1376404 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Tagaytay | 083731022 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 566401 | 141600 | 708001 |  |  | 453120.8 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mabuhay | 083731007 | Pathway Concreting | 1 | Basic Access Infrastructure | Access Trail | 0.27 | kms | 258381 | 66456 | 324837 | 2012-03-07 |  | 206704.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Cuatro de Agosto | 083731002 | Expansion of water System Level II | 1 | Basic Social Services | Water System | 1 | system | 457775 | 114444 | 572219 |  |  | 366200 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mahayhay | 083731011 | Improvement of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 475551 | 118888 | 594439 |  |  | 380440.8 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Upper | 083731025 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.1267 | kms | 278633 | 74293 | 352926 | 2012-05-01 |  | 222906.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Hilusig | 083731003 | Construction of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 549092 | 137401 | 686493 | 2012-03-19 |  | 439273.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Mahayag | 083731010 | Construction of 1 CL elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 555691 | 139521 | 695212 | 2012-02-27 |  | 444552.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Mahaplag | 083731 | Hiluctugan | 083731026 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 595970 | 149001 | 744971 | 2012-02-14 |  | 476776 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Abuyogay | 083724001 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 1029703 | 412279 | 1441982 | 2012-02-23 |  | 823762.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Calzada | 083724005 | Cobnstruction of 1 Unit elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 488693 | 210847 | 699540 | 2012-03-05 |  | 390954.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Ulhay | 083724029 | Construction of Single Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 7 | ln.m | 582520 | 249305 | 831825 | 2012-02-29 |  | 466016 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Caraye | 083724008 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 511351 | 219011 | 730362 | 2012-03-07 |  | 409080.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Manarug | 083724016 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 326 | ln.m | 526249 | 226895 | 753144 | 2012-02-22 |  | 420992.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Poblacion Zone I | 083724022 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 734605 | 318575 | 1053180 | 2012-03-12 |  | 587684 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Poblacion Zone II | 083724023 | Construction of Level I water System | 1 | Basic Social Services | Water System | 1 | system | 392526 | 168193 | 560719 | 2012-03-09 |  | 314020.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Sta. Cruz | 083724026 | Construction of Level I Water System | 1 | Basic Social Services | Water System | 1 | system | 392436 | 168283 | 560719 | 2012-03-03 |  | 313948.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Casulongan | 083724009 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 526959 | 222913 | 749872 | 2012-03-03 |  | 421507.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Inayupan | 083724012 | Construction of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.671 | kms | 591547 | 249059 | 840606 | 2012-03-01 | 2012-06-30 | 473237.6 | 1st | Completed
VIII | 08 | Leyte | 0837 | Javier | 083724 | Laray | 083724013 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 524898 | 224974 | 749872 | 2012-02-28 |  | 419918.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Magsaysay | 083724014 | Construction of Water Level II Gravity Driven | 1 | Basic Social Services | Water System | 1 | system | 408752 | 187111 | 595863 |  |  | 327001.6 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Javier | 083724 | Manlilisid | 083724017 | Construction of Covered Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 275 | ln.m | 537127 | 227214 | 764341 | 2012-02-28 | 2012-05-30 | 429701.6 | 1st | Completed
VIII | 08 | Leyte | 0837 | Javier | 083724 | Odiong | 083724019 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.5 | kms | 567501 | 227880 | 795381 | 2012-05-15 |  | 454000.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Batug | 083724003 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 496693 | 202847 | 699540 | 2012-03-21 |  | 397354.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Comatin | 083724010 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.436 | kms | 495159 | 212217 | 707376 | 2012-02-20 |  | 396127.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | Javier | 083724 | Malitbogay | 083724015 | Construction of Ricemill | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | sq.m | 844665 | 333589 | 1178254 |  |  | 675732 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Javier | 083724 | Binulho | 083724004 | Construction of Level II Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 976241 | 418343 | 1394584 |  |  | 780992.8 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Javier | 083724 | San Sotero | 083724028 | Construction of Level II Water System Gravity Driven | 1 | Basic Social Services | Water System | 1 | system | 1121837 | 490383 | 1612220 |  |  | 897469.6 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Javier | 083724 | Caranhug | 083724007 | Construction of Open Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 628 | ln.m | 850538 | 542193 | 1392731 |  |  | 680430.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Pansud | 083728022 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 719693 | 212210 | 931903 | 2012-02-01 |  | 575754.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Poblacion Dist. II | 083728026 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 572598 | 176820 | 749418 | 2012-02-16 |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Caabangan | 083728006 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail |  | kms | 294924 | 95987 | 390911 | 2012-06-04 | 2012-07-25 | 235939.2 | 1st | Completed
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Gimiranat West | 083728016 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 340 | ln.m | 473470 | 159648 | 633118 | 2012-04-10 |  | 378776 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Moroboro | 083728021 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 528 | ln.m | 705984 | 293902 | 999886 | 2012-03-26 |  | 564787.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Pawa | 083728023 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 583057 | 166003 | 749060 | 2012-03-23 |  | 524751.3 | 2nd | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Lubi-Lubi | 083728018 | Water System Level II Gravity Fed | 1 | Basic Social Services | Water System | 1 | system | 132321 | 43776 | 176097 | 2012-02-13 |  | 105856.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Duyog | 083728014 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control |  | ln.m | 239236 | 77961 | 317197 |  |  | 191388.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Caltayan | 083728011 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 350 | ln.m | 472892 | 150447 | 623339 | 2012-03-05 |  | 378313.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Quiong | 083728029 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 574445 | 175256 | 749701 | 2012-03-15 |  | 459556 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Sta. Ana | 083728032 | Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 350 | ln.m | 493191 | 153842 | 647033 | 2012-03-20 |  | 394552.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Bagacay West | 083728002 | Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 688809 | 203156 | 891965 | 2012-03-15 |  | 551047.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Bagacay East | 083728001 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.4 | kms | 635195 | 200152 | 835347 | 2012-03-12 |  | 508156 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Gimiranat East | 083728015 | Construction of box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 11 | ln.m | 132873 | 50516 | 183389 |  |  | 106298.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Tabang | 083728034 | Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.15 | kms | 538736 | 157564 | 696300 |  |  | 430988.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Limba | 083728017 | Concrete Tire Path | 1 | Basic Access Infrastructure | Road | 0.29 | kms | 455015 | 143639 | 598654 | 2012-03-05 |  | 409513.5 | 2nd | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Cagngaran | 083728008 | Improvement of farm to market Road | 1 | Basic Access Infrastructure | Road | 0.86 | kms | 433857 | 121556 | 555413 | 2012-03-14 |  | 347085.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Calabni-an | 083728009 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 1017446 | 639738 | 1657184 |  |  | 610467.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Canbanez | 083728012 | Street Lights | 1 | Basic Social Services | Electrification |  | HH | 222181 | 63798 | 285979 | 2012-03-05 |  | 177744.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Sta. Elena | 083728033 | Improvement of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 220096 | 65396 | 285492 | 2012-03-13 |  | 176076 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Cogon | 083728013 | Improvement of 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 316891 | 97011 | 413902 | 2012-03-05 |  | 253512.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Bongtod | 083728003 | Construction of Tirepath | 1 | Basic Access Infrastructure | Road | 0.235 | kms | 413793 | 131023 | 544816 |  |  | 331034 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Calaghusan | 083728010 | Construction of Gravity Fed Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 597768 | 196838 | 794606 | 2012-03-12 |  | 478214.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Rizal | 083728030 | Construction of Level I Water System | 1 | Basic Social Services | Water System | 1 | system | 183826 | 69439 | 253265 | 2012-03-22 | 2012-05-30 | 147060.8 | 1st | Completed
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Bocawon | 083728004 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 491012 | 148688 | 639700 |  |  | 392810 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Poblacion District 3 | 083728027 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 408 | ln.m | 418384 | 132345 | 550729 | 2012-02-27 |  | 376545 | 2nd | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Cacao | 083728007 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 577600 | 172249 | 749849 | 2012-03-25 |  | 519840 | 2nd | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Buracan | 083728005 | Construction of Level I Water System | 1 | Basic Social Services | Water System | 1 | system | 186827 | 66769 | 253596 | 2012-03-29 | 2012-06-30 | 149461.6 | 1st | Completed
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Luneta | 083728019 | Construction of Gravity Fed Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1466236 | 437253 | 1903489 | 2012-02-18 |  | 1172988.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | La Paz | 083728 | Mag-aso | 083728020 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 532256 | 169836 | 702092 | 2012-02-18 |  | 425804.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Mac Arthur District 4 | 083746016 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 500 | ln.m | 568455 | 190460 | 758915 | 2012-02-28 |  | 454764 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Mercaduhay | 083746009 | Construction of River Erosion Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | 100 | ln.m | 1785024 | 559730 | 2344754 |  |  | 1428019.2 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Bonifacio District 3 | 083746015 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 514242 | 187484 | 701726 | 2012-03-08 |  | 411393.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Quezon District 1 | 083746013 | Construction of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.265 | kms | 545324 | 164898 | 710222 | 2012-02-20 | 2012-05-30 | 436259.2 | 1st | Completed
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Jiabong | 083746008 | Rehab of farm to market road | 1 | Basic Access Infrastructure | Road | 0.59 | kms | 523447 | 154848 | 678295 | 2012-02-24 |  | 425957.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Cambucao | 083746005 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 180608 | 60040 | 240648 | 2012-01-25 | 2012-03-30 | 144486.4 | 1st | Completed
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Guingauan | 083746007 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 553236 | 172152 | 725388 | 2012-05-16 |  | 442588.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Belisong | 083746004 | 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 538748 | 165180 | 703928 | 2012-02-20 |  | 430998.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Capahuan | 083746006 | Construction of 1 Unit 2CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 906020 | 301029 | 1207049 | 2012-02-09 |  | 724816 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Aslum | 083746002 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 260 | ln.m | 294903 | 96306 | 391209 | 2012-01-26 | 2012-04-30 | 235992.4 | 1st | Completed
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Balingasag | 083746003 | Rehab of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.767 | kms | 467006 | 133713 | 600719 | 2012-03-08 |  | 373604.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | TabonTabon | 083746 | Rizal District 2 | 083746014 | Pre-Post Harvest Facility with Structure | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | sq.m | 289192 | 98213 | 387405 | 2012-02-28 |  | 231353.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Capinahan | 083742009 | Concreting of of Farm to market road | 1 | Basic Access Infrastructure | Road | 0.14 | kms | 625380 | 201299 | 826679 | 2012-05-19 |  | 500304 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Crossing | 083742010 | Constrution of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 339804 | 113392 | 453196 | 2012-04-30 |  | 271843.2 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Banat-I | 083742001 | Rehabilitation of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.2 | kms | 399880 | 143570 | 543450 | 2012-05-29 |  | 319904 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Tinago | 083742020 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.071 | kms | 364972 | 119523 | 484495 | 2012-05-09 |  | 292777.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | San Miguel | 083742022 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.09 | kms | 428160 | 142675 | 570835 | 2012-05-30 |  | 342528 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Busay | 083742021 | Electrification | 1 | Basic Social Services | Electrification | 483 | HH | 572700 | 172475 | 745175 |  |  | 458160 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Daja-diot | 083742012 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.125 | kms | 595992 | 188195 | 784187 | 2012-05-23 |  | 476793.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Bawod | 083742004 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.13 | kms | 368680 | 125662 | 494342 | 2012-05-09 |  | 294944 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Paril | 083742017 | Electrification | 1 | Basic Social Services | Electrification | 314 | HH | 448199.2 | 136049.8 | 584249 |  |  | 358559.36 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Daja-daku | 083742011 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 562900 | 172093 | 734993 | 2012-05-09 |  | 450320 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Biasong | 083742005 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 513008 | 161329 | 674337 | 2012-05-09 | 2012-07-25 | 410406.4 | 1st | Completed
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Banucan | 083742006 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.076 | kms | 386932 | 126893 | 513825 | 2012-05-22 |  | 309545.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Matungao | 083742015 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 573168.8 | 173709.2 | 746878 | 2012-04-24 |  | 458535.04 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Linao | 083742014 | Construction of footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 18 | ln.m | 294640 | 96955 | 391595 | 2012-05-24 |  | 235712 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Cabunga-an | 083742008 | Concreting of farm to market road | 1 | Basic Access Infrastructure | Road | 0.075 | kms | 386340 | 125778 | 512118 | 2012-05-16 |  | 309072 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Hacienda Maria | 083742013 | Construction of footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 16 | ln.m | 258340 | 86484 | 344824 |  |  | 206672 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | San Jose | 083742018 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.098 | kms | 462080 | 147840 | 609920 | 2012-05-10 |  | 369664 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Taglawigan | 083742019 | Construction of 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 573168.8 | 173709.2 | 746878 | 2012-05-07 |  | 458535.04 | 1st | On-going
VIII | 08 | Leyte | 0837 | San Isidro | 083742 | Basud | 083742003 | Construction of Public Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) |  | sq.m | 394588.6 | 207851.4 | 602440 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Culasi | 083729009 | Rehabilitation of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.791 | kms | 1374160 | 343540 | 1717700 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Bachao | 083729001 | Road Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.44 | kms | 2127840 | 531960 | 2659800 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Maanda | 083729014 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.28 | kms | 2170240 | 542560 | 2712800 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Tapol | 083729025 | Construction of Concrete Tirepath | 1 | Basic Access Infrastructure | Road | 1 | kms | 1563600 | 390900 | 1954500 |  |  | 1250880 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Mataloto | 083729016 | Construction of 1 Unit 3CL Elem. School Building | 1 | Basic Social Services | School | 189 | sq. m | 1697280 | 424320 | 2121600 |  |  | 1357824 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Ugbon | 083729029 | Construction of School Building | 1 | Basic Social Services | School | 63 | sq. m | 599760 | 149940 | 749700 | 2012-04-12 |  | 479808 | 1st | On-going
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Parasan | 083729020 | Construction of 1.2 Km Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.2 | kms | 2581440 | 645360 | 3226800 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Leyte | 083729 | Toctoc | 083729028 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 300 | ln.m | 1057100 | 1037100 | 2094200 |  |  | 0 |  | Not yet started
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Butason 1 | 083745002 | Construction of Concrete tire Path | 1 | Basic Access Infrastructure | Road | 0.24 | kms | 482755 | 177490 | 660245 |  |  | 386204 | 1st | On-going
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Gibacungan | 083745007 | Improvement of Gravity Fed Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 493321 | 176323 | 669644 | 2012-05-08 | 2012-06-30 | 0 |  | Completed
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Tugas | 083745014 | Concreting of tire Path | 1 | Basic Access Infrastructure | Road | 0.28 | kms | 482727 | 181727 | 664454 | 2012-05-08 | 2012-07-15 | 386181.6 | 1st | Completed
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Butason II | 083745003 | Construction of concrete tirepath | 1 | Basic Access Infrastructure | Road | 0.23 | kms | 519122 | 166540 | 685662 |  |  | 415297.6 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Inangatan | 083745008 | Construction of Concrete tirepath | 1 | Basic Access Infrastructure | Road | 0.45 | kms | 836959 | 264580 | 1101539 | 2012-05-10 |  | 502175.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Manlawaan | 083745009 | Construction of 1 Cl Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 511473 | 169438 | 680911 | 2012-05-10 |  | 409178.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Gimarco | 083745006 | Construction of health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 565137 | 184863 | 750000 | 2012-05-07 |  | 452109.6 | 1st | On-going
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Omaganhan | 083745010 | Construction of Single Barrel Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 226896 | 158583 | 385479 |  |  | 181516.8 | 1st | On-going
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Sta. Rosa | 083745012 | Construction of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.17 | kms | 281129 | 99012 | 380141 | 2012-05-15 | 2012-07-15 | 224903.2 | 1st | Completed
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Catmon | 083745005 | Construction of Concrete Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 16 | ln.m | 382849 | 147100 | 529949 |  |  | 306279.2 | 1st | Not yet started
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Tabing | 083745013 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 488 | ln.m | 617008 | 198922 | 815930 |  |  | 493606.4 | 1st | On-going
VIII | 08 | Leyte | 0837 | Tabango | 083745 | Campokpok | 083745004 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.45 | kms | 369537 | 248889 | 618426 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bagacay | 174002001 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1199137.6 | 210482.4 | 1409620 |  |  | 948752.48 | 1st | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Timbo | 174002012 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.249 | kms | 1064052.4 | 200402.6 | 1264455 |  |  | 851241.92 | 1st | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Caigangan | 174002004 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 1107303.2 | 236596.8 | 1343900 | 2012-06-10 |  | 883818.56 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bagtingon | 174002002 | Construction of 1 CL high School Building | 1 | Basic Social Services | School | 63 | sq. m | 571481.02 | 124146.26 | 695627.28 | 2012-05-17 |  | 457184.81 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Libas | 174002006 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 1237545.2 | 293454.8 | 1531000 |  |  | 990036.16 | 1st | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Yook | 174002014 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 1166953.32 | 252218.58 | 1419171.9 |  |  | 933573.6 | 1st | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Dos | 174002016 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall |  | ln.m | 977332.83 | 195466.57 | 1172799.4 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Sihi | 174002011 | Construction of Water System | 1 | Basic Social Services | Water System | 1 | system | 403518.8 | 83484.45 | 487003.25 |  |  | 269220.46 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Bicas-bicas | 174002003 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road |  | kms | 976256.18 | 195251.24 | 1171507.42 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Daykitin | 174002005 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 1028227.1 | 205645.42 | 1233872.52 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Buenavista | 174002 | Tungib-Lipata | 174002013 | Imorovement of Farm to Market Road | 1 | Basic Access Infrastructure | Road |  | kms | 1126151.13 | 225230.23 | 1351381.36 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Bolo | 174006003 | Construction of 2 barrel box culvert | 1 | Basic Access Infrastructure | Foot/Small Bridges | 6.9 | ln.m | 729168.5 | 324833.5 | 1054002 | 2012-07-24 |  | 582134.8 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Matuyatuya | 174006016 | Improvement of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2352310 | 554690 | 2907000 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Pakaskasan | 174006018 | Road Rehab with with Concreting | 1 | Basic Access Infrastructure | Road | 1.4 | kms | 1140253.6 | 412746.4 | 1553000 |  |  | 912202.88 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Mabuhay | 174006010 | Construction of 5 units shallow well with jetmatic pump | 1 | Basic Social Services | Water System | 1 | system | 406160 | 93840 | 500000 |  |  | 324928 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Bonliw | 174006004 | Improvmeent of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1876125 | 438875 | 2315000 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Bayakbakin | 174006002 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 610314 | 138336 | 748650 | 2012-06-09 |  | 488251.2 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Payanas | 174006019 | Road Rehabilitation with Road Concreting | 1 | Basic Access Infrastructure | Road | 1.002 | kms | 1203680.8 | 423319.2 | 1627000 |  |  | 0 |  | Not yet started
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Suha | 174006023 | Construction of of pathway | 1 | Basic Access Infrastructure | Access Trail | 0.237 | kms | 236865 | 55135 | 292000 | 2012-07-17 |  | 189492 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Sibuyao | 174006022 | Improvement of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 851710 | 188290 | 1040000 | 2012-07-25 |  | 681368 | 1st | On-going
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Bangwayin | 174006001 | Road Rehabilitaion with Concreting on Critical Slope | 1 | Basic Access Infrastructure | Road | 0.615 | kms | 1191986.4 | 452013.6 | 1644000 |  |  | 953589.12 | 1st | Not yet started
IV-B | 17 | Marinduque | 1740 | Torrijos | 174006 | Marlanga | 174006015 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 648994 | 148006 | 797000 | 2012-06-04 |  | 519195.2 | 1st | On-going
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Besao East | 144403004 | Rehabilitation of Bekes-Besao Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 361 | ln.m | 369513.4 | 169736.02 | 539249.42 | 2012-02-14 | 2012-05-30 | 295610.72 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Kiniway | 144403015 | Improvement of Kiniway Village Water System | 1 | Basic Social Services | Water System | 1 | system | 527346.85 | 278369.15 | 805716 | 2012-03-30 | 2012-06-30 | 421877.48 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Padangaan | 144403011 | Improvement of Lebkan Pathway and Erosion Control | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 20 | ln.m | 379218.38 | 168013.62 | 547232 | 2012-02-08 | 2012-06-30 | 303374.7 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Laylaya | 144403010 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 746945.09 | 308717.91 | 1055663 | 2012-02-25 | 2012-06-30 | 507745.88 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Lacmaan | 144403009 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 719307.04 | 294692.96 | 1014000 | 2012-02-06 | 2012-06-30 | 521845.94 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Payeo | 144403012 | Improvement of Kuminga-Sasaan Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 358.69 | ln.m | 686847.11 | 284127.34 | 970974.45 | 2012-02-10 | 2012-06-30 | 549477.69 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Besao West | 144403005 | Rehabilitation of Bekes- lalalayan-Sikog Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 184.69 | ln.m | 337250.99 | 178321.75 | 515572.74 | 2012-02-15 | 2012-05-30 | 269800.79 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Ambaguio | 144403002 | Construction of Sledge Trail | 1 | Basic Access Infrastructure | Access Trail | 4.126 | kms | 641126 | 262458.44 | 903584.44 | 2012-02-09 | 2012-06-30 | 512900.8 | 1st | On-going
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Tamboan | 144403014 | Improvement of water System | 1 | Basic Social Services | Water System | 1 | system | 383028.8 | 185324.2 | 568353 | 2012-03-05 | 2012-06-30 | 306423.04 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Suquib | 144403013 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 725242.54 | 303257.46 | 1028500 | 2012-02-07 | 2012-06-30 | 519272.48 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Catengan | 144403006 | Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 459 | ln.m | 592960.42 | 259023.58 | 851984 | 2012-03-05 | 2012-06-30 | 474368.34 | 1st | Completed
CAR | 14 | Mountain Province | 1444 | Besao | 144403 | Agawa | 144403001 | Improvement of Eg-ew Communal Irrigation System 295 Lm line Canal | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 191213.38 | 250908.36 | 442121.74 | 2012-02-20 | 2012-06-30 | 152970.7 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Gen. Emilio Aguinaldo | 175109005 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 755000 | 151000 | 906000 | 2012-03-19 | 2012-06-30 | 604000 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Victoria | 175109021 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 700000 | 175000 | 875000 | 2012-03-30 | 2012-05-30 | 560000 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Paetan | 175109010 | Road Construction with 3 barrel box culvert | 1 | Basic Access Infrastructure | Road | 0.414 | kms | 2411200 | 602800 | 3014000 | 2012-03-13 | 2012-05-30 | 1928960 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Agustin | 175109013 | Improvement of Access Road | 1 | Basic Access Infrastructure | Road | 1.2 | kms | 1826667 | 365333 | 2192000 | 2012-03-13 | 2012-06-30 | 1465713 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Batong Buhay | 175109001 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.28 | kms | 2123200 | 530800 | 2654000 | 2012-03-14 | 2012-06-30 | 1698560 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Nicolas | 175109016 | Construction of Multi Purpose Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | sq.m | 700000 | 175000 | 875000 | 2012-03-19 | 2012-05-30 | 560000 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | Pag-asa | 175109011 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 729600 | 182400 | 912000 | 2012-03-20 | 2012-05-30 | 583680 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sablayan | 175109 | San Francisco | 175109014 | Concreting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 700000 | 175000 | 875000 | 2012-03-28 | 2012-06-30 | 523466.4 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Poblacion 1 | 175111009 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 60 | ln.m | 587563.33 | 1354436.67 | 1942000 | 2012-05-18 |  | 469758.16 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | San Vicente | 175111010 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 500816.67 | 357183.33 | 858000 | 2012-05-10 |  | 400653.34 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Kurtingan | 175111012 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 513225.53 | 346774.47 | 860000 | 2012-05-24 |  | 410244.42 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Alacaak | 175111001 | Installation of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 326833.33 | 587166.67 | 914000 | 2012-05-16 |  | 261466.66 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Casague | 175111003 | Concrete Lining of Irigation Canal | 1 | Community Production, Economic Support and Common Service Facility | Small Scale Irrigation |  | has. | 498333.33 | 429666.67 | 928000 | 2012-05-26 |  | 398666.66 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Dayap | 175111004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 308348.58 | 333651.42 | 642000 | 2012-05-28 |  | 246678.86 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Pinagturilan | 175111008 | Construction of 1 Unit 2 CL School Building | 1 | Basic Social Services | School | 126 | sq. m | 673333.33 | 553666.67 | 1227000 | 2012-06-05 |  | 510958.95 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Lumangbayan | 175111006 | Construction of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 636666.67 | 644333.33 | 1281000 |  |  | 509333.34 | 1st | On-going
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Poblacion II | 175111011 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 589091.67 | 169508.33 | 758600 | 2012-05-16 | 2012-07-15 | 471273.34 | 1st | Completed
IV-B | 17 | Occidental Mindoro | 1751 | Sta. Cruz | 175111 | Mulawin | 175111007 | Construction of Training Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 228 | sq.m | 315787.56 | 561212.44 | 877000 | 2012-05-24 |  | 252630.05 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Ipil | 175203036 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 973 | ln.m | 2744080.26 | 755919.74 | 3500000 |  |  | 2195264.2 | 1st | Not yet started
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Hagupit | 175203010 | Construction of Multi Purpose Pavement with Slope Protection | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 126 | sq.m | 782930.59 | 179219.41 | 962150 | 2012-05-05 | 2012-06-30 | 582228.99 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Malitbog | 175203017 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 3375659.24 | 914340.76 | 4290000 |  |  | 0 |  | Not yet started
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Batangan | 175203002 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.435 | kms | 1403381.23 | 479618.77 | 1883000 | 2012-04-19 | 2012-07-15 | 1078529.98 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Lisap | 175203015 | Rehabilitation of Bailey Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges |  | ln.m | 1803428.69 | 466571.31 | 2270000 |  |  | 1413002.93 | 1st | Not yet started
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Formon | 175203008 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1640281.08 | 627719 | 2268000.08 | 2012-04-30 | 2012-06-30 | 1312224.86 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Mina de Oro | 175203037 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 1.4 | kms | 1598262.49 | 601115.51 | 2199378 | 2012-05-08 | 2012-06-30 | 1278609.99 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Libertad | 175203014 | Construction of Heath Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 590328.6 | 207672 | 798000.6 | 2012-04-19 | 2012-06-30 | 472262.88 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Sta. Cruz | 175203028 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 509728.4 | 290271.6 | 800000 | 2012-04-18 | 2012-06-30 | 407782.72 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | San Jose | 175203026 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 584273.47 | 215726.53 | 800000 | 2012-04-09 | 2012-06-30 | 467418.78 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Masaguisi | 175203019 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 586734.6 | 213265.4 | 800000 | 2012-04-16 | 2012-06-30 | 469387.68 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bongabong | 175203 | Luna | 175203016 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 580911.35 | 217373.65 | 798285 | 2012-04-19 | 2012-07-15 | 464729.08 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Bagong Sikat | 175204001 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 450000 | 180000 | 630000 | 2012-05-04 |  | 360000 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Balatasan | 175204002 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 456881.2 | 183118.8 | 640000 | 2012-04-30 | 2012-07-15 | 365504.96 | 1st | Completed
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Benli | 175204003 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 444132.4 | 235867.6 | 680000 | 2012-05-11 |  | 355305.92 | 1st | Not yet started
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Cabugao | 175204005 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 448001.2 | 191998.8 | 640000 | 2012-05-02 |  | 358400.96 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Cambunang | 175204006 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 450000 | 180000 | 630000 | 2012-05-04 |  | 360000 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Campaasan | 175204007 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 429802.8 | 195197.2 | 625000 | 2012-04-23 |  | 343842.24 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Maasin | 175204008 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 460561.8 | 199438.2 | 660000 | 2012-05-04 |  | 368450.24 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Maujao | 175204009 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 450000 | 180000 | 630000 | 2012-05-04 |  | 360000 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Milagrosa | 175204010 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 453624.8 | 181375.2 | 635000 | 2012-05-07 |  | 362899.84 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Nasucob | 175204011 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 450000 | 180000 | 630000 | 2012-05-04 |  | 360000 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | Poblacion | 175204012 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 450562.8 | 179437.2 | 630000 | 2012-05-04 |  | 360450.24 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | San Francisco | 175204013 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 453624.8 | 181375.2 | 635000 | 2012-05-03 |  | 362899.84 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | San Isidro | 175204014 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 461201.2 | 178798.8 | 640000 | 2012-04-30 |  | 368960.96 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | San Juan | 175204015 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 444132.4 | 175867.6 | 620000 | 2012-04-24 |  | 355305.92 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Bulalacao | 175204 | San Roque | 175204017 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 444132.4 | 175867.6 | 620000 | 2012-05-04 |  | 355305.92 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Manaul | 175207011 | Construction of 1 unit 2 CL elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1145365.87 | 304634.13 | 1450000 |  |  | 902479.71 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Waygan | 175207021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 625510.27 | 172489.73 | 798000 |  |  | 490756.66 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Sta. Brigida | 175207016 | Improvement of Farm to market road | 1 | Basic Access Infrastructure | Road | 0.42 | kms | 1461319.47 | 350180.53 | 1811500 |  |  | 1127392.38 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Teresita | 175207020 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 1187061.97 | 322938.03 | 1510000 |  |  | 949649.58 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Maliwanag | 175207010 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 1261159.47 | 308840.53 | 1570000 |  |  | 983317.34 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Bonbon | 175207003 | Construction of 1 Unit 2 CL High School Building | 1 | Basic Social Services | School | 126 | sq. m | 1162139.87 | 287860.13 | 1450000 |  |  | 915898.92 | 1st | On-going
IV-B | 17 | Oriental Mindoro | 1752 | Mansalay | 175207 | Budburan | 175207004 | Construction of Slope Protection and Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 136 | ln.m | 620653.47 | 164846.53 | 785500 |  |  | 477921.47 | 1st | On-going
IV-B | 17 | Palawan | 1753 | Linapacan | 175313 | Pical | 175313009 | Improvement of water system level II | 1 | Basic Social Services | Water System | 1 | system | 1524553.33 | 335447 | 1860000.33 |  |  | 0 |  | Not yet started
IV-B | 17 | Palawan | 1753 | Linapacan | 175313 | Decaibaitot | 175313004 | Concreting on Critical Section 380 ln.m with line ditch and Slope Protection | 1 | Basic Access Infrastructure | Road | 0.38 | kms | 1712686.67 | 462313.33 | 2175000 |  |  | 1370149.34 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Linapacan | 175313 | San Nicholas | 175313011 | Concreting of farm to market Road 235 ln.m with 2 Units RCDG | 1 | Basic Access Infrastructure | Road | 0.235 | kms | 1262760 | 424240 | 1687000 |  |  | 1010208 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Linapacan | 175313 | Pical | 175313009 | Improvement of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1524553.33 | 335446.67 | 1860000 |  |  | 0 |  | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Bohol | 175311002 | Construction of 6 Units Rain Water Tank Collector | 1 | Basic Social Services | Water System | 1 | system | 1285689.16 | 414310.84 | 1700000 |  |  | 0 |  | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Calasag | 175311003 | Construction of 2 Units Rain Water Tank Collector | 1 | Basic Social Services | Water System | 1 | system | 451050 | 128950 | 580000 |  |  | 360840 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Itangil | 175311009 | Construction of level II Water Supply System | 1 | Basic Social Services | Water System | 1 | system | 1065829.16 | 291170.84 | 1357000 |  |  | 871163.33 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Tanatanaon | 175311015 | Concreting of 4m X 300m and gravelling of 4m X 280m FMR | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 1678625 | 617375 | 2296000 |  |  | 1342900 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Poblacion | 175311008 | Improvement of Farm to Market road with PCCP and Lined Canal | 1 | Basic Access Infrastructure | Road |  | kms | 842175.83 | 215824.17 | 1058000 |  |  | 673740.66 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Catep | 175311005 | Construction of 1 Unit Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 664008.33 | 160991.67 | 825000 |  |  | 531206.66 | 1st | Not yet started
IV-B | 17 | Palawan | 1753 | Dumaran | 175311 | Sta. Teresita | 175311013 | Construction of 1 Unit 20m X 30m Solar Drier with 9m X 6m Storage Room | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 654 | sq.m | 1083268.75 | 274731.25 | 1358000 |  |  | 866615 | 1st | Not yet started
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | San Roque | 175901012 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 250 | ln.m | 1618290 | 424710 | 2043000 | 2012-04-10 | 2012-07-15 | 1288271.73 | 1st | Completed
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Bagsik | 175901009 | Construction of Slope Protection | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 34 | ln.m | 414726.1 | 148273.9 | 563000 | 2012-04-10 | 2012-06-30 | 410937.25 | 2nd | Completed
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Bonlao | 175901001 | Construction of River Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 305 | ln.m | 1771452.31 | 488547.69 | 2260000 | 2012-05-03 | 2012-07-15 | 1417161.85 | 1st | Completed
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | San Isidro | 175901007 | Construction of Seawall with Road Improvement | 1 | Environmental Protection and Conservation | Sea Wall | 255 | ln.m | 671229.83 | 246770.17 | 918000 | 2012-04-16 | 2012-07-15 | 536833.53 | 1st | Completed
IV-B | 17 | Romblon | 1759 | Alcantara | 175901 | Lawan | 175901011 | Concreting and improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 924301.76 | 218698.24 | 1143000 | 2012-05-11 | 2012-06-30 | 739441.41 | 1st | Completed
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Lumbang Este | 175903009 | Water System | 1 | Basic Social Services | Water System | 1 | system | 1497250 | 390750 | 1888000 | 2012-05-14 |  | 1197800 | 1st | On-going
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Marigindon | 175903011 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2295375 | 813625 | 3109000 | 2012-07-02 |  | 1836300 | 1st | Not yet started
IV-B | 17 | Romblon | 1759 | Cajidiocan | 175903 | Danao | 175903006 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2503591.67 | 1590408.33 | 4094000 |  |  | 1884970.67 | 1st | Not yet started
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Mabini | 175913006 | Upgrading of of existing gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 525000 | 291000 | 816000 |  |  | 420000 | 1st | On-going
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Mabulo | 175913007 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 2010000 | 992000 | 3002000 |  |  | 1608000 | 1st | Not yet started
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Agtiwa | 175913001 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 600000 | 200000 | 800000 | 2012-05-14 | 2012-07-15 | 480000 | 1st | Completed
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Campalingo | 175913003 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1600000 | 494000.01 | 2094000.01 |  |  | 1280000 | 1st | Not yet started
IV-B | 17 | Romblon | 1759 | San Fernando | 175913 | Azagra | 175913002 | School Building | 1 | Basic Social Services | School | 63 | sq. m | 580000 | 290000 | 870000 | 2012-05-22 |  | 464000 | 1st | On-going
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Poblacion | 175914005 | Construction of 410 ln.m FMR with double barrel Reinforced Concrete Culvert | 1 | Basic Access Infrastructure | Road | 0.41 | kms | 1203218.5 | 370781.5 | 1574000 | 2012-05-23 |  | 951517.3 | 1st | On-going
IV-B | 17 | Romblon | 1759 | San Jose | 175914 | Lanas | 175914003 | Concreting of of 517 ln.m farm to market road | 1 | Basic Access Infrastructure | Road | 517 | kms | 835740.83 | 332259.17 | 1168000 | 2012-05-23 |  | 636352.66 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tinago | 076106041 | Construction of Solar Drier Pavement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 588.92 | sq.m | 381169.6 | 163358.4 | 544528 | 2012-02-20 | 2012-04-30 | 304935.68 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Lambojon/Cangmohao | 076106023 | Water System Level II | 2 | Basic Social Services | Water System | 1 | system | 797536.6 | 341801.4 | 1139338 | 2012-03-19 |  | 638029.28 | 1st | On-going
[6 empty] | Cangmohao | 076106018
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Dumanhog | 076106021 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 102 | ln.m | 351054.2 | 150451.8 | 501506 | 2012-01-31 | 2012-07-15 | 273287.36 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Panlautan | 076106028 | Electrification | 1 | Basic Social Services | Electrification | 38 | HH | 381502.8 | 369233.2 | 750736 | 2012-03-05 | 2012-07-15 | 305202.24 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Olo | 076106026 | Asphalt Paving of Farm to market Road | 1 | Basic Access Infrastructure | Road | 0.504 | kms | 627877.6 | 269090.4 | 896968 | 2012-02-15 | 2012-04-30 | 616037.69 | 2nd | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-inte | 076106014 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 516240.9 | 221246.1 | 737487 | 2012-02-28 |  | 413752.64 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-isad | 076106015 | Opening of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 516240.9 | 221246.1 | 737487 | 2012-02-22 |  | 412992.72 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Poblacion | 076106031 | Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 289 | ln.m | 626245.9 | 268391.1 | 894637 | 2012-02-20 | 2012-06-30 | 500996.72 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cantabon | 076106019 | Construction of Ricemill with Equipement | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | Unit | 427269.92 | 182729.1 | 609999.02 | 2012-03-19 |  | 341815.94 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cangmatnog | 076106017 | Expansion of Water System | 1 | Basic Social Services | Water System | 1 | system | 362078.5 | 155176.5 | 517255 | 2012-03-05 | 2012-06-30 | 289662.8 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-atuyom | 076106006 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.48 | kms | 512668.1 | 219714.9 | 732383 | 2012-03-03 |  | 410134.48 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tacdog | 076106037 | Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 623665 | 267285 | 890950 | 2012-02-20 |  | 311832.5 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Ibabao | 076106022 | Electrification Expansion | 1 | Basic Social Services | Electrification | 31 | HH | 347310.8 | 330356.2 | 677667 | 2012-02-27 | 2012-07-15 | 277848.64 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Sabang | 076106034 | Asphalting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.295 | kms | 449888 | 192810 | 642698 | 2012-03-05 | 2012-06-30 | 359910.88 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Canghunoghunog | 076106016 | Installation of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 494869 | 212086 | 706955 | 2012-03-15 | 2012-07-15 | 395894.8 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Polangyuta | 076106032 | Expansion of water System | 1 | Basic Social Services | Water System | 1 | system | 599750.9 | 257036.1 | 856787 | 2012-02-27 |  | 299875.45 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Cang-alwang | 076106012 | Construction of Alternative Learning System livelihood Program | 1 | Basic Social Services | School | 48 | sq. m | 582287.93 | 249551.97 | 831839.9 | 2012-02-15 | 2012-06-30 | 465830.34 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Ponong | 076106033 | Electrification | 1 | Basic Social Services | Electrification | 60 | HH | 581508.22 | 391662.78 | 973171 | 2012-02-16 | 2012-07-15 | 465206.58 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Luyang | 076106024 | 1 Unit Vehicle with Garage | 1 | Community Production, Economic Support and Common Service Facility | Community Transport | 1 | unit | 383866 | 164514 | 548380 | 2012-04-20 | 2012-07-15 | 307092.8 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Calalinan | 076106005 | Asphalting of farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.26 | kms | 493841.6 | 211646.4 | 705488 | 2012-02-20 | 2012-04-30 | 489851.85 | 2nd | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Canal | 076106007 | Improvement of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.16 | kms | 818057.8 | 350596.2 | 1168654 |  |  | 654446.24 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tambisan | 076106039 | Electrification | 1 | Basic Social Services | Electrification | 67 | HH | 571922.8 | 412687.2 | 984610 | 2012-02-17 | 2012-04-30 | 457538.24 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tebjong | 076106040 | Electrification | 1 | Basic Social Services | Electrification | 26 | HH | 384944.98 | 274944.02 | 659889 | 2012-02-28 | 2012-07-15 | 346450.48 | 2nd | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caipilan | 076106003 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 616577.23 | 257870.59 | 874447.82 |  |  | 493261.78 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Luzong | 076106025 | Electrification | 1 | Basic Social Services | Electrification | 65 | HH | 714867.6 | 458032.4 | 1172900 | 2012-02-06 | 2012-07-15 | 563114.08 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Banban | 076106001 | Construction of Livelihood Program Alternative Learning Sytem | 1 | Basic Social Services | School | 160.5 | sq. m | 661071.75 | 283215.46 | 944287.21 |  |  | 493555 | 1st | On-going
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pasihagon | 076106029 | Acquisition of 1 Unit Motorized Vehicle | 1 | Community Production, Economic Support and Common Service Facility | Community Transport | 1 | unit | 383866 | 164514 | 548380 |  |  | 307092.8 | 1st | Not yet started
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tongo | 076106042 | Asphalting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 500763.9 | 214613.1 | 715377 | 2012-03-08 | 2012-04-30 | 400611.12 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Candanay Norte | 076106008 | Asphalting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.539 | kms | 815797.3 | 349627.7 | 1165425 | 2012-02-23 | 2012-04-30 | 652637.84 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caticugan | 076106020 | Asphalting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.167 | kms | 303054 | 129881 | 432935 | 2012-02-15 | 2012-04-30 | 286940.64 | 2nd | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | San Antonio | 076106035 | Installation of Water System | 1 | Basic Social Services | Water System | 1 | system | 1061892.3 | 455096.7 | 1516989 | 2012-02-04 | 2012-06-30 | 849513.84 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Pangi | 076106027 | 1 CL School Building | 1 | Basic Social Services | School | 63 | sq. m | 556310.21 | 240984.19 | 797294.4 | 2012-02-28 | 2012-06-30 | 445048.17 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Tacloban | 076106038 | Road Opening | 1 | Basic Access Infrastructure | Road | 0.4 | kms | 425582.5 | 182392.5 | 607975 | 2012-02-07 | 2012-04-30 | 340466 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Candanay Sur | 076106009 | Asphalting of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.5 | kms | 630049.2 | 270021.8 | 900071 | 2012-01-23 | 2012-06-30 | 504039.36 | 1st | Completed
VII | 07 | Siquijor | 0761 | Siquijor | 076106 | Caitican | 076106004 | Acquisition of 1 unit Tractor | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | Unit | 397419.46 | 232310.54 | 629730 | 2012-04-30 | 2012-06-30 | 317935.57 | 1st | Completed
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Parian | 076101012 | Construction of Livelihood Training Center | 1 | Community Production, Economic Support and Common Service Facility | Multi-use Building/Facility | 48 | sq.m | 436051.26 | 286943.74 | 722995 | 2012-03-06 |  | 392446.13 | 2nd | On-going
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Lomangcapan | 076101008 | Rehabilitation of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1279624 | 503326 | 1782950 | 2012-03-15 |  | 1023699.2 | 1st | On-going
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Balolong | 076101001 | Health Station with Ferrocement Tank | 1 | Basic Social Services | Health Station | 51 | sq.m | 598053.6 | 188553.4 | 786607 | 2012-03-13 |  | 478442.88 | 1st | On-going
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Bolot | 076101004 | Rehabilitation of farm to market road | 1 | Basic Access Infrastructure | Road | 1 | kms | 1942731.63 | 614773.37 | 2557505 | 2012-05-14 |  | 1554185.3 | 1st | On-going
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Manan-ao | 076101010 | Rehabilitation of level I Water System | 1 | Basic Social Services | Water System | 1 | system | 174729.18 | 175072.82 | 349802 | 2012-05-02 | 2012-07-15 | 139783.34 | 1st | Completed
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Camogao | 076101005 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 582452 | 162828 | 745280 | 2012-03-05 | 2012-07-15 | 524206.8 | 2nd | Completed
VII | 08 | Siquijor | 0761 | Enrique Villanueva | 076101 | Cangmangki | 076101006 | Rehabilitation of Farm to Market Road | 1 | Basic Access Infrastructure | Road | 0.8 | kms | 1286358.33 | 939127.67 | 2225486 | 2012-05-14 | 2012-07-15 | 1029086.67 | 1st | Completed
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 1 | 086022028 | Expansion of .050km Brgy. Road with with Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 0.05 | ln.m | 870849 | 225465 | 1096314 | 2012-02-20 |  | 696680 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Paco | 086022023 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 569208 | 145675 | 714883 | 2012-03-05 |  | 455366.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tutubigan | 086022047 | Construction of 50 Lm Hanging Bridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 50 | ln.m | 1344320 | 341080 | 1685400 |  |  | 1075456 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 2 | 086022029 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 547696 | 140298 | 687994 | 2012-03-05 |  | 438157 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lawaan 2 | 086022049 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 547696 | 140298 | 687994 | 2012-02-27 |  | 504820.1 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lawaan 1 | 086022015 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 560911 | 145228 | 706139 | 2012-02-27 |  | 504820.1 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 4 | 086022031 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 208 | ln.m | 686077 | 174892 | 860969 | 2012-02-27 |  | 548862 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 6 | 086022033 | Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 156 | ln.m | 332313 | 86451 | 418764 | 2012-02-20 |  | 299082 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Bato | 086022005 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 589896 | 152473 | 742369 | 2012-02-13 | 2012-05-30 | 471917 | 1st | Completed
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 3 | 086022030 | Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 489 | ln.m | 537624 | 137780 | 675404 | 2012-02-27 |  | 430100 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lipata et. Al | 086022016 | Concreting of Lipata-Minarog Road | 2 | Basic Access Infrastructure | Road | 0.4 | kms | 1447944 | 367242 | 1815186 |  |  | 1158355.2 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Poblacion 5 | 086022032 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 105 | ln.m | 639653 | 163288 | 802941 | 2012-05-01 |  | 575688.3 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | San Isidro | 086022039 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 595912 | 153977 | 749889 | 2012-02-27 |  | 536320.8 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tigbawon | 086022045 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.551 | kms | 866418 | 221604 | 1088022 | 2012-04-02 |  | 779775.4 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Layo | 086013014 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 301110 | 90000 | 391110 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Pahug | 086013021 | Construction of Public Market | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) |  | sq.m | 324148 | 90000 | 414148 |  |  | 259318 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Loctob | 086013015 | Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 143 | ln.m | 377480 | 131155 | 508635 | 2012-04-02 |  | 301984 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Magdawat | 086013017 | Farm Production Facilities | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | sq.m | 261860 | 69465 | 331325 |  |  | 209448 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Lale | 086013011 | Constrution of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 80 | ln.m | 312205 | 119400 | 431605 | 2012-03-29 |  | 249764 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Calampong | 086013006 | Concreting of Pathwalk with grouted Riprap | 1 | Basic Access Infrastructure | Access Trail | 0.204 | kms | 432520 | 123302 | 555822 |  |  | 346016 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Mambog | 086013018 | Rehab of bailey Bridge with Cover | 1 | Basic Access Infrastructure | Foot/Small Bridges | 18.3 | ln.m | 463666 | 134728 | 598394 |  |  | 370932 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Bugho | 086013005 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.4 | kms | 420492 | 183809 | 604301 | 2012-04-16 |  | 336394 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Poblacion 1 | 086013002 | Construction of 50 Linear Meters Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 50 | ln.m | 457158 | 134290 | 591448 |  |  | 365726 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Madalunot | 086013016 | 1 CL elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 496850 | 147983 | 644833 | 2012-03-19 |  | 397480 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Botoc | 086013004 | Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.3 | kms | 444832 | 151428 | 596260 | 2012-03-23 |  | 355866 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Nabong | 086013026 | Construction of Grouted Riprap | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 60 | ln.m | 412436 | 120522 | 532958 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Bangon | 086013001 | Concrete Covered Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 275 | ln.m | 474231 | 167792 | 642023 | 2012-04-09 |  | 379385 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Obayan | 086013020 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 263 | ln.m | 481580 | 137850 | 619430 | 2012-03-26 |  | 385264 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Laygayon | 086013013 | 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 474440 | 175393 | 649833 | 2012-04-23 |  | 379540 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Dolores | 086013010 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 143 | ln.m | 367734 | 155800 | 523534 | 2012-03-26 |  | 294186 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Parasanon | 086013022 | Construction of River Bank Protection | 1 | Environmental Protection and Conservation | River Control/Flood Control | 160 | ln.m | 457118 | 137398 | 594516 |  |  | 365694 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Canlobo | 086013007 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 403352 | 152115 | 555467 |  |  | 322682 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Lawaan | 086013012 | 1 CL elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 569886 | 194297 | 764183 |  |  | 455908 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | San Isidro | 086013025 | Construction of Level II Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 596575 | 232932 | 829507 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Pelaon | 086013023 | 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 576161 | 217445 | 793606 |  |  | 460928 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Poblacion 2 | 086013003 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 180 | ln.m | 409726 | 121836 | 531562 |  |  | 327780 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Manaing | 086013019 | 1 CL elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 610602 | 183004 | 793606 |  |  | 366361 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Pinabacdao | 086013 | Catigawan | 086013008 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 593558 | 200692 | 794250 |  |  | 474846 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Jose Rono | 086022013 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.16 | kms | 289646 | 77412 | 367058 |  |  | 231717 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Solupan | 086022041 | Cncreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.35 | kms | 638697 | 164673 | 803370 | 2012-02-27 | 2012-06-30 | 510957.6 | 1st | Completed
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Tula | 086022046 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.492 | kms | 956418 | 244105 | 1200523 | 2012-04-23 |  | 765134.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Mangcal | 086022018 | Pre-Harvest Facility | 1 | Community Production, Economic Support and Common Service Facility | Pre and Post Production Facility | 1 | sq.m | 1041004 | 265251 | 1306255 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Lokilokon | 086022017 | Construction of Open Lined Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 648 | ln.m | 506346 | 131587 | 637933 | 2012-02-27 |  | 455711.4 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Anagasi | 086022001 | Capability Building for Sustainable Agriculture | 1 | Skills Training/Capability Building/Community Library | Skills Training/Capability Building/Community Library |  | unit | 312600 | 81526 | 394126 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Apolonia | 086022002 | Soil Erosion Control | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 75 | ln.m | 378462 | 99616 | 478078 |  |  | 340616 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Casandig 1 | 086022011 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 560911 | 145228 | 706139 | 2012-02-27 |  | 504820.1 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Casandig 2 | 086022048 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 560911 | 145228 | 706139 | 2012-02-20 |  | 504819.9 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Patag | 086022026 | Contruction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 410 | ln.m | 806435 | 204985 | 1011420 | 2012-03-08 |  | 645148 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantaguic | 086022008 | Concrete Pathwalk with Grouted Riprap | 1 | Basic Access Infrastructure | Access Trail | 0.135 | kms | 593294 | 153323 | 746617 | 2012-04-23 |  | 474635 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantato | 086022010 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 560911 | 145228 | 706139 | 2012-02-27 |  | 504820.1 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Pabanog | 086022022 | Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 591912 | 152979 | 744891 | 2012-02-13 |  | 532721.2 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Balbagan | 086022004 | Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 929789 | 235821 | 1165610 | 2012-02-13 |  | 836810.5 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Cantao-an | 086022009 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.248 | kms | 372406 | 98102 | 470508 | 2012-03-05 |  | 335165.6 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Paranas | 086022 | Buray | 086022006 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 544659 | 143335 | 687994 | 2012-02-20 |  | 490496.7 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Nabulo | 086016026 | Construction of 1 Unit School Building | 1 | Basic Social Services | School | 63 | sq. m | 612117 | 158283 | 770400 | 2012-04-09 |  | 550905.3 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Monbon | 086016025 | Concreting of Barangay Road with Groted riprap | 1 | Basic Access Infrastructure | Road | 0.207 | kms | 999869 | 301431 | 1301300 | 2012-03-22 |  | 899882.1 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Panaruan | 086016030 | Improvement of 1 Unit 1 CL School Building | 1 | Basic Social Services | School |  | sq. m | 285700 | 74800 | 360500 | 2012-05-14 |  | 228560 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Palale | 086016028 | Construction of Riprap river Control Wharf | 1 | Environmental Protection and Conservation | River Control/Flood Control | 140 | ln.m | 895037 | 288563 | 1183600 | 2012-05-14 |  | 805533.3 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Salvacion | 086016032 | Construction of 3 Units 2 Compartment Public Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 3 | unit | 199300 | 53200 | 252500 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Panabatan | 086016029 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 42 | unit | 463977 | 215223 | 679200 | 2012-06-04 |  | 371181.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cagsumje | 086016035 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.525 | kms | 765540 | 237460 | 1003000 | 2012-04-16 |  | 612432 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Canmoros | 086016013 | 1 Unit Elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 624433 | 161361 | 785794 |  |  | 499546.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Roxas | 086016031 | One Unit Elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 625160 | 161544 | 786704 |  |  | 500128 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Lambao | 086016022 | Construction of 67 Ln.m Pathwalk,30 ln.m DRG & 1 Row 12" RCPC | 1 | Basic Access Infrastructure | Access Trail | 0.067 | kms | 308337 | 95563 | 403900 | 2012-06-25 |  | 246669.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Sundara | 086016034 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 36 | unit | 369717 | 156183 | 525900 | 2012-04-30 |  | 295773.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Avelino | 086016003 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 588921 | 152485 | 741406 |  |  | 471136.8 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Matayonas | 086016036 | Construction of of Sanitary toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 32 | unit | 463637 | 173163 | 636800 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Curry | 086016015 | Construction of Gravelled pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.5 | kms | 1222939.4 | 311060.6 | 1534000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Inoraguiao | 086016020 | Constrution of 1 unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 964490 | 288310 | 1252800 | 2012-03-26 |  | 868041 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Agrufacion | 086016001 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 31 | unit | 493897 | 179103 | 673000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Napuro 2 | 086016027 | One Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 525541 | 162859 | 688400 | 2012-04-11 |  | 472986.9 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Mabuhay | 086016023 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.175 | kms | 236100 | 62400 | 298500 | 2012-06-04 |  | 188880 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Arapison | 086016002 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 573317 | 148583 | 721900 | 2012-03-23 |  | 515985.3 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Ilo | 086016018 | One Unit Elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 515012.8 | 168687.2 | 683700 | 2012-04-16 |  | 463511.52 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Solsogon | 086016033 | 150 Lm Grouted Riprap & 352 sq.m Pathwalk | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 150 | ln.m | 1620445 | 488355 | 2108800 |  |  | 1296356 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Bahay | 086016004 | Improvement of 1 Unit Primary School Building | 1 | Basic Social Services | School |  | sq. m | 295620 | 77280 | 372900 |  |  | 236496 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Bana-ao | 086016006 | One Unit Elem School Building | 1 | Basic Social Services | School | 63 | sq. m | 599797 | 155203 | 755000 | 2012-05-14 |  | 479837.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Gajo | 086016016 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 609410 | 157609 | 767019 |  |  | 487528 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Cautod | 086016009 | Construction of 160 Lined Canal with 6l Ln.m RCPC | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 160 | ln.m | 292500 | 76500 | 369000 | 2012-05-14 |  | 263250 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Sta. Margarita | 086016 | Napuro 1 | 086016027 | Construction of 80 L.m Grouted Riprap & 80 L.m Conc. Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.8 | kms | 778423 | 235377 | 1013800 | 2012-04-09 |  | 622738.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Tomabe | 086021042 | Concreting of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 2.18 | kms | 1239297 | 355942 | 1595239 | 2012-05-11 |  | 991437.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Tayud | 086021041 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 635 | ln.m | 725425 | 225030 | 950455 | 2012-05-01 |  | 601795.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | San Roque | 086021037 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.768 | kms | 739147 | 227770 | 966917 |  |  | 591317.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Sto. Nino | 086021039 | Construction of Concrete Tirepath | 1 | Basic Access Infrastructure | Road | 0.9 | kms | 1399404 | 487738 | 1887142 |  |  | 1077824 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Ulayan | 086021043 | Construction of Concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.808 | kms | 742165 | 221919 | 964084 | 2012-05-14 |  | 593732 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Sta. Rosa | 086021038 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.257 | kms | 273248 | 127053 | 400301 | 2012-03-28 |  | 218598.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Villarosa | 086021006 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 593328 | 187134 | 780462 | 2012-04-16 |  | 454864 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | San Andres | 086021034 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.476 | kms | 536730 | 162107 | 698837 | 2012-05-04 |  | 400166 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Patag | 086021044 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.968 | kms | 715904 | 216390 | 932294 | 2012-04-23 |  | 572723.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Plaridel | 086021025 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 72 | ln.m | 795021 | 236866 | 1031887 |  |  | 625529.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Mahayag | 086021017 | Construction of Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6.4 | ln.m | 778038 | 256604 | 1034642 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Camucat | 086021005 | Construction of Concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.9 | kms | 932754 | 274086 | 1206840 | 2012-05-16 |  | 746203.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Polangi | 086021033 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 2.27 | kms | 1136615 | 375289 | 1511904 | 2012-04-09 |  | 909292 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Pang-pang | 086021024 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.9 | kms | 897736 | 264959 | 1162695 | 2012-04-10 |  | 718188.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Lam-awan | 086021015 | Cobstruction of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 2.04 | kms | 1328672 | 401458 | 1730130 | 2012-04-23 |  | 1062937.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Mercado | 086021019 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 747411 | 226464 | 973875 |  |  | 597928.8 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Miramar | 086021020 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 725377 | 217122 | 942499 | 2012-04-30 |  | 463003.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Himyangan | 086021009 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 593231 | 178846 | 772077 | 2012-03-30 |  | 533907.9 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Malonoy | 086021018 | Improvement of Level II Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 659624 | 197957 | 857581 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | Lawa-an | 086021015 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1.88 | kms | 1176698 | 345108 | 1521806 | 2012-03-28 |  | 941358.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Villareal | 086021 | San Fernando | 086021035 | Construction of 22 Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 22 | unit | 361588 | 98722 | 460310 | 2012-04-24 |  | 325429.2 | 2nd | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion E | 086020045 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 153.6 | ln.m | 337340 | 164530 | 501870 | 2012-05-14 |  | 269872 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Libucan Dacu | 086020027 | Construction of Grouted Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 169.7 | ln.m | 597041 | 297787 | 894828 | 2012-05-30 |  | 477632.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Libucan Gote | 086020028 | Construction of 1 Unit 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 462188 | 218957 | 681145 | 2012-05-07 |  | 369750.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Sugod | 086020049 | Construction of concrete tirepath | 1 | Basic Access Infrastructure | Road | 1.49 | kms | 1385809 | 631904 | 2017713 | 2012-06-15 |  | 1108647.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Lahong | 086020026 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 513043 | 225131 | 738174 | 2012-04-16 |  | 410434.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion C | 086020043 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 370 | ln.m | 714554 | 351051 | 1065605 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bahay | 086020003 | Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.5 | kms | 902032 | 394381 | 1296413 |  |  | 721625.6 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Talinga | 086020050 | Construction of CHB Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 430 | ln.m | 902032 | 394381 | 1296413 | 2012-05-09 |  | 487052.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Mancares | 086020030 | Construction of Concrete Pathway | 1 | Basic Access Infrastructure | Access Trail | 1.5 | kms | 1467256 | 683689 | 2150945 |  |  | 1027079.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Alcazar | 086020001 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 507528 | 230446 | 737974 | 2012-04-28 |  | 406022.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Binalayan | 086020009 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 53 | unit | 611503 | 294976 | 906479 | 2012-06-06 |  | 489202.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Camb. Viejo | 086020019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 507528 | 230446 | 737974 | 2012-05-09 |  | 406022.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Poblacion D | 086020044 | Construction of Pathway | 1 | Basic Access Infrastructure | Access Trail | 0.738 | kms | 907868 | 398079 | 1305947 |  |  | 726294.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Canunghan | 086020020 | Construction of Tirepath | 1 | Basic Access Infrastructure | Road | 0.55 | kms | 806311 | 387192 | 1193503 | 2012-05-21 |  | 645048.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Balonga-as | 086020004 | Construction of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.961 | kms | 605444 | 341321 | 946765 |  |  | 484355.2 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Lucerdoni | 086020025 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.71 | kms | 783690 | 365549 | 1149239 | 2012-05-02 |  | 626952 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bonga | 086020011 | Construction of Tirepath | 1 | Basic Access Infrastructure | Road | 1.028 | kms | 1065612 | 514932 | 1580544 | 2012-06-05 |  | 852489.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Catan-agan | 086020021 | Construction of Tirepath | 1 | Basic Access Infrastructure | Road | 3.5 | kms | 946840 | 473812 | 1420652 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Imelda | 086020024 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 115.5 | ln.m | 311977 | 145325 | 457302 | 2012-04-27 |  | 249581.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Gallego | 086020023 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 150 | ln.m | 1198352 | 544419 | 1742771 |  |  | 958681.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Bisitahan | 086020010 | Road Concreting | 1 | Basic Access Infrastructure | Road | 1.285 | kms | 1245449 | 544886 | 1790335 | 2012-05-09 |  | 996359.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Palencia | 086020039 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 450991 | 214157 | 665148 | 2012-06-05 |  | 360792.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Majacob | 086020029 | Construction of Concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.775 | kms | 833506 | 375025 | 1208531 | 2012-05-28 |  | 666804.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Oeste A | 086020032 | Construction of Concrete Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.728 | kms | 334206 | 146609 | 480815 | 2012-05-18 |  | 267364.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Tarangnan | 086020 | Oeste B | 086020033 | Construction of Health Station | 1 | Basic Social Services | Health Station | 63 | sq.m | 410020 | 345116 | 755136 | 2012-05-19 |  | 276092.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Parasan | 086006037 | Construction of Drainage Canal with Box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 1508712 | 410288 | 1919000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Nipa | 086006035 | Construction of 2 Unit Elem School Building | 1 | Basic Social Services | School | 126 | sq. m | 1074008 | 304292 | 1378300 |  |  | 859206.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Sugod | 086006058 | Construction of 25 Unit Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 25 | unit | 354256.8 | 193943.2 | 548200 |  |  | 283405.44 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Guindapunan | 086006024 | Construction of 1 Unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1094752 | 299448 | 1394200 |  |  | 875801.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Campelipa | 086006020 | Construction of Pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.39 | kms | 784353 | 215347 | 999700 |  |  | 627482.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | San Jose | 086006045 | Construction of 60 ln.m fishing Boat Bething Facility | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 60 | ln.m | 1130397.6 | 307202.4 | 1437600 |  |  | 904318.08 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Tugas | 086006052 | Concreting of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.49 | kms | 657637 | 184763 | 842400 |  |  | 526109.6 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Baclayan | 086006004 | Construction of fishing boat berthing facility | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 8 | ln.m | 1536536 | 413464 | 1950000 |  |  | 1075575.2 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Talisay | 086006051 | Construction of Level II Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 683669 | 195031 | 878700 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Buenavista | 086006010 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 563236.2 | 156763.8 | 720000 |  |  | 450588.96 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | San Miguel | 086006046 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 567484.8 | 157415.2 | 724900 |  |  | 453987.84 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Ubo | 086006053 | Construction of 1 Unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1074968 | 303032 | 1378000 |  |  | 859974.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Bono-anon | 086006009 | Construction of level 2 Gravity Fed water system | 1 | Basic Social Services | Water System | 1 | system | 421780 | 122220 | 544000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Casab-ahan | 086006023 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 126 | unit | 1478656 | 838844 | 2317500 |  |  | 1182924.8 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Astorga | 086006002 | Construction of Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 1373300 | 371700 | 1745000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Poso | 086006041 | Construction of Water System Level II Gravity | 1 | Basic Social Services | Water System | 1 | system | 750525 | 210475 | 961000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Cabil-isan | 086006013 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 70 | ln.m | 1682040 | 484860 | 2166900 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Betaug | 086006008 | Construction of Erosion Control | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 150 | ln.m | 1051964 | 285036 | 1337000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | San Antonio | 086006044 | Consgtruction of Erosion Control | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 160 | ln.m | 661075.4 | 185124.6 | 846200 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Jacopon | 086006027 | Construction of 1 Unit 2 CL Elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1069568 | 298232 | 1367800 |  |  | 855654.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Valles Bello | 086006054 | Construction of Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 59 | ln.m | 1029906.4 | 276693.6 | 1306600 |  |  | 823925.12 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Cambuhay | 086006017 | Extension of mini wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 100 | ln.m | 1207720 | 332380 | 1540100 |  |  | 966176 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Bayog | 086006006 | Construction of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.2 | kms | 281148 | 78652 | 359800 |  |  | 224918.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Mabini | 086006029 | Construction of box Culvert | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 6 | ln.m | 220020 | 60980 | 281000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Mayabay | 086006034 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 456 | ln.m | 599234.6 | 166065.4 | 765300 |  |  | 479387.68 | 1st | On-going
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Cabugao | 086006015 | Construction of Draiange Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 324 | ln.m | 565384 | 155616 | 721000 |  |  | 452307.2 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Cabac | 086006012 | Construction of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.75 | kms | 1834608 | 498392 | 2333000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Daram | 086006 | Bachao | 086006003 | Improvement of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.07 | kms | 577438.4 | 158361.6 | 735800 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Poblacion 2 | 086015002 | Construction of 0.025 km Barangay Road | 1 | Basic Access Infrastructure | Road | 0.025 | kms | 231525 | 61259 | 292784 |  |  | 185220 | 1st | On-going
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Poblacion 4 | 086015004 | Construction of 170 ln.m Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 170 | ln.m | 326062 | 96987 | 423049 |  |  | 260849.6 | 1st | On-going
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Poblacion 3 | 086015003 | Construction of drainage canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 150 | ln.m | 333648 | 101118 | 434766 |  |  | 266918.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Poblacion 1 | 086015001 | Construction of Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 200 | ln.m | 396346 | 119790 | 516136 |  |  | 317076.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Canduyocan | 086015014 | Construction of riverbank erosion protection | 1 | Environmental Protection and Conservation | Soil Protection (Riprap)/Slope Protection/Protection Railing | 100 | ln.m | 505270 | 146573 | 651843 |  |  | 404216 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Cabaywa | 086015013 | Road Concreting | 1 | Basic Access Infrastructure | Road | 0.3 | kms | 667693 | 210588 | 878281 |  |  | 534154.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Inobongan | 086015012 | Construction of day care center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 540843 | 155466 | 696309 |  |  | 432674.4 | 1st | On-going
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Dolores | 086015010 | Construction of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail |  | kms | 386776 | 121175 | 507951 |  |  | 309420.8 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Hita-asan 1 | 086015011 | Construction of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.335 | kms | 620483 | 218037 | 838520 |  |  | 496386.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Balogo | 086015005 | Construction of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 1 | kms | 650016 | 189762 | 839778 |  |  | 520012.8 | 1st | On-going
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Hita-asan 2 | 086015015 | Construction of Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 60 | ln.m | 571970 | 176388 | 748358 |  |  | 457576 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Bontod | 086015006 | Construction of pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.5 | kms | 408498 | 123975 | 532473 |  |  | 326798.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Camanhagay | 086015007 | Road Construction | 1 | Basic Access Infrastructure | Road | 0.135 | kms | 383907 | 120203 | 504110 |  |  | 307125.6 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Sebastian | 086015 | Campiyak | 086015008 | Construction of concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.7 | kms | 276963 | 327170 | 604133 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | San Jose De Buan | 086014 | San Nicolas | 086014014 | Construction of Level II water System | 1 | Basic Social Services | Water System | 1 | system | 643163 | 241200 | 884363 |  |  | 514530.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Jose De Buan | 086014 | Poblacion 1 | 086014010 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) |  | unit | 1799707 | 1358115 | 3157822 |  |  | 1439765.6 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Jose De Buan | 086014 | Gusa | 086014006 | Construction of 1 Unit Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 691245 | 273753 | 964998 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | San Jose De Buan | 086014 | Hiduroma | 086014008 | Construction of 1 Unit 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 525591 | 224510 | 750101 |  |  | 420472.8 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | San Jose De Buan | 086014 | Babaclayon | 086014002 | Construction of Level II Gravity Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 719722 | 272024 | 991746 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | San Jose De Buan | 086014 | Poblacion 4 | 086014013 | Construction of Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) |  | unit | 1674354 | 1202356 | 2876710 |  |  | 1339483.2 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tagapul-an | 086024 | San Vicente,Luna & Nipa | 086024010 | Construction of 3 Phase Primary Electrical Lines | 3 | Basic Social Services | Electrification |  | HH | 3891740 | 1249260 | 5141000 |  |  | 0 |  | Not yet started
[6 empty] | Luna | 086024005
[6 empty] | Nipa | 086024007
VIII | 08 | Western Samar | 0860 | Tagapul-an | 086024 | Pantalan | 086024008 | Construction of Level System Level I | 1 | Basic Social Services | Water System | 1 | system | 336210 | 133153 | 469363 |  |  | 268968 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tagapul-an | 086024 | Manlangit | 086024013 | Water System level I | 1 | Basic Social Services | Water System | 1 | system | 124900 | 45289 | 170189 |  |  | 99920 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tagapul-an | 086024 | Labangbaybay | 086024004 | Construction of Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 270.7 | ln.m | 682171 | 250010 | 932181 |  |  | 545736 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Tagapul-an | 086024 | Sugod & San Jose | 086024011 | Construction of Drainage Canal With Cover | 2 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 383.5 | ln.m | 758738 | 277011 | 1035749 |  |  | 606990 | 1st | Not yet started
[6 empty] | San Jose | 086024014
VIII | 08 | Western Samar | 0860 | Tagapul-an | 086024 | Banquiw | 086024001 | Construction of Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 503538 | 159613 | 663151 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | Malaguining | 086019002 | Construction of 118 Linear Meters River Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 118 | ln.m | 992800 | 386309 | 1379109 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | Victory | 086019011 | Construction of 100 Linear Meters Pier | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 100 | ln.m | 961390 | 318691 | 1280081 |  |  | 769112 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | Placer | 086019006 | Construction of 100 Linear Meter Flood Control | 1 | Environmental Protection and Conservation | River Control/Flood Control | 100 | ln.m | 583050 | 228591 | 811641 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | Independencia | 086019001 | Construction of 70 ln.m Seawall | 1 | Environmental Protection and Conservation | Sea Wall | 100 | ln.m | 651420 | 248950 | 900370 |  |  | 521136 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | San Juan | 086019009 | Construction of 1 CL Elem. School Building | 1 | Basic Social Services | School | 63 | sq. m | 528000 | 221997 | 749997 |  |  | 422400 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | Navatas Daku | 086019004 | Construction of Health Station | 1 | Basic Social Services | Health Station | 51 | sq.m | 506560 | 221591 | 728151 |  |  | 405248 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Talalora | 086019 | Poblacion II | 086019008 | Construction of 400 linear meters Drainage Canal | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 400 | ln.m | 648650 | 252695 | 901345 |  |  | 518920 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Sevilla | 086018011 | Construction of 1 unit 2 CL elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 835150.4 | 268259.6 | 1103410 |  |  | 668120.32 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Balat Guti | 086018001 | Extension of Barangay Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) |  | ln.m | 988971.2 | 419206.8 | 1408178 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Corocawayan | 086018006 | Construction of Concrete pathwalk with guardrail | 1 | Basic Access Infrastructure | Access Trail | 0.208 | kms | 599670 | 169542 | 769212 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Pinanangnan | 086018010 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 491374 | 152819 | 644193 |  |  | 393099.52 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Lobe Lobe | 086018009 | Extension of Barangay Wharf | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) |  | ln.m | 430384 | 149906 | 580290 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Villahermosa | 086018013 | Construction of 1 Unit High School Building | 1 | Basic Social Services | School | 63 | sq. m | 531494.4 | 169024 | 700518.4 |  |  | 425195.52 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Cabungaan | 086018005 | Construction of Gravity Fed Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 995808 | 329672 | 1325480 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Buenavista | 086018004 | Construction of pathwalk with canal | 1 | Basic Access Infrastructure | Access Trail |  | kms | 436168 | 114302 | 550470 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Santo Niño | 086018 | Ilijan | 086018007 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 482551.2 | 157115.8 | 639667 |  |  | 386040.96 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Minda | 086007052 | Construction of Water System Level II Pump Driven | 1 | Basic Social Services | Water System | 1 | system | 899177 | 251279 | 1150456 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Samoyao | 086007070 | Construction of Concrete pathwalk with 6 ln.m 900mm Culvert | 1 | Basic Access Infrastructure | Access Trail | 0.426 | kms | 1272000 | 372499 | 1644499 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Palanas | 086007060 | Construction of Water System Level I | 1 | Basic Social Services | Water System | 1 | system | 354648 | 95593 | 450241 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | San Francisco | 086007074 | Construction of Level II Water System Gravity | 1 | Basic Social Services | Water System | 1 | system | 334822 | 95460 | 430282 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Pizarro | 086007062 | Construction of Level II Gravity Driven WS | 1 | Basic Social Services | Water System | 1 | system | 920159 | 264269 | 1184428 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | San Miguel | 086007079 | Construction of Level II Gravity Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 423067 | 113127 | 536194 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Casab-ahan | 086007026 | Construction of Level II Gravity Driven WS | 1 | Basic Social Services | Water System | 1 | system | 871535 | 255205 | 1126740 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Tambongan | 086007088 | Construction of 1 Unit 2CL Elem SB | 1 | Basic Social Services | School | 126 | sq. m | 974539 | 275461 | 1250000 |  |  | 779610.4 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Purog | 086007064 | Construction of Level II Gravity Driven WS | 1 | Basic Social Services | Water System | 1 | system | 493636 | 149063 | 642699 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Elcano | 086007032 | Construction of 1 Unit 3 CL Elem SB | 1 | Basic Social Services | School | 189 | sq. m | 1696669 | 451974 | 2148643 |  |  | 848336.5 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | San Isidro | 086007076 | Construction of 2.620 km Concrete pathwalk From Brgy. Hinayagan-San Isidro | 2 | Basic Access Infrastructure | Access Trail | 2.26 | kms | 2452496 | 738924 | 3191420 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Buao | 086007010 | Construction of 1 Unit 3 CL Elem SB | 1 | Basic Social Services | School | 189 | sq. m | 1665033 | 444223 | 2109256 |  |  | 832517 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Nalihugan | 086007055 | Construction of .452km Concrete pwathwalk with stairway | 1 | Basic Access Infrastructure | Access Trail | 0.452 | kms | 632881 | 189174 | 822055 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Cuatro de Agosto | 086007096 | Construction of .703km Concrete Pathwalk with Box Culvert from Cuatro de Agosto - Brgy. Calirocan | 1 | Basic Access Infrastructure | Access Trail | 0.703 | kms | 789250 | 229514 | 1018764 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | San Jose | 086007078 | Construction of 10 ln.m Concrete Footbridge with Erosion Control | 1 | Basic Access Infrastructure | Foot/Small Bridges | 10 | ln.m | 775281 | 244221 | 1019502 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Napalisan | 086007056 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 624 | ln.m | 705108 | 193048 | 898156 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Himamaloto | 086007100 | Construction of Level I Water System | 1 | Basic Social Services | Water System | 1 | system | 255550 | 70484 | 326034 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Rawis | 086007067 | Construction of Level II Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 866779 | 244752 | 1111531 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Lungib | 086007048 | Construction of 155 Ln.m Pier With Step Lnading | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) | 155 | ln.m | 1550713 | 438472 | 1989185 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Sidmon | 086007103 | Construction of 6 Linear Meter Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 6 | ln.m | 283614 | 81936 | 365550 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Gerali | 086007034 | Construction of Gravity Driven Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 558592 | 161384 | 719976 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Hinayagan | 086007041 | Construction of .797km ncrete Pathwalk From Brgy. Giaboc-Brgy. Hinayagan | 1 | Basic Access Infrastructure | Access Trail | 0.797 | kms | 965678 | 292898 | 1258576 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Rizal | 086007068 | Construction of Level II Gravity Driven WS | 1 | Basic Social Services | Water System | 1 | system | 711568 | 198250 | 909818 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Hinogacan | 086007042 | Construction of 1 unit 2 CL elem. School Building | 1 | Basic Social Services | School | 126 | sq. m | 1103559 | 310903 | 1414462 |  |  | 481335 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Giaboc | 086007035 | Construction of 2.076km Concrete pathwalk with box Culvert from Buao-Giaboc | 1 | Basic Access Infrastructure | Access Trail | 2.076 | kms | 2704038 | 772770 | 3476808 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Carmona | 086007025 | Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 586273 | 169938 | 756211 |  |  | 293137 | 1st | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | San Antonio | 086007072 | Construction of 2.355km Concrete Pathwalk Hinayagan-San Antonio | 1 | Basic Access Infrastructure | Access Trail | 2.355 | kms | 2566023 | 746756 | 3312779 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Concepcion | 086007029 | Concstruction of Level II Pump Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 981313 | 320235 | 1301548 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Beslig | 086007006 | Construction of 8 Ln.m Concrete Footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 8 | ln.m | 440460 | 122365 | 562825 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Jasminez | 086007044 | Construction of Level II Gravity Driven WS | 1 | Basic Social Services | Water System | 1 | system | 707628 | 219507 | 927135 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Caparangasan | 086007023 | Concstruction of Level II Pump Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 542784 | 156411 | 699195 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Gandara | 086007 | Hampton | 086007039 | Construction of Rive landing | 1 | Community Production, Economic Support and Common Service Facility | Economic/Livelihood Support (Training/Trading Center, Market, Bagsakan, Mini Port/Wharf) |  | ln.m | 299720 | 89655 | 389375 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Angyap | 086011001 | Construction of Concrete Stairs | 1 | Basic Access Infrastructure | Access Trail |  | kms | 288187.2 | 78046.8 | 366234 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Sta. Cruz | 086011020 | Construction of Concrete Stairs | 1 | Basic Access Infrastructure | Access Trail |  | kms | 278356.8 | 71089.2 | 349446 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Bag-otan | 086011021 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 760876 | 195473 | 956349 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Deit | 086011007 | 5o Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 50 | unit | 945574.4 | 368803.6 | 1314378 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Del Rosario | 086011008 | Construction of .106 kms Concrete pathwalk with stairs | 1 | Basic Access Infrastructure | Access Trail | 0.106 | kms | 1076052.8 | 276512.2 | 1352565 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Salvacion | 086011018 | Electrification | 1 | Basic Social Services | Electrification |  | HH | 350829.6 | 91082.4 | 441912 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Nagpapacao | 086011016 | Construction of Concrete pathwalk with Stairs | 1 | Basic Access Infrastructure | Access Trail | 0.0625 | kms | 561504.8 | 143751.2 | 705256 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Mahanud | 086011013 | Construction of 5 ln.m footbridge | 1 | Basic Access Infrastructure | Foot/Small Bridges | 5 | ln.m | 428672 | 110543 | 539215 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Barruz | 086011004 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 706312 | 181832 | 888144 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | San Isidro | 086011019 | Construction of 0.054 km pathwalk with stairs | 1 | Basic Access Infrastructure | Access Trail | 0.054 | kms | 564387.6 | 144471.4 | 708859 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Camonoan | 086011005 | Construction of 19 Units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 19 | unit | 427630.4 | 157882.6 | 585513 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Carolina | 086011006 | Construction of 0.07 kms Concrete pathwalk with concrete stairs | 1 | Basic Access Infrastructure | Access Trail | 0.07 | kms | 898186.4 | 232046.6 | 1130233 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Libertad | 086011009 | Construction of 6 units Sanitary Toilets | 1 | Environmental Protection and Conservation | Sanitation Facilities (Toilets, Solid Waste Management System) | 6 | unit | 333209.6 | 114931.4 | 448141 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Matuguinao | 086011 | Inubod | 086011022 | Construction of .05 kms Concrete pathwalk with Stairs | 1 | Basic Access Infrastructure | Access Trail | 0.05 | kms | 816735.4 | 211681.6 | 1028417 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Capaysagan | 086012015 | Improvement of Water System | 1 | Basic Social Services | Water System | 1 | system | 281148 | 87171 | 368319 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Calapi | 086012009 | Construction of Level II Water System | 1 | Basic Social Services | Water System | 1 | system | 3074457 | 982600 | 4057057 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Sarao | 086012030 | Construction of 2.456km Concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 2.456 | kms | 1910460 | 532769 | 2443229 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Bonga | 086012007 | Construction of level II Gravity feed Water System | 1 | Basic Social Services | Water System | 1 | system | 538537 | 156863 | 695400 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Caranas | 086012016 | Consttruction of Gravity Feed Water System | 1 | Basic Social Services | Water System | 1 | system | 683303 | 199967 | 883270 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Angyap | 086012003 | Imorovement of Gravity fed Water System with handrail | 1 | Basic Social Services | Water System | 1 | system | 251435 | 83416 | 334851 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | New Minarog | 086012025 | Construction of Gravity fed Water System Level II | 1 | Basic Social Services | Water System | 1 | system | 634340 | 180314 | 814654 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Calantawan | 086012008 | Construction of 2.6 km concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 2.6 | kms | 1734200 | 601431 | 2335631 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Inalad | 086012019 | Construction of Day Care Center | 1 | Basic Social Services | Day Care Center | 48 | sq.m | 577884 | 172116 | 750000 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | San Andres | 086012028 | Construction of Level I water System with .225km concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.225 | kms | 426207 | 128250 | 554457 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Malonoy | 086012022 | Improvement of Level II Gravity Fed Water System | 1 | Basic Social Services | Water System | 1 | system | 233366 | 75217 | 308583 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Hinica-an | 086012018 | Construction of Level II water System Level II Gravity | 1 | Basic Social Services | Water System | 1 | system | 403849 | 126101 | 529950 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Caulayanan | 086012017 | Improvement of Level II Water System Gravity Fed | 1 | Basic Social Services | Water System | 1 | system | 564260 | 156259 | 720519 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Beri | 086012006 | Consctruction of Gravity fed Level II water System | 1 | Basic Social Services | Water System | 1 | system | 235979 | 83599 | 319578 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Bayog | 086012005 | Construction of Level II Pump Driven Water System | 1 | Basic Social Services | Water System | 1 | system | 754852 | 214502 | 969354 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Posongan | 086012031 | Construction of Gravity Fed Level II water System | 1 | Basic Social Services | Water System | 1 | system | 425620 | 128537 | 554157 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Candomacol | 086012013 | Construction of .21 km concrete pathwalk | 1 | Basic Access Infrastructure | Access Trail | 0.21 | kms | 379151 | 117484 | 496635 |  |  | 0 |  | Not yet started
VIII | 08 | Western Samar | 0860 | Motiong | 086012 | Poblacion 1 | 086012001 | Construction of Drainage System | 1 | Environmental Protection and Conservation | Drainage Structures (Culverts, Overflow, Spillway) | 33 | ln.m | 390952 | 127025 | 517977 |  |  | 0 |  | Not yet started